## KPI Plan
PRIORITY PG A to B Pending ITRs and KPI Strategy - EIT (Pending ITRs and Daily Completion Target) | [13 empty] | PRIORITY PG C to D Pending ITRs and KPI Strategy - EIT (Pending ITRs and Daily Completion Target)
| 186 |  | 471 |  | 75 |  | 82 |  | 28 | [5 empty] | 320 |  | 452 |  | 62 |  | 90 |  | 23
DATE | Cable Testing (STATIC ITRS) |  | Glanding & Termination (Confirmity ITR) |  | Electrical Others |  | Instrumentation Others |  | RFC |  | PG-A/B ITRs + RFC (814 ITR + 28 RFC) |  | REMARKS | DATE | Cable Testing (STATIC ITRS) |  | Glanding & Termination (Confirmity ITR) |  | Electrical Others |  | Instrumentation Others |  | RFC |  | PG-A/B ITRs + RFC (924 ITR + 23 RFC) |  | REMARKS
| 186 | 0 | 471 | 0 | 75 | 0 | 82 | 0 | 28 | 0 | 842 | 0 |  |  | 320 | 0 | 452 | 0 | 62 | 0 | 90 | 0 | 23 | 0 | 947 | 0
| PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL |  |  | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL | PLAN | ACTUAL
2026-07-13 | 7 | [9 empty] | 7 |  |  | 2026-07-13 | [10 empty] | 0
2026-07-14 | 20 | [9 empty] | 20 |  |  | 2026-07-14 | [10 empty] | 0
2026-07-15 | 20 |  | 22 |  | 7 | [5 empty] | 49 |  |  | 2026-07-15 | [10 empty] | 0
2026-07-16 | 20 |  | 25 |  | 8 | [5 empty] | 53 |  |  | 2026-07-16 | [10 empty] | 0
2026-07-17 | 20 |  | 25 |  | 8 | [5 empty] | 53 |  |  | 2026-07-17 | [10 empty] | 0
2026-07-18 | 20 |  | 25 |  | 8 | [5 empty] | 53 |  |  | 2026-07-18 | [10 empty] | 0
2026-07-19 | 15 |  | 26 |  | 8 |  | 8 |  |  |  | 57 |  |  | 2026-07-19 | [10 empty] | 0
2026-07-20 | 15 |  | 20 |  | 8 |  | 8 |  |  |  | 51 |  |  | 2026-07-20 | 20 |  | 25 |  | 5 | [5 empty] | 50
2026-07-21 | 15 |  | 20 |  | 8 |  | 8 |  |  |  | 51 |  |  | 2026-07-21 | 20 |  | 25 |  | 5 | [5 empty] | 50
2026-07-22 | 15 |  | 20 |  | 9 |  | 8 |  |  |  | 52 |  |  | 2026-07-22 | 20 |  | 28 |  | 5 |  | 8 |  |  |  | 61
2026-07-23 | 15 |  | 20 |  | 6 |  | 8 |  | 1 |  | 50 |  |  | 2026-07-23 | 20 |  | 28 |  | 7 |  | 8 |  | 1 |  | 64
2026-07-24 | 4 |  | 20 |  | 5 |  | 7 |  | 3 |  | 39 |  |  | 2026-07-24 | 30 |  | 28 |  | 5 |  | 8 |  | 1 |  | 72
2026-07-25 |  |  | 30 |  |  |  | 7 |  | 4 |  | 41 |  |  | 2026-07-25 | 30 |  | 28 |  | 5 |  | 8 |  | 1 |  | 72
2026-07-26 | - | - | - | - | - | - | - | - |  |  | 0 |  | SUNDAY | 2026-07-26 | - | - | - | - | - | - | - | - |  |  | 0 |  | SUNDAY
2026-07-27 |  |  | 45 |  |  |  | 10 |  | 4 |  | 59 |  |  | 2026-07-27 | 30 |  | 18 |  | 5 |  | 8 |  |  |  | 61
2026-07-28 |  |  | 45 |  |  |  | 10 |  | 4 |  | 59 |  |  | 2026-07-28 | 30 |  | 18 |  | 5 |  | 8 |  | 2 |  | 63
2026-07-29 |  |  | 44 |  |  |  | 8 |  | 3 |  | 55 |  |  | 2026-07-29 | 30 |  | 18 |  | 5 |  | 8 |  | 2 |  | 63
2026-07-30 |  |  | 42 | [5 empty] | 3 |  | 45 |  |  | 2026-07-30 | 30 |  | 18 |  | 5 |  | 8 |  | 2 |  | 63
2026-07-31 |  |  | 42 | [5 empty] | 3 |  | 45 |  |  | 2026-07-31 | 30 |  | 20 |  | 5 |  | 8 |  | 2 |  | 65
2026-08-01 | [8 empty] | 3 |  | 3 |  |  | 2026-08-01 | 30 |  | 38 |  | 5 |  | 8 |  | 2 |  | 83
2026-08-02 | [10 empty] | 0 |  |  | 2026-08-02 |  |  | 40 |  |  |  | 6 |  | 2 |  | 48
2026-08-03 | [10 empty] | 0 |  |  | 2026-08-03 |  |  | 40 |  |  |  | 4 |  | 2 |  | 46
2026-08-04 | [10 empty] | 0 |  |  | 2026-08-04 |  |  | 40 | [5 empty] | 2 |  | 42
2026-08-05 | [10 empty] | 0 |  |  | 2026-08-05 |  |  | 40 | [5 empty] | 2 |  | 42
2026-08-06 | [10 empty] | 0 |  |  | 2026-08-06 | [8 empty] | 2 |  | 2
Total | 186 | 0 | 471 | 0 | 75 | 0 | 82 | 0 | 28 | 0 | 842 | 0 |  | Total | 320 | 0 | 452 | 0 | 62 | 0 | 90 | 0 | 23 | 0 | 947 | 0

## Manpower
LOT2 PS5 - EIT PENDING ITR & MANPOWER STRATEGY
ITR Count
Description | PGB A | PGB B | PGB C | PGB D | Fuel Treatment | PG Electrical Room | Electrical Earthing (Power Dist, PG & Cooling tower) | Outside PG | Total
Cable Testing (STATIC ITRS) | 52 | 42 | 80 | 82 | 98 | 146 | 4 | 6 | 510
Glanding & Termination (Confirmity ITR) | 118 | 107 | 108 | 121 | 135 | 253 | 4 | 81 | 927
Electrical Others | 19 | 19 | 19 | 19 | 12 | 21 | 0 | 20 | 129
Instrumentation Other | 12 | 11 | 11 | 11 | 18 | 26 | 0 | 83 | 172
Total | 201 | 179 | 218 | 233 | 263 | 446 | 8 | 190 | 1738
Description | PGB A | PGB B | PGB C | PGB D | Fuel Treatment | PG Electrical Room | Electrical Earthing (Power Dist, PG & Cooling tower) | Outside PG | Required Qty (Existing 8th June POB+ Task Force) | Currently Available at site as per POB | Required Manpower to execute the PG Job | Balance required to Mobilize | Notes
EIT General | MANPOWER
Completion Lead-Site Follow up | 1 | [8 empty] | 1 | 1 | 0
Completions- CMT Office | 1 | [8 empty] | 1 | 1 | 0
ELECTRICAL
QC Inspector-Electrical | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.5 | 0.5 | 0.5 | 3 | 2 | 3 | 1 | Note-1
Supervisor | 0.75 | 0.75 | 0.75 | 0.75 | 0.5 | 1 | 0.75 | 0.75 | 6 | 5 | 6 | 1 | Note-1
Foreman | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 6 | 6 | 6 | 0 | Note-1
Technician (expats+chinese) | 3 | 3 | 3 | 3 | 2 | 8 | 4 | 4 | 30 | 19 | 30 | 11 | Note-1
Helpers (local) | 15 | 15 | 10 | 10 | 10 | 25 | 15 | 15 | 115 | 100 | 115 | 15 | Note-1
Punch List Team | 1 Crew ( 1 Foremen + 2 skilled Technician + 2 helper) | [8 empty] | 0 | 5 | 5 | Punch List Team to be created - 5 People
INSTRUMENTATION
QC Inspector-Instrument | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.25 | 0.25 | 0.25 | 1 | 1 | 1 | 0 | Note-1
INS Supervisor | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 4 | 4 | 4 | 0 | Note-1
Foreman | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 4 | 4 | 4 | 0 | Note-1
Technician (expats+chinese) | 2 | 2 | 1.5 | 1.5 | 1 | 1 | 2 | 2 | 17 | 9 | 13 | 4 | Note-1
Helpers (local) | 10 | 10 | 8 | 8 | 7 | 7 | 7 | 7 | 64 | 55 | 64 | 9 | Note-1
Punch List Team | 1 Crew ( 1 Foremen + 2 skilled Technician + 2 helper) | [8 empty] | 0 | 5 | 5 | Punch List Team to be created- 5 People
Impulse Tubing Team | 1 Crew ( 1 Technician + 1 helper) -Required Min 2 Crew | [8 empty] | 0 | 4 | 4 | Impulse Tubing Team to be created
[8 empty] | Total | 252 | 207 | 262 | 55
Note -1 : All available manpower shall be allocated to PG priorities to achieve RFCs by 01 Aug for PG A and B, and by 06 Aug for PG C and D. CPY will not respond to RFIs for non-priority activities; only RFIs/ITRs related to PG A, B, C and D will be actioned.
ELECTRICAL ACTIVITIES
1. Cable tray & support installtion (incl. secondary routing). Support painting; 2. Cable installation (dressing, tagging, fixation) + branch cables; 3. Trench backfilling under PG EL BLD. Soil removing 4. Glanding & Cable termination; 5. Cable testing; 6. PL clereance
INSTRUMENTATION ACTIVITIES
1. Cable tray & support installtion (incl. secondary routing). Support painting; 2. Cable installation (dressing, tagging, fixation) + branch cables; 3. Instrument Impulse Tubing and Control Valve Impulse Lines; 4. Flushing and Pressure Testing; 5. Glanding & Cable termination; 6. Cable testing; 7. PL clereance

## Sheet1 (hidden)
Description | (All)
Task State | (Multiple Items)
Discipline (Summary) | (All)
Task Priority | Task Type (Name) | Count of Task ID
Priority-1 | Conformity Check | 595
| Static Test | 219
Priority-1 Total |  | 814
Priority-2 | Conformity Check | 582
| Static Test | 342
Priority-2 Total |  | 924
Grand Total |  | 1738

## EIT CMT Tasks
Task ID | Asset - Tag | Asset Pack ID | Cable Pack ID | Pipe Pack ID | Loop Name | Description | Category (Summary) | Discipline | Task Type (Name) | Discipline (Summary) | Asset - Description | Systemization - Process Plant ID | Responsible Company (Summary) | Actual Duration | Scheduled Duration | Task Duration | Title - Actual MH/Person | Title - Planned MH/Person | Field005 (Custom) | Physical Location - Area (Summary) | Systemization - Subsystem (Summary) | Closing Date | Subsystem ID | Task Priority | Priority | Test Form - Description | Asset Discipline | Task State | Subsystem Priority | Task Model | Closed By | Document - Name
T-00018-0192 | PS5-61-IU-0001A |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 16 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Power Transformer | E | To be completed | PS5 - Milestone B | TM-00018
T-00018-0193 | PS5-61-IU-0001B |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 16 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Power Transformer | E | To be completed | PS5 - Milestone B | TM-00018
T-00018-0194 | PS5-61-IU-0001C |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 16 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Power Transformer | E | To be completed | PS5 - Milestone D | TM-00018
T-00018-0195 | PS5-61-IU-0001D |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 16 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Power Transformer | E | To be completed | PS5 - Milestone D | TM-00018
T-00022-3334 | PS5-60-IJ-0001A-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-60-IJ-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-03-07 11:29 | PS5-60-01 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00022 | arun, jabesteen | TZ-MID-68-WPR2-150101
T-00022-3335 | PS5-60-IJ-0001B-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-60-IJ-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-03-07 11:36 | PS5-60-04 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00022 | arun, jabesteen | TZ-MID-68-WPR2-150101
T-00022-3336 | PS5-60-IJ-0001C-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100C TO PS5-60-IJ-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-03-07 11:39 | PS5-60-07 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00022 | arun, jabesteen | TZ-MID-68-WPR2-150101
T-00022-3337 | PS5-60-IJ-0001D-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100D TO PS5-60-IJ-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-03-07 11:42 | PS5-60-10 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00022 | arun, jabesteen | TZ-MID-68-WPR2-150101
T-00022-3377 | PS5-61-IJ-0001-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-24 08:12 | PS5-60-01 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00022 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00022-3378 | PS5-61-IJ-0001-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-24 12:59 | PS5-60-01 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00022 | Mohamed, Amira | TZ-MID-68-WPR2-150101
T-00022-3379 | PS5-61-IJ-0001-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-24 13:00 | PS5-60-01 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00022 | Mohamed, Amira | TZ-MID-68-WPR2-150101
T-00022-3380 | PS5-61-IJ-0001-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-24 13:01 | PS5-60-04 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00022 | Mohamed, Amira | TZ-MID-68-WPR2-150101
T-00022-3381 | PS5-61-IJ-0001-CH05 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-24 13:01 | PS5-60-04 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00022 | Mohamed, Amira | TZ-MID-68-WPR2-150101
T-00022-3382 | PS5-61-IJ-0001-CH06 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-24 13:48 | PS5-60-04 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00022 | Mohamed, Amira | TZ-MID-68-WPR2-150101
T-00022-3383 | PS5-61-IJ-0001-CH07 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001C TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-24 13:48 | PS5-60-07 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00022 | Mohamed, Amira | TZ-MID-68-WPR2-150101
T-00022-3384 | PS5-61-IJ-0001-CH08 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001C TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-24 13:49 | PS5-60-07 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00022 | Mohamed, Amira | TZ-MID-68-WPR2-150101
T-00022-3385 | PS5-61-IJ-0001-CH09 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001C TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-24 08:14 | PS5-60-07 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00022 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00022-3386 | PS5-61-IJ-0001-CH10 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001D TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-24 08:15 | PS5-60-10 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00022 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00022-3387 | PS5-61-IJ-0001-CH11 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001D TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-24 08:15 | PS5-60-10 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00022 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00022-3388 | PS5-61-IJ-0001-CH12 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001D TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-24 08:17 | PS5-60-10 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00022 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00022-3410 | PS5-61-IU-0001A-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-18 12:59 | PS5-60-01 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00022 | arun, jabesteen | TZ-MID-68-WPR2-150101
T-00022-3411 | PS5-61-IU-0001A-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-18 13:03 | PS5-60-01 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00022 | arun, jabesteen | TZ-MID-68-WPR2-150101
T-00022-3412 | PS5-61-IU-0001A-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-18 13:06 | PS5-60-01 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00022 | arun, jabesteen | TZ-MID-68-WPR2-150101
T-00022-3413 | PS5-61-IU-0001B-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-18 13:09 | PS5-60-04 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00022 | arun, jabesteen | TZ-MID-68-WPR2-150101
T-00022-3414 | PS5-61-IU-0001B-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-18 13:11 | PS5-60-04 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00022 | arun, jabesteen | TZ-MID-68-WPR2-150101
T-00022-3415 | PS5-61-IU-0001B-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-18 13:13 | PS5-60-04 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00022 | arun, jabesteen | TZ-MID-68-WPR2-150101
T-00022-3416 | PS5-61-IU-0001C-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100C TO PS5-61-IU-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-02-19 12:39 | PS5-60-07 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00022 | arun, jabesteen | TZ-MID-68-WPR2-150101
T-00022-3417 | PS5-61-IU-0001C-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100C TO PS5-61-IU-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-02-19 12:40 | PS5-60-07 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00022 | arun, jabesteen | TZ-MID-68-WPR2-150101
T-00022-3418 | PS5-61-IU-0001C-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100C TO PS5-61-IU-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-02-19 12:45 | PS5-60-07 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00022 | arun, jabesteen | TZ-MID-68-WPR2-150101
T-00022-3419 | PS5-61-IU-0001D-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100D TO PS5-61-IU-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-02-19 12:46 | PS5-60-10 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00022 | arun, jabesteen | TZ-MID-68-WPR2-150101
T-00022-3420 | PS5-61-IU-0001D-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100D TO PS5-61-IU-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-02-19 12:48 | PS5-60-10 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00022 | arun, jabesteen | TZ-MID-68-WPR2-150101
T-00022-3421 | PS5-61-IU-0001D-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100D TO PS5-61-IU-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-02-19 12:50 | PS5-60-10 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00022 | arun, jabesteen | TZ-MID-68-WPR2-150101
T-00023-10536 | PS5-60-IN-0002A-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-10537 | PS5-60-IN-0002B-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-10538 | PS5-60-IN-0002C-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-10539 | PS5-60-IN-0002D-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-10593 | PS5-60-IH-0001A-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-10594 | PS5-60-IH-0001B-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-10595 | PS5-60-IH-0001C-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-10596 | PS5-60-IH-0001D-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-10600 | PS5-60-IH-0002-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-10601 | PS5-60-IH-0002-CG02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-10887 | PS5-60-BE-0007A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-10888 | PS5-60-BE-0007A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-10889 | PS5-60-BE-0007B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-10890 | PS5-60-BE-0007B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-10891 | PS5-60-BE-0007C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0007C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-10892 | PS5-60-BE-0007C-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0007C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-10893 | PS5-60-BE-0007D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0007D | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-10894 | PS5-60-BE-0007D-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0007D | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-10901 | PS5-60-ISO-62800A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-ISO-62800A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-10902 | PS5-60-ISO-62800C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-ISO-62800C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-11250 | PS5-71-BE-0001A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11251 | PS5-71-BE-0001A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11252 | PS5-71-BE-0001A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11253 | PS5-71-BE-0001A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11254 | PS5-71-BE-0001A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11255 | PS5-71-BE-0001A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11256 | PS5-71-BE-0001A-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11257 | PS5-71-BE-0001A-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11258 | PS5-71-BE-0001A-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11259 | PS5-71-BE-0001A-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11260 | PS5-71-BE-0001A-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11261 | PS5-71-BE-0001A-CL12 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11262 | PS5-71-BE-0001B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11263 | PS5-71-BE-0001B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11264 | PS5-71-BE-0001B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11265 | PS5-71-BE-0001B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11266 | PS5-71-BE-0001B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11267 | PS5-71-BE-0001B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11268 | PS5-71-BE-0001B-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11269 | PS5-71-BE-0001B-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11270 | PS5-71-BE-0001B-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11271 | PS5-71-BE-0001B-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11272 | PS5-71-BE-0001B-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-11273 | PS5-71-BE-0001B-CL12 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-4725 | PS5-03-SEA-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-03-SEA-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone E | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-4978 | PS5-60-BE-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-4979 | PS5-60-BE-0001-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-4981 | PS5-60-BE-0001-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-4982 | PS5-60-BE-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-4983 | PS5-60-BE-0002-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-4984 | PS5-60-BE-0002-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-4986 | PS5-60-BE-0002-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-4987 | PS5-60-BE-0003A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0003A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-4988 | PS5-60-BE-0003B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-4989 | PS5-60-BE-0003C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0003C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-4990 | PS5-60-BE-0003D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0003D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-4994 | PS5-60-BE-0004A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0004A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-4995 | PS5-60-BE-0004B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0004B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-4996 | PS5-60-BE-0004C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0004C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-4997 | PS5-60-BE-0004D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0004D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5001 | PS5-60-BE-0005A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0005A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5002 | PS5-60-BE-0005B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0005B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5003 | PS5-60-BE-0005C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0005C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5004 | PS5-60-BE-0005D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0005D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5008 | PS5-60-BE-0011A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5009 | PS5-60-BE-0011A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5010 | PS5-60-BE-0011A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5011 | PS5-60-BE-0011A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5012 | PS5-60-BE-0011A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5013 | PS5-60-BE-0011A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5014 | PS5-60-BE-0011B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5015 | PS5-60-BE-0011B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5016 | PS5-60-BE-0011B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5017 | PS5-60-BE-0011B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5018 | PS5-60-BE-0011B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5019 | PS5-60-BE-0011B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5020 | PS5-60-BE-0012A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5021 | PS5-60-BE-0012A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5022 | PS5-60-BE-0012A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5023 | PS5-60-BE-0012A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5024 | PS5-60-BE-0012A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5025 | PS5-60-BE-0012A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5026 | PS5-60-BE-0012B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5027 | PS5-60-BE-0012B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5028 | PS5-60-BE-0012B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5029 | PS5-60-BE-0012B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5030 | PS5-60-BE-0012B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5031 | PS5-60-BE-0012B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5032 | PS5-60-BE-0013A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5033 | PS5-60-BE-0013A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5034 | PS5-60-BE-0013A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5035 | PS5-60-BE-0013A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5036 | PS5-60-BE-0013A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5037 | PS5-60-BE-0013A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5038 | PS5-60-BE-0013B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5039 | PS5-60-BE-0013B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5040 | PS5-60-BE-0013B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5041 | PS5-60-BE-0013B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5042 | PS5-60-BE-0013B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5043 | PS5-60-BE-0013B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5044 | PS5-60-BE-0014A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5045 | PS5-60-BE-0014A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5046 | PS5-60-BE-0014A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5047 | PS5-60-BE-0014A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5048 | PS5-60-BE-0014A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5049 | PS5-60-BE-0014A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5050 | PS5-60-BE-0014B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5051 | PS5-60-BE-0014B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5052 | PS5-60-BE-0014B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5053 | PS5-60-BE-0014B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5054 | PS5-60-BE-0014B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5055 | PS5-60-BE-0014B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5092 | PS5-60-BE-0021A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0021A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5093 | PS5-60-BE-0021B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0021B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5094 | PS5-60-BE-0024A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0024A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5095 | PS5-60-BE-0024A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0024A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5096 | PS5-60-BE-0024B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0024B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5097 | PS5-60-BE-0024B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0024B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5098 | PS5-60-BE-0024C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0024C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5099 | PS5-60-BE-0024C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0024C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5100 | PS5-60-BE-0024D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0024D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5101 | PS5-60-BE-0024D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0024D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5108 | PS5-60-BE-0025A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0025A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5109 | PS5-60-BE-0025B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0025B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5110 | PS5-60-BE-0025C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0025C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5111 | PS5-60-BE-0025D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0025D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5115 | PS5-60-BE-0026A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0026A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5116 | PS5-60-BE-0026A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0026A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5117 | PS5-60-BE-0026B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0026B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5118 | PS5-60-BE-0026B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0026B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5119 | PS5-60-BE-0026C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0026C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5120 | PS5-60-BE-0026C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0026C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5121 | PS5-60-BE-0026D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0026D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5122 | PS5-60-BE-0026D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0026D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5129 | PS5-60-BI-0005A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0005A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5130 | PS5-60-BI-0005B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0005B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5131 | PS5-60-BI-0005C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0005C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5132 | PS5-60-BI-0005D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0005D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5136 | PS5-60-BI-0015A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5137 | PS5-60-BI-0015A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5138 | PS5-60-BI-0015A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5139 | PS5-60-BI-0015B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5140 | PS5-60-BI-0015B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5141 | PS5-60-BI-0015B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5142 | PS5-60-BI-0015C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0015C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5143 | PS5-60-BI-0015C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0015C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5144 | PS5-60-BI-0015C-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0015C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5145 | PS5-60-BI-0015D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0015D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5146 | PS5-60-BI-0015D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0015D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5147 | PS5-60-BI-0015D-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0015D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5157 | PS5-60-DD-62800A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-DD-62800A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5159 | PS5-60-DD-62800C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-DD-62800C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5166 | PS5-60-IE-0002A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5167 | PS5-60-IE-0002A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5168 | PS5-60-IE-0002A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5169 | PS5-60-IE-0002B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5170 | PS5-60-IE-0002B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5171 | PS5-60-IE-0002B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5172 | PS5-60-IE-0002C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5173 | PS5-60-IE-0002C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5174 | PS5-60-IE-0002C-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5175 | PS5-60-IE-0002D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5176 | PS5-60-IE-0002D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5177 | PS5-60-IE-0002D-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5187 | PS5-60-IE-0003A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5188 | PS5-60-IE-0003A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5189 | PS5-60-IE-0003B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5190 | PS5-60-IE-0003B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5191 | PS5-60-IE-0003C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5192 | PS5-60-IE-0003C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5193 | PS5-60-IE-0003D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5194 | PS5-60-IE-0003D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5201 | PS5-60-IE-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5202 | PS5-60-IE-0004-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5204 | PS5-60-IH-0001A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5205 | PS5-60-IH-0001A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5206 | PS5-60-IH-0001A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5207 | PS5-60-IH-0001A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5208 | PS5-60-IH-0001A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5209 | PS5-60-IH-0001A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5211 | PS5-60-IH-0001B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5212 | PS5-60-IH-0001B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5213 | PS5-60-IH-0001B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5214 | PS5-60-IH-0001B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5215 | PS5-60-IH-0001B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5216 | PS5-60-IH-0001B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5218 | PS5-60-IH-0001C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5219 | PS5-60-IH-0001C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5220 | PS5-60-IH-0001C-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5221 | PS5-60-IH-0001C-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5222 | PS5-60-IH-0001C-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5223 | PS5-60-IH-0001C-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5225 | PS5-60-IH-0001D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5226 | PS5-60-IH-0001D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5227 | PS5-60-IH-0001D-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5228 | PS5-60-IH-0001D-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5229 | PS5-60-IH-0001D-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5230 | PS5-60-IH-0001D-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5254 | PS5-60-IH-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5255 | PS5-60-IH-0002-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5256 | PS5-60-IH-0002-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5257 | PS5-60-IH-0002-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5258 | PS5-60-IH-0002-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5259 | PS5-60-IH-0002-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5260 | PS5-60-IH-0002-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5261 | PS5-60-IH-0002-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5262 | PS5-60-IH-0002-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5263 | PS5-60-IH-0002-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5264 | PS5-60-IN-0001A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5265 | PS5-60-IN-0001B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5266 | PS5-60-IN-0001C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5267 | PS5-60-IN-0001D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5271 | PS5-60-IN-0002A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5272 | PS5-60-IN-0002A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5273 | PS5-60-IN-0002A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5274 | PS5-60-IN-0002B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5275 | PS5-60-IN-0002B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5276 | PS5-60-IN-0002B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5277 | PS5-60-IN-0002C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5278 | PS5-60-IN-0002C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5279 | PS5-60-IN-0002C-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5280 | PS5-60-IN-0002D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5281 | PS5-60-IN-0002D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5282 | PS5-60-IN-0002D-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5292 | PS5-60-IWK-0001A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5293 | PS5-60-IWK-0001A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5294 | PS5-60-IWK-0001B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5295 | PS5-60-IWK-0001B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5296 | PS5-60-IWK-0001C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5297 | PS5-60-IWK-0001C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5298 | PS5-60-LA-0002A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5299 | PS5-60-LA-0002A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5300 | PS5-60-LA-0002B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5301 | PS5-60-LA-0002B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5304 | PS5-60-LA-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5305 | PS5-60-LA-0003-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5310 | PS5-60-SEA-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone E | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5311 | PS5-60-SEA-0001-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone E | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5312 | PS5-60-VS-9100A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-VS-9100A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5313 | PS5-60-VS-9100B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-VS-9100B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5314 | PS5-60-VS-9100C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-VS-9100C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C |  | PS5-60-44 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5315 | PS5-60-VS-9100D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-VS-9100D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D |  | PS5-60-45 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5319 | PS5-61-BI-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5320 | PS5-61-BI-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5321 | PS5-61-BI-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-61-BI-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5322 | PS5-61-BI-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-61-BI-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5562 | PS5-71-FCV-0019-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0043 TO PS5-71-FCV-0019 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5584 | PS5-71-IN-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5585 | PS5-71-IN-0003-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5586 | PS5-71-IN-0003-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5587 | PS5-71-IN-0004A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5588 | PS5-71-IN-0004A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5589 | PS5-71-IN-0004A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5590 | PS5-71-IN-0004B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5591 | PS5-71-IN-0004B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5592 | PS5-71-IN-0004B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5594 | PS5-71-MOV-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5595 | PS5-71-MOV-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5596 | PS5-71-MOV-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5597 | PS5-71-MOV-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5599 | PS5-71-MOV-0008-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0008 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5601 | PS5-71-MOV-0010-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0010 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5602 | PS5-71-SDV-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0043 TO PS5-71-SDV-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5609 | PS5-71-XV-0091-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-XV-0091 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone F | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-5610 | PS5-71-XV-0092-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-XV-0092 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023 |  | TZ-MID-68-WPR2-150101
T-00023-9131 | PS5-60-BE-0007A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9132 | PS5-60-BE-0007B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9133 | PS5-60-BE-0007C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0007C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9134 | PS5-60-BE-0007D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0007D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9138 | PS5-60-BE-0027A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0027A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9139 | PS5-60-BE-0027B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0027B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9140 | PS5-60-BE-0027C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0027C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9141 | PS5-60-BE-0027D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0027D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9145 | PS5-60-BE-0028A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0028A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9146 | PS5-60-BE-0028B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0028B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9147 | PS5-60-BE-0028C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0028C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9148 | PS5-60-BE-0028D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0028D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9152 | PS5-60-BI-0006A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9153 | PS5-60-BI-0006A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9154 | PS5-60-BI-0006A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9155 | PS5-60-BI-0006A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9156 | PS5-60-BI-0006A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9157 | PS5-60-BI-0006A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9158 | PS5-60-BI-0006A-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9159 | PS5-60-BI-0006A-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9160 | PS5-60-BI-0006A-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9161 | PS5-60-BI-0006A-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9162 | PS5-60-BI-0006A-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9163 | PS5-60-BI-0006B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9164 | PS5-60-BI-0006B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9165 | PS5-60-BI-0006B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9166 | PS5-60-BI-0006B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9167 | PS5-60-BI-0006B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9168 | PS5-60-BI-0006B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9169 | PS5-60-BI-0006B-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9170 | PS5-60-BI-0006B-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9171 | PS5-60-BI-0006B-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9172 | PS5-60-BI-0006B-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9173 | PS5-60-BI-0006B-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9174 | PS5-60-BI-0006C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9175 | PS5-60-BI-0006C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9176 | PS5-60-BI-0006C-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9177 | PS5-60-BI-0006C-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9178 | PS5-60-BI-0006C-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9179 | PS5-60-BI-0006C-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9180 | PS5-60-BI-0006C-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9181 | PS5-60-BI-0006C-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9182 | PS5-60-BI-0006C-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9183 | PS5-60-BI-0006C-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9184 | PS5-60-BI-0006C-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9185 | PS5-60-BI-0006D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9186 | PS5-60-BI-0006D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9187 | PS5-60-BI-0006D-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9188 | PS5-60-BI-0006D-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9189 | PS5-60-BI-0006D-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9190 | PS5-60-BI-0006D-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9191 | PS5-60-BI-0006D-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9192 | PS5-60-BI-0006D-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9193 | PS5-60-BI-0006D-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9194 | PS5-60-BI-0006D-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9195 | PS5-60-BI-0006D-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9229 | PS5-60-BI-0017A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0017A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9230 | PS5-60-BI-0017B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0017B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9231 | PS5-60-BI-0017C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0017C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9232 | PS5-60-BI-0017D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0017D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9236 | PS5-60-EA-2900A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-EA-2900A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9237 | PS5-60-EA-2900B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-EA-2900B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9238 | PS5-60-EA-2900C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-EA-2900C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9239 | PS5-60-EA-2900D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-EA-2900D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00023
T-00023-9244 | PS5-71-BE-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-9245 | PS5-71-BE-0004-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-9246 | PS5-71-BE-0004-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-9247 | PS5-71-BI-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-9248 | PS5-71-BI-0003-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-9249 | PS5-71-BI-0003-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-9250 | PS5-71-BI-0003-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-9251 | PS5-71-BI-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00023
T-00023-9252 | PS5-71-BI-0005-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9253 | PS5-71-BI-0005-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9254 | PS5-71-BI-0005-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00023-9255 | PS5-71-BI-0006-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0006 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00023
T-00024-2101 | PS5-60-IE-0002A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2102 | PS5-60-IE-0002A-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2103 | PS5-60-IE-0002A-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2104 | PS5-60-IE-0002B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2105 | PS5-60-IE-0002B-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2106 | PS5-60-IE-0002B-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2107 | PS5-60-IE-0002C-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2108 | PS5-60-IE-0002C-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2109 | PS5-60-IE-0002C-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2110 | PS5-60-IE-0002D-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2111 | PS5-60-IE-0002D-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2112 | PS5-60-IE-0002D-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2123 | PS5-60-IE-0003A-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2124 | PS5-60-IE-0003A-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2125 | PS5-60-IE-0003A-CD04 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0005A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2126 | PS5-60-IE-0003A-CD05 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2135 | PS5-60-IE-0003A-CD14 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2136 | PS5-60-IE-0003A-CD15 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2138 | PS5-60-IE-0003B-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2139 | PS5-60-IE-0003B-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2140 | PS5-60-IE-0003B-CD04 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0005B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2141 | PS5-60-IE-0003B-CD05 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2150 | PS5-60-IE-0003B-CD14 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2151 | PS5-60-IE-0003B-CD15 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2153 | PS5-60-IE-0003C-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2154 | PS5-60-IE-0003C-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2155 | PS5-60-IE-0003C-CD04 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0005C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2156 | PS5-60-IE-0003C-CD05 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2165 | PS5-60-IE-0003C-CD14 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2166 | PS5-60-IE-0003C-CD15 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2168 | PS5-60-IE-0003D-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2169 | PS5-60-IE-0003D-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2170 | PS5-60-IE-0003D-CD04 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0005D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2171 | PS5-60-IE-0003D-CD05 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2180 | PS5-60-IE-0003D-CD14 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00024-2181 | PS5-60-IE-0003D-CD15 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00024 |  | TZ-MID-68-WPR2-150101
T-00026-0178 | PS5-71-DM-3500A |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Diesel Transfer Pump Motor A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | LV Motor | E | To be completed | PS5 - Milestone B | TM-00026
T-00026-0179 | PS5-71-DM-3500B |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Diesel Transfer Pump Motor B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | LV Motor | E | To be completed | PS5 - Milestone B | TM-00026
T-00034-0059 | PS5-60-IJ-0001A |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Neutral Grounding resistor for Generator set 1 (A) | EACOP | CPP AGI |  |  | 8 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone B | TM-00034
T-00034-0060 | PS5-60-IJ-0001B |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Neutral Grounding resistor for Generator set 2 (B) | EACOP | CPP AGI |  |  | 8 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone B | TM-00034
T-00034-0061 | PS5-60-IJ-0001C |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Neutral Grounding resistor for Generator set 3 (C) | EACOP | CPP AGI |  |  | 8 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone D | TM-00034
T-00034-0062 | PS5-60-IJ-0001D |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Neutral Grounding resistor for Generator set 4 (D) | EACOP | CPP AGI |  |  | 8 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone D | TM-00034
T-00039-0295 | PS5 - POWER DISTRIBUTION AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  | 10 | TZ-MID-68-WPR2-151148 | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | Priority-1 |  | Earthing System | E | Submitted | PS5 - Milestone A | TM-00039 |  | TZ-MID-68-WPR2-151148
T-00039-0296 | PS5 - POWER GENERATION BUILDING AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-151152 | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | Priority-1 |  | Earthing System | E | Submitted | PS5 - Milestone A | TM-00039 |  | TZ-MID-68-WPR2-151152
T-00039-0297 | PS5 - POWER GENERATION COOLING TOWER AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-151154 | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | Priority-1 |  | Earthing System | E | Submitted | PS5 - Milestone A | TM-00039 |  | TZ-MID-68-WPR2-151154
T-00039-0309 | PS5-84-OB-0005_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing for Generator Electrical Building | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-151181 | PS5 - TZA - PS5 - Tanzania | PS5-63-03 - Electrical Earthing - Generator Building |  | PS5-63-03 | Priority-1 |  | Earthing System | E | To be completed | PS5 - Milestone B | TM-00039 |  | TZ-MID-68-WPR2-151181
T-00044-0090 | PS5-60-IE-0003A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GCP G-1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | TM-00044
T-00044-0091 | PS5-60-IE-0003B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GCP G-2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | TM-00044
T-00044-0092 | PS5-60-IE-0003C |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GCP G-3 (C) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Console / Control Panel | E | To be completed | PS5 - Milestone D | TM-00044
T-00044-0093 | PS5-60-IE-0003D |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GCP G-4 (D) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Console / Control Panel | E | To be completed | PS5 - Milestone D | TM-00044
T-00044-0097 | PS5-60-IE-0004 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | MCP- MASTER CONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | TM-00044
T-00044-0098 | PS5-60-IH-0001A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENSET MCC -1 - G1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 | Priority-1 |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | TM-00044
T-00044-0099 | PS5-60-IH-0001B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENSET MCC -2 - G2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 | Priority-1 |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | TM-00044
T-00044-0100 | PS5-60-IH-0001C |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENSET MCC -3 - G3 (C) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 | Priority-2 |  | Console / Control Panel | E | To be completed | PS5 - Milestone D | TM-00044
T-00044-0101 | PS5-60-IH-0001D |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENSET MCC -4 - G4 (D) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 | Priority-2 |  | Console / Control Panel | E | To be completed | PS5 - Milestone D | TM-00044
T-00044-0105 | PS5-60-IH-0002 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COMMON / TREATMENT MCC | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | TM-00044
T-00044-0106 | PS5-60-IE-0002A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | TM-00044
T-00044-0107 | PS5-60-IE-0002B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | TM-00044
T-00044-0108 | PS5-60-IE-0002C |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Console / Control Panel | E | To be completed | PS5 - Milestone D | TM-00044
T-00044-0109 | PS5-60-IE-0002D |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Console / Control Panel | E | To be completed | PS5 - Milestone D | TM-00044
T-00044-0185 | PS5-60-IN-0002A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | TM-00044
T-00044-0186 | PS5-60-IN-0002B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | TM-00044
T-00044-0187 | PS5-60-IN-0002C |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Console / Control Panel | E | To be completed | PS5 - Milestone D | TM-00044
T-00044-0188 | PS5-60-IN-0002D |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Console / Control Panel | E | To be completed | PS5 - Milestone D | TM-00044
T-00044-0199 | PS5-71-IN-0003 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | DFO- PRE PRESSURE CONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 | Priority-1 |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | TM-00044
T-00044-0200 | PS5-71-IN-0004A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRO- SEPARATOR CONTROL PANEL-1 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Console / Control Panel | E | To be completed | PS5 - Milestone H | TM-00044
T-00044-0201 | PS5-71-IN-0004B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRO- SEPARATOR CONTROL PANEL-2 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Console / Control Panel | E | To be completed | PS5 - Milestone H | TM-00044
T-00046-0291 | PS5-60-UR-8100A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION PACKAGE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135100
T-00046-0292 | PS5-60-UR-8100B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION PACKAGE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135103
T-00046-0293 | PS5-60-UR-8100C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION PACKAGE C | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135106
T-00046-0294 | PS5-60-UR-8100D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION PACKAGE D | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135109
T-00046-0300 | PS5-60-UA-5100 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COMPRESSOR AIR STARTING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135128 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135128
T-00046-0301 | PS5-60-UO-81100A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135124
T-00046-0302 | PS5-60-UO-81100B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135124
T-00046-0303 | PS5-60-UO-81100C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135124
T-00046-0304 | PS5-60-UO-81100D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135124
T-00046-0308 | PS5-60-UZ-8200A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135129
T-00046-0309 | PS5-60-UZ-8200B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135129
T-00046-0310 | PS5-60-UZ-8200C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135129
T-00046-0311 | PS5-60-UZ-8200D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135129
T-00046-0314 | PS5-60-VS-9100A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135130
T-00046-0315 | PS5-60-VS-9100B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135130
T-00046-0316 | PS5-60-VS-9100C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C |  | PS5-60-44 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135130
T-00046-0317 | PS5-60-VS-9100D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D |  | PS5-60-45 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135130
T-00046-0321 | PS5-71-UZ-6500 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | DIESEL FUEL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135009 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone F | TM-00046 |  | TZ-MID-68-WPR2-135009
T-00046-0322 | PS5-71-UZ-6800A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE FUEL SEPARATOR MODULE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135002 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone H | TM-00046 |  | TZ-MID-68-WPR2-135002
T-00046-0323 | PS5-71-UZ-6800B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE FUEL SEPARATOR MODULE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135002 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone H | TM-00046 |  | TZ-MID-68-WPR2-135002
T-00046-0327 | PS5-60-EA-2100A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135122
T-00046-0328 | PS5-60-EA-2100B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135122
T-00046-0329 | PS5-60-EA-21100A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135100
T-00046-0330 | PS5-60-EA-21100B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135103
T-00046-0331 | PS5-60-EA-21100C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135106
T-00046-0332 | PS5-60-EA-21100D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135109
T-00046-0336 | PS5-60-EA-21200A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135100
T-00046-0337 | PS5-60-EA-21200B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135103
T-00046-0338 | PS5-60-EA-21200C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135106
T-00046-0339 | PS5-60-EA-21200D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135109
T-00046-0343 | PS5-60-EA-2200A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135122
T-00046-0344 | PS5-60-EA-2200B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135122
T-00046-0345 | PS5-60-EA-2300A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135122
T-00046-0346 | PS5-60-EA-2300B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135122
T-00046-0347 | PS5-60-EA-2400A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135122
T-00046-0348 | PS5-60-EA-2400B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135122
T-00046-0355 | PS5-60-EA-2800A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135129
T-00046-0356 | PS5-60-EA-2800B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135129
T-00046-0357 | PS5-60-EA-2800C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135129
T-00046-0358 | PS5-60-EA-2800D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135129
T-00046-0362 | PS5-60-EA-2900A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135123
T-00046-0363 | PS5-60-EA-2900B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135123
T-00046-0364 | PS5-60-EA-2900C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135123
T-00046-0365 | PS5-60-EA-2900D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135123
T-00046-0369 | PS5-60-TCV-0001A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135136
T-00046-0370 | PS5-60-TCV-0001B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135136
T-00046-0371 | PS5-60-TCV-0001C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135136
T-00046-0372 | PS5-60-TCV-0001D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135136
T-00046-0376 | PS5-60-TCV-0002A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135137
T-00046-0377 | PS5-60-TCV-0002B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135137
T-00046-0378 | PS5-60-TCV-0002C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135137
T-00046-0379 | PS5-60-TCV-0002D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135137
T-00046-0383 | PS5-60-UA-5200 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INSTRUMENT AIR COMPRESSOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135127 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135127
T-00046-0384 | PS5-60-UR-8200A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135100
T-00046-0385 | PS5-60-UR-8200B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135103
T-00046-0386 | PS5-60-UR-8200C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135106
T-00046-0387 | PS5-60-UR-8200D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135109
T-00046-0392 | PS5-60-UZ-8900A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135123
T-00046-0393 | PS5-60-UZ-8900B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135123
T-00046-0394 | PS5-60-UZ-8900C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135123
T-00046-0395 | PS5-60-UZ-8900D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046 |  | TZ-MID-68-WPR2-135123
T-00046-0400 | PS5-71-UZ-6400 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135004 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone H | TM-00046 |  | TZ-MID-68-WPR2-135004
T-00046-0401 | PS5-71-UZ-6700 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | DIESEL FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135126 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046 |  | TZ-MID-68-WPR2-135126
T-00046-0552 | PS5-60-UR-8300A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046
T-00046-0553 | PS5-60-UR-8300B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00046
T-00046-0554 | PS5-60-UR-8300C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046
T-00046-0555 | PS5-60-UR-8300D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00046
T-00227-0133 | PS5-61-IU-0001A |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 24 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Power Transformer | E | To be completed | PS5 - Milestone B | TM-00227
T-00227-0134 | PS5-61-IU-0001B |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 24 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Power Transformer | E | To be completed | PS5 - Milestone B | TM-00227
T-00227-0135 | PS5-61-IU-0001C |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 24 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Power Transformer | E | To be completed | PS5 - Milestone D | TM-00227
T-00227-0136 | PS5-61-IU-0001D |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 24 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Power Transformer | E | To be completed | PS5 - Milestone D | TM-00227
T-00232-0970 | PS5-60-IJ-0001A-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-60-IJ-0001A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-03-14 04:26 | PS5-60-01 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-0971 | PS5-60-IJ-0001B-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-60-IJ-0001B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-03-14 04:27 | PS5-60-04 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-0972 | PS5-60-IJ-0001C-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100C TO PS5-60-IJ-0001C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-03-14 04:28 | PS5-60-07 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-0973 | PS5-60-IJ-0001D-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100D TO PS5-60-IJ-0001D | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-03-14 04:28 | PS5-60-10 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1013 | PS5-61-IJ-0001-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-13 05:39 | PS5-60-01 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1014 | PS5-61-IJ-0001-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-13 05:42 | PS5-60-01 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1015 | PS5-61-IJ-0001-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-13 05:42 | PS5-60-01 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1016 | PS5-61-IJ-0001-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-13 05:43 | PS5-60-04 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1017 | PS5-61-IJ-0001-CH05 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-13 05:44 | PS5-60-04 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1018 | PS5-61-IJ-0001-CH06 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-13 05:44 | PS5-60-04 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1019 | PS5-61-IJ-0001-CH07 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001C TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-13 05:45 | PS5-60-07 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1020 | PS5-61-IJ-0001-CH08 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001C TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-13 05:45 | PS5-60-07 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1021 | PS5-61-IJ-0001-CH09 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001C TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-13 05:46 | PS5-60-07 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1022 | PS5-61-IJ-0001-CH10 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001D TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-13 05:46 | PS5-60-10 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1023 | PS5-61-IJ-0001-CH11 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001D TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-13 05:47 | PS5-60-10 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1024 | PS5-61-IJ-0001-CH12 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001D TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-13 05:47 | PS5-60-10 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1046 | PS5-61-IU-0001A-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-17 05:50 | PS5-60-01 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1047 | PS5-61-IU-0001A-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-17 05:50 | PS5-60-01 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1048 | PS5-61-IU-0001A-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-17 05:51 | PS5-60-01 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1049 | PS5-61-IU-0001B-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-17 05:51 | PS5-60-04 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1050 | PS5-61-IU-0001B-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-17 05:52 | PS5-60-04 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1051 | PS5-61-IU-0001B-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-17 05:52 | PS5-60-04 | Priority-1 |  | HV Power Cable | E | Closed | PS5 - Milestone B | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1052 | PS5-61-IU-0001C-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100C TO PS5-61-IU-0001C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-17 05:53 | PS5-60-07 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1053 | PS5-61-IU-0001C-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100C TO PS5-61-IU-0001C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-17 05:53 | PS5-60-07 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1054 | PS5-61-IU-0001C-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100C TO PS5-61-IU-0001C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-17 05:54 | PS5-60-07 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1055 | PS5-61-IU-0001D-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100D TO PS5-61-IU-0001D | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-17 05:55 | PS5-60-10 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1056 | PS5-61-IU-0001D-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100D TO PS5-61-IU-0001D | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-17 05:55 | PS5-60-10 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00232-1057 | PS5-61-IU-0001D-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100D TO PS5-61-IU-0001D | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-17 05:56 | PS5-60-10 | Priority-2 |  | HV Power Cable | E | Closed | PS5 - Milestone D | TM-00232 | ovchinnikov, konstantin | TZ-MID-68-WPR2-150101
T-00233-10536 | PS5-60-IN-0002A-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00233
T-00233-10537 | PS5-60-IN-0002B-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00233
T-00233-10538 | PS5-60-IN-0002C-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-10539 | PS5-60-IN-0002D-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-10593 | PS5-60-IH-0001A-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00233
T-00233-10594 | PS5-60-IH-0001B-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00233
T-00233-10595 | PS5-60-IH-0001C-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-10596 | PS5-60-IH-0001D-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-10600 | PS5-60-IH-0002-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:17 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-10601 | PS5-60-IH-0002-CG02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:17 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-10890 | PS5-60-BE-0007A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-06-27 08:59 | PS5-60-56 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-10891 | PS5-60-BE-0007A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-06-27 09:04 | PS5-60-56 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-10892 | PS5-60-BE-0007B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-06-27 09:24 | PS5-60-58 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-10893 | PS5-60-BE-0007B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-06-27 09:25 | PS5-60-58 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-10894 | PS5-60-BE-0007C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0007C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 2026-07-11 13:38 | PS5-60-60 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed
T-00233-10895 | PS5-60-BE-0007C-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0007C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 2026-07-11 13:40 | PS5-60-60 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed
T-00233-10896 | PS5-60-BE-0007D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0007D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2026-06-11 05:19 | PS5-60-62 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed
T-00233-10897 | PS5-60-BE-0007D-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0007D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2026-06-11 05:19 | PS5-60-62 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed
T-00233-10904 | PS5-60-ISO-62800A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-ISO-62800A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-07-11 08:48 | PS5-60-03 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-10905 | PS5-60-ISO-62800C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-ISO-62800C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-11253 | PS5-71-BE-0001A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11254 | PS5-71-BE-0001A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11255 | PS5-71-BE-0001A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11256 | PS5-71-BE-0001A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11257 | PS5-71-BE-0001A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11258 | PS5-71-BE-0001A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11259 | PS5-71-BE-0001A-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11260 | PS5-71-BE-0001A-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11261 | PS5-71-BE-0001A-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11262 | PS5-71-BE-0001A-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11263 | PS5-71-BE-0001A-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11264 | PS5-71-BE-0001A-CL12 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004A TO PS5-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11265 | PS5-71-BE-0001B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11266 | PS5-71-BE-0001B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11267 | PS5-71-BE-0001B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11268 | PS5-71-BE-0001B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11269 | PS5-71-BE-0001B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11270 | PS5-71-BE-0001B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11271 | PS5-71-BE-0001B-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11272 | PS5-71-BE-0001B-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11273 | PS5-71-BE-0001B-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11274 | PS5-71-BE-0001B-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11275 | PS5-71-BE-0001B-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-11276 | PS5-71-BE-0001B-CL12 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0004B TO PS5-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-4725 | PS5-03-SEA-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-03-SEA-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone E | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-4978 | PS5-60-BE-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-06-27 09:27 | PS5-60-27 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-4979 | PS5-60-BE-0001-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-06-27 09:28 | PS5-60-27 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-4981 | PS5-60-BE-0001-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-06-27 08:44 | PS5-60-27 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-4982 | PS5-60-BE-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-27 08:53 | PS5-60-26 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-4983 | PS5-60-BE-0002-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-27 08:55 | PS5-60-26 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-4984 | PS5-60-BE-0002-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-27 09:29 | PS5-60-26 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-4986 | PS5-60-BE-0002-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-27 08:52 | PS5-60-26 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-4987 | PS5-60-BE-0003A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 04:41 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-4988 | PS5-60-BE-0003B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 04:42 | PS5-60-04 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-4989 | PS5-60-BE-0003C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-4990 | PS5-60-BE-0003D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-4994 | PS5-60-BE-0004A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0004A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-4995 | PS5-60-BE-0004B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0004B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-4996 | PS5-60-BE-0004C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0004C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-4997 | PS5-60-BE-0004D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0004D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5001 | PS5-60-BE-0005A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0005A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-11 05:20 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5002 | PS5-60-BE-0005B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0005B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-04 11:52 | PS5-60-04 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5003 | PS5-60-BE-0005C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0005C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5004 | PS5-60-BE-0005D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0005D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-19 05:12 | PS5-60-10 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5008 | PS5-60-BE-0011A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-05 07:47 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5009 | PS5-60-BE-0011A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-05 07:49 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5010 | PS5-60-BE-0011A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-07-04 11:52 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5011 | PS5-60-BE-0011A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-06 04:42 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5012 | PS5-60-BE-0011A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-07-04 11:53 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5013 | PS5-60-BE-0011A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-07-04 11:54 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5014 | PS5-60-BE-0011B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-07-04 11:54 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5015 | PS5-60-BE-0011B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-07-04 11:57 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5016 | PS5-60-BE-0011B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-07-04 11:58 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5017 | PS5-60-BE-0011B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-07-04 11:59 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5018 | PS5-60-BE-0011B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-07-04 11:59 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5019 | PS5-60-BE-0011B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-07-04 12:00 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5020 | PS5-60-BE-0012A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-04 12:01 | PS5-60-04 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5021 | PS5-60-BE-0012A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-04 12:02 | PS5-60-04 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5022 | PS5-60-BE-0012A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-04 12:02 | PS5-60-04 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5023 | PS5-60-BE-0012A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-04 12:03 | PS5-60-04 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5024 | PS5-60-BE-0012A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-04 12:04 | PS5-60-04 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5025 | PS5-60-BE-0012A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-04 12:05 | PS5-60-04 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5026 | PS5-60-BE-0012B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-04 12:05 | PS5-60-04 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5027 | PS5-60-BE-0012B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-04 12:06 | PS5-60-04 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5028 | PS5-60-BE-0012B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-04 12:07 | PS5-60-04 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5029 | PS5-60-BE-0012B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-04 12:08 | PS5-60-04 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5030 | PS5-60-BE-0012B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-04 12:09 | PS5-60-04 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5031 | PS5-60-BE-0012B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 04:43 | PS5-60-04 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5032 | PS5-60-BE-0013A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5033 | PS5-60-BE-0013A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5034 | PS5-60-BE-0013A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5035 | PS5-60-BE-0013A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5036 | PS5-60-BE-0013A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5037 | PS5-60-BE-0013A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5038 | PS5-60-BE-0013B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5039 | PS5-60-BE-0013B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5040 | PS5-60-BE-0013B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5041 | PS5-60-BE-0013B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5042 | PS5-60-BE-0013B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5043 | PS5-60-BE-0013B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5044 | PS5-60-BE-0014A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5045 | PS5-60-BE-0014A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5046 | PS5-60-BE-0014A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5047 | PS5-60-BE-0014A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5048 | PS5-60-BE-0014A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5049 | PS5-60-BE-0014A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5050 | PS5-60-BE-0014B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5051 | PS5-60-BE-0014B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5052 | PS5-60-BE-0014B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5053 | PS5-60-BE-0014B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5054 | PS5-60-BE-0014B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5055 | PS5-60-BE-0014B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5092 | PS5-60-BE-0021A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0021A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-06 04:42 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5093 | PS5-60-BE-0021B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0021B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 08:29 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5094 | PS5-60-BE-0024A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0024A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-06-11 10:41 | PS5-60-35 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5095 | PS5-60-BE-0024A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0024A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-06-11 10:42 | PS5-60-35 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5096 | PS5-60-BE-0024B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0024B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-06-11 10:43 | PS5-60-36 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5097 | PS5-60-BE-0024B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0024B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-06-11 10:43 | PS5-60-36 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5098 | PS5-60-BE-0024C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0024C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C | 2026-07-11 07:39 | PS5-60-37 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5099 | PS5-60-BE-0024C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0024C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C | 2026-07-11 08:03 | PS5-60-37 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5100 | PS5-60-BE-0024D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0024D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D | 2026-06-11 10:44 | PS5-60-38 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5101 | PS5-60-BE-0024D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0024D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D | 2026-06-11 10:45 | PS5-60-38 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5108 | PS5-60-BE-0025A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0025A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-06-19 04:43 | PS5-60-35 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5109 | PS5-60-BE-0025B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0025B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-06-19 04:44 | PS5-60-36 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5110 | PS5-60-BE-0025C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0025C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C | 2026-07-11 08:19 | PS5-60-37 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5111 | PS5-60-BE-0025D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0025D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D | 2026-06-19 08:35 | PS5-60-38 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5115 | PS5-60-BE-0026A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0026A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-19 04:45 | PS5-60-70 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5116 | PS5-60-BE-0026A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0026A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-19 04:45 | PS5-60-70 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5117 | PS5-60-BE-0026B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0026B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-19 04:45 | PS5-60-71 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5118 | PS5-60-BE-0026B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0026B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-19 04:46 | PS5-60-71 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5119 | PS5-60-BE-0026C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0026C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-07-11 08:31 | PS5-60-72 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5120 | PS5-60-BE-0026C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0026C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-19 04:46 | PS5-60-72 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5121 | PS5-60-BE-0026D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0026D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-11 10:45 | PS5-60-73 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5122 | PS5-60-BE-0026D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0026D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-11 10:46 | PS5-60-73 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5129 | PS5-60-BI-0005A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0005A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-05 07:51 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5130 | PS5-60-BI-0005B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0005B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-05 07:52 | PS5-60-04 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5131 | PS5-60-BI-0005C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0005C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-06-05 07:52 | PS5-60-07 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5132 | PS5-60-BI-0005D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0005D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-06 04:43 | PS5-60-10 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5136 | PS5-60-BI-0015A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5137 | PS5-60-BI-0015A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 04:48 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5138 | PS5-60-BI-0015A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 04:48 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5139 | PS5-60-BI-0015B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5140 | PS5-60-BI-0015B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 04:48 | PS5-60-04 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5141 | PS5-60-BI-0015B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 04:49 | PS5-60-04 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5142 | PS5-60-BI-0015C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0015C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5143 | PS5-60-BI-0015C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0015C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5144 | PS5-60-BI-0015C-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0015C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5145 | PS5-60-BI-0015D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0015D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5146 | PS5-60-BI-0015D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0015D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-19 04:50 | PS5-60-10 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5147 | PS5-60-BI-0015D-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0015D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-19 04:51 | PS5-60-10 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5157 | PS5-60-DD-62800A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-DD-62800A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5159 | PS5-60-DD-62800C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-DD-62800C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5166 | PS5-60-IE-0002A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:28 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5167 | PS5-60-IE-0002A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:31 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5168 | PS5-60-IE-0002A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:31 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5169 | PS5-60-IE-0002B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-06 04:44 | PS5-60-04 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5170 | PS5-60-IE-0002B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-06 04:45 | PS5-60-04 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5171 | PS5-60-IE-0002B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:31 | PS5-60-04 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5172 | PS5-60-IE-0002C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5173 | PS5-60-IE-0002C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-11 09:13 | PS5-60-07 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5174 | PS5-60-IE-0002C-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5175 | PS5-60-IE-0002D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-19 04:23 | PS5-60-10 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5176 | PS5-60-IE-0002D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-19 04:23 | PS5-60-10 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5177 | PS5-60-IE-0002D-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5187 | PS5-60-IE-0003A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) | 2026-06-19 04:25 | PS5-60-02 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5188 | PS5-60-IE-0003A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) | 2026-06-19 04:26 | PS5-60-02 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5189 | PS5-60-IE-0003B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) | 2026-06-19 04:26 | PS5-60-05 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5190 | PS5-60-IE-0003B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) | 2026-06-19 04:27 | PS5-60-05 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5191 | PS5-60-IE-0003C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5192 | PS5-60-IE-0003C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5193 | PS5-60-IE-0003D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5194 | PS5-60-IE-0003D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) | 2026-06-19 04:27 | PS5-60-11 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5201 | PS5-60-IE-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:28 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5202 | PS5-60-IE-0004-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:28 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5204 | PS5-60-IH-0001A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-19 08:23 | PS5-60-03 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5205 | PS5-60-IH-0001A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-19 08:24 | PS5-60-03 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5206 | PS5-60-IH-0001A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-19 08:25 | PS5-60-03 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5207 | PS5-60-IH-0001A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-19 08:26 | PS5-60-03 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5208 | PS5-60-IH-0001A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-19 08:31 | PS5-60-03 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5209 | PS5-60-IH-0001A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-19 04:28 | PS5-60-03 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5211 | PS5-60-IH-0001B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-19 08:28 | PS5-60-06 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5212 | PS5-60-IH-0001B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-19 08:28 | PS5-60-06 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5213 | PS5-60-IH-0001B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-19 08:28 | PS5-60-06 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5214 | PS5-60-IH-0001B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-19 08:29 | PS5-60-06 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5215 | PS5-60-IH-0001B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-19 04:29 | PS5-60-06 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5216 | PS5-60-IH-0001B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-19 04:32 | PS5-60-06 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5218 | PS5-60-IH-0001C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | 2026-07-11 09:30 | PS5-60-09 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5219 | PS5-60-IH-0001C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | 2026-07-11 09:32 | PS5-60-09 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5220 | PS5-60-IH-0001C-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | 2026-07-11 09:34 | PS5-60-09 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5221 | PS5-60-IH-0001C-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | 2026-07-11 09:38 | PS5-60-09 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5222 | PS5-60-IH-0001C-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5223 | PS5-60-IH-0001C-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5225 | PS5-60-IH-0001D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5226 | PS5-60-IH-0001D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5227 | PS5-60-IH-0001D-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5228 | PS5-60-IH-0001D-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5229 | PS5-60-IH-0001D-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | 2026-06-19 04:33 | PS5-60-12 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5230 | PS5-60-IH-0001D-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5254 | PS5-60-IH-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:33 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5255 | PS5-60-IH-0002-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:33 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5256 | PS5-60-IH-0002-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:18 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5257 | PS5-60-IH-0002-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:20 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5258 | PS5-60-IH-0002-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:20 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5259 | PS5-60-IH-0002-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:20 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5260 | PS5-60-IH-0002-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:21 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5261 | PS5-60-IH-0002-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:21 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5262 | PS5-60-IH-0002-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:21 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5263 | PS5-60-IH-0002-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:20 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5264 | PS5-60-IN-0001A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2026-06-19 04:51 | PS5-60-49 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5265 | PS5-60-IN-0001B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2026-06-19 04:51 | PS5-60-50 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5266 | PS5-60-IN-0001C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5267 | PS5-60-IN-0001D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | 2026-06-19 04:50 | PS5-60-52 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5271 | PS5-60-IN-0002A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | 2026-06-19 08:35 | PS5-60-57 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5272 | PS5-60-IN-0002A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | 2026-06-19 08:31 | PS5-60-57 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5273 | PS5-60-IN-0002A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | 2026-06-19 08:31 | PS5-60-57 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5274 | PS5-60-IN-0002B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | 2026-06-19 08:35 | PS5-60-59 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5275 | PS5-60-IN-0002B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | 2026-06-19 08:31 | PS5-60-59 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5276 | PS5-60-IN-0002B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | 2026-06-19 08:33 | PS5-60-59 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5277 | PS5-60-IN-0002C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5278 | PS5-60-IN-0002C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5279 | PS5-60-IN-0002C-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5280 | PS5-60-IN-0002D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | 2026-06-19 04:53 | PS5-60-63 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5281 | PS5-60-IN-0002D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | 2026-06-19 04:32 | PS5-60-63 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5282 | PS5-60-IN-0002D-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | 2026-06-19 04:32 | PS5-60-63 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5292 | PS5-60-IWK-0001A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5293 | PS5-60-IWK-0001A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5294 | PS5-60-IWK-0001B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:32 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5295 | PS5-60-IWK-0001B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:32 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5296 | PS5-60-IWK-0001C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:34 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5297 | PS5-60-IWK-0001C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:34 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5298 | PS5-60-LA-0002A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 04:34 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5299 | PS5-60-LA-0002A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 04:34 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5300 | PS5-60-LA-0002B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5301 | PS5-60-LA-0002B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5304 | PS5-60-LA-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 08:33 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5305 | PS5-60-LA-0003-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 08:32 | PS5-60-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5310 | PS5-60-SEA-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone E | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5311 | PS5-60-SEA-0001-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone E | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5312 | PS5-60-VS-9100A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-VS-9100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-06-19 04:53 | PS5-60-42 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5313 | PS5-60-VS-9100B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-VS-9100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-06-19 04:53 | PS5-60-43 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5314 | PS5-60-VS-9100C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-VS-9100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C |  | PS5-60-44 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5315 | PS5-60-VS-9100D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-VS-9100D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | 2026-06-19 04:54 | PS5-60-45 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5319 | PS5-61-BI-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-05-25 17:35 | PS5-60-01 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5320 | PS5-61-BI-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-05-25 17:35 | PS5-60-04 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5321 | PS5-61-BI-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-61-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-05-29 14:43 | PS5-60-07 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Anwar, Zeeshan | TZ-MID-68-WPR2-150101
T-00233-5322 | PS5-61-BI-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-61-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-05-29 14:42 | PS5-60-10 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Anwar, Zeeshan | TZ-MID-68-WPR2-150101
T-00233-5562 | PS5-71-FCV-0019-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0043 TO PS5-71-FCV-0019 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B | 2026-05-25 17:33 | PS5-71-21 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5584 | PS5-71-IN-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-06-19 04:37 | PS5-71-23 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5585 | PS5-71-IN-0003-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-06-19 04:38 | PS5-71-23 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5586 | PS5-71-IN-0003-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-06-06 04:50 | PS5-71-23 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5587 | PS5-71-IN-0004A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-11 09:23 | PS5-71-07 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone H | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5588 | PS5-71-IN-0004A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-11 09:27 | PS5-71-07 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone H | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5589 | PS5-71-IN-0004A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) | 2026-06-05 08:05 | PS5-71-07 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone H | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5590 | PS5-71-IN-0004B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5591 | PS5-71-IN-0004B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5592 | PS5-71-IN-0004B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) | 2026-06-05 08:07 | PS5-71-07 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone H | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5594 | PS5-71-MOV-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-06-11 04:56 | PS5-71-08 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone H | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5595 | PS5-71-MOV-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-06-04 17:59 | PS5-71-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5596 | PS5-71-MOV-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-06-11 04:56 | PS5-71-08 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone H | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5597 | PS5-71-MOV-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-06-04 18:00 | PS5-71-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5599 | PS5-71-MOV-0008-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-06-04 18:01 | PS5-71-08 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone H | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5601 | PS5-71-MOV-0010-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-06-11 04:57 | PS5-71-08 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone H | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5602 | PS5-71-SDV-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0043 TO PS5-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank | 2026-05-25 17:31 | PS5-71-20 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-5609 | PS5-71-XV-0091-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone F | TM-00233 |  | TZ-MID-68-WPR2-150101
T-00233-5610 | PS5-71-XV-0092-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank | 2026-05-25 17:29 | PS5-71-20 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00233-9131 | PS5-60-BE-0007A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-06-27 08:56 | PS5-60-56 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9132 | PS5-60-BE-0007B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-06-27 09:13 | PS5-60-58 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9133 | PS5-60-BE-0007C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0007C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 2026-07-11 13:36 | PS5-60-60 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed
T-00233-9134 | PS5-60-BE-0007D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0007D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2026-06-19 04:22 | PS5-60-62 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed
T-00233-9138 | PS5-60-BE-0027A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0027A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:40 | PS5-60-56 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9139 | PS5-60-BE-0027B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0027B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00233
T-00233-9140 | PS5-60-BE-0027C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0027C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9141 | PS5-60-BE-0027D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0027D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9145 | PS5-60-BE-0028A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0028A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:39 | PS5-60-56 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9146 | PS5-60-BE-0028B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0028B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 13:25 | PS5-60-58 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9147 | PS5-60-BE-0028C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0028C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9148 | PS5-60-BE-0028D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0028D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9152 | PS5-60-BI-0006A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:38 | PS5-60-56 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9153 | PS5-60-BI-0006A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 14:12 | PS5-60-56 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9154 | PS5-60-BI-0006A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 13:28 | PS5-60-56 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9155 | PS5-60-BI-0006A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:36 | PS5-60-56 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9156 | PS5-60-BI-0006A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:34 | PS5-60-56 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9157 | PS5-60-BI-0006A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:33 | PS5-60-56 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9158 | PS5-60-BI-0006A-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:33 | PS5-60-56 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9159 | PS5-60-BI-0006A-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:32 | PS5-60-56 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9160 | PS5-60-BI-0006A-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 13:29 | PS5-60-56 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9161 | PS5-60-BI-0006A-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:32 | PS5-60-56 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9162 | PS5-60-BI-0006A-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:30 | PS5-60-56 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9163 | PS5-60-BI-0006B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:29 | PS5-60-58 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9164 | PS5-60-BI-0006B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 13:31 | PS5-60-58 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9165 | PS5-60-BI-0006B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 13:32 | PS5-60-58 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9166 | PS5-60-BI-0006B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:28 | PS5-60-58 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9167 | PS5-60-BI-0006B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:28 | PS5-60-58 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9168 | PS5-60-BI-0006B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:27 | PS5-60-58 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9169 | PS5-60-BI-0006B-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:26 | PS5-60-58 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9170 | PS5-60-BI-0006B-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:25 | PS5-60-58 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9171 | PS5-60-BI-0006B-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:25 | PS5-60-58 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9172 | PS5-60-BI-0006B-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:24 | PS5-60-58 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9173 | PS5-60-BI-0006B-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:24 | PS5-60-58 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9174 | PS5-60-BI-0006C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 2026-07-11 06:35 | PS5-60-60 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed
T-00233-9175 | PS5-60-BI-0006C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9176 | PS5-60-BI-0006C-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9177 | PS5-60-BI-0006C-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9178 | PS5-60-BI-0006C-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9179 | PS5-60-BI-0006C-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9180 | PS5-60-BI-0006C-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9181 | PS5-60-BI-0006C-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9182 | PS5-60-BI-0006C-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9183 | PS5-60-BI-0006C-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9184 | PS5-60-BI-0006C-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9185 | PS5-60-BI-0006D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2026-07-11 06:37 | PS5-60-62 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed
T-00233-9186 | PS5-60-BI-0006D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9187 | PS5-60-BI-0006D-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9188 | PS5-60-BI-0006D-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9189 | PS5-60-BI-0006D-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9190 | PS5-60-BI-0006D-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9191 | PS5-60-BI-0006D-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9192 | PS5-60-BI-0006D-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9193 | PS5-60-BI-0006D-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9194 | PS5-60-BI-0006D-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9195 | PS5-60-BI-0006D-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9229 | PS5-60-BI-0017A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0017A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:23 | PS5-60-56 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9230 | PS5-60-BI-0017B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0017B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:23 | PS5-60-58 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9231 | PS5-60-BI-0017C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0017C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9232 | PS5-60-BI-0017D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0017D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone D | TM-00233
T-00233-9236 | PS5-60-EA-2900A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-EA-2900A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00233
T-00233-9237 | PS5-60-EA-2900B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-EA-2900B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | LV Power Cable | E | To be completed | PS5 - Milestone B | TM-00233
T-00233-9238 | PS5-60-EA-2900C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-EA-2900C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 2026-07-11 06:42 | PS5-60-60 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed
T-00233-9239 | PS5-60-EA-2900D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-EA-2900D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2026-07-11 06:45 | PS5-60-62 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone D | TM-00233 | Gawad, Mohamed
T-00233-9244 | PS5-71-BE-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-07-03 09:19 | PS5-71-08 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone H | TM-00233 | Gawad, Mohamed
T-00233-9245 | PS5-71-BE-0004-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-9246 | PS5-71-BE-0004-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-07-03 09:21 | PS5-71-08 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone H | TM-00233 | Gawad, Mohamed
T-00233-9247 | PS5-71-BI-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-07-03 09:24 | PS5-71-08 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone H | TM-00233 | Gawad, Mohamed
T-00233-9248 | PS5-71-BI-0003-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-07-11 14:05 | PS5-71-08 | Priority-2 |  | LV Power Cable | E | Closed | PS5 - Milestone H | TM-00233 | Gawad, Mohamed
T-00233-9249 | PS5-71-BI-0003-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-9250 | PS5-71-BI-0003-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-9251 | PS5-71-BI-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | LV Power Cable | E | To be completed | PS5 - Milestone H | TM-00233
T-00233-9252 | PS5-71-BI-0005-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-01 12:21 | PS5-71-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9253 | PS5-71-BI-0005-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-01 12:19 | PS5-71-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9254 | PS5-71-BI-0005-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-01 14:11 | PS5-71-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00233-9255 | PS5-71-BI-0006-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-01 12:17 | PS5-71-22 | Priority-1 |  | LV Power Cable | E | Closed | PS5 - Milestone B | TM-00233 | Gawad, Mohamed
T-00234-2101 | PS5-60-IE-0002A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:36 | PS5-60-01 | Priority-1 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2102 | PS5-60-IE-0002A-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:36 | PS5-60-01 | Priority-1 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2103 | PS5-60-IE-0002A-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:37 | PS5-60-01 | Priority-1 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2104 | PS5-60-IE-0002B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:37 | PS5-60-04 | Priority-1 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2105 | PS5-60-IE-0002B-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:36 | PS5-60-04 | Priority-1 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2106 | PS5-60-IE-0002B-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:39 | PS5-60-04 | Priority-1 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2107 | PS5-60-IE-0002C-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-03 08:45 | PS5-60-07 | Priority-2 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2108 | PS5-60-IE-0002C-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-03 08:50 | PS5-60-07 | Priority-2 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2109 | PS5-60-IE-0002C-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-03 08:52 | PS5-60-07 | Priority-2 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2110 | PS5-60-IE-0002D-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-07-03 08:57 | PS5-60-10 | Priority-2 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2111 | PS5-60-IE-0002D-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-07-03 09:01 | PS5-60-10 | Priority-2 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2112 | PS5-60-IE-0002D-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00234 |  | TZ-MID-68-WPR2-150101
T-00234-2123 | PS5-60-IE-0003A-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 04:54 | PS5-60-01 | Priority-1 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2124 | PS5-60-IE-0003A-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:37 | PS5-60-01 | Priority-1 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2125 | PS5-60-IE-0003A-CD04 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0005A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 04:38 | PS5-60-01 | Priority-1 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2126 | PS5-60-IE-0003A-CD05 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:39 | PS5-60-01 | Priority-1 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2135 | PS5-60-IE-0003A-CD14 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:38 | PS5-60-01 | Priority-1 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2136 | PS5-60-IE-0003A-CD15 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-27 09:30 | PS5-60-01 | Priority-1 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2138 | PS5-60-IE-0003B-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:39 | PS5-60-04 | Priority-1 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2139 | PS5-60-IE-0003B-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:40 | PS5-60-04 | Priority-1 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2140 | PS5-60-IE-0003B-CD04 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0005B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:34 | PS5-60-04 | Priority-1 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2141 | PS5-60-IE-0003B-CD05 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 04:55 | PS5-60-04 | Priority-1 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2150 | PS5-60-IE-0003B-CD14 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:40 | PS5-60-04 | Priority-1 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2151 | PS5-60-IE-0003B-CD15 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-27 09:31 | PS5-60-04 | Priority-1 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2153 | PS5-60-IE-0003C-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00234 |  | TZ-MID-68-WPR2-150101
T-00234-2154 | PS5-60-IE-0003C-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00234 |  | TZ-MID-68-WPR2-150101
T-00234-2155 | PS5-60-IE-0003C-CD04 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0005C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-01 14:12 | PS5-60-07 | Priority-2 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2156 | PS5-60-IE-0003C-CD05 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00234 |  | TZ-MID-68-WPR2-150101
T-00234-2165 | PS5-60-IE-0003C-CD14 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00234 |  | TZ-MID-68-WPR2-150101
T-00234-2166 | PS5-60-IE-0003C-CD15 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00234 |  | TZ-MID-68-WPR2-150101
T-00234-2168 | PS5-60-IE-0003D-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00234 |  | TZ-MID-68-WPR2-150101
T-00234-2169 | PS5-60-IE-0003D-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-19 04:56 | PS5-60-10 | Priority-2 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2170 | PS5-60-IE-0003D-CD04 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0005D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-19 04:41 | PS5-60-10 | Priority-2 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2171 | PS5-60-IE-0003D-CD05 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-19 04:56 | PS5-60-10 | Priority-2 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2180 | PS5-60-IE-0003D-CD14 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-19 04:57 | PS5-60-10 | Priority-2 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D | TM-00234 | Gawad, Mohamed | TZ-MID-68-WPR2-150101
T-00234-2181 | PS5-60-IE-0003D-CD15 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00234 |  | TZ-MID-68-WPR2-150101
T-00236-0178 | PS5-71-DM-3500A |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Diesel Transfer Pump Motor A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | LV Motor | E | To be completed | PS5 - Milestone B | TM-00236
T-00236-0179 | PS5-71-DM-3500B |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Diesel Transfer Pump Motor B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | LV Motor | E | To be completed | PS5 - Milestone B | TM-00236
T-00238-0457 | PS5-60-IE-0003A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GCP G-1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | TM-00238
T-00238-0458 | PS5-60-IE-0003B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GCP G-2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | TM-00238
T-00238-0459 | PS5-60-IE-0003C |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GCP G-3 (C) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D | TM-00238
T-00238-0460 | PS5-60-IE-0003D |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GCP G-4 (D) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D | TM-00238
T-00238-0464 | PS5-60-IE-0004 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | MCP- MASTER CONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | TM-00238
T-00238-0465 | PS5-60-IH-0001A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GENSET MCC -1 - G1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 | Priority-1 |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | TM-00238
T-00238-0466 | PS5-60-IH-0001B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GENSET MCC -2 - G2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 | Priority-1 |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | TM-00238
T-00238-0467 | PS5-60-IH-0001C |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GENSET MCC -3 - G3 (C) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 | Priority-2 |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D | TM-00238
T-00238-0468 | PS5-60-IH-0001D |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GENSET MCC -4 - G4 (D) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 | Priority-2 |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D | TM-00238
T-00238-0472 | PS5-60-IH-0002 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | COMMON / TREATMENT MCC | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | TM-00238
T-00238-0473 | PS5-60-IE-0002A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | TM-00238
T-00238-0474 | PS5-60-IE-0002B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | TM-00238
T-00238-0475 | PS5-60-IE-0002C |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D | TM-00238
T-00238-0476 | PS5-60-IE-0002D |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D | TM-00238
T-00238-0552 | PS5-60-IN-0002A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | TM-00238
T-00238-0553 | PS5-60-IN-0002B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | TM-00238
T-00238-0554 | PS5-60-IN-0002C |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D | TM-00238
T-00238-0555 | PS5-60-IN-0002D |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D | TM-00238
T-00238-0566 | PS5-71-IN-0003 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | DFO- PRE PRESSURE CONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 | Priority-1 |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | TM-00238
T-00238-0567 | PS5-71-IN-0004A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | CRO- SEPARATOR CONTROL PANEL-1 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone H | TM-00238
T-00238-0568 | PS5-71-IN-0004B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | CRO- SEPARATOR CONTROL PANEL-2 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone H | TM-00238
T-00243-0059 | PS5-60-IJ-0001A |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Neutral Grounding resistor for Generator set 1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone B | TM-00243
T-00243-0060 | PS5-60-IJ-0001B |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Neutral Grounding resistor for Generator set 2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone B | TM-00243
T-00243-0061 | PS5-60-IJ-0001C |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Neutral Grounding resistor for Generator set 3 (C) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone D | TM-00243
T-00243-0062 | PS5-60-IJ-0001D |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Neutral Grounding resistor for Generator set 4 (D) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone D | TM-00243
T-00247-0146 | PS5 - POWER DISTRIBUTION AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-151148 | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | Priority-1 |  | Earthing System | E | To be completed | PS5 - Milestone A | TM-00247 |  | TZ-MID-68-WPR2-151148
T-00247-0147 | PS5 - POWER GENERATION BUILDING AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-151152 | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | Priority-1 |  | Earthing System | E | To be completed | PS5 - Milestone A | TM-00247 |  | TZ-MID-68-WPR2-151152
T-00247-0148 | PS5 - POWER GENERATION COOLING TOWER AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-151154 | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 | Priority-1 |  | Earthing System | E | To be completed | PS5 - Milestone A | TM-00247 |  | TZ-MID-68-WPR2-151154
T-00247-0160 | PS5-84-OB-0005_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing for Generator Electrical Building | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-151181 | PS5 - TZA - PS5 - Tanzania | PS5-63-03 - Electrical Earthing - Generator Building |  | PS5-63-03 | Priority-1 |  | Earthing System | E | To be completed | PS5 - Milestone B | TM-00247 |  | TZ-MID-68-WPR2-151181
T-00608-0456 | PS5-71-DM-3500A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0001 TO PS5-71-DM-3500A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  |  | E | To be completed | PS5 - Milestone B | TM-00608
T-00608-0457 | PS5-71-DM-3500B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0001 TO PS5-71-DM-3500B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  |  | E | To be completed | PS5 - Milestone B | TM-00608
T-00610-0220 | PS5-60-IE-0003A-CD06 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00610
T-00610-0221 | PS5-60-IE-0003A-CD08 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00610
T-00610-0222 | PS5-60-IE-0003A-CD12 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00610
T-00610-0223 | PS5-60-IE-0003B-CD06 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00610
T-00610-0224 | PS5-60-IE-0003B-CD08 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00610
T-00610-0225 | PS5-60-IE-0003B-CD12 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00610
T-00610-0226 | PS5-60-IE-0003C-CD06 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00610
T-00610-0227 | PS5-60-IE-0003C-CD08 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00610
T-00610-0228 | PS5-60-IE-0003C-CD12 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00610
T-00610-0229 | PS5-60-IE-0003D-CD06 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00610
T-00610-0230 | PS5-60-IE-0003D-CD08 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00610
T-00610-0231 | PS5-60-IE-0003D-CD12 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D | TM-00610
T-00610-0241 | PS5-60-IE-0004-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00610
T-00610-0242 | PS5-60-IE-0004-CD02 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00610
T-00610-0284 | PS5-71-IES-3500A-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0001 TO PS5-71-IES-3500A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B | 2026-07-03 14:27 | PS5-71-21 | Priority-1 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | TM-00610 | Gawad, Mohamed
T-00610-0285 | PS5-71-IES-3500B-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0001 TO PS5-71-IES-3500B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B | 2026-07-03 14:30 | PS5-71-21 | Priority-1 |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | TM-00610 | Gawad, Mohamed
T-00610-0574 | PS5-60-IE-0004-CD14 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00610
T-00610-0575 | PS5-60-IE-0004-CD15 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00610
T-00610-0576 | PS5-60-IE-0004-CD16 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | TM-00610
T-00066-0066 | PS5-71-FCV-0019 |  |  |  |  | CJX06 - Tubing Hydraulic | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | Tubing Hydraulic | I | To be completed | PS5 - Milestone B | TM-00066
T-00067-0659 | PS5-03-RMAC-1409 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Electrical Instrument | I | To be completed | PS5 - Milestone E | TM-00067 |  | TZ-MID-68-WPR2-121106
T-00067-0659 | PS5-03-RMAC-1409 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Electrical Instrument | I | To be completed | PS5 - Milestone E | TM-00067 |  | UT-MID-60-WPR2-160211
T-00067-0660 | PS5-03-RMAC-1410 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Electrical Instrument | I | To be completed | PS5 - Milestone E | TM-00067 |  | TZ-MID-68-WPR2-121106
T-00067-0660 | PS5-03-RMAC-1410 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Electrical Instrument | I | To be completed | PS5 - Milestone E | TM-00067 |  | UT-MID-60-WPR2-160211
T-00067-0661 | PS5-03-RMAC-1411 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Electrical Instrument | I | To be completed | PS5 - Milestone E | TM-00067 |  | TZ-MID-68-WPR2-121106
T-00067-0661 | PS5-03-RMAC-1411 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Electrical Instrument | I | To be completed | PS5 - Milestone E | TM-00067 |  | UT-MID-60-WPR2-160211
T-00067-2052 | PS5-71-HZL-0059 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Position Switch Closed | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135009 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Electrical Instrument | I | To be completed | PS5 - Milestone F | TM-00067 |  | TZ-MID-68-WPR2-135009
T-00067-2053 | PS5-71-HZH-0059 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Position Switch Opened | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135009 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Electrical Instrument | I | To be completed | PS5 - Milestone F | TM-00067 |  | TZ-MID-68-WPR2-135009
T-00067-2057 | PS5-71-FIT-0019 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DP Flow Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135008 | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | Electrical Instrument | I | To be completed | PS5 - Milestone B | TM-00067 |  | TZ-MID-68-WPR2-135008
T-00067-2073 | PS5-71-LIT-1202 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DP Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135205 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Electrical Instrument | I | To be completed | PS5 - Milestone B | TM-00067 |  | TZ-MID-68-WPR2-135205
T-00067-2093 | PS5-71-LIT-1201 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DP Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135205 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Electrical Instrument | I | To be completed | PS5 - Milestone B | TM-00067 |  | TZ-MID-68-WPR2-135205
T-00067-2168 | PS5-71-HZL-0058 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Position Switch Closed | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | Electrical Instrument | I | To be completed | PS5 - Milestone B | TM-00067
T-00067-2169 | PS5-71-HZH-0058 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Position Switch Opened | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | Electrical Instrument | I | To be completed | PS5 - Milestone B | TM-00067
T-00067-2468 | PS5-71-IES-3500A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Diesel Transfer Pump Motor A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | Electrical Instrument | E | To be completed | PS5 - Milestone B | TM-00067
T-00067-2469 | PS5-71-IES-3500B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Diesel Transfer Pump Motor B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | Electrical Instrument | E | To be completed | PS5 - Milestone B | TM-00067
T-00069-12948 | PS5-60-BI-0001A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-12949 | PS5-60-BI-0001B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-12950 | PS5-60-BI-0001C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-BI-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-12951 | PS5-60-BI-0001D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-BI-0001D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-12955 | PS5-60-BI-0003-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-12956 | PS5-60-IE-0002A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-12957 | PS5-60-IE-0002A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-12958 | PS5-60-IE-0002A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-12959 | PS5-60-IE-0002B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-12960 | PS5-60-IE-0002B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-12961 | PS5-60-IE-0002B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-12962 | PS5-60-IE-0002C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-12963 | PS5-60-IE-0002C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-12964 | PS5-60-IE-0002C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-12965 | PS5-60-IE-0002D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-12966 | PS5-60-IE-0002D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-12967 | PS5-60-IE-0002D-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-12977 | PS5-60-IH-0001A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-12978 | PS5-60-IH-0001A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-12979 | PS5-60-IH-0001B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-12980 | PS5-60-IH-0001B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-12981 | PS5-60-IH-0001C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-12982 | PS5-60-IH-0001C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-12983 | PS5-60-IH-0001D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-12984 | PS5-60-IH-0001D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-12991 | PS5-60-IH-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-12992 | PS5-60-IH-0002-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-12993 | PS5-60-LA-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-12994 | PS5-60-LA-0003-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-12995 | PS5-60-PIT-8113A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BE-0027A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-12996 | PS5-60-PIT-8113B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BE-0027B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-12997 | PS5-60-PIT-8113C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-BE-0027C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-12998 | PS5-60-PIT-8113D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-BE-0027D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-13002 | PS5-60-PIT-8114A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BE-0027A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-13003 | PS5-60-PIT-8114B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BE-0027B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-13004 | PS5-60-PIT-8114C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-BE-0027C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-13005 | PS5-60-PIT-8114D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-BE-0027D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-13009 | PS5-71-IN-0004A-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-4487 | PS5-03-RDOS-1401-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-RMAC-1411 TO PS5-03-RDOS-1401 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-4488 | PS5-03-RDOS-1402-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-RDOS-1401 TO PS5-03-RDOS-1402 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-4489 | PS5-03-RDOS-1403-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-RDOS-1402 TO PS5-03-RDOS-1403 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-4490 | PS5-03-RDOS-1404-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-RDOS-1403 TO PS5-03-RDOS-1404 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-4491 | PS5-03-RDOS-1405-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-RDOS-1404 TO PS5-03-RDOS-1405 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-4492 | PS5-03-RDOS-1406-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-RDOS-1503 TO PS5-03-RDOS-1406 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-4493 | PS5-03-RDOS-1407-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-RDOS-1405 TO PS5-03-RDOS-1407 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-4494 | PS5-03-RDOS-1408-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-RDOS-1407 TO PS5-03-RDOS-1408 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-4540 | PS5-03-RMAC-1410-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-RDOS-2103 TO PS5-03-RMAC-1410 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-4541 | PS5-03-RMAC-1411-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-RDOS-1406 TO PS5-03-RMAC-1411 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-4888 | PS5-60-BE-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4889 | PS5-60-BE-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4890 | PS5-60-BE-0004A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0001A TO PS5-60-BE-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4891 | PS5-60-BE-0004B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0001B TO PS5-60-BE-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4892 | PS5-60-BE-0004C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0001C TO PS5-60-BE-0004C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4893 | PS5-60-BE-0004D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0001D TO PS5-60-BE-0004D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4897 | PS5-60-BI-0001A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4898 | PS5-60-BI-0001A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4899 | PS5-60-BI-0001B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4900 | PS5-60-BI-0001B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4901 | PS5-60-BI-0001C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4902 | PS5-60-BI-0001C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4903 | PS5-60-BI-0001D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4904 | PS5-60-BI-0001D-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4911 | PS5-60-BI-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4912 | PS5-60-BI-0002-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4913 | PS5-60-BI-0002-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4914 | PS5-60-BI-0002-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4915 | PS5-60-BI-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4916 | PS5-60-BI-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4917 | PS5-60-BI-0004A-CCO1 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4918 | PS5-60-BI-0004B-CCO1 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4919 | PS5-60-BI-0004C-CCO1 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-BI-0004C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4920 | PS5-60-BI-0004D-CCO1 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-BI-0004D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4924 | PS5-60-BI-0005A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0005A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4925 | PS5-60-BI-0005A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0005A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4926 | PS5-60-BI-0005B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0005B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4927 | PS5-60-BI-0005B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0005B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4928 | PS5-60-BI-0005C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0005C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4929 | PS5-60-BI-0005C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0005C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4930 | PS5-60-BI-0005D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0005D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4931 | PS5-60-BI-0005D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0005D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4938 | PS5-60-BI-0006A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4939 | PS5-60-BI-0006A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4940 | PS5-60-BI-0006A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4941 | PS5-60-BI-0006A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4942 | PS5-60-BI-0006A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4943 | PS5-60-BI-0006A-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4944 | PS5-60-BI-0006B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4945 | PS5-60-BI-0006B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4946 | PS5-60-BI-0006B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4947 | PS5-60-BI-0006B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4948 | PS5-60-BI-0006B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4949 | PS5-60-BI-0006B-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4950 | PS5-60-BI-0006C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4951 | PS5-60-BI-0006C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4952 | PS5-60-BI-0006C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4953 | PS5-60-BI-0006C-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4954 | PS5-60-BI-0006C-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4955 | PS5-60-BI-0006C-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4956 | PS5-60-BI-0006D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4957 | PS5-60-BI-0006D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4958 | PS5-60-BI-0006D-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4959 | PS5-60-BI-0006D-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4960 | PS5-60-BI-0006D-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4961 | PS5-60-BI-0006D-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4980 | PS5-60-BI-0008A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4981 | PS5-60-BI-0008A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4982 | PS5-60-BI-0008B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4983 | PS5-60-BI-0008B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4984 | PS5-60-BI-0009A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0009A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4985 | PS5-60-BI-0009A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0009A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4986 | PS5-60-BI-0009B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0009B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4987 | PS5-60-BI-0009B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0009B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-4988 | PS5-60-BI-0010A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0010A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4989 | PS5-60-BI-0010A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0010A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4990 | PS5-60-BI-0010B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0010B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4991 | PS5-60-BI-0010B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0010B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4992 | PS5-60-BI-0011A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4993 | PS5-60-BI-0011A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4994 | PS5-60-BI-0011B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-4995 | PS5-60-BI-0011B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5008 | PS5-60-BI-0016A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5009 | PS5-60-BI-0016A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5010 | PS5-60-BI-0016A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5011 | PS5-60-BI-0016A-CCO4 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5012 | PS5-60-BI-0016B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5013 | PS5-60-BI-0016B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5014 | PS5-60-BI-0016B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5015 | PS5-60-BI-0016B-CCO4 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5016 | PS5-60-BI-0016C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5017 | PS5-60-BI-0016C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5018 | PS5-60-BI-0016C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5019 | PS5-60-BI-0016C-CCO4 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5020 | PS5-60-BI-0016D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5021 | PS5-60-BI-0016D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5022 | PS5-60-BI-0016D-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5023 | PS5-60-BI-0016D-CCO4 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5036 | PS5-60-BI-0017A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0017A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5037 | PS5-60-BI-0017B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0017B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5038 | PS5-60-BI-0017C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0017C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5039 | PS5-60-BI-0017D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0017D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5043 | PS5-60-BI-0019A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0019A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5044 | PS5-60-BI-0019A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0019A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5045 | PS5-60-BI-0019B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0019B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5046 | PS5-60-BI-0019B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0019B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5047 | PS5-60-BI-0019C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0019C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5048 | PS5-60-BI-0019C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0019C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5049 | PS5-60-BI-0019D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0019D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5050 | PS5-60-BI-0019D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0019D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5057 | PS5-60-IE-0002B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5058 | PS5-60-IE-0002C-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5059 | PS5-60-IE-0002D-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5063 | PS5-60-IE-0003A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5064 | PS5-60-IE-0003A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5065 | PS5-60-IE-0003A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5066 | PS5-60-IE-0003A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5067 | PS5-60-IE-0003A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5068 | PS5-60-IE-0003A-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5069 | PS5-60-IE-0003A-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5070 | PS5-60-IE-0003A-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5071 | PS5-60-IE-0003A-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5072 | PS5-60-IE-0003A-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5073 | PS5-60-IE-0003A-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5074 | PS5-60-IE-0003A-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5075 | PS5-60-IE-0003A-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5076 | PS5-60-IE-0003A-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5081 | PS5-60-IE-0003A-CC25 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41100A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5082 | PS5-60-IE-0003A-CC26 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41100B TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5083 | PS5-60-IE-0003B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5084 | PS5-60-IE-0003B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5085 | PS5-60-IE-0003B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5086 | PS5-60-IE-0003B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5087 | PS5-60-IE-0003B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5088 | PS5-60-IE-0003B-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5089 | PS5-60-IE-0003B-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5090 | PS5-60-IE-0003B-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5091 | PS5-60-IE-0003B-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5092 | PS5-60-IE-0003B-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5093 | PS5-60-IE-0003B-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5094 | PS5-60-IE-0003B-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5095 | PS5-60-IE-0003B-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5096 | PS5-60-IE-0003B-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5101 | PS5-60-IE-0003B-CC25 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41200A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5102 | PS5-60-IE-0003B-CC26 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41200B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5103 | PS5-60-IE-0003C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5104 | PS5-60-IE-0003C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5105 | PS5-60-IE-0003C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5106 | PS5-60-IE-0003C-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5107 | PS5-60-IE-0003C-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5108 | PS5-60-IE-0003C-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5109 | PS5-60-IE-0003C-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5110 | PS5-60-IE-0003C-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5111 | PS5-60-IE-0003C-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5112 | PS5-60-IE-0003C-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5113 | PS5-60-IE-0003C-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5114 | PS5-60-IE-0003C-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5115 | PS5-60-IE-0003C-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5116 | PS5-60-IE-0003C-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5121 | PS5-60-IE-0003C-CC25 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41300A TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5122 | PS5-60-IE-0003C-CC26 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41300B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5123 | PS5-60-IE-0003D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5124 | PS5-60-IE-0003D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5125 | PS5-60-IE-0003D-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5126 | PS5-60-IE-0003D-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5127 | PS5-60-IE-0003D-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5128 | PS5-60-IE-0003D-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5129 | PS5-60-IE-0003D-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5130 | PS5-60-IE-0003D-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5131 | PS5-60-IE-0003D-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5132 | PS5-60-IE-0003D-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5133 | PS5-60-IE-0003D-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5134 | PS5-60-IE-0003D-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5135 | PS5-60-IE-0003D-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5136 | PS5-60-IE-0003D-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5141 | PS5-60-IE-0003D-CC25 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41400A TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5142 | PS5-60-IE-0003D-CC26 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41400B TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5203 | PS5-60-IE-0004-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5204 | PS5-60-IE-0004-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5205 | PS5-60-IE-0004-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5206 | PS5-60-IE-0004-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5207 | PS5-60-IE-0004-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5208 | PS5-60-IE-0004-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5209 | PS5-60-IE-0004-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5213 | PS5-60-IN-0001A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5214 | PS5-60-IN-0001A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5215 | PS5-60-IN-0001A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5216 | PS5-60-IN-0001A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5217 | PS5-60-IN-0001B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5218 | PS5-60-IN-0001B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5219 | PS5-60-IN-0001B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5220 | PS5-60-IN-0001B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5221 | PS5-60-IN-0001C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5222 | PS5-60-IN-0001C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5223 | PS5-60-IN-0001C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5224 | PS5-60-IN-0001C-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5225 | PS5-60-IN-0001D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5226 | PS5-60-IN-0001D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5227 | PS5-60-IN-0001D-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5228 | PS5-60-IN-0001D-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5241 | PS5-60-IN-0002A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5242 | PS5-60-IN-0002A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5243 | PS5-60-IN-0002A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5244 | PS5-60-IN-0002A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5245 | PS5-60-IN-0002A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5246 | PS5-60-IN-0002A-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5247 | PS5-60-IN-0002B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5248 | PS5-60-IN-0002B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5249 | PS5-60-IN-0002B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5250 | PS5-60-IN-0002B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5251 | PS5-60-IN-0002B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5252 | PS5-60-IN-0002B-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5253 | PS5-60-IN-0002C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5254 | PS5-60-IN-0002C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5255 | PS5-60-IN-0002C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5256 | PS5-60-IN-0002C-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5257 | PS5-60-IN-0002C-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5258 | PS5-60-IN-0002C-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5259 | PS5-60-IN-0002D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5260 | PS5-60-IN-0002D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5261 | PS5-60-IN-0002D-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5262 | PS5-60-IN-0002D-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5263 | PS5-60-IN-0002D-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5264 | PS5-60-IN-0002D-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5283 | PS5-60-IN-0004A-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5284 | PS5-60-LA-0002A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5285 | PS5-60-LA-0002A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5286 | PS5-60-LA-0002A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5287 | PS5-60-LA-0002A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5288 | PS5-60-LA-0002A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5289 | PS5-60-LA-0002A-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5290 | PS5-60-LA-0002A-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5291 | PS5-60-LA-0002A-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5292 | PS5-60-LA-0002A-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5293 | PS5-60-LA-0002B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5294 | PS5-60-LA-0002B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5295 | PS5-60-LA-0002B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5296 | PS5-60-LA-0002B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5297 | PS5-60-LA-0002B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5298 | PS5-60-LA-0002B-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5305 | PS5-60-LA-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5316 | PS5-60-SEA-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-5317 | PS5-60-SEA-0001-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-5318 | PS5-60-SEA-0001-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-5319 | PS5-60-SEA-0001-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-5320 | PS5-60-SEA-0001-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-5321 | PS5-60-SEA-0001-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-5322 | PS5-60-SEA-0001-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-5323 | PS5-60-SEA-0001-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-5324 | PS5-60-SEA-0001-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-5325 | PS5-60-SEA-0001-CC12 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-5326 | PS5-60-SEA-0001-CC13 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-5327 | PS5-60-SEA-0001-CC14 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-5328 | PS5-60-SEA-0001-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-5329 | PS5-60-SEA-0001-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-5330 | PS5-60-SEA-0001-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00069-5339 | PS5-60-VS-9101A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-VS-9101A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5340 | PS5-60-VS-9101B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-VS-9101B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5341 | PS5-60-VS-9101C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-VS-9101C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C |  | PS5-60-44 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5342 | PS5-60-VS-9101D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-VS-9101D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D |  | PS5-60-45 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5346 | PS5-61-BI-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5347 | PS5-61-BI-0001-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5348 | PS5-61-BI-0001-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-61-TE-0003A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5349 | PS5-61-BI-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5350 | PS5-61-BI-0002-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5351 | PS5-61-BI-0002-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-61-TE-0003B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5352 | PS5-61-BI-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-61-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5353 | PS5-61-BI-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-61-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5354 | PS5-61-BI-0003-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-61-TE-0003C TO PS5-61-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5355 | PS5-61-BI-0004-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-61-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5356 | PS5-61-BI-0004-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-61-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5357 | PS5-61-BI-0004-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-61-TE-0003D TO PS5-61-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00069
T-00069-5376 | PS5-71-BAV-0058-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2113 TO PS5-71-BAV-0058 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5377 | PS5-71-BAV-0059-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2113 TO PS5-71-BAV-0059 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone F | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5378 | PS5-71-BI-0001A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5379 | PS5-71-BI-0001B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5381 | PS5-71-BI-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone F | TM-00069
T-00069-5382 | PS5-71-BI-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5383 | PS5-71-BI-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5384 | PS5-71-BI-0003-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5385 | PS5-71-BI-0003-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5386 | PS5-71-BI-0004-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5387 | PS5-71-BI-0005-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5388 | PS5-71-BI-0005-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5389 | PS5-71-BI-0006-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5390 | PS5-71-BI-0008A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5391 | PS5-71-BI-0008A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5392 | PS5-71-BI-0008B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5393 | PS5-71-BI-0008B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5394 | PS5-71-BI-0009-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0009 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone F | TM-00069
T-00069-5395 | PS5-71-BI-0009-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0009 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone F | TM-00069
T-00069-5396 | PS5-71-BI-0009-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0009 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone F | TM-00069
T-00069-5397 | PS5-71-BI-0009-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0009 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone F | TM-00069
T-00069-5398 | PS5-71-BI-0010-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0010 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone F | TM-00069
T-00069-5399 | PS5-71-BI-0011A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5400 | PS5-71-BI-0011A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5401 | PS5-71-BI-0011A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5402 | PS5-71-BI-0011A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5403 | PS5-71-BI-0011A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5404 | PS5-71-BI-0011B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5405 | PS5-71-BI-0011B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5406 | PS5-71-BI-0011B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5407 | PS5-71-BI-0011B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5408 | PS5-71-BI-0011B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5442 | PS5-71-FCV-0019-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-FCV-0019-HPU TO PS5-71-FCV-0019 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5449 | PS5-71-FIT-0019-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-1110 TO PS5-71-FIT-0019 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5452 | PS5-71-FXS-0019-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2114 TO PS5-71-FCV-0019 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5455 | PS5-71-FY-0019-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-1113 TO PS5-71-FCV-0019 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5474 | PS5-71-IN-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5475 | PS5-71-IN-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5476 | PS5-71-IN-0003-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5477 | PS5-71-IN-0003-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069
T-00069-5481 | PS5-71-IN-0004A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5482 | PS5-71-IN-0004A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5483 | PS5-71-IN-0004A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5484 | PS5-71-IN-0004A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-0011A TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5485 | PS5-71-IN-0004A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-0011A TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5486 | PS5-71-IN-0004A-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5487 | PS5-71-IN-0004A-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5490 | PS5-71-IN-0004A-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5492 | PS5-71-IN-0004A-CC13 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004B TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5493 | PS5-71-IN-0004B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5494 | PS5-71-IN-0004B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5495 | PS5-71-IN-0004B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5496 | PS5-71-IN-0004B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-0011B TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5497 | PS5-71-IN-0004B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-0011B TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5498 | PS5-71-IN-0004B-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5499 | PS5-71-IN-0004B-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5502 | PS5-71-IN-0004B-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0001 TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069
T-00069-5506 | PS5-71-LIT-1201-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-1113 TO PS5-71-LIT-1201 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5507 | PS5-71-LIT-1202-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-28-BI-1307 TO PS5-71-LIT-1202 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5516 | PS5-71-MOV-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2120 TO PS5-71-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5517 | PS5-71-MOV-0001-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2124 TO PS5-71-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5518 | PS5-71-MOV-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2120 TO PS5-71-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5519 | PS5-71-MOV-0002-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2124 TO PS5-71-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5520 | PS5-71-MOV-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2121 TO PS5-71-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5521 | PS5-71-MOV-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2125 TO PS5-71-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5522 | PS5-71-MOV-0004-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2121 TO PS5-71-MOV-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5523 | PS5-71-MOV-0004-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2125 TO PS5-71-MOV-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5524 | PS5-71-MOV-0007-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2118 TO PS5-71-MOV-0007 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5525 | PS5-71-MOV-0007-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2122 TO PS5-71-MOV-0007 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5526 | PS5-71-MOV-0008-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2118 TO PS5-71-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5527 | PS5-71-MOV-0008-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2122 TO PS5-71-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5528 | PS5-71-MOV-0009-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2119 TO PS5-71-MOV-0009 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5529 | PS5-71-MOV-0009-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2123 TO PS5-71-MOV-0009 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5530 | PS5-71-MOV-0010-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2119 TO PS5-71-MOV-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5531 | PS5-71-MOV-0010-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2123 TO PS5-71-MOV-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5535 | PS5-71-PIT-0001-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-28-BI-1307 TO PS5-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5538 | PS5-71-PIT-0019A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-1113 TO PS5-71-FCV-0019 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5545 | PS5-71-PIT-0091-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-1113 TO PS5-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone F | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5546 | PS5-71-PIT-0092-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-1113 TO PS5-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5558 | PS5-71-SDV-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-25-BI-2315 TO PS5-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5559 | PS5-71-SDV-0001-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-SDV-0001-HPU TO PS5-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | UT-MID-60-NBV3-160008 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | UT-MID-60-NBV3-160008
T-00069-5566 | PS5-71-SXS-0001-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-25-BI-2312 TO PS5-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5570 | PS5-71-SY-0001-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-25-BI-2316 TO PS5-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5592 | PS5-71-XV-0091-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2113 TO PS5-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone F | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5593 | PS5-71-XV-0091-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-XV-0091-HPU TO PS5-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  | UT-MID-60-NBV3-160008 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone F | TM-00069 |  | UT-MID-60-NBV3-160008
T-00069-5594 | PS5-71-XV-0092-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2113 TO PS5-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5595 | PS5-71-XV-0092-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-XV-0092-HPU TO PS5-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  | UT-MID-60-NBV3-160008 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | UT-MID-60-NBV3-160008
T-00069-5598 | PS5-71-XXS-0091-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2114 TO PS5-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone F | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5599 | PS5-71-XXS-0092-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2114 TO PS5-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5602 | PS5-71-XY-0091-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2115 TO PS5-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone F | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-5603 | PS5-71-XY-0092-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2115 TO PS5-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00069 |  | TZ-MID-68-WPR2-161503
T-00069-9408 | PS5-03-RMAC-1409-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SEA-0003 TO PS5-03-RMAC-1409 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00069
T-00071-0027 | PS5-60-IE-0004-CX03 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-SSF1-161401 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B | TM-00071 |  | TZ-MID-68-SSF1-161401
T-00071-0028 | PS5-60-IE-0004-CX04 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-SSF1-161401 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B | TM-00071 |  | TZ-MID-68-SSF1-161401
T-00071-0029 | PS5-60-LA-0003-CX01 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-SSF1-161401 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B | TM-00071 |  | TZ-MID-68-SSF1-161401
T-00071-0090 | PS5-60-LA-0003-CX02 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B | TM-00071
T-00072-0169 | PS5-60-TW-0007C |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | Thermowell | I | To be completed | PS5 - Milestone D | TM-00072 |  | TZ-MID-68-WPR2-135106
T-00072-0173 | PS5-60-TW-0007B |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | Thermowell | I | To be completed | PS5 - Milestone B | TM-00072 |  | TZ-MID-68-WPR2-135103
T-00072-0174 | PS5-60-TW-0006C |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | Thermowell | I | To be completed | PS5 - Milestone D | TM-00072 |  | TZ-MID-68-WPR2-135106
T-00072-0175 | PS5-60-TW-0008A |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | Thermowell | I | To be completed | PS5 - Milestone B | TM-00072 |  | TZ-MID-68-WPR2-135100
T-00072-0176 | PS5-60-TW-0007D |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | Thermowell | I | To be completed | PS5 - Milestone D | TM-00072 |  | TZ-MID-68-WPR2-135109
T-00072-0177 | PS5-60-TW-0008C |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | Thermowell | I | To be completed | PS5 - Milestone D | TM-00072 |  | TZ-MID-68-WPR2-135106
T-00072-0182 | PS5-60-TW-0007A |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | Thermowell | I | To be completed | PS5 - Milestone B | TM-00072 |  | TZ-MID-68-WPR2-135100
T-00072-0183 | PS5-60-TW-0006D |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | Thermowell | I | To be completed | PS5 - Milestone D | TM-00072 |  | TZ-MID-68-WPR2-135109
T-00072-0184 | PS5-60-TW-0008B |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | Thermowell | I | To be completed | PS5 - Milestone B | TM-00072 |  | TZ-MID-68-WPR2-135103
T-00072-0186 | PS5-60-TW-0008D |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | Thermowell | I | To be completed | PS5 - Milestone D | TM-00072 |  | TZ-MID-68-WPR2-135109
T-00072-0194 | PS5-60-TW-0006B |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | Thermowell | I | To be completed | PS5 - Milestone B | TM-00072 |  | TZ-MID-68-WPR2-135103
T-00072-0198 | PS5-60-TW-0006A |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | Thermowell | I | To be completed | PS5 - Milestone B | TM-00072 |  | TZ-MID-68-WPR2-135100
T-00072-0207 | PS5-60-TW-0005A |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | Thermowell | I | To be completed | PS5 - Milestone B | TM-00072 |  | TZ-MID-68-WPR2-135100
T-00072-0208 | PS5-60-TW-0005B |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | Thermowell | I | To be completed | PS5 - Milestone B | TM-00072 |  | TZ-MID-68-WPR2-135103
T-00072-0209 | PS5-60-TW-0005C |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | Thermowell | I | To be completed | PS5 - Milestone D | TM-00072 |  | TZ-MID-68-WPR2-135106
T-00072-0210 | PS5-60-TW-0005D |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | Thermowell | I | To be completed | PS5 - Milestone D | TM-00072 |  | TZ-MID-68-WPR2-135109
T-00075-0200 | PS5-60-TG-0005C |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D | TM-00075 |  | TZ-MID-68-WPR2-135106
T-00075-0205 | PS5-60-TG-0008D |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D | TM-00075 |  | TZ-MID-68-WPR2-135109
T-00075-0209 | PS5-71-PG-0050B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135008 | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B | TM-00075 |  | TZ-MID-68-WPR2-135008
T-00075-0210 | PS5-71-PG-0050A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135008 | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B | TM-00075 |  | TZ-MID-68-WPR2-135008
T-00075-0211 | PS5-60-TG-0005A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B | TM-00075 |  | TZ-MID-68-WPR2-135100
T-00075-0218 | PS5-60-TG-0008A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B | TM-00075 |  | TZ-MID-68-WPR2-135100
T-00075-0224 | PS5-60-TG-0008C |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D | TM-00075 |  | TZ-MID-68-WPR2-135106
T-00075-0229 | PS5-60-TG-0007D |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D | TM-00075 |  | TZ-MID-68-WPR2-135109
T-00075-0239 | PS5-60-TG-0007A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B | TM-00075 |  | TZ-MID-68-WPR2-135100
T-00075-0241 | PS5-71-PDG-0049A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Diff Press Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135008 | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B | TM-00075 |  | TZ-MID-68-WPR2-135008
T-00075-0244 | PS5-60-TG-0007C |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D | TM-00075 |  | TZ-MID-68-WPR2-135106
T-00075-0251 | PS5-60-TG-0006D |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D | TM-00075 |  | TZ-MID-68-WPR2-135109
T-00075-0255 | PS5-71-PDG-0049B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Diff Press Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135008 | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B | TM-00075 |  | TZ-MID-68-WPR2-135008
T-00075-0264 | PS5-60-TG-0005D |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D | TM-00075 |  | TZ-MID-68-WPR2-135109
T-00075-0265 | PS5-60-TG-0006A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B | TM-00075 |  | TZ-MID-68-WPR2-135100
T-00075-0266 | PS5-60-TG-0006C |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D | TM-00075 |  | TZ-MID-68-WPR2-135106
T-00075-0270 | PS5-60-TG-0006B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B | TM-00075 |  | TZ-MID-68-WPR2-135103
T-00075-0271 | PS5-60-TG-0005B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B | TM-00075 |  | TZ-MID-68-WPR2-135103
T-00075-0272 | PS5-60-TG-0007B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B | TM-00075 |  | TZ-MID-68-WPR2-135103
T-00075-0273 | PS5-60-TG-0008B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B | TM-00075 |  | TZ-MID-68-WPR2-135103
T-00077-0238 | PS5-71-XV-0091 |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | On / Off Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135205 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS5 - Milestone F | TM-00077 |  | TZ-MID-68-WPR2-135205
T-00077-0254 | PS5-71-XV-0092 |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | On / Off Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135205 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS5 - Milestone B | TM-00077 |  | TZ-MID-68-WPR2-135205
T-00077-0256 | PS5-71-SDV-0001 |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Shutdown Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135205 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS5 - Milestone B | TM-00077 |  | TZ-MID-68-WPR2-135205
T-00078-0140 | PS5-71-MOV-0007 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone H | TM-00078 |  | TZ-MID-68-WPR2-135138
T-00078-0143 | PS5-71-MOV-0010 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone B | TM-00078 |  | TZ-MID-68-WPR2-135138
T-00078-0144 | PS5-71-MOV-0003 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone H | TM-00078 |  | TZ-MID-68-WPR2-135123
T-00078-0147 | PS5-71-MOV-0004 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone B | TM-00078 |  | TZ-MID-68-WPR2-135123
T-00078-0149 | PS5-71-MOV-0001 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone H | TM-00078 |  | TZ-MID-68-WPR2-135123
T-00078-0151 | PS5-71-MOV-0002 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone B | TM-00078 |  | TZ-MID-68-WPR2-135123
T-00078-0152 | PS5-71-MOV-0008 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone B | TM-00078 |  | TZ-MID-68-WPR2-135138
T-00078-0153 | PS5-71-MOV-0009 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone H | TM-00078 |  | TZ-MID-68-WPR2-135138
T-00079-0069 | PS5-71-FCV-0019 |  |  |  |  | CJX27 - Control valve - Pneumatic / Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135008 | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | Control Valve-Pneumatic/Hydraulic Type | I | To be completed | PS5 - Milestone B | TM-00079 |  | TZ-MID-68-WPR2-135008
T-00082-0460 | PS5-01-BI-1117 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 07:55 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0461 | PS5-01-BI-1118 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 07:56 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0463 | PS5-01-BI-1515 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 07:57 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0466 | PS5-01-BI-2110 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 07:58 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0484 | PS5-03-BI-2503 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-19 04:59 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0487 | PS5-03-BI-2506 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  | 1 | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-19 05:03 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0490 | PS5-03-BI-2509 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:00 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0494 | PS5-03-BI-2514 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-19 05:04 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0495 | PS5-03-BI-2515 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:01 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0500 | PS5-25-BI-1101 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:01 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0501 | PS5-25-BI-1102 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:02 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0502 | PS5-25-BI-1103 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:38 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0503 | PS5-25-BI-1104 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:16 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0504 | PS5-25-BI-1115 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:41 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0508 | PS5-25-BI-1201 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:41 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0512 | PS5-25-BI-1301 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:42 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0513 | PS5-25-BI-1302 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:16 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0514 | PS5-25-BI-1310 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:17 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0517 | PS5-25-BI-2103 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:03 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0518 | PS5-25-BI-2104 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-07-10 13:05 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0519 | PS5-25-BI-2105 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:42 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0520 | PS5-25-BI-2106 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:18 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0521 | PS5-25-BI-2108 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:19 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0522 | PS5-25-BI-2109 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:19 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0523 | PS5-25-BI-2201 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-05-30 12:03 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0524 | PS5-25-BI-2203 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-05-30 12:02 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0526 | PS5-25-BI-2301 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:43 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0527 | PS5-25-BI-2302 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:44 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0528 | PS5-25-BI-2305 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:20 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0529 | PS5-25-BI-2308 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:21 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0530 | PS5-25-BI-2309 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:44 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0531 | PS5-25-BI-2312 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:21 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Anwar, Zeeshan
T-00082-0532 | PS5-25-BI-2315 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:20 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Anwar, Zeeshan
T-00082-0533 | PS5-25-BI-2316 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:19 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Anwar, Zeeshan
T-00082-0534 | PS5-28-BI-1105 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-19 04:59 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0537 | PS5-28-BI-1303 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:05 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0538 | PS5-28-BI-1307 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:05 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0540 | PS5-50-BI-1107 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:07 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0541 | PS5-53-BI-1108 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-07-10 13:07 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0543 | PS5-71-BI-1109 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-05-30 12:05 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0544 | PS5-71-BI-1110 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:45 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0545 | PS5-71-BI-1111 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:18 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Anwar, Zeeshan
T-00082-0547 | PS5-71-BI-1113 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:17 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Anwar, Zeeshan
T-00082-0548 | PS5-71-BI-1116 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:16 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Anwar, Zeeshan
T-00082-0549 | PS5-71-BI-1117 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:46 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0550 | PS5-71-BI-1305 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-05-30 12:04 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0551 | PS5-71-BI-1306 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:15 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Anwar, Zeeshan
T-00082-0553 | PS5-71-BI-2101 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:46 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0554 | PS5-71-BI-2107 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:48 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0555 | PS5-71-BI-2113 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:13 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Anwar, Zeeshan
T-00082-0556 | PS5-71-BI-2114 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:12 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Anwar, Zeeshan
T-00082-0557 | PS5-71-BI-2115 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:12 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Anwar, Zeeshan
T-00082-0558 | PS5-71-BI-2116 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:07 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0559 | PS5-71-BI-2118 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:10 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Anwar, Zeeshan
T-00082-0560 | PS5-71-BI-2119 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:08 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0561 | PS5-71-BI-2120 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:08 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0562 | PS5-71-BI-2121 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-19 05:05 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0563 | PS5-71-BI-2122 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:09 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Anwar, Zeeshan
T-00082-0564 | PS5-71-BI-2123 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:09 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0565 | PS5-71-BI-2124 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:09 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0566 | PS5-71-BI-2125 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-19 05:05 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0567 | PS5-71-BI-2306 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:23 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Anwar, Zeeshan
T-00082-0569 | PS5-71-BI-2310 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:10 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00082-0571 | PS5-71-BI-2314 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:49 | PS5-91-01 | Priority-1 |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | TM-00082 | Gawad, Mohamed
T-00083-0865 | PS5-03-RDOS-1401 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E | TM-00083 |  | TZ-MID-68-WPR2-121106
T-00083-0865 | PS5-03-RDOS-1401 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E | TM-00083 |  | UT-MID-60-WPR2-160211
T-00083-0866 | PS5-03-RDOS-1402 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E | TM-00083 |  | TZ-MID-68-WPR2-121106
T-00083-0866 | PS5-03-RDOS-1402 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E | TM-00083 |  | UT-MID-60-WPR2-160211
T-00083-0867 | PS5-03-RDOS-1403 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E | TM-00083 |  | TZ-MID-68-WPR2-121106
T-00083-0867 | PS5-03-RDOS-1403 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E | TM-00083 |  | UT-MID-60-WPR2-160211
T-00083-0868 | PS5-03-RDOS-1404 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E | TM-00083 |  | TZ-MID-68-WPR2-121106
T-00083-0868 | PS5-03-RDOS-1404 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E | TM-00083 |  | UT-MID-60-WPR2-160211
T-00083-0869 | PS5-03-RDOS-1405 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E | TM-00083 |  | TZ-MID-68-WPR2-121106
T-00083-0869 | PS5-03-RDOS-1405 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E | TM-00083 |  | UT-MID-60-WPR2-160211
T-00083-0870 | PS5-03-RDOS-1406 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E | TM-00083 |  | TZ-MID-68-WPR2-121106
T-00083-0870 | PS5-03-RDOS-1406 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E | TM-00083 |  | UT-MID-60-WPR2-160211
T-00083-0871 | PS5-03-RDOS-1407 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E | TM-00083 |  | TZ-MID-68-WPR2-121106
T-00083-0871 | PS5-03-RDOS-1407 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E | TM-00083 |  | UT-MID-60-WPR2-160211
T-00083-0872 | PS5-03-RDOS-1408 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E | TM-00083 |  | TZ-MID-68-WPR2-121106
T-00083-0872 | PS5-03-RDOS-1408 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E | TM-00083 |  | UT-MID-60-WPR2-160211
T-00087-0103 | PS5-03-SEA-0003 |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FIRE ALARM CONTROL PANEL | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121133 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Indoor Cabinet/Panel | I | To be completed | PS5 - Milestone E | TM-00087 |  | TZ-MID-68-WPR2-121133
T-00087-0103 | PS5-03-SEA-0003 |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FIRE ALARM CONTROL PANEL | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121133 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Indoor Cabinet/Panel | I | To be completed | PS5 - Milestone E | TM-00087 |  | UT-MID-60-WPR2-160211
T-00087-0105 | PS5-60-SEA-0001 |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTION PANEL | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Indoor Cabinet/Panel | I | To be completed | PS5 - Milestone E | TM-00087
T-00087-0500 | PS5-60-LA-0002A |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | VTMS VIBRATION AND TEMPERATURE MONITORING SYSTEM | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Indoor Cabinet/Panel | I | To be completed | PS5 - Milestone B | TM-00087
T-00087-0501 | PS5-60-LA-0002B |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | VTMS VIBRATION AND TEMPERATURE MONITORING SYSTEM | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-07-11 07:03 | PS5-60-10 | Priority-2 |  | Indoor Cabinet/Panel | I | Closed | PS5 - Milestone D | TM-00087 | Gawad, Mohamed
T-00087-0528 | PS5-60-LA-0003 |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Remote Access Panel | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Indoor Cabinet/Panel | I | To be completed | PS5 - Milestone B | TM-00087
T-00090-0179 | PS5-60-UR-8100A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION PACKAGE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135100
T-00090-0180 | PS5-60-UR-8100B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION PACKAGE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135103
T-00090-0181 | PS5-60-UR-8100C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION PACKAGE C | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135106
T-00090-0182 | PS5-60-UR-8100D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION PACKAGE D | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135109
T-00090-0188 | PS5-60-UA-5100 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COMPRESSOR AIR STARTING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135128 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135128
T-00090-0189 | PS5-60-UO-81100A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135124
T-00090-0190 | PS5-60-UO-81100B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135124
T-00090-0191 | PS5-60-UO-81100C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135124
T-00090-0192 | PS5-60-UO-81100D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135124
T-00090-0196 | PS5-60-UZ-8200A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135129
T-00090-0197 | PS5-60-UZ-8200B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135129
T-00090-0198 | PS5-60-UZ-8200C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135129
T-00090-0199 | PS5-60-UZ-8200D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135129
T-00090-0202 | PS5-60-VS-9100A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135130
T-00090-0203 | PS5-60-VS-9100B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135130
T-00090-0204 | PS5-60-VS-9100C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C |  | PS5-60-44 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135130
T-00090-0205 | PS5-60-VS-9100D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D |  | PS5-60-45 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135130
T-00090-0209 | PS5-71-UZ-6500 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DIESEL FUEL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135009 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone F | TM-00090 |  | TZ-MID-68-WPR2-135009
T-00090-0210 | PS5-71-UZ-6800A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CRUDE FUEL SEPARATOR MODULE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135002 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone H | TM-00090 |  | TZ-MID-68-WPR2-135002
T-00090-0211 | PS5-71-UZ-6800B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CRUDE FUEL SEPARATOR MODULE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135002 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone H | TM-00090 |  | TZ-MID-68-WPR2-135002
T-00090-0215 | PS5-60-EA-2100A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135122
T-00090-0216 | PS5-60-EA-2100B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135122
T-00090-0217 | PS5-60-EA-21100A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135100
T-00090-0218 | PS5-60-EA-21100B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135103
T-00090-0219 | PS5-60-EA-21100C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135106
T-00090-0220 | PS5-60-EA-21100D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135109
T-00090-0224 | PS5-60-EA-21200A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135100
T-00090-0225 | PS5-60-EA-21200B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135103
T-00090-0226 | PS5-60-EA-21200C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135106
T-00090-0227 | PS5-60-EA-21200D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135109
T-00090-0231 | PS5-60-EA-2200A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135122
T-00090-0232 | PS5-60-EA-2200B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135122
T-00090-0233 | PS5-60-EA-2300A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135122
T-00090-0234 | PS5-60-EA-2300B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135122
T-00090-0235 | PS5-60-EA-2400A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135122
T-00090-0236 | PS5-60-EA-2400B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135122
T-00090-0243 | PS5-60-EA-2800A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135129
T-00090-0244 | PS5-60-EA-2800B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135129
T-00090-0245 | PS5-60-EA-2800C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135129
T-00090-0246 | PS5-60-EA-2800D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135129
T-00090-0250 | PS5-60-EA-2900A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135123
T-00090-0251 | PS5-60-EA-2900B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135123
T-00090-0252 | PS5-60-EA-2900C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135123
T-00090-0253 | PS5-60-EA-2900D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135123
T-00090-0257 | PS5-60-TCV-0001A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135136
T-00090-0258 | PS5-60-TCV-0001B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135136
T-00090-0259 | PS5-60-TCV-0001C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135136
T-00090-0260 | PS5-60-TCV-0001D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135136
T-00090-0264 | PS5-60-TCV-0002A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135137
T-00090-0265 | PS5-60-TCV-0002B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135137
T-00090-0266 | PS5-60-TCV-0002C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135137
T-00090-0267 | PS5-60-TCV-0002D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135137
T-00090-0271 | PS5-60-UA-5200 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INSTRUMENT AIR COMPRESSOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135127 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135127
T-00090-0272 | PS5-60-UR-8200A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135100
T-00090-0273 | PS5-60-UR-8200B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135103
T-00090-0274 | PS5-60-UR-8200C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135106
T-00090-0275 | PS5-60-UR-8200D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135109
T-00090-0280 | PS5-60-UZ-8900A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135123
T-00090-0281 | PS5-60-UZ-8900B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135123
T-00090-0282 | PS5-60-UZ-8900C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135123
T-00090-0283 | PS5-60-UZ-8900D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090 |  | TZ-MID-68-WPR2-135123
T-00090-0288 | PS5-71-UZ-6400 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CRUDE FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135004 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone H | TM-00090 |  | TZ-MID-68-WPR2-135004
T-00090-0289 | PS5-71-UZ-6700 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DIESEL FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135126 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090 |  | TZ-MID-68-WPR2-135126
T-00090-0436 | PS5-60-UR-8300A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090
T-00090-0437 | PS5-60-UR-8300B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 | Priority-1 |  | Package | M | To be completed | PS5 - Milestone B | TM-00090
T-00090-0438 | PS5-60-UR-8300C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090
T-00090-0439 | PS5-60-UR-8300D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 | Priority-2 |  | Package | M | To be completed | PS5 - Milestone D | TM-00090
T-00254-12960 | PS5-60-BI-0001A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-12961 | PS5-60-BI-0001B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-12962 | PS5-60-BI-0001C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-BI-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-12963 | PS5-60-BI-0001D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-BI-0001D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-12967 | PS5-60-BI-0003-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-12968 | PS5-60-IE-0002A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-12969 | PS5-60-IE-0002A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-12970 | PS5-60-IE-0002A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-12971 | PS5-60-IE-0002B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-12972 | PS5-60-IE-0002B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-12973 | PS5-60-IE-0002B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-12974 | PS5-60-IE-0002C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-12975 | PS5-60-IE-0002C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-12976 | PS5-60-IE-0002C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-12977 | PS5-60-IE-0002D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-12978 | PS5-60-IE-0002D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-12979 | PS5-60-IE-0002D-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-12989 | PS5-60-IH-0001A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-12990 | PS5-60-IH-0001A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-12991 | PS5-60-IH-0001B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-12992 | PS5-60-IH-0001B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-12993 | PS5-60-IH-0001C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-12994 | PS5-60-IH-0001C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-12995 | PS5-60-IH-0001D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-12996 | PS5-60-IH-0001D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-13003 | PS5-60-IH-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-13004 | PS5-60-IH-0002-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-13005 | PS5-60-LA-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-13006 | PS5-60-LA-0003-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-13007 | PS5-60-PIT-8113A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BE-0027A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-13008 | PS5-60-PIT-8113B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BE-0027B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-13009 | PS5-60-PIT-8113C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-BE-0027C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-13010 | PS5-60-PIT-8113D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-BE-0027D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-13014 | PS5-60-PIT-8114A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BE-0027A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-13015 | PS5-60-PIT-8114B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BE-0027B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-13016 | PS5-60-PIT-8114C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-BE-0027C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-13017 | PS5-60-PIT-8114D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-BE-0027D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-13021 | PS5-71-IN-0004A-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-4499 | PS5-03-RDOS-1401-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-RMAC-1411 TO PS5-03-RDOS-1401 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00254
T-00254-4500 | PS5-03-RDOS-1402-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-RDOS-1401 TO PS5-03-RDOS-1402 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00254
T-00254-4501 | PS5-03-RDOS-1403-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-RDOS-1402 TO PS5-03-RDOS-1403 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00254
T-00254-4502 | PS5-03-RDOS-1404-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-RDOS-1403 TO PS5-03-RDOS-1404 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00254
T-00254-4503 | PS5-03-RDOS-1405-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-RDOS-1404 TO PS5-03-RDOS-1405 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00254
T-00254-4504 | PS5-03-RDOS-1406-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-RDOS-1503 TO PS5-03-RDOS-1406 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00254
T-00254-4505 | PS5-03-RDOS-1407-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-RDOS-1405 TO PS5-03-RDOS-1407 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00254
T-00254-4506 | PS5-03-RDOS-1408-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-RDOS-1407 TO PS5-03-RDOS-1408 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00254
T-00254-4552 | PS5-03-RMAC-1410-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-RDOS-2103 TO PS5-03-RMAC-1410 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00254
T-00254-4553 | PS5-03-RMAC-1411-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-RDOS-1406 TO PS5-03-RMAC-1411 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00254
T-00254-4900 | PS5-60-BE-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-07-10 16:39 | PS5-60-27 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-4901 | PS5-60-BE-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-07-10 17:13 | PS5-60-26 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-4902 | PS5-60-BE-0004A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0001A TO PS5-60-BE-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2026-07-10 16:30 | PS5-60-49 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-4903 | PS5-60-BE-0004B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0001B TO PS5-60-BE-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2026-07-10 16:30 | PS5-60-50 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-4904 | PS5-60-BE-0004C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0001C TO PS5-60-BE-0004C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | 2026-07-10 16:31 | PS5-60-51 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-4905 | PS5-60-BE-0004D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0001D TO PS5-60-BE-0004D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | 2026-07-10 16:31 | PS5-60-52 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-4909 | PS5-60-BI-0001A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-07-10 15:58 | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-4910 | PS5-60-BI-0001A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-07-10 15:43 | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-4911 | PS5-60-BI-0001B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-10 16:02 | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-4912 | PS5-60-BI-0001B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-10 15:46 | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-4913 | PS5-60-BI-0001C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-10 16:03 | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-4914 | PS5-60-BI-0001C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-10 15:47 | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-4915 | PS5-60-BI-0001D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-07-10 16:05 | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-4916 | PS5-60-BI-0001D-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-07-10 15:48 | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-4923 | PS5-60-BI-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4924 | PS5-60-BI-0002-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-07-08 06:06 | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-4925 | PS5-60-BI-0002-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4926 | PS5-60-BI-0002-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4927 | PS5-60-BI-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4928 | PS5-60-BI-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4929 | PS5-60-BI-0004A-CCO1 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4930 | PS5-60-BI-0004B-CCO1 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4931 | PS5-60-BI-0004C-CCO1 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-BI-0004C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-4932 | PS5-60-BI-0004D-CCO1 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-BI-0004D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-4936 | PS5-60-BI-0005A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0005A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4937 | PS5-60-BI-0005A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0005A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4938 | PS5-60-BI-0005B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0005B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4939 | PS5-60-BI-0005B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0005B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4940 | PS5-60-BI-0005C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0005C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-4941 | PS5-60-BI-0005C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0005C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-4942 | PS5-60-BI-0005D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0005D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-4943 | PS5-60-BI-0005D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0005D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-4950 | PS5-60-BI-0006A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4951 | PS5-60-BI-0006A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4952 | PS5-60-BI-0006A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4953 | PS5-60-BI-0006A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4954 | PS5-60-BI-0006A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4955 | PS5-60-BI-0006A-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4956 | PS5-60-BI-0006B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4957 | PS5-60-BI-0006B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4958 | PS5-60-BI-0006B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4959 | PS5-60-BI-0006B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4960 | PS5-60-BI-0006B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4961 | PS5-60-BI-0006B-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4962 | PS5-60-BI-0006C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-4963 | PS5-60-BI-0006C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-4964 | PS5-60-BI-0006C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-4965 | PS5-60-BI-0006C-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-4966 | PS5-60-BI-0006C-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-4967 | PS5-60-BI-0006C-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-4968 | PS5-60-BI-0006D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-4969 | PS5-60-BI-0006D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-4970 | PS5-60-BI-0006D-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-4971 | PS5-60-BI-0006D-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-4972 | PS5-60-BI-0006D-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-4973 | PS5-60-BI-0006D-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-4992 | PS5-60-BI-0008A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4993 | PS5-60-BI-0008A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4994 | PS5-60-BI-0008B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4995 | PS5-60-BI-0008B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4996 | PS5-60-BI-0009A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0009A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4997 | PS5-60-BI-0009A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0009A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4998 | PS5-60-BI-0009B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0009B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-4999 | PS5-60-BI-0009B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0009B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5000 | PS5-60-BI-0010A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0010A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5001 | PS5-60-BI-0010A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0010A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5002 | PS5-60-BI-0010B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0010B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5003 | PS5-60-BI-0010B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0010B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5004 | PS5-60-BI-0011A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5005 | PS5-60-BI-0011A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5006 | PS5-60-BI-0011B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5007 | PS5-60-BI-0011B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5020 | PS5-60-BI-0016A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5021 | PS5-60-BI-0016A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5022 | PS5-60-BI-0016A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-07-01 13:12 | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-5023 | PS5-60-BI-0016A-CCO4 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5024 | PS5-60-BI-0016B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5025 | PS5-60-BI-0016B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5026 | PS5-60-BI-0016B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-01 13:13 | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-5027 | PS5-60-BI-0016B-CCO4 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5028 | PS5-60-BI-0016C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5029 | PS5-60-BI-0016C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5030 | PS5-60-BI-0016C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-01 13:14 | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-5031 | PS5-60-BI-0016C-CCO4 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5032 | PS5-60-BI-0016D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5033 | PS5-60-BI-0016D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5034 | PS5-60-BI-0016D-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-07-01 13:15 | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-5035 | PS5-60-BI-0016D-CCO4 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5048 | PS5-60-BI-0017A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0017A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5049 | PS5-60-BI-0017B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0017B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5050 | PS5-60-BI-0017C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0017C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5051 | PS5-60-BI-0017D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0017D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5055 | PS5-60-BI-0019A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0019A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5056 | PS5-60-BI-0019A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0019A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5057 | PS5-60-BI-0019B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0019B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5058 | PS5-60-BI-0019B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0019B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5059 | PS5-60-BI-0019C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0019C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5060 | PS5-60-BI-0019C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0019C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5061 | PS5-60-BI-0019D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0019D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5062 | PS5-60-BI-0019D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0019D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5069 | PS5-60-IE-0002B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5070 | PS5-60-IE-0002C-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-10 16:13 | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-5071 | PS5-60-IE-0002D-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-07-10 16:15 | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-5075 | PS5-60-IE-0003A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5076 | PS5-60-IE-0003A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5077 | PS5-60-IE-0003A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5078 | PS5-60-IE-0003A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5079 | PS5-60-IE-0003A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5080 | PS5-60-IE-0003A-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5081 | PS5-60-IE-0003A-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5082 | PS5-60-IE-0003A-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5083 | PS5-60-IE-0003A-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5084 | PS5-60-IE-0003A-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5085 | PS5-60-IE-0003A-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5086 | PS5-60-IE-0003A-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5087 | PS5-60-IE-0003A-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5088 | PS5-60-IE-0003A-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5093 | PS5-60-IE-0003A-CC25 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41100A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) | 2026-07-10 16:56 | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-5094 | PS5-60-IE-0003A-CC26 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41100B TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) | 2026-07-10 16:55 | PS5-60-02 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-5095 | PS5-60-IE-0003B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5096 | PS5-60-IE-0003B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5097 | PS5-60-IE-0003B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5098 | PS5-60-IE-0003B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5099 | PS5-60-IE-0003B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5100 | PS5-60-IE-0003B-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5101 | PS5-60-IE-0003B-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5102 | PS5-60-IE-0003B-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5103 | PS5-60-IE-0003B-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5104 | PS5-60-IE-0003B-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5105 | PS5-60-IE-0003B-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5106 | PS5-60-IE-0003B-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5107 | PS5-60-IE-0003B-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5108 | PS5-60-IE-0003B-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5113 | PS5-60-IE-0003B-CC25 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41200A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) | 2026-07-10 16:55 | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-5114 | PS5-60-IE-0003B-CC26 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41200B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) | 2026-07-10 16:54 | PS5-60-05 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-5115 | PS5-60-IE-0003C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5116 | PS5-60-IE-0003C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5117 | PS5-60-IE-0003C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5118 | PS5-60-IE-0003C-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5119 | PS5-60-IE-0003C-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5120 | PS5-60-IE-0003C-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5121 | PS5-60-IE-0003C-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5122 | PS5-60-IE-0003C-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5123 | PS5-60-IE-0003C-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5124 | PS5-60-IE-0003C-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5125 | PS5-60-IE-0003C-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5126 | PS5-60-IE-0003C-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5127 | PS5-60-IE-0003C-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5128 | PS5-60-IE-0003C-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5133 | PS5-60-IE-0003C-CC25 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41300A TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) | 2026-07-10 17:03 | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-5134 | PS5-60-IE-0003C-CC26 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41300B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) | 2026-07-10 17:04 | PS5-60-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-5135 | PS5-60-IE-0003D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5136 | PS5-60-IE-0003D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5137 | PS5-60-IE-0003D-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5138 | PS5-60-IE-0003D-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5139 | PS5-60-IE-0003D-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5140 | PS5-60-IE-0003D-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5141 | PS5-60-IE-0003D-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5142 | PS5-60-IE-0003D-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5143 | PS5-60-IE-0003D-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5144 | PS5-60-IE-0003D-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5145 | PS5-60-IE-0003D-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5146 | PS5-60-IE-0003D-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5147 | PS5-60-IE-0003D-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5148 | PS5-60-IE-0003D-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5153 | PS5-60-IE-0003D-CC25 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41400A TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) | 2026-07-10 17:03 | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-5154 | PS5-60-IE-0003D-CC26 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41400B TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) | 2026-07-10 17:03 | PS5-60-11 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-5215 | PS5-60-IE-0004-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5216 | PS5-60-IE-0004-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5217 | PS5-60-IE-0004-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5218 | PS5-60-IE-0004-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5219 | PS5-60-IE-0004-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5220 | PS5-60-IE-0004-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5221 | PS5-60-IE-0004-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5225 | PS5-60-IN-0001A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5226 | PS5-60-IN-0001A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5227 | PS5-60-IN-0001A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5228 | PS5-60-IN-0001A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2026-07-01 13:18 | PS5-60-49 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-5229 | PS5-60-IN-0001B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5230 | PS5-60-IN-0001B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5231 | PS5-60-IN-0001B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5232 | PS5-60-IN-0001B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2026-07-01 13:18 | PS5-60-50 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-5233 | PS5-60-IN-0001C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5234 | PS5-60-IN-0001C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | 2026-07-01 13:19 | PS5-60-51 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-5235 | PS5-60-IN-0001C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5236 | PS5-60-IN-0001C-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | 2026-07-01 13:19 | PS5-60-51 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-5237 | PS5-60-IN-0001D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5238 | PS5-60-IN-0001D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | 2026-07-01 13:20 | PS5-60-52 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-5239 | PS5-60-IN-0001D-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5240 | PS5-60-IN-0001D-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | 2026-07-01 13:21 | PS5-60-52 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-5253 | PS5-60-IN-0002A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5254 | PS5-60-IN-0002A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5255 | PS5-60-IN-0002A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5256 | PS5-60-IN-0002A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5257 | PS5-60-IN-0002A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5258 | PS5-60-IN-0002A-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5259 | PS5-60-IN-0002B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | 2026-07-07 14:06 | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-5260 | PS5-60-IN-0002B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5261 | PS5-60-IN-0002B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5262 | PS5-60-IN-0002B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | 2026-07-07 14:06 | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-5263 | PS5-60-IN-0002B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5264 | PS5-60-IN-0002B-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5265 | PS5-60-IN-0002C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | 2026-07-07 14:07 | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-5266 | PS5-60-IN-0002C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5267 | PS5-60-IN-0002C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5268 | PS5-60-IN-0002C-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | 2026-07-07 14:09 | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-5269 | PS5-60-IN-0002C-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5270 | PS5-60-IN-0002C-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5271 | PS5-60-IN-0002D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | 2026-07-07 14:11 | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-5272 | PS5-60-IN-0002D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5273 | PS5-60-IN-0002D-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5274 | PS5-60-IN-0002D-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | 2026-07-08 06:04 | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-5275 | PS5-60-IN-0002D-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5276 | PS5-60-IN-0002D-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5295 | PS5-60-IN-0004A-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5296 | PS5-60-LA-0002A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5297 | PS5-60-LA-0002A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5298 | PS5-60-LA-0002A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5299 | PS5-60-LA-0002A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5300 | PS5-60-LA-0002A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5301 | PS5-60-LA-0002A-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5302 | PS5-60-LA-0002A-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5303 | PS5-60-LA-0002A-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5304 | PS5-60-LA-0002A-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5305 | PS5-60-LA-0002B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5306 | PS5-60-LA-0002B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5307 | PS5-60-LA-0002B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5308 | PS5-60-LA-0002B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5309 | PS5-60-LA-0002B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5310 | PS5-60-LA-0002B-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5317 | PS5-60-LA-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5328 | PS5-60-SEA-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-08 04:54 | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone E | TM-00254 | Gawad, Mohamed
T-00254-5329 | PS5-60-SEA-0001-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00254
T-00254-5330 | PS5-60-SEA-0001-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-08 04:56 | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone E | TM-00254 | Gawad, Mohamed
T-00254-5331 | PS5-60-SEA-0001-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-08 05:01 | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone E | TM-00254 | Gawad, Mohamed
T-00254-5332 | PS5-60-SEA-0001-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-08 05:05 | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone E | TM-00254 | Gawad, Mohamed
T-00254-5333 | PS5-60-SEA-0001-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-08 05:06 | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone E | TM-00254 | Gawad, Mohamed
T-00254-5334 | PS5-60-SEA-0001-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-08 05:08 | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone E | TM-00254 | Gawad, Mohamed
T-00254-5335 | PS5-60-SEA-0001-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-08 05:10 | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone E | TM-00254 | Gawad, Mohamed
T-00254-5336 | PS5-60-SEA-0001-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-10 17:12 | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone E | TM-00254 | Gawad, Mohamed
T-00254-5337 | PS5-60-SEA-0001-CC12 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-10 17:13 | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone E | TM-00254 | Gawad, Mohamed
T-00254-5338 | PS5-60-SEA-0001-CC13 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00254
T-00254-5339 | PS5-60-SEA-0001-CC14 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-08 05:14 | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone E | TM-00254 | Gawad, Mohamed
T-00254-5340 | PS5-60-SEA-0001-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-08 05:20 | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone E | TM-00254 | Gawad, Mohamed
T-00254-5341 | PS5-60-SEA-0001-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-08 05:24 | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone E | TM-00254 | Gawad, Mohamed
T-00254-5342 | PS5-60-SEA-0001-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-08 05:26 | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone E | TM-00254 | Gawad, Mohamed
T-00254-5351 | PS5-60-VS-9101A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-VS-9101A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-07-08 05:29 | PS5-60-42 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-5352 | PS5-60-VS-9101B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-VS-9101B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-07-08 05:32 | PS5-60-43 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-5353 | PS5-60-VS-9101C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-VS-9101C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | 2026-07-08 05:34 | PS5-60-44 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-5354 | PS5-60-VS-9101D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-VS-9101D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | 2026-07-08 05:36 | PS5-60-45 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D | TM-00254 | Gawad, Mohamed
T-00254-5358 | PS5-61-BI-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5359 | PS5-61-BI-0001-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5360 | PS5-61-BI-0001-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-61-TE-0003A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5361 | PS5-61-BI-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5362 | PS5-61-BI-0002-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5363 | PS5-61-BI-0002-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-61-TE-0003B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5364 | PS5-61-BI-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-61-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5365 | PS5-61-BI-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-61-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5366 | PS5-61-BI-0003-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-61-TE-0003C TO PS5-61-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5367 | PS5-61-BI-0004-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-61-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5368 | PS5-61-BI-0004-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-61-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5369 | PS5-61-BI-0004-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-61-TE-0003D TO PS5-61-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | TM-00254
T-00254-5388 | PS5-71-BAV-0058-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2113 TO PS5-71-BAV-0058 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B | 2026-07-02 06:14 | PS5-71-21 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed | TZ-MID-68-WPR2-161503
T-00254-5389 | PS5-71-BAV-0059-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2113 TO PS5-71-BAV-0059 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module | 2026-07-02 06:23 | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone F | TM-00254 | Gawad, Mohamed | TZ-MID-68-WPR2-161503
T-00254-5390 | PS5-71-BI-0001A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5391 | PS5-71-BI-0001B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5393 | PS5-71-BI-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone F | TM-00254
T-00254-5394 | PS5-71-BI-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5395 | PS5-71-BI-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5396 | PS5-71-BI-0003-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5397 | PS5-71-BI-0003-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5398 | PS5-71-BI-0004-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5399 | PS5-71-BI-0005-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5400 | PS5-71-BI-0005-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5401 | PS5-71-BI-0006-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5402 | PS5-71-BI-0008A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5403 | PS5-71-BI-0008A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5404 | PS5-71-BI-0008B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5405 | PS5-71-BI-0008B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5406 | PS5-71-BI-0009-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0009 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone F | TM-00254
T-00254-5407 | PS5-71-BI-0009-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0009 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone F | TM-00254
T-00254-5408 | PS5-71-BI-0009-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0009 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone F | TM-00254
T-00254-5409 | PS5-71-BI-0009-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0009 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone F | TM-00254
T-00254-5410 | PS5-71-BI-0010-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0001 TO PS5-71-BI-0010 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone F | TM-00254
T-00254-5411 | PS5-71-BI-0011A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5412 | PS5-71-BI-0011A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5413 | PS5-71-BI-0011A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5414 | PS5-71-BI-0011A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5415 | PS5-71-BI-0011A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5416 | PS5-71-BI-0011B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5417 | PS5-71-BI-0011B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5418 | PS5-71-BI-0011B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5419 | PS5-71-BI-0011B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5420 | PS5-71-BI-0011B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5454 | PS5-71-FCV-0019-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-FCV-0019-HPU TO PS5-71-FCV-0019 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5461 | PS5-71-FIT-0019-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-1110 TO PS5-71-FIT-0019 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B | 2026-06-14 10:28 | PS5-71-21 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Anwar, Zeeshan | TZ-MID-68-WPR2-161503
T-00254-5464 | PS5-71-FXS-0019-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2114 TO PS5-71-FCV-0019 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B | 2026-07-02 06:20 | PS5-71-21 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed | TZ-MID-68-WPR2-161503
T-00254-5467 | PS5-71-FY-0019-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-1113 TO PS5-71-FCV-0019 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B | 2026-07-02 06:26 | PS5-71-21 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed | TZ-MID-68-WPR2-161503
T-00254-5486 | PS5-71-IN-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-07-08 05:57 | PS5-71-23 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-5487 | PS5-71-IN-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-07-08 05:59 | PS5-71-23 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed
T-00254-5488 | PS5-71-IN-0003-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5489 | PS5-71-IN-0003-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254
T-00254-5493 | PS5-71-IN-0004A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5494 | PS5-71-IN-0004A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5495 | PS5-71-IN-0004A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5496 | PS5-71-IN-0004A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-0011A TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-10 16:46 | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone H | TM-00254 | Gawad, Mohamed
T-00254-5497 | PS5-71-IN-0004A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-0011A TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-10 16:45 | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone H | TM-00254 | Gawad, Mohamed
T-00254-5498 | PS5-71-IN-0004A-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5499 | PS5-71-IN-0004A-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5502 | PS5-71-IN-0004A-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5504 | PS5-71-IN-0004A-CC13 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004B TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5505 | PS5-71-IN-0004B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5506 | PS5-71-IN-0004B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5507 | PS5-71-IN-0004B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5508 | PS5-71-IN-0004B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-0011B TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-10 16:45 | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone H | TM-00254 | Gawad, Mohamed
T-00254-5509 | PS5-71-IN-0004B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-0011B TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-10 16:56 | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone H | TM-00254 | Gawad, Mohamed
T-00254-5510 | PS5-71-IN-0004B-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5511 | PS5-71-IN-0004B-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5514 | PS5-71-IN-0004B-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0001 TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254
T-00254-5518 | PS5-71-LIT-1201-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-1113 TO PS5-71-LIT-1201 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank | 2026-07-02 06:25 | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed | TZ-MID-68-WPR2-161503
T-00254-5519 | PS5-71-LIT-1202-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-28-BI-1307 TO PS5-71-LIT-1202 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank | 2026-07-02 06:27 | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed | TZ-MID-68-WPR2-161503
T-00254-5528 | PS5-71-MOV-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2120 TO PS5-71-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254 |  | TZ-MID-68-WPR2-161503
T-00254-5529 | PS5-71-MOV-0001-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2124 TO PS5-71-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254 |  | TZ-MID-68-WPR2-161503
T-00254-5530 | PS5-71-MOV-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2120 TO PS5-71-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254 |  | TZ-MID-68-WPR2-161503
T-00254-5531 | PS5-71-MOV-0002-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2124 TO PS5-71-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254 |  | TZ-MID-68-WPR2-161503
T-00254-5532 | PS5-71-MOV-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2121 TO PS5-71-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254 |  | TZ-MID-68-WPR2-161503
T-00254-5533 | PS5-71-MOV-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2125 TO PS5-71-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254 |  | TZ-MID-68-WPR2-161503
T-00254-5534 | PS5-71-MOV-0004-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2121 TO PS5-71-MOV-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254 |  | TZ-MID-68-WPR2-161503
T-00254-5535 | PS5-71-MOV-0004-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2125 TO PS5-71-MOV-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254 |  | TZ-MID-68-WPR2-161503
T-00254-5536 | PS5-71-MOV-0007-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2118 TO PS5-71-MOV-0007 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254 |  | TZ-MID-68-WPR2-161503
T-00254-5537 | PS5-71-MOV-0007-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2122 TO PS5-71-MOV-0007 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254 |  | TZ-MID-68-WPR2-161503
T-00254-5538 | PS5-71-MOV-0008-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2118 TO PS5-71-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254 |  | TZ-MID-68-WPR2-161503
T-00254-5539 | PS5-71-MOV-0008-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2122 TO PS5-71-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254 |  | TZ-MID-68-WPR2-161503
T-00254-5540 | PS5-71-MOV-0009-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2119 TO PS5-71-MOV-0009 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254 |  | TZ-MID-68-WPR2-161503
T-00254-5541 | PS5-71-MOV-0009-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2123 TO PS5-71-MOV-0009 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | TM-00254 |  | TZ-MID-68-WPR2-161503
T-00254-5542 | PS5-71-MOV-0010-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2119 TO PS5-71-MOV-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254 |  | TZ-MID-68-WPR2-161503
T-00254-5543 | PS5-71-MOV-0010-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2123 TO PS5-71-MOV-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254 |  | TZ-MID-68-WPR2-161503
T-00254-5547 | PS5-71-PIT-0001-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-28-BI-1307 TO PS5-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank | 2026-07-02 06:35 | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed | TZ-MID-68-WPR2-161503
T-00254-5550 | PS5-71-PIT-0019A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-1113 TO PS5-71-FCV-0019 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B | 2026-07-02 06:35 | PS5-71-21 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed | TZ-MID-68-WPR2-161503
T-00254-5557 | PS5-71-PIT-0091-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-1113 TO PS5-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module | 2026-07-02 06:40 | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone F | TM-00254 | Gawad, Mohamed | TZ-MID-68-WPR2-161503
T-00254-5558 | PS5-71-PIT-0092-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-1113 TO PS5-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank | 2026-07-02 06:46 | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed | TZ-MID-68-WPR2-161503
T-00254-5570 | PS5-71-SDV-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-25-BI-2315 TO PS5-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254 |  | TZ-MID-68-WPR2-161503
T-00254-5571 | PS5-71-SDV-0001-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-SDV-0001-HPU TO PS5-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | UT-MID-60-NBV3-160008 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254 |  | UT-MID-60-NBV3-160008
T-00254-5578 | PS5-71-SXS-0001-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-25-BI-2312 TO PS5-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254 |  | TZ-MID-68-WPR2-161503
T-00254-5582 | PS5-71-SY-0001-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-25-BI-2316 TO PS5-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254 |  | TZ-MID-68-WPR2-161503
T-00254-5604 | PS5-71-XV-0091-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2113 TO PS5-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module | 2026-07-02 06:51 | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone F | TM-00254 | Gawad, Mohamed | TZ-MID-68-WPR2-161503
T-00254-5605 | PS5-71-XV-0091-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-XV-0091-HPU TO PS5-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  | UT-MID-60-NBV3-160008 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module |  | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone F | TM-00254 |  | UT-MID-60-NBV3-160008
T-00254-5606 | PS5-71-XV-0092-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2113 TO PS5-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank | 2026-07-02 06:53 | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed | TZ-MID-68-WPR2-161503
T-00254-5607 | PS5-71-XV-0092-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-XV-0092-HPU TO PS5-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  | UT-MID-60-NBV3-160008 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | TM-00254 |  | UT-MID-60-NBV3-160008
T-00254-5610 | PS5-71-XXS-0091-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2114 TO PS5-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module | 2026-07-02 06:54 | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone F | TM-00254 | Gawad, Mohamed | TZ-MID-68-WPR2-161503
T-00254-5611 | PS5-71-XXS-0092-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2114 TO PS5-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank | 2026-07-02 06:51 | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed | TZ-MID-68-WPR2-161503
T-00254-5614 | PS5-71-XY-0091-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2115 TO PS5-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-18 - Diesel Separator Module | 2026-07-02 06:58 | PS5-71-18 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone F | TM-00254 | Gawad, Mohamed | TZ-MID-68-WPR2-161503
T-00254-5615 | PS5-71-XY-0092-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2115 TO PS5-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank | 2026-07-02 06:59 | PS5-71-20 | Priority-1 |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | TM-00254 | Gawad, Mohamed | TZ-MID-68-WPR2-161503
T-00254-9420 | PS5-03-RMAC-1409-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-SEA-0003 TO PS5-03-RMAC-1409 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | TM-00254
T-00256-0027 | PS5-60-IE-0004-CX03 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-SSF1-161401 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B | TM-00256 |  | TZ-MID-68-SSF1-161401
T-00256-0028 | PS5-60-IE-0004-CX04 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-SSF1-161401 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B | TM-00256 |  | TZ-MID-68-SSF1-161401
T-00256-0029 | PS5-60-LA-0003-CX01 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-SSF1-161401 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B | TM-00256 |  | TZ-MID-68-SSF1-161401
T-00256-0090 | PS5-60-LA-0003-CX02 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B | TM-00256
T-00257-0169 | PS5-60-TW-0007C |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | Thermowell | I | To be completed | PS5 - Milestone D | TM-00257 |  | TZ-MID-68-WPR2-135106
T-00257-0173 | PS5-60-TW-0007B |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | Thermowell | I | To be completed | PS5 - Milestone B | TM-00257 |  | TZ-MID-68-WPR2-135103
T-00257-0174 | PS5-60-TW-0006C |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | Thermowell | I | To be completed | PS5 - Milestone D | TM-00257 |  | TZ-MID-68-WPR2-135106
T-00257-0175 | PS5-60-TW-0008A |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | Thermowell | I | To be completed | PS5 - Milestone B | TM-00257 |  | TZ-MID-68-WPR2-135100
T-00257-0176 | PS5-60-TW-0007D |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | Thermowell | I | To be completed | PS5 - Milestone D | TM-00257 |  | TZ-MID-68-WPR2-135109
T-00257-0177 | PS5-60-TW-0008C |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | Thermowell | I | To be completed | PS5 - Milestone D | TM-00257 |  | TZ-MID-68-WPR2-135106
T-00257-0182 | PS5-60-TW-0007A |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | Thermowell | I | To be completed | PS5 - Milestone B | TM-00257 |  | TZ-MID-68-WPR2-135100
T-00257-0183 | PS5-60-TW-0006D |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | Thermowell | I | To be completed | PS5 - Milestone D | TM-00257 |  | TZ-MID-68-WPR2-135109
T-00257-0184 | PS5-60-TW-0008B |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | Thermowell | I | To be completed | PS5 - Milestone B | TM-00257 |  | TZ-MID-68-WPR2-135103
T-00257-0186 | PS5-60-TW-0008D |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | Thermowell | I | To be completed | PS5 - Milestone D | TM-00257 |  | TZ-MID-68-WPR2-135109
T-00257-0194 | PS5-60-TW-0006B |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | Thermowell | I | To be completed | PS5 - Milestone B | TM-00257 |  | TZ-MID-68-WPR2-135103
T-00257-0198 | PS5-60-TW-0006A |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | Thermowell | I | To be completed | PS5 - Milestone B | TM-00257 |  | TZ-MID-68-WPR2-135100
T-00257-0207 | PS5-60-TW-0005A |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 | Priority-1 |  | Thermowell | I | To be completed | PS5 - Milestone B | TM-00257 |  | TZ-MID-68-WPR2-135100
T-00257-0208 | PS5-60-TW-0005B |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 | Priority-1 |  | Thermowell | I | To be completed | PS5 - Milestone B | TM-00257 |  | TZ-MID-68-WPR2-135103
T-00257-0209 | PS5-60-TW-0005C |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 | Priority-2 |  | Thermowell | I | To be completed | PS5 - Milestone D | TM-00257 |  | TZ-MID-68-WPR2-135106
T-00257-0210 | PS5-60-TW-0005D |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 | Priority-2 |  | Thermowell | I | To be completed | PS5 - Milestone D | TM-00257 |  | TZ-MID-68-WPR2-135109
T-00284-0085 | PS5-71-FIT-0019 |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | DP Flow Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135008 | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | Tubing Pressure Test | I | To be completed | PS5 - Milestone B | TM-00284 |  | TZ-MID-68-WPR2-135008
T-00284-0091 | PS5-71-LIT-1202 |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | DP Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135205 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Tubing Pressure Test | I | To be completed | PS5 - Milestone B | TM-00284 |  | TZ-MID-68-WPR2-135205
T-00284-0096 | PS5-71-LIT-1201 |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | DP Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135205 | PS5 - TZA - PS5 - Tanzania | PS5-71-20 - Diesel Fuel Day Tank |  | PS5-71-20 | Priority-1 |  | Tubing Pressure Test | I | To be completed | PS5 - Milestone B | TM-00284 |  | TZ-MID-68-WPR2-135205
T-00284-0186 | PS5-71-FCV-0019 |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-21 - Diesel Transfer Pump A/B |  | PS5-71-21 | Priority-1 |  | Tubing Pressure Test | I | To be completed | PS5 - Milestone B | TM-00284
T-00614-0853 | PS5-01-BI-1117-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0002 TO PS5-01-BI-1117 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0854 | PS5-01-BI-1118-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0001 TO PS5-01-BI-1118 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0856 | PS5-01-BI-1515-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0008 TO PS5-01-BI-1515 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0859 | PS5-01-BI-2110-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0006 TO PS5-01-BI-2110 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0893 | PS5-03-BI-2503-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2503 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-07-04 10:58 | PS5-91-01 | Priority-1 |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | TM-00614 | Gawad, Mohamed
T-00614-0896 | PS5-03-BI-2506-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0010 TO PS5-03-BI-2506 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0899 | PS5-03-BI-2509-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0010 TO PS5-03-BI-2509 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0903 | PS5-03-BI-2514-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2514 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0904 | PS5-03-BI-2515-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2515 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0922 | PS5-03-SEA-0003-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0010 TO PS5-03-SEA-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  |  | I | To be completed | PS5 - Milestone E | TM-00614
T-00614-0923 | PS5-03-SEA-0003-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-03-SEA-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  |  | I | To be completed | PS5 - Milestone E | TM-00614
T-00614-0953 | PS5-25-BI-1101-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0001 TO PS5-25-BI-1101 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0954 | PS5-25-BI-1102-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0002 TO PS5-25-BI-1102 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0955 | PS5-25-BI-1103-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0001 TO PS5-25-BI-1103 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:36 | PS5-91-01 | Priority-1 |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | TM-00614 | Gawad, Mohamed
T-00614-0956 | PS5-25-BI-1104-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0002 TO PS5-25-BI-1104 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:33 | PS5-91-01 | Priority-1 |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | TM-00614 | Gawad, Mohamed
T-00614-0957 | PS5-25-BI-1115-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0002 TO PS5-25-BI-1115 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0961 | PS5-25-BI-1201-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0001 TO PS5-25-BI-1201 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0965 | PS5-25-BI-1301-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0002 TO PS5-25-BI-1301 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0966 | PS5-25-BI-1302-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0002 TO PS5-25-BI-1302 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0967 | PS5-25-BI-1310-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0002 TO PS5-25-BI-1310 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0982 | PS5-25-BI-2103-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0006 TO PS5-25-BI-2103 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0983 | PS5-25-BI-2104-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0003 TO PS5-25-BI-2104 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0984 | PS5-25-BI-2105-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0006 TO PS5-25-BI-2105 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0985 | PS5-25-BI-2106-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0006 TO PS5-25-BI-2106 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0986 | PS5-25-BI-2108-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-25-BI-2108 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:27 | PS5-91-01 | Priority-1 |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | TM-00614 | Gawad, Mohamed
T-00614-0987 | PS5-25-BI-2109-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-25-BI-2109 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:29 | PS5-91-01 | Priority-1 |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | TM-00614 | Gawad, Mohamed
T-00614-0988 | PS5-25-BI-2201-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0001 TO PS5-25-BI-2201 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0989 | PS5-25-BI-2203-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0001 TO PS5-25-BI-2203 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0991 | PS5-25-BI-2301-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0003 TO PS5-25-BI-2301 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0992 | PS5-25-BI-2302-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0004 TO PS5-25-BI-2302 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0993 | PS5-25-BI-2305-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0003 TO PS5-25-BI-2305 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0994 | PS5-25-BI-2308-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0005 TO PS5-25-BI-2308 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:26 | PS5-91-01 | Priority-1 |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | TM-00614 | Gawad, Mohamed
T-00614-0995 | PS5-25-BI-2309-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0005 TO PS5-25-BI-2309 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-0996 | PS5-25-BI-2312-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0003 TO PS5-25-BI-2312 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:32 | PS5-91-01 | Priority-1 |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | TM-00614 | Gawad, Mohamed
T-00614-0997 | PS5-25-BI-2315-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0003 TO PS5-25-BI-2315 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:28 | PS5-91-01 | Priority-1 |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | TM-00614 | Gawad, Mohamed
T-00614-0998 | PS5-25-BI-2316-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0006 TO PS5-25-BI-2316 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:30 | PS5-91-01 | Priority-1 |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | TM-00614 | Gawad, Mohamed
T-00614-1014 | PS5-28-BI-1105-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0001 TO PS5-28-BI-1105 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1017 | PS5-28-BI-1303-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0001 TO PS5-28-BI-1303 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1018 | PS5-28-BI-1307-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0001 TO PS5-28-BI-1307 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1023 | PS5-50-BI-1107-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0002 TO PS5-50-BI-1107 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1030 | PS5-53-BI-1108-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0002 TO PS5-53-BI-1108 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1034 | PS5-60-IE-0003A-CC21 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  |  | I | To be completed | PS5 - Milestone B | TM-00614
T-00614-1035 | PS5-60-IE-0003A-CC22 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  |  | I | To be completed | PS5 - Milestone B | TM-00614
T-00614-1036 | PS5-60-IE-0003A-CC23 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0003 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  |  | I | To be completed | PS5 - Milestone B | TM-00614
T-00614-1037 | PS5-60-IE-0003A-CC24 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 | Priority-1 |  |  | I | To be completed | PS5 - Milestone B | TM-00614
T-00614-1038 | PS5-60-IE-0003B-CC21 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  |  | I | To be completed | PS5 - Milestone B | TM-00614
T-00614-1039 | PS5-60-IE-0003B-CC22 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  |  | I | To be completed | PS5 - Milestone B | TM-00614
T-00614-1040 | PS5-60-IE-0003B-CC23 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0003 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  |  | I | To be completed | PS5 - Milestone B | TM-00614
T-00614-1041 | PS5-60-IE-0003B-CC24 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  |  | I | To be completed | PS5 - Milestone B | TM-00614
T-00614-1042 | PS5-60-IE-0003C-CC21 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  |  | I | To be completed | PS5 - Milestone D | TM-00614
T-00614-1043 | PS5-60-IE-0003C-CC22 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  |  | I | To be completed | PS5 - Milestone D | TM-00614
T-00614-1044 | PS5-60-IE-0003C-CC23 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0003 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  |  | I | To be completed | PS5 - Milestone D | TM-00614
T-00614-1045 | PS5-60-IE-0003C-CC24 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0006 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  |  | I | To be completed | PS5 - Milestone D | TM-00614
T-00614-1046 | PS5-60-IE-0003D-CC21 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  |  | I | To be completed | PS5 - Milestone D | TM-00614
T-00614-1047 | PS5-60-IE-0003D-CC22 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  |  | I | To be completed | PS5 - Milestone D | TM-00614
T-00614-1048 | PS5-60-IE-0003D-CC23 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0003 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  |  | I | To be completed | PS5 - Milestone D | TM-00614
T-00614-1049 | PS5-60-IE-0003D-CC24 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  |  | I | To be completed | PS5 - Milestone D | TM-00614
T-00614-1062 | PS5-60-IE-0004-CC08 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  |  | I | To be completed | PS5 - Milestone B | TM-00614
T-00614-1063 | PS5-60-IE-0004-CC11 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0004 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  |  | I | To be completed | PS5 - Milestone B | TM-00614
T-00614-1064 | PS5-60-IE-0004-CC12 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  |  | I | To be completed | PS5 - Milestone B | TM-00614
T-00614-1065 | PS5-60-SEA-0001-CC18 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0009 TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  |  | I | To be completed | PS5 - Milestone E | TM-00614
T-00614-1078 | PS5-71-BI-1109-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0002 TO PS5-71-BI-1109 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1079 | PS5-71-BI-1110-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0001 TO PS5-71-BI-1110 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:22 | PS5-91-01 | Priority-1 |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | TM-00614 | Gawad, Mohamed
T-00614-1080 | PS5-71-BI-1111-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0002 TO PS5-71-BI-1111 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1082 | PS5-71-BI-1113-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0002 TO PS5-71-BI-1113 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1083 | PS5-71-BI-1116-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0002 TO PS5-71-BI-1116 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:23 | PS5-91-01 | Priority-1 |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | TM-00614 | Gawad, Mohamed
T-00614-1084 | PS5-71-BI-1117-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0001 TO PS5-71-BI-1117 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1085 | PS5-71-BI-2101-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-71-BI-2101 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-07-04 11:28 | PS5-91-01 | Priority-1 |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | TM-00614 | Gawad, Mohamed
T-00614-1086 | PS5-71-BI-1305-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0002 TO PS5-71-BI-1305 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1087 | PS5-71-BI-1306-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0002 TO PS5-71-BI-1306 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:25 | PS5-91-01 | Priority-1 |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | TM-00614 | Gawad, Mohamed
T-00614-1089 | PS5-71-BI-2107-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0006 TO PS5-71-BI-2107 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1090 | PS5-71-BI-2113-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0003 TO PS5-71-BI-2113 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1091 | PS5-71-BI-2114-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0006 TO PS5-71-BI-2114 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1092 | PS5-71-BI-2115-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-71-BI-2115 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1093 | PS5-71-BI-2116-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0003 TO PS5-71-BI-2116 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1094 | PS5-71-BI-2118-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0005 TO PS5-71-BI-2118 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1095 | PS5-71-BI-2119-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0005 TO PS5-71-BI-2119 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1096 | PS5-71-BI-2120-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0005 TO PS5-71-BI-2120 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1097 | PS5-71-BI-2121-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0005 TO PS5-71-BI-2121 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1098 | PS5-71-BI-2122-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-71-BI-2122 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1099 | PS5-71-BI-2123-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0006 TO PS5-71-BI-2123 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1100 | PS5-71-BI-2124-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0006 TO PS5-71-BI-2124 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1101 | PS5-71-BI-2125-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0006 TO PS5-71-BI-2125 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1102 | PS5-71-BI-2306-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0004 TO PS5-71-BI-2306 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1104 | PS5-71-BI-2310-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0006 TO PS5-71-BI-2310 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 | Priority-1 |  |  | I | To be completed | PS5 - Milestone A | TM-00614
T-00614-1106 | PS5-71-BI-2314-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0004 TO PS5-71-BI-2314 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:39 | PS5-91-01 | Priority-1 |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | TM-00614 | Gawad, Mohamed
T-00614-1114 | PS5-71-IN-0003-CC05 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 | Priority-1 |  |  | I | To be completed | PS5 - Milestone B | TM-00614
T-00614-1115 | PS5-71-IN-0003-CC06 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 | Priority-1 |  |  | I | To be completed | PS5 - Milestone B | TM-00614
T-00614-1116 | PS5-71-IN-0003-CC07 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0006 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 | Priority-1 |  |  | I | To be completed | PS5 - Milestone B | TM-00614
T-00614-1117 | PS5-71-IN-0004A-CC08 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  |  | I | To be completed | PS5 - Milestone H | TM-00614
T-00614-1118 | PS5-71-IN-0004A-CC09 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0003 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  |  | I | To be completed | PS5 - Milestone H | TM-00614
T-00614-1119 | PS5-71-IN-0004A-CC12 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0005 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  |  | I | To be completed | PS5 - Milestone H | TM-00614
T-00614-1120 | PS5-71-IN-0004B-CC08 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  |  | I | To be completed | PS5 - Milestone H | TM-00614
T-00614-1121 | PS5-71-IN-0004B-CC09 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0003 TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  |  | I | To be completed | PS5 - Milestone H | TM-00614
T-00614-1122 | PS5-71-IN-0004B-CC12 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0005 TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  |  | I | To be completed | PS5 - Milestone H | TM-00614
T-00171-4342 | PS5-60-IE-0003B-CA02 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | TM-00171
T-00171-4343 | PS5-60-IE-0003B-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | TM-00171
T-00171-4344 | PS5-60-IE-0003B-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | TM-00171
T-00171-4345 | PS5-60-IE-0003B-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | TM-00171
T-00171-4346 | PS5-60-IE-0003C-CA02 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | TM-00171
T-00171-4347 | PS5-60-IE-0003C-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | TM-00171
T-00171-4348 | PS5-60-IE-0003C-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | TM-00171
T-00171-4349 | PS5-60-IE-0003C-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | TM-00171
T-00171-4350 | PS5-60-IE-0003D-CA02 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | TM-00171
T-00171-4351 | PS5-60-IE-0003D-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | TM-00171
T-00171-4352 | PS5-60-IE-0003D-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | TM-00171
T-00171-4353 | PS5-60-IE-0003D-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | TM-00171
T-00171-4365 | PS5-60-IE-0004-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | TM-00171
T-00171-4366 | PS5-60-IE-0004-CA07 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | TM-00171
T-00171-4367 | PS5-60-IE-0004-CA08 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | TM-00171
T-00171-4368 | PS5-60-IE-0004-CA14 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | TM-00171
T-00171-4369 | PS5-60-IE-0004-CA15 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | TM-00171
T-00171-4370 | PS5-60-IE-0004-CA21 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | TM-00171
T-00171-4371 | PS5-60-IH-0001A-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 | Priority-1 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | TM-00171
T-00171-4372 | PS5-60-IH-0001B-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0001B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 | Priority-1 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | TM-00171
T-00171-4373 | PS5-60-IH-0001C-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0001C TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | TM-00171
T-00171-4374 | PS5-60-IH-0001D-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0001D TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | TM-00171
T-00171-4378 | PS5-60-IN-0001A-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 | Priority-1 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | TM-00171
T-00171-4379 | PS5-60-IN-0001B-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 | Priority-1 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | TM-00171
T-00171-4380 | PS5-60-IN-0001C-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | TM-00171
T-00171-4381 | PS5-60-IN-0001D-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | TM-00171
T-00171-4385 | PS5-60-IN-0002A-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | TM-00171
T-00171-4386 | PS5-60-IN-0002B-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | TM-00171
T-00171-4387 | PS5-60-IN-0002C-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | TM-00171
T-00171-4388 | PS5-60-IN-0002D-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | TM-00171
T-00171-4392 | PS5-60-LA-0002B-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | TM-00171
T-00171-4393 | PS5-60-LA-0002B-CA02 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | TM-00171
T-00171-4394 | PS5-60-LA-0002B-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | TM-00171
T-00171-4395 | PS5-60-LA-0002B-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | TM-00171
T-00171-4396 | PS5-60-LA-0002B-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002C TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | TM-00171
T-00171-4397 | PS5-60-LA-0002B-CA06 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002C TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | TM-00171
T-00171-4404 | PS5-60-SEA-0001-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone E | TM-00171
T-00171-4408 | PS5-71-IN-0003-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 | Priority-1 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | TM-00171
T-00171-4409 | PS5-71-IN-0004A-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone H | TM-00171
T-00171-4410 | PS5-71-IN-0004B-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone H | TM-00171
T-00275-1945 | PS5-60-IE-0003B-CA02 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | TM-00275
T-00275-1946 | PS5-60-IE-0003B-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | TM-00275
T-00275-1947 | PS5-60-IE-0003B-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | TM-00275
T-00275-1948 | PS5-60-IE-0003B-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 | Priority-1 |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | TM-00275
T-00275-1949 | PS5-60-IE-0003C-CA02 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | TM-00275
T-00275-1950 | PS5-60-IE-0003C-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | TM-00275
T-00275-1951 | PS5-60-IE-0003C-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | TM-00275
T-00275-1952 | PS5-60-IE-0003C-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | TM-00275
T-00275-1953 | PS5-60-IE-0003D-CA02 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | TM-00275
T-00275-1954 | PS5-60-IE-0003D-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | TM-00275
T-00275-1955 | PS5-60-IE-0003D-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | TM-00275
T-00275-1956 | PS5-60-IE-0003D-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | TM-00275
T-00275-1968 | PS5-60-IE-0004-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | TM-00275
T-00275-1969 | PS5-60-IE-0004-CA07 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | TM-00275
T-00275-1970 | PS5-60-IE-0004-CA08 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | TM-00275
T-00275-1971 | PS5-60-IE-0004-CA14 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | TM-00275
T-00275-1972 | PS5-60-IE-0004-CA15 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | TM-00275
T-00275-1973 | PS5-60-IE-0004-CA21 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 | Priority-1 |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | TM-00275
T-00275-1974 | PS5-60-IH-0001A-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 | Priority-1 |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | TM-00275
T-00275-1975 | PS5-60-IH-0001B-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0001B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 | Priority-1 |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | TM-00275
T-00275-1976 | PS5-60-IH-0001C-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0001C TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | TM-00275
T-00275-1977 | PS5-60-IH-0001D-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0001D TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | TM-00275
T-00275-1981 | PS5-60-IN-0001A-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 | Priority-1 |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | TM-00275
T-00275-1982 | PS5-60-IN-0001B-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 | Priority-1 |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | TM-00275
T-00275-1983 | PS5-60-IN-0001C-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | TM-00275
T-00275-1984 | PS5-60-IN-0001D-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | TM-00275
T-00275-1988 | PS5-60-IN-0002A-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 | Priority-1 |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | TM-00275
T-00275-1989 | PS5-60-IN-0002B-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 | Priority-1 |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | TM-00275
T-00275-1990 | PS5-60-IN-0002C-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | TM-00275
T-00275-1991 | PS5-60-IN-0002D-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | TM-00275
T-00275-1995 | PS5-60-LA-0002B-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | TM-00275
T-00275-1996 | PS5-60-LA-0002B-CA02 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | TM-00275
T-00275-1997 | PS5-60-LA-0002B-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | TM-00275
T-00275-1998 | PS5-60-LA-0002B-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | TM-00275
T-00275-1999 | PS5-60-LA-0002B-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002C TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | TM-00275
T-00275-2000 | PS5-60-LA-0002B-CA06 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002C TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | TM-00275
T-00275-2007 | PS5-60-SEA-0001-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone E | TM-00275
T-00275-2011 | PS5-71-IN-0003-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 | Priority-1 |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | TM-00275
T-00275-2012 | PS5-71-IN-0004A-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004A | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone H | TM-00275
T-00275-2013 | PS5-71-IN-0004B-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0004B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-07 - Crude Fuel Separation Module (UCP) |  | PS5-71-07 | Priority-2 |  | RJ45 Cable | T | To be completed | PS5 - Milestone H | TM-00275