## Sheet1
EACOP PIPELINE PROJECT — CMT Based Precommissioning Progress Status - PS5
Discipline | Total | Open / Balance | Closed / Approved | % Closed | Cables Laid | Laying RFI | Testing RFI | GLANDING & TERMINATION INSPECTION | Conformity no | Conf Backlog | CMT Closed | Static no | Static Closed | Static Backlog
E-Electrical | 1918 | 1833 | 85 | 4 | 1918 | 824 | 745 | 23 | 1918 | 1833 | 85 | 1406 | 539 | 867
Both End HOOKUP by CPP EIT Team (Both end by CPP) | 1553 | 1535 | 18 | 1 | 1553 | 486 | 443 | 0 | 1553 | 1535 | 18 | 1406 | 539 | 867
Both End HOOKUP by Kent Team (both end by HU CTR) | 78 | 34 | 44 | 56 | 78 | 77 | 74 | 0 | 78 | 34 | 44 | 0 | 0 | 0
One End HOOKUP by Kent Team | 287 | 264 | 23 | 8 | 287 | 261 | 228 | 23 | 287 | 264 | 23 | 0 | 0 | 0
Both end Hookup by schiender Team | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
instrument | 2838 | 2792 | 46 | 2 | 2838 | 710 | 442 | 2 | 2838 | 2792 | 46 | 1663 | 182 | 1481
Both End HOOKUP by CPP EIT Team (Both end by CPP) | 2525 | 2498 | 27 | 1 | 2525 | 424 | 288 | 0 | 2525 | 2498 | 27 | 1663 | 182 | 1481
Both End HOOKUP by Kent Team (both end by HU CTR) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
One End HOOKUP by Kent Team | 313 | 294 | 19 | 6 | 313 | 286 | 154 | 2 | 313 | 294 | 19 | 0 | 0 | 0
Both end Hookup by schiender Team | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T-Telecom | 822 | 799 | 23 | 3 | 822 | 80 | 72 | 0 | 822 | 794 | 23 | 256 | 0 | 256
CPP AGI | 71 | 71 | 0 | 0 | 71 | 0 | 0 | 0 | 71 | 71 | 0 | 71 | 0 | 71
EITS | 751 | 728 | 23 | 3 | 751 | 80 | 72 | 0 | 751 | 723 | 23 | 185 | 0 | 185