## ITR Tracker
Asset Tag | Task ID | Discipline | Subsystem | Description | Construction | RFI? | RFI Status | Punch | Open Punch | Variation
PS5-61-ISR-0101 | T-00018-0098 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-ISR-0102 | T-00018-0099 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX02 - Power transformer | Started (not Completed) | No | No RFI Yet | - |  | Not Started
PS5-61-IU-0010 | T-00018-0100 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | CPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IU-0011 | T-00018-0101 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | CPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IV-0001A | T-00018-0102 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX02 - Power transformer | Closed | Yes | Accepted | B:0/1, C:0/1 | Yes | Closed + Accepted
PS5-61-IV-0001B | T-00018-0103 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX02 - Power transformer | To be completed | Yes | Other | A:0/2 | Yes | Open + RFI Submitted
PS5-63-IV-0010 | T-00018-0104 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-63-IV-0011 | T-00018-0105 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IV-0002A | T-00018-0121 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX02 - Power transformer | To be completed | Yes | Other | A:2/4, C:0/1 | Yes | Open + RFI Submitted
PS5-61-IV-0002B | T-00018-0122 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX02 - Power transformer | To be completed | Yes | Other | A:1/3, C:0/1 | Yes | Open + RFI Submitted
PS5-61-IV-0007A | T-00018-0123 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX02 - Power transformer | To be completed | Yes | Other | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IV-0007B | T-00018-0124 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX02 - Power transformer | To be completed | Yes | Other | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IU-3100A | T-00018-0171 | E | PS5-25-02 - Crude Oil Export Pump A | CPX02 - Power transformer | Closed | Yes | Accepted | C:0/1 | Yes | Closed + Accepted
PS5-61-IU-3100B | T-00018-0172 | E | PS5-25-03 - Crude Oil Export Pump B | CPX02 - Power transformer | Closed | Yes | Accepted | C:0/1 | Yes | Closed + Accepted
PS5-61-IU-3100C | T-00018-0173 | E | PS5-25-04 - Crude Oil Export Pump C | CPX02 - Power transformer | Closed | Yes | Accepted | C:0/1 | Yes | Closed + Accepted
PS5-61-IU-0001A | T-00018-0192 | E | PS5-60-01 - Power Generation Package A | CPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IU-0001B | T-00018-0193 | E | PS5-60-04 - Power Generation Package B | CPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IU-0001C | T-00018-0194 | E | PS5-60-07 - Power Generation Package C | CPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IU-0001D | T-00018-0195 | E | PS5-60-10 - Power Generation Package D | CPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IU-0001E | T-00018-0196 | E | PS5-60-13 - Power Generation Package E | CPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IU-0001F | T-00018-0197 | E | PS5-60-16 - Power Generation Package F | CPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IU-0001G | T-00018-0198 | E | PS5-60-19 - Power Generation Package G | CPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IV-0001 | T-00018-0237 | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution | CPX02 - Power transformer | To be completed | Yes | Accepted with Punch | C:0/1 | Yes | Open + RFI Submitted
PS5-79-IV-0002 | T-00018-0238 | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution | CPX02 - Power transformer | To be completed | Yes | Accepted with Punch | C:0/1 | Yes | Open + RFI Submitted
PS5-79-IV-0003 | T-00018-0239 | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution | CPX02 - Power transformer | To be completed | Yes | Accepted with Punch | C:0/1 | Yes | Open + RFI Submitted
PS5-79-IV-0004 | T-00018-0240 | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution | CPX02 - Power transformer | To be completed | Yes | Accepted with Punch | C:0/1 | Yes | Open + RFI Submitted
PS5-79-IV-0005 | T-00018-0241 | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution | CPX02 - Power transformer | To be completed | Yes | Accepted with Punch | C:0/1 | Yes | Open + RFI Submitted
PS5-79-IV-0006 | T-00018-0242 | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution | CPX02 - Power transformer | To be completed | Yes | Accepted with Punch | B:0/1, C:0/1 | Yes | Open + RFI Submitted
PS5-79-IV-0007 | T-00018-0243 | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution | CPX02 - Power transformer | To be completed | Yes | Accepted with Punch | C:0/1 | Yes | Open + RFI Submitted
PS5-79-IV-0008 | T-00018-0244 | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution | CPX02 - Power transformer | To be completed | Yes | Accepted with Punch | C:0/1 | Yes | Open + RFI Submitted
PS5-79-IV-0009 | T-00018-0245 | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution | CPX02 - Power transformer | To be completed | Yes | Accepted with Punch | C:0/1 | Yes | Open + RFI Submitted
PS5-79-IV-0010 | T-00018-0246 | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution | CPX02 - Power transformer | To be completed | Yes | Accepted with Punch | C:0/1 | Yes | Open + RFI Submitted
PS5-79-IV-0011 | T-00018-0247 | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution | CPX02 - Power transformer | To be completed | Yes | Accepted with Punch | C:0/1 | Yes | Open + RFI Submitted
PS5-79-IV-0012 | T-00018-0248 | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution | CPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-87-IRF-0001 | T-00018-0249 | E | PS5-53-01 - Utility Water / Storage Tank | CPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-87-IRF-0002 | T-00018-0250 | E | PS5-71-04 - CFO Storage Tank | CPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-87-IRF-0003 | T-00018-0251 | E | PS5-71-12 - CFO Service Tank | CPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-87-IRF-0004 | T-00018-0252 | E | PS5-71-15 - Diesel Fuel Storage Tank | CPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IV-0005A | T-00018-0294 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IV-0005B | T-00018-0295 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0003 | T-00019-0035 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX05 - LV switchboard | To be completed | Yes | Open | A:0/2, C:0/1 | Yes | Open + RFI Submitted
PS5-61-IK-0006 | T-00019-0036 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX05 - LV switchboard | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-DM-3100A-CH01 | T-00022-3316 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100A-CH02 | T-00022-3317 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100A-CH03 | T-00022-3318 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100A-CH04 | T-00022-3319 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100A-CH05 | T-00022-3320 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100A-CH06 | T-00022-3321 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100B-CH01 | T-00022-3322 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100B-CH02 | T-00022-3323 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100B-CH03 | T-00022-3324 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100B-CH04 | T-00022-3325 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100B-CH05 | T-00022-3326 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100B-CH06 | T-00022-3327 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100C-CH01 | T-00022-3328 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100C-CH02 | T-00022-3329 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100C-CH03 | T-00022-3330 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100C-CH04 | T-00022-3331 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100C-CH05 | T-00022-3332 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100C-CH06 | T-00022-3333 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-60-IJ-0001A-CH04 | T-00022-3334 | E | PS5-60-01 - Power Generation Package A | CPX08 - HV Power Cable | Closed | Yes | Accepted | - |  | Complete
PS5-60-IJ-0001B-CH04 | T-00022-3335 | E | PS5-60-04 - Power Generation Package B | CPX08 - HV Power Cable | Closed | Yes | Accepted | - |  | Complete
PS5-60-IJ-0001C-CH04 | T-00022-3336 | E | PS5-60-07 - Power Generation Package C | CPX08 - HV Power Cable | Closed | Yes | Accepted | - |  | Complete
PS5-60-IJ-0001D-CH04 | T-00022-3337 | E | PS5-60-10 - Power Generation Package D | CPX08 - HV Power Cable | Closed | Yes | Accepted | - |  | Complete
PS5-60-IJ-0001E-CH04 | T-00022-3338 | E | PS5-60-13 - Power Generation Package E | CPX08 - HV Power Cable | Closed | Yes | Accepted | - |  | Complete
PS5-60-IJ-0001F-CH04 | T-00022-3339 | E | PS5-60-16 - Power Generation Package F | CPX08 - HV Power Cable | Closed | Yes | Accepted | - |  | Complete
PS5-60-IJ-0001G-CH04 | T-00022-3340 | E | PS5-60-19 - Power Generation Package G | CPX08 - HV Power Cable | Closed | Yes | Accepted | - |  | Complete
PS5-61-IDH-3100A-CH01 | T-00022-3341 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH02 | T-00022-3342 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH03 | T-00022-3343 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH04 | T-00022-3344 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH05 | T-00022-3345 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH06 | T-00022-3346 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH07 | T-00022-3347 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH08 | T-00022-3348 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH09 | T-00022-3349 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH10 | T-00022-3350 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH11 | T-00022-3351 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH12 | T-00022-3352 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH01 | T-00022-3353 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH02 | T-00022-3354 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH03 | T-00022-3355 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH04 | T-00022-3356 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH05 | T-00022-3357 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH06 | T-00022-3358 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH07 | T-00022-3359 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH08 | T-00022-3360 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH09 | T-00022-3361 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH10 | T-00022-3362 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH11 | T-00022-3363 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH12 | T-00022-3364 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH01 | T-00022-3365 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH02 | T-00022-3366 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH03 | T-00022-3367 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH04 | T-00022-3368 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH05 | T-00022-3369 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH06 | T-00022-3370 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH07 | T-00022-3371 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH08 | T-00022-3372 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH09 | T-00022-3373 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH10 | T-00022-3374 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH11 | T-00022-3375 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH12 | T-00022-3376 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH01 | T-00022-3377 | E | PS5-60-01 - Power Generation Package A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH02 | T-00022-3378 | E | PS5-60-01 - Power Generation Package A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH03 | T-00022-3379 | E | PS5-60-01 - Power Generation Package A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH04 | T-00022-3380 | E | PS5-60-04 - Power Generation Package B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH05 | T-00022-3381 | E | PS5-60-04 - Power Generation Package B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH06 | T-00022-3382 | E | PS5-60-04 - Power Generation Package B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH07 | T-00022-3383 | E | PS5-60-07 - Power Generation Package C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH08 | T-00022-3384 | E | PS5-60-07 - Power Generation Package C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH09 | T-00022-3385 | E | PS5-60-07 - Power Generation Package C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH10 | T-00022-3386 | E | PS5-60-10 - Power Generation Package D | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH11 | T-00022-3387 | E | PS5-60-10 - Power Generation Package D | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH12 | T-00022-3388 | E | PS5-60-10 - Power Generation Package D | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH13 | T-00022-3389 | E | PS5-60-13 - Power Generation Package E | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH14 | T-00022-3390 | E | PS5-60-13 - Power Generation Package E | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH15 | T-00022-3391 | E | PS5-60-13 - Power Generation Package E | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH16 | T-00022-3392 | E | PS5-60-16 - Power Generation Package F | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH17 | T-00022-3393 | E | PS5-60-16 - Power Generation Package F | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH18 | T-00022-3394 | E | PS5-60-16 - Power Generation Package F | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH19 | T-00022-3395 | E | PS5-60-19 - Power Generation Package G | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH20 | T-00022-3396 | E | PS5-60-19 - Power Generation Package G | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH21 | T-00022-3397 | E | PS5-60-19 - Power Generation Package G | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0010-CH01 | T-00022-3398 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-IJ-0010-CH02 | T-00022-3399 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-IJ-0010-CH03 | T-00022-3400 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-IJ-0011-CH01 | T-00022-3401 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-IJ-0011-CH02 | T-00022-3402 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-IJ-0011-CH03 | T-00022-3403 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-ISR-0101-CH01 | T-00022-3404 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-ISR-0101-CH02 | T-00022-3405 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-ISR-0101-CH03 | T-00022-3406 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-ISR-0102-CH01 | T-00022-3407 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-ISR-0102-CH02 | T-00022-3408 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-ISR-0102-CH03 | T-00022-3409 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-IU-0001A-CH01 | T-00022-3410 | E | PS5-60-01 - Power Generation Package A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001A-CH02 | T-00022-3411 | E | PS5-60-01 - Power Generation Package A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001A-CH03 | T-00022-3412 | E | PS5-60-01 - Power Generation Package A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001B-CH01 | T-00022-3413 | E | PS5-60-04 - Power Generation Package B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001B-CH02 | T-00022-3414 | E | PS5-60-04 - Power Generation Package B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001B-CH03 | T-00022-3415 | E | PS5-60-04 - Power Generation Package B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001C-CH01 | T-00022-3416 | E | PS5-60-07 - Power Generation Package C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001C-CH02 | T-00022-3417 | E | PS5-60-07 - Power Generation Package C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001C-CH03 | T-00022-3418 | E | PS5-60-07 - Power Generation Package C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001D-CH01 | T-00022-3419 | E | PS5-60-10 - Power Generation Package D | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001D-CH02 | T-00022-3420 | E | PS5-60-10 - Power Generation Package D | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001D-CH03 | T-00022-3421 | E | PS5-60-10 - Power Generation Package D | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001E-CH01 | T-00022-3422 | E | PS5-60-13 - Power Generation Package E | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001E-CH02 | T-00022-3423 | E | PS5-60-13 - Power Generation Package E | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001E-CH03 | T-00022-3424 | E | PS5-60-13 - Power Generation Package E | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001F-CH01 | T-00022-3425 | E | PS5-60-16 - Power Generation Package F | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001F-CH02 | T-00022-3426 | E | PS5-60-16 - Power Generation Package F | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001F-CH03 | T-00022-3427 | E | PS5-60-16 - Power Generation Package F | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001G-CH01 | T-00022-3428 | E | PS5-60-19 - Power Generation Package G | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001G-CH02 | T-00022-3429 | E | PS5-60-19 - Power Generation Package G | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001G-CH03 | T-00022-3430 | E | PS5-60-19 - Power Generation Package G | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0010-CH01 | T-00022-3431 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-IU-0010-CH02 | T-00022-3432 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-IU-0010-CH03 | T-00022-3433 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-IU-0011-CH01 | T-00022-3434 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-IU-0011-CH02 | T-00022-3435 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-IU-0011-CH03 | T-00022-3436 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-IU-3100A-CH01 | T-00022-3437 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100A-CH02 | T-00022-3438 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100A-CH03 | T-00022-3439 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100A-CH04 | T-00022-3440 | E | PS5-25-02 - Crude Oil Export Pump A | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100B-CH01 | T-00022-3441 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100B-CH02 | T-00022-3442 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100B-CH03 | T-00022-3443 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100B-CH04 | T-00022-3444 | E | PS5-25-03 - Crude Oil Export Pump B | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100C-CH01 | T-00022-3445 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100C-CH02 | T-00022-3446 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100C-CH03 | T-00022-3447 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100C-CH04 | T-00022-3448 | E | PS5-25-04 - Crude Oil Export Pump C | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IV-0001A-CH01 | T-00022-3449 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IV-0001A-CH02 | T-00022-3450 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IV-0001A-CH03 | T-00022-3451 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IV-0001B-CH01 | T-00022-3452 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IV-0001B-CH02 | T-00022-3453 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IV-0001B-CH03 | T-00022-3454 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IV-0002A-CH01 | T-00022-3455 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0002A-CH02 | T-00022-3456 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | A:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0002A-CH03 | T-00022-3457 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | C:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0002B-CH01 | T-00022-3458 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0002B-CH02 | T-00022-3459 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0002B-CH03 | T-00022-3460 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0005A-CH01 | T-00022-3461 | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building ( | CPX08 - HV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IV-0005A-CH02 | T-00022-3462 | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building ( | CPX08 - HV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IV-0005A-CH03 | T-00022-3463 | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building ( | CPX08 - HV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IV-0005B-CH01 | T-00022-3464 | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building ( | CPX08 - HV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IV-0005B-CH02 | T-00022-3465 | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building ( | CPX08 - HV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IV-0005B-CH03 | T-00022-3466 | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building ( | CPX08 - HV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IV-0007A-CH01 | T-00022-3467 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0007A-CH02 | T-00022-3468 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0007A-CH03 | T-00022-3469 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0007B-CH01 | T-00022-3470 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0007B-CH02 | T-00022-3471 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0007B-CH03 | T-00022-3472 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX08 - HV Power Cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-NER-0010-CH01 | T-00022-3473 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-61-NER-0011-CH01 | T-00022-3474 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-63-IV-0010-CH01 | T-00022-3475 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-63-IV-0010-CH02 | T-00022-3476 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-63-IV-0010-CH03 | T-00022-3477 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-63-IV-0011-CH01 | T-00022-3478 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-63-IV-0011-CH02 | T-00022-3479 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-63-IV-0011-CH03 | T-00022-3480 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-63-NER-0010-CH01 | T-00022-3481 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX08 - HV Power Cable | To be completed | Yes | Hold by EACOP | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-63-NER-0011-CH01 | T-00022-3482 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX08 - HV Power Cable | To be completed | Yes | Hold by EACOP | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-79-BH-0001-CH01 | T-00022-3483 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-79-BH-0001-CH02 | T-00022-3484 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-79-BH-0001-CH03 | T-00022-3485 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-79-BH-0002-CH01 | T-00022-3486 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-79-BH-0002-CH02 | T-00022-3487 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-79-BH-0002-CH03 | T-00022-3488 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | CPX08 - HV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-62-IE-0001-CL02 | T-00023-10060 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL03 | T-00023-10061 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL05 | T-00023-10062 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL06 | T-00023-10063 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL07 | T-00023-10064 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL51 | T-00023-10065 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL52 | T-00023-10066 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL53 | T-00023-10067 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL54 | T-00023-10068 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL55 | T-00023-10069 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL56 | T-00023-10070 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL57 | T-00023-10071 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL58 | T-00023-10072 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL59 | T-00023-10073 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL02 | T-00023-10074 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL03 | T-00023-10075 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL04 | T-00023-10076 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL05 | T-00023-10077 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL06 | T-00023-10078 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL07 | T-00023-10079 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL52 | T-00023-10080 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL53 | T-00023-10081 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL54 | T-00023-10082 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL55 | T-00023-10083 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL56 | T-00023-10084 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL57 | T-00023-10085 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL58 | T-00023-10086 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL59 | T-00023-10087 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL60 | T-00023-10088 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-06-GB-0003-CG01 | T-00023-10535 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002A-CG01 | T-00023-10536 | E | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002B-CG01 | T-00023-10537 | E | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002C-CG01 | T-00023-10538 | E | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002D-CG01 | T-00023-10539 | E | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002E-CG01 | T-00023-10540 | E | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002F-CG01 | T-00023-10541 | E | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002G-CG01 | T-00023-10542 | E | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-BE-0001-CG01 | T-00023-10584 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-06-IG-0004A-CG01 | T-00023-10585 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-06-IG-0004B-CG01 | T-00023-10586 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-DM-3100A-CG01 | T-00023-10587 | E | PS5-25-02 - Crude Oil Export Pump A | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-25-DM-3100A-CG02 | T-00023-10588 | E | PS5-25-02 - Crude Oil Export Pump A | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-25-DM-3100B-CG01 | T-00023-10589 | E | PS5-25-03 - Crude Oil Export Pump B | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-25-DM-3100B-CG02 | T-00023-10590 | E | PS5-25-03 - Crude Oil Export Pump B | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-25-DM-3100C-CG01 | T-00023-10591 | E | PS5-25-04 - Crude Oil Export Pump C | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-25-DM-3100C-CG02 | T-00023-10592 | E | PS5-25-04 - Crude Oil Export Pump C | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-60-IH-0001A-CG01 | T-00023-10593 | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001B-CG01 | T-00023-10594 | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001C-CG01 | T-00023-10595 | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001D-CG01 | T-00023-10596 | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001E-CG01 | T-00023-10597 | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001F-CG01 | T-00023-10598 | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001G-CG01 | T-00023-10599 | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0002-CG01 | T-00023-10600 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-60-IH-0002-CG02 | T-00023-10601 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-61-IH-0004-CG01 | T-00023-10602 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CG02 | T-00023-10603 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CG03 | T-00023-10604 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CG04 | T-00023-10605 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0003-CG07 | T-00023-10616 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-28-DM-31100-CL01 | T-00023-10886 | E | PS5-28-10 - Oil Skimmer Package | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0007A-CL02 | T-00023-10887 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPX09 - LV Power Cable | To be completed | Yes | Other | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0007A-CL03 | T-00023-10888 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPX09 - LV Power Cable | To be completed | Yes | Other | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0007B-CL02 | T-00023-10889 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPX09 - LV Power Cable | To be completed | Yes | Other | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0007B-CL03 | T-00023-10890 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPX09 - LV Power Cable | To be completed | Yes | Other | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0007C-CL02 | T-00023-10891 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0007C-CL03 | T-00023-10892 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0007D-CL02 | T-00023-10893 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0007D-CL03 | T-00023-10894 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0007E-CL02 | T-00023-10895 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0007E-CL03 | T-00023-10896 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0007F-CL02 | T-00023-10897 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0007F-CL03 | T-00023-10898 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0007G-CL02 | T-00023-10899 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0007G-CL03 | T-00023-10900 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-ISO-62800A-CL01 | T-00023-10901 | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | B:0/2 | Yes | Open + RFI Submitted
PS5-60-ISO-62800C-CL01 | T-00023-10902 | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-ISO-62800E-CL01 | T-00023-10903 | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-ISO-62800G-CL01 | T-00023-10904 | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85CP-1201-CS01 | T-00023-10965 | E | PS5-08-85 - Access Control, POB & e-Mustering | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85CP-1202-CS01 | T-00023-10966 | E | PS5-08-85 - Access Control, POB & e-Mustering | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85CP-1601-CS01 | T-00023-10967 | E | PS5-08-85 - Access Control, POB & e-Mustering | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-BE-0001-CL12 | T-00023-11058 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-09-DM-84500A-CL01 | T-00023-11059 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-DM-84500B-CL01 | T-00023-11060 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL01 | T-00023-11250 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL02 | T-00023-11251 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL03 | T-00023-11252 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL04 | T-00023-11253 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL05 | T-00023-11254 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL06 | T-00023-11255 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL07 | T-00023-11256 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL08 | T-00023-11257 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL09 | T-00023-11258 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL10 | T-00023-11259 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL11 | T-00023-11260 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL12 | T-00023-11261 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL01 | T-00023-11262 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | Started (not Completed) | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL02 | T-00023-11263 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL03 | T-00023-11264 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL04 | T-00023-11265 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL05 | T-00023-11266 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL06 | T-00023-11267 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL07 | T-00023-11268 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL08 | T-00023-11269 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL09 | T-00023-11270 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL10 | T-00023-11271 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL11 | T-00023-11272 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL12 | T-00023-11273 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0005-CL01 | T-00023-11274 | E | PS5-71-19 - Diesel Separator Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0005-CL02 | T-00023-11275 | E | PS5-71-19 - Diesel Separator Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0005-CL03 | T-00023-11276 | E | PS5-71-19 - Diesel Separator Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0005-CL04 | T-00023-11277 | E | PS5-71-19 - Diesel Separator Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-BE-0001-CL01 | T-00023-4695 | E | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Open + RFI Submitted
PS5-01-FCV-0003A-CL01 | T-00023-4696 | E | PS5-01-02 - Fire Water Pump A | CPX09 - LV Power Cable | Started (not Completed) | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-01-FCV-0003B-CL01 | T-00023-4697 | E | PS5-01-03 - Fire Water Pump B | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-01-FCV-0004A-CL01 | T-00023-4698 | E | PS5-01-01 - Fire Water Jockey Pump A/B | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:2/4 | Yes | Open + RFI Submitted
PS5-01-FCV-0004B-CL01 | T-00023-4699 | E | PS5-01-01 - Fire Water Jockey Pump A/B | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:2/4 | Yes | Open + RFI Submitted
PS5-01-IG-0001-CL01 | T-00023-4710 | E | PS5-01-10 - Water Mist Package | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-LB-0004-CL01 | T-00023-4711 | E | PS5-01-11 - Inergen for Power Gen Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-LB-0004-CL02 | T-00023-4712 | E | PS5-01-11 - Inergen for Power Gen Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-LB-0004-CL03 | T-00023-4713 | E | PS5-01-11 - Inergen for Power Gen Building | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-01-MOV-8701-CL01 | T-00023-4714 | E | PS5-01-05 - Foam Skid | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-SEA-0002-CL01 | T-00023-4724 | E | PS5-03-22 - FZ-G1 - Guard House | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-SEA-0003-CL01 | T-00023-4725 | E | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-BE-0001-CL01 | T-00023-4727 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-05-BE-0001-CL02 | T-00023-4728 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-05-BE-0001-CL03 | T-00023-4729 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-05-BE-0001-CL04 | T-00023-4730 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-05-BE-0001-CL05 | T-00023-4731 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-05-BE-0001-CL06 | T-00023-4732 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-05-BE-0001-CL07 | T-00023-4733 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-05-BE-0001-CL08 | T-00023-4734 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-05-BE-0001-CL09 | T-00023-4735 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-05-BE-0001-CL10 | T-00023-4736 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-05-BE-0001-CL11 | T-00023-4737 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CL01 | T-00023-4738 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-IE-8100-CL02 | T-00023-4739 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-IG-0009-CL01 | T-00023-4742 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IG-0009-CL02 | T-00023-4743 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-05-IG-0025-CL01 | T-00023-4744 | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-05-IG-0026-CL01 | T-00023-4745 | E | PS5-62-07 - CRO Generator Electrical Building Emergency Ligh | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-06-GB-0003-CL01 | T-00023-4746 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX09 - LV Power Cable | To be completed | Yes | Open | B:1/2 | Yes | Open + RFI Submitted
PS5-06-GB-0003-CL02 | T-00023-4747 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX09 - LV Power Cable | To be completed | Yes | Open | B:0/2 | Yes | Open + RFI Submitted
PS5-06-GB-0003-CL03 | T-00023-4748 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX09 - LV Power Cable | To be completed | Yes | Open | B:0/2 | Yes | Open + RFI Submitted
PS5-06-GB-0003-CL04 | T-00023-4749 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX09 - LV Power Cable | To be completed | Yes | Open | B:0/2 | Yes | Open + RFI Submitted
PS5-06-GB-0003-CL05 | T-00023-4750 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX09 - LV Power Cable | To be completed | Yes | Open | B:0/2 | Yes | Open + RFI Submitted
PS5-06-GB-0003-CL06 | T-00023-4751 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX09 - LV Power Cable | To be completed | Yes | Open | B:0/2 | Yes | Open + RFI Submitted
PS5-06-GU-0003A-CL01 | T-00023-4752 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX09 - LV Power Cable | To be completed | Yes | Open | B:0/2 | Yes | Open + RFI Submitted
PS5-06-GU-0003B-CL01 | T-00023-4753 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX09 - LV Power Cable | To be completed | Yes | Open | B:0/2 | Yes | Open + RFI Submitted
PS5-06-GU-0003C-CL01 | T-00023-4754 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX09 - LV Power Cable | To be completed | Yes | Open | B:0/2 | Yes | Open + RFI Submitted
PS5-06-IG-0004A-CL01 | T-00023-4756 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX09 - LV Power Cable | To be completed | Yes | Open | B:0/2 | Yes | Open + RFI Submitted
PS5-06-IG-0004A-CL02 | T-00023-4757 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX09 - LV Power Cable | To be completed | Yes | Open | B:0/2 | Yes | Open + RFI Submitted
PS5-06-IG-0004A-CL03 | T-00023-4758 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX09 - LV Power Cable | To be completed | Yes | Open | B:0/2 | Yes | Open + RFI Submitted
PS5-06-IG-0004A-CL04 | T-00023-4759 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX09 - LV Power Cable | To be completed | Yes | Open | B:0/2 | Yes | Open + RFI Submitted
PS5-06-IG-0004B-CL01 | T-00023-4761 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX09 - LV Power Cable | To be completed | Yes | Open | B:0/2 | Yes | Open + RFI Submitted
PS5-06-IG-0004B-CL02 | T-00023-4762 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX09 - LV Power Cable | To be completed | Yes | Open | B:0/2 | Yes | Open + RFI Submitted
PS5-06-IG-0004B-CL03 | T-00023-4763 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX09 - LV Power Cable | To be completed | Yes | Open | B:0/2 | Yes | Open + RFI Submitted
PS5-06-IG-0004B-CL04 | T-00023-4764 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX09 - LV Power Cable | To be completed | Yes | Open | B:0/2 | Yes | Open + RFI Submitted
PS5-08-11CB-1501-CL01 | T-00023-4808 | E | PS5-08-11 - Corporate LAN (SIE) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-11CB-1901-CL01 | T-00023-4809 | E | PS5-08-11 - Corporate LAN (SIE) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-11CB-1901-CL02 | T-00023-4810 | E | PS5-08-11 - Corporate LAN (SIE) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-11CB-1901-CL03 | T-00023-4811 | E | PS5-08-11 - Corporate LAN (SIE) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-0008-CL01 | T-00023-4878 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-0008-CL02 | T-00023-4879 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-DM-3100A-CL01 | T-00023-4882 | E | PS5-25-02 - Crude Oil Export Pump A | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-DM-3100A-CL02 | T-00023-4883 | E | PS5-25-02 - Crude Oil Export Pump A | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-DM-3100B-CL01 | T-00023-4886 | E | PS5-25-03 - Crude Oil Export Pump B | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-DM-3100B-CL02 | T-00023-4887 | E | PS5-25-03 - Crude Oil Export Pump B | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-DM-3100C-CL01 | T-00023-4890 | E | PS5-25-04 - Crude Oil Export Pump C | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-DM-3100C-CL02 | T-00023-4891 | E | PS5-25-04 - Crude Oil Export Pump C | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-ESDV-0021-CL01 | T-00023-4904 | E | PS5-25-01 - Export Pipeline Pig Receiver | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-25-ESDV-0023-CL01 | T-00023-4905 | E | PS5-25-07 - Export Pipeline Pig Launcher | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-25-FCV-0003A-CL01 | T-00023-4906 | E | PS5-25-02 - Crude Oil Export Pump A | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-25-FCV-0003B-CL01 | T-00023-4907 | E | PS5-25-03 - Crude Oil Export Pump B | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-25-FCV-0003C-CL01 | T-00023-4908 | E | PS5-25-04 - Crude Oil Export Pump C | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-25-FCV-0004-CL01 | T-00023-4909 | E | PS5-25-06 - Crude Oil Export Pumps Discharge | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MOV-0001-CL01 | T-00023-4918 | E | PS5-25-01 - Export Pipeline Pig Receiver | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-MOV-0002-CL01 | T-00023-4919 | E | PS5-25-01 - Export Pipeline Pig Receiver | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-MOV-0003-CL01 | T-00023-4920 | E | PS5-25-01 - Export Pipeline Pig Receiver | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-MOV-0008-CL01 | T-00023-4921 | E | PS5-25-07 - Export Pipeline Pig Launcher | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Open + RFI Submitted
PS5-25-MOV-0011-CL01 | T-00023-4922 | E | PS5-25-07 - Export Pipeline Pig Launcher | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-MOV-0012-CL01 | T-00023-4923 | E | PS5-25-07 - Export Pipeline Pig Launcher | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-MOV-0025-CL01 | T-00023-4924 | E | PS5-25-01 - Export Pipeline Pig Receiver | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Open + RFI Submitted
PS5-25-MOV-0026-CL01 | T-00023-4925 | E | PS5-25-01 - Export Pipeline Pig Receiver | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Open + RFI Submitted
PS5-25-MOV-0027-CL01 | T-00023-4926 | E | PS5-25-06 - Crude Oil Export Pumps Discharge | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-MOV-0028-CL01 | T-00023-4927 | E | PS5-25-07 - Export Pipeline Pig Launcher | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-SDV-0022-CL01 | T-00023-4928 | E | PS5-25-01 - Export Pipeline Pig Receiver | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-SDV-0035A-CL01 | T-00023-4929 | E | PS5-25-02 - Crude Oil Export Pump A | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-SDV-0035B-CL01 | T-00023-4930 | E | PS5-25-03 - Crude Oil Export Pump B | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-SDV-0035C-CL01 | T-00023-4931 | E | PS5-25-04 - Crude Oil Export Pump C | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-SDV-0036A-CL01 | T-00023-4932 | E | PS5-25-02 - Crude Oil Export Pump A | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-SDV-0036B-CL01 | T-00023-4933 | E | PS5-25-03 - Crude Oil Export Pump B | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-SDV-0036C-CL01 | T-00023-4934 | E | PS5-25-04 - Crude Oil Export Pump C | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-SDV-0046-CL01 | T-00023-4935 | E | PS5-25-05 - Crude Oil Export Pumps Bypass | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Open + RFI Submitted
PS5-25-SDV-0052-CL01 | T-00023-4936 | E | PS5-25-07 - Export Pipeline Pig Launcher | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-SDV-0054A-CL01 | T-00023-4937 | E | PS5-25-02 - Crude Oil Export Pump A | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-25-SDV-0054B-CL01 | T-00023-4938 | E | PS5-25-03 - Crude Oil Export Pump B | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-25-SDV-0054C-CL01 | T-00023-4939 | E | PS5-25-04 - Crude Oil Export Pump C | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-25-XV-0053-CL01 | T-00023-4941 | E | PS5-25-05 - Crude Oil Export Pumps Bypass | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-25-XV-0070-CL01 | T-00023-4942 | E | PS5-25-05 - Crude Oil Export Pumps Bypass | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-BE-0002A-CL02 | T-00023-4944 | E | PS5-28-17 - Reinjection Pump | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-28-BE-0002B-CL02 | T-00023-4946 | E | PS5-28-17 - Reinjection Pump | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-28-HE-2100-CL02 | T-00023-4962 | E | PS5-28-03 - Closed Drain Drum and Pump 01 | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-28-HE-2200-CL02 | T-00023-4964 | E | PS5-28-04 - Closed Drain Drum and Pump 02 | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-28-LB-8200-CL01 | T-00023-4966 | E | PS5-28-11 - Open Drain Interceptor | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-28-SDV-0045-CL01 | T-00023-4967 | E | PS5-28-17 - Reinjection Pump | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SDV-0053A-CL01 | T-00023-4968 | E | PS5-28-13 - Seal Oil Drain Drum & Pump A | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-28-SDV-0053B-CL01 | T-00023-4969 | E | PS5-28-14 - Seal Oil Drain Drum & Pump B | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-28-SDV-0053C-CL01 | T-00023-4970 | E | PS5-28-15 - Seal Oil Drain Drum & Pump C | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-60-BE-0001-CL01 | T-00023-4978 | E | PS5-60-27 - Compressed Air Starting Skid | CPX09 - LV Power Cable | To be completed | Yes | Other | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0001-CL02 | T-00023-4979 | E | PS5-60-27 - Compressed Air Starting Skid | CPX09 - LV Power Cable | To be completed | Yes | Other | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0001-CL04 | T-00023-4981 | E | PS5-60-27 - Compressed Air Starting Skid | CPX09 - LV Power Cable | To be completed | Yes | Other | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0002-CL01 | T-00023-4982 | E | PS5-60-26 - Instrument Air Compressor Skid | CPX09 - LV Power Cable | To be completed | Yes | Other | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0002-CL02 | T-00023-4983 | E | PS5-60-26 - Instrument Air Compressor Skid | CPX09 - LV Power Cable | To be completed | Yes | Other | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0002-CL03 | T-00023-4984 | E | PS5-60-26 - Instrument Air Compressor Skid | CPX09 - LV Power Cable | To be completed | Yes | Other | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0002-CL05 | T-00023-4986 | E | PS5-60-26 - Instrument Air Compressor Skid | CPX09 - LV Power Cable | To be completed | Yes | Other | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0003A-CL01 | T-00023-4987 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-BE-0003B-CL01 | T-00023-4988 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-BE-0003C-CL01 | T-00023-4989 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0003D-CL01 | T-00023-4990 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0003E-CL01 | T-00023-4991 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0003F-CL01 | T-00023-4992 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0003G-CL01 | T-00023-4993 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0004A-CL01 | T-00023-4994 | E | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0004B-CL01 | T-00023-4995 | E | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0004C-CL01 | T-00023-4996 | E | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0004D-CL01 | T-00023-4997 | E | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0004E-CL01 | T-00023-4998 | E | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0004F-CL01 | T-00023-4999 | E | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0004G-CL01 | T-00023-5000 | E | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0005A-CL01 | T-00023-5001 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0005B-CL01 | T-00023-5002 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:1/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0005C-CL01 | T-00023-5003 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0005D-CL01 | T-00023-5004 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-BE-0005E-CL01 | T-00023-5005 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0005F-CL01 | T-00023-5006 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0005G-CL01 | T-00023-5007 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0011A-CL01 | T-00023-5008 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0011A-CL02 | T-00023-5009 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0011A-CL03 | T-00023-5010 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:1/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0011A-CL04 | T-00023-5011 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0011A-CL05 | T-00023-5012 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:1/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0011A-CL06 | T-00023-5013 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:1/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0011B-CL01 | T-00023-5014 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:1/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0011B-CL02 | T-00023-5015 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:1/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0011B-CL03 | T-00023-5016 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:1/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0011B-CL04 | T-00023-5017 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:1/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0011B-CL05 | T-00023-5018 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:1/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0011B-CL06 | T-00023-5019 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:1/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0012A-CL01 | T-00023-5020 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:1/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0012A-CL02 | T-00023-5021 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:1/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0012A-CL03 | T-00023-5022 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:1/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0012A-CL04 | T-00023-5023 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:1/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0012A-CL05 | T-00023-5024 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:1/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0012A-CL06 | T-00023-5025 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:1/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0012B-CL01 | T-00023-5026 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:1/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0012B-CL02 | T-00023-5027 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:1/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0012B-CL03 | T-00023-5028 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:1/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0012B-CL04 | T-00023-5029 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:1/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0012B-CL05 | T-00023-5030 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:1/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0012B-CL06 | T-00023-5031 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-BE-0013A-CL01 | T-00023-5032 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0013A-CL02 | T-00023-5033 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0013A-CL03 | T-00023-5034 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0013A-CL04 | T-00023-5035 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0013A-CL05 | T-00023-5036 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0013A-CL06 | T-00023-5037 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0013B-CL01 | T-00023-5038 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0013B-CL02 | T-00023-5039 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0013B-CL03 | T-00023-5040 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0013B-CL04 | T-00023-5041 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0013B-CL05 | T-00023-5042 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0013B-CL06 | T-00023-5043 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0014A-CL01 | T-00023-5044 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0014A-CL02 | T-00023-5045 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0014A-CL03 | T-00023-5046 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0014A-CL04 | T-00023-5047 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0014A-CL05 | T-00023-5048 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0014A-CL06 | T-00023-5049 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0014B-CL01 | T-00023-5050 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0014B-CL02 | T-00023-5051 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0014B-CL03 | T-00023-5052 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0014B-CL04 | T-00023-5053 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0014B-CL05 | T-00023-5054 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0014B-CL06 | T-00023-5055 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0015A-CL01 | T-00023-5056 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0015A-CL02 | T-00023-5057 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0015A-CL03 | T-00023-5058 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0015A-CL04 | T-00023-5059 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0015A-CL05 | T-00023-5060 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0015A-CL06 | T-00023-5061 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0015B-CL01 | T-00023-5062 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0015B-CL02 | T-00023-5063 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0015B-CL03 | T-00023-5064 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0015B-CL04 | T-00023-5065 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0015B-CL05 | T-00023-5066 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0015B-CL06 | T-00023-5067 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0016A-CL01 | T-00023-5068 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0016A-CL02 | T-00023-5069 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0016A-CL03 | T-00023-5070 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0016A-CL04 | T-00023-5071 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0016A-CL05 | T-00023-5072 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0016A-CL06 | T-00023-5073 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0016B-CL01 | T-00023-5074 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0016B-CL02 | T-00023-5075 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0016B-CL03 | T-00023-5076 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0016B-CL04 | T-00023-5077 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0016B-CL05 | T-00023-5078 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0016B-CL06 | T-00023-5079 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0017A-CL01 | T-00023-5080 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0017A-CL02 | T-00023-5081 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0017A-CL03 | T-00023-5082 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0017A-CL04 | T-00023-5083 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0017A-CL05 | T-00023-5084 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0017A-CL06 | T-00023-5085 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0017B-CL01 | T-00023-5086 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0017B-CL02 | T-00023-5087 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0017B-CL03 | T-00023-5088 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0017B-CL04 | T-00023-5089 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0017B-CL05 | T-00023-5090 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0017B-CL06 | T-00023-5091 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0021A-CL01 | T-00023-5092 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0021B-CL01 | T-00023-5093 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0024A-CL01 | T-00023-5094 | E | PS5-60-35 - Injector Tip Cooling Module A | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0024A-CL02 | T-00023-5095 | E | PS5-60-35 - Injector Tip Cooling Module A | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0024B-CL01 | T-00023-5096 | E | PS5-60-36 - Injector Tip Cooling Module B | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0024B-CL02 | T-00023-5097 | E | PS5-60-36 - Injector Tip Cooling Module B | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0024C-CL01 | T-00023-5098 | E | PS5-60-37 - Injector Tip Cooling Module C | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0024C-CL02 | T-00023-5099 | E | PS5-60-37 - Injector Tip Cooling Module C | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0024D-CL01 | T-00023-5100 | E | PS5-60-38 - Injector Tip Cooling Module D | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0024D-CL02 | T-00023-5101 | E | PS5-60-38 - Injector Tip Cooling Module D | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0024E-CL01 | T-00023-5102 | E | PS5-60-39 - Injector Tip Cooling Module E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0024E-CL02 | T-00023-5103 | E | PS5-60-39 - Injector Tip Cooling Module E | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0024F-CL01 | T-00023-5104 | E | PS5-60-40 - Injector Tip Cooling Module F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0024F-CL02 | T-00023-5105 | E | PS5-60-40 - Injector Tip Cooling Module F | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0024G-CL01 | T-00023-5106 | E | PS5-60-41 - Injector Tip Cooling Module G | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0024G-CL02 | T-00023-5107 | E | PS5-60-41 - Injector Tip Cooling Module G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0025A-CL01 | T-00023-5108 | E | PS5-60-35 - Injector Tip Cooling Module A | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-BE-0025B-CL01 | T-00023-5109 | E | PS5-60-36 - Injector Tip Cooling Module B | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-BE-0025C-CL01 | T-00023-5110 | E | PS5-60-37 - Injector Tip Cooling Module C | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0025D-CL01 | T-00023-5111 | E | PS5-60-38 - Injector Tip Cooling Module D | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0025E-CL01 | T-00023-5112 | E | PS5-60-39 - Injector Tip Cooling Module E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0025F-CL01 | T-00023-5113 | E | PS5-60-40 - Injector Tip Cooling Module F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0025G-CL01 | T-00023-5114 | E | PS5-60-41 - Injector Tip Cooling Module G | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0026A-CL01 | T-00023-5115 | E | PS5-60-70 - Engine A Cooling system | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-BE-0026A-CL02 | T-00023-5116 | E | PS5-60-70 - Engine A Cooling system | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-BE-0026B-CL01 | T-00023-5117 | E | PS5-60-71 - Engine B Cooling system | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-BE-0026B-CL02 | T-00023-5118 | E | PS5-60-71 - Engine B Cooling system | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-BE-0026C-CL01 | T-00023-5119 | E | PS5-60-72 - Engine C Cooling system | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0026C-CL02 | T-00023-5120 | E | PS5-60-72 - Engine C Cooling system | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-BE-0026D-CL01 | T-00023-5121 | E | PS5-60-73 - Engine D Cooling system | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0026D-CL02 | T-00023-5122 | E | PS5-60-73 - Engine D Cooling system | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0026E-CL01 | T-00023-5123 | E | PS5-60-74 - Engine E Cooling system | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0026E-CL02 | T-00023-5124 | E | PS5-60-74 - Engine E Cooling system | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0026F-CL01 | T-00023-5125 | E | PS5-60-75 - Engine F Cooling system | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0026F-CL02 | T-00023-5126 | E | PS5-60-75 - Engine F Cooling system | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0026G-CL01 | T-00023-5127 | E | PS5-60-76 - Engine G Cooling system | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0026G-CL02 | T-00023-5128 | E | PS5-60-76 - Engine G Cooling system | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-BI-0005A-CL01 | T-00023-5129 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0005B-CL01 | T-00023-5130 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0005C-CL01 | T-00023-5131 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0005D-CL01 | T-00023-5132 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0005E-CL01 | T-00023-5133 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0005F-CL01 | T-00023-5134 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0005G-CL01 | T-00023-5135 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0015A-CL01 | T-00023-5136 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0015A-CL02 | T-00023-5137 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-BI-0015A-CL03 | T-00023-5138 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-BI-0015B-CL01 | T-00023-5139 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0015B-CL02 | T-00023-5140 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-BI-0015B-CL03 | T-00023-5141 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-BI-0015C-CL01 | T-00023-5142 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0015C-CL02 | T-00023-5143 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0015C-CL03 | T-00023-5144 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0015D-CL01 | T-00023-5145 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0015D-CL02 | T-00023-5146 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-BI-0015D-CL03 | T-00023-5147 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-BI-0015E-CL01 | T-00023-5148 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0015E-CL02 | T-00023-5149 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0015E-CL03 | T-00023-5150 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0015F-CL01 | T-00023-5151 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0015F-CL02 | T-00023-5152 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0015F-CL03 | T-00023-5153 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0015G-CL01 | T-00023-5154 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0015G-CL02 | T-00023-5155 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0015G-CL03 | T-00023-5156 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-DD-62800A-CL01 | T-00023-5157 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-DD-62800C-CL01 | T-00023-5159 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-DD-62800E-CL01 | T-00023-5161 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-DD-62800G-CL01 | T-00023-5163 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002A-CL01 | T-00023-5166 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0002A-CL02 | T-00023-5167 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0002A-CL03 | T-00023-5168 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0002B-CL01 | T-00023-5169 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0002B-CL02 | T-00023-5170 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0002B-CL03 | T-00023-5171 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0002C-CL01 | T-00023-5172 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002C-CL02 | T-00023-5173 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0002C-CL03 | T-00023-5174 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002D-CL01 | T-00023-5175 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IE-0002D-CL02 | T-00023-5176 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IE-0002D-CL03 | T-00023-5177 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002E-CL01 | T-00023-5178 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0002E-CL02 | T-00023-5179 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0002E-CL03 | T-00023-5180 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002F-CL01 | T-00023-5181 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002F-CL02 | T-00023-5182 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002F-CL03 | T-00023-5183 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002G-CL01 | T-00023-5184 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002G-CL02 | T-00023-5185 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002G-CL03 | T-00023-5186 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003A-CL01 | T-00023-5187 | E | PS5-60-02 - Power Gen Package A (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IE-0003A-CL02 | T-00023-5188 | E | PS5-60-02 - Power Gen Package A (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IE-0003B-CL01 | T-00023-5189 | E | PS5-60-05 - Power Gen Package B (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IE-0003B-CL02 | T-00023-5190 | E | PS5-60-05 - Power Gen Package B (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IE-0003C-CL01 | T-00023-5191 | E | PS5-60-08 - Power Gen Package C (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CL02 | T-00023-5192 | E | PS5-60-08 - Power Gen Package C (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CL01 | T-00023-5193 | E | PS5-60-11 - Power Gen Package D (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CL02 | T-00023-5194 | E | PS5-60-11 - Power Gen Package D (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-60-IE-0003E-CL01 | T-00023-5195 | E | PS5-60-14 - Power Gen Package E (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CL02 | T-00023-5196 | E | PS5-60-14 - Power Gen Package E (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CL01 | T-00023-5197 | E | PS5-60-17 - Power Gen Package F (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CL02 | T-00023-5198 | E | PS5-60-17 - Power Gen Package F (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CL01 | T-00023-5199 | E | PS5-60-20 - Power Gen Package G (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CL02 | T-00023-5200 | E | PS5-60-20 - Power Gen Package G (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CL01 | T-00023-5201 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-60-IE-0004-CL02 | T-00023-5202 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-60-IH-0001A-CL01 | T-00023-5204 | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IH-0001A-CL02 | T-00023-5205 | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IH-0001A-CL03 | T-00023-5206 | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IH-0001A-CL04 | T-00023-5207 | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IH-0001A-CL05 | T-00023-5208 | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IH-0001A-CL06 | T-00023-5209 | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IH-0001B-CL01 | T-00023-5211 | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IH-0001B-CL02 | T-00023-5212 | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IH-0001B-CL03 | T-00023-5213 | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IH-0001B-CL04 | T-00023-5214 | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IH-0001B-CL05 | T-00023-5215 | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-60-IH-0001B-CL06 | T-00023-5216 | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-60-IH-0001C-CL01 | T-00023-5218 | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IH-0001C-CL02 | T-00023-5219 | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IH-0001C-CL03 | T-00023-5220 | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IH-0001C-CL04 | T-00023-5221 | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IH-0001C-CL05 | T-00023-5222 | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001C-CL06 | T-00023-5223 | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001D-CL01 | T-00023-5225 | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001D-CL02 | T-00023-5226 | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001D-CL03 | T-00023-5227 | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001D-CL04 | T-00023-5228 | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001D-CL05 | T-00023-5229 | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-60-IH-0001D-CL06 | T-00023-5230 | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001E-CL01 | T-00023-5232 | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001E-CL02 | T-00023-5233 | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001E-CL03 | T-00023-5234 | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001E-CL04 | T-00023-5235 | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001E-CL05 | T-00023-5236 | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001E-CL06 | T-00023-5237 | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001F-CL01 | T-00023-5239 | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001F-CL02 | T-00023-5240 | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001F-CL03 | T-00023-5241 | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001F-CL04 | T-00023-5242 | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001F-CL05 | T-00023-5243 | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001F-CL06 | T-00023-5244 | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001G-CL01 | T-00023-5246 | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001G-CL02 | T-00023-5247 | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001G-CL03 | T-00023-5248 | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001G-CL04 | T-00023-5249 | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | Started (not Completed) | Yes | Hold by EACOP | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IH-0001G-CL05 | T-00023-5250 | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001G-CL06 | T-00023-5251 | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0002-CL01 | T-00023-5254 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-60-IH-0002-CL02 | T-00023-5255 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-60-IH-0002-CL03 | T-00023-5256 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-60-IH-0002-CL04 | T-00023-5257 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-60-IH-0002-CL05 | T-00023-5258 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-60-IH-0002-CL06 | T-00023-5259 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-60-IH-0002-CL07 | T-00023-5260 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-60-IH-0002-CL08 | T-00023-5261 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-60-IH-0002-CL09 | T-00023-5262 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-60-IH-0002-CL10 | T-00023-5263 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-60-IN-0001A-CL01 | T-00023-5264 | E | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IN-0001B-CL01 | T-00023-5265 | E | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IN-0001C-CL01 | T-00023-5266 | E | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001D-CL01 | T-00023-5267 | E | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IN-0001E-CL01 | T-00023-5268 | E | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001F-CL01 | T-00023-5269 | E | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001G-CL01 | T-00023-5270 | E | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002A-CL01 | T-00023-5271 | E | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IN-0002A-CL02 | T-00023-5272 | E | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-60-IN-0002A-CL03 | T-00023-5273 | E | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IN-0002B-CL01 | T-00023-5274 | E | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IN-0002B-CL02 | T-00023-5275 | E | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IN-0002B-CL03 | T-00023-5276 | E | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IN-0002C-CL01 | T-00023-5277 | E | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002C-CL02 | T-00023-5278 | E | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002C-CL03 | T-00023-5279 | E | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002D-CL01 | T-00023-5280 | E | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IN-0002D-CL02 | T-00023-5281 | E | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IN-0002D-CL03 | T-00023-5282 | E | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IN-0002E-CL01 | T-00023-5283 | E | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002E-CL02 | T-00023-5284 | E | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002E-CL03 | T-00023-5285 | E | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002F-CL01 | T-00023-5286 | E | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002F-CL02 | T-00023-5287 | E | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002F-CL03 | T-00023-5288 | E | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002G-CL01 | T-00023-5289 | E | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002G-CL02 | T-00023-5290 | E | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002G-CL03 | T-00023-5291 | E | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IWK-0001A-CL01 | T-00023-5292 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IWK-0001A-CL02 | T-00023-5293 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IWK-0001B-CL01 | T-00023-5294 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IWK-0001B-CL02 | T-00023-5295 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IWK-0001C-CL01 | T-00023-5296 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IWK-0001C-CL02 | T-00023-5297 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-LA-0002A-CL01 | T-00023-5298 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-60-LA-0002A-CL02 | T-00023-5299 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-60-LA-0002B-CL01 | T-00023-5300 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B-CL02 | T-00023-5301 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002C-CL01 | T-00023-5302 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002C-CL02 | T-00023-5303 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0003-CL01 | T-00023-5304 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-60-LA-0003-CL02 | T-00023-5305 | E | PS5-60-22 - Power Gen Master UCP | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-60-MOV-0005-CL01 | T-00023-5306 | E | PS5-71-12 - CFO Service Tank | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:1/2, B:1/2 | Yes | Open + RFI Submitted
PS5-60-MOV-0006-CL01 | T-00023-5307 | E | PS5-71-12 - CFO Service Tank | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:1/2, B:0/2 | Yes | Open + RFI Submitted
PS5-60-MOV-0011-CL01 | T-00023-5308 | E | PS5-71-12 - CFO Service Tank | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:1/2, B:0/2 | Yes | Open + RFI Submitted
PS5-60-MOV-0012-CL01 | T-00023-5309 | E | PS5-71-12 - CFO Service Tank | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:1/2, B:0/2 | Yes | Open + RFI Submitted
PS5-60-SEA-0001-CL01 | T-00023-5310 | E | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-SEA-0001-CL02 | T-00023-5311 | E | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-VS-9100A-CL01 | T-00023-5312 | E | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-VS-9100B-CL01 | T-00023-5313 | E | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-VS-9100C-CL01 | T-00023-5314 | E | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-VS-9100D-CL01 | T-00023-5315 | E | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-VS-9100E-CL01 | T-00023-5316 | E | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-VS-9100F-CL01 | T-00023-5317 | E | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-VS-9100G-CL01 | T-00023-5318 | E | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-BI-0001-CL01 | T-00023-5319 | E | PS5-60-01 - Power Generation Package A | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-BI-0002-CL01 | T-00023-5320 | E | PS5-60-04 - Power Generation Package B | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-61-BI-0003-CL01 | T-00023-5321 | E | PS5-60-07 - Power Generation Package C | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-BI-0004-CL01 | T-00023-5322 | E | PS5-60-10 - Power Generation Package D | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-61-BI-0005-CL01 | T-00023-5323 | E | PS5-60-13 - Power Generation Package E | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-BI-0006-CL01 | T-00023-5324 | E | PS5-60-16 - Power Generation Package F | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-61-BI-0007-CL01 | T-00023-5325 | E | PS5-60-19 - Power Generation Package G | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IG-0015-CL01 | T-00023-5335 | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61- | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-61-IG-0016-CL01 | T-00023-5336 | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-61-IH-0004-CL01 | T-00023-5343 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL02 | T-00023-5344 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL03 | T-00023-5345 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL04 | T-00023-5346 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL05 | T-00023-5347 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL06 | T-00023-5348 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL07 | T-00023-5349 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL08 | T-00023-5350 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL09 | T-00023-5351 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL10 | T-00023-5352 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL11 | T-00023-5353 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL12 | T-00023-5354 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL13 | T-00023-5355 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL14 | T-00023-5356 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL15 | T-00023-5357 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL16 | T-00023-5358 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL17 | T-00023-5359 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL18 | T-00023-5360 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL19 | T-00023-5361 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL20 | T-00023-5362 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL21 | T-00023-5363 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL22 | T-00023-5364 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0003-CL01 | T-00023-5425 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Other | B:0/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL02 | T-00023-5426 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Other | B:0/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL03 | T-00023-5427 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0003-CL04 | T-00023-5428 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-61-IK-0003-CL05 | T-00023-5429 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-61-IK-0003-CL06 | T-00023-5430 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-61-IK-0003-CL07 | T-00023-5431 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL08 | T-00023-5432 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL09 | T-00023-5433 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL10 | T-00023-5434 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL11 | T-00023-5435 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL12 | T-00023-5436 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL13 | T-00023-5437 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL14 | T-00023-5438 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL15 | T-00023-5439 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL16 | T-00023-5440 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL17 | T-00023-5441 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL18 | T-00023-5442 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL19 | T-00023-5443 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL20 | T-00023-5444 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL21 | T-00023-5445 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL22 | T-00023-5446 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL23 | T-00023-5447 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL24 | T-00023-5448 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL25 | T-00023-5449 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL26 | T-00023-5450 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL27 | T-00023-5451 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL28 | T-00023-5452 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL29 | T-00023-5453 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL30 | T-00023-5454 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL31 | T-00023-5455 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL32 | T-00023-5456 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL33 | T-00023-5457 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL34 | T-00023-5458 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL35 | T-00023-5459 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL36 | T-00023-5460 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL37 | T-00023-5461 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL38 | T-00023-5462 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL39 | T-00023-5463 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL40 | T-00023-5464 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL41 | T-00023-5465 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL42 | T-00023-5466 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL43 | T-00023-5467 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL44 | T-00023-5468 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL45 | T-00023-5469 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL46 | T-00023-5470 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL47 | T-00023-5471 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL48 | T-00023-5472 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL49 | T-00023-5473 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL50 | T-00023-5474 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL51 | T-00023-5475 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL52 | T-00023-5476 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL53 | T-00023-5477 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL54 | T-00023-5478 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL55 | T-00023-5479 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL56 | T-00023-5480 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL57 | T-00023-5481 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL58 | T-00023-5482 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL59 | T-00023-5483 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL60 | T-00023-5484 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CL61 | T-00023-5485 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0003-CL62 | T-00023-5486 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-05-IG-0002-CL01 | T-00023-5487 | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-00 | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0006-CL01 | T-00023-5492 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL02 | T-00023-5493 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL03 | T-00023-5494 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL04 | T-00023-5495 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL05 | T-00023-5496 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL06 | T-00023-5497 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL07 | T-00023-5498 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL08 | T-00023-5499 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL09 | T-00023-5500 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL10 | T-00023-5501 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL11 | T-00023-5502 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL12 | T-00023-5503 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL13 | T-00023-5504 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL14 | T-00023-5505 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL15 | T-00023-5506 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL16 | T-00023-5507 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL17 | T-00023-5508 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL18 | T-00023-5509 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL19 | T-00023-5510 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL20 | T-00023-5511 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL21 | T-00023-5512 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL22 | T-00023-5513 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL23 | T-00023-5514 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL24 | T-00023-5515 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL25 | T-00023-5516 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL26 | T-00023-5517 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/2, B:0/2 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL27 | T-00023-5518 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/2, B:0/2 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL28 | T-00023-5519 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/2, B:0/2 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL29 | T-00023-5520 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0006-CL30 | T-00023-5521 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0006-CL31 | T-00023-5522 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0006-CL32 | T-00023-5523 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0006-CL33 | T-00023-5524 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0006-CL34 | T-00023-5525 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IU-3100A-CL01 | T-00023-5532 | E | PS5-25-02 - Crude Oil Export Pump A | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-IU-3100B-CL01 | T-00023-5533 | E | PS5-25-03 - Crude Oil Export Pump B | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-IU-3100C-CL01 | T-00023-5534 | E | PS5-25-04 - Crude Oil Export Pump C | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-IV-0002A-CL01 | T-00023-5537 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-61-IV-0002B-CL01 | T-00023-5538 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-61-IV-0007A-CL01 | T-00023-5542 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IV-0007B-CL01 | T-00023-5543 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-62-IE-0001-CL01 | T-00023-5546 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-62-IE-0002-CL01 | T-00023-5547 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-71-FCV-0018-CL01 | T-00023-5561 | E | PS5-71-13 - CFO Service Pump A/B | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-FCV-0019-CL01 | T-00023-5562 | E | PS5-71-21 - Diesel Transfer Pump A/B | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-FCV-0020-CL01 | T-00023-5563 | E | PS5-71-05 - CFO Transfer Pump A/B | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Open + RFI Submitted
PS5-71-HE-2200-CL02 | T-00023-5567 | E | PS5-71-12 - CFO Service Tank | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-71-HE-2300-CL02 | T-00023-5569 | E | PS5-71-04 - CFO Storage Tank | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-IN-0001-CL01 | T-00023-5578 | E | PS5-71-19 - Diesel Separator Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0001-CL02 | T-00023-5579 | E | PS5-71-19 - Diesel Separator Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0001-CL03 | T-00023-5580 | E | PS5-71-19 - Diesel Separator Module (UCP) | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-71-IN-0002-CL01 | T-00023-5581 | E | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0002-CL02 | T-00023-5582 | E | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0002-CL03 | T-00023-5583 | E | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0003-CL01 | T-00023-5584 | E | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-71-IN-0003-CL02 | T-00023-5585 | E | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-71-IN-0003-CL03 | T-00023-5586 | E | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-71-IN-0004A-CL01 | T-00023-5587 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | B:0/2 | Yes | Open + RFI Submitted
PS5-71-IN-0004A-CL02 | T-00023-5588 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | Yes | Hold by EACOP | B:0/2 | Yes | Open + RFI Submitted
PS5-71-IN-0004A-CL03 | T-00023-5589 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-71-IN-0004B-CL01 | T-00023-5590 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004B-CL02 | T-00023-5591 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004B-CL03 | T-00023-5592 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-71-LCV-4101-CL01 | T-00023-5593 | E | PS5-71-04 - CFO Storage Tank | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Open + RFI Submitted
PS5-71-MOV-0001-CL01 | T-00023-5594 | E | PS5-71-08 - CFO Pre-Pressure Modules | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-71-MOV-0002-CL01 | T-00023-5595 | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-71-MOV-0003-CL01 | T-00023-5596 | E | PS5-71-08 - CFO Pre-Pressure Modules | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-71-MOV-0004-CL01 | T-00023-5597 | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-71-MOV-0007-CL01 | T-00023-5598 | E | PS5-71-04 - CFO Storage Tank | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:1/2, B:1/2 | Yes | Open + RFI Submitted
PS5-71-MOV-0008-CL01 | T-00023-5599 | E | PS5-71-08 - CFO Pre-Pressure Modules | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:1/2, B:1/2 | Yes | Open + RFI Submitted
PS5-71-MOV-0009-CL01 | T-00023-5600 | E | PS5-71-04 - CFO Storage Tank | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-71-MOV-0010-CL01 | T-00023-5601 | E | PS5-71-08 - CFO Pre-Pressure Modules | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-71-SDV-0001-CL01 | T-00023-5602 | E | PS5-71-20 - Diesel Fuel Day Tank | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-SDV-0022-CL01 | T-00023-5603 | E | PS5-71-04 - CFO Storage Tank | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SDV-0029-CL01 | T-00023-5604 | E | PS5-71-15 - Diesel Fuel Storage Tank | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-SDV-0039-CL01 | T-00023-5605 | E | PS5-71-12 - CFO Service Tank | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-71-UZ-6200-CL01 | T-00023-5606 | E | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-XV-0089-CL01 | T-00023-5607 | E | PS5-71-04 - CFO Storage Tank | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-71-XV-0090-CL01 | T-00023-5608 | E | PS5-71-12 - CFO Service Tank | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Open + RFI Submitted
PS5-71-XV-0091-CL01 | T-00023-5609 | E | PS5-71-18 - Diesel Separator Module | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-XV-0092-CL01 | T-00023-5610 | E | PS5-71-20 - Diesel Fuel Day Tank | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-74-LB-5101-CL01 | T-00023-5612 | E | PS5-74-02 - N2 Generation Skid (UCP) | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-74-LB-5101-CL02 | T-00023-5613 | E | PS5-74-02 - N2 Generation Skid (UCP) | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-75-MOV-0001-CL01 | T-00023-5620 | E | PS5-28-07 - Open Drains (OD2) | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Open + RFI Submitted
PS5-75-UI-6200-CL01 | T-00023-5621 | E | PS5-75-01 - DRA Injection Package | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-75-UI-6200-CL02 | T-00023-5622 | E | PS5-75-01 - DRA Injection Package | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-78-JC-9100A-CL01 | T-00023-5623 | E | PS5-78-01 - Lifting and handling equipment | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-78-JC-9100B-CL01 | T-00023-5624 | E | PS5-78-01 - Lifting and handling equipment | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-78-JC-9100C-CL01 | T-00023-5625 | E | PS5-78-01 - Lifting and handling equipment | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-78-JC-9100D-CL01 | T-00023-5626 | E | PS5-78-01 - Lifting and handling equipment | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-87-IRF-0001-CL01 | T-00023-5640 | E | PS5-53-01 - Utility Water / Storage Tank | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-87-IRF-0002-CL01 | T-00023-5641 | E | PS5-71-04 - CFO Storage Tank | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-87-IRF-0003-CL01 | T-00023-5642 | E | PS5-71-12 - CFO Service Tank | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-87-IRF-0004-CL01 | T-00023-5643 | E | PS5-71-15 - Diesel Fuel Storage Tank | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-79-IG-0001-CL01 | T-00023-8829 | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0002-CL01 | T-00023-8830 | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0003-CL01 | T-00023-8831 | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0004-CL01 | T-00023-8832 | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0005-CL01 | T-00023-8833 | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0006-CL01 | T-00023-8834 | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0007-CL01 | T-00023-8835 | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0008-CL01 | T-00023-8836 | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0009-CL01 | T-00023-8837 | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0010-CL01 | T-00023-8838 | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0011-CL01 | T-00023-8839 | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0012-CL01 | T-00023-8840 | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-02-SWSI-0001-CL01 | T-00023-9120 | E | PS5-02-01 - Miscellaneous Safety equipment | CPX09 - LV Power Cable | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-02-SWSI-0003-CL01 | T-00023-9121 | E | PS5-02-01 - Miscellaneous Safety equipment | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-06-GU-0005-CL01 | T-00023-9122 | E | PS5-06-04 - AC UPS - Guard House | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-7001-CL01 | T-00023-9128 | E | PS5-09-02 - HVAC for Guard House | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0007A-CL01 | T-00023-9131 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPX09 - LV Power Cable | To be completed | Yes | Other | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0007B-CL01 | T-00023-9132 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPX09 - LV Power Cable | To be completed | Yes | Other | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0007C-CL01 | T-00023-9133 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0007D-CL01 | T-00023-9134 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-60-BE-0007E-CL01 | T-00023-9135 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0007F-CL01 | T-00023-9136 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0007G-CL01 | T-00023-9137 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0027A-CL01 | T-00023-9138 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0027B-CL01 | T-00023-9139 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0027C-CL01 | T-00023-9140 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0027D-CL01 | T-00023-9141 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0027E-CL01 | T-00023-9142 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0027F-CL01 | T-00023-9143 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0027G-CL01 | T-00023-9144 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0028A-CL01 | T-00023-9145 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0028B-CL01 | T-00023-9146 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BE-0028C-CL01 | T-00023-9147 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0028D-CL01 | T-00023-9148 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0028E-CL01 | T-00023-9149 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0028F-CL01 | T-00023-9150 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0028G-CL01 | T-00023-9151 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006A-CL01 | T-00023-9152 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006A-CL02 | T-00023-9153 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006A-CL03 | T-00023-9154 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006A-CL04 | T-00023-9155 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006A-CL05 | T-00023-9156 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006A-CL06 | T-00023-9157 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006A-CL07 | T-00023-9158 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006A-CL08 | T-00023-9159 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006A-CL09 | T-00023-9160 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006A-CL10 | T-00023-9161 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006A-CL11 | T-00023-9162 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006B-CL01 | T-00023-9163 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006B-CL02 | T-00023-9164 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006B-CL03 | T-00023-9165 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006B-CL04 | T-00023-9166 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006B-CL05 | T-00023-9167 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006B-CL06 | T-00023-9168 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006B-CL07 | T-00023-9169 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006B-CL08 | T-00023-9170 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006B-CL09 | T-00023-9171 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006B-CL10 | T-00023-9172 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006B-CL11 | T-00023-9173 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0006C-CL01 | T-00023-9174 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006C-CL02 | T-00023-9175 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006C-CL03 | T-00023-9176 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006C-CL04 | T-00023-9177 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006C-CL05 | T-00023-9178 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006C-CL06 | T-00023-9179 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006C-CL07 | T-00023-9180 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006C-CL08 | T-00023-9181 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006C-CL09 | T-00023-9182 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006C-CL10 | T-00023-9183 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006C-CL11 | T-00023-9184 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006D-CL01 | T-00023-9185 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006D-CL02 | T-00023-9186 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006D-CL03 | T-00023-9187 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006D-CL04 | T-00023-9188 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006D-CL05 | T-00023-9189 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006D-CL06 | T-00023-9190 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006D-CL07 | T-00023-9191 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006D-CL08 | T-00023-9192 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006D-CL09 | T-00023-9193 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006D-CL10 | T-00023-9194 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006D-CL11 | T-00023-9195 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CL01 | T-00023-9196 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CL02 | T-00023-9197 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CL03 | T-00023-9198 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CL04 | T-00023-9199 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CL05 | T-00023-9200 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CL06 | T-00023-9201 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CL07 | T-00023-9202 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CL08 | T-00023-9203 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CL09 | T-00023-9204 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CL10 | T-00023-9205 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CL11 | T-00023-9206 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CL01 | T-00023-9207 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CL02 | T-00023-9208 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CL03 | T-00023-9209 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CL04 | T-00023-9210 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CL05 | T-00023-9211 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CL06 | T-00023-9212 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CL07 | T-00023-9213 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CL08 | T-00023-9214 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CL09 | T-00023-9215 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CL10 | T-00023-9216 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CL11 | T-00023-9217 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CL01 | T-00023-9218 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CL02 | T-00023-9219 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CL03 | T-00023-9220 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CL04 | T-00023-9221 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CL05 | T-00023-9222 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CL06 | T-00023-9223 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CL07 | T-00023-9224 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CL08 | T-00023-9225 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CL09 | T-00023-9226 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CL10 | T-00023-9227 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CL11 | T-00023-9228 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0017A-CL01 | T-00023-9229 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0017B-CL01 | T-00023-9230 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPX09 - LV Power Cable | To be completed | Yes | Open | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0017C-CL01 | T-00023-9231 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0017D-CL01 | T-00023-9232 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0017E-CL01 | T-00023-9233 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0017F-CL01 | T-00023-9234 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0017G-CL01 | T-00023-9235 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2900A-CL01 | T-00023-9236 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2900B-CL01 | T-00023-9237 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2900C-CL01 | T-00023-9238 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2900D-CL01 | T-00023-9239 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2900E-CL01 | T-00023-9240 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2900F-CL01 | T-00023-9241 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2900G-CL01 | T-00023-9242 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0005-CL01 | T-00023-9243 | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building ( | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0004-CL01 | T-00023-9244 | E | PS5-71-08 - CFO Pre-Pressure Modules | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-71-BE-0004-CL02 | T-00023-9245 | E | PS5-71-08 - CFO Pre-Pressure Modules | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0004-CL03 | T-00023-9246 | E | PS5-71-08 - CFO Pre-Pressure Modules | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-71-BI-0003-CL01 | T-00023-9247 | E | PS5-71-08 - CFO Pre-Pressure Modules | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-71-BI-0003-CL02 | T-00023-9248 | E | PS5-71-08 - CFO Pre-Pressure Modules | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0003-CL03 | T-00023-9249 | E | PS5-71-08 - CFO Pre-Pressure Modules | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0003-CL04 | T-00023-9250 | E | PS5-71-08 - CFO Pre-Pressure Modules | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0004-CL01 | T-00023-9251 | E | PS5-71-08 - CFO Pre-Pressure Modules | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0005-CL01 | T-00023-9252 | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPX09 - LV Power Cable | To be completed | Yes | Open | B:0/2 | Yes | Open + RFI Submitted
PS5-71-BI-0005-CL02 | T-00023-9253 | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPX09 - LV Power Cable | To be completed | Yes | Open | B:0/2 | Yes | Open + RFI Submitted
PS5-71-BI-0005-CL03 | T-00023-9254 | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPX09 - LV Power Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-71-BI-0006-CL01 | T-00023-9255 | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | CPX09 - LV Power Cable | To be completed | Yes | Open | B:0/2 | Yes | Open + RFI Submitted
PS5-09-AHU-8111A-CL01 | T-00023-9680 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8111B-CL01 | T-00023-9681 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8211A-CL01 | T-00023-9682 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8211B-CL01 | T-00023-9683 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8311A-CL01 | T-00023-9684 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8311A-CL02 | T-00023-9685 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8311B-CL01 | T-00023-9686 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8311B-CL02 | T-00023-9687 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8321A-CL01 | T-00023-9688 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8321A-CL02 | T-00023-9689 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8321B-CL01 | T-00023-9690 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8321B-CL02 | T-00023-9691 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8331A-CL01 | T-00023-9692 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8331A-CL02 | T-00023-9693 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8331B-CL01 | T-00023-9694 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8331B-CL02 | T-00023-9695 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8341-CL01 | T-00023-9696 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8341-CL02 | T-00023-9697 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8411A-CL01 | T-00023-9698 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8411A-CL02 | T-00023-9699 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8411B-CL01 | T-00023-9700 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8411B-CL02 | T-00023-9701 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442A-CL01 | T-00023-9702 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442B-CL01 | T-00023-9703 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442C-CL01 | T-00023-9704 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442D-CL01 | T-00023-9705 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442E-CL01 | T-00023-9706 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442F-CL01 | T-00023-9707 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442G-CL01 | T-00023-9708 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442H-CL01 | T-00023-9709 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-0008-CL03 | T-00023-9710 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PA-84500A-CL01 | T-00023-9711 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PA-84500B-CL01 | T-00023-9712 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-QX-8451A-CL01 | T-00023-9713 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-QX-8451A-CL02 | T-00023-9714 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-QX-8451B-CL01 | T-00023-9715 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-QX-8451B-CL02 | T-00023-9716 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-81200A-CL01 | T-00023-9717 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-81200B-CL01 | T-00023-9718 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-81200C-CL01 | T-00023-9719 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-82200A-CL01 | T-00023-9720 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-82200B-CL01 | T-00023-9721 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-82200C-CL01 | T-00023-9722 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-82200D-CL01 | T-00023-9723 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500A-CL01 | T-00023-9724 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500B-CL01 | T-00023-9725 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500C-CL01 | T-00023-9726 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500D-CL01 | T-00023-9727 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500E-CL01 | T-00023-9728 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500F-CL01 | T-00023-9729 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500G-CL01 | T-00023-9730 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500H-CL01 | T-00023-9731 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500J-CL01 | T-00023-9732 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500K-CL01 | T-00023-9733 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500L-CL01 | T-00023-9734 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500M-CL01 | T-00023-9735 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500N-CL01 | T-00023-9736 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500P-CL01 | T-00023-9737 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600A-CL01 | T-00023-9738 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600B-CL01 | T-00023-9739 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600C-CL01 | T-00023-9740 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600D-CL01 | T-00023-9741 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600E-CL01 | T-00023-9742 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600F-CL01 | T-00023-9743 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600G-CL01 | T-00023-9744 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600H-CL01 | T-00023-9745 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600J-CL01 | T-00023-9746 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600K-CL01 | T-00023-9747 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600L-CL01 | T-00023-9748 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600M-CL01 | T-00023-9749 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600N-CL01 | T-00023-9750 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600P-CL01 | T-00023-9751 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700A-CL01 | T-00023-9752 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700B-CL01 | T-00023-9753 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700C-CL01 | T-00023-9754 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700D-CL01 | T-00023-9755 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700E-CL01 | T-00023-9756 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700F-CL01 | T-00023-9757 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700G-CL01 | T-00023-9758 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700H-CL01 | T-00023-9759 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700J-CL01 | T-00023-9760 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700K-CL01 | T-00023-9761 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700L-CL01 | T-00023-9762 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700M-CL01 | T-00023-9763 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700N-CL01 | T-00023-9764 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700P-CL01 | T-00023-9765 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83800A-CL01 | T-00023-9766 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83800B-CL01 | T-00023-9767 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83800C-CL01 | T-00023-9768 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83800D-CL01 | T-00023-9769 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83800E-CL01 | T-00023-9770 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83800F-CL01 | T-00023-9771 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83800G-CL01 | T-00023-9772 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-84200A-CL01 | T-00023-9773 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-84200B-CL01 | T-00023-9774 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-UZ-84600-CL01 | T-00023-9775 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004A-CL01 | T-00023-9776 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004B-CL01 | T-00023-9777 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004C-CL01 | T-00023-9778 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004D-CL01 | T-00023-9779 | E | PS5-09-03 - HVAC for Generator Building | CPX09 - LV Power Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-IE-8100-CD01 | T-00024-2028 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD02 | T-00024-2029 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD03 | T-00024-2030 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD04 | T-00024-2031 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD05 | T-00024-2032 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD06 | T-00024-2033 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD07 | T-00024-2034 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD08 | T-00024-2035 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD10 | T-00024-2037 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD11 | T-00024-2038 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD12 | T-00024-2039 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD13 | T-00024-2040 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD14 | T-00024-2041 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD15 | T-00024-2042 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD16 | T-00024-2043 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD17 | T-00024-2044 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD18 | T-00024-2045 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD19 | T-00024-2046 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD20 | T-00024-2047 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD21 | T-00024-2048 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD25 | T-00024-2052 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-25-DM-3100A-CD01 | T-00024-2061 | E | PS5-25-02 - Crude Oil Export Pump A | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-25-DM-3100B-CD01 | T-00024-2062 | E | PS5-25-03 - Crude Oil Export Pump B | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-25-DM-3100C-CD01 | T-00024-2063 | E | PS5-25-04 - Crude Oil Export Pump C | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-25-IES-3100A-CD01 | T-00024-2067 | E | PS5-25-02 - Crude Oil Export Pump A | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-IES-3100B-CD01 | T-00024-2068 | E | PS5-25-03 - Crude Oil Export Pump B | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-IES-3100C-CD01 | T-00024-2069 | E | PS5-25-04 - Crude Oil Export Pump C | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-50-IE-0001-CD01 | T-00024-2097 | E | PS5-50-01 - Water Well Submersible Pumps (3100) | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-50-IE-0002-CD01 | T-00024-2098 | E | PS5-50-02 - Water Well Submersible Pumps (3200) | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002A-CD01 | T-00024-2101 | E | PS5-60-01 - Power Generation Package A | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0002A-CD02 | T-00024-2102 | E | PS5-60-01 - Power Generation Package A | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0002A-CD03 | T-00024-2103 | E | PS5-60-01 - Power Generation Package A | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0002B-CD01 | T-00024-2104 | E | PS5-60-04 - Power Generation Package B | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0002B-CD02 | T-00024-2105 | E | PS5-60-04 - Power Generation Package B | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0002B-CD03 | T-00024-2106 | E | PS5-60-04 - Power Generation Package B | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0002C-CD01 | T-00024-2107 | E | PS5-60-07 - Power Generation Package C | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0002C-CD02 | T-00024-2108 | E | PS5-60-07 - Power Generation Package C | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0002C-CD03 | T-00024-2109 | E | PS5-60-07 - Power Generation Package C | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0002D-CD01 | T-00024-2110 | E | PS5-60-10 - Power Generation Package D | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0002D-CD02 | T-00024-2111 | E | PS5-60-10 - Power Generation Package D | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0002D-CD03 | T-00024-2112 | E | PS5-60-10 - Power Generation Package D | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002E-CD01 | T-00024-2113 | E | PS5-60-13 - Power Generation Package E | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002E-CD02 | T-00024-2114 | E | PS5-60-13 - Power Generation Package E | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002E-CD03 | T-00024-2115 | E | PS5-60-13 - Power Generation Package E | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002F-CD01 | T-00024-2116 | E | PS5-60-16 - Power Generation Package F | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002F-CD02 | T-00024-2117 | E | PS5-60-16 - Power Generation Package F | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002F-CD03 | T-00024-2118 | E | PS5-60-16 - Power Generation Package F | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002G-CD01 | T-00024-2119 | E | PS5-60-19 - Power Generation Package G | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002G-CD02 | T-00024-2120 | E | PS5-60-19 - Power Generation Package G | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002G-CD03 | T-00024-2121 | E | PS5-60-19 - Power Generation Package G | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003A-CD02 | T-00024-2123 | E | PS5-60-01 - Power Generation Package A | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IE-0003A-CD03 | T-00024-2124 | E | PS5-60-01 - Power Generation Package A | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-60-IE-0003A-CD04 | T-00024-2125 | E | PS5-60-01 - Power Generation Package A | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IE-0003A-CD05 | T-00024-2126 | E | PS5-60-01 - Power Generation Package A | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-60-IE-0003A-CD14 | T-00024-2135 | E | PS5-60-01 - Power Generation Package A | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003A-CD15 | T-00024-2136 | E | PS5-60-01 - Power Generation Package A | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Other | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003B-CD02 | T-00024-2138 | E | PS5-60-04 - Power Generation Package B | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003B-CD03 | T-00024-2139 | E | PS5-60-04 - Power Generation Package B | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003B-CD04 | T-00024-2140 | E | PS5-60-04 - Power Generation Package B | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003B-CD05 | T-00024-2141 | E | PS5-60-04 - Power Generation Package B | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IE-0003B-CD14 | T-00024-2150 | E | PS5-60-04 - Power Generation Package B | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003B-CD15 | T-00024-2151 | E | PS5-60-04 - Power Generation Package B | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Other | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003C-CD02 | T-00024-2153 | E | PS5-60-07 - Power Generation Package C | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CD03 | T-00024-2154 | E | PS5-60-07 - Power Generation Package C | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CD04 | T-00024-2155 | E | PS5-60-07 - Power Generation Package C | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003C-CD05 | T-00024-2156 | E | PS5-60-07 - Power Generation Package C | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CD14 | T-00024-2165 | E | PS5-60-07 - Power Generation Package C | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CD15 | T-00024-2166 | E | PS5-60-07 - Power Generation Package C | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CD02 | T-00024-2168 | E | PS5-60-10 - Power Generation Package D | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CD03 | T-00024-2169 | E | PS5-60-10 - Power Generation Package D | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IE-0003D-CD04 | T-00024-2170 | E | PS5-60-10 - Power Generation Package D | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IE-0003D-CD05 | T-00024-2171 | E | PS5-60-10 - Power Generation Package D | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IE-0003D-CD14 | T-00024-2180 | E | PS5-60-10 - Power Generation Package D | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Not Started
PS5-60-IE-0003D-CD15 | T-00024-2181 | E | PS5-60-10 - Power Generation Package D | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CD02 | T-00024-2183 | E | PS5-60-13 - Power Generation Package E | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CD03 | T-00024-2184 | E | PS5-60-13 - Power Generation Package E | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CD04 | T-00024-2185 | E | PS5-60-13 - Power Generation Package E | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003E-CD05 | T-00024-2186 | E | PS5-60-13 - Power Generation Package E | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CD14 | T-00024-2195 | E | PS5-60-13 - Power Generation Package E | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CD15 | T-00024-2196 | E | PS5-60-13 - Power Generation Package E | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CD02 | T-00024-2198 | E | PS5-60-16 - Power Generation Package F | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CD03 | T-00024-2199 | E | PS5-60-16 - Power Generation Package F | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CD04 | T-00024-2200 | E | PS5-60-16 - Power Generation Package F | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003F-CD05 | T-00024-2201 | E | PS5-60-16 - Power Generation Package F | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CD14 | T-00024-2210 | E | PS5-60-16 - Power Generation Package F | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CD15 | T-00024-2211 | E | PS5-60-16 - Power Generation Package F | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CD02 | T-00024-2213 | E | PS5-60-19 - Power Generation Package G | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CD03 | T-00024-2214 | E | PS5-60-19 - Power Generation Package G | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CD04 | T-00024-2215 | E | PS5-60-19 - Power Generation Package G | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003G-CD05 | T-00024-2216 | E | PS5-60-19 - Power Generation Package G | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CD14 | T-00024-2225 | E | PS5-60-19 - Power Generation Package G | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CD15 | T-00024-2226 | E | PS5-60-19 - Power Generation Package G | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IDH-3100A-CD03 | T-00024-2233 | E | PS5-25-02 - Crude Oil Export Pump A | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-61-IDH-3100B-CD03 | T-00024-2236 | E | PS5-25-03 - Crude Oil Export Pump B | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-61-IDH-3100C-CD03 | T-00024-2239 | E | PS5-25-04 - Crude Oil Export Pump C | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-62-IE-0001-CD01 | T-00024-2288 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-79-IG-0001-CD01 | T-00024-3288 | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0002-CD01 | T-00024-3289 | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0003-CD01 | T-00024-3290 | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0004-CD01 | T-00024-3291 | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0005-CD01 | T-00024-3292 | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0006-CD01 | T-00024-3293 | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0007-CD01 | T-00024-3294 | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0008-CD01 | T-00024-3295 | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0009-CD01 | T-00024-3296 | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0010-CD01 | T-00024-3297 | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0011-CD01 | T-00024-3298 | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0012-CD01 | T-00024-3299 | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-06-GU-0003A-CD02 | T-00024-3399 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | Yes | Other | B:0/2 | Yes | Open + RFI Submitted
PS5-09-IES-8101A-CD01 | T-00024-3634 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8101B-CD01 | T-00024-3635 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8102A-CD01 | T-00024-3636 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8102B-CD01 | T-00024-3637 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8102C-CD01 | T-00024-3638 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8201A-CD01 | T-00024-3639 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8201B-CD01 | T-00024-3640 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8202A-CD01 | T-00024-3641 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8202B-CD01 | T-00024-3642 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8202C-CD01 | T-00024-3643 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8202D-CD01 | T-00024-3644 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8301A-CD01 | T-00024-3645 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8301B-CD01 | T-00024-3646 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8302A-CD01 | T-00024-3647 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8302B-CD01 | T-00024-3648 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8304A-CD01 | T-00024-3649 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8304B-CD01 | T-00024-3650 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8305A-CD01 | T-00024-3651 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8305B-CD01 | T-00024-3652 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8307A-CD01 | T-00024-3653 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8307B-CD01 | T-00024-3654 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8308A-CD01 | T-00024-3655 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8308B-CD01 | T-00024-3656 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8311A-CD01 | T-00024-3657 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8311B-CD01 | T-00024-3658 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8313-CD01 | T-00024-3659 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8314-CD01 | T-00024-3660 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8315-CD01 | T-00024-3661 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8316-CD01 | T-00024-3662 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8317-CD01 | T-00024-3663 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8318-CD01 | T-00024-3664 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8319-CD01 | T-00024-3665 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8321-CD01 | T-00024-3666 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8322-CD01 | T-00024-3667 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8323-CD01 | T-00024-3668 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8324-CD01 | T-00024-3669 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8325-CD01 | T-00024-3670 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8401A-CD01 | T-00024-3671 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8401B-CD01 | T-00024-3672 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8403A-CD01 | T-00024-3673 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8403B-CD01 | T-00024-3674 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8404A-CD01 | T-00024-3675 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8404B-CD01 | T-00024-3676 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8405A-CD01 | T-00024-3677 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8405B-CD01 | T-00024-3678 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406A-CD01 | T-00024-3679 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406B-CD01 | T-00024-3680 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406C-CD01 | T-00024-3681 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406D-CD01 | T-00024-3682 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406E-CD01 | T-00024-3683 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406F-CD01 | T-00024-3684 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406G-CD01 | T-00024-3685 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406H-CD01 | T-00024-3686 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8407-CD01 | T-00024-3687 | E | PS5-09-03 - HVAC for Generator Building | CPX10 - Multicore Electrical Control Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-DM-3100A | T-00025-0013 | E | PS5-25-02 - Crude Oil Export Pump A | CPX12 - HV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-DM-3100B | T-00025-0014 | E | PS5-25-03 - Crude Oil Export Pump B | CPX12 - HV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-DM-3100C | T-00025-0015 | E | PS5-25-04 - Crude Oil Export Pump C | CPX12 - HV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3300 | T-00026-0155 | E | PS5-28-06 - Relief Drum and Pump | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3400 | T-00026-0156 | E | PS5-28-03 - Closed Drain Drum and Pump 01 | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3500 | T-00026-0157 | E | PS5-28-08 - Open Drain Sump and Pumps | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3600A | T-00026-0158 | E | PS5-28-08 - Open Drain Sump and Pumps | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3600B | T-00026-0159 | E | PS5-28-08 - Open Drain Sump and Pumps | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3700A | T-00026-0160 | E | PS5-28-04 - Closed Drain Drum and Pump 02 | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3700B | T-00026-0161 | E | PS5-28-04 - Closed Drain Drum and Pump 02 | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3800A | T-00026-0162 | E | PS5-28-13 - Seal Oil Drain Drum & Pump A | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3800B | T-00026-0163 | E | PS5-28-14 - Seal Oil Drain Drum & Pump B | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3800C | T-00026-0164 | E | PS5-28-15 - Seal Oil Drain Drum & Pump C | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3900A | T-00026-0165 | E | PS5-28-17 - Reinjection Pump | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3900B | T-00026-0166 | E | PS5-28-17 - Reinjection Pump | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-DM-3100A | T-00026-0167 | E | PS5-53-02 - Water Distribution Pump A/B | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-DM-3100B | T-00026-0168 | E | PS5-53-02 - Water Distribution Pump A/B | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-DM-3300 | T-00026-0169 | E | PS5-60-24 - Cooling Water Tank & Pump | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-DM-3400 | T-00026-0170 | E | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-DM-3100A | T-00026-0171 | E | PS5-71-16 - Diesel Fuel Supply Pump A/B | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-DM-3100B | T-00026-0172 | E | PS5-71-16 - Diesel Fuel Supply Pump A/B | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-DM-3200 | T-00026-0173 | E | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-DM-3300A | T-00026-0174 | E | PS5-71-05 - CFO Transfer Pump A/B | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-DM-3300B | T-00026-0175 | E | PS5-71-05 - CFO Transfer Pump A/B | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-DM-3400A | T-00026-0176 | E | PS5-71-13 - CFO Service Pump A/B | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-DM-3400B | T-00026-0177 | E | PS5-71-13 - CFO Service Pump A/B | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-DM-3500A | T-00026-0178 | E | PS5-71-21 - Diesel Transfer Pump A/B | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-DM-3500B | T-00026-0179 | E | PS5-71-21 - Diesel Transfer Pump A/B | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-31100 | T-00026-0286 | E | PS5-28-10 - Oil Skimmer Package | CPX13 - LV Motor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-IG-0001 | T-00028-0462 | E | PS5-01-10 - Water Mist Package | CPX15 - Distribution Board | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-IG-0002 | T-00028-0463 | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-00 | CPX15 - Distribution Board | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-IG-0004 | T-00028-0464 | E | PS5-62-03 - Outdoor Emergency Lighting DB - PS5-05-IG-0004 | CPX15 - Distribution Board | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1, C:0/1 | Yes | Open + RFI Submitted
PS5-05-IG-0006 | T-00028-0465 | E | PS5-62-04 - Outdoor Emergency Lighting DB - PS5-05-IG-0006 | CPX15 - Distribution Board | To be completed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Open + RFI Submitted
PS5-05-IG-0007 | T-00028-0466 | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | CPX15 - Distribution Board | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-IG-0025 | T-00028-0467 | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - | CPX15 - Distribution Board | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-IG-0026 | T-00028-0468 | E | PS5-62-07 - CRO Generator Electrical Building Emergency Ligh | CPX15 - Distribution Board | To be completed | No | No RFI Yet | - |  | Not Started
PS5-06-IG-0004A | T-00028-0469 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX15 - Distribution Board | To be completed | No | No RFI Yet | C:0/2 | Yes | Not Started
PS5-06-IG-0004B | T-00028-0470 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX15 - Distribution Board | To be completed | No | No RFI Yet | C:0/2 | Yes | Not Started
PS5-61-IG-0006 | T-00028-0471 | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | CPX15 - Distribution Board | To be completed | Yes | Accepted with Punch | B:0/1, C:0/1 | Yes | Open + RFI Submitted
PS5-61-IG-0007 | T-00028-0472 | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | CPX15 - Distribution Board | To be completed | Yes | Accepted with Punch | A:0/1, C:0/2 | Yes | Open + RFI Submitted
PS5-61-IG-0014 | T-00028-0473 | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-001 | CPX15 - Distribution Board | To be completed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Open + RFI Submitted
PS5-61-IG-0015 | T-00028-0474 | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61- | CPX15 - Distribution Board | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IG-0016 | T-00028-0475 | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB | CPX15 - Distribution Board | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IG-0042 | T-00028-0476 | E | PS5-61-10 - Outdoor Valves Distribution Board - PS5-61-IG-00 | CPX15 - Distribution Board | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1, C:0/1 | Yes | Open + RFI Submitted
PS5-61-IG-0043 | T-00028-0477 | E | PS5-61-11 - Outdoor Valves Distribution Board - PS5-61-IG-00 | CPX15 - Distribution Board | To be completed | Yes | Accepted with Punch | B:0/1, C:0/1 | Yes | Open + RFI Submitted
PS5-74-IG-5101 | T-00028-0478 | E | PS5-74-01 - N2 Generation Skid | CPX15 - Distribution Board | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0001 | T-00028-0479 | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution | CPX15 - Distribution Board | Started (not Completed) | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Open + RFI Submitted
PS5-79-IG-0002 | T-00028-0480 | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution | CPX15 - Distribution Board | To be completed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Open + RFI Submitted
PS5-79-IG-0003 | T-00028-0481 | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution | CPX15 - Distribution Board | To be completed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Open + RFI Submitted
PS5-79-IG-0004 | T-00028-0482 | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution | CPX15 - Distribution Board | To be completed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Open + RFI Submitted
PS5-79-IG-0005 | T-00028-0483 | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution | CPX15 - Distribution Board | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1, C:0/1 | Yes | Open + RFI Submitted
PS5-79-IG-0006 | T-00028-0484 | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution | CPX15 - Distribution Board | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1, C:0/1 | Yes | Open + RFI Submitted
PS5-79-IG-0007 | T-00028-0485 | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution | CPX15 - Distribution Board | To be completed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Open + RFI Submitted
PS5-79-IG-0008 | T-00028-0486 | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution | CPX15 - Distribution Board | To be completed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Open + RFI Submitted
PS5-79-IG-0009 | T-00028-0487 | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution | CPX15 - Distribution Board | To be completed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Open + RFI Submitted
PS5-79-IG-0010 | T-00028-0488 | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution | CPX15 - Distribution Board | To be completed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Open + RFI Submitted
PS5-79-IG-0011 | T-00028-0489 | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution | CPX15 - Distribution Board | To be completed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Open + RFI Submitted
PS5-79-IG-0012 | T-00028-0490 | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution | CPX15 - Distribution Board | To be completed | No | No RFI Yet | - |  | Not Started
PS5-06-GU-0003A | T-00029-0234 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX16 - Charger/Inverter | To be completed | No | No RFI Yet | - |  | Not Started
PS5-06-GU-0003B | T-00029-0235 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX16 - Charger/Inverter | To be completed | No | No RFI Yet | - |  | Not Started
PS5-06-GU-0003C | T-00029-0236 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX16 - Charger/Inverter | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-UD-3100A | T-00032-0165 | E | PS5-25-02 - Crude Oil Export Pump A | CPX19 - Power Socket Outlet | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-ISO-2008 | T-00032-0166 | E | PS5-28-10 - Oil Skimmer Package | CPX19 - Power Socket Outlet | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-HE-2100 | T-00033-0044 | E | PS5-28-03 - Closed Drain Drum and Pump 01 | CPX20 - Heater | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-HE-2200 | T-00033-0045 | E | PS5-28-04 - Closed Drain Drum and Pump 02 | CPX20 - Heater | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-HE-2200 | T-00033-0046 | E | PS5-71-12 - CFO Service Tank | CPX20 - Heater | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-HE-2300 | T-00033-0047 | E | PS5-71-04 - CFO Storage Tank | CPX20 - Heater | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-HE-2400A | T-00033-0048 | E | PS5-71-01 - CFO Storage Tank Feed Heater | CPX20 - Heater | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-HE-2400B | T-00033-0049 | E | PS5-71-01 - CFO Storage Tank Feed Heater | CPX20 - Heater | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-HE-2100 | T-00033-0068 | E | PS5-25-02 - Crude Oil Export Pump A | CPX20 - Heater | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-HE-2200 | T-00033-0069 | E | PS5-25-03 - Crude Oil Export Pump B | CPX20 - Heater | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-HE-2300 | T-00033-0070 | E | PS5-25-04 - Crude Oil Export Pump C | CPX20 - Heater | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-NER-0010 | T-00034-0041 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | CPX21 - Neutral Earthing Resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-NER-0011 | T-00034-0042 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | CPX21 - Neutral Earthing Resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-63-NER-0010 | T-00034-0043 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX21 - Neutral Earthing Resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-63-NER-0011 | T-00034-0044 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX21 - Neutral Earthing Resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IJ-0001A | T-00034-0059 | E | PS5-60-01 - Power Generation Package A | CPX21 - Neutral Earthing Resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IJ-0001B | T-00034-0060 | E | PS5-60-04 - Power Generation Package B | CPX21 - Neutral Earthing Resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IJ-0001C | T-00034-0061 | E | PS5-60-07 - Power Generation Package C | CPX21 - Neutral Earthing Resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IJ-0001D | T-00034-0062 | E | PS5-60-10 - Power Generation Package D | CPX21 - Neutral Earthing Resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IJ-0001E | T-00034-0063 | E | PS5-60-13 - Power Generation Package E | CPX21 - Neutral Earthing Resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IJ-0001F | T-00034-0064 | E | PS5-60-16 - Power Generation Package F | CPX21 - Neutral Earthing Resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IJ-0001G | T-00034-0065 | E | PS5-60-19 - Power Generation Package G | CPX21 - Neutral Earthing Resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - CFO AREA_Earthing | T-00039-0283 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | Submitted | No | No RFI Yet | - |  | Submitted No RFI
PS5 - CHEMICAL AND WASTE STORAGE AREA_Earthing | T-00039-0284 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | Submitted | No | No RFI Yet | - |  | Submitted No RFI
PS5 - CLOSED DRAIN DRUM AREA_Earthing | T-00039-0285 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | Submitted | No | No RFI Yet | - |  | Submitted No RFI
PS5 - DIESEL FUEL STORAGE AND PUMP AREA_Earthing | T-00039-0286 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | Submitted | No | No RFI Yet | - |  | Submitted No RFI
PS5 - EXPORT PUMP VSD AREA_Earthing | T-00039-0287 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | Submitted | No | No RFI Yet | - |  | Submitted No RFI
PS5 - EXPORT LOADING PUMP AREA_Earthing | T-00039-0288 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | Submitted | No | No RFI Yet | - |  | Submitted No RFI
PS5 - FENCE EAST AREA_Earthing | T-00039-0289 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - FENCE SOUTH WEST AREA_Earthing | T-00039-0290 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - FENCE WEST AREA_Earthing | T-00039-0291 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | Submitted | No | No RFI Yet | - |  | Submitted No RFI
PS5 - FENCE SOUTH EAST AREA_Earthing | T-00039-0292 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - LAUNCHER/RECEIVER AREA_Earthing | T-00039-0293 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | Submitted | No | No RFI Yet | - |  | Submitted No RFI
PS5 - OBSERVATION BASIN AREA_Earthing | T-00039-0294 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - POWER DISTRIBUTION AREA_Earthing | T-00039-0295 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | Submitted | No | No RFI Yet | - |  | Submitted No RFI
PS5 - POWER GENERATION BUILDING AREA_Earthing | T-00039-0296 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | Submitted | No | No RFI Yet | - |  | Submitted No RFI
PS5 - POWER GENERATION COOLING TOWER AREA_Earthing | T-00039-0297 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | Submitted | No | No RFI Yet | - |  | Submitted No RFI
PS5 - TURNSTILE GATE AND OFFICE BUILDING AREA_Earthing | T-00039-0298 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - UTILITY AREA_Earthing | T-00039-0299 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | Submitted | No | No RFI Yet | - |  | Submitted No RFI
PS5 - UTILITY/FIRE WATER STORAGE TANK AREA_Earthing | T-00039-0300 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | Submitted | No | No RFI Yet | - |  | Submitted No RFI
PS5-82-OB-0001_Earthing | T-00039-0301 | E | PS5-63-02 - Electrical Earthing - Office and Facilities buil | CPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-OB-0005_Earthing | T-00039-0302 | E | PS5-63-06 - Electrical Earthing - Guard House | CPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-OB-0009A_Earthing | T-00039-0303 | E | PS5-63-05 - Electrical Earthing - Guard Hut A & B | CPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-OB-0009B_Earthing | T-00039-0304 | E | PS5-63-05 - Electrical Earthing - Guard Hut A & B | CPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0001_Earthing | T-00039-0306 | E | PS5-63-07 - Electrical Earthing - Workshop & Warehouse | CPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0003_Earthing | T-00039-0307 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | Submitted | No | No RFI Yet | - |  | Submitted No RFI
PS5-84-OB-0004_Earthing | T-00039-0308 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | Submitted | No | No RFI Yet | - |  | Submitted No RFI
PS5-84-OB-0005_Earthing | T-00039-0309 | E | PS5-63-03 - Electrical Earthing - Generator Building | CPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0006_Earthing | T-00039-0310 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | Started (not Completed) | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0007_Earthing | T-00039-0311 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | Submitted | No | No RFI Yet | - |  | Submitted No RFI
PS5-86-OB-0001_Earthing | T-00039-0312 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-86-OB-0002_Earthing | T-00039-0313 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-86-OB-0003_Earthing | T-00039-0314 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-86-OB-0004_Earthing | T-00039-0315 | E | PS5-63-01 - Electrical Earthing | CPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - RECEIVER AND LAUNCHER AREA_Lightning | T-00040-0052 | E | PS5-63-01 - Electrical Earthing | CPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-OB-0001_Lightning | T-00040-0053 | E | PS5-63-02 - Electrical Earthing - Office and Facilities buil | CPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-OB-0005_Lightning | T-00040-0054 | E | PS5-63-06 - Electrical Earthing - Guard House | CPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-OB-0009A_Lightning | T-00040-0055 | E | PS5-63-05 - Electrical Earthing - Guard Hut A & B | CPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-OB-0009B_Lightning | T-00040-0056 | E | PS5-63-05 - Electrical Earthing - Guard Hut A & B | CPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0001_Lightning | T-00040-0057 | E | PS5-63-07 - Electrical Earthing - Workshop & Warehouse | CPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0003_Lightning | T-00040-0058 | E | PS5-63-01 - Electrical Earthing | CPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0005_Lightning | T-00040-0059 | E | PS5-63-03 - Electrical Earthing - Generator Building | CPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0006_Lightning | T-00040-0060 | E | PS5-63-01 - Electrical Earthing | CPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0007_Lightning | T-00040-0061 | E | PS5-63-01 - Electrical Earthing | CPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-86-OB-0001_Lightning | T-00040-0062 | E | PS5-63-01 - Electrical Earthing | CPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-86-OB-0002_Lightning | T-00040-0063 | E | PS5-63-01 - Electrical Earthing | CPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-86-OB-0003_Lightning | T-00040-0064 | E | PS5-63-01 - Electrical Earthing | CPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-86-OB-0004_Lightning | T-00040-0065 | E | PS5-63-01 - Electrical Earthing | CPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-OB-0001 | T-00041-0026 | E | PS5-82-05 - Office and Facilities building | CPX29 - MCT cabling | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-OB-0005 | T-00041-0027 | E | PS5-82-06 - Guard House Building | CPX29 - MCT cabling | To be completed | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0005 | T-00041-0028 | E | PS5-84-01 - Generator Building | CPX29 - MCT cabling | To be completed | No | No RFI Yet | - |  | Not Started
PS5_AREA_COMPLETION_FOR_BUILDING_AREA_-_NORTH | T-00042-0142 | E | PS5-99-01 - Area Completion for Building area | CPX30 - Cable tray / ladder | To be completed | No | No RFI Yet | - |  | Not Started
PS5_AREA_COMPLETION_FOR_BUILDING_AREA_-_NORTH_WEST | T-00042-0143 | E | PS5-99-01 - Area Completion for Building area | CPX30 - Cable tray / ladder | To be completed | No | No RFI Yet | - |  | Not Started
PS5_AREA_COMPLETION_FOR_CFO_AREA | T-00042-0144 | E | PS5-99-05 - Area Completion for CFO area | CPX30 - Cable tray / ladder | To be completed | No | No RFI Yet | - |  | Not Started
PS5_AREA_COMPLETION_FOR_POWER_DISTRIBUTION_AREA | T-00042-0145 | E | PS5-99-03 - Area Completion for Power Distribution area | CPX30 - Cable tray / ladder | To be completed | No | No RFI Yet | - |  | Not Started
PS5_AREA_COMPLETION_FOR_POWER_GENERATION_AREA | T-00042-0146 | E | PS5-99-06 - Area Completion for Power Generation area | CPX30 - Cable tray / ladder | To be completed | No | No RFI Yet | - |  | Not Started
PS5_AREA_COMPLETION_FOR_PROCESS_AREA | T-00042-0147 | E | PS5-99-04 - Area Completion for Process area | CPX30 - Cable tray / ladder | To be completed | No | No RFI Yet | - |  | Not Started
PS5_AREA_COMPLETION_FOR_PROCESS_AREA_-_NORTH | T-00042-0148 | E | PS5-99-04 - Area Completion for Process area | CPX30 - Cable tray / ladder | To be completed | No | No RFI Yet | - |  | Not Started
PS5_AREA_COMPLETION_FOR_PROCESS_AREA_SOUTH | T-00042-0149 | E | PS5-99-04 - Area Completion for Process area | CPX30 - Cable tray / ladder | To be completed | No | No RFI Yet | - |  | Not Started
PS5_AREA_COMPLETION_FOR_UTILITY_AREA | T-00042-0150 | E | PS5-99-02 - Area Completion for Utility area | CPX30 - Cable tray / ladder | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-OB-0001 | T-00042-0167 | E | PS5-82-05 - Office and Facilities building | CPX30 - Cable tray / ladder | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-OB-0005 | T-00042-0168 | E | PS5-82-06 - Guard House Building | CPX30 - Cable tray / ladder | To be completed | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0005 | T-00042-0169 | E | PS5-84-01 - Generator Building | CPX30 - Cable tray / ladder | To be completed | No | No RFI Yet | - |  | Not Started
PS5-83-OB-0001_Installation | T-00042-0208 | E | PS5-83-01 - EITS Building | CPX30 - Cable tray / ladder | Submitted | No | No RFI Yet | - |  | Submitted No RFI
PS5-79-BH-0001 | T-00043-0045 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | CPX31 - Junction and marshalling box | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-BH-0002 | T-00043-0046 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | CPX31 - Junction and marshalling box | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-BE-0001 | T-00043-0073 | E | PS5-05-01 - Emergency Diesel Generator Package | CPX31 - Junction and marshalling box | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003A | T-00044-0090 | E | PS5-60-02 - Power Gen Package A (UCP) | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B | T-00044-0091 | E | PS5-60-05 - Power Gen Package B (UCP) | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C | T-00044-0092 | E | PS5-60-08 - Power Gen Package C (UCP) | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D | T-00044-0093 | E | PS5-60-11 - Power Gen Package D (UCP) | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E | T-00044-0094 | E | PS5-60-14 - Power Gen Package E (UCP) | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F | T-00044-0095 | E | PS5-60-17 - Power Gen Package F (UCP) | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G | T-00044-0096 | E | PS5-60-20 - Power Gen Package G (UCP) | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004 | T-00044-0097 | E | PS5-60-22 - Power Gen Master UCP | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001A | T-00044-0098 | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001B | T-00044-0099 | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001C | T-00044-0100 | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001D | T-00044-0101 | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001E | T-00044-0102 | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001F | T-00044-0103 | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001G | T-00044-0104 | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0002 | T-00044-0105 | E | PS5-60-22 - Power Gen Master UCP | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002A | T-00044-0106 | E | PS5-60-01 - Power Generation Package A | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002B | T-00044-0107 | E | PS5-60-04 - Power Generation Package B | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002C | T-00044-0108 | E | PS5-60-07 - Power Generation Package C | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002D | T-00044-0109 | E | PS5-60-10 - Power Generation Package D | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002E | T-00044-0110 | E | PS5-60-13 - Power Generation Package E | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002F | T-00044-0111 | E | PS5-60-16 - Power Generation Package F | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002G | T-00044-0112 | E | PS5-60-19 - Power Generation Package G | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-IE-0001A | T-00044-0175 | E | PS5-01-05 - Foam Skid | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-IE-0001B | T-00044-0176 | E | PS5-01-05 - Foam Skid | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-IE-0002A | T-00044-0177 | E | PS5-01-01 - Fire Water Jockey Pump A/B | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-IE-0002B | T-00044-0178 | E | PS5-01-01 - Fire Water Jockey Pump A/B | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-IE-0009A | T-00044-0179 | E | PS5-01-02 - Fire Water Pump A | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-IE-0009B | T-00044-0180 | E | PS5-01-03 - Fire Water Pump B | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-IE-8100 | T-00044-0182 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX32 - Console / control panel | Closed | No | No RFI Yet | B:0/1, C:0/2 | Yes | Closed but No RFI
PS5-50-IE-0001 | T-00044-0183 | E | PS5-50-01 - Water Well Submersible Pumps (3100) | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-50-IE-0002 | T-00044-0184 | E | PS5-50-02 - Water Well Submersible Pumps (3200) | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002A | T-00044-0185 | E | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002B | T-00044-0186 | E | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002C | T-00044-0187 | E | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002D | T-00044-0188 | E | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002E | T-00044-0189 | E | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002F | T-00044-0190 | E | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002G | T-00044-0191 | E | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004 | T-00044-0192 | E | PS5-09-03 - HVAC for Generator Building | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004A | T-00044-0193 | E | PS5-09-03 - HVAC for Generator Building | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004B | T-00044-0194 | E | PS5-09-03 - HVAC for Generator Building | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001 | T-00044-0195 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | CPX32 - Console / control panel | Closed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-62-IE-0002 | T-00044-0196 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPX32 - Console / control panel | Closed | Yes | Accepted with Punch | B:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-71-IN-0001 | T-00044-0197 | E | PS5-71-19 - Diesel Separator Module (UCP) | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0002 | T-00044-0198 | E | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0003 | T-00044-0199 | E | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004A | T-00044-0200 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004B | T-00044-0201 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-0008 | T-00044-0267 | E | PS5-09-03 - HVAC for Generator Building | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004C | T-00044-0268 | E | PS5-09-03 - HVAC for Generator Building | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004D | T-00044-0269 | E | PS5-09-03 - HVAC for Generator Building | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-7001 | T-00044-0279 | E | PS5-09-02 - HVAC for Guard House | CPX32 - Console / control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-TR-4100 | T-00045-0008 | E | PS5-53-01 - Utility Water / Storage Tank | CPX33 - Cathodic protection | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TR-4100 | T-00045-0009 | E | PS5-71-04 - CFO Storage Tank | CPX33 - Cathodic protection | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TR-4200 | T-00045-0010 | E | PS5-71-12 - CFO Service Tank | CPX33 - Cathodic protection | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TR-4400 | T-00045-0011 | E | PS5-71-15 - Diesel Fuel Storage Tank | CPX33 - Cathodic protection | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-UK-6100 | T-00046-0013 | E | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | CZX01E - Package | Started (not Completed) | No | No RFI Yet | - |  | Not Started
PS5-01-UV-8700 | T-00046-0014 | E | PS5-01-05 - Foam Skid | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8100A | T-00046-0291 | E | PS5-60-01 - Power Generation Package A | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-UR-8100B | T-00046-0292 | E | PS5-60-04 - Power Generation Package B | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-UR-8100C | T-00046-0293 | E | PS5-60-07 - Power Generation Package C | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-UR-8100D | T-00046-0294 | E | PS5-60-10 - Power Generation Package D | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-UR-8100E | T-00046-0295 | E | PS5-60-13 - Power Generation Package E | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8100F | T-00046-0296 | E | PS5-60-16 - Power Generation Package F | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8100G | T-00046-0297 | E | PS5-60-19 - Power Generation Package G | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-UR-8100 | T-00046-0298 | E | PS5-05-01 - Emergency Diesel Generator Package | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-UZ-6200 | T-00046-0299 | E | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UA-5100 | T-00046-0300 | E | PS5-60-27 - Compressed Air Starting Skid | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-UO-81100A | T-00046-0301 | E | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-UO-81100B | T-00046-0302 | E | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-UO-81100C | T-00046-0303 | E | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-UO-81100D | T-00046-0304 | E | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-UO-81100E | T-00046-0305 | E | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UO-81100F | T-00046-0306 | E | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UO-81100G | T-00046-0307 | E | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8200A | T-00046-0308 | E | PS5-60-35 - Injector Tip Cooling Module A | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-UZ-8200B | T-00046-0309 | E | PS5-60-36 - Injector Tip Cooling Module B | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-UZ-8200C | T-00046-0310 | E | PS5-60-37 - Injector Tip Cooling Module C | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-UZ-8200D | T-00046-0311 | E | PS5-60-38 - Injector Tip Cooling Module D | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-UZ-8200E | T-00046-0312 | E | PS5-60-39 - Injector Tip Cooling Module E | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8200F | T-00046-0313 | E | PS5-60-40 - Injector Tip Cooling Module F | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-VS-9100A | T-00046-0314 | E | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-VS-9100B | T-00046-0315 | E | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-VS-9100C | T-00046-0316 | E | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-VS-9100D | T-00046-0317 | E | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-VS-9100E | T-00046-0318 | E | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-VS-9100F | T-00046-0319 | E | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-VS-9100G | T-00046-0320 | E | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-UZ-6500 | T-00046-0321 | E | PS5-71-18 - Diesel Separator Module | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-UZ-6800A | T-00046-0322 | E | PS5-71-06 - Crude Fuel Separation Module | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-UZ-6800B | T-00046-0323 | E | PS5-71-06 - Crude Fuel Separation Module | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-01-UZ-6900 | T-00046-0324 | E | PS5-01-10 - Water Mist Package | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-UT-8100 | T-00046-0325 | E | PS5-50-03 - Water Pre-Treatment Package | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-UT-8200 | T-00046-0326 | E | PS5-53-04 - Water Treatment Purification Package | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2100A | T-00046-0327 | E | PS5-60-70 - Engine A Cooling system | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-2100B | T-00046-0328 | E | PS5-60-70 - Engine A Cooling system | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-21100A | T-00046-0329 | E | PS5-60-01 - Power Generation Package A | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-21100B | T-00046-0330 | E | PS5-60-04 - Power Generation Package B | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-21100C | T-00046-0331 | E | PS5-60-07 - Power Generation Package C | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-21100D | T-00046-0332 | E | PS5-60-10 - Power Generation Package D | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-21100E | T-00046-0333 | E | PS5-60-13 - Power Generation Package E | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-21100F | T-00046-0334 | E | PS5-60-16 - Power Generation Package F | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-21100G | T-00046-0335 | E | PS5-60-19 - Power Generation Package G | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-21200A | T-00046-0336 | E | PS5-60-01 - Power Generation Package A | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-21200B | T-00046-0337 | E | PS5-60-04 - Power Generation Package B | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-21200C | T-00046-0338 | E | PS5-60-07 - Power Generation Package C | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-21200D | T-00046-0339 | E | PS5-60-10 - Power Generation Package D | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-21200E | T-00046-0340 | E | PS5-60-13 - Power Generation Package E | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-21200F | T-00046-0341 | E | PS5-60-16 - Power Generation Package F | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-21200G | T-00046-0342 | E | PS5-60-19 - Power Generation Package G | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2200A | T-00046-0343 | E | PS5-60-71 - Engine B Cooling system | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-2200B | T-00046-0344 | E | PS5-60-71 - Engine B Cooling system | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-2300A | T-00046-0345 | E | PS5-60-72 - Engine C Cooling system | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-2300B | T-00046-0346 | E | PS5-60-72 - Engine C Cooling system | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-2400A | T-00046-0347 | E | PS5-60-73 - Engine D Cooling system | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-2400B | T-00046-0348 | E | PS5-60-73 - Engine D Cooling system | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-2500A | T-00046-0349 | E | PS5-60-74 - Engine E Cooling system | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2500B | T-00046-0350 | E | PS5-60-74 - Engine E Cooling system | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2600A | T-00046-0351 | E | PS5-60-75 - Engine F Cooling system | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2600B | T-00046-0352 | E | PS5-60-75 - Engine F Cooling system | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2700A | T-00046-0353 | E | PS5-60-76 - Engine G Cooling system | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2700B | T-00046-0354 | E | PS5-60-76 - Engine G Cooling system | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2800A | T-00046-0355 | E | PS5-60-35 - Injector Tip Cooling Module A | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-2800B | T-00046-0356 | E | PS5-60-36 - Injector Tip Cooling Module B | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-2800C | T-00046-0357 | E | PS5-60-37 - Injector Tip Cooling Module C | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-2800D | T-00046-0358 | E | PS5-60-38 - Injector Tip Cooling Module D | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-2800E | T-00046-0359 | E | PS5-60-39 - Injector Tip Cooling Module E | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2800F | T-00046-0360 | E | PS5-60-40 - Injector Tip Cooling Module F | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2800G | T-00046-0361 | E | PS5-60-41 - Injector Tip Cooling Module G | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2900A | T-00046-0362 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-2900B | T-00046-0363 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-2900C | T-00046-0364 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-2900D | T-00046-0365 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-2900E | T-00046-0366 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2900F | T-00046-0367 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2900G | T-00046-0368 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0001A | T-00046-0369 | E | PS5-60-70 - Engine A Cooling system | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-TCV-0001B | T-00046-0370 | E | PS5-60-71 - Engine B Cooling system | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-TCV-0001C | T-00046-0371 | E | PS5-60-72 - Engine C Cooling system | CZX01E - Package | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-TCV-0001D | T-00046-0372 | E | PS5-60-73 - Engine D Cooling system | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0001E | T-00046-0373 | E | PS5-60-74 - Engine E Cooling system | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0001F | T-00046-0374 | E | PS5-60-75 - Engine F Cooling system | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0001G | T-00046-0375 | E | PS5-60-76 - Engine G Cooling system | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0002A | T-00046-0376 | E | PS5-60-70 - Engine A Cooling system | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0002B | T-00046-0377 | E | PS5-60-71 - Engine B Cooling system | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0002C | T-00046-0378 | E | PS5-60-72 - Engine C Cooling system | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0002D | T-00046-0379 | E | PS5-60-73 - Engine D Cooling system | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0002E | T-00046-0380 | E | PS5-60-74 - Engine E Cooling system | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0002F | T-00046-0381 | E | PS5-60-75 - Engine F Cooling system | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0002G | T-00046-0382 | E | PS5-60-76 - Engine G Cooling system | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UA-5200 | T-00046-0383 | E | PS5-60-26 - Instrument Air Compressor Skid | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8200A | T-00046-0384 | E | PS5-60-01 - Power Generation Package A | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8200B | T-00046-0385 | E | PS5-60-04 - Power Generation Package B | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8200C | T-00046-0386 | E | PS5-60-07 - Power Generation Package C | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8200D | T-00046-0387 | E | PS5-60-10 - Power Generation Package D | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8200E | T-00046-0388 | E | PS5-60-13 - Power Generation Package E | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8200F | T-00046-0389 | E | PS5-60-16 - Power Generation Package F | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8200G | T-00046-0390 | E | PS5-60-19 - Power Generation Package G | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8200G | T-00046-0391 | E | PS5-60-41 - Injector Tip Cooling Module G | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8900A | T-00046-0392 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8900B | T-00046-0393 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8900C | T-00046-0394 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8900D | T-00046-0395 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8900E | T-00046-0396 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8900F | T-00046-0397 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8900G | T-00046-0398 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-UN-7200 | T-00046-0399 | E | PS5-71-02 - CFO Allocation Metering Package | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-UZ-6400 | T-00046-0400 | E | PS5-71-08 - CFO Pre-Pressure Modules | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-UZ-6700 | T-00046-0401 | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-74-UB-5100 | T-00046-0402 | E | PS5-74-01 - N2 Generation Skid | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-75-UI-6100 | T-00046-0403 | E | PS5-75-02 - Biocide Injection Package | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-75-UI-6200 | T-00046-0404 | E | PS5-75-01 - DRA Injection Package | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-75-UI-6300 | T-00046-0405 | E | PS5-75-03 - Corrosion Inhibitor Injection Package | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-77-UZ-8200 | T-00046-0406 | E | PS5-53-03 - Water Softener Package | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-UZ-8100 | T-00046-0407 | E | PS5-82-02 - Sewage Treatment Plant Package | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-83-EHO-0001A | T-00046-0542 | E | PS5-25-02 - Crude Oil Export Pump A | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-83-EHO-0001B | T-00046-0543 | E | PS5-25-03 - Crude Oil Export Pump B | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-83-EHO-0001C | T-00046-0544 | E | PS5-25-04 - Crude Oil Export Pump C | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-UZ-610 | T-00046-0549 | E | PS5-01-11 - Inergen for Power Gen Building | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8300A | T-00046-0552 | E | PS5-60-35 - Injector Tip Cooling Module A | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8300B | T-00046-0553 | E | PS5-60-36 - Injector Tip Cooling Module B | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8300C | T-00046-0554 | E | PS5-60-37 - Injector Tip Cooling Module C | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8300D | T-00046-0555 | E | PS5-60-38 - Injector Tip Cooling Module D | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8300E | T-00046-0556 | E | PS5-60-39 - Injector Tip Cooling Module E | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8300F | T-00046-0557 | E | PS5-60-40 - Injector Tip Cooling Module F | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8300G | T-00046-0558 | E | PS5-60-41 - Injector Tip Cooling Module G | CZX01E - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61001A | T-00064-0412 | I | PS5-01-11 - Inergen for Power Gen Building | CJX00 - Miscellaneous | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61001B | T-00064-0413 | I | PS5-01-11 - Inergen for Power Gen Building | CJX00 - Miscellaneous | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61002A | T-00064-0414 | I | PS5-01-11 - Inergen for Power Gen Building | CJX00 - Miscellaneous | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61002B | T-00064-0415 | I | PS5-01-11 - Inergen for Power Gen Building | CJX00 - Miscellaneous | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61003A | T-00064-0416 | I | PS5-01-11 - Inergen for Power Gen Building | CJX00 - Miscellaneous | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61003B | T-00064-0417 | I | PS5-01-11 - Inergen for Power Gen Building | CJX00 - Miscellaneous | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61004A | T-00064-0418 | I | PS5-01-11 - Inergen for Power Gen Building | CJX00 - Miscellaneous | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61004B | T-00064-0419 | I | PS5-01-11 - Inergen for Power Gen Building | CJX00 - Miscellaneous | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RAB-B402 | T-00064-0437 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX00 - Miscellaneous | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RAB-B902 | T-00064-0438 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX00 - Miscellaneous | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RAB-W502 | T-00064-0439 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX00 - Miscellaneous | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PSV-1103 | T-00065-0115 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PSV-0064C | T-00065-0116 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PSV-1203 | T-00065-0117 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PRV-0047B | T-00065-0118 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-74-PSV-0003 | T-00065-0119 | I | PS5-74-03 - Nitrogen Receiver | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PRV-0040 | T-00065-0120 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-50-PSV-0004A | T-00065-0121 | I | PS5-50-01 - Water Well Submersible Pumps (3100) | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PSV-2403A | T-00065-0122 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PSV-3901B | T-00065-0123 | I | PS5-28-17 - Reinjection Pump | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PRV-0047A | T-00065-0124 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PVSV-4202 | T-00065-0125 | I | PS5-71-12 - CFO Service Tank | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PVSV-4102 | T-00065-0126 | I | PS5-71-04 - CFO Storage Tank | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PRV-0046A | T-00065-0127 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PRV-0008 | T-00065-0128 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PSV-0064A | T-00065-0129 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PRV-0054 | T-00065-0130 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PSV-0044 | T-00065-0131 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PRV-0016 | T-00065-0132 | I | PS5-71-04 - CFO Storage Tank | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PRV-0046B | T-00065-0133 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PRV-0015 | T-00065-0134 | I | PS5-71-04 - CFO Storage Tank | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PRV-0018 | T-00065-0135 | I | PS5-71-12 - CFO Service Tank | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PRV-0041 | T-00065-0136 | I | PS5-71-12 - CFO Service Tank | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PSV-2403B | T-00065-0137 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PRV-0046C | T-00065-0138 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PRV-0047C | T-00065-0139 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PRV-0055 | T-00065-0140 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PSV-0061 | T-00065-0141 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PSV-0064B | T-00065-0142 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PSV-3901A | T-00065-0143 | I | PS5-28-17 - Reinjection Pump | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-50-PSV-0004B | T-00065-0144 | I | PS5-50-02 - Water Well Submersible Pumps (3200) | CJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FCV-0004B | T-00066-0059 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX06 - Tubing Hydraulic | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FCV-0004 | T-00066-0060 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | CJX06 - Tubing Hydraulic | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FCV-0003A | T-00066-0061 | I | PS5-01-02 - Fire Water Pump A | CJX06 - Tubing Hydraulic | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FCV-0003B | T-00066-0062 | I | PS5-01-03 - Fire Water Pump B | CJX06 - Tubing Hydraulic | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FCV-0018 | T-00066-0063 | I | PS5-71-13 - CFO Service Pump A/B | CJX06 - Tubing Hydraulic | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FCV-0003B | T-00066-0064 | I | PS5-25-03 - Crude Oil Export Pump B | CJX06 - Tubing Hydraulic | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LCV-4101 | T-00066-0065 | I | PS5-71-04 - CFO Storage Tank | CJX06 - Tubing Hydraulic | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FCV-0019 | T-00066-0066 | I | PS5-71-21 - Diesel Transfer Pump A/B | CJX06 - Tubing Hydraulic | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FCV-0020 | T-00066-0067 | I | PS5-71-05 - CFO Transfer Pump A/B | CJX06 - Tubing Hydraulic | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FCV-0004A | T-00066-0068 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX06 - Tubing Hydraulic | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FCV-0003A | T-00066-0069 | I | PS5-25-02 - Crude Oil Export Pump A | CJX06 - Tubing Hydraulic | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FCV-0003C | T-00066-0070 | I | PS5-25-04 - Crude Oil Export Pump C | CJX06 - Tubing Hydraulic | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0101 | T-00067-0072 | I | PS5-03-01 - FZ-01 - Process Area | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0102 | T-00067-0073 | I | PS5-03-01 - FZ-01 - Process Area | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0103 | T-00067-0074 | I | PS5-03-01 - FZ-01 - Process Area | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0120 | T-00067-0075 | I | PS5-03-01 - FZ-01 - Process Area | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0301 | T-00067-0076 | I | PS5-03-03 - FZ-03 - Buildings Area | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0401 | T-00067-0077 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0402 | T-00067-0078 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0613 | T-00067-0079 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0827 | T-00067-0081 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-NMR-0801 | T-00067-0640 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-NMR-0802 | T-00067-0641 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-NMR-0803 | T-00067-0642 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-NMR-0804 | T-00067-0643 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0304 | T-00067-0652 | I | PS5-03-03 - FZ-03 - Buildings Area | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0706 | T-00067-0653 | I | PS5-03-07 - FZ-07 - Pretreatment Area | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0707 | T-00067-0654 | I | PS5-03-07 - FZ-07 - Pretreatment Area | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0824 | T-00067-0655 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0825 | T-00067-0656 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0834 | T-00067-0657 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-1301 | T-00067-0658 | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument A | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-1409 | T-00067-0659 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-1410 | T-00067-0660 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-1411 | T-00067-0661 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-ZIT-0001 | T-00067-2049 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-ZS-1101 | T-00067-2050 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-HS-7002 | T-00067-2051 | I | PS5-03-03 - FZ-03 - Buildings Area | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-HZL-0059 | T-00067-2052 | I | PS5-71-18 - Diesel Separator Module | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-HZH-0059 | T-00067-2053 | I | PS5-71-18 - Diesel Separator Module | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-ZIT-0002 | T-00067-2054 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-ZS-1201 | T-00067-2055 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FIT-0003B | T-00067-2056 | I | PS5-25-03 - Crude Oil Export Pump B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0019 | T-00067-2057 | I | PS5-71-21 - Diesel Transfer Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0011B | T-00067-2058 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-50-FIT-0001 | T-00067-2059 | I | PS5-50-03 - Water Pre-Treatment Package | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FIT-0003B | T-00067-2060 | I | PS5-01-03 - Fire Water Pump B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FIT-0003A | T-00067-2061 | I | PS5-25-02 - Crude Oil Export Pump A | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0018 | T-00067-2062 | I | PS5-71-13 - CFO Service Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FIT-0003A | T-00067-2063 | I | PS5-01-02 - Fire Water Pump A | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0020 | T-00067-2064 | I | PS5-71-05 - CFO Transfer Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FIT-0004 | T-00067-2065 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FIT-0003C | T-00067-2066 | I | PS5-25-04 - Crude Oil Export Pump C | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FIT-0001 | T-00067-2067 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0012 | T-00067-2068 | I | PS5-71-17 - Diesel Fuel Distribution Header | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0005 | T-00067-2069 | I | PS5-71-17 - Diesel Fuel Distribution Header | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0011A | T-00067-2070 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FIT-0004A | T-00067-2071 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FIT-0004B | T-00067-2072 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-1202 | T-00067-2073 | I | PS5-71-20 - Diesel Fuel Day Tank | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-4202 | T-00067-2074 | I | PS5-71-12 - CFO Service Tank | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-LIT-4101B | T-00067-2075 | I | PS5-01-03 - Fire Water Pump B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-LIT-1301A | T-00067-2076 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-LIT-1102 | T-00067-2077 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-50-LIT-0001 | T-00067-2078 | I | PS5-50-01 - Water Well Submersible Pumps (3100) | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-LIT-1301B | T-00067-2079 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-4101 | T-00067-2080 | I | PS5-71-04 - CFO Storage Tank | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LIT-4401 | T-00067-2081 | I | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-4102 | T-00067-2082 | I | PS5-71-04 - CFO Storage Tank | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-4401 | T-00067-2083 | I | PS5-71-15 - Diesel Fuel Storage Tank | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-LIT-1202 | T-00067-2084 | I | PS5-28-06 - Relief Drum and Pump | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-LIT-0002 | T-00067-2085 | I | PS5-28-08 - Open Drain Sump and Pumps | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-LIT-4101 | T-00067-2086 | I | PS5-53-01 - Utility Water / Storage Tank | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-LIT-1402 | T-00067-2087 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-4201 | T-00067-2088 | I | PS5-71-12 - CFO Service Tank | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-LIT-1201 | T-00067-2089 | I | PS5-28-06 - Relief Drum and Pump | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LIT-4301 | T-00067-2090 | I | PS5-60-24 - Cooling Water Tank & Pump | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-LIT-1301C | T-00067-2091 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-LIT-1101 | T-00067-2092 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-1201 | T-00067-2093 | I | PS5-71-20 - Diesel Fuel Day Tank | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-4402 | T-00067-2094 | I | PS5-71-15 - Diesel Fuel Storage Tank | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-LIT-4101A | T-00067-2095 | I | PS5-01-02 - Fire Water Pump A | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-LIT-0008 | T-00067-2096 | I | PS5-28-08 - Open Drain Sump and Pumps | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-LIT-1401 | T-00067-2097 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-50-LIT-0002 | T-00067-2098 | I | PS5-50-02 - Water Well Submersible Pumps (3200) | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-LIT-4102 | T-00067-2099 | I | PS5-53-01 - Utility Water / Storage Tank | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PDIT-0034A | T-00067-2100 | I | PS5-25-02 - Crude Oil Export Pump A | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0008C | T-00067-2101 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PDIT-0012B | T-00067-2102 | I | PS5-01-03 - Fire Water Pump B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PIT-0010 | T-00067-2103 | I | PS5-01-07 - Fire Water Ring Main & Distribution | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0018 | T-00067-2104 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PDIT-0011A | T-00067-2105 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PDIT-0050 | T-00067-2106 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PIT-0015 | T-00067-2107 | I | PS5-28-17 - Reinjection Pump | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PIT-0041 | T-00067-2108 | I | PS5-28-17 - Reinjection Pump | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0004C | T-00067-2109 | I | PS5-25-04 - Crude Oil Export Pump C | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PDIT-0034C | T-00067-2110 | I | PS5-25-04 - Crude Oil Export Pump C | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PIT-0016 | T-00067-2111 | I | PS5-01-07 - Fire Water Ring Main & Distribution | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PDIT-0030 | T-00067-2112 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0071B | T-00067-2113 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PDIT-0011B | T-00067-2114 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0001 | T-00067-2115 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PDIT-0056B | T-00067-2116 | I | PS5-71-05 - CFO Transfer Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-1202 | T-00067-2117 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0005B | T-00067-2118 | I | PS5-25-03 - Crude Oil Export Pump B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0004A | T-00067-2119 | I | PS5-25-02 - Crude Oil Export Pump A | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PIT-0015 | T-00067-2120 | I | PS5-01-07 - Fire Water Ring Main & Distribution | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PDIT-0056A | T-00067-2121 | I | PS5-71-05 - CFO Transfer Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-74-PIT-0002 | T-00067-2122 | I | PS5-74-04 - Nitrogen Distribution Header | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PIT-0033 | T-00067-2123 | I | PS5-28-06 - Relief Drum and Pump | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PIT-0017 | T-00067-2124 | I | PS5-01-07 - Fire Water Ring Main & Distribution | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-1102 | T-00067-2125 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0004B | T-00067-2126 | I | PS5-25-03 - Crude Oil Export Pump B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0007B | T-00067-2127 | I | PS5-25-03 - Crude Oil Export Pump B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PIT-0014 | T-00067-2128 | I | PS5-01-07 - Fire Water Ring Main & Distribution | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0071C | T-00067-2129 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-PIT-0005 | T-00067-2130 | I | PS5-53-02 - Water Distribution Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0007A | T-00067-2131 | I | PS5-25-02 - Crude Oil Export Pump A | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0005A | T-00067-2132 | I | PS5-25-02 - Crude Oil Export Pump A | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0071A | T-00067-2133 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PIT-0014 | T-00067-2134 | I | PS5-71-17 - Diesel Fuel Distribution Header | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0013 | T-00067-2135 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PIT-2402A | T-00067-2136 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PIT-2402B | T-00067-2137 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PDIT-0012A | T-00067-2138 | I | PS5-01-02 - Fire Water Pump A | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PIT-0013 | T-00067-2139 | I | PS5-01-07 - Fire Water Ring Main & Distribution | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PDIT-0034B | T-00067-2140 | I | PS5-25-03 - Crude Oil Export Pump B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0005C | T-00067-2141 | I | PS5-25-04 - Crude Oil Export Pump C | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0007C | T-00067-2142 | I | PS5-25-04 - Crude Oil Export Pump C | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0008A | T-00067-2143 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0008B | T-00067-2144 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-0003 | T-00067-2145 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-0006 | T-00067-2146 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-4203 | T-00067-2147 | I | PS5-71-12 - CFO Service Tank | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-TIT-1402 | T-00067-2148 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TIT-0002B | T-00067-2149 | I | PS5-25-03 - Crude Oil Export Pump B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TIT-1201 | T-00067-2150 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TIT-0003B | T-00067-2151 | I | PS5-25-03 - Crude Oil Export Pump B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-TIT-1401 | T-00067-2152 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TIT-0003A | T-00067-2153 | I | PS5-25-02 - Crude Oil Export Pump A | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-0007 | T-00067-2154 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-TIT-1104 | T-00067-2155 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-0004 | T-00067-2156 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-4202 | T-00067-2157 | I | PS5-71-12 - CFO Service Tank | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TIT-0003C | T-00067-2158 | I | PS5-25-04 - Crude Oil Export Pump C | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TIT-1101 | T-00067-2159 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-TIT-1105 | T-00067-2160 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-4103 | T-00067-2161 | I | PS5-71-04 - CFO Storage Tank | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TIT-0002C | T-00067-2162 | I | PS5-25-04 - Crude Oil Export Pump C | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-4102 | T-00067-2163 | I | PS5-71-04 - CFO Storage Tank | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TIT-0001 | T-00067-2164 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TIT-0002A | T-00067-2165 | I | PS5-25-02 - Crude Oil Export Pump A | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TIT-0004 | T-00067-2166 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-TIT-1201 | T-00067-2167 | I | PS5-28-06 - Relief Drum and Pump | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-HZL-0058 | T-00067-2168 | I | PS5-71-21 - Diesel Transfer Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-HZH-0058 | T-00067-2169 | I | PS5-71-21 - Diesel Transfer Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-IES-3200A | T-00067-2432 | I | PS5-25-02 - Crude Oil Export Pump A | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-IES-3200B | T-00067-2433 | I | PS5-25-02 - Crude Oil Export Pump A | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-IES-3300A | T-00067-2434 | I | PS5-25-03 - Crude Oil Export Pump B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-IES-3300B | T-00067-2435 | I | PS5-25-03 - Crude Oil Export Pump B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-IES-3400A | T-00067-2436 | I | PS5-25-04 - Crude Oil Export Pump C | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-IES-3400B | T-00067-2437 | I | PS5-25-04 - Crude Oil Export Pump C | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-IES-6400A | T-00067-2438 | I | PS5-25-02 - Crude Oil Export Pump A | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-IES-6400B | T-00067-2439 | I | PS5-25-02 - Crude Oil Export Pump A | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-IES-6500A | T-00067-2440 | I | PS5-25-03 - Crude Oil Export Pump B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-IES-6500B | T-00067-2441 | I | PS5-25-03 - Crude Oil Export Pump B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-IES-6600A | T-00067-2442 | I | PS5-25-04 - Crude Oil Export Pump C | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-IES-6600B | T-00067-2443 | I | PS5-25-04 - Crude Oil Export Pump C | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-IES-2008 | T-00067-2444 | I | PS5-28-10 - Oil Skimmer Package | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-IES-3300 | T-00067-2445 | I | PS5-28-06 - Relief Drum and Pump | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-IES-3400 | T-00067-2446 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-IES-3500 | T-00067-2447 | I | PS5-28-08 - Open Drain Sump and Pumps | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-IES-3600A | T-00067-2448 | I | PS5-28-08 - Open Drain Sump and Pumps | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-IES-3600B | T-00067-2449 | I | PS5-28-08 - Open Drain Sump and Pumps | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-IES-3700A | T-00067-2450 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-IES-3700B | T-00067-2451 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-IES-3800A | T-00067-2452 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-IES-3800B | T-00067-2453 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-IES-3800C | T-00067-2454 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-IES-3900A | T-00067-2455 | I | PS5-28-17 - Reinjection Pump | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-IES-3900B | T-00067-2456 | I | PS5-28-17 - Reinjection Pump | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-IES-3100A | T-00067-2457 | I | PS5-53-02 - Water Distribution Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-IES-3100B | T-00067-2458 | I | PS5-53-02 - Water Distribution Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IES-3300 | T-00067-2459 | I | PS5-60-24 - Cooling Water Tank & Pump | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IES-3400 | T-00067-2460 | I | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IES-3100A | T-00067-2461 | I | PS5-71-16 - Diesel Fuel Supply Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IES-3100B | T-00067-2462 | I | PS5-71-16 - Diesel Fuel Supply Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IES-3200 | T-00067-2463 | I | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IES-3300A | T-00067-2464 | I | PS5-71-05 - CFO Transfer Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IES-3300B | T-00067-2465 | I | PS5-71-05 - CFO Transfer Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IES-3400A | T-00067-2466 | I | PS5-71-13 - CFO Service Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IES-3400B | T-00067-2467 | I | PS5-71-13 - CFO Service Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IES-3500A | T-00067-2468 | I | PS5-71-21 - Diesel Transfer Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IES-3500B | T-00067-2469 | I | PS5-71-21 - Diesel Transfer Pump A/B | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-LB-6101A | T-00067-2560 | I | PS5-01-11 - Inergen for Power Gen Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-LB-6102A | T-00067-2561 | I | PS5-01-11 - Inergen for Power Gen Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-LB-6103A | T-00067-2562 | I | PS5-01-11 - Inergen for Power Gen Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-LB-6104A | T-00067-2563 | I | PS5-01-11 - Inergen for Power Gen Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-B401 | T-00067-2643 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-B901 | T-00067-2644 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-W501 | T-00067-2645 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AH-8401 | T-00067-2728 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AH-8402 | T-00067-2729 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AH-8403 | T-00067-2730 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8101A | T-00067-2731 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8101B | T-00067-2732 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8102A | T-00067-2733 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8102B | T-00067-2734 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8102C | T-00067-2735 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8201A | T-00067-2736 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8201B | T-00067-2737 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8202A | T-00067-2738 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8202B | T-00067-2739 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8202C | T-00067-2740 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8202D | T-00067-2741 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8301A | T-00067-2742 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8301B | T-00067-2743 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8302A | T-00067-2744 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8302B | T-00067-2745 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8304A | T-00067-2746 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8304B | T-00067-2747 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8305A | T-00067-2748 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8305B | T-00067-2749 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8307A | T-00067-2750 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8307B | T-00067-2751 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8308A | T-00067-2752 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8308B | T-00067-2753 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8311A | T-00067-2754 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8311B | T-00067-2755 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8313 | T-00067-2756 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8314 | T-00067-2757 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8315 | T-00067-2758 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8316 | T-00067-2759 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8317 | T-00067-2760 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8318 | T-00067-2761 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8319 | T-00067-2762 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8321 | T-00067-2763 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8322 | T-00067-2764 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8323 | T-00067-2765 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8324 | T-00067-2766 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8325 | T-00067-2767 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8401A | T-00067-2768 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8401B | T-00067-2769 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8403A | T-00067-2770 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8403B | T-00067-2771 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8404A | T-00067-2772 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8404B | T-00067-2773 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8405A | T-00067-2774 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8405B | T-00067-2775 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406A | T-00067-2776 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406B | T-00067-2777 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406C | T-00067-2778 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406D | T-00067-2779 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406E | T-00067-2780 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406F | T-00067-2781 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406G | T-00067-2782 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406H | T-00067-2783 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8407 | T-00067-2784 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PDIT-8207 | T-00067-2785 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PDIT-8407 | T-00067-2786 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PDIT-8408 | T-00067-2787 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PDIT-8409 | T-00067-2788 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PDIT-8411 | T-00067-2789 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PIT-8401 | T-00067-2790 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PIT-8402 | T-00067-2791 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PIT-8403 | T-00067-2792 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PIT-8404 | T-00067-2793 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8101 | T-00067-2794 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8201 | T-00067-2795 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8301 | T-00067-2796 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8302 | T-00067-2797 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8303 | T-00067-2798 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8304 | T-00067-2799 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8401 | T-00067-2800 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8402 | T-00067-2801 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8403 | T-00067-2802 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8404 | T-00067-2803 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8405 | T-00067-2804 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8406 | T-00067-2805 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8407 | T-00067-2806 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8408 | T-00067-2807 | I | PS5-09-03 - HVAC for Generator Building | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-23-SPZM-0003A | T-00067-2929 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-23-SPZM-0003B | T-00067-2930 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-23-SPZM-0003C | T-00067-2931 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-23-SPZM-0003D | T-00067-2932 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-23-SPZM-0004A | T-00067-2933 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-23-SPZM-0004B | T-00067-2934 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-23-SPZM-0004C | T-00067-2935 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-23-SPZM-0004D | T-00067-2936 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX08 - Electrical instrument | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RAB-B402-CC01 | T-00069-10850 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RAB-B902-CC01 | T-00069-10851 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RAB-W502-CC01 | T-00069-10852 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101A-CJ01 | T-00069-10853 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101B-CJ01 | T-00069-10854 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101C-CJ01 | T-00069-10855 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101D-CJ01 | T-00069-10856 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101E-CJ01 | T-00069-10857 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101F-CJ01 | T-00069-10858 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101G-CJ01 | T-00069-10859 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101H-CJ01 | T-00069-10860 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101I-CJ01 | T-00069-10861 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601A-CJ01 | T-00069-10862 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601B-CJ01 | T-00069-10863 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601C-CJ01 | T-00069-10864 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601D-CJ01 | T-00069-10865 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601E-CJ01 | T-00069-10866 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601F-CJ01 | T-00069-10867 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601G-CJ01 | T-00069-10868 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601H-CJ01 | T-00069-10869 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601I-CJ01 | T-00069-10870 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601J-CJ01 | T-00069-10871 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601K-CJ01 | T-00069-10872 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601L-CJ01 | T-00069-10873 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601M-CJ01 | T-00069-10874 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601N-CJ01 | T-00069-10875 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601O-CJ01 | T-00069-10876 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601P-CJ01 | T-00069-10877 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B101A-CJ01 | T-00069-10878 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B101B-CJ01 | T-00069-10879 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B101C-CJ01 | T-00069-10880 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B101D-CJ01 | T-00069-10881 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B201A-CJ01 | T-00069-10882 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B201B-CJ01 | T-00069-10883 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B201C-CJ01 | T-00069-10884 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B201D-CJ01 | T-00069-10885 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B201E-CJ01 | T-00069-10886 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B301A-CJ01 | T-00069-10887 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B301B-CJ01 | T-00069-10888 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B301C-CJ01 | T-00069-10889 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B301D-CJ01 | T-00069-10890 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B401A-CJ01 | T-00069-10891 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B401B-CJ01 | T-00069-10892 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B401C-CJ01 | T-00069-10893 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B401D-CJ01 | T-00069-10894 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B501A-CJ01 | T-00069-10895 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B601A-CJ01 | T-00069-10896 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701A-CJ01 | T-00069-10897 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701B-CJ01 | T-00069-10898 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701C-CJ01 | T-00069-10899 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701D-CJ01 | T-00069-10900 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701E-CJ01 | T-00069-10901 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701F-CJ01 | T-00069-10902 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701G-CJ01 | T-00069-10903 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701H-CJ01 | T-00069-10904 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701I-CJ01 | T-00069-10905 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B801A-CJ01 | T-00069-10906 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B801B-CJ01 | T-00069-10907 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B901A-CJ01 | T-00069-10908 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B901B-CJ01 | T-00069-10909 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B901C-CJ01 | T-00069-10910 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B901D-CJ01 | T-00069-10911 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B901E-CJ01 | T-00069-10912 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W201A-CJ01 | T-00069-10913 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W201B-CJ01 | T-00069-10914 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W201C-CJ01 | T-00069-10915 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W201D-CJ01 | T-00069-10916 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W301A-CJ01 | T-00069-10917 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W401A-CJ01 | T-00069-10918 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W501A-CJ01 | T-00069-10919 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W501B-CJ01 | T-00069-10920 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W501C-CJ01 | T-00069-10921 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W501D-CJ01 | T-00069-10922 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W501E-CJ01 | T-00069-10923 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W501F-CJ01 | T-00069-10924 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-B401-CJ01 | T-00069-10925 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-B901-CJ01 | T-00069-10926 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-W501-CJ01 | T-00069-10927 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AH-8401-CU01 | T-00069-11574 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AH-8401-CU02 | T-00069-11575 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AH-8402-CU01 | T-00069-11576 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AH-8402-CU02 | T-00069-11577 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AH-8403-CU01 | T-00069-11578 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AH-8403-CU02 | T-00069-11579 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8111A-CU01 | T-00069-11580 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8111A-CU02 | T-00069-11581 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8111B-CU01 | T-00069-11582 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8111B-CU02 | T-00069-11583 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8211A-CU01 | T-00069-11584 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8211A-CU02 | T-00069-11585 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8211B-CU01 | T-00069-11586 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8211B-CU02 | T-00069-11587 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8311A-A-CU01 | T-00069-11588 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8311A-A-CU02 | T-00069-11589 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8311B-B-CU01 | T-00069-11590 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8311B-B-CU02 | T-00069-11591 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8311C-A-CU01 | T-00069-11592 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8311C-A-CU02 | T-00069-11593 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8311D-B-CU01 | T-00069-11594 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8311D-B-CU02 | T-00069-11595 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8321A-A-CU01 | T-00069-11596 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8321A-A-CU02 | T-00069-11597 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8321B-B-CU01 | T-00069-11598 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8321B-B-CU02 | T-00069-11599 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8321C-A-CU01 | T-00069-11600 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8321C-A-CU02 | T-00069-11601 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8321D-B-CU01 | T-00069-11602 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8321D-B-CU02 | T-00069-11603 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8331A-A-CU01 | T-00069-11604 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8331A-A-CU02 | T-00069-11605 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8331B-B-CU01 | T-00069-11606 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8331B-B-CU02 | T-00069-11607 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8331C-A-CU01 | T-00069-11608 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8331C-A-CU02 | T-00069-11609 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8331D-B-CU01 | T-00069-11610 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8331D-B-CU02 | T-00069-11611 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8341A-A-CU01 | T-00069-11612 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8341A-A-CU02 | T-00069-11613 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8341B-B-CU01 | T-00069-11614 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8341B-B-CU02 | T-00069-11615 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8411A-CU01 | T-00069-11616 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8411A-CU02 | T-00069-11617 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8411B-CU01 | T-00069-11618 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8411B-CU02 | T-00069-11619 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8412A-CU01 | T-00069-11620 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8412A-CU02 | T-00069-11621 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8412B-CU01 | T-00069-11622 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8412B-CU02 | T-00069-11623 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8421A-CU01 | T-00069-11624 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8421A-CU02 | T-00069-11625 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8421B-CU01 | T-00069-11626 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8421B-CU02 | T-00069-11627 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8432A-CU01 | T-00069-11628 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8432A-CU02 | T-00069-11629 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8432B-CU01 | T-00069-11630 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8432B-CU02 | T-00069-11631 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8111A-CU01 | T-00069-11632 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8111B-CU01 | T-00069-11633 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8211A-CU01 | T-00069-11634 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8211B-CU01 | T-00069-11635 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8311A-A-CU01 | T-00069-11636 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8311A-B-CU01 | T-00069-11637 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8311B-A-CU01 | T-00069-11638 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8311B-B-CU01 | T-00069-11639 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8321A-A-CU01 | T-00069-11640 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8321A-B-CU01 | T-00069-11641 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8321B-A-CU01 | T-00069-11642 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8321B-B-CU01 | T-00069-11643 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8331A-A-CU01 | T-00069-11644 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8331A-B-CU01 | T-00069-11645 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8331B-A-CU01 | T-00069-11646 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8331B-B-CU01 | T-00069-11647 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8341A-A-CU01 | T-00069-11648 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8341A-B-CU01 | T-00069-11649 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8411A-CU01 | T-00069-11650 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8411B-CU01 | T-00069-11651 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442A-CU01 | T-00069-11652 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442A-CU02 | T-00069-11653 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442B-CU01 | T-00069-11654 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442B-CU02 | T-00069-11655 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442C-CU01 | T-00069-11656 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442C-CU02 | T-00069-11657 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442D-CU01 | T-00069-11658 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442D-CU02 | T-00069-11659 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442E-CU01 | T-00069-11660 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442E-CU02 | T-00069-11661 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442F-CU01 | T-00069-11662 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442F-CU02 | T-00069-11663 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442G-CU01 | T-00069-11664 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442G-CU02 | T-00069-11665 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442H-CU01 | T-00069-11666 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442H-CU02 | T-00069-11667 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0019-CJ01 | T-00069-11668 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0019-CU01 | T-00069-11669 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0019-CU02 | T-00069-11670 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0021-CJ01 | T-00069-11671 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0021-CU01 | T-00069-11672 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0021-CU02 | T-00069-11673 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0024-CJ01 | T-00069-11674 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0024-CU01 | T-00069-11675 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0024-CU02 | T-00069-11676 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0025-CJ01 | T-00069-11677 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0025-CU01 | T-00069-11678 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0025-CU02 | T-00069-11679 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0026-CJ01 | T-00069-11680 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0026-CU01 | T-00069-11681 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0026-CU02 | T-00069-11682 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0027-CJ01 | T-00069-11683 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0027-CU01 | T-00069-11684 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0027-CU02 | T-00069-11685 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0028-CJ01 | T-00069-11686 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0028-CU01 | T-00069-11687 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0028-CU02 | T-00069-11688 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0029-CJ01 | T-00069-11689 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0029-CU01 | T-00069-11690 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0029-CU02 | T-00069-11691 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0030-CJ01 | T-00069-11692 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0030-CU01 | T-00069-11693 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0030-CU02 | T-00069-11694 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0031-CJ01 | T-00069-11695 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0031-CU01 | T-00069-11696 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0031-CU02 | T-00069-11697 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0032-CJ01 | T-00069-11698 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0032-CU01 | T-00069-11699 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0032-CU02 | T-00069-11700 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0033-CJ01 | T-00069-11701 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0033-CU01 | T-00069-11702 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0033-CU02 | T-00069-11703 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-HE-8401A-CU01 | T-00069-11704 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-HE-8401B-CU01 | T-00069-11705 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8111A-CC01 | T-00069-11706 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8111B-CC01 | T-00069-11707 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8211A-CC01 | T-00069-11708 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8211B-CC01 | T-00069-11709 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8311A-A-CC01 | T-00069-11710 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8311A-B-CC01 | T-00069-11711 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8311B-A-CC01 | T-00069-11712 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8311B-B-CC01 | T-00069-11713 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8321A-A-CC01 | T-00069-11714 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8321A-B-CC01 | T-00069-11715 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8321B-A-CC01 | T-00069-11716 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8321B-B-CC01 | T-00069-11717 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8331A-A-CC01 | T-00069-11718 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8331A-B-CC01 | T-00069-11719 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8331B-A-CC01 | T-00069-11720 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8331B-B-CC01 | T-00069-11721 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8341A-A-CC01 | T-00069-11722 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8341A-B-CC01 | T-00069-11723 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8411A-CC01 | T-00069-11724 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8411B-CC01 | T-00069-11725 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8442A-CC01 | T-00069-11726 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8442B-CC01 | T-00069-11727 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8442C-CC01 | T-00069-11728 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8442D-CC01 | T-00069-11729 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8442E-CC01 | T-00069-11730 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8442F-CC01 | T-00069-11731 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8442G-CC01 | T-00069-11732 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8442H-CC01 | T-00069-11733 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8451A-CU01 | T-00069-11734 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8451A-CU02 | T-00069-11735 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8451B-CU01 | T-00069-11736 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8451B-CU02 | T-00069-11737 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PDIT-8207-CU01 | T-00069-11738 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PDIT-8407-CU01 | T-00069-11739 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PDIT-8408-CU01 | T-00069-11740 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PDIT-8409-CU01 | T-00069-11741 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PDIT-8411-CU01 | T-00069-11742 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PIT-8401-CU01 | T-00069-11743 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PIT-8402-CU01 | T-00069-11744 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PIT-8403-CU01 | T-00069-11745 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PIT-8404-CU01 | T-00069-11746 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TCV-8401-CU01 | T-00069-11747 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TCV-8401-CU02 | T-00069-11748 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TCV-8402-CU01 | T-00069-11749 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TCV-8402-CU02 | T-00069-11750 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8101-CU01 | T-00069-11751 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8201-CU01 | T-00069-11752 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8301-CU01 | T-00069-11753 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8302-CU01 | T-00069-11754 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8303-CU01 | T-00069-11755 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8304-CU01 | T-00069-11756 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8401-CU01 | T-00069-11757 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8402-CU01 | T-00069-11758 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8403-CU01 | T-00069-11759 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8404-CU01 | T-00069-11760 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8405-CU01 | T-00069-11761 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8406-CU01 | T-00069-11762 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8407-CU01 | T-00069-11763 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8408-CU01 | T-00069-11764 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-UZ-84600-CU01 | T-00069-11765 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-UZ-84600-CU02 | T-00069-11766 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8401-CU01 | T-00069-11767 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8401-CU02 | T-00069-11768 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8402-CU01 | T-00069-11769 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8402-CU02 | T-00069-11770 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8403-CU01 | T-00069-11771 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8403-CU02 | T-00069-11772 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8404-CU01 | T-00069-11773 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8404-CU02 | T-00069-11774 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8413-CU01 | T-00069-11775 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8413-CU02 | T-00069-11776 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8414-CU01 | T-00069-11777 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8414-CU02 | T-00069-11778 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004A-CU01 | T-00069-11779 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004A-CU02 | T-00069-11780 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004A-CU03 | T-00069-11781 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004A-CU04 | T-00069-11782 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004B-CU01 | T-00069-11783 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004B-CU02 | T-00069-11784 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004B-CU03 | T-00069-11785 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004B-CU04 | T-00069-11786 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004C-CU01 | T-00069-11787 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004C-CU02 | T-00069-11788 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004C-CU03 | T-00069-11789 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004C-CU04 | T-00069-11790 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU01 | T-00069-11791 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU02 | T-00069-11792 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU03 | T-00069-11793 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU04 | T-00069-11794 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU05 | T-00069-11795 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU06 | T-00069-11796 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU07 | T-00069-11797 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU08 | T-00069-11798 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU09 | T-00069-11799 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU10 | T-00069-11800 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU11 | T-00069-11801 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU12 | T-00069-11802 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU13 | T-00069-11803 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU14 | T-00069-11804 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU15 | T-00069-11805 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU16 | T-00069-11806 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU17 | T-00069-11807 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU18 | T-00069-11808 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU19 | T-00069-11809 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU20 | T-00069-11810 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU21 | T-00069-11811 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU22 | T-00069-11812 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU23 | T-00069-11813 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU24 | T-00069-11814 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU25 | T-00069-11815 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU26 | T-00069-11816 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU27 | T-00069-11817 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU28 | T-00069-11818 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU29 | T-00069-11819 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004D-CU01 | T-00069-11820 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004D-CU02 | T-00069-11821 | I | PS5-09-03 - HVAC for Generator Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1902-CJ01 | T-00069-12946 | I | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1703-CJ01 | T-00069-12947 | I | PS5-03-17 - FZ-17 - Power Generation Building - Generator Ro | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0001A-CC02 | T-00069-12948 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0001B-CC02 | T-00069-12949 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0001C-CC02 | T-00069-12950 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0001D-CC02 | T-00069-12951 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0001E-CC02 | T-00069-12952 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0001F-CC02 | T-00069-12953 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0001G-CC02 | T-00069-12954 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0003-CC03 | T-00069-12955 | I | PS5-60-22 - Power Gen Master UCP | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002A-CC01 | T-00069-12956 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002A-CC02 | T-00069-12957 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002A-CC03 | T-00069-12958 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002B-CC01 | T-00069-12959 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002B-CC02 | T-00069-12960 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002B-CC03 | T-00069-12961 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002C-CC01 | T-00069-12962 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002C-CC02 | T-00069-12963 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002C-CC03 | T-00069-12964 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002D-CC01 | T-00069-12965 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002D-CC02 | T-00069-12966 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002D-CC03 | T-00069-12967 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002E-CC01 | T-00069-12968 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002E-CC02 | T-00069-12969 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002E-CC03 | T-00069-12970 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002F-CC01 | T-00069-12971 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002F-CC02 | T-00069-12972 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002F-CC03 | T-00069-12973 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002G-CC01 | T-00069-12974 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002G-CC02 | T-00069-12975 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002G-CC03 | T-00069-12976 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001A-CC01 | T-00069-12977 | I | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001A-CC02 | T-00069-12978 | I | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001B-CC01 | T-00069-12979 | I | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001B-CC02 | T-00069-12980 | I | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001C-CC01 | T-00069-12981 | I | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001C-CC02 | T-00069-12982 | I | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001D-CC01 | T-00069-12983 | I | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001D-CC02 | T-00069-12984 | I | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001E-CC01 | T-00069-12985 | I | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001E-CC02 | T-00069-12986 | I | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001F-CC01 | T-00069-12987 | I | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001F-CC02 | T-00069-12988 | I | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001G-CC01 | T-00069-12989 | I | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001G-CC02 | T-00069-12990 | I | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0002-CC01 | T-00069-12991 | I | PS5-60-22 - Power Gen Master UCP | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0002-CC02 | T-00069-12992 | I | PS5-60-22 - Power Gen Master UCP | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0003-CC02 | T-00069-12993 | I | PS5-60-22 - Power Gen Master UCP | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0003-CC03 | T-00069-12994 | I | PS5-60-22 - Power Gen Master UCP | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8113A-CC01 | T-00069-12995 | I | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8113B-CC01 | T-00069-12996 | I | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8113C-CC01 | T-00069-12997 | I | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8113D-CC01 | T-00069-12998 | I | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8113E-CC01 | T-00069-12999 | I | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8113F-CC01 | T-00069-13000 | I | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8113G-CC01 | T-00069-13001 | I | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8114A-CC01 | T-00069-13002 | I | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8114B-CC01 | T-00069-13003 | I | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8114C-CC01 | T-00069-13004 | I | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8114D-CC01 | T-00069-13005 | I | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8114E-CC01 | T-00069-13006 | I | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8114F-CC01 | T-00069-13007 | I | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8114G-CC01 | T-00069-13008 | I | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004A-CC10 | T-00069-13009 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-BI-0007-CC01 | T-00069-4210 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-BI-0008-CC01 | T-00069-4211 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-BI-0009-CC01 | T-00069-4212 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FCV-0003A-CC01 | T-00069-4223 | I | PS5-01-02 - Fire Water Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FCV-0003B-CC01 | T-00069-4224 | I | PS5-01-03 - Fire Water Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FCV-0004A-CC01 | T-00069-4225 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FCV-0004B-CC01 | T-00069-4226 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FIT-0003A-CJ01 | T-00069-4227 | I | PS5-01-02 - Fire Water Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FIT-0003B-CJ01 | T-00069-4228 | I | PS5-01-03 - Fire Water Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FIT-0004A-CJ01 | T-00069-4229 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FIT-0004B-CJ01 | T-00069-4230 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FXS-0003A-CJ01 | T-00069-4231 | I | PS5-01-02 - Fire Water Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FXS-0003B-CJ01 | T-00069-4232 | I | PS5-01-03 - Fire Water Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FXS-0004A-CJ01 | T-00069-4233 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FXS-0004B-CJ01 | T-00069-4234 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FY-0003A-CJ01 | T-00069-4235 | I | PS5-01-02 - Fire Water Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FY-0003B-CJ01 | T-00069-4236 | I | PS5-01-03 - Fire Water Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FY-0004A-CJ01 | T-00069-4237 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FY-0004B-CJ01 | T-00069-4238 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-HS-3108AB-CJ01 | T-00069-4239 | I | PS5-01-02 - Fire Water Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-HS-3108BB-CJ01 | T-00069-4240 | I | PS5-01-03 - Fire Water Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-LB-6101A-CC01 | T-00069-4252 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-LB-6102A-CC01 | T-00069-4253 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-LB-6103A-CC01 | T-00069-4254 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-LB-6104A-CC01 | T-00069-4255 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-LIT-4101A-CJ01 | T-00069-4256 | I | PS5-01-02 - Fire Water Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-LIT-4101B-CJ01 | T-00069-4257 | I | PS5-01-02 - Fire Water Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-NMR-61001-CJ01 | T-00069-4259 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-NMR-61002-CJ01 | T-00069-4260 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-NMR-61003-CJ01 | T-00069-4261 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-NMR-61004-CJ01 | T-00069-4262 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-NMRA-61001-CJ01 | T-00069-4263 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-NMRA-61002-CJ01 | T-00069-4264 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-NMRA-61003-CJ01 | T-00069-4265 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-NMRA-61004-CJ01 | T-00069-4266 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-PDIT-0011A-CJ01 | T-00069-4267 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PDIT-0011B-CJ01 | T-00069-4268 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PDIT-0012A-CJ01 | T-00069-4269 | I | PS5-01-02 - Fire Water Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PDIT-0012B-CJ01 | T-00069-4270 | I | PS5-01-03 - Fire Water Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PIT-0003AA-CJ01 | T-00069-4271 | I | PS5-01-02 - Fire Water Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PIT-0003BA-CJ01 | T-00069-4272 | I | PS5-01-03 - Fire Water Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PIT-0004AA-CJ01 | T-00069-4273 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PIT-0004BA-CJ01 | T-00069-4274 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PIT-0010-CJ01 | T-00069-4275 | I | PS5-01-07 - Fire Water Ring Main & Distribution | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-01-PIT-0013-CJ01 | T-00069-4276 | I | PS5-01-07 - Fire Water Ring Main & Distribution | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-PIT-8101A-CJ01 | T-00069-4281 | I | PS5-01-10 - Water Mist Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-PIT-8101B-CJ01 | T-00069-4282 | I | PS5-01-10 - Water Mist Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-PIT-8101C-CJ01 | T-00069-4283 | I | PS5-01-10 - Water Mist Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-PIT-8101D-CJ01 | T-00069-4284 | I | PS5-01-10 - Water Mist Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-PIT-8101E-CJ01 | T-00069-4285 | I | PS5-01-10 - Water Mist Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-PIT-8101F-CJ01 | T-00069-4286 | I | PS5-01-10 - Water Mist Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-PIT-8101G-CJ01 | T-00069-4287 | I | PS5-01-10 - Water Mist Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-PIT-8101H-CJ01 | T-00069-4288 | I | PS5-01-10 - Water Mist Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-RAB-61001A-CJ01 | T-00069-4289 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61001B-CJ01 | T-00069-4290 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61002A-CJ01 | T-00069-4291 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61002B-CJ01 | T-00069-4292 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61003A-CJ01 | T-00069-4293 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61003B-CJ01 | T-00069-4294 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61004A-CJ01 | T-00069-4295 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61004B-CJ01 | T-00069-4296 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-SY-8101A-CJ01 | T-00069-4297 | I | PS5-01-10 - Water Mist Package | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-SY-8101B-CJ01 | T-00069-4298 | I | PS5-01-10 - Water Mist Package | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-SY-8101C-CJ01 | T-00069-4299 | I | PS5-01-10 - Water Mist Package | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-SY-8101D-CJ01 | T-00069-4300 | I | PS5-01-10 - Water Mist Package | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-SY-8101E-CJ01 | T-00069-4301 | I | PS5-01-10 - Water Mist Package | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-SY-8101F-CJ01 | T-00069-4302 | I | PS5-01-10 - Water Mist Package | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-SY-8101G-CJ01 | T-00069-4303 | I | PS5-01-10 - Water Mist Package | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-SY-8101H-CJ01 | T-00069-4304 | I | PS5-01-10 - Water Mist Package | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-0901-CC01 | T-00069-4331 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-0902-CC01 | T-00069-4332 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-0903-CC01 | T-00069-4333 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-0904-CC01 | T-00069-4334 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-0906-CC01 | T-00069-4335 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-0907-CC01 | T-00069-4336 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-0908-CC01 | T-00069-4337 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-0909-CC01 | T-00069-4338 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-1001-CC01 | T-00069-4339 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-1002-CC01 | T-00069-4340 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-1003-CC01 | T-00069-4341 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-1004-CC01 | T-00069-4342 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-1006-CC01 | T-00069-4343 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-1007-CC01 | T-00069-4344 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-1008-CC01 | T-00069-4345 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-1009-CC01 | T-00069-4346 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-1101-CC01 | T-00069-4347 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1102-CC01 | T-00069-4348 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1103-CC01 | T-00069-4349 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1104-CC01 | T-00069-4350 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1106-CC01 | T-00069-4351 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1107-CC01 | T-00069-4352 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1108-CC01 | T-00069-4353 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1109-CC01 | T-00069-4354 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1201-CC01 | T-00069-4355 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1202-CC01 | T-00069-4356 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1203-CC01 | T-00069-4357 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1204-CC01 | T-00069-4358 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDLHP-0137-CJ01 | T-00069-4359 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDLHP-0142-CJ01 | T-00069-4360 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDLHP-0143-CJ01 | T-00069-4361 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDLHP-0144-CJ01 | T-00069-4362 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDLHP-0146-CJ01 | T-00069-4363 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDLHP-0147-CJ01 | T-00069-4364 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-03-GDLHP-0149-CJ01 | T-00069-4365 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-03-GDLHP-0150-CJ01 | T-00069-4366 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-03-GDLHP-0401-CJ01 | T-00069-4367 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-RDH-0302-CJ01 | T-00069-4381 | I | PS5-03-03 - FZ-03 - Buildings Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0303-CJ01 | T-00069-4382 | I | PS5-03-03 - FZ-03 - Buildings Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0601-CJ01 | T-00069-4383 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDH-0602-CJ01 | T-00069-4384 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDH-0603-CJ01 | T-00069-4385 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDH-0604-CJ01 | T-00069-4386 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDH-0605-CJ01 | T-00069-4387 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDH-0606-CJ01 | T-00069-4388 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDH-0607-CJ01 | T-00069-4389 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0608-CJ01 | T-00069-4390 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0609-CJ01 | T-00069-4391 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0610-CJ01 | T-00069-4392 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0611-CJ01 | T-00069-4393 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0612-CJ01 | T-00069-4394 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0614-CJ01 | T-00069-4395 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-RDH-0615-CJ01 | T-00069-4396 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-RDH-0616-CJ01 | T-00069-4397 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-RDH-0617-CJ01 | T-00069-4398 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDH-0618-CJ01 | T-00069-4399 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDH-0620-CJ01 | T-00069-4400 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDH-0828-CJ01 | T-00069-4401 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0829-CJ01 | T-00069-4402 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0830-CJ01 | T-00069-4403 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-03-RDH-0831-CJ01 | T-00069-4404 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-03-RDH-0901-CJ01 | T-00069-4405 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0902-CJ01 | T-00069-4406 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0903-CJ01 | T-00069-4407 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0904-CJ01 | T-00069-4408 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0905-CJ01 | T-00069-4409 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0906-CJ01 | T-00069-4410 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0909-CJ01 | T-00069-4411 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0910-CJ01 | T-00069-4412 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0911-CJ01 | T-00069-4413 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0912-CJ01 | T-00069-4414 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1001-CJ01 | T-00069-4415 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1002-CJ01 | T-00069-4416 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1003-CJ01 | T-00069-4417 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1004-CJ01 | T-00069-4418 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1005-CJ01 | T-00069-4419 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1006-CJ01 | T-00069-4420 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1009-CJ01 | T-00069-4421 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1010-CJ01 | T-00069-4422 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1011-CJ01 | T-00069-4423 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1012-CJ01 | T-00069-4424 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1101-CJ01 | T-00069-4425 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1102-CJ01 | T-00069-4426 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1103-CJ01 | T-00069-4427 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1104-CJ01 | T-00069-4428 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1105-CJ01 | T-00069-4429 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1106-CJ01 | T-00069-4430 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1109-CJ01 | T-00069-4431 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1110-CJ01 | T-00069-4432 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1111-CJ01 | T-00069-4433 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1112-CJ01 | T-00069-4434 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1201-CJ01 | T-00069-4435 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1202-CJ01 | T-00069-4436 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1203-CJ01 | T-00069-4437 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1204-CJ01 | T-00069-4438 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1205-CJ01 | T-00069-4439 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1302-CJ01 | T-00069-4440 | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1303-CJ01 | T-00069-4441 | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1304-CJ01 | T-00069-4442 | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1901-CJ01 | T-00069-4443 | I | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1903-CJ01 | T-00069-4444 | I | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0104-CJ01 | T-00069-4445 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDIR-0105-CJ01 | T-00069-4446 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDIR-0106-CJ01 | T-00069-4447 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDIR-0107-CJ01 | T-00069-4448 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0108-CJ01 | T-00069-4449 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDIR-0109-CJ01 | T-00069-4450 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDIR-0110-CJ01 | T-00069-4451 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDIR-0111-CJ01 | T-00069-4452 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDIR-0112-CJ01 | T-00069-4453 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDIR-0113-CJ01 | T-00069-4454 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDIR-0114-CJ01 | T-00069-4455 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-03-RDIR-0115-CJ01 | T-00069-4456 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-03-RDIR-0116-CJ01 | T-00069-4457 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-03-RDIR-0117-CJ01 | T-00069-4458 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-03-RDIR-0118-CJ01 | T-00069-4459 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-03-RDIR-0121-CJ01 | T-00069-4460 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-03-RDIR-0122-CJ01 | T-00069-4461 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-03-RDIR-0123-CJ01 | T-00069-4462 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-03-RDIR-0124-CJ01 | T-00069-4463 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0125-CJ01 | T-00069-4464 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-03-RDIR-0126-CJ01 | T-00069-4465 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-03-RDIR-0127-CJ01 | T-00069-4466 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-03-RDIR-0128-CJ01 | T-00069-4467 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0129-CJ01 | T-00069-4468 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0130-CJ01 | T-00069-4469 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0131-CJ01 | T-00069-4470 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0132-CJ01 | T-00069-4471 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0133-CJ01 | T-00069-4472 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0137-CJ01 | T-00069-4473 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | B:0/1 | Yes | Open + RFI Submitted
PS5-03-RDIR-0138-CJ01 | T-00069-4474 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDIR-0141-CJ01 | T-00069-4475 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDIR-0142-CJ01 | T-00069-4476 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | B:0/1 | Yes | Open + RFI Submitted
PS5-03-RDIR-0403-CJ01 | T-00069-4477 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-03-RDIR-0404-CJ01 | T-00069-4478 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDIR-0405-CJ01 | T-00069-4479 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDIR-0406-CJ01 | T-00069-4480 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0409-CJ01 | T-00069-4481 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDIR-0411-CJ01 | T-00069-4482 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDIR-0819-CJ01 | T-00069-4483 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-RDIR-0820-CJ01 | T-00069-4484 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-RDIR-0832-CJ01 | T-00069-4485 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-RDIR-0833-CJ01 | T-00069-4486 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1401-CJ01 | T-00069-4487 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1402-CJ01 | T-00069-4488 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1403-CJ01 | T-00069-4489 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1404-CJ01 | T-00069-4490 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1405-CJ01 | T-00069-4491 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1406-CJ01 | T-00069-4492 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1407-CJ01 | T-00069-4493 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1408-CJ01 | T-00069-4494 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1501-CJ01 | T-00069-4495 | I | PS5-03-15 - FZ-15 - Power Generation Building - Generator Ro | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1502-CJ01 | T-00069-4496 | I | PS5-03-15 - FZ-15 - Power Generation Building - Generator Ro | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1503-CJ01 | T-00069-4497 | I | PS5-03-15 - FZ-15 - Power Generation Building - Generator Ro | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1601-CJ01 | T-00069-4498 | I | PS5-03-16 - FZ-16 - Power Generation Building - Generator Ro | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1602-CJ01 | T-00069-4499 | I | PS5-03-16 - FZ-16 - Power Generation Building - Generator Ro | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1603-CJ01 | T-00069-4500 | I | PS5-03-16 - FZ-16 - Power Generation Building - Generator Ro | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1701-CJ01 | T-00069-4501 | I | PS5-03-17 - FZ-17 - Power Generation Building - Generator Ro | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1702-CJ01 | T-00069-4502 | I | PS5-03-17 - FZ-17 - Power Generation Building - Generator Ro | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1801-CJ01 | T-00069-4503 | I | PS5-03-18 - FZ-18 - Power Generation Building - Generator Ro | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1802-CJ01 | T-00069-4504 | I | PS5-03-18 - FZ-18 - Power Generation Building - Generator Ro | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1803-CJ01 | T-00069-4505 | I | PS5-03-18 - FZ-18 - Power Generation Building - Generator Ro | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-2101-CJ01 | T-00069-4506 | I | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-2102-CJ01 | T-00069-4507 | I | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-2103-CJ01 | T-00069-4508 | I | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-G101A-CJ01 | T-00069-4509 | I | PS5-03-22 - FZ-G1 - Guard House | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-G101B-CJ01 | T-00069-4510 | I | PS5-03-22 - FZ-G1 - Guard House | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-0701-CJ01 | T-00069-4511 | I | PS5-03-07 - FZ-07 - Pretreatment Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-0702-CJ01 | T-00069-4512 | I | PS5-03-07 - FZ-07 - Pretreatment Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-0703-CJ01 | T-00069-4513 | I | PS5-03-07 - FZ-07 - Pretreatment Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-0704-CJ01 | T-00069-4514 | I | PS5-03-07 - FZ-07 - Pretreatment Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-0705-CJ01 | T-00069-4515 | I | PS5-03-07 - FZ-07 - Pretreatment Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-0907-CJ01 | T-00069-4516 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-0908-CJ01 | T-00069-4517 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-1007-CJ01 | T-00069-4518 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-1008-CJ01 | T-00069-4519 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-1107-CJ01 | T-00069-4520 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-1108-CJ01 | T-00069-4521 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-1207-CJ01 | T-00069-4522 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-1208-CJ01 | T-00069-4523 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0101-CJ01 | T-00069-4524 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-03-RMAC-0102-CJ01 | T-00069-4525 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-03-RMAC-0103-CJ01 | T-00069-4526 | I | PS5-03-01 - FZ-01 - Process Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-03-RMAC-0301-CJ01 | T-00069-4528 | I | PS5-03-03 - FZ-03 - Buildings Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0304-CJ01 | T-00069-4529 | I | PS5-03-03 - FZ-03 - Buildings Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0401-CJ01 | T-00069-4530 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-03-RMAC-0402-CJ01 | T-00069-4531 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-RMAC-0613-CJ01 | T-00069-4532 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-03-RMAC-0706-CJ01 | T-00069-4533 | I | PS5-03-07 - FZ-07 - Pretreatment Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0707-CJ01 | T-00069-4534 | I | PS5-03-07 - FZ-07 - Pretreatment Area | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0825-CJ01 | T-00069-4536 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0827-CJ01 | T-00069-4537 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0834-CJ01 | T-00069-4538 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-1301-CJ01 | T-00069-4539 | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-1410-CJ01 | T-00069-4540 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-1411-CJ01 | T-00069-4541 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-SEA-0001-CC01 | T-00069-4542 | I | PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-05-BI-0002-CC01 | T-00069-4551 | I | PS5-05-01 - Emergency Diesel Generator Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-05-BI-0002-CC02 | T-00069-4552 | I | PS5-05-01 - Emergency Diesel Generator Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-05-BI-0002-CC03 | T-00069-4553 | I | PS5-05-01 - Emergency Diesel Generator Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-05-BI-0002-CC04 | T-00069-4554 | I | PS5-05-01 - Emergency Diesel Generator Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-05-BI-0002-CC05 | T-00069-4555 | I | PS5-05-01 - Emergency Diesel Generator Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-05-BI-0002-CC06 | T-00069-4556 | I | PS5-05-01 - Emergency Diesel Generator Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-05-BI-0002-CJ01 | T-00069-4559 | I | PS5-05-01 - Emergency Diesel Generator Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-05-BI-0002-CJ02 | T-00069-4560 | I | PS5-05-01 - Emergency Diesel Generator Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-BI-0002-CJ03 | T-00069-4561 | I | PS5-05-01 - Emergency Diesel Generator Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-05-GC-8100-CC01 | T-00069-4562 | I | PS5-05-01 - Emergency Diesel Generator Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-05-IE-8101-CC01 | T-00069-4565 | I | PS5-05-01 - Emergency Diesel Generator Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-05-IG-0009-CC01 | T-00069-4566 | I | PS5-05-01 - Emergency Diesel Generator Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-05-IG-0009-CC02 | T-00069-4567 | I | PS5-05-01 - Emergency Diesel Generator Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-05-IG-0009-CJ01 | T-00069-4568 | I | PS5-05-01 - Emergency Diesel Generator Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-05-LIT-4101-CJ01 | T-00069-4569 | I | PS5-05-01 - Emergency Diesel Generator Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-05-UH-8100-CC01 | T-00069-4570 | I | PS5-05-01 - Emergency Diesel Generator Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-05-UH-8100-CC02 | T-00069-4571 | I | PS5-05-01 - Emergency Diesel Generator Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-1802A-CC01 | T-00069-4611 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-1802B-CC01 | T-00069-4613 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-1802C-CC01 | T-00069-4615 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-ESDV-0021-CC01 | T-00069-4642 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-ESDV-0021-CC02 | T-00069-4643 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-ESDV-0021-CC03 | T-00069-4644 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-ESDV-0023-CC01 | T-00069-4645 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-ESDV-0023-CC02 | T-00069-4646 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-ESDV-0023-CC03 | T-00069-4647 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-ESY-0021A-CJ01 | T-00069-4648 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-ESY-0021B-CJ01 | T-00069-4649 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-ESY-0023B-CJ01 | T-00069-4650 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-FCV-0003A-CC01 | T-00069-4651 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FCV-0003B-CC01 | T-00069-4652 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FCV-0003C-CC01 | T-00069-4653 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FCV-0004-CC01 | T-00069-4654 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FIT-0001-CJ01 | T-00069-4655 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | B:0/1 | Yes | Open + RFI Submitted
PS5-25-FIT-0003A-CJ01 | T-00069-4656 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-FIT-0003B-CJ01 | T-00069-4657 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-FIT-0003C-CJ01 | T-00069-4658 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FIT-0004-CJ01 | T-00069-4659 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-FXS-0003A-CJ01 | T-00069-4660 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FXS-0003B-CJ01 | T-00069-4661 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FXS-0003C-CJ01 | T-00069-4662 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FXS-0004-CJ01 | T-00069-4663 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FY-0003A-CJ01 | T-00069-4664 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-FY-0003B-CJ01 | T-00069-4665 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | B:0/1 | Yes | Open + RFI Submitted
PS5-25-FY-0003C-CJ01 | T-00069-4666 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FY-0004-CJ01 | T-00069-4667 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-HS-8101A-CJ01 | T-00069-4668 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-HS-8101B-CJ01 | T-00069-4669 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-HS-8101C-CJ01 | T-00069-4670 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-HS-8102A-CJ01 | T-00069-4671 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-HS-8102B-CJ01 | T-00069-4672 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-HS-8102C-CJ01 | T-00069-4673 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-MOV-0001-CC01 | T-00069-4674 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MOV-0002-CC01 | T-00069-4675 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-MOV-0003-CC01 | T-00069-4676 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-MOV-0008-CC01 | T-00069-4677 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MOV-0011-CC01 | T-00069-4678 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-MOV-0012-CC01 | T-00069-4679 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-MOV-0025-CC01 | T-00069-4680 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MOV-0026-CC01 | T-00069-4681 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-MOV-0026-CC02 | T-00069-4682 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-MOV-0027-CC01 | T-00069-4683 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-MOV-0027-CC02 | T-00069-4684 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | B:0/1 | Yes | Open + RFI Submitted
PS5-25-MOV-0028-CC01 | T-00069-4685 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MXS-0001-CJ01 | T-00069-4686 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MXS-0008-CJ01 | T-00069-4687 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MXS-0025-CJ01 | T-00069-4688 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MXS-0028-CJ01 | T-00069-4689 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PDIT-0034A-CJ01 | T-00069-4696 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PDIT-0034B-CJ01 | T-00069-4697 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-PDIT-0034C-CJ01 | T-00069-4698 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PDIT-0050-CJ01 | T-00069-4699 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PI-1102B-CJ01 | T-00069-4700 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | B:0/1 | Yes | Open + RFI Submitted
PS5-25-PI-1202B-CJ01 | T-00069-4701 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | B:0/1 | Yes | Open + RFI Submitted
PS5-25-PIT-0001-CJ01 | T-00069-4702 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-PIT-0003AA-CJ01 | T-00069-4703 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-PIT-0003BA-CJ01 | T-00069-4704 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-PIT-0003CA-CJ01 | T-00069-4705 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0004AA-CJ01 | T-00069-4706 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0004A-CJ01 | T-00069-4707 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0004B-CJ01 | T-00069-4708 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0004C-CJ01 | T-00069-4709 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0005A-CJ01 | T-00069-4710 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | B:0/1 | Yes | Open + RFI Submitted
PS5-25-PIT-0005B-CJ01 | T-00069-4711 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-PIT-0005C-CJ01 | T-00069-4712 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0007A-CJ01 | T-00069-4713 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-PIT-0007B-CJ01 | T-00069-4714 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-PIT-0007C-CJ01 | T-00069-4715 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0008A-CJ01 | T-00069-4716 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-PIT-0008B-CJ01 | T-00069-4717 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-PIT-0008C-CJ01 | T-00069-4718 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-PIT-0013-CJ01 | T-00069-4719 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-PIT-0018-CJ01 | T-00069-4720 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-PIT-0022-CJ01 | T-00069-4721 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-PIT-0035A-CJ01 | T-00069-4722 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0035B-CJ01 | T-00069-4723 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0035C-CJ01 | T-00069-4724 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0036A-CJ01 | T-00069-4725 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0036B-CJ01 | T-00069-4726 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0036C-CJ01 | T-00069-4727 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0046-CJ01 | T-00069-4728 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0053-CJ01 | T-00069-4730 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-PIT-0054A-CJ01 | T-00069-4731 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0054B-CJ01 | T-00069-4732 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0054C-CJ01 | T-00069-4733 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0070-CJ01 | T-00069-4734 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | B:0/1 | Yes | Open + RFI Submitted
PS5-25-PIT-1102-CJ01 | T-00069-4738 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | B:0/1 | Yes | Open + RFI Submitted
PS5-25-PIT-1202-CJ01 | T-00069-4739 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | B:0/1 | Yes | Open + RFI Submitted
PS5-25-SDV-0022-CC01 | T-00069-4740 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-SDV-0022-CC02 | T-00069-4741 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SDV-0035A-CC01 | T-00069-4742 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-SDV-0035B-CC01 | T-00069-4743 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-SDV-0035C-CC01 | T-00069-4744 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SDV-0036A-CC01 | T-00069-4745 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-SDV-0036B-CC01 | T-00069-4746 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SDV-0036C-CC01 | T-00069-4747 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SDV-0046-CC01 | T-00069-4748 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-SDV-0054A-CC01 | T-00069-4751 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-SDV-0054B-CC01 | T-00069-4752 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-SDV-0054C-CC01 | T-00069-4753 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SXS-0022-CJ01 | T-00069-4755 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SXS-0035A-CJ01 | T-00069-4756 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-SXS-0035B-CJ01 | T-00069-4757 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-SXS-0035C-CJ01 | T-00069-4758 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-SXS-0036A-CJ01 | T-00069-4759 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-SXS-0036B-CJ01 | T-00069-4760 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-SXS-0036C-CJ01 | T-00069-4761 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-SXS-0046-CJ01 | T-00069-4762 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-SXS-0054A-CJ01 | T-00069-4764 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SXS-0054B-CJ01 | T-00069-4765 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SXS-0054C-CJ01 | T-00069-4766 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0022-CJ01 | T-00069-4767 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-SY-0035AA-CJ01 | T-00069-4768 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-SY-0035AB-CJ01 | T-00069-4769 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0035BA-CJ01 | T-00069-4770 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-SY-0035BB-CJ01 | T-00069-4771 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0035CA-CJ01 | T-00069-4772 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0035CB-CJ01 | T-00069-4773 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0036AA-CJ01 | T-00069-4774 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-SY-0036AB-CJ01 | T-00069-4775 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0036BA-CJ01 | T-00069-4776 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0036BB-CJ01 | T-00069-4777 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0036CA-CJ01 | T-00069-4778 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0036CB-CJ01 | T-00069-4779 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0046A-CJ01 | T-00069-4780 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-SY-0046B-CJ01 | T-00069-4781 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-SY-0052B-CJ01 | T-00069-4783 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0054AA-CJ01 | T-00069-4784 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-SY-0054AB-CJ01 | T-00069-4785 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-SY-0054BA-CJ01 | T-00069-4786 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0054BB-CJ01 | T-00069-4787 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0054CA-CJ01 | T-00069-4788 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0054CB-CJ01 | T-00069-4789 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TIT-0001-CJ01 | T-00069-4790 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | B:0/1 | Yes | Open + RFI Submitted
PS5-25-TIT-0002A-CJ01 | T-00069-4791 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TIT-0002B-CJ01 | T-00069-4792 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TIT-0002C-CJ01 | T-00069-4793 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-TIT-0003A-CJ01 | T-00069-4794 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-TIT-0003B-CJ01 | T-00069-4795 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-TIT-0003C-CJ01 | T-00069-4796 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TIT-0004-CJ01 | T-00069-4797 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-TIT-1101-CJ01 | T-00069-4798 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | B:0/1 | Yes | Open + RFI Submitted
PS5-25-TIT-1201-CJ01 | T-00069-4799 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | B:0/1 | Yes | Open + RFI Submitted
PS5-25-XV-0053-CC01 | T-00069-4800 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-XV-0053-CC02 | T-00069-4801 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-XV-0070-CC01 | T-00069-4802 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-XXS-0053-CJ01 | T-00069-4803 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-XXS-0070-CJ01 | T-00069-4804 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-XY-0053-CJ01 | T-00069-4805 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-XY-0070-CJ01 | T-00069-4806 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-25-ZIT-0001-CC01 | T-00069-4807 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-ZIT-0002-CC01 | T-00069-4808 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-ZS-1101-CJ01 | T-00069-4809 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-ZS-1201-CJ01 | T-00069-4810 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-HXA-1402-CJ01 | T-00069-4818 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-HY-3901A-CJ01 | T-00069-4819 | I | PS5-28-17 - Reinjection Pump | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-28-HY-3901B-CJ01 | T-00069-4820 | I | PS5-28-17 - Reinjection Pump | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-28-LI-1101B-CJ01 | T-00069-4823 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-28-LI-1101C-CJ01 | T-00069-4824 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | B:0/1 | Yes | Open + RFI Submitted
PS5-28-LI-1402B-CJ01 | T-00069-4825 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-28-LIT-0002-CJ01 | T-00069-4826 | I | PS5-28-08 - Open Drain Sump and Pumps | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-28-LIT-0008-CJ01 | T-00069-4827 | I | PS5-28-08 - Open Drain Sump and Pumps | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-28-LIT-1101-CJ01 | T-00069-4828 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-28-LIT-1102-CJ01 | T-00069-4829 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-28-LIT-1201-CJ01 | T-00069-4830 | I | PS5-28-06 - Relief Drum and Pump | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-LIT-1202-CJ01 | T-00069-4831 | I | PS5-28-06 - Relief Drum and Pump | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-28-LIT-1301A-CJ01 | T-00069-4832 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-28-LIT-1301B-CJ01 | T-00069-4833 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-28-LIT-1301C-CJ01 | T-00069-4834 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-LIT-1401-CJ01 | T-00069-4835 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-28-LIT-1402-CJ01 | T-00069-4836 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-28-PIT-0015-CJ01 | T-00069-4837 | I | PS5-28-17 - Reinjection Pump | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-28-PIT-0033-CJ01 | T-00069-4838 | I | PS5-28-06 - Relief Drum and Pump | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PIT-0041-CJ01 | T-00069-4839 | I | PS5-28-17 - Reinjection Pump | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-28-PIT-0045-CJ01 | T-00069-4840 | I | PS5-28-17 - Reinjection Pump | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-28-PIT-0053A-CJ01 | T-00069-4841 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PIT-0053B-CJ01 | T-00069-4842 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PIT-0053C-CJ01 | T-00069-4843 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PIT-3901A-CJ01 | T-00069-4844 | I | PS5-28-17 - Reinjection Pump | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-28-PIT-3901B-CJ01 | T-00069-4845 | I | PS5-28-17 - Reinjection Pump | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-28-SDV-0045-CC01 | T-00069-4846 | I | PS5-28-17 - Reinjection Pump | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SDV-0045-CC02 | T-00069-4847 | I | PS5-28-17 - Reinjection Pump | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SDV-0053A-CC01 | T-00069-4848 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-28-SDV-0053A-CC02 | T-00069-4849 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SDV-0053B-CC01 | T-00069-4850 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SDV-0053B-CC02 | T-00069-4851 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SDV-0053C-CC01 | T-00069-4852 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SDV-0053C-CC02 | T-00069-4853 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SXS-0045-CJ01 | T-00069-4854 | I | PS5-28-17 - Reinjection Pump | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SXS-0053A-CJ01 | T-00069-4855 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-28-SXS-0053B-CJ01 | T-00069-4856 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-28-SXS-0053C-CJ01 | T-00069-4857 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SY-0045A-CJ01 | T-00069-4858 | I | PS5-28-17 - Reinjection Pump | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-28-SY-0045B-CJ01 | T-00069-4859 | I | PS5-28-17 - Reinjection Pump | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-28-SY-0053AA-CJ01 | T-00069-4860 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-28-SY-0053AB-CJ01 | T-00069-4861 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SY-0053BA-CJ01 | T-00069-4862 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-28-SY-0053BB-CJ01 | T-00069-4863 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-28-SY-0053CA-CJ01 | T-00069-4864 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SY-0053CB-CJ01 | T-00069-4865 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-TIT-1104-CJ01 | T-00069-4866 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-28-TIT-1105-CJ01 | T-00069-4867 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-28-TIT-1201-CJ01 | T-00069-4868 | I | PS5-28-06 - Relief Drum and Pump | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-TIT-1401-CJ01 | T-00069-4869 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-28-TIT-1402-CJ01 | T-00069-4870 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-28-TIT-2101-CJ01 | T-00069-4871 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-28-TIT-2201-CJ01 | T-00069-4872 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-50-FIT-0001-CJ01 | T-00069-4874 | I | PS5-50-03 - Water Pre-Treatment Package | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-53-LIT-4101-CJ01 | T-00069-4885 | I | PS5-53-01 - Utility Water / Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-LIT-4102-CJ01 | T-00069-4886 | I | PS5-53-01 - Utility Water / Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-PIT-0005-CJ01 | T-00069-4887 | I | PS5-53-02 - Water Distribution Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0001-CC01 | T-00069-4888 | I | PS5-60-27 - Compressed Air Starting Skid | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BE-0002-CC01 | T-00069-4889 | I | PS5-60-26 - Instrument Air Compressor Skid | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BE-0004A-CC01 | T-00069-4890 | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BE-0004B-CC01 | T-00069-4891 | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BE-0004C-CC01 | T-00069-4892 | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BE-0004D-CC01 | T-00069-4893 | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BE-0004E-CC01 | T-00069-4894 | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BE-0004F-CC01 | T-00069-4895 | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BE-0004G-CC01 | T-00069-4896 | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0001A-CC01 | T-00069-4897 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0001A-CC03 | T-00069-4898 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0001B-CC01 | T-00069-4899 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0001B-CC03 | T-00069-4900 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0001C-CC01 | T-00069-4901 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0001C-CC03 | T-00069-4902 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0001D-CC01 | T-00069-4903 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0001D-CC03 | T-00069-4904 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0001E-CC01 | T-00069-4905 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0001E-CC03 | T-00069-4906 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0001F-CC01 | T-00069-4907 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0001F-CC03 | T-00069-4908 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0001G-CC01 | T-00069-4909 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0001G-CC03 | T-00069-4910 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0002-CC01 | T-00069-4911 | I | PS5-60-22 - Power Gen Master UCP | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0002-CC02 | T-00069-4912 | I | PS5-60-22 - Power Gen Master UCP | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0002-CC03 | T-00069-4913 | I | PS5-60-22 - Power Gen Master UCP | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0002-CC04 | T-00069-4914 | I | PS5-60-22 - Power Gen Master UCP | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0003-CC01 | T-00069-4915 | I | PS5-60-22 - Power Gen Master UCP | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0003-CC02 | T-00069-4916 | I | PS5-60-22 - Power Gen Master UCP | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0004A-CCO1 | T-00069-4917 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0004B-CCO1 | T-00069-4918 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0004C-CCO1 | T-00069-4919 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0004D-CCO1 | T-00069-4920 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0004E-CCO1 | T-00069-4921 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0004F-CCO1 | T-00069-4922 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0004G-CCO1 | T-00069-4923 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005A-CC01 | T-00069-4924 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005A-CC02 | T-00069-4925 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005B-CC01 | T-00069-4926 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005B-CC02 | T-00069-4927 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005C-CC01 | T-00069-4928 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005C-CC02 | T-00069-4929 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005D-CC01 | T-00069-4930 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005D-CC02 | T-00069-4931 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005E-CC01 | T-00069-4932 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005E-CC02 | T-00069-4933 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005F-CC01 | T-00069-4934 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005F-CC02 | T-00069-4935 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005G-CC01 | T-00069-4936 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005G-CC02 | T-00069-4937 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006A-CC01 | T-00069-4938 | I | PS5-60-02 - Power Gen Package A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0006A-CC02 | T-00069-4939 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006A-CC03 | T-00069-4940 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006A-CC04 | T-00069-4941 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006A-CC05 | T-00069-4942 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0006A-CC06 | T-00069-4943 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006B-CC01 | T-00069-4944 | I | PS5-60-05 - Power Gen Package B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0006B-CC02 | T-00069-4945 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006B-CC03 | T-00069-4946 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006B-CC04 | T-00069-4947 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006B-CC05 | T-00069-4948 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0006B-CC06 | T-00069-4949 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006C-CC01 | T-00069-4950 | I | PS5-60-08 - Power Gen Package C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0006C-CC02 | T-00069-4951 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006C-CC03 | T-00069-4952 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006C-CC04 | T-00069-4953 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006C-CC05 | T-00069-4954 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0006C-CC06 | T-00069-4955 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006D-CC01 | T-00069-4956 | I | PS5-60-11 - Power Gen Package D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0006D-CC02 | T-00069-4957 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006D-CC03 | T-00069-4958 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006D-CC04 | T-00069-4959 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006D-CC05 | T-00069-4960 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0006D-CC06 | T-00069-4961 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CC01 | T-00069-4962 | I | PS5-60-14 - Power Gen Package E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0006E-CC02 | T-00069-4963 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CC03 | T-00069-4964 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CC04 | T-00069-4965 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CC05 | T-00069-4966 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0006E-CC06 | T-00069-4967 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CC01 | T-00069-4968 | I | PS5-60-17 - Power Gen Package F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0006F-CC02 | T-00069-4969 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CC03 | T-00069-4970 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CC04 | T-00069-4971 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CC05 | T-00069-4972 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0006F-CC06 | T-00069-4973 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CC01 | T-00069-4974 | I | PS5-60-20 - Power Gen Package G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0006G-CC02 | T-00069-4975 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CC03 | T-00069-4976 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CC04 | T-00069-4977 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CC05 | T-00069-4978 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0006G-CC06 | T-00069-4979 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0008A-CC01 | T-00069-4980 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0008A-CC02 | T-00069-4981 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0008B-CC01 | T-00069-4982 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0008B-CC02 | T-00069-4983 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0009A-CC01 | T-00069-4984 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0009A-CC02 | T-00069-4985 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0009B-CC01 | T-00069-4986 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0009B-CC02 | T-00069-4987 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0010A-CC01 | T-00069-4988 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0010A-CC02 | T-00069-4989 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0010B-CC01 | T-00069-4990 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0010B-CC02 | T-00069-4991 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0011A-CC01 | T-00069-4992 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0011A-CC02 | T-00069-4993 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0011B-CC01 | T-00069-4994 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0011B-CC02 | T-00069-4995 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0012A-CC01 | T-00069-4996 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0012A-CC02 | T-00069-4997 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0012B-CC01 | T-00069-4998 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0012B-CC02 | T-00069-4999 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0013A-CC01 | T-00069-5000 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0013A-CC02 | T-00069-5001 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0013B-CC01 | T-00069-5002 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0013B-CC02 | T-00069-5003 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0014A-CC01 | T-00069-5004 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0014A-CC02 | T-00069-5005 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0014B-CC01 | T-00069-5006 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0014B-CC02 | T-00069-5007 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016A-CC01 | T-00069-5008 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0016A-CC02 | T-00069-5009 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016A-CC03 | T-00069-5010 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0016A-CCO4 | T-00069-5011 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016B-CC01 | T-00069-5012 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0016B-CC02 | T-00069-5013 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016B-CC03 | T-00069-5014 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0016B-CCO4 | T-00069-5015 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016C-CC01 | T-00069-5016 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0016C-CC02 | T-00069-5017 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016C-CC03 | T-00069-5018 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0016C-CCO4 | T-00069-5019 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016D-CC01 | T-00069-5020 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0016D-CC02 | T-00069-5021 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016D-CC03 | T-00069-5022 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0016D-CCO4 | T-00069-5023 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016E-CC01 | T-00069-5024 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0016E-CC02 | T-00069-5025 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016E-CC03 | T-00069-5026 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0016E-CCO4 | T-00069-5027 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016F-CC01 | T-00069-5028 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0016F-CC02 | T-00069-5029 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016F-CC03 | T-00069-5030 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0016F-CCO4 | T-00069-5031 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016G-CC01 | T-00069-5032 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0016G-CC02 | T-00069-5033 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016G-CC03 | T-00069-5034 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-BI-0016G-CCO4 | T-00069-5035 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0017A-CC02 | T-00069-5036 | I | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0017B-CC02 | T-00069-5037 | I | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0017C-CC02 | T-00069-5038 | I | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0017D-CC02 | T-00069-5039 | I | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0017E-CC02 | T-00069-5040 | I | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0017F-CC02 | T-00069-5041 | I | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0017G-CC02 | T-00069-5042 | I | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0019A-CC01 | T-00069-5043 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019A-CC02 | T-00069-5044 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019B-CC01 | T-00069-5045 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019B-CC02 | T-00069-5046 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019C-CC01 | T-00069-5047 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019C-CC02 | T-00069-5048 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019D-CC01 | T-00069-5049 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019D-CC02 | T-00069-5050 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019E-CC01 | T-00069-5051 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019E-CC02 | T-00069-5052 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019F-CC01 | T-00069-5053 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0019F-CC02 | T-00069-5054 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019G-CC01 | T-00069-5055 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0019G-CC02 | T-00069-5056 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0002B-CC05 | T-00069-5057 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002C-CC05 | T-00069-5058 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0002D-CC05 | T-00069-5059 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0002E-CC05 | T-00069-5060 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0002F-CC05 | T-00069-5061 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0002G-CC05 | T-00069-5062 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003A-CC01 | T-00069-5063 | I | PS5-60-02 - Power Gen Package A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003A-CC02 | T-00069-5064 | I | PS5-60-02 - Power Gen Package A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003A-CC03 | T-00069-5065 | I | PS5-60-02 - Power Gen Package A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003A-CC04 | T-00069-5066 | I | PS5-60-02 - Power Gen Package A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003A-CC05 | T-00069-5067 | I | PS5-60-02 - Power Gen Package A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003A-CC06 | T-00069-5068 | I | PS5-60-02 - Power Gen Package A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003A-CC07 | T-00069-5069 | I | PS5-60-02 - Power Gen Package A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003A-CC08 | T-00069-5070 | I | PS5-60-02 - Power Gen Package A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003A-CC09 | T-00069-5071 | I | PS5-60-02 - Power Gen Package A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003A-CC10 | T-00069-5072 | I | PS5-60-02 - Power Gen Package A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003A-CC11 | T-00069-5073 | I | PS5-60-02 - Power Gen Package A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003A-CC15 | T-00069-5074 | I | PS5-60-02 - Power Gen Package A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003A-CC16 | T-00069-5075 | I | PS5-60-02 - Power Gen Package A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003A-CC17 | T-00069-5076 | I | PS5-60-02 - Power Gen Package A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003A-CC25 | T-00069-5081 | I | PS5-60-02 - Power Gen Package A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003A-CC26 | T-00069-5082 | I | PS5-60-02 - Power Gen Package A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003B-CC01 | T-00069-5083 | I | PS5-60-05 - Power Gen Package B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B-CC02 | T-00069-5084 | I | PS5-60-05 - Power Gen Package B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B-CC03 | T-00069-5085 | I | PS5-60-05 - Power Gen Package B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B-CC04 | T-00069-5086 | I | PS5-60-05 - Power Gen Package B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B-CC05 | T-00069-5087 | I | PS5-60-05 - Power Gen Package B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B-CC06 | T-00069-5088 | I | PS5-60-05 - Power Gen Package B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B-CC07 | T-00069-5089 | I | PS5-60-05 - Power Gen Package B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B-CC08 | T-00069-5090 | I | PS5-60-05 - Power Gen Package B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003B-CC09 | T-00069-5091 | I | PS5-60-05 - Power Gen Package B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003B-CC10 | T-00069-5092 | I | PS5-60-05 - Power Gen Package B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B-CC11 | T-00069-5093 | I | PS5-60-05 - Power Gen Package B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B-CC15 | T-00069-5094 | I | PS5-60-05 - Power Gen Package B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003B-CC16 | T-00069-5095 | I | PS5-60-05 - Power Gen Package B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003B-CC17 | T-00069-5096 | I | PS5-60-05 - Power Gen Package B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003B-CC25 | T-00069-5101 | I | PS5-60-05 - Power Gen Package B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003B-CC26 | T-00069-5102 | I | PS5-60-05 - Power Gen Package B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003C-CC01 | T-00069-5103 | I | PS5-60-08 - Power Gen Package C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CC02 | T-00069-5104 | I | PS5-60-08 - Power Gen Package C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CC03 | T-00069-5105 | I | PS5-60-08 - Power Gen Package C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CC04 | T-00069-5106 | I | PS5-60-08 - Power Gen Package C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CC05 | T-00069-5107 | I | PS5-60-08 - Power Gen Package C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CC06 | T-00069-5108 | I | PS5-60-08 - Power Gen Package C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CC07 | T-00069-5109 | I | PS5-60-08 - Power Gen Package C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CC08 | T-00069-5110 | I | PS5-60-08 - Power Gen Package C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003C-CC09 | T-00069-5111 | I | PS5-60-08 - Power Gen Package C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003C-CC10 | T-00069-5112 | I | PS5-60-08 - Power Gen Package C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CC11 | T-00069-5113 | I | PS5-60-08 - Power Gen Package C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CC15 | T-00069-5114 | I | PS5-60-08 - Power Gen Package C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CC16 | T-00069-5115 | I | PS5-60-08 - Power Gen Package C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003C-CC17 | T-00069-5116 | I | PS5-60-08 - Power Gen Package C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003C-CC25 | T-00069-5121 | I | PS5-60-08 - Power Gen Package C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003C-CC26 | T-00069-5122 | I | PS5-60-08 - Power Gen Package C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003D-CC01 | T-00069-5123 | I | PS5-60-11 - Power Gen Package D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CC02 | T-00069-5124 | I | PS5-60-11 - Power Gen Package D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CC03 | T-00069-5125 | I | PS5-60-11 - Power Gen Package D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CC04 | T-00069-5126 | I | PS5-60-11 - Power Gen Package D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CC05 | T-00069-5127 | I | PS5-60-11 - Power Gen Package D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CC06 | T-00069-5128 | I | PS5-60-11 - Power Gen Package D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CC07 | T-00069-5129 | I | PS5-60-11 - Power Gen Package D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CC08 | T-00069-5130 | I | PS5-60-11 - Power Gen Package D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003D-CC09 | T-00069-5131 | I | PS5-60-11 - Power Gen Package D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003D-CC10 | T-00069-5132 | I | PS5-60-11 - Power Gen Package D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CC11 | T-00069-5133 | I | PS5-60-11 - Power Gen Package D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CC15 | T-00069-5134 | I | PS5-60-11 - Power Gen Package D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CC16 | T-00069-5135 | I | PS5-60-11 - Power Gen Package D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003D-CC17 | T-00069-5136 | I | PS5-60-11 - Power Gen Package D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003D-CC25 | T-00069-5141 | I | PS5-60-11 - Power Gen Package D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003D-CC26 | T-00069-5142 | I | PS5-60-11 - Power Gen Package D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003E-CC01 | T-00069-5143 | I | PS5-60-14 - Power Gen Package E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CC02 | T-00069-5144 | I | PS5-60-14 - Power Gen Package E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CC03 | T-00069-5145 | I | PS5-60-14 - Power Gen Package E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CC04 | T-00069-5146 | I | PS5-60-14 - Power Gen Package E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CC05 | T-00069-5147 | I | PS5-60-14 - Power Gen Package E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CC06 | T-00069-5148 | I | PS5-60-14 - Power Gen Package E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003E-CC07 | T-00069-5149 | I | PS5-60-14 - Power Gen Package E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CC08 | T-00069-5150 | I | PS5-60-14 - Power Gen Package E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003E-CC09 | T-00069-5151 | I | PS5-60-14 - Power Gen Package E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003E-CC10 | T-00069-5152 | I | PS5-60-14 - Power Gen Package E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CC11 | T-00069-5153 | I | PS5-60-14 - Power Gen Package E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CC15 | T-00069-5154 | I | PS5-60-14 - Power Gen Package E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CC16 | T-00069-5155 | I | PS5-60-14 - Power Gen Package E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003E-CC17 | T-00069-5156 | I | PS5-60-14 - Power Gen Package E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003E-CC25 | T-00069-5161 | I | PS5-60-14 - Power Gen Package E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003E-CC26 | T-00069-5162 | I | PS5-60-14 - Power Gen Package E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003F-CC01 | T-00069-5163 | I | PS5-60-17 - Power Gen Package F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC02 | T-00069-5164 | I | PS5-60-17 - Power Gen Package F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC03 | T-00069-5165 | I | PS5-60-17 - Power Gen Package F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC04 | T-00069-5166 | I | PS5-60-17 - Power Gen Package F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC05 | T-00069-5167 | I | PS5-60-17 - Power Gen Package F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC06 | T-00069-5168 | I | PS5-60-17 - Power Gen Package F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC07 | T-00069-5169 | I | PS5-60-17 - Power Gen Package F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC08 | T-00069-5170 | I | PS5-60-17 - Power Gen Package F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC09 | T-00069-5171 | I | PS5-60-17 - Power Gen Package F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC10 | T-00069-5172 | I | PS5-60-17 - Power Gen Package F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC11 | T-00069-5173 | I | PS5-60-17 - Power Gen Package F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC15 | T-00069-5174 | I | PS5-60-17 - Power Gen Package F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC16 | T-00069-5175 | I | PS5-60-17 - Power Gen Package F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003F-CC17 | T-00069-5176 | I | PS5-60-17 - Power Gen Package F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003F-CC25 | T-00069-5181 | I | PS5-60-17 - Power Gen Package F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003F-CC26 | T-00069-5182 | I | PS5-60-17 - Power Gen Package F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003G-CC01 | T-00069-5183 | I | PS5-60-20 - Power Gen Package G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC02 | T-00069-5184 | I | PS5-60-20 - Power Gen Package G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC03 | T-00069-5185 | I | PS5-60-20 - Power Gen Package G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003G-CC04 | T-00069-5186 | I | PS5-60-20 - Power Gen Package G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC05 | T-00069-5187 | I | PS5-60-20 - Power Gen Package G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC06 | T-00069-5188 | I | PS5-60-20 - Power Gen Package G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC07 | T-00069-5189 | I | PS5-60-20 - Power Gen Package G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC08 | T-00069-5190 | I | PS5-60-20 - Power Gen Package G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC09 | T-00069-5191 | I | PS5-60-20 - Power Gen Package G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC10 | T-00069-5192 | I | PS5-60-20 - Power Gen Package G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC11 | T-00069-5193 | I | PS5-60-20 - Power Gen Package G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC15 | T-00069-5194 | I | PS5-60-20 - Power Gen Package G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC16 | T-00069-5195 | I | PS5-60-20 - Power Gen Package G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003G-CC17 | T-00069-5196 | I | PS5-60-20 - Power Gen Package G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003G-CC25 | T-00069-5201 | I | PS5-60-20 - Power Gen Package G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003G-CC26 | T-00069-5202 | I | PS5-60-20 - Power Gen Package G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0004-CC01 | T-00069-5203 | I | PS5-60-22 - Power Gen Master UCP | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CC02 | T-00069-5204 | I | PS5-60-22 - Power Gen Master UCP | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CC03 | T-00069-5205 | I | PS5-60-22 - Power Gen Master UCP | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CC04 | T-00069-5206 | I | PS5-60-22 - Power Gen Master UCP | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CC05 | T-00069-5207 | I | PS5-60-22 - Power Gen Master UCP | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CC06 | T-00069-5208 | I | PS5-60-22 - Power Gen Master UCP | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CC07 | T-00069-5209 | I | PS5-60-22 - Power Gen Master UCP | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001A-CC01 | T-00069-5213 | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0001A-CC02 | T-00069-5214 | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001A-CC03 | T-00069-5215 | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0001A-CC04 | T-00069-5216 | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IN-0001B-CC01 | T-00069-5217 | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0001B-CC02 | T-00069-5218 | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001B-CC03 | T-00069-5219 | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0001B-CC04 | T-00069-5220 | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IN-0001C-CC01 | T-00069-5221 | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0001C-CC02 | T-00069-5222 | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IN-0001C-CC03 | T-00069-5223 | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0001C-CC04 | T-00069-5224 | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IN-0001D-CC01 | T-00069-5225 | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0001D-CC02 | T-00069-5226 | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IN-0001D-CC03 | T-00069-5227 | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0001D-CC04 | T-00069-5228 | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IN-0001E-CC01 | T-00069-5229 | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0001E-CC02 | T-00069-5230 | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IN-0001E-CC03 | T-00069-5231 | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0001E-CC04 | T-00069-5232 | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IN-0001F-CC01 | T-00069-5233 | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0001F-CC02 | T-00069-5234 | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IN-0001F-CC03 | T-00069-5235 | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0001F-CC04 | T-00069-5236 | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IN-0001G-CC01 | T-00069-5237 | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0001G-CC02 | T-00069-5238 | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IN-0001G-CC03 | T-00069-5239 | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0001G-CC04 | T-00069-5240 | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IN-0002A-CC01 | T-00069-5241 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002A-CC02 | T-00069-5242 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002A-CC03 | T-00069-5243 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002A-CC04 | T-00069-5244 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002A-CC05 | T-00069-5245 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002A-CC06 | T-00069-5246 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0002B-CC01 | T-00069-5247 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0002B-CC02 | T-00069-5248 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002B-CC03 | T-00069-5249 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002B-CC04 | T-00069-5250 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0002B-CC05 | T-00069-5251 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002B-CC06 | T-00069-5252 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0002C-CC01 | T-00069-5253 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0002C-CC02 | T-00069-5254 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002C-CC03 | T-00069-5255 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002C-CC04 | T-00069-5256 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0002C-CC05 | T-00069-5257 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002C-CC06 | T-00069-5258 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0002D-CC01 | T-00069-5259 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0002D-CC02 | T-00069-5260 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002D-CC03 | T-00069-5261 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002D-CC04 | T-00069-5262 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0002D-CC05 | T-00069-5263 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002D-CC06 | T-00069-5264 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0002E-CC01 | T-00069-5265 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0002E-CC02 | T-00069-5266 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002E-CC03 | T-00069-5267 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002E-CC04 | T-00069-5268 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0002E-CC05 | T-00069-5269 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002E-CC06 | T-00069-5270 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0002F-CC01 | T-00069-5271 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0002F-CC02 | T-00069-5272 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002F-CC03 | T-00069-5273 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002F-CC04 | T-00069-5274 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0002F-CC05 | T-00069-5275 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002F-CC06 | T-00069-5276 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0002G-CC01 | T-00069-5277 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0002G-CC02 | T-00069-5278 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002G-CC03 | T-00069-5279 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002G-CC04 | T-00069-5280 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0002G-CC05 | T-00069-5281 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002G-CC06 | T-00069-5282 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IN-0004A-CC11 | T-00069-5283 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002A-CC01 | T-00069-5284 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002A-CC02 | T-00069-5285 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002A-CC03 | T-00069-5286 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002A-CC04 | T-00069-5287 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002A-CC05 | T-00069-5288 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002A-CC06 | T-00069-5289 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002A-CC07 | T-00069-5290 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002A-CC08 | T-00069-5291 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002A-CC09 | T-00069-5292 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B-CC01 | T-00069-5293 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B-CC02 | T-00069-5294 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B-CC03 | T-00069-5295 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B-CC04 | T-00069-5296 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B-CC05 | T-00069-5297 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B-CC06 | T-00069-5298 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002C-CC01 | T-00069-5299 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-LA-0002C-CC02 | T-00069-5300 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-LA-0002C-CC03 | T-00069-5301 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-LA-0002C-CC04 | T-00069-5302 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-LA-0002C-CC05 | T-00069-5303 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-LA-0002C-CC06 | T-00069-5304 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-LA-0003-CC01 | T-00069-5305 | I | PS5-60-22 - Power Gen Master UCP | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LIT-4301-CJ01 | T-00069-5306 | I | PS5-60-24 - Cooling Water Tank & Pump | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-LIT-4401-CJ01 | T-00069-5307 | I | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-MOV-0005-CC01 | T-00069-5308 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-MOV-0005-CC02 | T-00069-5309 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-MOV-0006-CC01 | T-00069-5310 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-MOV-0006-CC02 | T-00069-5311 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-MOV-0011-CC01 | T-00069-5312 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-MOV-0011-CC02 | T-00069-5313 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-MOV-0012-CC01 | T-00069-5314 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-MOV-0012-CC02 | T-00069-5315 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-SEA-0001-CC01 | T-00069-5316 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-SEA-0001-CC02 | T-00069-5317 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-SEA-0001-CC03 | T-00069-5318 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-SEA-0001-CC04 | T-00069-5319 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-SEA-0001-CC05 | T-00069-5320 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-SEA-0001-CC06 | T-00069-5321 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-SEA-0001-CC07 | T-00069-5322 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-SEA-0001-CC10 | T-00069-5323 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-SEA-0001-CC11 | T-00069-5324 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-SEA-0001-CC12 | T-00069-5325 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-SEA-0001-CC13 | T-00069-5326 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-SEA-0001-CC14 | T-00069-5327 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-SEA-0001-CC15 | T-00069-5328 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-SEA-0001-CC16 | T-00069-5329 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-SEA-0001-CC17 | T-00069-5330 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-SY-0007-CC01 | T-00069-5332 | I | PS5-60-28 - Air Receiver A & Air Regulator A | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-SY-0008-CC01 | T-00069-5333 | I | PS5-60-29 - Air Receiver B & Air Regulator B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-SY-0009-CC01 | T-00069-5334 | I | PS5-60-30 - Air Receiver C & Air Regulator C | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-SY-0010-CC01 | T-00069-5335 | I | PS5-60-31 - Air Receiver D & Air Regulator D | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-SY-0011-CC01 | T-00069-5336 | I | PS5-60-32 - Air Receiver E & Air Regulator E | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-SY-0012-CC01 | T-00069-5337 | I | PS5-60-33 - Air Receiver F & Air Regulator F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-SY-0013-CC01 | T-00069-5338 | I | PS5-60-34 - Air Receiver G & Air Regulator G | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-VS-9101A-CC01 | T-00069-5339 | I | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-VS-9101B-CC01 | T-00069-5340 | I | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-VS-9101C-CC01 | T-00069-5341 | I | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-VS-9101D-CC01 | T-00069-5342 | I | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-VS-9101E-CC01 | T-00069-5343 | I | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-VS-9101F-CC01 | T-00069-5344 | I | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-VS-9101G-CC01 | T-00069-5345 | I | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-61-BI-0001-CC01 | T-00069-5346 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-BI-0001-CC02 | T-00069-5347 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-BI-0001-CC03 | T-00069-5348 | I | PS5-60-01 - Power Generation Package A | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-61-BI-0002-CC01 | T-00069-5349 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-BI-0002-CC02 | T-00069-5350 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/5 | Yes | Open + RFI Submitted
PS5-61-BI-0002-CC03 | T-00069-5351 | I | PS5-60-04 - Power Generation Package B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-61-BI-0003-CC01 | T-00069-5352 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-BI-0003-CC02 | T-00069-5353 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-BI-0003-CC03 | T-00069-5354 | I | PS5-60-07 - Power Generation Package C | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-61-BI-0004-CC01 | T-00069-5355 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-BI-0004-CC02 | T-00069-5356 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-BI-0004-CC03 | T-00069-5357 | I | PS5-60-10 - Power Generation Package D | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-61-BI-0005-CC01 | T-00069-5358 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-BI-0005-CC02 | T-00069-5359 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-BI-0005-CC03 | T-00069-5360 | I | PS5-60-13 - Power Generation Package E | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-61-BI-0006-CC01 | T-00069-5361 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-BI-0006-CC02 | T-00069-5362 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-BI-0006-CC03 | T-00069-5363 | I | PS5-60-16 - Power Generation Package F | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-61-BI-0007-CC01 | T-00069-5364 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-BI-0007-CC02 | T-00069-5365 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/3 | Yes | Open + RFI Submitted
PS5-61-BI-0007-CC03 | T-00069-5366 | I | PS5-60-19 - Power Generation Package G | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-71-BAV-0058-CC01 | T-00069-5376 | I | PS5-71-21 - Diesel Transfer Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-BAV-0059-CC01 | T-00069-5377 | I | PS5-71-18 - Diesel Separator Module | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-BI-0001A-CC01 | T-00069-5378 | I | PS5-71-06 - Crude Fuel Separation Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0001B-CC01 | T-00069-5379 | I | PS5-71-06 - Crude Fuel Separation Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0002-CC01 | T-00069-5381 | I | PS5-71-18 - Diesel Separator Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0003-CC01 | T-00069-5382 | I | PS5-71-08 - CFO Pre-Pressure Modules | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-BI-0003-CC02 | T-00069-5383 | I | PS5-71-08 - CFO Pre-Pressure Modules | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0003-CC03 | T-00069-5384 | I | PS5-71-08 - CFO Pre-Pressure Modules | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0003-CC04 | T-00069-5385 | I | PS5-71-08 - CFO Pre-Pressure Modules | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0004-CC01 | T-00069-5386 | I | PS5-71-08 - CFO Pre-Pressure Modules | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0005-CC01 | T-00069-5387 | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0005-CC02 | T-00069-5388 | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-BI-0006-CC01 | T-00069-5389 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0008A-CC01 | T-00069-5390 | I | PS5-71-06 - Crude Fuel Separation Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0008A-CC02 | T-00069-5391 | I | PS5-71-06 - Crude Fuel Separation Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0008B-CC01 | T-00069-5392 | I | PS5-71-06 - Crude Fuel Separation Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0008B-CC02 | T-00069-5393 | I | PS5-71-06 - Crude Fuel Separation Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0009-CC01 | T-00069-5394 | I | PS5-71-18 - Diesel Separator Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0009-CC02 | T-00069-5395 | I | PS5-71-18 - Diesel Separator Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0009-CC03 | T-00069-5396 | I | PS5-71-18 - Diesel Separator Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0009-CC04 | T-00069-5397 | I | PS5-71-18 - Diesel Separator Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0010-CC01 | T-00069-5398 | I | PS5-71-18 - Diesel Separator Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0011A-CC01 | T-00069-5399 | I | PS5-71-06 - Crude Fuel Separation Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0011A-CC02 | T-00069-5400 | I | PS5-71-06 - Crude Fuel Separation Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0011A-CC03 | T-00069-5401 | I | PS5-71-06 - Crude Fuel Separation Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0011A-CC04 | T-00069-5402 | I | PS5-71-06 - Crude Fuel Separation Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0011A-CC05 | T-00069-5403 | I | PS5-71-06 - Crude Fuel Separation Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0011B-CC01 | T-00069-5404 | I | PS5-71-06 - Crude Fuel Separation Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0011B-CC02 | T-00069-5405 | I | PS5-71-06 - Crude Fuel Separation Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0011B-CC03 | T-00069-5406 | I | PS5-71-06 - Crude Fuel Separation Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0011B-CC04 | T-00069-5407 | I | PS5-71-06 - Crude Fuel Separation Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0011B-CC05 | T-00069-5408 | I | PS5-71-06 - Crude Fuel Separation Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FCV-0018-CC01 | T-00069-5441 | I | PS5-71-13 - CFO Service Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FCV-0019-CC01 | T-00069-5442 | I | PS5-71-21 - Diesel Transfer Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FCV-0020-CC01 | T-00069-5443 | I | PS5-71-05 - CFO Transfer Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0005-CJ01 | T-00069-5444 | I | PS5-71-17 - Diesel Fuel Distribution Header | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-FIT-0011A-CJ01 | T-00069-5445 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0011B-CJ01 | T-00069-5446 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0012-CJ01 | T-00069-5447 | I | PS5-71-17 - Diesel Fuel Distribution Header | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0018-CJ01 | T-00069-5448 | I | PS5-71-13 - CFO Service Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0019-CJ01 | T-00069-5449 | I | PS5-71-21 - Diesel Transfer Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-71-FIT-0020-CJ01 | T-00069-5450 | I | PS5-71-05 - CFO Transfer Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FXS-0018-CJ01 | T-00069-5451 | I | PS5-71-13 - CFO Service Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-FXS-0019-CJ01 | T-00069-5452 | I | PS5-71-21 - Diesel Transfer Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-FXS-0020-CJ01 | T-00069-5453 | I | PS5-71-05 - CFO Transfer Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-71-FY-0018-CJ01 | T-00069-5454 | I | PS5-71-13 - CFO Service Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FY-0019-CJ01 | T-00069-5455 | I | PS5-71-21 - Diesel Transfer Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-FY-0020-CJ01 | T-00069-5456 | I | PS5-71-05 - CFO Transfer Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-71-IN-0001-CC01 | T-00069-5457 | I | PS5-71-19 - Diesel Separator Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0001-CC02 | T-00069-5458 | I | PS5-71-19 - Diesel Separator Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0001-CC03 | T-00069-5459 | I | PS5-71-19 - Diesel Separator Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0001-CC04 | T-00069-5460 | I | PS5-71-19 - Diesel Separator Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0001-CC05 | T-00069-5461 | I | PS5-71-19 - Diesel Separator Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0001-CC06 | T-00069-5462 | I | PS5-71-19 - Diesel Separator Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0001-CC07 | T-00069-5463 | I | PS5-71-19 - Diesel Separator Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0002-CC01 | T-00069-5467 | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0002-CC02 | T-00069-5468 | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0002-CC03 | T-00069-5469 | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0002-CC04 | T-00069-5470 | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0003-CC01 | T-00069-5474 | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0003-CC02 | T-00069-5475 | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0003-CC03 | T-00069-5476 | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0003-CC04 | T-00069-5477 | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0004A-CC01 | T-00069-5481 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004A-CC02 | T-00069-5482 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004A-CC03 | T-00069-5483 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0004A-CC04 | T-00069-5484 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0004A-CC05 | T-00069-5485 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0004A-CC06 | T-00069-5486 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0004A-CC07 | T-00069-5487 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0004A-CC11 | T-00069-5490 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004A-CC13 | T-00069-5492 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004B-CC01 | T-00069-5493 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004B-CC02 | T-00069-5494 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004B-CC03 | T-00069-5495 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004B-CC04 | T-00069-5496 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0004B-CC05 | T-00069-5497 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0004B-CC06 | T-00069-5498 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0004B-CC07 | T-00069-5499 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0004B-CC11 | T-00069-5502 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LCV-4101-CC01 | T-00069-5504 | I | PS5-71-04 - CFO Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LI-4201B-CJ01 | T-00069-5505 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-1201-CJ01 | T-00069-5506 | I | PS5-71-20 - Diesel Fuel Day Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-LIT-1202-CJ01 | T-00069-5507 | I | PS5-71-20 - Diesel Fuel Day Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-LIT-4101-CJ01 | T-00069-5508 | I | PS5-71-04 - CFO Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-4102-CJ01 | T-00069-5509 | I | PS5-71-04 - CFO Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-4201-CJ01 | T-00069-5510 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-4202-CJ01 | T-00069-5511 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-4401-CJ01 | T-00069-5512 | I | PS5-71-15 - Diesel Fuel Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-LIT-4402-CJ01 | T-00069-5513 | I | PS5-71-15 - Diesel Fuel Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-LXS-4101-CJ01 | T-00069-5514 | I | PS5-71-04 - CFO Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-LY-4101-CJ01 | T-00069-5515 | I | PS5-71-04 - CFO Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0001-CC01 | T-00069-5516 | I | PS5-71-08 - CFO Pre-Pressure Modules | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0001-CC02 | T-00069-5517 | I | PS5-71-08 - CFO Pre-Pressure Modules | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0002-CC01 | T-00069-5518 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0002-CC02 | T-00069-5519 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0003-CC01 | T-00069-5520 | I | PS5-71-08 - CFO Pre-Pressure Modules | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0003-CC02 | T-00069-5521 | I | PS5-71-08 - CFO Pre-Pressure Modules | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0004-CC01 | T-00069-5522 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0004-CC02 | T-00069-5523 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0007-CC01 | T-00069-5524 | I | PS5-71-08 - CFO Pre-Pressure Modules | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0007-CC02 | T-00069-5525 | I | PS5-71-08 - CFO Pre-Pressure Modules | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0008-CC01 | T-00069-5526 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0008-CC02 | T-00069-5527 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0009-CC01 | T-00069-5528 | I | PS5-71-08 - CFO Pre-Pressure Modules | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0009-CC02 | T-00069-5529 | I | PS5-71-08 - CFO Pre-Pressure Modules | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0010-CC01 | T-00069-5530 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0010-CC02 | T-00069-5531 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PDIT-0030-CJ01 | T-00069-5532 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PDIT-0056A-CJ01 | T-00069-5533 | I | PS5-71-05 - CFO Transfer Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PDIT-0056B-CJ01 | T-00069-5534 | I | PS5-71-05 - CFO Transfer Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PIT-0001-CJ01 | T-00069-5535 | I | PS5-71-20 - Diesel Fuel Day Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-PIT-0014-CJ01 | T-00069-5536 | I | PS5-71-17 - Diesel Fuel Distribution Header | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-PIT-0018A-CJ01 | T-00069-5537 | I | PS5-71-13 - CFO Service Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PIT-0019A-CJ01 | T-00069-5538 | I | PS5-71-21 - Diesel Transfer Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-PIT-0020A-CJ01 | T-00069-5539 | I | PS5-71-05 - CFO Transfer Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PIT-0022-CJ01 | T-00069-5540 | I | PS5-71-04 - CFO Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-71-PIT-0029-CJ01 | T-00069-5541 | I | PS5-71-15 - Diesel Fuel Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-PIT-0039-CJ01 | T-00069-5542 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-PIT-0089-CJ01 | T-00069-5543 | I | PS5-71-04 - CFO Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PIT-0090-CJ01 | T-00069-5544 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PIT-0091-CJ01 | T-00069-5545 | I | PS5-71-18 - Diesel Separator Module | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-PIT-0092-CJ01 | T-00069-5546 | I | PS5-71-20 - Diesel Fuel Day Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-PIT-2402A-CJ01 | T-00069-5547 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PIT-2402B-CJ01 | T-00069-5548 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PIT-3301A-CJ01 | T-00069-5549 | I | PS5-71-05 - CFO Transfer Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-71-PIT-3301B-CJ01 | T-00069-5550 | I | PS5-71-05 - CFO Transfer Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-PIT-3302A-CJ01 | T-00069-5551 | I | PS5-71-05 - CFO Transfer Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-71-PIT-3302B-CJ01 | T-00069-5552 | I | PS5-71-05 - CFO Transfer Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-PIT-3401A-CJ01 | T-00069-5553 | I | PS5-71-13 - CFO Service Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-PIT-3401B-CJ01 | T-00069-5554 | I | PS5-71-13 - CFO Service Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-PIT-3402A-CJ01 | T-00069-5555 | I | PS5-71-13 - CFO Service Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-PIT-3402B-CJ01 | T-00069-5556 | I | PS5-71-13 - CFO Service Pump A/B | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-PIT-4101A-CJ01 | T-00069-5557 | I | PS5-71-04 - CFO Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SDV-0001-CC01 | T-00069-5558 | I | PS5-71-20 - Diesel Fuel Day Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SDV-0001-CC02 | T-00069-5559 | I | PS5-71-20 - Diesel Fuel Day Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SDV-0022-CC01 | T-00069-5560 | I | PS5-71-04 - CFO Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SDV-0022-CC02 | T-00069-5561 | I | PS5-71-04 - CFO Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SDV-0029-CC01 | T-00069-5562 | I | PS5-71-15 - Diesel Fuel Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-SDV-0029-CC02 | T-00069-5563 | I | PS5-71-15 - Diesel Fuel Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SDV-0039-CC01 | T-00069-5564 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SDV-0039-CC02 | T-00069-5565 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SXS-0001-CJ01 | T-00069-5566 | I | PS5-71-20 - Diesel Fuel Day Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SXS-0022-CJ01 | T-00069-5567 | I | PS5-71-04 - CFO Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-SXS-0029-CJ01 | T-00069-5568 | I | PS5-71-15 - Diesel Fuel Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-SXS-0039-CJ01 | T-00069-5569 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-SY-0001-CJ01 | T-00069-5570 | I | PS5-71-20 - Diesel Fuel Day Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SY-0022-CJ01 | T-00069-5571 | I | PS5-71-04 - CFO Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-SY-0029-CJ01 | T-00069-5572 | I | PS5-71-15 - Diesel Fuel Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-SY-0039-CJ01 | T-00069-5573 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-TIT-0003-CJ01 | T-00069-5574 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-0004-CJ01 | T-00069-5575 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-0006-CJ01 | T-00069-5576 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-71-TIT-0007-CJ01 | T-00069-5577 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-71-TIT-2204-CJ01 | T-00069-5578 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-2301-CJ01 | T-00069-5579 | I | PS5-71-04 - CFO Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-2402AA-CJ01 | T-00069-5580 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-71-TIT-2402BA-CJ01 | T-00069-5581 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-71-TIT-4102-CJ01 | T-00069-5584 | I | PS5-71-04 - CFO Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-4103-CJ01 | T-00069-5585 | I | PS5-71-04 - CFO Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-4202-CJ01 | T-00069-5586 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-4203-CJ01 | T-00069-5587 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-XV-0089-CC01 | T-00069-5588 | I | PS5-71-04 - CFO Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-XV-0089-CC02 | T-00069-5589 | I | PS5-71-04 - CFO Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-XV-0090-CC01 | T-00069-5590 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-XV-0090-CC02 | T-00069-5591 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-XV-0091-CC01 | T-00069-5592 | I | PS5-71-18 - Diesel Separator Module | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-XV-0091-CC02 | T-00069-5593 | I | PS5-71-18 - Diesel Separator Module | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-XV-0092-CC01 | T-00069-5594 | I | PS5-71-20 - Diesel Fuel Day Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-XV-0092-CC02 | T-00069-5595 | I | PS5-71-20 - Diesel Fuel Day Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-XXS-0089-CJ01 | T-00069-5596 | I | PS5-71-04 - CFO Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-XXS-0090-CJ01 | T-00069-5597 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-XXS-0091-CJ01 | T-00069-5598 | I | PS5-71-18 - Diesel Separator Module | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-XXS-0092-CJ01 | T-00069-5599 | I | PS5-71-20 - Diesel Fuel Day Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-XY-0089-CJ01 | T-00069-5600 | I | PS5-71-04 - CFO Storage Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-XY-0090-CJ01 | T-00069-5601 | I | PS5-71-12 - CFO Service Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-XY-0091-CJ01 | T-00069-5602 | I | PS5-71-18 - Diesel Separator Module | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-XY-0092-CJ01 | T-00069-5603 | I | PS5-71-20 - Diesel Fuel Day Tank | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-74-PIT-0002-CJ01 | T-00069-5606 | I | PS5-74-04 - Nitrogen Distribution Header | CJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-03-RMAC-1409-CJ01 | T-00069-9408 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FO-0013B | T-00070-0051 | I | PS5-71-16 - Diesel Fuel Supply Pump A/B | CJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-FO-0009A | T-00070-0052 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-FO-0009B | T-00070-0053 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-FO-0003 | T-00070-0054 | I | PS5-28-05 - HP Relief Header | CJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-50-FE-0001 | T-00070-0055 | I | PS5-50-03 - Water Pre-Treatment Package | CJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-FO-0002 | T-00070-0056 | I | PS5-60-24 - Cooling Water Tank & Pump | CJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-FO-0005 | T-00070-0057 | I | PS5-28-06 - Relief Drum and Pump | CJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-FO-0001 | T-00070-0058 | I | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | CJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FO-0008 | T-00070-0059 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | CJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FO-0013A | T-00070-0060 | I | PS5-71-16 - Diesel Fuel Supply Pump A/B | CJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-74-FO-0001 | T-00070-0061 | I | PS5-74-04 - Nitrogen Distribution Header | CJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-FO-0002A | T-00070-0062 | I | PS5-28-08 - Open Drain Sump and Pumps | CJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-FO-0002B | T-00070-0063 | I | PS5-28-08 - Open Drain Sump and Pumps | CJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-FO-0004 | T-00070-0064 | I | PS5-28-16 - LP Relief Header | CJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-FO-0006 | T-00070-0065 | I | PS5-28-08 - Open Drain Sump and Pumps | CJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-FO-0007 | T-00070-0066 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-0006-CX01 | T-00071-0023 | I | PS5-09-01 - HVAC for Office and Facilities building | CJX12 - Optical fiber cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-0007-CX01 | T-00071-0024 | I | PS5-09-04 - HVAC for Workshop & Warehouse | CJX12 - Optical fiber cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-09-LB-0008-CX01 | T-00071-0025 | I | PS5-09-03 - HVAC for Generator Building | CJX12 - Optical fiber cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-53-LA-0001-CX01 | T-00071-0026 | I | PS5-53-04 - Water Treatment Purification Package | CJX12 - Optical fiber cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-60-IE-0004-CX03 | T-00071-0027 | I | PS5-60-22 - Power Gen Master UCP | CJX12 - Optical fiber cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0004-CX04 | T-00071-0028 | I | PS5-60-22 - Power Gen Master UCP | CJX12 - Optical fiber cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-LA-0003-CX01 | T-00071-0029 | I | PS5-60-22 - Power Gen Master UCP | CJX12 - Optical fiber cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-74-LB-5101-CX01 | T-00071-0030 | I | PS5-74-02 - N2 Generation Skid (UCP) | CJX12 - Optical fiber cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-82-LA-0001-CX01 | T-00071-0031 | I | PS5-82-03 - Sewage Treatment Plant Package (UCP) | CJX12 - Optical fiber cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-75-LA-6200-CX01 | T-00071-0085 | I | PS5-75-01 - DRA Injection Package | CJX12 - Optical fiber cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-60-LA-0003-CX02 | T-00071-0090 | I | PS5-60-22 - Power Gen Master UCP | CJX12 - Optical fiber cable | To be completed | No | No RFI Yet | A:0/1, B:0/2 | Yes | Not Started
PS5-60-TW-0006G | T-00072-0165 | I | PS5-60-76 - Engine G Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TW-4203 | T-00072-0166 | I | PS5-71-12 - CFO Service Tank | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TW-0007 | T-00072-0167 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TW-0003 | T-00072-0168 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0007C | T-00072-0169 | I | PS5-60-72 - Engine C Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TW-0004 | T-00072-0170 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0005F | T-00072-0171 | I | PS5-60-75 - Engine F Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-TW-1201 | T-00072-0172 | I | PS5-28-06 - Relief Drum and Pump | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0007B | T-00072-0173 | I | PS5-60-71 - Engine B Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0006C | T-00072-0174 | I | PS5-60-72 - Engine C Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0008A | T-00072-0175 | I | PS5-60-70 - Engine A Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0007D | T-00072-0176 | I | PS5-60-73 - Engine D Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0008C | T-00072-0177 | I | PS5-60-72 - Engine C Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-TW-1402 | T-00072-0178 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0005G | T-00072-0179 | I | PS5-60-76 - Engine G Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-TW-1104 | T-00072-0180 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0008E | T-00072-0181 | I | PS5-60-74 - Engine E Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0007A | T-00072-0182 | I | PS5-60-70 - Engine A Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0006D | T-00072-0183 | I | PS5-60-73 - Engine D Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0008B | T-00072-0184 | I | PS5-60-71 - Engine B Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0007E | T-00072-0185 | I | PS5-60-74 - Engine E Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0008D | T-00072-0186 | I | PS5-60-73 - Engine D Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TW-0003B | T-00072-0187 | I | PS5-25-03 - Crude Oil Export Pump B | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TW-4202 | T-00072-0188 | I | PS5-71-12 - CFO Service Tank | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0008F | T-00072-0189 | I | PS5-60-75 - Engine F Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0006E | T-00072-0190 | I | PS5-60-74 - Engine E Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TW-0002A | T-00072-0191 | I | PS5-25-02 - Crude Oil Export Pump A | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TW-0003C | T-00072-0192 | I | PS5-25-04 - Crude Oil Export Pump C | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TW-0006 | T-00072-0193 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0006B | T-00072-0194 | I | PS5-60-71 - Engine B Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TW-0003A | T-00072-0195 | I | PS5-25-02 - Crude Oil Export Pump A | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TW-4103 | T-00072-0196 | I | PS5-71-04 - CFO Storage Tank | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-TW-1105 | T-00072-0197 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0006A | T-00072-0198 | I | PS5-60-70 - Engine A Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0007F | T-00072-0199 | I | PS5-60-75 - Engine F Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TW-0002B | T-00072-0200 | I | PS5-25-03 - Crude Oil Export Pump B | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TW-0001 | T-00072-0201 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TW-0004 | T-00072-0202 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TW-0002C | T-00072-0203 | I | PS5-25-04 - Crude Oil Export Pump C | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TW-4102 | T-00072-0204 | I | PS5-71-04 - CFO Storage Tank | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-74-TW-0001 | T-00072-0205 | I | PS5-74-04 - Nitrogen Distribution Header | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-TW-1401 | T-00072-0206 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0005A | T-00072-0207 | I | PS5-60-70 - Engine A Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0005B | T-00072-0208 | I | PS5-60-71 - Engine B Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0005C | T-00072-0209 | I | PS5-60-72 - Engine C Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0005D | T-00072-0210 | I | PS5-60-73 - Engine D Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0005E | T-00072-0211 | I | PS5-60-74 - Engine E Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0006F | T-00072-0212 | I | PS5-60-75 - Engine F Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0007G | T-00072-0213 | I | PS5-60-76 - Engine G Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0008G | T-00072-0214 | I | PS5-60-76 - Engine G Cooling system | CJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PG-1101B | T-00075-0197 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PG-0001 | T-00075-0198 | I | PS5-28-08 - Open Drain Sump and Pumps | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PG-0071 | T-00075-0199 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0005C | T-00075-0200 | I | PS5-60-72 - Engine C Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PG-0044 | T-00075-0201 | I | PS5-71-04 - CFO Storage Tank | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0006F | T-00075-0202 | I | PS5-60-75 - Engine F Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PG-0067B | T-00075-0203 | I | PS5-28-17 - Reinjection Pump | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0005E | T-00075-0204 | I | PS5-60-74 - Engine E Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0008D | T-00075-0205 | I | PS5-60-73 - Engine D Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PG-0053B | T-00075-0206 | I | PS5-71-05 - CFO Transfer Pump A/B | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PG-0053A | T-00075-0207 | I | PS5-71-05 - CFO Transfer Pump A/B | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PG-0070C | T-00075-0208 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PG-0050B | T-00075-0209 | I | PS5-71-21 - Diesel Transfer Pump A/B | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PG-0050A | T-00075-0210 | I | PS5-71-21 - Diesel Transfer Pump A/B | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0005A | T-00075-0211 | I | PS5-60-70 - Engine A Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PG-0007A | T-00075-0212 | I | PS5-28-08 - Open Drain Sump and Pumps | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PG-1201A | T-00075-0213 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PG-0002F | T-00075-0214 | I | PS5-60-33 - Air Receiver F & Air Regulator F | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0007G | T-00075-0215 | I | PS5-60-76 - Engine G Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0005F | T-00075-0216 | I | PS5-60-75 - Engine F Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0006G | T-00075-0217 | I | PS5-60-76 - Engine G Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0008A | T-00075-0218 | I | PS5-60-70 - Engine A Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PG-1101A | T-00075-0219 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PG-0027 | T-00075-0220 | I | PS5-60-24 - Cooling Water Tank & Pump | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PG-0002A | T-00075-0221 | I | PS5-60-28 - Air Receiver A & Air Regulator A | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PG-1401 | T-00075-0222 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-PG-0022B | T-00075-0223 | I | PS5-53-02 - Water Distribution Pump A/B | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0008C | T-00075-0224 | I | PS5-60-72 - Engine C Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PG-0002C | T-00075-0225 | I | PS5-60-30 - Air Receiver C & Air Regulator C | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PG-0002E | T-00075-0226 | I | PS5-60-32 - Air Receiver E & Air Regulator E | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PDG-0043A | T-00075-0227 | I | PS5-71-16 - Diesel Fuel Supply Pump A/B | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PG-0014A | T-00075-0228 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0007D | T-00075-0229 | I | PS5-60-73 - Engine D Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-74-TG-0001 | T-00075-0230 | I | PS5-74-04 - Nitrogen Distribution Header | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-PG-0022A | T-00075-0231 | I | PS5-53-02 - Water Distribution Pump A/B | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PG-0002B | T-00075-0232 | I | PS5-60-29 - Air Receiver B & Air Regulator B | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LG-0001 | T-00075-0233 | I | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0008E | T-00075-0234 | I | PS5-60-74 - Engine E Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PDG-0043B | T-00075-0235 | I | PS5-71-16 - Diesel Fuel Supply Pump A/B | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PG-1201 | T-00075-0236 | I | PS5-28-06 - Relief Drum and Pump | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PG-0002D | T-00075-0237 | I | PS5-60-31 - Air Receiver D & Air Regulator D | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-74-PG-0001 | T-00075-0238 | I | PS5-74-03 - Nitrogen Receiver | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0007A | T-00075-0239 | I | PS5-60-70 - Engine A Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PG-0005 | T-00075-0240 | I | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PDG-0049A | T-00075-0241 | I | PS5-71-21 - Diesel Transfer Pump A/B | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0008F | T-00075-0242 | I | PS5-60-75 - Engine F Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PG-1201B | T-00075-0243 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0007C | T-00075-0244 | I | PS5-60-72 - Engine C Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PG-0007B | T-00075-0245 | I | PS5-28-08 - Open Drain Sump and Pumps | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PG-0059B | T-00075-0246 | I | PS5-71-13 - CFO Service Pump A/B | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PG-0059A | T-00075-0247 | I | PS5-71-13 - CFO Service Pump A/B | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PG-0014B | T-00075-0248 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PG-0006A | T-00075-0249 | I | PS5-71-16 - Diesel Fuel Supply Pump A/B | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0005G | T-00075-0250 | I | PS5-60-76 - Engine G Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0006D | T-00075-0251 | I | PS5-60-73 - Engine D Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0007E | T-00075-0252 | I | PS5-60-74 - Engine E Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PG-0045 | T-00075-0253 | I | PS5-71-12 - CFO Service Tank | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PG-0007 | T-00075-0254 | I | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PDG-0049B | T-00075-0255 | I | PS5-71-21 - Diesel Transfer Pump A/B | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PG-0006B | T-00075-0256 | I | PS5-71-16 - Diesel Fuel Supply Pump A/B | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PG-0010 | T-00075-0257 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PG-0019 | T-00075-0258 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PG-0067A | T-00075-0259 | I | PS5-28-17 - Reinjection Pump | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PG-0070A | T-00075-0260 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PG-0070B | T-00075-0261 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PG-1101 | T-00075-0262 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PG-0002G | T-00075-0263 | I | PS5-60-34 - Air Receiver G & Air Regulator G | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0005D | T-00075-0264 | I | PS5-60-73 - Engine D Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0006A | T-00075-0265 | I | PS5-60-70 - Engine A Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0006C | T-00075-0266 | I | PS5-60-72 - Engine C Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0006E | T-00075-0267 | I | PS5-60-74 - Engine E Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0007F | T-00075-0268 | I | PS5-60-75 - Engine F Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0008G | T-00075-0269 | I | PS5-60-76 - Engine G Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0006B | T-00075-0270 | I | PS5-60-71 - Engine B Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0005B | T-00075-0271 | I | PS5-60-71 - Engine B Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0007B | T-00075-0272 | I | PS5-60-71 - Engine B Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TG-0008B | T-00075-0273 | I | PS5-60-71 - Engine B Cooling system | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PI-8401 | T-00075-0376 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PI-8402 | T-00075-0377 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PI-8403 | T-00075-0378 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PI-8404 | T-00075-0379 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PI-8405 | T-00075-0380 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PI-8406 | T-00075-0381 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PI-8407 | T-00075-0382 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PI-8408 | T-00075-0383 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PI-8409 | T-00075-0384 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PI-8411 | T-00075-0385 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PI-8412 | T-00075-0386 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PI-8413 | T-00075-0387 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PI-8414 | T-00075-0388 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PI-8415 | T-00075-0389 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PI-8416 | T-00075-0390 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TI-8401 | T-00075-0391 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TI-8402 | T-00075-0392 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TI-8403 | T-00075-0393 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TI-8404 | T-00075-0394 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TI-8405 | T-00075-0395 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TI-8406 | T-00075-0396 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TI-8407 | T-00075-0397 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TI-8408 | T-00075-0398 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TI-8409 | T-00075-0399 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TI-8411 | T-00075-0400 | I | PS5-09-03 - HVAC for Generator Building | CJX16 - Local gauge / indicator | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PSE-2401A | T-00076-0013 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX20 - Bursting disc | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PSE-2401B | T-00076-0014 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX20 - Bursting disc | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-ESDV-0021 | T-00077-0236 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-ESDV-0023 | T-00077-0237 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-XV-0091 | T-00077-0238 | I | PS5-71-18 - Diesel Separator Module | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-XV-0090 | T-00077-0239 | I | PS5-71-12 - CFO Service Tank | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SDV-0052 | T-00077-0240 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SDV-0054A | T-00077-0241 | I | PS5-25-02 - Crude Oil Export Pump A | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SDV-0053B | T-00077-0242 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SDV-0039 | T-00077-0243 | I | PS5-71-12 - CFO Service Tank | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SDV-0029 | T-00077-0244 | I | PS5-71-15 - Diesel Fuel Storage Tank | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SDV-0036A | T-00077-0245 | I | PS5-25-02 - Crude Oil Export Pump A | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SDV-0036C | T-00077-0246 | I | PS5-25-04 - Crude Oil Export Pump C | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SDV-0035B | T-00077-0247 | I | PS5-25-03 - Crude Oil Export Pump B | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SDV-0022 | T-00077-0248 | I | PS5-71-04 - CFO Storage Tank | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SDV-0054C | T-00077-0249 | I | PS5-25-04 - Crude Oil Export Pump C | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SDV-0053C | T-00077-0250 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-XV-0089 | T-00077-0251 | I | PS5-71-04 - CFO Storage Tank | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SDV-0045 | T-00077-0252 | I | PS5-28-17 - Reinjection Pump | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-XV-0053 | T-00077-0253 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-XV-0092 | T-00077-0254 | I | PS5-71-20 - Diesel Fuel Day Tank | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SDV-0053A | T-00077-0255 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SDV-0001 | T-00077-0256 | I | PS5-71-20 - Diesel Fuel Day Tank | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SDV-0022 | T-00077-0257 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SDV-0035A | T-00077-0258 | I | PS5-25-02 - Crude Oil Export Pump A | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SDV-0035C | T-00077-0259 | I | PS5-25-04 - Crude Oil Export Pump C | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SDV-0036B | T-00077-0260 | I | PS5-25-03 - Crude Oil Export Pump B | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SDV-0046 | T-00077-0261 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SDV-0054B | T-00077-0262 | I | PS5-25-03 - Crude Oil Export Pump B | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-XV-0070 | T-00077-0263 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MOV-0001 | T-00078-0131 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MOV-0008 | T-00078-0132 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MOV-0025 | T-00078-0133 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MOV-0028 | T-00078-0134 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MOV-0026 | T-00078-0137 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MOV-0027 | T-00078-0138 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-MOV-0012 | T-00078-0139 | I | PS5-71-12 - CFO Service Tank | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0007 | T-00078-0140 | I | PS5-71-08 - CFO Pre-Pressure Modules | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MOV-0003 | T-00078-0141 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-75-MOV-0001 | T-00078-0142 | I | PS5-28-07 - Open Drains (OD2) | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0010 | T-00078-0143 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0003 | T-00078-0144 | I | PS5-71-08 - CFO Pre-Pressure Modules | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MOV-0011 | T-00078-0145 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-MOV-0005 | T-00078-0146 | I | PS5-71-12 - CFO Service Tank | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0004 | T-00078-0147 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MOV-0012 | T-00078-0148 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0001 | T-00078-0149 | I | PS5-71-08 - CFO Pre-Pressure Modules | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-MOV-0006 | T-00078-0150 | I | PS5-71-12 - CFO Service Tank | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0002 | T-00078-0151 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0008 | T-00078-0152 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0009 | T-00078-0153 | I | PS5-71-08 - CFO Pre-Pressure Modules | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MOV-0002 | T-00078-0154 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-MOV-0011 | T-00078-0155 | I | PS5-71-12 - CFO Service Tank | CJX24 - Actuated on/off valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FCV-0004B | T-00079-0062 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX27 - Control valve - Pneumatic / Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FCV-0004 | T-00079-0063 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | CJX27 - Control valve - Pneumatic / Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FCV-0003A | T-00079-0064 | I | PS5-01-02 - Fire Water Pump A | CJX27 - Control valve - Pneumatic / Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FCV-0003B | T-00079-0065 | I | PS5-01-03 - Fire Water Pump B | CJX27 - Control valve - Pneumatic / Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FCV-0018 | T-00079-0066 | I | PS5-71-13 - CFO Service Pump A/B | CJX27 - Control valve - Pneumatic / Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FCV-0003B | T-00079-0067 | I | PS5-25-03 - Crude Oil Export Pump B | CJX27 - Control valve - Pneumatic / Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LCV-4101 | T-00079-0068 | I | PS5-71-04 - CFO Storage Tank | CJX27 - Control valve - Pneumatic / Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FCV-0019 | T-00079-0069 | I | PS5-71-21 - Diesel Transfer Pump A/B | CJX27 - Control valve - Pneumatic / Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FCV-0020 | T-00079-0070 | I | PS5-71-05 - CFO Transfer Pump A/B | CJX27 - Control valve - Pneumatic / Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FCV-0004A | T-00079-0071 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX27 - Control valve - Pneumatic / Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FCV-0003A | T-00079-0072 | I | PS5-25-02 - Crude Oil Export Pump A | CJX27 - Control valve - Pneumatic / Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FCV-0003C | T-00079-0073 | I | PS5-25-04 - Crude Oil Export Pump C | CJX27 - Control valve - Pneumatic / Hydraulic type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TCV-8401 | T-00080-0003 | I | PS5-09-03 - HVAC for Generator Building | CJX28 - Control valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TCV-8402 | T-00080-0004 | I | PS5-09-03 - HVAC for Generator Building | CJX28 - Control valve - Electrical type | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-BI-0001 | T-00082-0454 | I | PS5-01-05 - Foam Skid | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-01-BI-0002 | T-00082-0455 | I | PS5-01-10 - Water Mist Package | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-01-BI-0003 | T-00082-0456 | I | PS5-01-10 - Water Mist Package | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-01-BI-0004 | T-00082-0457 | I | PS5-01-10 - Water Mist Package | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-01-BI-0005 | T-00082-0458 | I | PS5-01-05 - Foam Skid | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-01-BI-0006 | T-00082-0459 | I | PS5-01-05 - Foam Skid | CJX31 - Junction & marshalling box | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-01-BI-1117 | T-00082-0460 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-01-BI-1118 | T-00082-0461 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-01-BI-1501 | T-00082-0462 | I | PS5-01-07 - Fire Water Ring Main & Distribution | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-01-BI-1515 | T-00082-0463 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-01-BI-1520 | T-00082-0464 | I | PS5-01-10 - Water Mist Package | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:2/3 | Yes | Closed + Accepted with Punch
PS5-01-BI-1571 | T-00082-0465 | I | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-01-BI-2110 | T-00082-0466 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-01-BI-2520 | T-00082-0467 | I | PS5-01-10 - Water Mist Package | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:2/4 | Yes | Closed + Accepted with Punch
PS5-01-BI-2571A | T-00082-0468 | I | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-01-BI-2571B | T-00082-0469 | I | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-03-BI-1502 | T-00082-0470 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-03-BI-1503 | T-00082-0471 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-03-BI-1506 | T-00082-0472 | I | PS5-03-01 - FZ-01 - Process Area | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:0/1 | Yes | Closed + Accepted with Punch
PS5-03-BI-1507 | T-00082-0473 | I | PS5-03-01 - FZ-01 - Process Area | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-03-BI-1508 | T-00082-0474 | I | PS5-03-01 - FZ-01 - Process Area | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-03-BI-1509 | T-00082-0475 | I | PS5-03-01 - FZ-01 - Process Area | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:2/3 | Yes | Closed + Accepted with Punch
PS5-03-BI-1510 | T-00082-0476 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-03-BI-1511 | T-00082-0477 | I | PS5-03-07 - FZ-07 - Pretreatment Area | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-03-BI-1512 | T-00082-0478 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:0/1 | Yes | Closed + Accepted with Punch
PS5-03-BI-1513 | T-00082-0479 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:0/1 | Yes | Closed + Accepted with Punch
PS5-03-BI-1514 | T-00082-0480 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:0/1 | Yes | Closed + Accepted with Punch
PS5-03-BI-1516 | T-00082-0481 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Closed + Accepted with Punch
PS5-03-BI-2501 | T-00082-0482 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX31 - Junction & marshalling box | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-03-BI-2502 | T-00082-0483 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-03-BI-2503 | T-00082-0484 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-03-BI-2504 | T-00082-0485 | I | PS5-03-01 - FZ-01 - Process Area | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-03-BI-2505 | T-00082-0486 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:0/1 | Yes | Closed + Accepted with Punch
PS5-03-BI-2506 | T-00082-0487 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:0/1 | Yes | Closed + Accepted with Punch
PS5-03-BI-2507 | T-00082-0488 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:0/1 | Yes | Closed + Accepted with Punch
PS5-03-BI-2508 | T-00082-0489 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:0/1 | Yes | Closed + Accepted with Punch
PS5-03-BI-2509 | T-00082-0490 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-03-BI-2510 | T-00082-0491 | I | PS5-03-03 - FZ-03 - Buildings Area | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:0/1 | Yes | Closed + Accepted with Punch
PS5-03-BI-2511 | T-00082-0492 | I | PS5-03-01 - FZ-01 - Process Area | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-03-BI-2512 | T-00082-0493 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-03-BI-2514 | T-00082-0494 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:0/1 | Yes | Closed + Accepted with Punch
PS5-03-BI-2515 | T-00082-0495 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-05-BI-0002 | T-00082-0496 | I | PS5-05-01 - Emergency Diesel Generator Package | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-09-BI-2501 | T-00082-0497 | I | PS5-09-04 - HVAC for Workshop & Warehouse | CJX31 - Junction & marshalling box | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-2502 | T-00082-0498 | I | PS5-09-01 - HVAC for Office and Facilities building | CJX31 - Junction & marshalling box | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-2503 | T-00082-0499 | I | PS5-09-03 - HVAC for Generator Building | CJX31 - Junction & marshalling box | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-BI-1101 | T-00082-0500 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-25-BI-1102 | T-00082-0501 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-25-BI-1103 | T-00082-0502 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-25-BI-1104 | T-00082-0503 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-25-BI-1115 | T-00082-0504 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-25-BI-1174A | T-00082-0505 | I | PS5-25-02 - Crude Oil Export Pump A | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-BI-1174B | T-00082-0506 | I | PS5-25-03 - Crude Oil Export Pump B | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-BI-1174C | T-00082-0507 | I | PS5-25-04 - Crude Oil Export Pump C | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-BI-1201 | T-00082-0508 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-25-BI-1274A | T-00082-0509 | I | PS5-25-02 - Crude Oil Export Pump A | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-BI-1274B | T-00082-0510 | I | PS5-25-03 - Crude Oil Export Pump B | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-BI-1274C | T-00082-0511 | I | PS5-25-04 - Crude Oil Export Pump C | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-BI-1301 | T-00082-0512 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-25-BI-1302 | T-00082-0513 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-25-BI-1310 | T-00082-0514 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-25-BI-2101 | T-00082-0515 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-25-BI-2102 | T-00082-0516 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-25-BI-2103 | T-00082-0517 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-25-BI-2104 | T-00082-0518 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:0/1 | Yes | Closed + Accepted with Punch
PS5-25-BI-2105 | T-00082-0519 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-25-BI-2106 | T-00082-0520 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:2/3 | Yes | Closed + Accepted with Punch
PS5-25-BI-2108 | T-00082-0521 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-25-BI-2109 | T-00082-0522 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-25-BI-2201 | T-00082-0523 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:2/3 | Yes | Closed + Accepted with Punch
PS5-25-BI-2203 | T-00082-0524 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:2/3 | Yes | Closed + Accepted with Punch
PS5-25-BI-2205 | T-00082-0525 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:2/3 | Yes | Closed + Accepted with Punch
PS5-25-BI-2301 | T-00082-0526 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-25-BI-2302 | T-00082-0527 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-25-BI-2305 | T-00082-0528 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-25-BI-2308 | T-00082-0529 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:2/3 | Yes | Closed + Accepted with Punch
PS5-25-BI-2309 | T-00082-0530 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-25-BI-2312 | T-00082-0531 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-25-BI-2315 | T-00082-0532 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-25-BI-2316 | T-00082-0533 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-28-BI-1105 | T-00082-0534 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-28-BI-1106 | T-00082-0535 | I | PS5-28-06 - Relief Drum and Pump | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-28-BI-1114 | T-00082-0536 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-28-BI-1303 | T-00082-0537 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-28-BI-1307 | T-00082-0538 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-28-BI-2304 | T-00082-0539 | I | PS5-28-17 - Reinjection Pump | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-50-BI-1107 | T-00082-0540 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-53-BI-1108 | T-00082-0541 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:0/1 | Yes | Closed + Accepted with Punch
PS5-53-BI-1304 | T-00082-0542 | I | PS5-53-01 - Utility Water / Storage Tank | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-71-BI-1109 | T-00082-0543 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-71-BI-1110 | T-00082-0544 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-71-BI-1111 | T-00082-0545 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-71-BI-1112 | T-00082-0546 | I | PS5-71-17 - Diesel Fuel Distribution Header | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-71-BI-1113 | T-00082-0547 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-71-BI-1116 | T-00082-0548 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:0/1 | Yes | Closed + Accepted with Punch
PS5-71-BI-1117 | T-00082-0549 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-71-BI-1305 | T-00082-0550 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:0/1 | Yes | Closed + Accepted with Punch
PS5-71-BI-1306 | T-00082-0551 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:0/1 | Yes | Closed + Accepted with Punch
PS5-71-BI-1308 | T-00082-0552 | I | PS5-71-15 - Diesel Fuel Storage Tank | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-71-BI-2101 | T-00082-0553 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-71-BI-2107 | T-00082-0554 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-71-BI-2113 | T-00082-0555 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-71-BI-2114 | T-00082-0556 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-71-BI-2115 | T-00082-0557 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-71-BI-2116 | T-00082-0558 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-71-BI-2118 | T-00082-0559 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:2/3 | Yes | Closed + Accepted with Punch
PS5-71-BI-2119 | T-00082-0560 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-71-BI-2120 | T-00082-0561 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-71-BI-2121 | T-00082-0562 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:0/1 | Yes | Closed + Accepted with Punch
PS5-71-BI-2122 | T-00082-0563 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:2/4 | Yes | Closed + Accepted with Punch
PS5-71-BI-2123 | T-00082-0564 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-71-BI-2124 | T-00082-0565 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-71-BI-2125 | T-00082-0566 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:0/1 | Yes | Closed + Accepted with Punch
PS5-71-BI-2306 | T-00082-0567 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted with Punch | A:0/1 | Yes | Closed + Accepted with Punch
PS5-71-BI-2307 | T-00082-0568 | I | PS5-71-15 - Diesel Fuel Storage Tank | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-71-BI-2310 | T-00082-0569 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-71-BI-2313 | T-00082-0570 | I | PS5-71-15 - Diesel Fuel Storage Tank | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-71-BI-2314 | T-00082-0571 | I | PS5-91-01 - Multicore cables & JB | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-71-BI-2317 | T-00082-0572 | I | PS5-71-15 - Diesel Fuel Storage Tank | CJX31 - Junction & marshalling box | Closed | Yes | Accepted | - |  | Complete
PS5-01-BI-0007 | T-00082-1230 | I | PS5-01-11 - Inergen for Power Gen Building | CJX31 - Junction & marshalling box | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-BI-0008 | T-00082-1231 | I | PS5-01-11 - Inergen for Power Gen Building | CJX31 - Junction & marshalling box | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-BI-0009 | T-00082-1232 | I | PS5-01-11 - Inergen for Power Gen Building | CJX31 - Junction & marshalling box | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-NMR-61001 | T-00082-1233 | I | PS5-01-11 - Inergen for Power Gen Building | CJX31 - Junction & marshalling box | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-NMR-61002 | T-00082-1234 | I | PS5-01-11 - Inergen for Power Gen Building | CJX31 - Junction & marshalling box | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-NMR-61003 | T-00082-1235 | I | PS5-01-11 - Inergen for Power Gen Building | CJX31 - Junction & marshalling box | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-NMR-61004 | T-00082-1236 | I | PS5-01-11 - Inergen for Power Gen Building | CJX31 - Junction & marshalling box | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-NMRA-61001 | T-00082-1237 | I | PS5-01-11 - Inergen for Power Gen Building | CJX31 - Junction & marshalling box | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-NMRA-61002 | T-00082-1238 | I | PS5-01-11 - Inergen for Power Gen Building | CJX31 - Junction & marshalling box | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-NMRA-61003 | T-00082-1239 | I | PS5-01-11 - Inergen for Power Gen Building | CJX31 - Junction & marshalling box | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-NMRA-61004 | T-00082-1240 | I | PS5-01-11 - Inergen for Power Gen Building | CJX31 - Junction & marshalling box | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDLHP-0137 | T-00083-0184 | I | PS5-03-01 - FZ-01 - Process Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDLHP-0142 | T-00083-0185 | I | PS5-03-01 - FZ-01 - Process Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDLHP-0143 | T-00083-0186 | I | PS5-03-01 - FZ-01 - Process Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDLHP-0144 | T-00083-0187 | I | PS5-03-01 - FZ-01 - Process Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDLHP-0401 | T-00083-0189 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0302 | T-00083-0191 | I | PS5-03-03 - FZ-03 - Buildings Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0303 | T-00083-0192 | I | PS5-03-03 - FZ-03 - Buildings Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0601 | T-00083-0193 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0602 | T-00083-0194 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0603 | T-00083-0195 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0604 | T-00083-0196 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0605 | T-00083-0197 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0606 | T-00083-0198 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0607 | T-00083-0199 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0608 | T-00083-0200 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0609 | T-00083-0201 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0610 | T-00083-0202 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0611 | T-00083-0203 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0612 | T-00083-0204 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0614 | T-00083-0205 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0615 | T-00083-0206 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0616 | T-00083-0207 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0617 | T-00083-0208 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0618 | T-00083-0209 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0828 | T-00083-0210 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0829 | T-00083-0211 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0830 | T-00083-0212 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0831 | T-00083-0213 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0901 | T-00083-0214 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0902 | T-00083-0215 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0903 | T-00083-0216 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0904 | T-00083-0217 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0905 | T-00083-0218 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0906 | T-00083-0219 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0909 | T-00083-0220 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0910 | T-00083-0221 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0911 | T-00083-0222 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0912 | T-00083-0223 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1001 | T-00083-0224 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1002 | T-00083-0225 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1003 | T-00083-0226 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1004 | T-00083-0227 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1005 | T-00083-0228 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1006 | T-00083-0229 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1009 | T-00083-0230 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1010 | T-00083-0231 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1011 | T-00083-0232 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1012 | T-00083-0233 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1101 | T-00083-0234 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1102 | T-00083-0235 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1103 | T-00083-0236 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1104 | T-00083-0237 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1105 | T-00083-0238 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1106 | T-00083-0239 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1109 | T-00083-0240 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1110 | T-00083-0241 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1111 | T-00083-0242 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1112 | T-00083-0243 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-0901 | T-00083-0820 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-0902 | T-00083-0821 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-0903 | T-00083-0822 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-0904 | T-00083-0823 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-0906 | T-00083-0824 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-0907 | T-00083-0825 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-0908 | T-00083-0826 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-0909 | T-00083-0827 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1001 | T-00083-0828 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1002 | T-00083-0829 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1003 | T-00083-0830 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1004 | T-00083-0831 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1006 | T-00083-0832 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1007 | T-00083-0833 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1008 | T-00083-0834 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1009 | T-00083-0835 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1101 | T-00083-0836 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1102 | T-00083-0837 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1103 | T-00083-0838 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1104 | T-00083-0839 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1106 | T-00083-0840 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1107 | T-00083-0841 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1108 | T-00083-0842 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1109 | T-00083-0843 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1201 | T-00083-0844 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1202 | T-00083-0845 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1203 | T-00083-0846 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1204 | T-00083-0847 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDLHP-0146 | T-00083-0848 | I | PS5-03-01 - FZ-01 - Process Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDLHP-0147 | T-00083-0849 | I | PS5-03-01 - FZ-01 - Process Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDLHP-0149 | T-00083-0850 | I | PS5-03-01 - FZ-01 - Process Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDLHP-0150 | T-00083-0851 | I | PS5-03-01 - FZ-01 - Process Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0619 | T-00083-0852 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0620 | T-00083-0853 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1201 | T-00083-0854 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1202 | T-00083-0855 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1203 | T-00083-0856 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1204 | T-00083-0857 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1205 | T-00083-0858 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1302 | T-00083-0859 | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument A | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1303 | T-00083-0860 | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument A | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1304 | T-00083-0861 | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument A | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1901 | T-00083-0862 | I | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1902 | T-00083-0863 | I | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1903 | T-00083-0864 | I | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1401 | T-00083-0865 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1402 | T-00083-0866 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1403 | T-00083-0867 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1404 | T-00083-0868 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1405 | T-00083-0869 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1406 | T-00083-0870 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1407 | T-00083-0871 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1408 | T-00083-0872 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1501 | T-00083-0873 | I | PS5-03-15 - FZ-15 - Power Generation Building - Generator Ro | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1502 | T-00083-0874 | I | PS5-03-15 - FZ-15 - Power Generation Building - Generator Ro | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1503 | T-00083-0875 | I | PS5-03-15 - FZ-15 - Power Generation Building - Generator Ro | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1601 | T-00083-0876 | I | PS5-03-16 - FZ-16 - Power Generation Building - Generator Ro | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1602 | T-00083-0877 | I | PS5-03-16 - FZ-16 - Power Generation Building - Generator Ro | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1603 | T-00083-0878 | I | PS5-03-16 - FZ-16 - Power Generation Building - Generator Ro | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1701 | T-00083-0879 | I | PS5-03-17 - FZ-17 - Power Generation Building - Generator Ro | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1702 | T-00083-0880 | I | PS5-03-17 - FZ-17 - Power Generation Building - Generator Ro | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1703 | T-00083-0881 | I | PS5-03-17 - FZ-17 - Power Generation Building - Generator Ro | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1801 | T-00083-0882 | I | PS5-03-18 - FZ-18 - Power Generation Building - Generator Ro | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1802 | T-00083-0883 | I | PS5-03-18 - FZ-18 - Power Generation Building - Generator Ro | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1803 | T-00083-0884 | I | PS5-03-18 - FZ-18 - Power Generation Building - Generator Ro | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-2101 | T-00083-0885 | I | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-2102 | T-00083-0886 | I | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-2103 | T-00083-0887 | I | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-G101A | T-00083-0888 | I | PS5-03-22 - FZ-G1 - Guard House | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-G101B | T-00083-0889 | I | PS5-03-22 - FZ-G1 - Guard House | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101A | T-00083-1560 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101B | T-00083-1561 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101C | T-00083-1562 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101D | T-00083-1563 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101E | T-00083-1564 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101F | T-00083-1565 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101G | T-00083-1566 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101H | T-00083-1567 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101I | T-00083-1568 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601A | T-00083-1569 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601B | T-00083-1570 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601C | T-00083-1571 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601D | T-00083-1572 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601E | T-00083-1573 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601F | T-00083-1574 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601G | T-00083-1575 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601H | T-00083-1576 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601I | T-00083-1577 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601J | T-00083-1578 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601K | T-00083-1579 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601L | T-00083-1580 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601M | T-00083-1581 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601N | T-00083-1582 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601O | T-00083-1583 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601P | T-00083-1584 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B101A | T-00083-1585 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B101B | T-00083-1586 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B101C | T-00083-1587 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B101D | T-00083-1588 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B201A | T-00083-1589 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B201B | T-00083-1590 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B201C | T-00083-1591 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B201D | T-00083-1592 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B201E | T-00083-1593 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B301A | T-00083-1594 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B301B | T-00083-1595 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B301C | T-00083-1596 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B301D | T-00083-1597 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B401A | T-00083-1598 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B401B | T-00083-1599 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B401C | T-00083-1600 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B401D | T-00083-1601 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B501A | T-00083-1602 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B601A | T-00083-1603 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701A | T-00083-1604 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701B | T-00083-1605 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701C | T-00083-1606 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701D | T-00083-1607 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701E | T-00083-1608 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701F | T-00083-1609 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701G | T-00083-1610 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701H | T-00083-1611 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701I | T-00083-1612 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B801A | T-00083-1613 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B801B | T-00083-1614 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B901A | T-00083-1615 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B901B | T-00083-1616 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B901C | T-00083-1617 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B901D | T-00083-1618 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B901E | T-00083-1619 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W201A | T-00083-1620 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W201B | T-00083-1621 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W201C | T-00083-1622 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W201D | T-00083-1623 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W301A | T-00083-1624 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W401A | T-00083-1625 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W501A | T-00083-1626 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W501B | T-00083-1627 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W501C | T-00083-1628 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W501D | T-00083-1629 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W501E | T-00083-1630 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W501F | T-00083-1631 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX42 - Gas / smoke detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0104 | T-00084-0277 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0105 | T-00084-0278 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0106 | T-00084-0279 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0107 | T-00084-0280 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0108 | T-00084-0281 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0109 | T-00084-0282 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0110 | T-00084-0283 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0111 | T-00084-0284 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0112 | T-00084-0285 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0113 | T-00084-0286 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0114 | T-00084-0287 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0115 | T-00084-0288 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0116 | T-00084-0289 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0117 | T-00084-0290 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0118 | T-00084-0291 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0121 | T-00084-0292 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0122 | T-00084-0293 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0123 | T-00084-0294 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0124 | T-00084-0295 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0125 | T-00084-0296 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0126 | T-00084-0297 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0127 | T-00084-0298 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0128 | T-00084-0299 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0129 | T-00084-0300 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0130 | T-00084-0301 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0131 | T-00084-0302 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0132 | T-00084-0303 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0133 | T-00084-0304 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0137 | T-00084-0305 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0138 | T-00084-0306 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0403 | T-00084-0309 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0404 | T-00084-0310 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0405 | T-00084-0311 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0406 | T-00084-0312 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0409 | T-00084-0313 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0411 | T-00084-0315 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0819 | T-00084-0320 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0820 | T-00084-0321 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0832 | T-00084-0322 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0833 | T-00084-0323 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-0701 | T-00084-0324 | I | PS5-03-07 - FZ-07 - Pretreatment Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-0702 | T-00084-0325 | I | PS5-03-07 - FZ-07 - Pretreatment Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-0703 | T-00084-0326 | I | PS5-03-07 - FZ-07 - Pretreatment Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-0704 | T-00084-0327 | I | PS5-03-07 - FZ-07 - Pretreatment Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-0705 | T-00084-0328 | I | PS5-03-07 - FZ-07 - Pretreatment Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-0907 | T-00084-0329 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-0908 | T-00084-0330 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-1007 | T-00084-0331 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-1008 | T-00084-0332 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-1107 | T-00084-0333 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-1108 | T-00084-0334 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0141 | T-00084-0349 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0142 | T-00084-0350 | I | PS5-03-01 - FZ-01 - Process Area | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-1207 | T-00084-0351 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-1208 | T-00084-0352 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX43 - Fire detector | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-SEA-0002 | T-00087-0102 | I | PS5-03-22 - FZ-G1 - Guard House | CJX48 - Indoor cabinet / panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-SEA-0003 | T-00087-0103 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX48 - Indoor cabinet / panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-SEA-0001 | T-00087-0105 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX48 - Indoor cabinet / panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-MTX-0001 | T-00087-0315 | I | PS5-04-02 - Office Building SIS/FGS System | CJX48 - Indoor cabinet / panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-LB-0004 | T-00087-0492 | I | PS5-01-11 - Inergen for Power Gen Building | CJX48 - Indoor cabinet / panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002A | T-00087-0500 | I | PS5-60-01 - Power Generation Package A | CJX48 - Indoor cabinet / panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B | T-00087-0501 | I | PS5-60-10 - Power Generation Package D | CJX48 - Indoor cabinet / panel | Closed | No | No RFI Yet | B:0/1, C:0/2 | Yes | Closed but No RFI
PS5-60-LA-0002C | T-00087-0502 | I | PS5-60-16 - Power Generation Package F | CJX48 - Indoor cabinet / panel | Closed | No | No RFI Yet | B:0/1, C:0/2 | Yes | Closed but No RFI
PS5-03-SEA-0005 | T-00087-0516 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX48 - Indoor cabinet / panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-SEA-0006 | T-00087-0517 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX48 - Indoor cabinet / panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0003 | T-00087-0528 | I | PS5-60-22 - Power Gen Master UCP | CJX48 - Indoor cabinet / panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-UK-6100 | T-00090-0009 | I | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-UV-8700 | T-00090-0010 | I | PS5-01-05 - Foam Skid | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8100A | T-00090-0179 | I | PS5-60-01 - Power Generation Package A | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8100B | T-00090-0180 | I | PS5-60-04 - Power Generation Package B | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8100C | T-00090-0181 | I | PS5-60-07 - Power Generation Package C | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8100D | T-00090-0182 | I | PS5-60-10 - Power Generation Package D | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8100E | T-00090-0183 | I | PS5-60-13 - Power Generation Package E | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8100F | T-00090-0184 | I | PS5-60-16 - Power Generation Package F | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8100G | T-00090-0185 | I | PS5-60-19 - Power Generation Package G | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-UR-8100 | T-00090-0186 | I | PS5-05-01 - Emergency Diesel Generator Package | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-UZ-6200 | T-00090-0187 | I | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UA-5100 | T-00090-0188 | I | PS5-60-27 - Compressed Air Starting Skid | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UO-81100A | T-00090-0189 | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UO-81100B | T-00090-0190 | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UO-81100C | T-00090-0191 | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UO-81100D | T-00090-0192 | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UO-81100E | T-00090-0193 | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UO-81100F | T-00090-0194 | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UO-81100G | T-00090-0195 | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8200A | T-00090-0196 | I | PS5-60-35 - Injector Tip Cooling Module A | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8200B | T-00090-0197 | I | PS5-60-36 - Injector Tip Cooling Module B | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8200C | T-00090-0198 | I | PS5-60-37 - Injector Tip Cooling Module C | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8200D | T-00090-0199 | I | PS5-60-38 - Injector Tip Cooling Module D | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8200E | T-00090-0200 | I | PS5-60-39 - Injector Tip Cooling Module E | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8200F | T-00090-0201 | I | PS5-60-40 - Injector Tip Cooling Module F | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-VS-9100A | T-00090-0202 | I | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-VS-9100B | T-00090-0203 | I | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-VS-9100C | T-00090-0204 | I | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-VS-9100D | T-00090-0205 | I | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-VS-9100E | T-00090-0206 | I | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-VS-9100F | T-00090-0207 | I | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-VS-9100G | T-00090-0208 | I | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-UZ-6500 | T-00090-0209 | I | PS5-71-18 - Diesel Separator Module | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-UZ-6800A | T-00090-0210 | I | PS5-71-06 - Crude Fuel Separation Module | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-UZ-6800B | T-00090-0211 | I | PS5-71-06 - Crude Fuel Separation Module | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-UZ-6900 | T-00090-0212 | I | PS5-01-10 - Water Mist Package | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-UT-8100 | T-00090-0213 | I | PS5-50-03 - Water Pre-Treatment Package | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-UT-8200 | T-00090-0214 | I | PS5-53-04 - Water Treatment Purification Package | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2100A | T-00090-0215 | I | PS5-60-70 - Engine A Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2100B | T-00090-0216 | I | PS5-60-70 - Engine A Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-21100A | T-00090-0217 | I | PS5-60-01 - Power Generation Package A | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-21100B | T-00090-0218 | I | PS5-60-04 - Power Generation Package B | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-21100C | T-00090-0219 | I | PS5-60-07 - Power Generation Package C | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-21100D | T-00090-0220 | I | PS5-60-10 - Power Generation Package D | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-21100E | T-00090-0221 | I | PS5-60-13 - Power Generation Package E | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-21100F | T-00090-0222 | I | PS5-60-16 - Power Generation Package F | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-21100G | T-00090-0223 | I | PS5-60-19 - Power Generation Package G | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-21200A | T-00090-0224 | I | PS5-60-01 - Power Generation Package A | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-21200B | T-00090-0225 | I | PS5-60-04 - Power Generation Package B | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-21200C | T-00090-0226 | I | PS5-60-07 - Power Generation Package C | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-21200D | T-00090-0227 | I | PS5-60-10 - Power Generation Package D | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-21200E | T-00090-0228 | I | PS5-60-13 - Power Generation Package E | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-21200F | T-00090-0229 | I | PS5-60-16 - Power Generation Package F | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-21200G | T-00090-0230 | I | PS5-60-19 - Power Generation Package G | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2200A | T-00090-0231 | I | PS5-60-71 - Engine B Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2200B | T-00090-0232 | I | PS5-60-71 - Engine B Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2300A | T-00090-0233 | I | PS5-60-72 - Engine C Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2300B | T-00090-0234 | I | PS5-60-72 - Engine C Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2400A | T-00090-0235 | I | PS5-60-73 - Engine D Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2400B | T-00090-0236 | I | PS5-60-73 - Engine D Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2500A | T-00090-0237 | I | PS5-60-74 - Engine E Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2500B | T-00090-0238 | I | PS5-60-74 - Engine E Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2600A | T-00090-0239 | I | PS5-60-75 - Engine F Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2600B | T-00090-0240 | I | PS5-60-75 - Engine F Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2700A | T-00090-0241 | I | PS5-60-76 - Engine G Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2700B | T-00090-0242 | I | PS5-60-76 - Engine G Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2800A | T-00090-0243 | I | PS5-60-35 - Injector Tip Cooling Module A | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2800B | T-00090-0244 | I | PS5-60-36 - Injector Tip Cooling Module B | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2800C | T-00090-0245 | I | PS5-60-37 - Injector Tip Cooling Module C | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2800D | T-00090-0246 | I | PS5-60-38 - Injector Tip Cooling Module D | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2800E | T-00090-0247 | I | PS5-60-39 - Injector Tip Cooling Module E | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2800F | T-00090-0248 | I | PS5-60-40 - Injector Tip Cooling Module F | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2800G | T-00090-0249 | I | PS5-60-41 - Injector Tip Cooling Module G | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2900A | T-00090-0250 | I | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2900B | T-00090-0251 | I | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2900C | T-00090-0252 | I | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2900D | T-00090-0253 | I | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2900E | T-00090-0254 | I | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2900F | T-00090-0255 | I | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2900G | T-00090-0256 | I | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0001A | T-00090-0257 | I | PS5-60-70 - Engine A Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0001B | T-00090-0258 | I | PS5-60-71 - Engine B Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0001C | T-00090-0259 | I | PS5-60-72 - Engine C Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0001D | T-00090-0260 | I | PS5-60-73 - Engine D Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0001E | T-00090-0261 | I | PS5-60-74 - Engine E Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0001F | T-00090-0262 | I | PS5-60-75 - Engine F Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0001G | T-00090-0263 | I | PS5-60-76 - Engine G Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0002A | T-00090-0264 | I | PS5-60-70 - Engine A Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0002B | T-00090-0265 | I | PS5-60-71 - Engine B Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0002C | T-00090-0266 | I | PS5-60-72 - Engine C Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0002D | T-00090-0267 | I | PS5-60-73 - Engine D Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0002E | T-00090-0268 | I | PS5-60-74 - Engine E Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0002F | T-00090-0269 | I | PS5-60-75 - Engine F Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TCV-0002G | T-00090-0270 | I | PS5-60-76 - Engine G Cooling system | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UA-5200 | T-00090-0271 | I | PS5-60-26 - Instrument Air Compressor Skid | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8200A | T-00090-0272 | I | PS5-60-01 - Power Generation Package A | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8200B | T-00090-0273 | I | PS5-60-04 - Power Generation Package B | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8200C | T-00090-0274 | I | PS5-60-07 - Power Generation Package C | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8200D | T-00090-0275 | I | PS5-60-10 - Power Generation Package D | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8200E | T-00090-0276 | I | PS5-60-13 - Power Generation Package E | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8200F | T-00090-0277 | I | PS5-60-16 - Power Generation Package F | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8200G | T-00090-0278 | I | PS5-60-19 - Power Generation Package G | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8200G | T-00090-0279 | I | PS5-60-41 - Injector Tip Cooling Module G | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8900A | T-00090-0280 | I | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8900B | T-00090-0281 | I | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8900C | T-00090-0282 | I | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8900D | T-00090-0283 | I | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8900E | T-00090-0284 | I | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8900F | T-00090-0285 | I | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UZ-8900G | T-00090-0286 | I | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-UN-7200 | T-00090-0287 | I | PS5-71-02 - CFO Allocation Metering Package | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-UZ-6400 | T-00090-0288 | I | PS5-71-08 - CFO Pre-Pressure Modules | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-UZ-6700 | T-00090-0289 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-74-UB-5100 | T-00090-0290 | I | PS5-74-01 - N2 Generation Skid | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-75-UI-6100 | T-00090-0291 | I | PS5-75-02 - Biocide Injection Package | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-75-UI-6200 | T-00090-0292 | I | PS5-75-01 - DRA Injection Package | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-75-UI-6300 | T-00090-0293 | I | PS5-75-03 - Corrosion Inhibitor Injection Package | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-77-UZ-8200 | T-00090-0294 | I | PS5-53-03 - Water Softener Package | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-UZ-8100 | T-00090-0295 | I | PS5-82-02 - Sewage Treatment Plant Package | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PRV-0008A | T-00090-0296 | I | PS5-60-28 - Air Receiver A & Air Regulator A | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PRV-0008B | T-00090-0297 | I | PS5-60-29 - Air Receiver B & Air Regulator B | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PRV-0008C | T-00090-0298 | I | PS5-60-30 - Air Receiver C & Air Regulator C | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PRV-0008D | T-00090-0299 | I | PS5-60-31 - Air Receiver D & Air Regulator D | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PRV-0008E | T-00090-0300 | I | PS5-60-32 - Air Receiver E & Air Regulator E | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PRV-0008F | T-00090-0301 | I | PS5-60-33 - Air Receiver F & Air Regulator F | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PRV-0008G | T-00090-0302 | I | PS5-60-34 - Air Receiver G & Air Regulator G | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-UZ-610 | T-00090-0433 | I | PS5-01-11 - Inergen for Power Gen Building | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8300A | T-00090-0436 | I | PS5-60-35 - Injector Tip Cooling Module A | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8300B | T-00090-0437 | I | PS5-60-36 - Injector Tip Cooling Module B | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8300C | T-00090-0438 | I | PS5-60-37 - Injector Tip Cooling Module C | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8300D | T-00090-0439 | I | PS5-60-38 - Injector Tip Cooling Module D | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8300E | T-00090-0440 | I | PS5-60-39 - Injector Tip Cooling Module E | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8300F | T-00090-0441 | I | PS5-60-40 - Injector Tip Cooling Module F | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-UR-8300G | T-00090-0442 | I | PS5-60-41 - Injector Tip Cooling Module G | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-SEA-0001 | T-00090-0455 | I | PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | CZX01I - Package | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B-CA02 | T-00171-4342 | T | PS5-60-05 - Power Gen Package B (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B-CA03 | T-00171-4343 | T | PS5-60-05 - Power Gen Package B (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B-CA04 | T-00171-4344 | T | PS5-60-05 - Power Gen Package B (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B-CA05 | T-00171-4345 | T | PS5-60-05 - Power Gen Package B (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CA02 | T-00171-4346 | T | PS5-60-08 - Power Gen Package C (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CA03 | T-00171-4347 | T | PS5-60-08 - Power Gen Package C (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CA04 | T-00171-4348 | T | PS5-60-08 - Power Gen Package C (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CA05 | T-00171-4349 | T | PS5-60-08 - Power Gen Package C (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CA02 | T-00171-4350 | T | PS5-60-11 - Power Gen Package D (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CA03 | T-00171-4351 | T | PS5-60-11 - Power Gen Package D (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CA04 | T-00171-4352 | T | PS5-60-11 - Power Gen Package D (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CA05 | T-00171-4353 | T | PS5-60-11 - Power Gen Package D (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CA02 | T-00171-4354 | T | PS5-60-14 - Power Gen Package E (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CA03 | T-00171-4355 | T | PS5-60-14 - Power Gen Package E (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CA04 | T-00171-4356 | T | PS5-60-14 - Power Gen Package E (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CA05 | T-00171-4357 | T | PS5-60-14 - Power Gen Package E (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CA02 | T-00171-4358 | T | PS5-60-17 - Power Gen Package F (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CA03 | T-00171-4359 | T | PS5-60-17 - Power Gen Package F (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CA04 | T-00171-4360 | T | PS5-60-17 - Power Gen Package F (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CA05 | T-00171-4361 | T | PS5-60-17 - Power Gen Package F (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CA03 | T-00171-4362 | T | PS5-60-20 - Power Gen Package G (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CA04 | T-00171-4363 | T | PS5-60-20 - Power Gen Package G (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CA05 | T-00171-4364 | T | PS5-60-20 - Power Gen Package G (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CA01 | T-00171-4365 | T | PS5-60-22 - Power Gen Master UCP | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CA07 | T-00171-4366 | T | PS5-60-22 - Power Gen Master UCP | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CA08 | T-00171-4367 | T | PS5-60-22 - Power Gen Master UCP | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CA14 | T-00171-4368 | T | PS5-60-22 - Power Gen Master UCP | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CA15 | T-00171-4369 | T | PS5-60-22 - Power Gen Master UCP | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CA21 | T-00171-4370 | T | PS5-60-22 - Power Gen Master UCP | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001A-CA01 | T-00171-4371 | T | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001B-CA01 | T-00171-4372 | T | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001C-CA01 | T-00171-4373 | T | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001D-CA01 | T-00171-4374 | T | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001E-CA01 | T-00171-4375 | T | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001F-CA01 | T-00171-4376 | T | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001G-CA01 | T-00171-4377 | T | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001A-CA01 | T-00171-4378 | T | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001B-CA01 | T-00171-4379 | T | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001C-CA01 | T-00171-4380 | T | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001D-CA01 | T-00171-4381 | T | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001E-CA01 | T-00171-4382 | T | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001F-CA01 | T-00171-4383 | T | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001G-CA01 | T-00171-4384 | T | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002A-CA01 | T-00171-4385 | T | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002B-CA01 | T-00171-4386 | T | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002C-CA01 | T-00171-4387 | T | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002D-CA01 | T-00171-4388 | T | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002E-CA01 | T-00171-4389 | T | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002F-CA01 | T-00171-4390 | T | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002G-CA01 | T-00171-4391 | T | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B-CA01 | T-00171-4392 | T | PS5-60-10 - Power Generation Package D | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B-CA02 | T-00171-4393 | T | PS5-60-10 - Power Generation Package D | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B-CA03 | T-00171-4394 | T | PS5-60-10 - Power Generation Package D | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B-CA04 | T-00171-4395 | T | PS5-60-10 - Power Generation Package D | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B-CA05 | T-00171-4396 | T | PS5-60-10 - Power Generation Package D | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B-CA06 | T-00171-4397 | T | PS5-60-10 - Power Generation Package D | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002C-CA01 | T-00171-4398 | T | PS5-60-16 - Power Generation Package F | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002C-CA02 | T-00171-4399 | T | PS5-60-16 - Power Generation Package F | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002C-CA03 | T-00171-4400 | T | PS5-60-16 - Power Generation Package F | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002C-CA04 | T-00171-4401 | T | PS5-60-16 - Power Generation Package F | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002C-CA05 | T-00171-4402 | T | PS5-60-16 - Power Generation Package F | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002C-CA06 | T-00171-4403 | T | PS5-60-16 - Power Generation Package F | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-SEA-0001-CA01 | T-00171-4404 | T | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0001-CA01 | T-00171-4405 | T | PS5-71-19 - Diesel Separator Module (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0001-CA11 | T-00171-4406 | T | PS5-71-19 - Diesel Separator Module (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0002-CA01 | T-00171-4407 | T | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0003-CA01 | T-00171-4408 | T | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004A-CA01 | T-00171-4409 | T | PS5-71-07 - Crude Fuel Separation Module (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004B-CA01 | T-00171-4410 | T | PS5-71-07 - Crude Fuel Separation Module (UCP) | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8451A-CA01 | T-00171-9468 | T | PS5-09-03 - HVAC for Generator Building | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8451B-CA01 | T-00171-9469 | T | PS5-09-03 - HVAC for Generator Building | CIX09 - Telecom cable power / Control / Multicore | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-ISR-0101 | T-00227-0068 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IU-0010 | T-00227-0070 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | TPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IU-0011 | T-00227-0071 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | TPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-63-IV-0010 | T-00227-0072 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-63-IV-0011 | T-00227-0073 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IU-3100A | T-00227-0112 | E | PS5-25-02 - Crude Oil Export Pump A | TPX02 - Power transformer | Closed | Yes | Accepted | C:0/1 | Yes | Closed + Accepted
PS5-61-IU-3100B | T-00227-0113 | E | PS5-25-03 - Crude Oil Export Pump B | TPX02 - Power transformer | Closed | Yes | Accepted | C:0/1 | Yes | Closed + Accepted
PS5-61-IU-3100C | T-00227-0114 | E | PS5-25-04 - Crude Oil Export Pump C | TPX02 - Power transformer | Closed | Yes | Accepted | C:0/1 | Yes | Closed + Accepted
PS5-61-IU-0001A | T-00227-0133 | E | PS5-60-01 - Power Generation Package A | TPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IU-0001B | T-00227-0134 | E | PS5-60-04 - Power Generation Package B | TPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IU-0001C | T-00227-0135 | E | PS5-60-07 - Power Generation Package C | TPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IU-0001D | T-00227-0136 | E | PS5-60-10 - Power Generation Package D | TPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IU-0001E | T-00227-0137 | E | PS5-60-13 - Power Generation Package E | TPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IU-0001F | T-00227-0138 | E | PS5-60-16 - Power Generation Package F | TPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IU-0001G | T-00227-0139 | E | PS5-60-19 - Power Generation Package G | TPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IV-0001A | T-00227-0152 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | TPX02 - Power transformer | Closed | Yes | Accepted | B:0/1, C:0/1 | Yes | Closed + Accepted
PS5-61-IV-0001B | T-00227-0153 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | TPX02 - Power transformer | Closed | Yes | Other | A:0/2 | Yes | Closed + Other
PS5-61-IV-0002A | T-00227-0162 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX02 - Power transformer | Closed | Yes | Other | A:2/4, C:0/1 | Yes | Closed + Other
PS5-61-IV-0002B | T-00227-0163 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX02 - Power transformer | Closed | Yes | Other | A:1/3, C:0/1 | Yes | Closed + Other
PS5-61-IV-0007A | T-00227-0164 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX02 - Power transformer | Closed | Yes | Other | A:0/2, B:1/2 | Yes | Closed + Other
PS5-61-IV-0007B | T-00227-0165 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX02 - Power transformer | Closed | Yes | Other | A:0/2, B:1/2 | Yes | Closed + Other
PS5-61-IV-0005A | T-00227-0175 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IV-0005B | T-00227-0176 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX02 - Power transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IV-0001 | T-00228-0096 | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution | TPX03 - LV transformer | Closed | Yes | Accepted with Punch | C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IV-0002 | T-00228-0097 | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution | TPX03 - LV transformer | Closed | Yes | Accepted with Punch | C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IV-0003 | T-00228-0098 | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution | TPX03 - LV transformer | Closed | Yes | Accepted with Punch | C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IV-0004 | T-00228-0099 | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution | TPX03 - LV transformer | Closed | Yes | Accepted with Punch | C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IV-0005 | T-00228-0100 | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution | TPX03 - LV transformer | Closed | Yes | Accepted with Punch | C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IV-0006 | T-00228-0101 | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution | TPX03 - LV transformer | Closed | Yes | Accepted with Punch | B:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IV-0007 | T-00228-0102 | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution | TPX03 - LV transformer | Closed | Yes | Accepted with Punch | C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IV-0008 | T-00228-0103 | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution | TPX03 - LV transformer | Closed | Yes | Accepted with Punch | C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IV-0009 | T-00228-0104 | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution | TPX03 - LV transformer | Closed | Yes | Accepted with Punch | C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IV-0010 | T-00228-0105 | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution | TPX03 - LV transformer | Closed | Yes | Accepted with Punch | C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IV-0011 | T-00228-0106 | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution | TPX03 - LV transformer | Closed | Yes | Accepted with Punch | C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IV-0012 | T-00228-0107 | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution | TPX03 - LV transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-87-IRF-0001 | T-00228-0108 | E | PS5-53-01 - Utility Water / Storage Tank | TPX03 - LV transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-87-IRF-0002 | T-00228-0109 | E | PS5-71-04 - CFO Storage Tank | TPX03 - LV transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-87-IRF-0003 | T-00228-0110 | E | PS5-71-12 - CFO Service Tank | TPX03 - LV transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-87-IRF-0004 | T-00228-0111 | E | PS5-71-15 - Diesel Fuel Storage Tank | TPX03 - LV transformer | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0003 | T-00230-0035 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX05 - LV switchboard | To be completed | Yes | Open | A:0/2, C:0/1 | Yes | Open + RFI Submitted
PS5-61-IK-0006 | T-00230-0036 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX05 - LV switchboard | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-DM-3100A-CH01 | T-00232-0952 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100A-CH02 | T-00232-0953 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100A-CH03 | T-00232-0954 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100A-CH04 | T-00232-0955 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100A-CH05 | T-00232-0956 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100A-CH06 | T-00232-0957 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100B-CH01 | T-00232-0958 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100B-CH02 | T-00232-0959 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100B-CH03 | T-00232-0960 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100B-CH04 | T-00232-0961 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100B-CH05 | T-00232-0962 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100B-CH06 | T-00232-0963 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100C-CH01 | T-00232-0964 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100C-CH02 | T-00232-0965 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100C-CH03 | T-00232-0966 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100C-CH04 | T-00232-0967 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100C-CH05 | T-00232-0968 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-25-DM-3100C-CH06 | T-00232-0969 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-60-IJ-0001A-CH04 | T-00232-0970 | E | PS5-60-01 - Power Generation Package A | TPX08 - HV power cable | Closed | Yes | Accepted | - |  | Complete
PS5-60-IJ-0001B-CH04 | T-00232-0971 | E | PS5-60-04 - Power Generation Package B | TPX08 - HV power cable | Closed | Yes | Accepted | - |  | Complete
PS5-60-IJ-0001C-CH04 | T-00232-0972 | E | PS5-60-07 - Power Generation Package C | TPX08 - HV power cable | Closed | Yes | Accepted | - |  | Complete
PS5-60-IJ-0001D-CH04 | T-00232-0973 | E | PS5-60-10 - Power Generation Package D | TPX08 - HV power cable | Closed | Yes | Accepted | - |  | Complete
PS5-60-IJ-0001E-CH04 | T-00232-0974 | E | PS5-60-13 - Power Generation Package E | TPX08 - HV power cable | Closed | Yes | Accepted | - |  | Complete
PS5-60-IJ-0001F-CH04 | T-00232-0975 | E | PS5-60-16 - Power Generation Package F | TPX08 - HV power cable | Closed | Yes | Accepted | - |  | Complete
PS5-60-IJ-0001G-CH04 | T-00232-0976 | E | PS5-60-19 - Power Generation Package G | TPX08 - HV power cable | Closed | Yes | Accepted | - |  | Complete
PS5-61-IDH-3100A-CH01 | T-00232-0977 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH02 | T-00232-0978 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH03 | T-00232-0979 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH04 | T-00232-0980 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH05 | T-00232-0981 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH06 | T-00232-0982 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH07 | T-00232-0983 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH08 | T-00232-0984 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH09 | T-00232-0985 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH10 | T-00232-0986 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH11 | T-00232-0987 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100A-CH12 | T-00232-0988 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH01 | T-00232-0989 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH02 | T-00232-0990 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH03 | T-00232-0991 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH04 | T-00232-0992 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH05 | T-00232-0993 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH06 | T-00232-0994 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH07 | T-00232-0995 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH08 | T-00232-0996 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH09 | T-00232-0997 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH10 | T-00232-0998 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH11 | T-00232-0999 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100B-CH12 | T-00232-1000 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH01 | T-00232-1001 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH02 | T-00232-1002 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH03 | T-00232-1003 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH04 | T-00232-1004 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH05 | T-00232-1005 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH06 | T-00232-1006 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH07 | T-00232-1007 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH08 | T-00232-1008 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH09 | T-00232-1009 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH10 | T-00232-1010 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH11 | T-00232-1011 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IDH-3100C-CH12 | T-00232-1012 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH01 | T-00232-1013 | E | PS5-60-01 - Power Generation Package A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH02 | T-00232-1014 | E | PS5-60-01 - Power Generation Package A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH03 | T-00232-1015 | E | PS5-60-01 - Power Generation Package A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH04 | T-00232-1016 | E | PS5-60-04 - Power Generation Package B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH05 | T-00232-1017 | E | PS5-60-04 - Power Generation Package B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH06 | T-00232-1018 | E | PS5-60-04 - Power Generation Package B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH07 | T-00232-1019 | E | PS5-60-07 - Power Generation Package C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH08 | T-00232-1020 | E | PS5-60-07 - Power Generation Package C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH09 | T-00232-1021 | E | PS5-60-07 - Power Generation Package C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH10 | T-00232-1022 | E | PS5-60-10 - Power Generation Package D | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH11 | T-00232-1023 | E | PS5-60-10 - Power Generation Package D | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH12 | T-00232-1024 | E | PS5-60-10 - Power Generation Package D | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH13 | T-00232-1025 | E | PS5-60-13 - Power Generation Package E | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH14 | T-00232-1026 | E | PS5-60-13 - Power Generation Package E | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH15 | T-00232-1027 | E | PS5-60-13 - Power Generation Package E | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH16 | T-00232-1028 | E | PS5-60-16 - Power Generation Package F | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH17 | T-00232-1029 | E | PS5-60-16 - Power Generation Package F | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH18 | T-00232-1030 | E | PS5-60-16 - Power Generation Package F | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH19 | T-00232-1031 | E | PS5-60-19 - Power Generation Package G | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH20 | T-00232-1032 | E | PS5-60-19 - Power Generation Package G | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0001-CH21 | T-00232-1033 | E | PS5-60-19 - Power Generation Package G | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0010-CH01 | T-00232-1034 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0010-CH02 | T-00232-1035 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0010-CH03 | T-00232-1036 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0011-CH01 | T-00232-1037 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0011-CH02 | T-00232-1038 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IJ-0011-CH03 | T-00232-1039 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-ISR-0101-CH01 | T-00232-1040 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-ISR-0101-CH02 | T-00232-1041 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-ISR-0101-CH03 | T-00232-1042 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-ISR-0102-CH01 | T-00232-1043 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-ISR-0102-CH02 | T-00232-1044 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-ISR-0102-CH03 | T-00232-1045 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001A-CH01 | T-00232-1046 | E | PS5-60-01 - Power Generation Package A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001A-CH02 | T-00232-1047 | E | PS5-60-01 - Power Generation Package A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001A-CH03 | T-00232-1048 | E | PS5-60-01 - Power Generation Package A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001B-CH01 | T-00232-1049 | E | PS5-60-04 - Power Generation Package B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001B-CH02 | T-00232-1050 | E | PS5-60-04 - Power Generation Package B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001B-CH03 | T-00232-1051 | E | PS5-60-04 - Power Generation Package B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001C-CH01 | T-00232-1052 | E | PS5-60-07 - Power Generation Package C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001C-CH02 | T-00232-1053 | E | PS5-60-07 - Power Generation Package C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001C-CH03 | T-00232-1054 | E | PS5-60-07 - Power Generation Package C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001D-CH01 | T-00232-1055 | E | PS5-60-10 - Power Generation Package D | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001D-CH02 | T-00232-1056 | E | PS5-60-10 - Power Generation Package D | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001D-CH03 | T-00232-1057 | E | PS5-60-10 - Power Generation Package D | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001E-CH01 | T-00232-1058 | E | PS5-60-13 - Power Generation Package E | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001E-CH02 | T-00232-1059 | E | PS5-60-13 - Power Generation Package E | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001E-CH03 | T-00232-1060 | E | PS5-60-13 - Power Generation Package E | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001F-CH01 | T-00232-1061 | E | PS5-60-16 - Power Generation Package F | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001F-CH02 | T-00232-1062 | E | PS5-60-16 - Power Generation Package F | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001F-CH03 | T-00232-1063 | E | PS5-60-16 - Power Generation Package F | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001G-CH01 | T-00232-1064 | E | PS5-60-19 - Power Generation Package G | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001G-CH02 | T-00232-1065 | E | PS5-60-19 - Power Generation Package G | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0001G-CH03 | T-00232-1066 | E | PS5-60-19 - Power Generation Package G | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0010-CH01 | T-00232-1067 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0010-CH02 | T-00232-1068 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0010-CH03 | T-00232-1069 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0011-CH01 | T-00232-1070 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0011-CH02 | T-00232-1071 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-0011-CH03 | T-00232-1072 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100A-CH01 | T-00232-1073 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100A-CH02 | T-00232-1074 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100A-CH03 | T-00232-1075 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100A-CH04 | T-00232-1076 | E | PS5-25-02 - Crude Oil Export Pump A | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100B-CH01 | T-00232-1077 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100B-CH02 | T-00232-1078 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100B-CH03 | T-00232-1079 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100B-CH04 | T-00232-1080 | E | PS5-25-03 - Crude Oil Export Pump B | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100C-CH01 | T-00232-1081 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100C-CH02 | T-00232-1082 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100C-CH03 | T-00232-1083 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IU-3100C-CH04 | T-00232-1084 | E | PS5-25-04 - Crude Oil Export Pump C | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IV-0001A-CH01 | T-00232-1085 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IV-0001A-CH02 | T-00232-1086 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IV-0001A-CH03 | T-00232-1087 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IV-0001B-CH01 | T-00232-1088 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IV-0001B-CH02 | T-00232-1089 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IV-0001B-CH03 | T-00232-1090 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-61-IV-0002A-CH01 | T-00232-1091 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0002A-CH02 | T-00232-1092 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | A:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0002A-CH03 | T-00232-1093 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | C:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0002B-CH01 | T-00232-1094 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0002B-CH02 | T-00232-1095 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0002B-CH03 | T-00232-1096 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0005A-CH01 | T-00232-1097 | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building ( | TPX08 - HV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IV-0005A-CH02 | T-00232-1098 | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building ( | TPX08 - HV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IV-0005A-CH03 | T-00232-1099 | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building ( | TPX08 - HV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IV-0005B-CH01 | T-00232-1100 | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building ( | TPX08 - HV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IV-0005B-CH02 | T-00232-1101 | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building ( | TPX08 - HV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IV-0005B-CH03 | T-00232-1102 | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building ( | TPX08 - HV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IV-0007A-CH01 | T-00232-1103 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0007A-CH02 | T-00232-1104 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0007A-CH03 | T-00232-1105 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0007B-CH01 | T-00232-1106 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0007B-CH02 | T-00232-1107 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IV-0007B-CH03 | T-00232-1108 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-NER-0010-CH01 | T-00232-1109 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-NER-0011-CH01 | T-00232-1110 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Closed + Accepted with Punch
PS5-63-IV-0010-CH01 | T-00232-1111 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-63-IV-0010-CH02 | T-00232-1112 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-63-IV-0010-CH03 | T-00232-1113 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-63-IV-0011-CH01 | T-00232-1114 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-63-IV-0011-CH02 | T-00232-1115 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-63-IV-0011-CH03 | T-00232-1116 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX08 - HV power cable | Closed | Yes | Accepted with Punch | - |  | Complete
PS5-63-NER-0010-CH01 | T-00232-1117 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX08 - HV power cable | Closed | Yes | Hold by EACOP | A:0/2, B:0/1 | Yes | Closed + Hold by EACOP
PS5-63-NER-0011-CH01 | T-00232-1118 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX08 - HV power cable | Closed | Yes | Hold by EACOP | A:0/2, B:0/1 | Yes | Closed + Hold by EACOP
PS5-79-BH-0001-CH01 | T-00232-1119 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | TPX08 - HV power cable | Completed (not Closed) | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-79-BH-0001-CH02 | T-00232-1120 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | TPX08 - HV power cable | Completed (not Closed) | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-79-BH-0001-CH03 | T-00232-1121 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | TPX08 - HV power cable | Completed (not Closed) | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-79-BH-0002-CH01 | T-00232-1122 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | TPX08 - HV power cable | Completed (not Closed) | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-79-BH-0002-CH02 | T-00232-1123 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | TPX08 - HV power cable | Completed (not Closed) | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-79-BH-0002-CH03 | T-00232-1124 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | TPX08 - HV power cable | Completed (not Closed) | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-62-IE-0001-CL02 | T-00233-10060 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL03 | T-00233-10061 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL05 | T-00233-10062 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL06 | T-00233-10063 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL07 | T-00233-10064 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL51 | T-00233-10065 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL52 | T-00233-10066 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL53 | T-00233-10067 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL54 | T-00233-10068 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL55 | T-00233-10069 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL56 | T-00233-10070 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL57 | T-00233-10071 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL58 | T-00233-10072 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001-CL59 | T-00233-10073 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL02 | T-00233-10074 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL03 | T-00233-10075 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL04 | T-00233-10076 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL05 | T-00233-10077 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL06 | T-00233-10078 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL07 | T-00233-10079 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL52 | T-00233-10080 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL53 | T-00233-10081 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL54 | T-00233-10082 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL55 | T-00233-10083 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL56 | T-00233-10084 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL57 | T-00233-10085 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL58 | T-00233-10086 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL59 | T-00233-10087 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CL60 | T-00233-10088 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-06-GB-0003-CG01 | T-00233-10535 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002A-CG01 | T-00233-10536 | E | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002B-CG01 | T-00233-10537 | E | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002C-CG01 | T-00233-10538 | E | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002D-CG01 | T-00233-10539 | E | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002E-CG01 | T-00233-10540 | E | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002F-CG01 | T-00233-10541 | E | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002G-CG01 | T-00233-10542 | E | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-BE-0001-CG01 | T-00233-10584 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-06-IG-0004A-CG01 | T-00233-10585 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-06-IG-0004B-CG01 | T-00233-10586 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-DM-3100A-CG01 | T-00233-10587 | E | PS5-25-02 - Crude Oil Export Pump A | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-25-DM-3100A-CG02 | T-00233-10588 | E | PS5-25-02 - Crude Oil Export Pump A | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-25-DM-3100B-CG01 | T-00233-10589 | E | PS5-25-03 - Crude Oil Export Pump B | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-25-DM-3100B-CG02 | T-00233-10590 | E | PS5-25-03 - Crude Oil Export Pump B | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-25-DM-3100C-CG01 | T-00233-10591 | E | PS5-25-04 - Crude Oil Export Pump C | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-25-DM-3100C-CG02 | T-00233-10592 | E | PS5-25-04 - Crude Oil Export Pump C | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-60-IH-0001A-CG01 | T-00233-10593 | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001B-CG01 | T-00233-10594 | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001C-CG01 | T-00233-10595 | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001D-CG01 | T-00233-10596 | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001E-CG01 | T-00233-10597 | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001F-CG01 | T-00233-10598 | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001G-CG01 | T-00233-10599 | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0002-CG01 | T-00233-10600 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-60-IH-0002-CG02 | T-00233-10601 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-61-IH-0004-CG01 | T-00233-10602 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CG02 | T-00233-10603 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CG03 | T-00233-10604 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CG04 | T-00233-10605 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0003-CG07 | T-00233-10616 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-28-DM-31100-CL01 | T-00233-10889 | E | PS5-28-10 - Oil Skimmer Package | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0007A-CL02 | T-00233-10890 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | TPX09 - LV power cable | Closed | Yes | Other | A:0/1, B:0/2 | Yes | Closed + Other
PS5-60-BE-0007A-CL03 | T-00233-10891 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | TPX09 - LV power cable | Closed | Yes | Other | A:0/1, B:0/2 | Yes | Closed + Other
PS5-60-BE-0007B-CL02 | T-00233-10892 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | TPX09 - LV power cable | Closed | Yes | Other | A:0/1, B:0/2 | Yes | Closed + Other
PS5-60-BE-0007B-CL03 | T-00233-10893 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | TPX09 - LV power cable | Closed | Yes | Other | A:0/1, B:0/2 | Yes | Closed + Other
PS5-60-BE-0007C-CL02 | T-00233-10894 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0007C-CL03 | T-00233-10895 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0007D-CL02 | T-00233-10896 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0007D-CL03 | T-00233-10897 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0007E-CL02 | T-00233-10898 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0007E-CL03 | T-00233-10899 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0007F-CL02 | T-00233-10900 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0007F-CL03 | T-00233-10901 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0007G-CL02 | T-00233-10902 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0007G-CL03 | T-00233-10903 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-ISO-62800A-CL01 | T-00233-10904 | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | B:0/2 | Yes | Closed + Hold by EACOP
PS5-60-ISO-62800C-CL01 | T-00233-10905 | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-ISO-62800E-CL01 | T-00233-10906 | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | A:0/1, B:0/2 | Yes | Closed + Hold by EACOP
PS5-60-ISO-62800G-CL01 | T-00233-10907 | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-08-85CP-1201-CS01 | T-00233-10968 | E | PS5-08-85 - Access Control, POB & e-Mustering | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85CP-1202-CS01 | T-00233-10969 | E | PS5-08-85 - Access Control, POB & e-Mustering | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85CP-1601-CS01 | T-00233-10970 | E | PS5-08-85 - Access Control, POB & e-Mustering | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-BE-0001-CL12 | T-00233-11061 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-09-DM-84500A-CL01 | T-00233-11062 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-DM-84500B-CL01 | T-00233-11063 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL01 | T-00233-11253 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL02 | T-00233-11254 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL03 | T-00233-11255 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL04 | T-00233-11256 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL05 | T-00233-11257 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL06 | T-00233-11258 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL07 | T-00233-11259 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL08 | T-00233-11260 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL09 | T-00233-11261 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL10 | T-00233-11262 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL11 | T-00233-11263 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001A-CL12 | T-00233-11264 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL01 | T-00233-11265 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL02 | T-00233-11266 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL03 | T-00233-11267 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL04 | T-00233-11268 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL05 | T-00233-11269 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL06 | T-00233-11270 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL07 | T-00233-11271 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL08 | T-00233-11272 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL09 | T-00233-11273 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL10 | T-00233-11274 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL11 | T-00233-11275 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0001B-CL12 | T-00233-11276 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0005-CL01 | T-00233-11277 | E | PS5-71-19 - Diesel Separator Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0005-CL02 | T-00233-11278 | E | PS5-71-19 - Diesel Separator Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0005-CL03 | T-00233-11279 | E | PS5-71-19 - Diesel Separator Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0005-CL04 | T-00233-11280 | E | PS5-71-19 - Diesel Separator Module (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-BE-0001-CL01 | T-00233-4695 | E | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Closed + Accepted with Punch
PS5-01-FCV-0003A-CL01 | T-00233-4696 | E | PS5-01-02 - Fire Water Pump A | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-01-FCV-0003B-CL01 | T-00233-4697 | E | PS5-01-03 - Fire Water Pump B | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-01-FCV-0004A-CL01 | T-00233-4698 | E | PS5-01-01 - Fire Water Jockey Pump A/B | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:2/4 | Yes | Closed + Accepted with Punch
PS5-01-FCV-0004B-CL01 | T-00233-4699 | E | PS5-01-01 - Fire Water Jockey Pump A/B | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:2/4 | Yes | Closed + Accepted with Punch
PS5-01-IG-0001-CL01 | T-00233-4710 | E | PS5-01-10 - Water Mist Package | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-01-LB-0004-CL01 | T-00233-4711 | E | PS5-01-11 - Inergen for Power Gen Building | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-01-LB-0004-CL02 | T-00233-4712 | E | PS5-01-11 - Inergen for Power Gen Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-LB-0004-CL03 | T-00233-4713 | E | PS5-01-11 - Inergen for Power Gen Building | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-01-MOV-8701-CL01 | T-00233-4714 | E | PS5-01-05 - Foam Skid | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-03-SEA-0002-CL01 | T-00233-4724 | E | PS5-03-22 - FZ-G1 - Guard House | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-SEA-0003-CL01 | T-00233-4725 | E | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-BE-0001-CL01 | T-00233-4727 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-05-BE-0001-CL02 | T-00233-4728 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-05-BE-0001-CL03 | T-00233-4729 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-05-BE-0001-CL04 | T-00233-4730 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-05-BE-0001-CL05 | T-00233-4731 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-05-BE-0001-CL06 | T-00233-4732 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-05-BE-0001-CL07 | T-00233-4733 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-05-BE-0001-CL08 | T-00233-4734 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-05-BE-0001-CL09 | T-00233-4735 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-05-BE-0001-CL10 | T-00233-4736 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-05-BE-0001-CL11 | T-00233-4737 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-05-IE-8100-CL01 | T-00233-4738 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-05-IE-8100-CL02 | T-00233-4739 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-05-IG-0009-CL01 | T-00233-4742 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-05-IG-0009-CL02 | T-00233-4743 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-05-IG-0025-CL01 | T-00233-4744 | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-05-IG-0026-CL01 | T-00233-4745 | E | PS5-62-07 - CRO Generator Electrical Building Emergency Ligh | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-06-GB-0003-CL01 | T-00233-4746 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX09 - LV power cable | Closed | Yes | Open | B:1/2 | Yes | Closed + Open
PS5-06-GB-0003-CL02 | T-00233-4747 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX09 - LV power cable | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-06-GB-0003-CL03 | T-00233-4748 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX09 - LV power cable | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-06-GB-0003-CL04 | T-00233-4749 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX09 - LV power cable | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-06-GB-0003-CL05 | T-00233-4750 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX09 - LV power cable | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-06-GB-0003-CL06 | T-00233-4751 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX09 - LV power cable | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-06-GU-0003A-CL01 | T-00233-4752 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX09 - LV power cable | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-06-GU-0003B-CL01 | T-00233-4753 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX09 - LV power cable | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-06-GU-0003C-CL01 | T-00233-4754 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX09 - LV power cable | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-06-IG-0004A-CL01 | T-00233-4756 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX09 - LV power cable | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-06-IG-0004A-CL02 | T-00233-4757 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX09 - LV power cable | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-06-IG-0004A-CL03 | T-00233-4758 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX09 - LV power cable | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-06-IG-0004A-CL04 | T-00233-4759 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX09 - LV power cable | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-06-IG-0004B-CL01 | T-00233-4761 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX09 - LV power cable | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-06-IG-0004B-CL02 | T-00233-4762 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX09 - LV power cable | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-06-IG-0004B-CL03 | T-00233-4763 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX09 - LV power cable | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-06-IG-0004B-CL04 | T-00233-4764 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX09 - LV power cable | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-08-11CB-1501-CL01 | T-00233-4808 | E | PS5-08-11 - Corporate LAN (SIE) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-08-11CB-1901-CL01 | T-00233-4809 | E | PS5-08-11 - Corporate LAN (SIE) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-11CB-1901-CL02 | T-00233-4810 | E | PS5-08-11 - Corporate LAN (SIE) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-11CB-1901-CL03 | T-00233-4811 | E | PS5-08-11 - Corporate LAN (SIE) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-0008-CL01 | T-00233-4878 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-0008-CL02 | T-00233-4879 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-DM-3100A-CL01 | T-00233-4882 | E | PS5-25-02 - Crude Oil Export Pump A | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-DM-3100A-CL02 | T-00233-4883 | E | PS5-25-02 - Crude Oil Export Pump A | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-DM-3100B-CL01 | T-00233-4886 | E | PS5-25-03 - Crude Oil Export Pump B | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-DM-3100B-CL02 | T-00233-4887 | E | PS5-25-03 - Crude Oil Export Pump B | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-DM-3100C-CL01 | T-00233-4890 | E | PS5-25-04 - Crude Oil Export Pump C | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-DM-3100C-CL02 | T-00233-4891 | E | PS5-25-04 - Crude Oil Export Pump C | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-ESDV-0021-CL01 | T-00233-4904 | E | PS5-25-01 - Export Pipeline Pig Receiver | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-ESDV-0023-CL01 | T-00233-4905 | E | PS5-25-07 - Export Pipeline Pig Launcher | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-FCV-0003A-CL01 | T-00233-4906 | E | PS5-25-02 - Crude Oil Export Pump A | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-FCV-0003B-CL01 | T-00233-4907 | E | PS5-25-03 - Crude Oil Export Pump B | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-FCV-0003C-CL01 | T-00233-4908 | E | PS5-25-04 - Crude Oil Export Pump C | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-FCV-0004-CL01 | T-00233-4909 | E | PS5-25-06 - Crude Oil Export Pumps Discharge | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-25-MOV-0001-CL01 | T-00233-4918 | E | PS5-25-01 - Export Pipeline Pig Receiver | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-MOV-0002-CL01 | T-00233-4919 | E | PS5-25-01 - Export Pipeline Pig Receiver | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-MOV-0003-CL01 | T-00233-4920 | E | PS5-25-01 - Export Pipeline Pig Receiver | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-MOV-0008-CL01 | T-00233-4921 | E | PS5-25-07 - Export Pipeline Pig Launcher | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Closed + Accepted with Punch
PS5-25-MOV-0011-CL01 | T-00233-4922 | E | PS5-25-07 - Export Pipeline Pig Launcher | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-MOV-0012-CL01 | T-00233-4923 | E | PS5-25-07 - Export Pipeline Pig Launcher | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-MOV-0025-CL01 | T-00233-4924 | E | PS5-25-01 - Export Pipeline Pig Receiver | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Closed + Accepted with Punch
PS5-25-MOV-0026-CL01 | T-00233-4925 | E | PS5-25-01 - Export Pipeline Pig Receiver | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Closed + Accepted with Punch
PS5-25-MOV-0027-CL01 | T-00233-4926 | E | PS5-25-06 - Crude Oil Export Pumps Discharge | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-MOV-0028-CL01 | T-00233-4927 | E | PS5-25-07 - Export Pipeline Pig Launcher | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-SDV-0022-CL01 | T-00233-4928 | E | PS5-25-01 - Export Pipeline Pig Receiver | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-SDV-0035A-CL01 | T-00233-4929 | E | PS5-25-02 - Crude Oil Export Pump A | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-SDV-0035B-CL01 | T-00233-4930 | E | PS5-25-03 - Crude Oil Export Pump B | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-SDV-0035C-CL01 | T-00233-4931 | E | PS5-25-04 - Crude Oil Export Pump C | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-SDV-0036A-CL01 | T-00233-4932 | E | PS5-25-02 - Crude Oil Export Pump A | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-SDV-0036B-CL01 | T-00233-4933 | E | PS5-25-03 - Crude Oil Export Pump B | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-SDV-0036C-CL01 | T-00233-4934 | E | PS5-25-04 - Crude Oil Export Pump C | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-SDV-0046-CL01 | T-00233-4935 | E | PS5-25-05 - Crude Oil Export Pumps Bypass | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Closed + Accepted with Punch
PS5-25-SDV-0052-CL01 | T-00233-4936 | E | PS5-25-07 - Export Pipeline Pig Launcher | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-SDV-0054A-CL01 | T-00233-4937 | E | PS5-25-02 - Crude Oil Export Pump A | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-SDV-0054B-CL01 | T-00233-4938 | E | PS5-25-03 - Crude Oil Export Pump B | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-SDV-0054C-CL01 | T-00233-4939 | E | PS5-25-04 - Crude Oil Export Pump C | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-XV-0053-CL01 | T-00233-4941 | E | PS5-25-05 - Crude Oil Export Pumps Bypass | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | A:0/2, B:1/2 | Yes | Closed + Hold by EACOP
PS5-25-XV-0070-CL01 | T-00233-4942 | E | PS5-25-05 - Crude Oil Export Pumps Bypass | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-28-BE-0002A-CL02 | T-00233-4944 | E | PS5-28-17 - Reinjection Pump | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Closed + Accepted with Punch
PS5-28-BE-0002B-CL02 | T-00233-4946 | E | PS5-28-17 - Reinjection Pump | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Closed + Accepted with Punch
PS5-28-HE-2100-CL02 | T-00233-4962 | E | PS5-28-03 - Closed Drain Drum and Pump 01 | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-28-HE-2200-CL02 | T-00233-4964 | E | PS5-28-04 - Closed Drain Drum and Pump 02 | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-28-LB-8200-CL01 | T-00233-4966 | E | PS5-28-11 - Open Drain Interceptor | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-28-SDV-0045-CL01 | T-00233-4967 | E | PS5-28-17 - Reinjection Pump | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-28-SDV-0053A-CL01 | T-00233-4968 | E | PS5-28-13 - Seal Oil Drain Drum & Pump A | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Closed + Accepted with Punch
PS5-28-SDV-0053B-CL01 | T-00233-4969 | E | PS5-28-14 - Seal Oil Drain Drum & Pump B | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-28-SDV-0053C-CL01 | T-00233-4970 | E | PS5-28-15 - Seal Oil Drain Drum & Pump C | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-60-BE-0001-CL01 | T-00233-4978 | E | PS5-60-27 - Compressed Air Starting Skid | TPX09 - LV power cable | Closed | Yes | Other | A:0/1, B:0/2 | Yes | Closed + Other
PS5-60-BE-0001-CL02 | T-00233-4979 | E | PS5-60-27 - Compressed Air Starting Skid | TPX09 - LV power cable | Closed | Yes | Other | A:0/1, B:0/2 | Yes | Closed + Other
PS5-60-BE-0001-CL04 | T-00233-4981 | E | PS5-60-27 - Compressed Air Starting Skid | TPX09 - LV power cable | Closed | Yes | Other | A:0/1, B:0/2 | Yes | Closed + Other
PS5-60-BE-0002-CL01 | T-00233-4982 | E | PS5-60-26 - Instrument Air Compressor Skid | TPX09 - LV power cable | Closed | Yes | Other | A:0/1, B:0/2 | Yes | Closed + Other
PS5-60-BE-0002-CL02 | T-00233-4983 | E | PS5-60-26 - Instrument Air Compressor Skid | TPX09 - LV power cable | Closed | Yes | Other | A:0/1, B:0/2 | Yes | Closed + Other
PS5-60-BE-0002-CL03 | T-00233-4984 | E | PS5-60-26 - Instrument Air Compressor Skid | TPX09 - LV power cable | Closed | Yes | Other | A:0/1, B:0/2 | Yes | Closed + Other
PS5-60-BE-0002-CL05 | T-00233-4986 | E | PS5-60-26 - Instrument Air Compressor Skid | TPX09 - LV power cable | Closed | Yes | Other | A:0/1, B:0/2 | Yes | Closed + Other
PS5-60-BE-0003A-CL01 | T-00233-4987 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-BE-0003B-CL01 | T-00233-4988 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-BE-0003C-CL01 | T-00233-4989 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0003D-CL01 | T-00233-4990 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0003E-CL01 | T-00233-4991 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0003F-CL01 | T-00233-4992 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0003G-CL01 | T-00233-4993 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0004A-CL01 | T-00233-4994 | E | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0004B-CL01 | T-00233-4995 | E | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0004C-CL01 | T-00233-4996 | E | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0004D-CL01 | T-00233-4997 | E | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0004E-CL01 | T-00233-4998 | E | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0004F-CL01 | T-00233-4999 | E | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0004G-CL01 | T-00233-5000 | E | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0005A-CL01 | T-00233-5001 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0005B-CL01 | T-00233-5002 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | Closed | Yes | Accepted | A:1/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0005C-CL01 | T-00233-5003 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0005D-CL01 | T-00233-5004 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-BE-0005E-CL01 | T-00233-5005 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0005F-CL01 | T-00233-5006 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | A:0/1, B:0/2 | Yes | Closed + Hold by EACOP
PS5-60-BE-0005G-CL01 | T-00233-5007 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0011A-CL01 | T-00233-5008 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-BE-0011A-CL02 | T-00233-5009 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-BE-0011A-CL03 | T-00233-5010 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | Yes | Accepted | A:1/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0011A-CL04 | T-00233-5011 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-BE-0011A-CL05 | T-00233-5012 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | Yes | Accepted | A:1/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0011A-CL06 | T-00233-5013 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | Yes | Accepted | A:1/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0011B-CL01 | T-00233-5014 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | Yes | Accepted | A:1/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0011B-CL02 | T-00233-5015 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | Yes | Accepted | A:1/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0011B-CL03 | T-00233-5016 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | Yes | Accepted | A:1/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0011B-CL04 | T-00233-5017 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | Yes | Accepted | A:1/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0011B-CL05 | T-00233-5018 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | Yes | Accepted | A:1/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0011B-CL06 | T-00233-5019 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | Yes | Accepted | A:1/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0012A-CL01 | T-00233-5020 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | Closed | Yes | Accepted | A:1/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0012A-CL02 | T-00233-5021 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | Closed | Yes | Accepted | A:1/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0012A-CL03 | T-00233-5022 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | Closed | Yes | Accepted | A:1/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0012A-CL04 | T-00233-5023 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | Closed | Yes | Accepted | A:1/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0012A-CL05 | T-00233-5024 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | Closed | Yes | Accepted | A:1/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0012A-CL06 | T-00233-5025 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | Closed | Yes | Accepted | A:1/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0012B-CL01 | T-00233-5026 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | Closed | Yes | Accepted | A:1/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0012B-CL02 | T-00233-5027 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | Closed | Yes | Accepted | A:1/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0012B-CL03 | T-00233-5028 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | Closed | Yes | Accepted | A:1/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0012B-CL04 | T-00233-5029 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | Closed | Yes | Accepted | A:1/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0012B-CL05 | T-00233-5030 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | Closed | Yes | Accepted | A:1/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0012B-CL06 | T-00233-5031 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-BE-0013A-CL01 | T-00233-5032 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0013A-CL02 | T-00233-5033 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0013A-CL03 | T-00233-5034 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0013A-CL04 | T-00233-5035 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0013A-CL05 | T-00233-5036 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0013A-CL06 | T-00233-5037 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0013B-CL01 | T-00233-5038 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0013B-CL02 | T-00233-5039 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0013B-CL03 | T-00233-5040 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0013B-CL04 | T-00233-5041 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0013B-CL05 | T-00233-5042 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0013B-CL06 | T-00233-5043 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0014A-CL01 | T-00233-5044 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0014A-CL02 | T-00233-5045 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0014A-CL03 | T-00233-5046 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0014A-CL04 | T-00233-5047 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0014A-CL05 | T-00233-5048 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0014A-CL06 | T-00233-5049 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0014B-CL01 | T-00233-5050 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0014B-CL02 | T-00233-5051 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0014B-CL03 | T-00233-5052 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0014B-CL04 | T-00233-5053 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0014B-CL05 | T-00233-5054 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0014B-CL06 | T-00233-5055 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0015A-CL01 | T-00233-5056 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0015A-CL02 | T-00233-5057 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0015A-CL03 | T-00233-5058 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0015A-CL04 | T-00233-5059 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0015A-CL05 | T-00233-5060 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0015A-CL06 | T-00233-5061 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0015B-CL01 | T-00233-5062 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0015B-CL02 | T-00233-5063 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0015B-CL03 | T-00233-5064 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0015B-CL04 | T-00233-5065 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0015B-CL05 | T-00233-5066 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0015B-CL06 | T-00233-5067 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0016A-CL01 | T-00233-5068 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0016A-CL02 | T-00233-5069 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0016A-CL03 | T-00233-5070 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0016A-CL04 | T-00233-5071 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0016A-CL05 | T-00233-5072 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0016A-CL06 | T-00233-5073 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0016B-CL01 | T-00233-5074 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0016B-CL02 | T-00233-5075 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0016B-CL03 | T-00233-5076 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0016B-CL04 | T-00233-5077 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0016B-CL05 | T-00233-5078 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0016B-CL06 | T-00233-5079 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0017A-CL01 | T-00233-5080 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0017A-CL02 | T-00233-5081 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0017A-CL03 | T-00233-5082 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0017A-CL04 | T-00233-5083 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0017A-CL05 | T-00233-5084 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0017A-CL06 | T-00233-5085 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0017B-CL01 | T-00233-5086 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0017B-CL02 | T-00233-5087 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0017B-CL03 | T-00233-5088 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0017B-CL04 | T-00233-5089 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0017B-CL05 | T-00233-5090 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0017B-CL06 | T-00233-5091 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0021A-CL01 | T-00233-5092 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0021B-CL01 | T-00233-5093 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-BE-0024A-CL01 | T-00233-5094 | E | PS5-60-35 - Injector Tip Cooling Module A | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0024A-CL02 | T-00233-5095 | E | PS5-60-35 - Injector Tip Cooling Module A | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0024B-CL01 | T-00233-5096 | E | PS5-60-36 - Injector Tip Cooling Module B | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0024B-CL02 | T-00233-5097 | E | PS5-60-36 - Injector Tip Cooling Module B | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0024C-CL01 | T-00233-5098 | E | PS5-60-37 - Injector Tip Cooling Module C | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | A:0/1, B:0/2 | Yes | Closed + Hold by EACOP
PS5-60-BE-0024C-CL02 | T-00233-5099 | E | PS5-60-37 - Injector Tip Cooling Module C | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | A:0/1, B:0/2 | Yes | Closed + Hold by EACOP
PS5-60-BE-0024D-CL01 | T-00233-5100 | E | PS5-60-38 - Injector Tip Cooling Module D | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0024D-CL02 | T-00233-5101 | E | PS5-60-38 - Injector Tip Cooling Module D | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0024E-CL01 | T-00233-5102 | E | PS5-60-39 - Injector Tip Cooling Module E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0024E-CL02 | T-00233-5103 | E | PS5-60-39 - Injector Tip Cooling Module E | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | A:0/1, B:0/2 | Yes | Closed + Hold by EACOP
PS5-60-BE-0024F-CL01 | T-00233-5104 | E | PS5-60-40 - Injector Tip Cooling Module F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0024F-CL02 | T-00233-5105 | E | PS5-60-40 - Injector Tip Cooling Module F | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | A:0/1, B:0/2 | Yes | Closed + Hold by EACOP
PS5-60-BE-0024G-CL01 | T-00233-5106 | E | PS5-60-41 - Injector Tip Cooling Module G | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | B:0/2 | Yes | Closed + Hold by EACOP
PS5-60-BE-0024G-CL02 | T-00233-5107 | E | PS5-60-41 - Injector Tip Cooling Module G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0025A-CL01 | T-00233-5108 | E | PS5-60-35 - Injector Tip Cooling Module A | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-BE-0025B-CL01 | T-00233-5109 | E | PS5-60-36 - Injector Tip Cooling Module B | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-BE-0025C-CL01 | T-00233-5110 | E | PS5-60-37 - Injector Tip Cooling Module C | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | B:0/2 | Yes | Closed + Hold by EACOP
PS5-60-BE-0025D-CL01 | T-00233-5111 | E | PS5-60-38 - Injector Tip Cooling Module D | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-BE-0025E-CL01 | T-00233-5112 | E | PS5-60-39 - Injector Tip Cooling Module E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0025F-CL01 | T-00233-5113 | E | PS5-60-40 - Injector Tip Cooling Module F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0025G-CL01 | T-00233-5114 | E | PS5-60-41 - Injector Tip Cooling Module G | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | B:0/2 | Yes | Closed + Hold by EACOP
PS5-60-BE-0026A-CL01 | T-00233-5115 | E | PS5-60-70 - Engine A Cooling system | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-BE-0026A-CL02 | T-00233-5116 | E | PS5-60-70 - Engine A Cooling system | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-BE-0026B-CL01 | T-00233-5117 | E | PS5-60-71 - Engine B Cooling system | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-BE-0026B-CL02 | T-00233-5118 | E | PS5-60-71 - Engine B Cooling system | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-BE-0026C-CL01 | T-00233-5119 | E | PS5-60-72 - Engine C Cooling system | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | B:0/2 | Yes | Closed + Hold by EACOP
PS5-60-BE-0026C-CL02 | T-00233-5120 | E | PS5-60-72 - Engine C Cooling system | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-BE-0026D-CL01 | T-00233-5121 | E | PS5-60-73 - Engine D Cooling system | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0026D-CL02 | T-00233-5122 | E | PS5-60-73 - Engine D Cooling system | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0026E-CL01 | T-00233-5123 | E | PS5-60-74 - Engine E Cooling system | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0026E-CL02 | T-00233-5124 | E | PS5-60-74 - Engine E Cooling system | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0026F-CL01 | T-00233-5125 | E | PS5-60-75 - Engine F Cooling system | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0026F-CL02 | T-00233-5126 | E | PS5-60-75 - Engine F Cooling system | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-60-BE-0026G-CL01 | T-00233-5127 | E | PS5-60-76 - Engine G Cooling system | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | B:0/2 | Yes | Closed + Hold by EACOP
PS5-60-BE-0026G-CL02 | T-00233-5128 | E | PS5-60-76 - Engine G Cooling system | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-BI-0005A-CL01 | T-00233-5129 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-BI-0005B-CL01 | T-00233-5130 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-BI-0005C-CL01 | T-00233-5131 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-BI-0005D-CL01 | T-00233-5132 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-BI-0005E-CL01 | T-00233-5133 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-BI-0005F-CL01 | T-00233-5134 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-BI-0005G-CL01 | T-00233-5135 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-BI-0015A-CL01 | T-00233-5136 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0015A-CL02 | T-00233-5137 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-BI-0015A-CL03 | T-00233-5138 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-BI-0015B-CL01 | T-00233-5139 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0015B-CL02 | T-00233-5140 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-BI-0015B-CL03 | T-00233-5141 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-BI-0015C-CL01 | T-00233-5142 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0015C-CL02 | T-00233-5143 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0015C-CL03 | T-00233-5144 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0015D-CL01 | T-00233-5145 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0015D-CL02 | T-00233-5146 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-BI-0015D-CL03 | T-00233-5147 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-BI-0015E-CL01 | T-00233-5148 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0015E-CL02 | T-00233-5149 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0015E-CL03 | T-00233-5150 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0015F-CL01 | T-00233-5151 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0015F-CL02 | T-00233-5152 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0015F-CL03 | T-00233-5153 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0015G-CL01 | T-00233-5154 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0015G-CL02 | T-00233-5155 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0015G-CL03 | T-00233-5156 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-DD-62800A-CL01 | T-00233-5157 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-DD-62800C-CL01 | T-00233-5159 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-DD-62800E-CL01 | T-00233-5161 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-DD-62800G-CL01 | T-00233-5163 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002A-CL01 | T-00233-5166 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0002A-CL02 | T-00233-5167 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0002A-CL03 | T-00233-5168 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0002B-CL01 | T-00233-5169 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-60-IE-0002B-CL02 | T-00233-5170 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0002B-CL03 | T-00233-5171 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0002C-CL01 | T-00233-5172 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0002C-CL02 | T-00233-5173 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | B:0/2 | Yes | Closed + Hold by EACOP
PS5-60-IE-0002C-CL03 | T-00233-5174 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0002D-CL01 | T-00233-5175 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IE-0002D-CL02 | T-00233-5176 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IE-0002D-CL03 | T-00233-5177 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002E-CL01 | T-00233-5178 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | B:0/2 | Yes | Closed + Hold by EACOP
PS5-60-IE-0002E-CL02 | T-00233-5179 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | B:0/2 | Yes | Closed + Hold by EACOP
PS5-60-IE-0002E-CL03 | T-00233-5180 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002F-CL01 | T-00233-5181 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0002F-CL02 | T-00233-5182 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0002F-CL03 | T-00233-5183 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002G-CL01 | T-00233-5184 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0002G-CL02 | T-00233-5185 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0002G-CL03 | T-00233-5186 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003A-CL01 | T-00233-5187 | E | PS5-60-02 - Power Gen Package A (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IE-0003A-CL02 | T-00233-5188 | E | PS5-60-02 - Power Gen Package A (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IE-0003B-CL01 | T-00233-5189 | E | PS5-60-05 - Power Gen Package B (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IE-0003B-CL02 | T-00233-5190 | E | PS5-60-05 - Power Gen Package B (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IE-0003C-CL01 | T-00233-5191 | E | PS5-60-08 - Power Gen Package C (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003C-CL02 | T-00233-5192 | E | PS5-60-08 - Power Gen Package C (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CL01 | T-00233-5193 | E | PS5-60-11 - Power Gen Package D (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CL02 | T-00233-5194 | E | PS5-60-11 - Power Gen Package D (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-60-IE-0003E-CL01 | T-00233-5195 | E | PS5-60-14 - Power Gen Package E (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003E-CL02 | T-00233-5196 | E | PS5-60-14 - Power Gen Package E (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003F-CL01 | T-00233-5197 | E | PS5-60-17 - Power Gen Package F (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003F-CL02 | T-00233-5198 | E | PS5-60-17 - Power Gen Package F (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003G-CL01 | T-00233-5199 | E | PS5-60-20 - Power Gen Package G (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003G-CL02 | T-00233-5200 | E | PS5-60-20 - Power Gen Package G (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0004-CL01 | T-00233-5201 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-60-IE-0004-CL02 | T-00233-5202 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-60-IH-0001A-CL01 | T-00233-5204 | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IH-0001A-CL02 | T-00233-5205 | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IH-0001A-CL03 | T-00233-5206 | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IH-0001A-CL04 | T-00233-5207 | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IH-0001A-CL05 | T-00233-5208 | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IH-0001A-CL06 | T-00233-5209 | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IH-0001B-CL01 | T-00233-5211 | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IH-0001B-CL02 | T-00233-5212 | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IH-0001B-CL03 | T-00233-5213 | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IH-0001B-CL04 | T-00233-5214 | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IH-0001B-CL05 | T-00233-5215 | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-60-IH-0001B-CL06 | T-00233-5216 | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-60-IH-0001C-CL01 | T-00233-5218 | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | B:0/2 | Yes | Closed + Hold by EACOP
PS5-60-IH-0001C-CL02 | T-00233-5219 | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | B:0/2 | Yes | Closed + Hold by EACOP
PS5-60-IH-0001C-CL03 | T-00233-5220 | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | B:0/2 | Yes | Closed + Hold by EACOP
PS5-60-IH-0001C-CL04 | T-00233-5221 | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | B:0/2 | Yes | Closed + Hold by EACOP
PS5-60-IH-0001C-CL05 | T-00233-5222 | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IH-0001C-CL06 | T-00233-5223 | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IH-0001D-CL01 | T-00233-5225 | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IH-0001D-CL02 | T-00233-5226 | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IH-0001D-CL03 | T-00233-5227 | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IH-0001D-CL04 | T-00233-5228 | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IH-0001D-CL05 | T-00233-5229 | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-60-IH-0001D-CL06 | T-00233-5230 | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IH-0001E-CL01 | T-00233-5232 | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IH-0001E-CL02 | T-00233-5233 | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IH-0001E-CL03 | T-00233-5234 | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IH-0001E-CL04 | T-00233-5235 | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001E-CL05 | T-00233-5236 | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IH-0001E-CL06 | T-00233-5237 | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IH-0001F-CL01 | T-00233-5239 | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001F-CL02 | T-00233-5240 | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001F-CL03 | T-00233-5241 | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001F-CL04 | T-00233-5242 | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001F-CL05 | T-00233-5243 | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001F-CL06 | T-00233-5244 | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IH-0001G-CL01 | T-00233-5246 | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001G-CL02 | T-00233-5247 | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001G-CL03 | T-00233-5248 | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001G-CL04 | T-00233-5249 | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | B:0/2 | Yes | Closed + Hold by EACOP
PS5-60-IH-0001G-CL05 | T-00233-5250 | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IH-0001G-CL06 | T-00233-5251 | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0002-CL01 | T-00233-5254 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-60-IH-0002-CL02 | T-00233-5255 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-60-IH-0002-CL03 | T-00233-5256 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-60-IH-0002-CL04 | T-00233-5257 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-60-IH-0002-CL05 | T-00233-5258 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-60-IH-0002-CL06 | T-00233-5259 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-60-IH-0002-CL07 | T-00233-5260 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-60-IH-0002-CL08 | T-00233-5261 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-60-IH-0002-CL09 | T-00233-5262 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-60-IH-0002-CL10 | T-00233-5263 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-60-IN-0001A-CL01 | T-00233-5264 | E | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IN-0001B-CL01 | T-00233-5265 | E | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IN-0001C-CL01 | T-00233-5266 | E | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IN-0001D-CL01 | T-00233-5267 | E | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IN-0001E-CL01 | T-00233-5268 | E | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IN-0001F-CL01 | T-00233-5269 | E | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IN-0001G-CL01 | T-00233-5270 | E | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IN-0002A-CL01 | T-00233-5271 | E | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IN-0002A-CL02 | T-00233-5272 | E | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Closed + Accepted with Punch
PS5-60-IN-0002A-CL03 | T-00233-5273 | E | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IN-0002B-CL01 | T-00233-5274 | E | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IN-0002B-CL02 | T-00233-5275 | E | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IN-0002B-CL03 | T-00233-5276 | E | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IN-0002C-CL01 | T-00233-5277 | E | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002C-CL02 | T-00233-5278 | E | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002C-CL03 | T-00233-5279 | E | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002D-CL01 | T-00233-5280 | E | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IN-0002D-CL02 | T-00233-5281 | E | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IN-0002D-CL03 | T-00233-5282 | E | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IN-0002E-CL01 | T-00233-5283 | E | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002E-CL02 | T-00233-5284 | E | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IN-0002E-CL03 | T-00233-5285 | E | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IN-0002F-CL01 | T-00233-5286 | E | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002F-CL02 | T-00233-5287 | E | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IN-0002F-CL03 | T-00233-5288 | E | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IN-0002G-CL01 | T-00233-5289 | E | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002G-CL02 | T-00233-5290 | E | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IN-0002G-CL03 | T-00233-5291 | E | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IWK-0001A-CL01 | T-00233-5292 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IWK-0001A-CL02 | T-00233-5293 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IWK-0001B-CL01 | T-00233-5294 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IWK-0001B-CL02 | T-00233-5295 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IWK-0001C-CL01 | T-00233-5296 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IWK-0001C-CL02 | T-00233-5297 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-LA-0002A-CL01 | T-00233-5298 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-60-LA-0002A-CL02 | T-00233-5299 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-60-LA-0002B-CL01 | T-00233-5300 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-LA-0002B-CL02 | T-00233-5301 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-LA-0002C-CL01 | T-00233-5302 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-LA-0002C-CL02 | T-00233-5303 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-LA-0003-CL01 | T-00233-5304 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Closed + Accepted with Punch
PS5-60-LA-0003-CL02 | T-00233-5305 | E | PS5-60-22 - Power Gen Master UCP | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Closed + Accepted with Punch
PS5-60-MOV-0005-CL01 | T-00233-5306 | E | PS5-71-12 - CFO Service Tank | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:1/2, B:1/2 | Yes | Closed + Accepted with Punch
PS5-60-MOV-0006-CL01 | T-00233-5307 | E | PS5-71-12 - CFO Service Tank | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:1/2, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-MOV-0011-CL01 | T-00233-5308 | E | PS5-71-12 - CFO Service Tank | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:1/2, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-MOV-0012-CL01 | T-00233-5309 | E | PS5-71-12 - CFO Service Tank | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:1/2, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-SEA-0001-CL01 | T-00233-5310 | E | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-SEA-0001-CL02 | T-00233-5311 | E | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-VS-9100A-CL01 | T-00233-5312 | E | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-VS-9100B-CL01 | T-00233-5313 | E | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-VS-9100C-CL01 | T-00233-5314 | E | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-VS-9100D-CL01 | T-00233-5315 | E | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-VS-9100E-CL01 | T-00233-5316 | E | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | A:0/1, B:0/2 | Yes | Closed + Hold by EACOP
PS5-60-VS-9100F-CL01 | T-00233-5317 | E | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-VS-9100G-CL01 | T-00233-5318 | E | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-BI-0001-CL01 | T-00233-5319 | E | PS5-60-01 - Power Generation Package A | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-BI-0002-CL01 | T-00233-5320 | E | PS5-60-04 - Power Generation Package B | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-61-BI-0003-CL01 | T-00233-5321 | E | PS5-60-07 - Power Generation Package C | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-BI-0004-CL01 | T-00233-5322 | E | PS5-60-10 - Power Generation Package D | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-61-BI-0005-CL01 | T-00233-5323 | E | PS5-60-13 - Power Generation Package E | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-BI-0006-CL01 | T-00233-5324 | E | PS5-60-16 - Power Generation Package F | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-61-BI-0007-CL01 | T-00233-5325 | E | PS5-60-19 - Power Generation Package G | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IG-0015-CL01 | T-00233-5335 | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61- | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-61-IG-0016-CL01 | T-00233-5336 | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IH-0004-CL01 | T-00233-5343 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IH-0004-CL02 | T-00233-5344 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IH-0004-CL03 | T-00233-5345 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IH-0004-CL04 | T-00233-5346 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IH-0004-CL05 | T-00233-5347 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IH-0004-CL06 | T-00233-5348 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IH-0004-CL07 | T-00233-5349 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IH-0004-CL08 | T-00233-5350 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IH-0004-CL09 | T-00233-5351 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IH-0004-CL10 | T-00233-5352 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IH-0004-CL11 | T-00233-5353 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IH-0004-CL12 | T-00233-5354 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IH-0004-CL13 | T-00233-5355 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IH-0004-CL14 | T-00233-5356 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IH-0004-CL15 | T-00233-5357 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL16 | T-00233-5358 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL17 | T-00233-5359 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IH-0004-CL18 | T-00233-5360 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL19 | T-00233-5361 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL20 | T-00233-5362 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL21 | T-00233-5363 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CL22 | T-00233-5364 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IK-0003-CL01 | T-00233-5425 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Other | B:0/2 | Yes | Closed + Other
PS5-61-IK-0003-CL02 | T-00233-5426 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Other | B:0/2 | Yes | Closed + Other
PS5-61-IK-0003-CL03 | T-00233-5427 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0003-CL04 | T-00233-5428 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-61-IK-0003-CL05 | T-00233-5429 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-61-IK-0003-CL06 | T-00233-5430 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-61-IK-0003-CL07 | T-00233-5431 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL08 | T-00233-5432 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL09 | T-00233-5433 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL10 | T-00233-5434 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL11 | T-00233-5435 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL12 | T-00233-5436 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL13 | T-00233-5437 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL14 | T-00233-5438 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL15 | T-00233-5439 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL16 | T-00233-5440 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL17 | T-00233-5441 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL18 | T-00233-5442 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL19 | T-00233-5443 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL20 | T-00233-5444 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL21 | T-00233-5445 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL22 | T-00233-5446 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL23 | T-00233-5447 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL24 | T-00233-5448 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL25 | T-00233-5449 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL26 | T-00233-5450 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL27 | T-00233-5451 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL28 | T-00233-5452 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL29 | T-00233-5453 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL30 | T-00233-5454 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL31 | T-00233-5455 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL32 | T-00233-5456 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL33 | T-00233-5457 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL34 | T-00233-5458 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL35 | T-00233-5459 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL36 | T-00233-5460 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL37 | T-00233-5461 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL38 | T-00233-5462 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL39 | T-00233-5463 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL40 | T-00233-5464 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL41 | T-00233-5465 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL42 | T-00233-5466 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL43 | T-00233-5467 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL44 | T-00233-5468 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL45 | T-00233-5469 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL46 | T-00233-5470 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL47 | T-00233-5471 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL48 | T-00233-5472 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL49 | T-00233-5473 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL50 | T-00233-5474 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL51 | T-00233-5475 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL52 | T-00233-5476 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL53 | T-00233-5477 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL54 | T-00233-5478 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL55 | T-00233-5479 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL56 | T-00233-5480 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL57 | T-00233-5481 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL58 | T-00233-5482 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL59 | T-00233-5483 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL60 | T-00233-5484 | E | PS5-05-01 - Emergency Diesel Generator Package | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0003-CL61 | T-00233-5485 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IK-0003-CL62 | T-00233-5486 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-05-IG-0002-CL01 | T-00233-5487 | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-00 | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0006-CL01 | T-00233-5492 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL02 | T-00233-5493 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL03 | T-00233-5494 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL04 | T-00233-5495 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL05 | T-00233-5496 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL06 | T-00233-5497 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL07 | T-00233-5498 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL08 | T-00233-5499 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL09 | T-00233-5500 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL10 | T-00233-5501 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL11 | T-00233-5502 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL12 | T-00233-5503 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL13 | T-00233-5504 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL14 | T-00233-5505 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL15 | T-00233-5506 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL16 | T-00233-5507 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL17 | T-00233-5508 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL18 | T-00233-5509 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL19 | T-00233-5510 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL20 | T-00233-5511 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL21 | T-00233-5512 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL22 | T-00233-5513 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL23 | T-00233-5514 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL24 | T-00233-5515 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL25 | T-00233-5516 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL26 | T-00233-5517 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/2, B:0/2 | Yes | Closed + Accepted
PS5-61-IK-0006-CL27 | T-00233-5518 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/2, B:0/2 | Yes | Closed + Accepted
PS5-61-IK-0006-CL28 | T-00233-5519 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/2, B:0/2 | Yes | Closed + Accepted
PS5-61-IK-0006-CL29 | T-00233-5520 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IK-0006-CL30 | T-00233-5521 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IK-0006-CL31 | T-00233-5522 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IK-0006-CL32 | T-00233-5523 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IK-0006-CL33 | T-00233-5524 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0006-CL34 | T-00233-5525 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IU-3100A-CL01 | T-00233-5532 | E | PS5-25-02 - Crude Oil Export Pump A | TPX09 - LV power cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-IU-3100B-CL01 | T-00233-5533 | E | PS5-25-03 - Crude Oil Export Pump B | TPX09 - LV power cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-IU-3100C-CL01 | T-00233-5534 | E | PS5-25-04 - Crude Oil Export Pump C | TPX09 - LV power cable | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-IV-0002A-CL01 | T-00233-5537 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-61-IV-0002B-CL01 | T-00233-5538 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-61-IV-0007A-CL01 | T-00233-5542 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IV-0007B-CL01 | T-00233-5543 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-62-IE-0001-CL01 | T-00233-5546 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Closed + Accepted with Punch
PS5-62-IE-0002-CL01 | T-00233-5547 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-71-FCV-0018-CL01 | T-00233-5561 | E | PS5-71-13 - CFO Service Pump A/B | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-FCV-0019-CL01 | T-00233-5562 | E | PS5-71-21 - Diesel Transfer Pump A/B | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-FCV-0020-CL01 | T-00233-5563 | E | PS5-71-05 - CFO Transfer Pump A/B | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Closed + Accepted with Punch
PS5-71-HE-2200-CL02 | T-00233-5567 | E | PS5-71-12 - CFO Service Tank | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-HE-2300-CL02 | T-00233-5569 | E | PS5-71-04 - CFO Storage Tank | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-IN-0001-CL01 | T-00233-5578 | E | PS5-71-19 - Diesel Separator Module (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-IN-0001-CL02 | T-00233-5579 | E | PS5-71-19 - Diesel Separator Module (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-IN-0001-CL03 | T-00233-5580 | E | PS5-71-19 - Diesel Separator Module (UCP) | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-71-IN-0002-CL01 | T-00233-5581 | E | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-IN-0002-CL02 | T-00233-5582 | E | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-IN-0002-CL03 | T-00233-5583 | E | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-IN-0003-CL01 | T-00233-5584 | E | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-71-IN-0003-CL02 | T-00233-5585 | E | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-71-IN-0003-CL03 | T-00233-5586 | E | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-71-IN-0004A-CL01 | T-00233-5587 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | B:0/2 | Yes | Closed + Hold by EACOP
PS5-71-IN-0004A-CL02 | T-00233-5588 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | Closed | Yes | Hold by EACOP | B:0/2 | Yes | Closed + Hold by EACOP
PS5-71-IN-0004A-CL03 | T-00233-5589 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-71-IN-0004B-CL01 | T-00233-5590 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-IN-0004B-CL02 | T-00233-5591 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-IN-0004B-CL03 | T-00233-5592 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-71-LCV-4101-CL01 | T-00233-5593 | E | PS5-71-04 - CFO Storage Tank | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Closed + Accepted with Punch
PS5-71-MOV-0001-CL01 | T-00233-5594 | E | PS5-71-08 - CFO Pre-Pressure Modules | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-MOV-0002-CL01 | T-00233-5595 | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-MOV-0003-CL01 | T-00233-5596 | E | PS5-71-08 - CFO Pre-Pressure Modules | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-MOV-0004-CL01 | T-00233-5597 | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-MOV-0007-CL01 | T-00233-5598 | E | PS5-71-04 - CFO Storage Tank | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:1/2, B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-MOV-0008-CL01 | T-00233-5599 | E | PS5-71-08 - CFO Pre-Pressure Modules | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:1/2, B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-MOV-0009-CL01 | T-00233-5600 | E | PS5-71-04 - CFO Storage Tank | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-MOV-0010-CL01 | T-00233-5601 | E | PS5-71-08 - CFO Pre-Pressure Modules | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-SDV-0001-CL01 | T-00233-5602 | E | PS5-71-20 - Diesel Fuel Day Tank | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-SDV-0022-CL01 | T-00233-5603 | E | PS5-71-04 - CFO Storage Tank | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SDV-0029-CL01 | T-00233-5604 | E | PS5-71-15 - Diesel Fuel Storage Tank | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-SDV-0039-CL01 | T-00233-5605 | E | PS5-71-12 - CFO Service Tank | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-UZ-6200-CL01 | T-00233-5606 | E | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-XV-0089-CL01 | T-00233-5607 | E | PS5-71-04 - CFO Storage Tank | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-XV-0090-CL01 | T-00233-5608 | E | PS5-71-12 - CFO Service Tank | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Closed + Accepted with Punch
PS5-71-XV-0091-CL01 | T-00233-5609 | E | PS5-71-18 - Diesel Separator Module | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-XV-0092-CL01 | T-00233-5610 | E | PS5-71-20 - Diesel Fuel Day Tank | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-74-LB-5101-CL01 | T-00233-5612 | E | PS5-74-02 - N2 Generation Skid (UCP) | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-74-LB-5101-CL02 | T-00233-5613 | E | PS5-74-02 - N2 Generation Skid (UCP) | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-75-MOV-0001-CL01 | T-00233-5620 | E | PS5-28-07 - Open Drains (OD2) | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Closed + Accepted with Punch
PS5-75-UI-6200-CL01 | T-00233-5621 | E | PS5-75-01 - DRA Injection Package | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-75-UI-6200-CL02 | T-00233-5622 | E | PS5-75-01 - DRA Injection Package | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-78-JC-9100A-CL01 | T-00233-5623 | E | PS5-78-01 - Lifting and handling equipment | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-78-JC-9100B-CL01 | T-00233-5624 | E | PS5-78-01 - Lifting and handling equipment | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-78-JC-9100C-CL01 | T-00233-5625 | E | PS5-78-01 - Lifting and handling equipment | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-78-JC-9100D-CL01 | T-00233-5626 | E | PS5-78-01 - Lifting and handling equipment | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-87-IRF-0001-CL01 | T-00233-5640 | E | PS5-53-01 - Utility Water / Storage Tank | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-87-IRF-0002-CL01 | T-00233-5641 | E | PS5-71-04 - CFO Storage Tank | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-87-IRF-0003-CL01 | T-00233-5642 | E | PS5-71-12 - CFO Service Tank | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Closed + Accepted with Punch
PS5-87-IRF-0004-CL01 | T-00233-5643 | E | PS5-71-15 - Diesel Fuel Storage Tank | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-79-IG-0001-CL01 | T-00233-8829 | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0002-CL01 | T-00233-8830 | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0003-CL01 | T-00233-8831 | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0004-CL01 | T-00233-8832 | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0005-CL01 | T-00233-8833 | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0006-CL01 | T-00233-8834 | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0007-CL01 | T-00233-8835 | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0008-CL01 | T-00233-8836 | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0009-CL01 | T-00233-8837 | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0010-CL01 | T-00233-8838 | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0011-CL01 | T-00233-8839 | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0012-CL01 | T-00233-8840 | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-02-SWSI-0001-CL01 | T-00233-9120 | E | PS5-02-01 - Miscellaneous Safety equipment | TPX09 - LV power cable | Closed | Yes | Accepted | A:0/1, B:0/2 | Yes | Closed + Accepted
PS5-02-SWSI-0003-CL01 | T-00233-9121 | E | PS5-02-01 - Miscellaneous Safety equipment | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-06-GU-0005-CL01 | T-00233-9122 | E | PS5-06-04 - AC UPS - Guard House | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-7001-CL01 | T-00233-9128 | E | PS5-09-02 - HVAC for Guard House | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0007A-CL01 | T-00233-9131 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | TPX09 - LV power cable | Closed | Yes | Other | A:0/1, B:0/2 | Yes | Closed + Other
PS5-60-BE-0007B-CL01 | T-00233-9132 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | TPX09 - LV power cable | Closed | Yes | Other | A:0/1, B:0/2 | Yes | Closed + Other
PS5-60-BE-0007C-CL01 | T-00233-9133 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0007D-CL01 | T-00233-9134 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | TPX09 - LV power cable | Closed | No | No RFI Yet | B:0/1 | Yes | Closed but No RFI
PS5-60-BE-0007E-CL01 | T-00233-9135 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0007F-CL01 | T-00233-9136 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0007G-CL01 | T-00233-9137 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0027A-CL01 | T-00233-9138 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BE-0027B-CL01 | T-00233-9139 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0027C-CL01 | T-00233-9140 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0027D-CL01 | T-00233-9141 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0027E-CL01 | T-00233-9142 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0027F-CL01 | T-00233-9143 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0027G-CL01 | T-00233-9144 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0028A-CL01 | T-00233-9145 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BE-0028B-CL01 | T-00233-9146 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BE-0028C-CL01 | T-00233-9147 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0028D-CL01 | T-00233-9148 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0028E-CL01 | T-00233-9149 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0028F-CL01 | T-00233-9150 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BE-0028G-CL01 | T-00233-9151 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006A-CL01 | T-00233-9152 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0006A-CL02 | T-00233-9153 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-BI-0006A-CL03 | T-00233-9154 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0006A-CL04 | T-00233-9155 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0006A-CL05 | T-00233-9156 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0006A-CL06 | T-00233-9157 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0006A-CL07 | T-00233-9158 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0006A-CL08 | T-00233-9159 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0006A-CL09 | T-00233-9160 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0006A-CL10 | T-00233-9161 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0006A-CL11 | T-00233-9162 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0006B-CL01 | T-00233-9163 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0006B-CL02 | T-00233-9164 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0006B-CL03 | T-00233-9165 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0006B-CL04 | T-00233-9166 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0006B-CL05 | T-00233-9167 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0006B-CL06 | T-00233-9168 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0006B-CL07 | T-00233-9169 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0006B-CL08 | T-00233-9170 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0006B-CL09 | T-00233-9171 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0006B-CL10 | T-00233-9172 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0006B-CL11 | T-00233-9173 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0006C-CL01 | T-00233-9174 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006C-CL02 | T-00233-9175 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006C-CL03 | T-00233-9176 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006C-CL04 | T-00233-9177 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006C-CL05 | T-00233-9178 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006C-CL06 | T-00233-9179 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006C-CL07 | T-00233-9180 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006C-CL08 | T-00233-9181 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006C-CL09 | T-00233-9182 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006C-CL10 | T-00233-9183 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006C-CL11 | T-00233-9184 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006D-CL01 | T-00233-9185 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006D-CL02 | T-00233-9186 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006D-CL03 | T-00233-9187 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006D-CL04 | T-00233-9188 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006D-CL05 | T-00233-9189 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006D-CL06 | T-00233-9190 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006D-CL07 | T-00233-9191 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006D-CL08 | T-00233-9192 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006D-CL09 | T-00233-9193 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006D-CL10 | T-00233-9194 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006D-CL11 | T-00233-9195 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006E-CL01 | T-00233-9196 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006E-CL02 | T-00233-9197 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CL03 | T-00233-9198 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006E-CL04 | T-00233-9199 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CL05 | T-00233-9200 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CL06 | T-00233-9201 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CL07 | T-00233-9202 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CL08 | T-00233-9203 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006E-CL09 | T-00233-9204 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CL10 | T-00233-9205 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CL11 | T-00233-9206 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006F-CL01 | T-00233-9207 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CL02 | T-00233-9208 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CL03 | T-00233-9209 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CL04 | T-00233-9210 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006F-CL05 | T-00233-9211 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CL06 | T-00233-9212 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CL07 | T-00233-9213 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CL08 | T-00233-9214 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CL09 | T-00233-9215 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CL10 | T-00233-9216 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CL11 | T-00233-9217 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0006G-CL01 | T-00233-9218 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CL02 | T-00233-9219 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CL03 | T-00233-9220 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CL04 | T-00233-9221 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CL05 | T-00233-9222 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CL06 | T-00233-9223 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CL07 | T-00233-9224 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CL08 | T-00233-9225 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CL09 | T-00233-9226 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CL10 | T-00233-9227 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CL11 | T-00233-9228 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0017A-CL01 | T-00233-9229 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0017B-CL01 | T-00233-9230 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | TPX09 - LV power cable | Closed | Yes | Open | A:0/1, B:0/2 | Yes | Closed + Open
PS5-60-BI-0017C-CL01 | T-00233-9231 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0017D-CL01 | T-00233-9232 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0017E-CL01 | T-00233-9233 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0017F-CL01 | T-00233-9234 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0017G-CL01 | T-00233-9235 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-2900A-CL01 | T-00233-9236 | E | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2900B-CL01 | T-00233-9237 | E | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-EA-2900C-CL01 | T-00233-9238 | E | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-2900D-CL01 | T-00233-9239 | E | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-2900E-CL01 | T-00233-9240 | E | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-2900F-CL01 | T-00233-9241 | E | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-EA-2900G-CL01 | T-00233-9242 | E | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IK-0005-CL01 | T-00233-9243 | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building ( | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0004-CL01 | T-00233-9244 | E | PS5-71-08 - CFO Pre-Pressure Modules | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-71-BE-0004-CL02 | T-00233-9245 | E | PS5-71-08 - CFO Pre-Pressure Modules | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BE-0004-CL03 | T-00233-9246 | E | PS5-71-08 - CFO Pre-Pressure Modules | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-71-BI-0003-CL01 | T-00233-9247 | E | PS5-71-08 - CFO Pre-Pressure Modules | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-71-BI-0003-CL02 | T-00233-9248 | E | PS5-71-08 - CFO Pre-Pressure Modules | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-BI-0003-CL03 | T-00233-9249 | E | PS5-71-08 - CFO Pre-Pressure Modules | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-BI-0003-CL04 | T-00233-9250 | E | PS5-71-08 - CFO Pre-Pressure Modules | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-BI-0004-CL01 | T-00233-9251 | E | PS5-71-08 - CFO Pre-Pressure Modules | TPX09 - LV power cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-BI-0005-CL01 | T-00233-9252 | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | TPX09 - LV power cable | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-71-BI-0005-CL02 | T-00233-9253 | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | TPX09 - LV power cable | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-71-BI-0005-CL03 | T-00233-9254 | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | TPX09 - LV power cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-71-BI-0006-CL01 | T-00233-9255 | E | PS5-71-22 - Diesel Fuel Pre Pressure Module | TPX09 - LV power cable | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-09-AHU-8111A-CL01 | T-00233-9680 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8111B-CL01 | T-00233-9681 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8211A-CL01 | T-00233-9682 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8211B-CL01 | T-00233-9683 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8311A-CL01 | T-00233-9684 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8311A-CL02 | T-00233-9685 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8311B-CL01 | T-00233-9686 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8311B-CL02 | T-00233-9687 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8321A-CL01 | T-00233-9688 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8321A-CL02 | T-00233-9689 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8321B-CL01 | T-00233-9690 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8321B-CL02 | T-00233-9691 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8331A-CL01 | T-00233-9692 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8331A-CL02 | T-00233-9693 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8331B-CL01 | T-00233-9694 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8331B-CL02 | T-00233-9695 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8341-CL01 | T-00233-9696 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8341-CL02 | T-00233-9697 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8411A-CL01 | T-00233-9698 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8411A-CL02 | T-00233-9699 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8411B-CL01 | T-00233-9700 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AHU-8411B-CL02 | T-00233-9701 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442A-CL01 | T-00233-9702 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442B-CL01 | T-00233-9703 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442C-CL01 | T-00233-9704 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442D-CL01 | T-00233-9705 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442E-CL01 | T-00233-9706 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442F-CL01 | T-00233-9707 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442G-CL01 | T-00233-9708 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442H-CL01 | T-00233-9709 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-0008-CL03 | T-00233-9710 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PA-84500A-CL01 | T-00233-9711 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PA-84500B-CL01 | T-00233-9712 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-QX-8451A-CL01 | T-00233-9713 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-QX-8451A-CL02 | T-00233-9714 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-QX-8451B-CL01 | T-00233-9715 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-QX-8451B-CL02 | T-00233-9716 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-81200A-CL01 | T-00233-9717 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-81200B-CL01 | T-00233-9718 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-81200C-CL01 | T-00233-9719 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-82200A-CL01 | T-00233-9720 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-82200B-CL01 | T-00233-9721 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-82200C-CL01 | T-00233-9722 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-82200D-CL01 | T-00233-9723 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500A-CL01 | T-00233-9724 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500B-CL01 | T-00233-9725 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500C-CL01 | T-00233-9726 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500D-CL01 | T-00233-9727 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500E-CL01 | T-00233-9728 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500F-CL01 | T-00233-9729 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500G-CL01 | T-00233-9730 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500H-CL01 | T-00233-9731 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500J-CL01 | T-00233-9732 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500K-CL01 | T-00233-9733 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500L-CL01 | T-00233-9734 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500M-CL01 | T-00233-9735 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500N-CL01 | T-00233-9736 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83500P-CL01 | T-00233-9737 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600A-CL01 | T-00233-9738 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600B-CL01 | T-00233-9739 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600C-CL01 | T-00233-9740 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600D-CL01 | T-00233-9741 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600E-CL01 | T-00233-9742 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600F-CL01 | T-00233-9743 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600G-CL01 | T-00233-9744 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600H-CL01 | T-00233-9745 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600J-CL01 | T-00233-9746 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600K-CL01 | T-00233-9747 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600L-CL01 | T-00233-9748 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600M-CL01 | T-00233-9749 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600N-CL01 | T-00233-9750 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83600P-CL01 | T-00233-9751 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700A-CL01 | T-00233-9752 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700B-CL01 | T-00233-9753 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700C-CL01 | T-00233-9754 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700D-CL01 | T-00233-9755 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700E-CL01 | T-00233-9756 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700F-CL01 | T-00233-9757 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700G-CL01 | T-00233-9758 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700H-CL01 | T-00233-9759 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700J-CL01 | T-00233-9760 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700K-CL01 | T-00233-9761 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700L-CL01 | T-00233-9762 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700M-CL01 | T-00233-9763 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700N-CL01 | T-00233-9764 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83700P-CL01 | T-00233-9765 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83800A-CL01 | T-00233-9766 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83800B-CL01 | T-00233-9767 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83800C-CL01 | T-00233-9768 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83800D-CL01 | T-00233-9769 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83800E-CL01 | T-00233-9770 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83800F-CL01 | T-00233-9771 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-83800G-CL01 | T-00233-9772 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-84200A-CL01 | T-00233-9773 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-RF-84200B-CL01 | T-00233-9774 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-UZ-84600-CL01 | T-00233-9775 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004A-CL01 | T-00233-9776 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004B-CL01 | T-00233-9777 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004C-CL01 | T-00233-9778 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004D-CL01 | T-00233-9779 | E | PS5-09-03 - HVAC for Generator Building | TPX09 - LV power cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-IE-8100-CD01 | T-00234-2028 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-05-IE-8100-CD02 | T-00234-2029 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-05-IE-8100-CD03 | T-00234-2030 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-05-IE-8100-CD04 | T-00234-2031 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-05-IE-8100-CD05 | T-00234-2032 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-05-IE-8100-CD06 | T-00234-2033 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-05-IE-8100-CD07 | T-00234-2034 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-05-IE-8100-CD08 | T-00234-2035 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX10 - Multicore electrical control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD10 | T-00234-2037 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX10 - Multicore electrical control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD11 | T-00234-2038 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-05-IE-8100-CD12 | T-00234-2039 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX10 - Multicore electrical control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD13 | T-00234-2040 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX10 - Multicore electrical control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD14 | T-00234-2041 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX10 - Multicore electrical control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD15 | T-00234-2042 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX10 - Multicore electrical control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD16 | T-00234-2043 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX10 - Multicore electrical control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD17 | T-00234-2044 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX10 - Multicore electrical control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD18 | T-00234-2045 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-05-IE-8100-CD19 | T-00234-2046 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-05-IE-8100-CD20 | T-00234-2047 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-05-IE-8100-CD21 | T-00234-2048 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-05-IE-8100-CD25 | T-00234-2052 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-25-DM-3100A-CD01 | T-00234-2061 | E | PS5-25-02 - Crude Oil Export Pump A | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-DM-3100B-CD01 | T-00234-2062 | E | PS5-25-03 - Crude Oil Export Pump B | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-DM-3100C-CD01 | T-00234-2063 | E | PS5-25-04 - Crude Oil Export Pump C | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/2, B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-IES-3100A-CD01 | T-00234-2067 | E | PS5-25-02 - Crude Oil Export Pump A | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-IES-3100B-CD01 | T-00234-2068 | E | PS5-25-03 - Crude Oil Export Pump B | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-IES-3100C-CD01 | T-00234-2069 | E | PS5-25-04 - Crude Oil Export Pump C | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-50-IE-0001-CD01 | T-00234-2097 | E | PS5-50-01 - Water Well Submersible Pumps (3100) | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-50-IE-0002-CD01 | T-00234-2098 | E | PS5-50-02 - Water Well Submersible Pumps (3200) | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002A-CD01 | T-00234-2101 | E | PS5-60-01 - Power Generation Package A | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0002A-CD02 | T-00234-2102 | E | PS5-60-01 - Power Generation Package A | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0002A-CD03 | T-00234-2103 | E | PS5-60-01 - Power Generation Package A | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0002B-CD01 | T-00234-2104 | E | PS5-60-04 - Power Generation Package B | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0002B-CD02 | T-00234-2105 | E | PS5-60-04 - Power Generation Package B | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0002B-CD03 | T-00234-2106 | E | PS5-60-04 - Power Generation Package B | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0002C-CD01 | T-00234-2107 | E | PS5-60-07 - Power Generation Package C | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0002C-CD02 | T-00234-2108 | E | PS5-60-07 - Power Generation Package C | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0002C-CD03 | T-00234-2109 | E | PS5-60-07 - Power Generation Package C | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0002D-CD01 | T-00234-2110 | E | PS5-60-10 - Power Generation Package D | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0002D-CD02 | T-00234-2111 | E | PS5-60-10 - Power Generation Package D | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0002D-CD03 | T-00234-2112 | E | PS5-60-10 - Power Generation Package D | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0002E-CD01 | T-00234-2113 | E | PS5-60-13 - Power Generation Package E | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0002E-CD02 | T-00234-2114 | E | PS5-60-13 - Power Generation Package E | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0002E-CD03 | T-00234-2115 | E | PS5-60-13 - Power Generation Package E | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0002F-CD01 | T-00234-2116 | E | PS5-60-16 - Power Generation Package F | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0002F-CD02 | T-00234-2117 | E | PS5-60-16 - Power Generation Package F | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0002F-CD03 | T-00234-2118 | E | PS5-60-16 - Power Generation Package F | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0002G-CD01 | T-00234-2119 | E | PS5-60-19 - Power Generation Package G | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0002G-CD02 | T-00234-2120 | E | PS5-60-19 - Power Generation Package G | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0002G-CD03 | T-00234-2121 | E | PS5-60-19 - Power Generation Package G | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003A-CD02 | T-00234-2123 | E | PS5-60-01 - Power Generation Package A | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IE-0003A-CD03 | T-00234-2124 | E | PS5-60-01 - Power Generation Package A | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Closed + Accepted with Punch
PS5-60-IE-0003A-CD04 | T-00234-2125 | E | PS5-60-01 - Power Generation Package A | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IE-0003A-CD05 | T-00234-2126 | E | PS5-60-01 - Power Generation Package A | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Closed + Accepted with Punch
PS5-60-IE-0003A-CD14 | T-00234-2135 | E | PS5-60-01 - Power Generation Package A | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0003A-CD15 | T-00234-2136 | E | PS5-60-01 - Power Generation Package A | TPX10 - Multicore electrical control cable | Closed | Yes | Other | B:0/2 | Yes | Closed + Other
PS5-60-IE-0003B-CD02 | T-00234-2138 | E | PS5-60-04 - Power Generation Package B | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0003B-CD03 | T-00234-2139 | E | PS5-60-04 - Power Generation Package B | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0003B-CD04 | T-00234-2140 | E | PS5-60-04 - Power Generation Package B | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0003B-CD05 | T-00234-2141 | E | PS5-60-04 - Power Generation Package B | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IE-0003B-CD14 | T-00234-2150 | E | PS5-60-04 - Power Generation Package B | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0003B-CD15 | T-00234-2151 | E | PS5-60-04 - Power Generation Package B | TPX10 - Multicore electrical control cable | Closed | Yes | Other | B:0/2 | Yes | Closed + Other
PS5-60-IE-0003C-CD02 | T-00234-2153 | E | PS5-60-07 - Power Generation Package C | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CD03 | T-00234-2154 | E | PS5-60-07 - Power Generation Package C | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CD04 | T-00234-2155 | E | PS5-60-07 - Power Generation Package C | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0003C-CD05 | T-00234-2156 | E | PS5-60-07 - Power Generation Package C | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CD14 | T-00234-2165 | E | PS5-60-07 - Power Generation Package C | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CD15 | T-00234-2166 | E | PS5-60-07 - Power Generation Package C | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CD02 | T-00234-2168 | E | PS5-60-10 - Power Generation Package D | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CD03 | T-00234-2169 | E | PS5-60-10 - Power Generation Package D | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IE-0003D-CD04 | T-00234-2170 | E | PS5-60-10 - Power Generation Package D | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IE-0003D-CD05 | T-00234-2171 | E | PS5-60-10 - Power Generation Package D | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IE-0003D-CD14 | T-00234-2180 | E | PS5-60-10 - Power Generation Package D | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | A:0/1, B:0/1 | Yes | Closed but No RFI
PS5-60-IE-0003D-CD15 | T-00234-2181 | E | PS5-60-10 - Power Generation Package D | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CD02 | T-00234-2183 | E | PS5-60-13 - Power Generation Package E | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CD03 | T-00234-2184 | E | PS5-60-13 - Power Generation Package E | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CD04 | T-00234-2185 | E | PS5-60-13 - Power Generation Package E | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0003E-CD05 | T-00234-2186 | E | PS5-60-13 - Power Generation Package E | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CD14 | T-00234-2195 | E | PS5-60-13 - Power Generation Package E | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CD15 | T-00234-2196 | E | PS5-60-13 - Power Generation Package E | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CD02 | T-00234-2198 | E | PS5-60-16 - Power Generation Package F | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003F-CD03 | T-00234-2199 | E | PS5-60-16 - Power Generation Package F | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003F-CD04 | T-00234-2200 | E | PS5-60-16 - Power Generation Package F | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0003F-CD05 | T-00234-2201 | E | PS5-60-16 - Power Generation Package F | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CD14 | T-00234-2210 | E | PS5-60-16 - Power Generation Package F | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CD15 | T-00234-2211 | E | PS5-60-16 - Power Generation Package F | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003G-CD02 | T-00234-2213 | E | PS5-60-19 - Power Generation Package G | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003G-CD03 | T-00234-2214 | E | PS5-60-19 - Power Generation Package G | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003G-CD04 | T-00234-2215 | E | PS5-60-19 - Power Generation Package G | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IE-0003G-CD05 | T-00234-2216 | E | PS5-60-19 - Power Generation Package G | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003G-CD14 | T-00234-2225 | E | PS5-60-19 - Power Generation Package G | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003G-CD15 | T-00234-2226 | E | PS5-60-19 - Power Generation Package G | TPX10 - Multicore electrical control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-61-IDH-3100A-CD03 | T-00234-2233 | E | PS5-25-02 - Crude Oil Export Pump A | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-61-IDH-3100B-CD03 | T-00234-2236 | E | PS5-25-03 - Crude Oil Export Pump B | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IDH-3100C-CD03 | T-00234-2239 | E | PS5-25-04 - Crude Oil Export Pump C | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-62-IE-0001-CD01 | T-00234-2288 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | TPX10 - Multicore electrical control cable | Closed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IG-0001-CD01 | T-00234-3288 | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0002-CD01 | T-00234-3289 | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0003-CD01 | T-00234-3290 | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0004-CD01 | T-00234-3291 | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0005-CD01 | T-00234-3292 | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0006-CD01 | T-00234-3293 | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0007-CD01 | T-00234-3294 | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0008-CD01 | T-00234-3295 | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0009-CD01 | T-00234-3296 | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0010-CD01 | T-00234-3297 | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0011-CD01 | T-00234-3298 | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0012-CD01 | T-00234-3299 | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-06-GU-0003A-CD02 | T-00234-3399 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX10 - Multicore electrical control cable | Closed | Yes | Other | B:0/2 | Yes | Closed + Other
PS5-09-IES-8101A-CD01 | T-00234-3634 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8101B-CD01 | T-00234-3635 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8102A-CD01 | T-00234-3636 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8102B-CD01 | T-00234-3637 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8102C-CD01 | T-00234-3638 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8201A-CD01 | T-00234-3639 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8201B-CD01 | T-00234-3640 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8202A-CD01 | T-00234-3641 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8202B-CD01 | T-00234-3642 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8202C-CD01 | T-00234-3643 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8202D-CD01 | T-00234-3644 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8301A-CD01 | T-00234-3645 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8301B-CD01 | T-00234-3646 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8302A-CD01 | T-00234-3647 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8302B-CD01 | T-00234-3648 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8304A-CD01 | T-00234-3649 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8304B-CD01 | T-00234-3650 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8305A-CD01 | T-00234-3651 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8305B-CD01 | T-00234-3652 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8307A-CD01 | T-00234-3653 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8307B-CD01 | T-00234-3654 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8308A-CD01 | T-00234-3655 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8308B-CD01 | T-00234-3656 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8311A-CD01 | T-00234-3657 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8311B-CD01 | T-00234-3658 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8313-CD01 | T-00234-3659 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8314-CD01 | T-00234-3660 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8315-CD01 | T-00234-3661 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8316-CD01 | T-00234-3662 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8317-CD01 | T-00234-3663 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8318-CD01 | T-00234-3664 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8319-CD01 | T-00234-3665 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8321-CD01 | T-00234-3666 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8322-CD01 | T-00234-3667 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8323-CD01 | T-00234-3668 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8324-CD01 | T-00234-3669 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8325-CD01 | T-00234-3670 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8401A-CD01 | T-00234-3671 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8401B-CD01 | T-00234-3672 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8403A-CD01 | T-00234-3673 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8403B-CD01 | T-00234-3674 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8404A-CD01 | T-00234-3675 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8404B-CD01 | T-00234-3676 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8405A-CD01 | T-00234-3677 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8405B-CD01 | T-00234-3678 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406A-CD01 | T-00234-3679 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406B-CD01 | T-00234-3680 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406C-CD01 | T-00234-3681 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406D-CD01 | T-00234-3682 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406E-CD01 | T-00234-3683 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406F-CD01 | T-00234-3684 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406G-CD01 | T-00234-3685 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8406H-CD01 | T-00234-3686 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-IES-8407-CD01 | T-00234-3687 | E | PS5-09-03 - HVAC for Generator Building | TPX10 - Multicore electrical control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-DM-3100A | T-00235-0013 | E | PS5-25-02 - Crude Oil Export Pump A | TPX12 - Motor HV | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-25-DM-3100B | T-00235-0014 | E | PS5-25-03 - Crude Oil Export Pump B | TPX12 - Motor HV | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-25-DM-3100C | T-00235-0015 | E | PS5-25-04 - Crude Oil Export Pump C | TPX12 - Motor HV | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-28-DM-3300 | T-00236-0155 | E | PS5-28-06 - Relief Drum and Pump | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3400 | T-00236-0156 | E | PS5-28-03 - Closed Drain Drum and Pump 01 | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3500 | T-00236-0157 | E | PS5-28-08 - Open Drain Sump and Pumps | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3600A | T-00236-0158 | E | PS5-28-08 - Open Drain Sump and Pumps | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3600B | T-00236-0159 | E | PS5-28-08 - Open Drain Sump and Pumps | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3700A | T-00236-0160 | E | PS5-28-04 - Closed Drain Drum and Pump 02 | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3700B | T-00236-0161 | E | PS5-28-04 - Closed Drain Drum and Pump 02 | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3800A | T-00236-0162 | E | PS5-28-13 - Seal Oil Drain Drum & Pump A | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3800B | T-00236-0163 | E | PS5-28-14 - Seal Oil Drain Drum & Pump B | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3800C | T-00236-0164 | E | PS5-28-15 - Seal Oil Drain Drum & Pump C | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3900A | T-00236-0165 | E | PS5-28-17 - Reinjection Pump | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-3900B | T-00236-0166 | E | PS5-28-17 - Reinjection Pump | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-DM-3100A | T-00236-0167 | E | PS5-53-02 - Water Distribution Pump A/B | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-DM-3100B | T-00236-0168 | E | PS5-53-02 - Water Distribution Pump A/B | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-DM-3300 | T-00236-0169 | E | PS5-60-24 - Cooling Water Tank & Pump | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-DM-3400 | T-00236-0170 | E | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-DM-3100A | T-00236-0171 | E | PS5-71-16 - Diesel Fuel Supply Pump A/B | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-DM-3100B | T-00236-0172 | E | PS5-71-16 - Diesel Fuel Supply Pump A/B | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-DM-3200 | T-00236-0173 | E | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-DM-3300A | T-00236-0174 | E | PS5-71-05 - CFO Transfer Pump A/B | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-DM-3300B | T-00236-0175 | E | PS5-71-05 - CFO Transfer Pump A/B | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-DM-3400A | T-00236-0176 | E | PS5-71-13 - CFO Service Pump A/B | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-DM-3400B | T-00236-0177 | E | PS5-71-13 - CFO Service Pump A/B | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-DM-3500A | T-00236-0178 | E | PS5-71-21 - Diesel Transfer Pump A/B | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-DM-3500B | T-00236-0179 | E | PS5-71-21 - Diesel Transfer Pump A/B | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-DM-31100 | T-00236-0286 | E | PS5-28-10 - Oil Skimmer Package | TPX13 - Motor LV | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003A | T-00238-0457 | E | PS5-60-02 - Power Gen Package A (UCP) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B | T-00238-0458 | E | PS5-60-05 - Power Gen Package B (UCP) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C | T-00238-0459 | E | PS5-60-08 - Power Gen Package C (UCP) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D | T-00238-0460 | E | PS5-60-11 - Power Gen Package D (UCP) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E | T-00238-0461 | E | PS5-60-14 - Power Gen Package E (UCP) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F | T-00238-0462 | E | PS5-60-17 - Power Gen Package F (UCP) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G | T-00238-0463 | E | PS5-60-20 - Power Gen Package G (UCP) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004 | T-00238-0464 | E | PS5-60-22 - Power Gen Master UCP | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001A | T-00238-0465 | E | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | TPX15 - Distribution board/console/control panel | Started (not Completed) | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001B | T-00238-0466 | E | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001C | T-00238-0467 | E | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001D | T-00238-0468 | E | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001E | T-00238-0469 | E | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001F | T-00238-0470 | E | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001G | T-00238-0471 | E | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0002 | T-00238-0472 | E | PS5-60-22 - Power Gen Master UCP | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002A | T-00238-0473 | E | PS5-60-01 - Power Generation Package A | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002B | T-00238-0474 | E | PS5-60-04 - Power Generation Package B | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002C | T-00238-0475 | E | PS5-60-07 - Power Generation Package C | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002D | T-00238-0476 | E | PS5-60-10 - Power Generation Package D | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002E | T-00238-0477 | E | PS5-60-13 - Power Generation Package E | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002F | T-00238-0478 | E | PS5-60-16 - Power Generation Package F | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002G | T-00238-0479 | E | PS5-60-19 - Power Generation Package G | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-IE-0001A | T-00238-0542 | E | PS5-01-05 - Foam Skid | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-IE-0001B | T-00238-0543 | E | PS5-01-05 - Foam Skid | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-IE-0002A | T-00238-0544 | E | PS5-01-01 - Fire Water Jockey Pump A/B | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-IE-0002B | T-00238-0545 | E | PS5-01-01 - Fire Water Jockey Pump A/B | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-IE-0009A | T-00238-0546 | E | PS5-01-02 - Fire Water Pump A | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-IE-0009B | T-00238-0547 | E | PS5-01-03 - Fire Water Pump B | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-IE-8100 | T-00238-0549 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | B:0/1, C:0/2 | Yes | Not Started
PS5-50-IE-0001 | T-00238-0550 | E | PS5-50-01 - Water Well Submersible Pumps (3100) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-50-IE-0002 | T-00238-0551 | E | PS5-50-02 - Water Well Submersible Pumps (3200) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002A | T-00238-0552 | E | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002B | T-00238-0553 | E | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002C | T-00238-0554 | E | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002D | T-00238-0555 | E | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002E | T-00238-0556 | E | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002F | T-00238-0557 | E | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002G | T-00238-0558 | E | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004 | T-00238-0559 | E | PS5-09-03 - HVAC for Generator Building | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004A | T-00238-0560 | E | PS5-09-03 - HVAC for Generator Building | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004B | T-00238-0561 | E | PS5-09-03 - HVAC for Generator Building | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0001 | T-00238-0562 | E | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | TPX15 - Distribution board/console/control panel | Closed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-62-IE-0002 | T-00238-0563 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | TPX15 - Distribution board/console/control panel | Closed | Yes | Accepted with Punch | B:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-71-IN-0001 | T-00238-0564 | E | PS5-71-19 - Diesel Separator Module (UCP) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0002 | T-00238-0565 | E | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0003 | T-00238-0566 | E | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004A | T-00238-0567 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004B | T-00238-0568 | E | PS5-71-07 - Crude Fuel Separation Module (UCP) | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-IG-0001 | T-00238-0714 | E | PS5-01-10 - Water Mist Package | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-IG-0002 | T-00238-0715 | E | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-00 | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-IG-0004 | T-00238-0716 | E | PS5-62-03 - Outdoor Emergency Lighting DB - PS5-05-IG-0004 | TPX15 - Distribution board/console/control panel | Closed | Yes | Accepted with Punch | A:0/1, B:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-05-IG-0006 | T-00238-0717 | E | PS5-62-04 - Outdoor Emergency Lighting DB - PS5-05-IG-0006 | TPX15 - Distribution board/console/control panel | Closed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-05-IG-0007 | T-00238-0718 | E | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-IG-0025 | T-00238-0719 | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-05-IG-0026 | T-00238-0720 | E | PS5-62-07 - CRO Generator Electrical Building Emergency Ligh | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-06-IG-0004A | T-00238-0721 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | C:0/2 | Yes | Not Started
PS5-06-IG-0004B | T-00238-0722 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | C:0/2 | Yes | Not Started
PS5-61-IG-0006 | T-00238-0723 | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | TPX15 - Distribution board/console/control panel | Closed | Yes | Accepted with Punch | B:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IG-0007 | T-00238-0724 | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | TPX15 - Distribution board/console/control panel | Closed | Yes | Accepted with Punch | A:0/1, C:0/2 | Yes | Closed + Accepted with Punch
PS5-61-IG-0014 | T-00238-0725 | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-001 | TPX15 - Distribution board/console/control panel | Closed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IG-0015 | T-00238-0726 | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61- | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IG-0016 | T-00238-0727 | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IG-0042 | T-00238-0728 | E | PS5-61-10 - Outdoor Valves Distribution Board - PS5-61-IG-00 | TPX15 - Distribution board/console/control panel | Closed | Yes | Accepted with Punch | A:0/1, B:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-61-IG-0043 | T-00238-0729 | E | PS5-61-11 - Outdoor Valves Distribution Board - PS5-61-IG-00 | TPX15 - Distribution board/console/control panel | Closed | Yes | Accepted with Punch | B:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-74-IG-5101 | T-00238-0730 | E | PS5-74-01 - N2 Generation Skid | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-79-IG-0001 | T-00238-0731 | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution | TPX15 - Distribution board/console/control panel | Closed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IG-0002 | T-00238-0732 | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution | TPX15 - Distribution board/console/control panel | Closed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IG-0003 | T-00238-0733 | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution | TPX15 - Distribution board/console/control panel | Closed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IG-0004 | T-00238-0734 | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution | TPX15 - Distribution board/console/control panel | Closed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IG-0005 | T-00238-0735 | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution | TPX15 - Distribution board/console/control panel | Closed | Yes | Accepted with Punch | A:0/1, B:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IG-0006 | T-00238-0736 | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution | TPX15 - Distribution board/console/control panel | Closed | Yes | Accepted with Punch | A:0/1, B:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IG-0007 | T-00238-0737 | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution | TPX15 - Distribution board/console/control panel | Closed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IG-0008 | T-00238-0738 | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution | TPX15 - Distribution board/console/control panel | Closed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IG-0009 | T-00238-0739 | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution | TPX15 - Distribution board/console/control panel | Closed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IG-0010 | T-00238-0740 | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution | TPX15 - Distribution board/console/control panel | Closed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IG-0011 | T-00238-0741 | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution | TPX15 - Distribution board/console/control panel | Closed | Yes | Accepted with Punch | A:0/1, C:0/1 | Yes | Closed + Accepted with Punch
PS5-79-IG-0012 | T-00238-0742 | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-0008 | T-00238-0819 | E | PS5-09-03 - HVAC for Generator Building | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004C | T-00238-0820 | E | PS5-09-03 - HVAC for Generator Building | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004D | T-00238-0821 | E | PS5-09-03 - HVAC for Generator Building | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-7001 | T-00238-0858 | E | PS5-09-02 - HVAC for Guard House | TPX15 - Distribution board/console/control panel | To be completed | No | No RFI Yet | - |  | Not Started
PS5-06-GU-0003A | T-00239-0234 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX16 - Charger / inverter | To be completed | No | No RFI Yet | - |  | Not Started
PS5-06-GU-0003B | T-00239-0235 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX16 - Charger / inverter | To be completed | No | No RFI Yet | - |  | Not Started
PS5-06-GU-0003C | T-00239-0236 | E | PS5-06-02 - AC UPS - Power Generator Building | TPX16 - Charger / inverter | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-UD-3100A | T-00241-0165 | E | PS5-25-02 - Crude Oil Export Pump A | TPX19 - Power socket outlet | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-ISO-2008 | T-00241-0166 | E | PS5-28-10 - Oil Skimmer Package | TPX19 - Power socket outlet | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-HE-2100 | T-00242-0044 | E | PS5-28-03 - Closed Drain Drum and Pump 01 | TPX20 - Heater | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-HE-2200 | T-00242-0045 | E | PS5-28-04 - Closed Drain Drum and Pump 02 | TPX20 - Heater | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-HE-2200 | T-00242-0046 | E | PS5-71-12 - CFO Service Tank | TPX20 - Heater | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-HE-2300 | T-00242-0047 | E | PS5-71-04 - CFO Storage Tank | TPX20 - Heater | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-HE-2400A | T-00242-0048 | E | PS5-71-01 - CFO Storage Tank Feed Heater | TPX20 - Heater | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-HE-2400B | T-00242-0049 | E | PS5-71-01 - CFO Storage Tank Feed Heater | TPX20 - Heater | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-HE-2100 | T-00242-0068 | E | PS5-25-02 - Crude Oil Export Pump A | TPX20 - Heater | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-HE-2200 | T-00242-0069 | E | PS5-25-03 - Crude Oil Export Pump B | TPX20 - Heater | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-HE-2300 | T-00242-0070 | E | PS5-25-04 - Crude Oil Export Pump C | TPX20 - Heater | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-NER-0010 | T-00243-0041 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | TPX21 - Neutral earthing resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-NER-0011 | T-00243-0042 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | TPX21 - Neutral earthing resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-63-NER-0010 | T-00243-0043 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX21 - Neutral earthing resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-63-NER-0011 | T-00243-0044 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | TPX21 - Neutral earthing resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IJ-0001A | T-00243-0059 | E | PS5-60-01 - Power Generation Package A | TPX21 - Neutral earthing resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IJ-0001B | T-00243-0060 | E | PS5-60-04 - Power Generation Package B | TPX21 - Neutral earthing resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IJ-0001C | T-00243-0061 | E | PS5-60-07 - Power Generation Package C | TPX21 - Neutral earthing resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IJ-0001D | T-00243-0062 | E | PS5-60-10 - Power Generation Package D | TPX21 - Neutral earthing resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IJ-0001E | T-00243-0063 | E | PS5-60-13 - Power Generation Package E | TPX21 - Neutral earthing resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IJ-0001F | T-00243-0064 | E | PS5-60-16 - Power Generation Package F | TPX21 - Neutral earthing resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IJ-0001G | T-00243-0065 | E | PS5-60-19 - Power Generation Package G | TPX21 - Neutral earthing resistor | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - CFO AREA_Earthing | T-00247-0134 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - CHEMICAL AND WASTE STORAGE AREA_Earthing | T-00247-0135 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - CLOSED DRAIN DRUM AREA_Earthing | T-00247-0136 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - DIESEL FUEL STORAGE AND PUMP AREA_Earthing | T-00247-0137 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | Started (not Completed) | No | No RFI Yet | - |  | Not Started
PS5 - EXPORT PUMP VSD AREA_Earthing | T-00247-0138 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - EXPORT LOADING PUMP AREA_Earthing | T-00247-0139 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - FENCE EAST AREA_Earthing | T-00247-0140 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - FENCE SOUTH WEST AREA_Earthing | T-00247-0141 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - FENCE WEST AREA_Earthing | T-00247-0142 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - FENCE SOUTH EAST AREA_Earthing | T-00247-0143 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - LAUNCHER/RECEIVER AREA_Earthing | T-00247-0144 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - OBSERVATION BASIN AREA_Earthing | T-00247-0145 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - POWER DISTRIBUTION AREA_Earthing | T-00247-0146 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - POWER GENERATION BUILDING AREA_Earthing | T-00247-0147 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - POWER GENERATION COOLING TOWER AREA_Earthing | T-00247-0148 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - TURNSTILE GATE AND OFFICE BUILDING AREA_Earthing | T-00247-0149 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - UTILITY AREA_Earthing | T-00247-0150 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - UTILITY/FIRE WATER STORAGE TANK AREA_Earthing | T-00247-0151 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-OB-0001_Earthing | T-00247-0152 | E | PS5-63-02 - Electrical Earthing - Office and Facilities buil | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-OB-0005_Earthing | T-00247-0153 | E | PS5-63-06 - Electrical Earthing - Guard House | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-OB-0009A_Earthing | T-00247-0154 | E | PS5-63-05 - Electrical Earthing - Guard Hut A & B | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-OB-0009B_Earthing | T-00247-0155 | E | PS5-63-05 - Electrical Earthing - Guard Hut A & B | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0001_Earthing | T-00247-0157 | E | PS5-63-07 - Electrical Earthing - Workshop & Warehouse | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0003_Earthing | T-00247-0158 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0004_Earthing | T-00247-0159 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0005_Earthing | T-00247-0160 | E | PS5-63-03 - Electrical Earthing - Generator Building | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0006_Earthing | T-00247-0161 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0007_Earthing | T-00247-0162 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-86-OB-0001_Earthing | T-00247-0163 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-86-OB-0002_Earthing | T-00247-0164 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-86-OB-0003_Earthing | T-00247-0165 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-86-OB-0004_Earthing | T-00247-0166 | E | PS5-63-01 - Electrical Earthing | TPX26 - Earthing system | To be completed | No | No RFI Yet | - |  | Not Started
PS5 - RECEIVER AND LAUNCHER AREA_Lightning | T-00248-0052 | E | PS5-63-01 - Electrical Earthing | TPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-OB-0001_Lightning | T-00248-0053 | E | PS5-63-02 - Electrical Earthing - Office and Facilities buil | TPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-OB-0005_Lightning | T-00248-0054 | E | PS5-63-06 - Electrical Earthing - Guard House | TPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-OB-0009A_Lightning | T-00248-0055 | E | PS5-63-05 - Electrical Earthing - Guard Hut A & B | TPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-OB-0009B_Lightning | T-00248-0056 | E | PS5-63-05 - Electrical Earthing - Guard Hut A & B | TPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0001_Lightning | T-00248-0057 | E | PS5-63-07 - Electrical Earthing - Workshop & Warehouse | TPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0003_Lightning | T-00248-0058 | E | PS5-63-01 - Electrical Earthing | TPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0005_Lightning | T-00248-0059 | E | PS5-63-03 - Electrical Earthing - Generator Building | TPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0006_Lightning | T-00248-0060 | E | PS5-63-01 - Electrical Earthing | TPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-84-OB-0007_Lightning | T-00248-0061 | E | PS5-63-01 - Electrical Earthing | TPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-86-OB-0001_Lightning | T-00248-0062 | E | PS5-63-01 - Electrical Earthing | TPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-86-OB-0002_Lightning | T-00248-0063 | E | PS5-63-01 - Electrical Earthing | TPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-86-OB-0003_Lightning | T-00248-0064 | E | PS5-63-01 - Electrical Earthing | TPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-86-OB-0004_Lightning | T-00248-0065 | E | PS5-63-01 - Electrical Earthing | TPX28 - Lightning protection system | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-TR-4100 | T-00249-0008 | E | PS5-53-01 - Utility Water / Storage Tank | TPX33 - Cathodic protection | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TR-4100 | T-00249-0009 | E | PS5-71-04 - CFO Storage Tank | TPX33 - Cathodic protection | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TR-4200 | T-00249-0010 | E | PS5-71-12 - CFO Service Tank | TPX33 - Cathodic protection | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TR-4400 | T-00249-0011 | E | PS5-71-15 - Diesel Fuel Storage Tank | TPX33 - Cathodic protection | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PSV-1103 | T-00251-0115 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PSV-0064C | T-00251-0116 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PSV-1203 | T-00251-0117 | I | PS5-25-07 - Export Pipeline Pig Launcher | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PRV-0047B | T-00251-0118 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-74-PSV-0003 | T-00251-0119 | I | PS5-74-03 - Nitrogen Receiver | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PRV-0040 | T-00251-0120 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-50-PSV-0004A | T-00251-0121 | I | PS5-50-01 - Water Well Submersible Pumps (3100) | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PSV-2403A | T-00251-0122 | I | PS5-71-01 - CFO Storage Tank Feed Heater | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PSV-3901B | T-00251-0123 | I | PS5-28-17 - Reinjection Pump | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PRV-0047A | T-00251-0124 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PVSV-4202 | T-00251-0125 | I | PS5-71-12 - CFO Service Tank | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PVSV-4102 | T-00251-0126 | I | PS5-71-04 - CFO Storage Tank | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PRV-0046A | T-00251-0127 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PRV-0008 | T-00251-0128 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PSV-0064A | T-00251-0129 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PRV-0054 | T-00251-0130 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PSV-0044 | T-00251-0131 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PRV-0016 | T-00251-0132 | I | PS5-71-04 - CFO Storage Tank | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PRV-0046B | T-00251-0133 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PRV-0015 | T-00251-0134 | I | PS5-71-04 - CFO Storage Tank | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PRV-0018 | T-00251-0135 | I | PS5-71-12 - CFO Service Tank | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PRV-0041 | T-00251-0136 | I | PS5-71-12 - CFO Service Tank | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PSV-2403B | T-00251-0137 | I | PS5-71-01 - CFO Storage Tank Feed Heater | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PRV-0046C | T-00251-0138 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PRV-0047C | T-00251-0139 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PRV-0055 | T-00251-0140 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PSV-0061 | T-00251-0141 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PSV-0064B | T-00251-0142 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PSV-3901A | T-00251-0143 | I | PS5-28-17 - Reinjection Pump | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-50-PSV-0004B | T-00251-0144 | I | PS5-50-02 - Water Well Submersible Pumps (3200) | TJX03 - Relief valve | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RAB-B402-CC01 | T-00254-10862 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RAB-B902-CC01 | T-00254-10863 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RAB-W502-CC01 | T-00254-10864 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101A-CJ01 | T-00254-10865 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101B-CJ01 | T-00254-10866 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101C-CJ01 | T-00254-10867 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101D-CJ01 | T-00254-10868 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101E-CJ01 | T-00254-10869 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101F-CJ01 | T-00254-10870 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101G-CJ01 | T-00254-10871 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101H-CJ01 | T-00254-10872 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W101I-CJ01 | T-00254-10873 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601A-CJ01 | T-00254-10874 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601B-CJ01 | T-00254-10875 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601C-CJ01 | T-00254-10876 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601D-CJ01 | T-00254-10877 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601E-CJ01 | T-00254-10878 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601F-CJ01 | T-00254-10879 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601G-CJ01 | T-00254-10880 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601H-CJ01 | T-00254-10881 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601I-CJ01 | T-00254-10882 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601J-CJ01 | T-00254-10883 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601K-CJ01 | T-00254-10884 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601L-CJ01 | T-00254-10885 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601M-CJ01 | T-00254-10886 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601N-CJ01 | T-00254-10887 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601O-CJ01 | T-00254-10888 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDHR-W601P-CJ01 | T-00254-10889 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B101A-CJ01 | T-00254-10890 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B101B-CJ01 | T-00254-10891 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B101C-CJ01 | T-00254-10892 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B101D-CJ01 | T-00254-10893 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B201A-CJ01 | T-00254-10894 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B201B-CJ01 | T-00254-10895 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B201C-CJ01 | T-00254-10896 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B201D-CJ01 | T-00254-10897 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B201E-CJ01 | T-00254-10898 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B301A-CJ01 | T-00254-10899 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B301B-CJ01 | T-00254-10900 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B301C-CJ01 | T-00254-10901 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B301D-CJ01 | T-00254-10902 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B401A-CJ01 | T-00254-10903 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B401B-CJ01 | T-00254-10904 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B401C-CJ01 | T-00254-10905 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B401D-CJ01 | T-00254-10906 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B501A-CJ01 | T-00254-10907 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B601A-CJ01 | T-00254-10908 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701A-CJ01 | T-00254-10909 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701B-CJ01 | T-00254-10910 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701C-CJ01 | T-00254-10911 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701D-CJ01 | T-00254-10912 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701E-CJ01 | T-00254-10913 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701F-CJ01 | T-00254-10914 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701G-CJ01 | T-00254-10915 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701H-CJ01 | T-00254-10916 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B701I-CJ01 | T-00254-10917 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B801A-CJ01 | T-00254-10918 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B801B-CJ01 | T-00254-10919 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B901A-CJ01 | T-00254-10920 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B901B-CJ01 | T-00254-10921 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B901C-CJ01 | T-00254-10922 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B901D-CJ01 | T-00254-10923 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-B901E-CJ01 | T-00254-10924 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W201A-CJ01 | T-00254-10925 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W201B-CJ01 | T-00254-10926 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W201C-CJ01 | T-00254-10927 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W201D-CJ01 | T-00254-10928 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W301A-CJ01 | T-00254-10929 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W401A-CJ01 | T-00254-10930 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W501A-CJ01 | T-00254-10931 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W501B-CJ01 | T-00254-10932 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W501C-CJ01 | T-00254-10933 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W501D-CJ01 | T-00254-10934 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W501E-CJ01 | T-00254-10935 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-W501F-CJ01 | T-00254-10936 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-B401-CJ01 | T-00254-10937 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-B901-CJ01 | T-00254-10938 | I | PS5-03-24 - FZ - Office and Facilities Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-W501-CJ01 | T-00254-10939 | I | PS5-03-25 - FZ - Workshop & Warehouse | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AH-8401-CU01 | T-00254-11586 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AH-8401-CU02 | T-00254-11587 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AH-8402-CU01 | T-00254-11588 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AH-8402-CU02 | T-00254-11589 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AH-8403-CU01 | T-00254-11590 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AH-8403-CU02 | T-00254-11591 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8111A-CU01 | T-00254-11592 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8111A-CU02 | T-00254-11593 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8111B-CU01 | T-00254-11594 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8111B-CU02 | T-00254-11595 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8211A-CU01 | T-00254-11596 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8211A-CU02 | T-00254-11597 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8211B-CU01 | T-00254-11598 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8211B-CU02 | T-00254-11599 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8311A-A-CU01 | T-00254-11600 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8311A-A-CU02 | T-00254-11601 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8311B-B-CU01 | T-00254-11602 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8311B-B-CU02 | T-00254-11603 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8311C-A-CU01 | T-00254-11604 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8311C-A-CU02 | T-00254-11605 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8311D-B-CU01 | T-00254-11606 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8311D-B-CU02 | T-00254-11607 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8321A-A-CU01 | T-00254-11608 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8321A-A-CU02 | T-00254-11609 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8321B-B-CU01 | T-00254-11610 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8321B-B-CU02 | T-00254-11611 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8321C-A-CU01 | T-00254-11612 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8321C-A-CU02 | T-00254-11613 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8321D-B-CU01 | T-00254-11614 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8321D-B-CU02 | T-00254-11615 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8331A-A-CU01 | T-00254-11616 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8331A-A-CU02 | T-00254-11617 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8331B-B-CU01 | T-00254-11618 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8331B-B-CU02 | T-00254-11619 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8331C-A-CU01 | T-00254-11620 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8331C-A-CU02 | T-00254-11621 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8331D-B-CU01 | T-00254-11622 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8331D-B-CU02 | T-00254-11623 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8341A-A-CU01 | T-00254-11624 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8341A-A-CU02 | T-00254-11625 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8341B-B-CU01 | T-00254-11626 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8341B-B-CU02 | T-00254-11627 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8411A-CU01 | T-00254-11628 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8411A-CU02 | T-00254-11629 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8411B-CU01 | T-00254-11630 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8411B-CU02 | T-00254-11631 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8412A-CU01 | T-00254-11632 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8412A-CU02 | T-00254-11633 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8412B-CU01 | T-00254-11634 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8412B-CU02 | T-00254-11635 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8421A-CU01 | T-00254-11636 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8421A-CU02 | T-00254-11637 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8421B-CU01 | T-00254-11638 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8421B-CU02 | T-00254-11639 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8432A-CU01 | T-00254-11640 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8432A-CU02 | T-00254-11641 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8432B-CU01 | T-00254-11642 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-AS-8432B-CU02 | T-00254-11643 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8111A-CU01 | T-00254-11644 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8111B-CU01 | T-00254-11645 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8211A-CU01 | T-00254-11646 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8211B-CU01 | T-00254-11647 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8311A-A-CU01 | T-00254-11648 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8311A-B-CU01 | T-00254-11649 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8311B-A-CU01 | T-00254-11650 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8311B-B-CU01 | T-00254-11651 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8321A-A-CU01 | T-00254-11652 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8321A-B-CU01 | T-00254-11653 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8321B-A-CU01 | T-00254-11654 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8321B-B-CU01 | T-00254-11655 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8331A-A-CU01 | T-00254-11656 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8331A-B-CU01 | T-00254-11657 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8331B-A-CU01 | T-00254-11658 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8331B-B-CU01 | T-00254-11659 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8341A-A-CU01 | T-00254-11660 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8341A-B-CU01 | T-00254-11661 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8411A-CU01 | T-00254-11662 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-8411B-CU01 | T-00254-11663 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442A-CU01 | T-00254-11664 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442A-CU02 | T-00254-11665 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442B-CU01 | T-00254-11666 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442B-CU02 | T-00254-11667 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442C-CU01 | T-00254-11668 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442C-CU02 | T-00254-11669 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442D-CU01 | T-00254-11670 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442D-CU02 | T-00254-11671 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442E-CU01 | T-00254-11672 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442E-CU02 | T-00254-11673 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442F-CU01 | T-00254-11674 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442F-CU02 | T-00254-11675 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442G-CU01 | T-00254-11676 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442G-CU02 | T-00254-11677 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442H-CU01 | T-00254-11678 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FCU-8442H-CU02 | T-00254-11679 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0019-CJ01 | T-00254-11680 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0019-CU01 | T-00254-11681 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0019-CU02 | T-00254-11682 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0021-CJ01 | T-00254-11683 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0021-CU01 | T-00254-11684 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0021-CU02 | T-00254-11685 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0024-CJ01 | T-00254-11686 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0024-CU01 | T-00254-11687 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0024-CU02 | T-00254-11688 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0025-CJ01 | T-00254-11689 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0025-CU01 | T-00254-11690 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0025-CU02 | T-00254-11691 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0026-CJ01 | T-00254-11692 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0026-CU01 | T-00254-11693 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0026-CU02 | T-00254-11694 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0027-CJ01 | T-00254-11695 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0027-CU01 | T-00254-11696 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0027-CU02 | T-00254-11697 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0028-CJ01 | T-00254-11698 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0028-CU01 | T-00254-11699 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0028-CU02 | T-00254-11700 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0029-CJ01 | T-00254-11701 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0029-CU01 | T-00254-11702 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0029-CU02 | T-00254-11703 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0030-CJ01 | T-00254-11704 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0030-CU01 | T-00254-11705 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0030-CU02 | T-00254-11706 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0031-CJ01 | T-00254-11707 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0031-CU01 | T-00254-11708 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0031-CU02 | T-00254-11709 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0032-CJ01 | T-00254-11710 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0032-CU01 | T-00254-11711 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0032-CU02 | T-00254-11712 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0033-CJ01 | T-00254-11713 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0033-CU01 | T-00254-11714 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-FD-0033-CU02 | T-00254-11715 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-HE-8401A-CU01 | T-00254-11716 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-HE-8401B-CU01 | T-00254-11717 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8111A-CC01 | T-00254-11718 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8111B-CC01 | T-00254-11719 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8211A-CC01 | T-00254-11720 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8211B-CC01 | T-00254-11721 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8311A-A-CC01 | T-00254-11722 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8311A-B-CC01 | T-00254-11723 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8311B-A-CC01 | T-00254-11724 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8311B-B-CC01 | T-00254-11725 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8321A-A-CC01 | T-00254-11726 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8321A-B-CC01 | T-00254-11727 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8321B-A-CC01 | T-00254-11728 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8321B-B-CC01 | T-00254-11729 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8331A-A-CC01 | T-00254-11730 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8331A-B-CC01 | T-00254-11731 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8331B-A-CC01 | T-00254-11732 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8331B-B-CC01 | T-00254-11733 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8341A-A-CC01 | T-00254-11734 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8341A-B-CC01 | T-00254-11735 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8411A-CC01 | T-00254-11736 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8411B-CC01 | T-00254-11737 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8442A-CC01 | T-00254-11738 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8442B-CC01 | T-00254-11739 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8442C-CC01 | T-00254-11740 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8442D-CC01 | T-00254-11741 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8442E-CC01 | T-00254-11742 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8442F-CC01 | T-00254-11743 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8442G-CC01 | T-00254-11744 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8442H-CC01 | T-00254-11745 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8451A-CU01 | T-00254-11746 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8451A-CU02 | T-00254-11747 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8451B-CU01 | T-00254-11748 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8451B-CU02 | T-00254-11749 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PDIT-8207-CU01 | T-00254-11750 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PDIT-8407-CU01 | T-00254-11751 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PDIT-8408-CU01 | T-00254-11752 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PDIT-8409-CU01 | T-00254-11753 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PDIT-8411-CU01 | T-00254-11754 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PIT-8401-CU01 | T-00254-11755 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PIT-8402-CU01 | T-00254-11756 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PIT-8403-CU01 | T-00254-11757 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PIT-8404-CU01 | T-00254-11758 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TCV-8401-CU01 | T-00254-11759 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TCV-8401-CU02 | T-00254-11760 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TCV-8402-CU01 | T-00254-11761 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TCV-8402-CU02 | T-00254-11762 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8101-CU01 | T-00254-11763 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8201-CU01 | T-00254-11764 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8301-CU01 | T-00254-11765 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8302-CU01 | T-00254-11766 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8303-CU01 | T-00254-11767 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8304-CU01 | T-00254-11768 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8401-CU01 | T-00254-11769 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8402-CU01 | T-00254-11770 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8403-CU01 | T-00254-11771 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8404-CU01 | T-00254-11772 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8405-CU01 | T-00254-11773 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8406-CU01 | T-00254-11774 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8407-CU01 | T-00254-11775 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-TIT-8408-CU01 | T-00254-11776 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-UZ-84600-CU01 | T-00254-11777 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-UZ-84600-CU02 | T-00254-11778 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8401-CU01 | T-00254-11779 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8401-CU02 | T-00254-11780 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8402-CU01 | T-00254-11781 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8402-CU02 | T-00254-11782 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8403-CU01 | T-00254-11783 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8403-CU02 | T-00254-11784 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8404-CU01 | T-00254-11785 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8404-CU02 | T-00254-11786 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8413-CU01 | T-00254-11787 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8413-CU02 | T-00254-11788 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8414-CU01 | T-00254-11789 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-XV-8414-CU02 | T-00254-11790 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004A-CU01 | T-00254-11791 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004A-CU02 | T-00254-11792 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004A-CU03 | T-00254-11793 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004A-CU04 | T-00254-11794 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004B-CU01 | T-00254-11795 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004B-CU02 | T-00254-11796 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004B-CU03 | T-00254-11797 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004B-CU04 | T-00254-11798 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004C-CU01 | T-00254-11799 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004C-CU02 | T-00254-11800 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004C-CU03 | T-00254-11801 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004C-CU04 | T-00254-11802 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU01 | T-00254-11803 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU02 | T-00254-11804 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU03 | T-00254-11805 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU04 | T-00254-11806 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU05 | T-00254-11807 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU06 | T-00254-11808 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU07 | T-00254-11809 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU08 | T-00254-11810 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU09 | T-00254-11811 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU10 | T-00254-11812 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU11 | T-00254-11813 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU12 | T-00254-11814 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU13 | T-00254-11815 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU14 | T-00254-11816 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU15 | T-00254-11817 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU16 | T-00254-11818 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU17 | T-00254-11819 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU18 | T-00254-11820 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU19 | T-00254-11821 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU20 | T-00254-11822 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU21 | T-00254-11823 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU22 | T-00254-11824 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU23 | T-00254-11825 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU24 | T-00254-11826 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU25 | T-00254-11827 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU26 | T-00254-11828 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU27 | T-00254-11829 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU28 | T-00254-11830 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004-CU29 | T-00254-11831 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004D-CU01 | T-00254-11832 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IH-0004D-CU02 | T-00254-11833 | I | PS5-09-03 - HVAC for Generator Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1902-CJ01 | T-00254-12958 | I | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1703-CJ01 | T-00254-12959 | I | PS5-03-17 - FZ-17 - Power Generation Building - Generator Ro | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0001A-CC02 | T-00254-12960 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0001B-CC02 | T-00254-12961 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0001C-CC02 | T-00254-12962 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0001D-CC02 | T-00254-12963 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0001E-CC02 | T-00254-12964 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0001F-CC02 | T-00254-12965 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0001G-CC02 | T-00254-12966 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0003-CC03 | T-00254-12967 | I | PS5-60-22 - Power Gen Master UCP | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002A-CC01 | T-00254-12968 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002A-CC02 | T-00254-12969 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002A-CC03 | T-00254-12970 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002B-CC01 | T-00254-12971 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002B-CC02 | T-00254-12972 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002B-CC03 | T-00254-12973 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002C-CC01 | T-00254-12974 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002C-CC02 | T-00254-12975 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002C-CC03 | T-00254-12976 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002D-CC01 | T-00254-12977 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002D-CC02 | T-00254-12978 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002D-CC03 | T-00254-12979 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002E-CC01 | T-00254-12980 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002E-CC02 | T-00254-12981 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002E-CC03 | T-00254-12982 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002F-CC01 | T-00254-12983 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002F-CC02 | T-00254-12984 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002F-CC03 | T-00254-12985 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002G-CC01 | T-00254-12986 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002G-CC02 | T-00254-12987 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002G-CC03 | T-00254-12988 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001A-CC01 | T-00254-12989 | I | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001A-CC02 | T-00254-12990 | I | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001B-CC01 | T-00254-12991 | I | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001B-CC02 | T-00254-12992 | I | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001C-CC01 | T-00254-12993 | I | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001C-CC02 | T-00254-12994 | I | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001D-CC01 | T-00254-12995 | I | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001D-CC02 | T-00254-12996 | I | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001E-CC01 | T-00254-12997 | I | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001E-CC02 | T-00254-12998 | I | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001F-CC01 | T-00254-12999 | I | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001F-CC02 | T-00254-13000 | I | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001G-CC01 | T-00254-13001 | I | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001G-CC02 | T-00254-13002 | I | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0002-CC01 | T-00254-13003 | I | PS5-60-22 - Power Gen Master UCP | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0002-CC02 | T-00254-13004 | I | PS5-60-22 - Power Gen Master UCP | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0003-CC02 | T-00254-13005 | I | PS5-60-22 - Power Gen Master UCP | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0003-CC03 | T-00254-13006 | I | PS5-60-22 - Power Gen Master UCP | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8113A-CC01 | T-00254-13007 | I | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8113B-CC01 | T-00254-13008 | I | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8113C-CC01 | T-00254-13009 | I | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8113D-CC01 | T-00254-13010 | I | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8113E-CC01 | T-00254-13011 | I | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8113F-CC01 | T-00254-13012 | I | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8113G-CC01 | T-00254-13013 | I | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8114A-CC01 | T-00254-13014 | I | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8114B-CC01 | T-00254-13015 | I | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8114C-CC01 | T-00254-13016 | I | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8114D-CC01 | T-00254-13017 | I | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8114E-CC01 | T-00254-13018 | I | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8114F-CC01 | T-00254-13019 | I | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-PIT-8114G-CC01 | T-00254-13020 | I | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004A-CC10 | T-00254-13021 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-BI-0007-CC01 | T-00254-4222 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-BI-0008-CC01 | T-00254-4223 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-BI-0009-CC01 | T-00254-4224 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FCV-0003A-CC01 | T-00254-4235 | I | PS5-01-02 - Fire Water Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FCV-0003B-CC01 | T-00254-4236 | I | PS5-01-03 - Fire Water Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FCV-0004A-CC01 | T-00254-4237 | I | PS5-01-01 - Fire Water Jockey Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FCV-0004B-CC01 | T-00254-4238 | I | PS5-01-01 - Fire Water Jockey Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FIT-0003A-CJ01 | T-00254-4239 | I | PS5-01-02 - Fire Water Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FIT-0003B-CJ01 | T-00254-4240 | I | PS5-01-03 - Fire Water Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FIT-0004A-CJ01 | T-00254-4241 | I | PS5-01-01 - Fire Water Jockey Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FIT-0004B-CJ01 | T-00254-4242 | I | PS5-01-01 - Fire Water Jockey Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FXS-0003A-CJ01 | T-00254-4243 | I | PS5-01-02 - Fire Water Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FXS-0003B-CJ01 | T-00254-4244 | I | PS5-01-03 - Fire Water Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FXS-0004A-CJ01 | T-00254-4245 | I | PS5-01-01 - Fire Water Jockey Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FXS-0004B-CJ01 | T-00254-4246 | I | PS5-01-01 - Fire Water Jockey Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FY-0003A-CJ01 | T-00254-4247 | I | PS5-01-02 - Fire Water Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FY-0003B-CJ01 | T-00254-4248 | I | PS5-01-03 - Fire Water Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FY-0004A-CJ01 | T-00254-4249 | I | PS5-01-01 - Fire Water Jockey Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FY-0004B-CJ01 | T-00254-4250 | I | PS5-01-01 - Fire Water Jockey Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-HS-3108AB-CJ01 | T-00254-4251 | I | PS5-01-02 - Fire Water Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-HS-3108BB-CJ01 | T-00254-4252 | I | PS5-01-03 - Fire Water Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-LB-6101A-CC01 | T-00254-4264 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-LB-6102A-CC01 | T-00254-4265 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-LB-6103A-CC01 | T-00254-4266 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-LB-6104A-CC01 | T-00254-4267 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-LIT-4101A-CJ01 | T-00254-4268 | I | PS5-01-02 - Fire Water Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-LIT-4101B-CJ01 | T-00254-4269 | I | PS5-01-02 - Fire Water Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-NMR-61001-CJ01 | T-00254-4271 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-NMR-61002-CJ01 | T-00254-4272 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-NMR-61003-CJ01 | T-00254-4273 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-NMR-61004-CJ01 | T-00254-4274 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-NMRA-61001-CJ01 | T-00254-4275 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-NMRA-61002-CJ01 | T-00254-4276 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-NMRA-61003-CJ01 | T-00254-4277 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-NMRA-61004-CJ01 | T-00254-4278 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-PDIT-0011A-CJ01 | T-00254-4279 | I | PS5-01-01 - Fire Water Jockey Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PDIT-0011B-CJ01 | T-00254-4280 | I | PS5-01-01 - Fire Water Jockey Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PDIT-0012A-CJ01 | T-00254-4281 | I | PS5-01-02 - Fire Water Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PDIT-0012B-CJ01 | T-00254-4282 | I | PS5-01-03 - Fire Water Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PIT-0003AA-CJ01 | T-00254-4283 | I | PS5-01-02 - Fire Water Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PIT-0003BA-CJ01 | T-00254-4284 | I | PS5-01-03 - Fire Water Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PIT-0004AA-CJ01 | T-00254-4285 | I | PS5-01-01 - Fire Water Jockey Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PIT-0004BA-CJ01 | T-00254-4286 | I | PS5-01-01 - Fire Water Jockey Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PIT-0010-CJ01 | T-00254-4287 | I | PS5-01-07 - Fire Water Ring Main & Distribution | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-01-PIT-0013-CJ01 | T-00254-4288 | I | PS5-01-07 - Fire Water Ring Main & Distribution | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-PIT-8101A-CJ01 | T-00254-4293 | I | PS5-01-10 - Water Mist Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-PIT-8101B-CJ01 | T-00254-4294 | I | PS5-01-10 - Water Mist Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-PIT-8101C-CJ01 | T-00254-4295 | I | PS5-01-10 - Water Mist Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-PIT-8101D-CJ01 | T-00254-4296 | I | PS5-01-10 - Water Mist Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-PIT-8101E-CJ01 | T-00254-4297 | I | PS5-01-10 - Water Mist Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-PIT-8101F-CJ01 | T-00254-4298 | I | PS5-01-10 - Water Mist Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-PIT-8101G-CJ01 | T-00254-4299 | I | PS5-01-10 - Water Mist Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-PIT-8101H-CJ01 | T-00254-4300 | I | PS5-01-10 - Water Mist Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | No RFI Yet | - |  | Open + RFI Submitted
PS5-01-RAB-61001A-CJ01 | T-00254-4301 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61001B-CJ01 | T-00254-4302 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61002A-CJ01 | T-00254-4303 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61002B-CJ01 | T-00254-4304 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61003A-CJ01 | T-00254-4305 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61003B-CJ01 | T-00254-4306 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61004A-CJ01 | T-00254-4307 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-RAB-61004B-CJ01 | T-00254-4308 | I | PS5-01-11 - Inergen for Power Gen Building | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-SY-8101A-CJ01 | T-00254-4309 | I | PS5-01-10 - Water Mist Package | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-SY-8101B-CJ01 | T-00254-4310 | I | PS5-01-10 - Water Mist Package | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-SY-8101C-CJ01 | T-00254-4311 | I | PS5-01-10 - Water Mist Package | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-SY-8101D-CJ01 | T-00254-4312 | I | PS5-01-10 - Water Mist Package | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-SY-8101E-CJ01 | T-00254-4313 | I | PS5-01-10 - Water Mist Package | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-SY-8101F-CJ01 | T-00254-4314 | I | PS5-01-10 - Water Mist Package | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-SY-8101G-CJ01 | T-00254-4315 | I | PS5-01-10 - Water Mist Package | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-SY-8101H-CJ01 | T-00254-4316 | I | PS5-01-10 - Water Mist Package | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-0901-CC01 | T-00254-4343 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-0902-CC01 | T-00254-4344 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-0903-CC01 | T-00254-4345 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-0904-CC01 | T-00254-4346 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-0906-CC01 | T-00254-4347 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-0907-CC01 | T-00254-4348 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-0908-CC01 | T-00254-4349 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-0909-CC01 | T-00254-4350 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-1001-CC01 | T-00254-4351 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-1002-CC01 | T-00254-4352 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-1003-CC01 | T-00254-4353 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-1004-CC01 | T-00254-4354 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-1006-CC01 | T-00254-4355 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-1007-CC01 | T-00254-4356 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-1008-CC01 | T-00254-4357 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-1009-CC01 | T-00254-4358 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDIR-1101-CC01 | T-00254-4359 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1102-CC01 | T-00254-4360 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1103-CC01 | T-00254-4361 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1104-CC01 | T-00254-4362 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1106-CC01 | T-00254-4363 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1107-CC01 | T-00254-4364 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1108-CC01 | T-00254-4365 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1109-CC01 | T-00254-4366 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1201-CC01 | T-00254-4367 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1202-CC01 | T-00254-4368 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1203-CC01 | T-00254-4369 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-GDIR-1204-CC01 | T-00254-4370 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDLHP-0137-CJ01 | T-00254-4371 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDLHP-0142-CJ01 | T-00254-4372 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDLHP-0143-CJ01 | T-00254-4373 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDLHP-0144-CJ01 | T-00254-4374 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDLHP-0146-CJ01 | T-00254-4375 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-03-GDLHP-0147-CJ01 | T-00254-4376 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-03-GDLHP-0149-CJ01 | T-00254-4377 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-03-GDLHP-0150-CJ01 | T-00254-4378 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-03-GDLHP-0401-CJ01 | T-00254-4379 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-03-RDH-0302-CJ01 | T-00254-4393 | I | PS5-03-03 - FZ-03 - Buildings Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0303-CJ01 | T-00254-4394 | I | PS5-03-03 - FZ-03 - Buildings Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0601-CJ01 | T-00254-4395 | I | PS5-03-06 - FZ-06 - Transformer Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | - |  | Complete
PS5-03-RDH-0602-CJ01 | T-00254-4396 | I | PS5-03-06 - FZ-06 - Transformer Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | - |  | Complete
PS5-03-RDH-0603-CJ01 | T-00254-4397 | I | PS5-03-06 - FZ-06 - Transformer Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | - |  | Complete
PS5-03-RDH-0604-CJ01 | T-00254-4398 | I | PS5-03-06 - FZ-06 - Transformer Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | - |  | Complete
PS5-03-RDH-0605-CJ01 | T-00254-4399 | I | PS5-03-06 - FZ-06 - Transformer Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | - |  | Complete
PS5-03-RDH-0606-CJ01 | T-00254-4400 | I | PS5-03-06 - FZ-06 - Transformer Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | - |  | Complete
PS5-03-RDH-0607-CJ01 | T-00254-4401 | I | PS5-03-06 - FZ-06 - Transformer Area | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-03-RDH-0608-CJ01 | T-00254-4402 | I | PS5-03-06 - FZ-06 - Transformer Area | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-03-RDH-0609-CJ01 | T-00254-4403 | I | PS5-03-06 - FZ-06 - Transformer Area | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-03-RDH-0610-CJ01 | T-00254-4404 | I | PS5-03-06 - FZ-06 - Transformer Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0611-CJ01 | T-00254-4405 | I | PS5-03-06 - FZ-06 - Transformer Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0612-CJ01 | T-00254-4406 | I | PS5-03-06 - FZ-06 - Transformer Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0614-CJ01 | T-00254-4407 | I | PS5-03-06 - FZ-06 - Transformer Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-03-RDH-0615-CJ01 | T-00254-4408 | I | PS5-03-06 - FZ-06 - Transformer Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-03-RDH-0616-CJ01 | T-00254-4409 | I | PS5-03-06 - FZ-06 - Transformer Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-03-RDH-0617-CJ01 | T-00254-4410 | I | PS5-03-06 - FZ-06 - Transformer Area | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDH-0618-CJ01 | T-00254-4411 | I | PS5-03-06 - FZ-06 - Transformer Area | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDH-0620-CJ01 | T-00254-4412 | I | PS5-03-06 - FZ-06 - Transformer Area | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-03-RDH-0828-CJ01 | T-00254-4413 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0829-CJ01 | T-00254-4414 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0830-CJ01 | T-00254-4415 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-03-RDH-0831-CJ01 | T-00254-4416 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-03-RDH-0901-CJ01 | T-00254-4417 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0902-CJ01 | T-00254-4418 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0903-CJ01 | T-00254-4419 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0904-CJ01 | T-00254-4420 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0905-CJ01 | T-00254-4421 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0906-CJ01 | T-00254-4422 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0909-CJ01 | T-00254-4423 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0910-CJ01 | T-00254-4424 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0911-CJ01 | T-00254-4425 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-0912-CJ01 | T-00254-4426 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1001-CJ01 | T-00254-4427 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1002-CJ01 | T-00254-4428 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1003-CJ01 | T-00254-4429 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1004-CJ01 | T-00254-4430 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1005-CJ01 | T-00254-4431 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1006-CJ01 | T-00254-4432 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1009-CJ01 | T-00254-4433 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1010-CJ01 | T-00254-4434 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1011-CJ01 | T-00254-4435 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1012-CJ01 | T-00254-4436 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1101-CJ01 | T-00254-4437 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1102-CJ01 | T-00254-4438 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1103-CJ01 | T-00254-4439 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1104-CJ01 | T-00254-4440 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1105-CJ01 | T-00254-4441 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1106-CJ01 | T-00254-4442 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1109-CJ01 | T-00254-4443 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1110-CJ01 | T-00254-4444 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1111-CJ01 | T-00254-4445 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1112-CJ01 | T-00254-4446 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1201-CJ01 | T-00254-4447 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1202-CJ01 | T-00254-4448 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1203-CJ01 | T-00254-4449 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1204-CJ01 | T-00254-4450 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1205-CJ01 | T-00254-4451 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1302-CJ01 | T-00254-4452 | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1303-CJ01 | T-00254-4453 | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1304-CJ01 | T-00254-4454 | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1901-CJ01 | T-00254-4455 | I | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDH-1903-CJ01 | T-00254-4456 | I | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0104-CJ01 | T-00254-4457 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | - |  | Complete
PS5-03-RDIR-0105-CJ01 | T-00254-4458 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | - |  | Complete
PS5-03-RDIR-0106-CJ01 | T-00254-4459 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | - |  | Complete
PS5-03-RDIR-0107-CJ01 | T-00254-4460 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0108-CJ01 | T-00254-4461 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | - |  | Complete
PS5-03-RDIR-0109-CJ01 | T-00254-4462 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | - |  | Complete
PS5-03-RDIR-0110-CJ01 | T-00254-4463 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | - |  | Complete
PS5-03-RDIR-0111-CJ01 | T-00254-4464 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | - |  | Complete
PS5-03-RDIR-0112-CJ01 | T-00254-4465 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | - |  | Complete
PS5-03-RDIR-0113-CJ01 | T-00254-4466 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | - |  | Complete
PS5-03-RDIR-0114-CJ01 | T-00254-4467 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-03-RDIR-0115-CJ01 | T-00254-4468 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-03-RDIR-0116-CJ01 | T-00254-4469 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-03-RDIR-0117-CJ01 | T-00254-4470 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-03-RDIR-0118-CJ01 | T-00254-4471 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-03-RDIR-0121-CJ01 | T-00254-4472 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:2/2 |  | Complete
PS5-03-RDIR-0122-CJ01 | T-00254-4473 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:2/2 |  | Complete
PS5-03-RDIR-0123-CJ01 | T-00254-4474 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-03-RDIR-0124-CJ01 | T-00254-4475 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0125-CJ01 | T-00254-4476 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-03-RDIR-0126-CJ01 | T-00254-4477 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-03-RDIR-0127-CJ01 | T-00254-4478 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-03-RDIR-0128-CJ01 | T-00254-4479 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0129-CJ01 | T-00254-4480 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0130-CJ01 | T-00254-4481 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0131-CJ01 | T-00254-4482 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0132-CJ01 | T-00254-4483 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0133-CJ01 | T-00254-4484 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0137-CJ01 | T-00254-4485 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | B:0/1 | Yes | Closed + Accepted
PS5-03-RDIR-0138-CJ01 | T-00254-4486 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | - |  | Complete
PS5-03-RDIR-0141-CJ01 | T-00254-4487 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | - |  | Complete
PS5-03-RDIR-0142-CJ01 | T-00254-4488 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | B:0/1 | Yes | Closed + Accepted
PS5-03-RDIR-0403-CJ01 | T-00254-4489 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-03-RDIR-0404-CJ01 | T-00254-4490 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | - |  | Complete
PS5-03-RDIR-0405-CJ01 | T-00254-4491 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | - |  | Complete
PS5-03-RDIR-0406-CJ01 | T-00254-4492 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDIR-0409-CJ01 | T-00254-4493 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | - |  | Complete
PS5-03-RDIR-0411-CJ01 | T-00254-4494 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted | - |  | Complete
PS5-03-RDIR-0819-CJ01 | T-00254-4495 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-03-RDIR-0820-CJ01 | T-00254-4496 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-03-RDIR-0832-CJ01 | T-00254-4497 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-03-RDIR-0833-CJ01 | T-00254-4498 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1401-CJ01 | T-00254-4499 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1402-CJ01 | T-00254-4500 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1403-CJ01 | T-00254-4501 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1404-CJ01 | T-00254-4502 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1405-CJ01 | T-00254-4503 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1406-CJ01 | T-00254-4504 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1407-CJ01 | T-00254-4505 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1408-CJ01 | T-00254-4506 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1501-CJ01 | T-00254-4507 | I | PS5-03-15 - FZ-15 - Power Generation Building - Generator Ro | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1502-CJ01 | T-00254-4508 | I | PS5-03-15 - FZ-15 - Power Generation Building - Generator Ro | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1503-CJ01 | T-00254-4509 | I | PS5-03-15 - FZ-15 - Power Generation Building - Generator Ro | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1601-CJ01 | T-00254-4510 | I | PS5-03-16 - FZ-16 - Power Generation Building - Generator Ro | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1602-CJ01 | T-00254-4511 | I | PS5-03-16 - FZ-16 - Power Generation Building - Generator Ro | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1603-CJ01 | T-00254-4512 | I | PS5-03-16 - FZ-16 - Power Generation Building - Generator Ro | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1701-CJ01 | T-00254-4513 | I | PS5-03-17 - FZ-17 - Power Generation Building - Generator Ro | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1702-CJ01 | T-00254-4514 | I | PS5-03-17 - FZ-17 - Power Generation Building - Generator Ro | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1801-CJ01 | T-00254-4515 | I | PS5-03-18 - FZ-18 - Power Generation Building - Generator Ro | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1802-CJ01 | T-00254-4516 | I | PS5-03-18 - FZ-18 - Power Generation Building - Generator Ro | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-1803-CJ01 | T-00254-4517 | I | PS5-03-18 - FZ-18 - Power Generation Building - Generator Ro | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-2101-CJ01 | T-00254-4518 | I | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-2102-CJ01 | T-00254-4519 | I | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-2103-CJ01 | T-00254-4520 | I | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-G101A-CJ01 | T-00254-4521 | I | PS5-03-22 - FZ-G1 - Guard House | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDOS-G101B-CJ01 | T-00254-4522 | I | PS5-03-22 - FZ-G1 - Guard House | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-0701-CJ01 | T-00254-4523 | I | PS5-03-07 - FZ-07 - Pretreatment Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-0702-CJ01 | T-00254-4524 | I | PS5-03-07 - FZ-07 - Pretreatment Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-0703-CJ01 | T-00254-4525 | I | PS5-03-07 - FZ-07 - Pretreatment Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-0704-CJ01 | T-00254-4526 | I | PS5-03-07 - FZ-07 - Pretreatment Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-0705-CJ01 | T-00254-4527 | I | PS5-03-07 - FZ-07 - Pretreatment Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-0907-CJ01 | T-00254-4528 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-0908-CJ01 | T-00254-4529 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-1007-CJ01 | T-00254-4530 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-1008-CJ01 | T-00254-4531 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-1107-CJ01 | T-00254-4532 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-1108-CJ01 | T-00254-4533 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-1207-CJ01 | T-00254-4534 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RDUIR-1208-CJ01 | T-00254-4535 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0101-CJ01 | T-00254-4536 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-03-RMAC-0102-CJ01 | T-00254-4537 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-03-RMAC-0103-CJ01 | T-00254-4538 | I | PS5-03-01 - FZ-01 - Process Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-03-RMAC-0301-CJ01 | T-00254-4540 | I | PS5-03-03 - FZ-03 - Buildings Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0304-CJ01 | T-00254-4541 | I | PS5-03-03 - FZ-03 - Buildings Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0401-CJ01 | T-00254-4542 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-03-RMAC-0402-CJ01 | T-00254-4543 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-03-RMAC-0613-CJ01 | T-00254-4544 | I | PS5-03-06 - FZ-06 - Transformer Area | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-03-RMAC-0706-CJ01 | T-00254-4545 | I | PS5-03-07 - FZ-07 - Pretreatment Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0707-CJ01 | T-00254-4546 | I | PS5-03-07 - FZ-07 - Pretreatment Area | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0825-CJ01 | T-00254-4548 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0827-CJ01 | T-00254-4549 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-0834-CJ01 | T-00254-4550 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-1301-CJ01 | T-00254-4551 | I | PS5-03-13 - FZ-13 - Power Generation Building - Instrument A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-1410-CJ01 | T-00254-4552 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-RMAC-1411-CJ01 | T-00254-4553 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-SEA-0001-CC01 | T-00254-4554 | I | PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-05-BI-0002-CC01 | T-00254-4563 | I | PS5-05-01 - Emergency Diesel Generator Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-05-BI-0002-CC02 | T-00254-4564 | I | PS5-05-01 - Emergency Diesel Generator Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-05-BI-0002-CC03 | T-00254-4565 | I | PS5-05-01 - Emergency Diesel Generator Package | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-05-BI-0002-CC04 | T-00254-4566 | I | PS5-05-01 - Emergency Diesel Generator Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-05-BI-0002-CC05 | T-00254-4567 | I | PS5-05-01 - Emergency Diesel Generator Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-05-BI-0002-CC06 | T-00254-4568 | I | PS5-05-01 - Emergency Diesel Generator Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-05-BI-0002-CJ01 | T-00254-4571 | I | PS5-05-01 - Emergency Diesel Generator Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-05-BI-0002-CJ02 | T-00254-4572 | I | PS5-05-01 - Emergency Diesel Generator Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-05-BI-0002-CJ03 | T-00254-4573 | I | PS5-05-01 - Emergency Diesel Generator Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-05-GC-8100-CC01 | T-00254-4574 | I | PS5-05-01 - Emergency Diesel Generator Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-05-IE-8101-CC01 | T-00254-4577 | I | PS5-05-01 - Emergency Diesel Generator Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-05-IG-0009-CC01 | T-00254-4578 | I | PS5-05-01 - Emergency Diesel Generator Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-05-IG-0009-CC02 | T-00254-4579 | I | PS5-05-01 - Emergency Diesel Generator Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-05-IG-0009-CJ01 | T-00254-4580 | I | PS5-05-01 - Emergency Diesel Generator Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-05-LIT-4101-CJ01 | T-00254-4581 | I | PS5-05-01 - Emergency Diesel Generator Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-05-UH-8100-CC01 | T-00254-4582 | I | PS5-05-01 - Emergency Diesel Generator Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-05-UH-8100-CC02 | T-00254-4583 | I | PS5-05-01 - Emergency Diesel Generator Package | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-1802A-CC01 | T-00254-4623 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-1802B-CC01 | T-00254-4625 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-1802C-CC01 | T-00254-4627 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-ESDV-0021-CC01 | T-00254-4654 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-ESDV-0021-CC02 | T-00254-4655 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-ESDV-0021-CC03 | T-00254-4656 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-ESDV-0023-CC01 | T-00254-4657 | I | PS5-25-07 - Export Pipeline Pig Launcher | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-ESDV-0023-CC02 | T-00254-4658 | I | PS5-25-07 - Export Pipeline Pig Launcher | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-ESDV-0023-CC03 | T-00254-4659 | I | PS5-25-07 - Export Pipeline Pig Launcher | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-ESY-0021A-CJ01 | T-00254-4660 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-ESY-0021B-CJ01 | T-00254-4661 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-ESY-0023B-CJ01 | T-00254-4662 | I | PS5-25-07 - Export Pipeline Pig Launcher | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-FCV-0003A-CC01 | T-00254-4663 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FCV-0003B-CC01 | T-00254-4664 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FCV-0003C-CC01 | T-00254-4665 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FCV-0004-CC01 | T-00254-4666 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FIT-0001-CJ01 | T-00254-4667 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-25-FIT-0003A-CJ01 | T-00254-4668 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-FIT-0003B-CJ01 | T-00254-4669 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-FIT-0003C-CJ01 | T-00254-4670 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FIT-0004-CJ01 | T-00254-4671 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-FXS-0003A-CJ01 | T-00254-4672 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FXS-0003B-CJ01 | T-00254-4673 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FXS-0003C-CJ01 | T-00254-4674 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FXS-0004-CJ01 | T-00254-4675 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FY-0003A-CJ01 | T-00254-4676 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-FY-0003B-CJ01 | T-00254-4677 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-25-FY-0003C-CJ01 | T-00254-4678 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FY-0004-CJ01 | T-00254-4679 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-HS-8101A-CJ01 | T-00254-4680 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-HS-8101B-CJ01 | T-00254-4681 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-HS-8101C-CJ01 | T-00254-4682 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-HS-8102A-CJ01 | T-00254-4683 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-HS-8102B-CJ01 | T-00254-4684 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-HS-8102C-CJ01 | T-00254-4685 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-MOV-0001-CC01 | T-00254-4686 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MOV-0002-CC01 | T-00254-4687 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-MOV-0003-CC01 | T-00254-4688 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-MOV-0008-CC01 | T-00254-4689 | I | PS5-25-07 - Export Pipeline Pig Launcher | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MOV-0011-CC01 | T-00254-4690 | I | PS5-25-07 - Export Pipeline Pig Launcher | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-MOV-0012-CC01 | T-00254-4691 | I | PS5-25-07 - Export Pipeline Pig Launcher | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-MOV-0025-CC01 | T-00254-4692 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MOV-0026-CC01 | T-00254-4693 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-MOV-0026-CC02 | T-00254-4694 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-MOV-0027-CC01 | T-00254-4695 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-MOV-0027-CC02 | T-00254-4696 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-25-MOV-0028-CC01 | T-00254-4697 | I | PS5-25-07 - Export Pipeline Pig Launcher | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MXS-0001-CJ01 | T-00254-4698 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MXS-0008-CJ01 | T-00254-4699 | I | PS5-25-07 - Export Pipeline Pig Launcher | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MXS-0025-CJ01 | T-00254-4700 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-MXS-0028-CJ01 | T-00254-4701 | I | PS5-25-07 - Export Pipeline Pig Launcher | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PDIT-0034A-CJ01 | T-00254-4708 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PDIT-0034B-CJ01 | T-00254-4709 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-PDIT-0034C-CJ01 | T-00254-4710 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PDIT-0050-CJ01 | T-00254-4711 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PI-1102B-CJ01 | T-00254-4712 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-25-PI-1202B-CJ01 | T-00254-4713 | I | PS5-25-07 - Export Pipeline Pig Launcher | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-25-PIT-0001-CJ01 | T-00254-4714 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-PIT-0003AA-CJ01 | T-00254-4715 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-PIT-0003BA-CJ01 | T-00254-4716 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-PIT-0003CA-CJ01 | T-00254-4717 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0004AA-CJ01 | T-00254-4718 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0004A-CJ01 | T-00254-4719 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0004B-CJ01 | T-00254-4720 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0004C-CJ01 | T-00254-4721 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0005A-CJ01 | T-00254-4722 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-25-PIT-0005B-CJ01 | T-00254-4723 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-PIT-0005C-CJ01 | T-00254-4724 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0007A-CJ01 | T-00254-4725 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-PIT-0007B-CJ01 | T-00254-4726 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-PIT-0007C-CJ01 | T-00254-4727 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0008A-CJ01 | T-00254-4728 | I | PS5-25-07 - Export Pipeline Pig Launcher | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-PIT-0008B-CJ01 | T-00254-4729 | I | PS5-25-07 - Export Pipeline Pig Launcher | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-PIT-0008C-CJ01 | T-00254-4730 | I | PS5-25-07 - Export Pipeline Pig Launcher | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-PIT-0013-CJ01 | T-00254-4731 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-PIT-0018-CJ01 | T-00254-4732 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-PIT-0022-CJ01 | T-00254-4733 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-PIT-0035A-CJ01 | T-00254-4734 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0035B-CJ01 | T-00254-4735 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0035C-CJ01 | T-00254-4736 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0036A-CJ01 | T-00254-4737 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0036B-CJ01 | T-00254-4738 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0036C-CJ01 | T-00254-4739 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0046-CJ01 | T-00254-4740 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0053-CJ01 | T-00254-4742 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-PIT-0054A-CJ01 | T-00254-4743 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0054B-CJ01 | T-00254-4744 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0054C-CJ01 | T-00254-4745 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PIT-0070-CJ01 | T-00254-4746 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-25-PIT-1102-CJ01 | T-00254-4750 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-25-PIT-1202-CJ01 | T-00254-4751 | I | PS5-25-07 - Export Pipeline Pig Launcher | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-25-SDV-0022-CC01 | T-00254-4752 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-SDV-0022-CC02 | T-00254-4753 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SDV-0035A-CC01 | T-00254-4754 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-SDV-0035B-CC01 | T-00254-4755 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-SDV-0035C-CC01 | T-00254-4756 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SDV-0036A-CC01 | T-00254-4757 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-SDV-0036B-CC01 | T-00254-4758 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SDV-0036C-CC01 | T-00254-4759 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SDV-0046-CC01 | T-00254-4760 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-SDV-0054A-CC01 | T-00254-4763 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-SDV-0054B-CC01 | T-00254-4764 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-SDV-0054C-CC01 | T-00254-4765 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SXS-0022-CJ01 | T-00254-4767 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SXS-0035A-CJ01 | T-00254-4768 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-SXS-0035B-CJ01 | T-00254-4769 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-SXS-0035C-CJ01 | T-00254-4770 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-SXS-0036A-CJ01 | T-00254-4771 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-SXS-0036B-CJ01 | T-00254-4772 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-SXS-0036C-CJ01 | T-00254-4773 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-SXS-0046-CJ01 | T-00254-4774 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-25-SXS-0054A-CJ01 | T-00254-4776 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SXS-0054B-CJ01 | T-00254-4777 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SXS-0054C-CJ01 | T-00254-4778 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0022-CJ01 | T-00254-4779 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-SY-0035AA-CJ01 | T-00254-4780 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-SY-0035AB-CJ01 | T-00254-4781 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0035BA-CJ01 | T-00254-4782 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-SY-0035BB-CJ01 | T-00254-4783 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0035CA-CJ01 | T-00254-4784 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0035CB-CJ01 | T-00254-4785 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0036AA-CJ01 | T-00254-4786 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-SY-0036AB-CJ01 | T-00254-4787 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0036BA-CJ01 | T-00254-4788 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0036BB-CJ01 | T-00254-4789 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0036CA-CJ01 | T-00254-4790 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0036CB-CJ01 | T-00254-4791 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0046A-CJ01 | T-00254-4792 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-SY-0046B-CJ01 | T-00254-4793 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-SY-0052B-CJ01 | T-00254-4795 | I | PS5-25-07 - Export Pipeline Pig Launcher | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0054AA-CJ01 | T-00254-4796 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-SY-0054AB-CJ01 | T-00254-4797 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-SY-0054BA-CJ01 | T-00254-4798 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0054BB-CJ01 | T-00254-4799 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0054CA-CJ01 | T-00254-4800 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-SY-0054CB-CJ01 | T-00254-4801 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TIT-0001-CJ01 | T-00254-4802 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-25-TIT-0002A-CJ01 | T-00254-4803 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TIT-0002B-CJ01 | T-00254-4804 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TIT-0002C-CJ01 | T-00254-4805 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-25-TIT-0003A-CJ01 | T-00254-4806 | I | PS5-25-02 - Crude Oil Export Pump A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-TIT-0003B-CJ01 | T-00254-4807 | I | PS5-25-03 - Crude Oil Export Pump B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-TIT-0003C-CJ01 | T-00254-4808 | I | PS5-25-04 - Crude Oil Export Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TIT-0004-CJ01 | T-00254-4809 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-25-TIT-1101-CJ01 | T-00254-4810 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-25-TIT-1201-CJ01 | T-00254-4811 | I | PS5-25-07 - Export Pipeline Pig Launcher | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-25-XV-0053-CC01 | T-00254-4812 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-XV-0053-CC02 | T-00254-4813 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-XV-0070-CC01 | T-00254-4814 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-XXS-0053-CJ01 | T-00254-4815 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-XXS-0070-CJ01 | T-00254-4816 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-XY-0053-CJ01 | T-00254-4817 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-XY-0070-CJ01 | T-00254-4818 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-25-ZIT-0001-CC01 | T-00254-4819 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-ZIT-0002-CC01 | T-00254-4820 | I | PS5-25-07 - Export Pipeline Pig Launcher | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-ZS-1101-CJ01 | T-00254-4821 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-ZS-1201-CJ01 | T-00254-4822 | I | PS5-25-07 - Export Pipeline Pig Launcher | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-HXA-1402-CJ01 | T-00254-4830 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-HY-3901A-CJ01 | T-00254-4831 | I | PS5-28-17 - Reinjection Pump | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-28-HY-3901B-CJ01 | T-00254-4832 | I | PS5-28-17 - Reinjection Pump | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-28-LI-1101B-CJ01 | T-00254-4835 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-28-LI-1101C-CJ01 | T-00254-4836 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-28-LI-1402B-CJ01 | T-00254-4837 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-28-LIT-0002-CJ01 | T-00254-4838 | I | PS5-28-08 - Open Drain Sump and Pumps | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-28-LIT-0008-CJ01 | T-00254-4839 | I | PS5-28-08 - Open Drain Sump and Pumps | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-28-LIT-1101-CJ01 | T-00254-4840 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-28-LIT-1102-CJ01 | T-00254-4841 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-28-LIT-1201-CJ01 | T-00254-4842 | I | PS5-28-06 - Relief Drum and Pump | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-LIT-1202-CJ01 | T-00254-4843 | I | PS5-28-06 - Relief Drum and Pump | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-28-LIT-1301A-CJ01 | T-00254-4844 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-28-LIT-1301B-CJ01 | T-00254-4845 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-28-LIT-1301C-CJ01 | T-00254-4846 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-LIT-1401-CJ01 | T-00254-4847 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-28-LIT-1402-CJ01 | T-00254-4848 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-28-PIT-0015-CJ01 | T-00254-4849 | I | PS5-28-17 - Reinjection Pump | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-28-PIT-0033-CJ01 | T-00254-4850 | I | PS5-28-06 - Relief Drum and Pump | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PIT-0041-CJ01 | T-00254-4851 | I | PS5-28-17 - Reinjection Pump | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-28-PIT-0045-CJ01 | T-00254-4852 | I | PS5-28-17 - Reinjection Pump | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-28-PIT-0053A-CJ01 | T-00254-4853 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PIT-0053B-CJ01 | T-00254-4854 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PIT-0053C-CJ01 | T-00254-4855 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-PIT-3901A-CJ01 | T-00254-4856 | I | PS5-28-17 - Reinjection Pump | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-28-PIT-3901B-CJ01 | T-00254-4857 | I | PS5-28-17 - Reinjection Pump | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-28-SDV-0045-CC01 | T-00254-4858 | I | PS5-28-17 - Reinjection Pump | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SDV-0045-CC02 | T-00254-4859 | I | PS5-28-17 - Reinjection Pump | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SDV-0053A-CC01 | T-00254-4860 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-28-SDV-0053A-CC02 | T-00254-4861 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SDV-0053B-CC01 | T-00254-4862 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SDV-0053B-CC02 | T-00254-4863 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SDV-0053C-CC01 | T-00254-4864 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SDV-0053C-CC02 | T-00254-4865 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SXS-0045-CJ01 | T-00254-4866 | I | PS5-28-17 - Reinjection Pump | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SXS-0053A-CJ01 | T-00254-4867 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-28-SXS-0053B-CJ01 | T-00254-4868 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-28-SXS-0053C-CJ01 | T-00254-4869 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SY-0045A-CJ01 | T-00254-4870 | I | PS5-28-17 - Reinjection Pump | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-28-SY-0045B-CJ01 | T-00254-4871 | I | PS5-28-17 - Reinjection Pump | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-28-SY-0053AA-CJ01 | T-00254-4872 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-28-SY-0053AB-CJ01 | T-00254-4873 | I | PS5-28-13 - Seal Oil Drain Drum & Pump A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SY-0053BA-CJ01 | T-00254-4874 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-28-SY-0053BB-CJ01 | T-00254-4875 | I | PS5-28-14 - Seal Oil Drain Drum & Pump B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-28-SY-0053CA-CJ01 | T-00254-4876 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-SY-0053CB-CJ01 | T-00254-4877 | I | PS5-28-15 - Seal Oil Drain Drum & Pump C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-TIT-1104-CJ01 | T-00254-4878 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-28-TIT-1105-CJ01 | T-00254-4879 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-28-TIT-1201-CJ01 | T-00254-4880 | I | PS5-28-06 - Relief Drum and Pump | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-TIT-1401-CJ01 | T-00254-4881 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-28-TIT-1402-CJ01 | T-00254-4882 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-28-TIT-2101-CJ01 | T-00254-4883 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-28-TIT-2201-CJ01 | T-00254-4884 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-50-FIT-0001-CJ01 | T-00254-4886 | I | PS5-50-03 - Water Pre-Treatment Package | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-53-LIT-4101-CJ01 | T-00254-4897 | I | PS5-53-01 - Utility Water / Storage Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-LIT-4102-CJ01 | T-00254-4898 | I | PS5-53-01 - Utility Water / Storage Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-PIT-0005-CJ01 | T-00254-4899 | I | PS5-53-02 - Water Distribution Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BE-0001-CC01 | T-00254-4900 | I | PS5-60-27 - Compressed Air Starting Skid | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BE-0002-CC01 | T-00254-4901 | I | PS5-60-26 - Instrument Air Compressor Skid | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BE-0004A-CC01 | T-00254-4902 | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BE-0004B-CC01 | T-00254-4903 | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BE-0004C-CC01 | T-00254-4904 | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BE-0004D-CC01 | T-00254-4905 | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BE-0004E-CC01 | T-00254-4906 | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BE-0004F-CC01 | T-00254-4907 | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BE-0004G-CC01 | T-00254-4908 | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0001A-CC01 | T-00254-4909 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0001A-CC03 | T-00254-4910 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0001B-CC01 | T-00254-4911 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0001B-CC03 | T-00254-4912 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0001C-CC01 | T-00254-4913 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0001C-CC03 | T-00254-4914 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0001D-CC01 | T-00254-4915 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0001D-CC03 | T-00254-4916 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0001E-CC01 | T-00254-4917 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0001E-CC03 | T-00254-4918 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0001F-CC01 | T-00254-4919 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0001F-CC03 | T-00254-4920 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0001G-CC01 | T-00254-4921 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0001G-CC03 | T-00254-4922 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0002-CC01 | T-00254-4923 | I | PS5-60-22 - Power Gen Master UCP | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0002-CC02 | T-00254-4924 | I | PS5-60-22 - Power Gen Master UCP | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0002-CC03 | T-00254-4925 | I | PS5-60-22 - Power Gen Master UCP | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0002-CC04 | T-00254-4926 | I | PS5-60-22 - Power Gen Master UCP | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0003-CC01 | T-00254-4927 | I | PS5-60-22 - Power Gen Master UCP | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0003-CC02 | T-00254-4928 | I | PS5-60-22 - Power Gen Master UCP | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0004A-CCO1 | T-00254-4929 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0004B-CCO1 | T-00254-4930 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0004C-CCO1 | T-00254-4931 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0004D-CCO1 | T-00254-4932 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0004E-CCO1 | T-00254-4933 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0004F-CCO1 | T-00254-4934 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0004G-CCO1 | T-00254-4935 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005A-CC01 | T-00254-4936 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005A-CC02 | T-00254-4937 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005B-CC01 | T-00254-4938 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005B-CC02 | T-00254-4939 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005C-CC01 | T-00254-4940 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005C-CC02 | T-00254-4941 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005D-CC01 | T-00254-4942 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005D-CC02 | T-00254-4943 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005E-CC01 | T-00254-4944 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005E-CC02 | T-00254-4945 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005F-CC01 | T-00254-4946 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005F-CC02 | T-00254-4947 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005G-CC01 | T-00254-4948 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0005G-CC02 | T-00254-4949 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006A-CC01 | T-00254-4950 | I | PS5-60-02 - Power Gen Package A (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0006A-CC02 | T-00254-4951 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006A-CC03 | T-00254-4952 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006A-CC04 | T-00254-4953 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006A-CC05 | T-00254-4954 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0006A-CC06 | T-00254-4955 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006B-CC01 | T-00254-4956 | I | PS5-60-05 - Power Gen Package B (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0006B-CC02 | T-00254-4957 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006B-CC03 | T-00254-4958 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006B-CC04 | T-00254-4959 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006B-CC05 | T-00254-4960 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0006B-CC06 | T-00254-4961 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006C-CC01 | T-00254-4962 | I | PS5-60-08 - Power Gen Package C (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0006C-CC02 | T-00254-4963 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006C-CC03 | T-00254-4964 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006C-CC04 | T-00254-4965 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006C-CC05 | T-00254-4966 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0006C-CC06 | T-00254-4967 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006D-CC01 | T-00254-4968 | I | PS5-60-11 - Power Gen Package D (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0006D-CC02 | T-00254-4969 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006D-CC03 | T-00254-4970 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006D-CC04 | T-00254-4971 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006D-CC05 | T-00254-4972 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0006D-CC06 | T-00254-4973 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CC01 | T-00254-4974 | I | PS5-60-14 - Power Gen Package E (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0006E-CC02 | T-00254-4975 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CC03 | T-00254-4976 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CC04 | T-00254-4977 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006E-CC05 | T-00254-4978 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0006E-CC06 | T-00254-4979 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CC01 | T-00254-4980 | I | PS5-60-17 - Power Gen Package F (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0006F-CC02 | T-00254-4981 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CC03 | T-00254-4982 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CC04 | T-00254-4983 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006F-CC05 | T-00254-4984 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0006F-CC06 | T-00254-4985 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CC01 | T-00254-4986 | I | PS5-60-20 - Power Gen Package G (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0006G-CC02 | T-00254-4987 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CC03 | T-00254-4988 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CC04 | T-00254-4989 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0006G-CC05 | T-00254-4990 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0006G-CC06 | T-00254-4991 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0008A-CC01 | T-00254-4992 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0008A-CC02 | T-00254-4993 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0008B-CC01 | T-00254-4994 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0008B-CC02 | T-00254-4995 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0009A-CC01 | T-00254-4996 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0009A-CC02 | T-00254-4997 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0009B-CC01 | T-00254-4998 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0009B-CC02 | T-00254-4999 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0010A-CC01 | T-00254-5000 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0010A-CC02 | T-00254-5001 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0010B-CC01 | T-00254-5002 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0010B-CC02 | T-00254-5003 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0011A-CC01 | T-00254-5004 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0011A-CC02 | T-00254-5005 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0011B-CC01 | T-00254-5006 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0011B-CC02 | T-00254-5007 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0012A-CC01 | T-00254-5008 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0012A-CC02 | T-00254-5009 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0012B-CC01 | T-00254-5010 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0012B-CC02 | T-00254-5011 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0013A-CC01 | T-00254-5012 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0013A-CC02 | T-00254-5013 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0013B-CC01 | T-00254-5014 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0013B-CC02 | T-00254-5015 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0014A-CC01 | T-00254-5016 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0014A-CC02 | T-00254-5017 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0014B-CC01 | T-00254-5018 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0014B-CC02 | T-00254-5019 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016A-CC01 | T-00254-5020 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0016A-CC02 | T-00254-5021 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016A-CC03 | T-00254-5022 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-BI-0016A-CCO4 | T-00254-5023 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016B-CC01 | T-00254-5024 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0016B-CC02 | T-00254-5025 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0016B-CC03 | T-00254-5026 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-BI-0016B-CCO4 | T-00254-5027 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016C-CC01 | T-00254-5028 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0016C-CC02 | T-00254-5029 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016C-CC03 | T-00254-5030 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-BI-0016C-CCO4 | T-00254-5031 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016D-CC01 | T-00254-5032 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0016D-CC02 | T-00254-5033 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016D-CC03 | T-00254-5034 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-BI-0016D-CCO4 | T-00254-5035 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016E-CC01 | T-00254-5036 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0016E-CC02 | T-00254-5037 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016E-CC03 | T-00254-5038 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-BI-0016E-CCO4 | T-00254-5039 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016F-CC01 | T-00254-5040 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0016F-CC02 | T-00254-5041 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016F-CC03 | T-00254-5042 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0016F-CCO4 | T-00254-5043 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016G-CC01 | T-00254-5044 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-BI-0016G-CC02 | T-00254-5045 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0016G-CC03 | T-00254-5046 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-BI-0016G-CCO4 | T-00254-5047 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0017A-CC02 | T-00254-5048 | I | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0017B-CC02 | T-00254-5049 | I | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-BI-0017C-CC02 | T-00254-5050 | I | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0017D-CC02 | T-00254-5051 | I | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0017E-CC02 | T-00254-5052 | I | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0017F-CC02 | T-00254-5053 | I | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0017G-CC02 | T-00254-5054 | I | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0019A-CC01 | T-00254-5055 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019A-CC02 | T-00254-5056 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019B-CC01 | T-00254-5057 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019B-CC02 | T-00254-5058 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019C-CC01 | T-00254-5059 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019C-CC02 | T-00254-5060 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019D-CC01 | T-00254-5061 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019D-CC02 | T-00254-5062 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019E-CC01 | T-00254-5063 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019E-CC02 | T-00254-5064 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019F-CC01 | T-00254-5065 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0019F-CC02 | T-00254-5066 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-BI-0019G-CC01 | T-00254-5067 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-BI-0019G-CC02 | T-00254-5068 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0002B-CC05 | T-00254-5069 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0002C-CC05 | T-00254-5070 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0002D-CC05 | T-00254-5071 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0002E-CC05 | T-00254-5072 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0002F-CC05 | T-00254-5073 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0002G-CC05 | T-00254-5074 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0003A-CC01 | T-00254-5075 | I | PS5-60-02 - Power Gen Package A (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003A-CC02 | T-00254-5076 | I | PS5-60-02 - Power Gen Package A (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003A-CC03 | T-00254-5077 | I | PS5-60-02 - Power Gen Package A (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003A-CC04 | T-00254-5078 | I | PS5-60-02 - Power Gen Package A (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003A-CC05 | T-00254-5079 | I | PS5-60-02 - Power Gen Package A (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003A-CC06 | T-00254-5080 | I | PS5-60-02 - Power Gen Package A (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003A-CC07 | T-00254-5081 | I | PS5-60-02 - Power Gen Package A (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003A-CC08 | T-00254-5082 | I | PS5-60-02 - Power Gen Package A (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003A-CC09 | T-00254-5083 | I | PS5-60-02 - Power Gen Package A (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003A-CC10 | T-00254-5084 | I | PS5-60-02 - Power Gen Package A (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003A-CC11 | T-00254-5085 | I | PS5-60-02 - Power Gen Package A (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003A-CC15 | T-00254-5086 | I | PS5-60-02 - Power Gen Package A (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0003A-CC16 | T-00254-5087 | I | PS5-60-02 - Power Gen Package A (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003A-CC17 | T-00254-5088 | I | PS5-60-02 - Power Gen Package A (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003A-CC25 | T-00254-5093 | I | PS5-60-02 - Power Gen Package A (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0003A-CC26 | T-00254-5094 | I | PS5-60-02 - Power Gen Package A (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0003B-CC01 | T-00254-5095 | I | PS5-60-05 - Power Gen Package B (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003B-CC02 | T-00254-5096 | I | PS5-60-05 - Power Gen Package B (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003B-CC03 | T-00254-5097 | I | PS5-60-05 - Power Gen Package B (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003B-CC04 | T-00254-5098 | I | PS5-60-05 - Power Gen Package B (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B-CC05 | T-00254-5099 | I | PS5-60-05 - Power Gen Package B (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B-CC06 | T-00254-5100 | I | PS5-60-05 - Power Gen Package B (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B-CC07 | T-00254-5101 | I | PS5-60-05 - Power Gen Package B (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B-CC08 | T-00254-5102 | I | PS5-60-05 - Power Gen Package B (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003B-CC09 | T-00254-5103 | I | PS5-60-05 - Power Gen Package B (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003B-CC10 | T-00254-5104 | I | PS5-60-05 - Power Gen Package B (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003B-CC11 | T-00254-5105 | I | PS5-60-05 - Power Gen Package B (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IE-0003B-CC15 | T-00254-5106 | I | PS5-60-05 - Power Gen Package B (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0003B-CC16 | T-00254-5107 | I | PS5-60-05 - Power Gen Package B (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003B-CC17 | T-00254-5108 | I | PS5-60-05 - Power Gen Package B (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003B-CC25 | T-00254-5113 | I | PS5-60-05 - Power Gen Package B (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0003B-CC26 | T-00254-5114 | I | PS5-60-05 - Power Gen Package B (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0003C-CC01 | T-00254-5115 | I | PS5-60-08 - Power Gen Package C (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CC02 | T-00254-5116 | I | PS5-60-08 - Power Gen Package C (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CC03 | T-00254-5117 | I | PS5-60-08 - Power Gen Package C (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CC04 | T-00254-5118 | I | PS5-60-08 - Power Gen Package C (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CC05 | T-00254-5119 | I | PS5-60-08 - Power Gen Package C (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CC06 | T-00254-5120 | I | PS5-60-08 - Power Gen Package C (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CC07 | T-00254-5121 | I | PS5-60-08 - Power Gen Package C (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CC08 | T-00254-5122 | I | PS5-60-08 - Power Gen Package C (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003C-CC09 | T-00254-5123 | I | PS5-60-08 - Power Gen Package C (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003C-CC10 | T-00254-5124 | I | PS5-60-08 - Power Gen Package C (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CC11 | T-00254-5125 | I | PS5-60-08 - Power Gen Package C (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CC15 | T-00254-5126 | I | PS5-60-08 - Power Gen Package C (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CC16 | T-00254-5127 | I | PS5-60-08 - Power Gen Package C (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003C-CC17 | T-00254-5128 | I | PS5-60-08 - Power Gen Package C (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003C-CC25 | T-00254-5133 | I | PS5-60-08 - Power Gen Package C (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0003C-CC26 | T-00254-5134 | I | PS5-60-08 - Power Gen Package C (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0003D-CC01 | T-00254-5135 | I | PS5-60-11 - Power Gen Package D (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CC02 | T-00254-5136 | I | PS5-60-11 - Power Gen Package D (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CC03 | T-00254-5137 | I | PS5-60-11 - Power Gen Package D (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CC04 | T-00254-5138 | I | PS5-60-11 - Power Gen Package D (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CC05 | T-00254-5139 | I | PS5-60-11 - Power Gen Package D (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CC06 | T-00254-5140 | I | PS5-60-11 - Power Gen Package D (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CC07 | T-00254-5141 | I | PS5-60-11 - Power Gen Package D (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CC08 | T-00254-5142 | I | PS5-60-11 - Power Gen Package D (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003D-CC09 | T-00254-5143 | I | PS5-60-11 - Power Gen Package D (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003D-CC10 | T-00254-5144 | I | PS5-60-11 - Power Gen Package D (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CC11 | T-00254-5145 | I | PS5-60-11 - Power Gen Package D (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CC15 | T-00254-5146 | I | PS5-60-11 - Power Gen Package D (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CC16 | T-00254-5147 | I | PS5-60-11 - Power Gen Package D (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003D-CC17 | T-00254-5148 | I | PS5-60-11 - Power Gen Package D (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003D-CC25 | T-00254-5153 | I | PS5-60-11 - Power Gen Package D (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0003D-CC26 | T-00254-5154 | I | PS5-60-11 - Power Gen Package D (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0003E-CC01 | T-00254-5155 | I | PS5-60-14 - Power Gen Package E (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CC02 | T-00254-5156 | I | PS5-60-14 - Power Gen Package E (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CC03 | T-00254-5157 | I | PS5-60-14 - Power Gen Package E (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CC04 | T-00254-5158 | I | PS5-60-14 - Power Gen Package E (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CC05 | T-00254-5159 | I | PS5-60-14 - Power Gen Package E (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CC06 | T-00254-5160 | I | PS5-60-14 - Power Gen Package E (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0003E-CC07 | T-00254-5161 | I | PS5-60-14 - Power Gen Package E (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CC08 | T-00254-5162 | I | PS5-60-14 - Power Gen Package E (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003E-CC09 | T-00254-5163 | I | PS5-60-14 - Power Gen Package E (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003E-CC10 | T-00254-5164 | I | PS5-60-14 - Power Gen Package E (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CC11 | T-00254-5165 | I | PS5-60-14 - Power Gen Package E (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CC15 | T-00254-5166 | I | PS5-60-14 - Power Gen Package E (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CC16 | T-00254-5167 | I | PS5-60-14 - Power Gen Package E (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003E-CC17 | T-00254-5168 | I | PS5-60-14 - Power Gen Package E (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003E-CC25 | T-00254-5173 | I | PS5-60-14 - Power Gen Package E (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0003E-CC26 | T-00254-5174 | I | PS5-60-14 - Power Gen Package E (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0003F-CC01 | T-00254-5175 | I | PS5-60-17 - Power Gen Package F (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC02 | T-00254-5176 | I | PS5-60-17 - Power Gen Package F (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC03 | T-00254-5177 | I | PS5-60-17 - Power Gen Package F (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC04 | T-00254-5178 | I | PS5-60-17 - Power Gen Package F (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC05 | T-00254-5179 | I | PS5-60-17 - Power Gen Package F (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC06 | T-00254-5180 | I | PS5-60-17 - Power Gen Package F (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC07 | T-00254-5181 | I | PS5-60-17 - Power Gen Package F (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC08 | T-00254-5182 | I | PS5-60-17 - Power Gen Package F (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC09 | T-00254-5183 | I | PS5-60-17 - Power Gen Package F (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC10 | T-00254-5184 | I | PS5-60-17 - Power Gen Package F (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC11 | T-00254-5185 | I | PS5-60-17 - Power Gen Package F (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC15 | T-00254-5186 | I | PS5-60-17 - Power Gen Package F (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CC16 | T-00254-5187 | I | PS5-60-17 - Power Gen Package F (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003F-CC17 | T-00254-5188 | I | PS5-60-17 - Power Gen Package F (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003F-CC25 | T-00254-5193 | I | PS5-60-17 - Power Gen Package F (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0003F-CC26 | T-00254-5194 | I | PS5-60-17 - Power Gen Package F (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0003G-CC01 | T-00254-5195 | I | PS5-60-20 - Power Gen Package G (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC02 | T-00254-5196 | I | PS5-60-20 - Power Gen Package G (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC03 | T-00254-5197 | I | PS5-60-20 - Power Gen Package G (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003G-CC04 | T-00254-5198 | I | PS5-60-20 - Power Gen Package G (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC05 | T-00254-5199 | I | PS5-60-20 - Power Gen Package G (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC06 | T-00254-5200 | I | PS5-60-20 - Power Gen Package G (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC07 | T-00254-5201 | I | PS5-60-20 - Power Gen Package G (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC08 | T-00254-5202 | I | PS5-60-20 - Power Gen Package G (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC09 | T-00254-5203 | I | PS5-60-20 - Power Gen Package G (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC10 | T-00254-5204 | I | PS5-60-20 - Power Gen Package G (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC11 | T-00254-5205 | I | PS5-60-20 - Power Gen Package G (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC15 | T-00254-5206 | I | PS5-60-20 - Power Gen Package G (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CC16 | T-00254-5207 | I | PS5-60-20 - Power Gen Package G (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003G-CC17 | T-00254-5208 | I | PS5-60-20 - Power Gen Package G (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-IE-0003G-CC25 | T-00254-5213 | I | PS5-60-20 - Power Gen Package G (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0003G-CC26 | T-00254-5214 | I | PS5-60-20 - Power Gen Package G (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IE-0004-CC01 | T-00254-5215 | I | PS5-60-22 - Power Gen Master UCP | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CC02 | T-00254-5216 | I | PS5-60-22 - Power Gen Master UCP | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CC03 | T-00254-5217 | I | PS5-60-22 - Power Gen Master UCP | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CC04 | T-00254-5218 | I | PS5-60-22 - Power Gen Master UCP | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CC05 | T-00254-5219 | I | PS5-60-22 - Power Gen Master UCP | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CC06 | T-00254-5220 | I | PS5-60-22 - Power Gen Master UCP | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CC07 | T-00254-5221 | I | PS5-60-22 - Power Gen Master UCP | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001A-CC01 | T-00254-5225 | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0001A-CC02 | T-00254-5226 | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001A-CC03 | T-00254-5227 | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0001A-CC04 | T-00254-5228 | I | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IN-0001B-CC01 | T-00254-5229 | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0001B-CC02 | T-00254-5230 | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001B-CC03 | T-00254-5231 | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0001B-CC04 | T-00254-5232 | I | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IN-0001C-CC01 | T-00254-5233 | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0001C-CC02 | T-00254-5234 | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IN-0001C-CC03 | T-00254-5235 | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0001C-CC04 | T-00254-5236 | I | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IN-0001D-CC01 | T-00254-5237 | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0001D-CC02 | T-00254-5238 | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IN-0001D-CC03 | T-00254-5239 | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0001D-CC04 | T-00254-5240 | I | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IN-0001E-CC01 | T-00254-5241 | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0001E-CC02 | T-00254-5242 | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IN-0001E-CC03 | T-00254-5243 | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0001E-CC04 | T-00254-5244 | I | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IN-0001F-CC01 | T-00254-5245 | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0001F-CC02 | T-00254-5246 | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IN-0001F-CC03 | T-00254-5247 | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0001F-CC04 | T-00254-5248 | I | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IN-0001G-CC01 | T-00254-5249 | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0001G-CC02 | T-00254-5250 | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IN-0001G-CC03 | T-00254-5251 | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0001G-CC04 | T-00254-5252 | I | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/2 | Yes | Closed + Accepted with Punch
PS5-60-IN-0002A-CC01 | T-00254-5253 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IN-0002A-CC02 | T-00254-5254 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IN-0002A-CC03 | T-00254-5255 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002A-CC04 | T-00254-5256 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IN-0002A-CC05 | T-00254-5257 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IN-0002A-CC06 | T-00254-5258 | I | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0002B-CC01 | T-00254-5259 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0002B-CC02 | T-00254-5260 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-IN-0002B-CC03 | T-00254-5261 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002B-CC04 | T-00254-5262 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0002B-CC05 | T-00254-5263 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002B-CC06 | T-00254-5264 | I | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0002C-CC01 | T-00254-5265 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0002C-CC02 | T-00254-5266 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002C-CC03 | T-00254-5267 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002C-CC04 | T-00254-5268 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0002C-CC05 | T-00254-5269 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002C-CC06 | T-00254-5270 | I | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0002D-CC01 | T-00254-5271 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0002D-CC02 | T-00254-5272 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002D-CC03 | T-00254-5273 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002D-CC04 | T-00254-5274 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0002D-CC05 | T-00254-5275 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002D-CC06 | T-00254-5276 | I | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0002E-CC01 | T-00254-5277 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0002E-CC02 | T-00254-5278 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002E-CC03 | T-00254-5279 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002E-CC04 | T-00254-5280 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0002E-CC05 | T-00254-5281 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002E-CC06 | T-00254-5282 | I | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0002F-CC01 | T-00254-5283 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0002F-CC02 | T-00254-5284 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002F-CC03 | T-00254-5285 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002F-CC04 | T-00254-5286 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0002F-CC05 | T-00254-5287 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002F-CC06 | T-00254-5288 | I | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0002G-CC01 | T-00254-5289 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0002G-CC02 | T-00254-5290 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002G-CC03 | T-00254-5291 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002G-CC04 | T-00254-5292 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0002G-CC05 | T-00254-5293 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002G-CC06 | T-00254-5294 | I | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-IN-0004A-CC11 | T-00254-5295 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002A-CC01 | T-00254-5296 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-LA-0002A-CC02 | T-00254-5297 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-LA-0002A-CC03 | T-00254-5298 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-LA-0002A-CC04 | T-00254-5299 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-LA-0002A-CC05 | T-00254-5300 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-LA-0002A-CC06 | T-00254-5301 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-LA-0002A-CC07 | T-00254-5302 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-LA-0002A-CC08 | T-00254-5303 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-LA-0002A-CC09 | T-00254-5304 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-LA-0002B-CC01 | T-00254-5305 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-LA-0002B-CC02 | T-00254-5306 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-LA-0002B-CC03 | T-00254-5307 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-60-LA-0002B-CC04 | T-00254-5308 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B-CC05 | T-00254-5309 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B-CC06 | T-00254-5310 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002C-CC01 | T-00254-5311 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-LA-0002C-CC02 | T-00254-5312 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-LA-0002C-CC03 | T-00254-5313 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-LA-0002C-CC04 | T-00254-5314 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-60-LA-0002C-CC05 | T-00254-5315 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-LA-0002C-CC06 | T-00254-5316 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-LA-0003-CC01 | T-00254-5317 | I | PS5-60-22 - Power Gen Master UCP | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LIT-4301-CJ01 | T-00254-5318 | I | PS5-60-24 - Cooling Water Tank & Pump | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-LIT-4401-CJ01 | T-00254-5319 | I | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-MOV-0005-CC01 | T-00254-5320 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-MOV-0005-CC02 | T-00254-5321 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-MOV-0006-CC01 | T-00254-5322 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-MOV-0006-CC02 | T-00254-5323 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-MOV-0011-CC01 | T-00254-5324 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-MOV-0011-CC02 | T-00254-5325 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-MOV-0012-CC01 | T-00254-5326 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-MOV-0012-CC02 | T-00254-5327 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-SEA-0001-CC01 | T-00254-5328 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-SEA-0001-CC02 | T-00254-5329 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-SEA-0001-CC03 | T-00254-5330 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-SEA-0001-CC04 | T-00254-5331 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-SEA-0001-CC05 | T-00254-5332 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-SEA-0001-CC06 | T-00254-5333 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-SEA-0001-CC07 | T-00254-5334 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-SEA-0001-CC10 | T-00254-5335 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-SEA-0001-CC11 | T-00254-5336 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-SEA-0001-CC12 | T-00254-5337 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-SEA-0001-CC13 | T-00254-5338 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-SEA-0001-CC14 | T-00254-5339 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-SEA-0001-CC15 | T-00254-5340 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-SEA-0001-CC16 | T-00254-5341 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-SEA-0001-CC17 | T-00254-5342 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-SY-0007-CC01 | T-00254-5344 | I | PS5-60-28 - Air Receiver A & Air Regulator A | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-SY-0008-CC01 | T-00254-5345 | I | PS5-60-29 - Air Receiver B & Air Regulator B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-SY-0009-CC01 | T-00254-5346 | I | PS5-60-30 - Air Receiver C & Air Regulator C | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-SY-0010-CC01 | T-00254-5347 | I | PS5-60-31 - Air Receiver D & Air Regulator D | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-SY-0011-CC01 | T-00254-5348 | I | PS5-60-32 - Air Receiver E & Air Regulator E | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-SY-0012-CC01 | T-00254-5349 | I | PS5-60-33 - Air Receiver F & Air Regulator F | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-SY-0013-CC01 | T-00254-5350 | I | PS5-60-34 - Air Receiver G & Air Regulator G | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-VS-9101A-CC01 | T-00254-5351 | I | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-VS-9101B-CC01 | T-00254-5352 | I | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-VS-9101C-CC01 | T-00254-5353 | I | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-VS-9101D-CC01 | T-00254-5354 | I | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-VS-9101E-CC01 | T-00254-5355 | I | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-VS-9101F-CC01 | T-00254-5356 | I | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-60-VS-9101G-CC01 | T-00254-5357 | I | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-61-BI-0001-CC01 | T-00254-5358 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-BI-0001-CC02 | T-00254-5359 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-BI-0001-CC03 | T-00254-5360 | I | PS5-60-01 - Power Generation Package A | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-61-BI-0002-CC01 | T-00254-5361 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-BI-0002-CC02 | T-00254-5362 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | A:0/1, B:1/5 | Yes | Closed + Accepted with Punch
PS5-61-BI-0002-CC03 | T-00254-5363 | I | PS5-60-04 - Power Generation Package B | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-61-BI-0003-CC01 | T-00254-5364 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-BI-0003-CC02 | T-00254-5365 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-BI-0003-CC03 | T-00254-5366 | I | PS5-60-07 - Power Generation Package C | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-61-BI-0004-CC01 | T-00254-5367 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-BI-0004-CC02 | T-00254-5368 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-BI-0004-CC03 | T-00254-5369 | I | PS5-60-10 - Power Generation Package D | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-61-BI-0005-CC01 | T-00254-5370 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-BI-0005-CC02 | T-00254-5371 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-BI-0005-CC03 | T-00254-5372 | I | PS5-60-13 - Power Generation Package E | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-61-BI-0006-CC01 | T-00254-5373 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-BI-0006-CC02 | T-00254-5374 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-BI-0006-CC03 | T-00254-5375 | I | PS5-60-16 - Power Generation Package F | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-61-BI-0007-CC01 | T-00254-5376 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-BI-0007-CC02 | T-00254-5377 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-BI-0007-CC03 | T-00254-5378 | I | PS5-60-19 - Power Generation Package G | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-71-BAV-0058-CC01 | T-00254-5388 | I | PS5-71-21 - Diesel Transfer Pump A/B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-BAV-0059-CC01 | T-00254-5389 | I | PS5-71-18 - Diesel Separator Module | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-BI-0001A-CC01 | T-00254-5390 | I | PS5-71-06 - Crude Fuel Separation Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0001B-CC01 | T-00254-5391 | I | PS5-71-06 - Crude Fuel Separation Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0002-CC01 | T-00254-5393 | I | PS5-71-18 - Diesel Separator Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0003-CC01 | T-00254-5394 | I | PS5-71-08 - CFO Pre-Pressure Modules | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-BI-0003-CC02 | T-00254-5395 | I | PS5-71-08 - CFO Pre-Pressure Modules | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0003-CC03 | T-00254-5396 | I | PS5-71-08 - CFO Pre-Pressure Modules | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0003-CC04 | T-00254-5397 | I | PS5-71-08 - CFO Pre-Pressure Modules | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0004-CC01 | T-00254-5398 | I | PS5-71-08 - CFO Pre-Pressure Modules | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0005-CC01 | T-00254-5399 | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0005-CC02 | T-00254-5400 | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-BI-0006-CC01 | T-00254-5401 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0008A-CC01 | T-00254-5402 | I | PS5-71-06 - Crude Fuel Separation Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0008A-CC02 | T-00254-5403 | I | PS5-71-06 - Crude Fuel Separation Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0008B-CC01 | T-00254-5404 | I | PS5-71-06 - Crude Fuel Separation Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0008B-CC02 | T-00254-5405 | I | PS5-71-06 - Crude Fuel Separation Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0009-CC01 | T-00254-5406 | I | PS5-71-18 - Diesel Separator Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0009-CC02 | T-00254-5407 | I | PS5-71-18 - Diesel Separator Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0009-CC03 | T-00254-5408 | I | PS5-71-18 - Diesel Separator Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0009-CC04 | T-00254-5409 | I | PS5-71-18 - Diesel Separator Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0010-CC01 | T-00254-5410 | I | PS5-71-18 - Diesel Separator Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0011A-CC01 | T-00254-5411 | I | PS5-71-06 - Crude Fuel Separation Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0011A-CC02 | T-00254-5412 | I | PS5-71-06 - Crude Fuel Separation Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0011A-CC03 | T-00254-5413 | I | PS5-71-06 - Crude Fuel Separation Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0011A-CC04 | T-00254-5414 | I | PS5-71-06 - Crude Fuel Separation Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0011A-CC05 | T-00254-5415 | I | PS5-71-06 - Crude Fuel Separation Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0011B-CC01 | T-00254-5416 | I | PS5-71-06 - Crude Fuel Separation Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0011B-CC02 | T-00254-5417 | I | PS5-71-06 - Crude Fuel Separation Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0011B-CC03 | T-00254-5418 | I | PS5-71-06 - Crude Fuel Separation Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0011B-CC04 | T-00254-5419 | I | PS5-71-06 - Crude Fuel Separation Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0011B-CC05 | T-00254-5420 | I | PS5-71-06 - Crude Fuel Separation Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FCV-0018-CC01 | T-00254-5453 | I | PS5-71-13 - CFO Service Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FCV-0019-CC01 | T-00254-5454 | I | PS5-71-21 - Diesel Transfer Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FCV-0020-CC01 | T-00254-5455 | I | PS5-71-05 - CFO Transfer Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0005-CJ01 | T-00254-5456 | I | PS5-71-17 - Diesel Fuel Distribution Header | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-FIT-0011A-CJ01 | T-00254-5457 | I | PS5-71-01 - CFO Storage Tank Feed Heater | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0011B-CJ01 | T-00254-5458 | I | PS5-71-01 - CFO Storage Tank Feed Heater | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0012-CJ01 | T-00254-5459 | I | PS5-71-17 - Diesel Fuel Distribution Header | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0018-CJ01 | T-00254-5460 | I | PS5-71-13 - CFO Service Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0019-CJ01 | T-00254-5461 | I | PS5-71-21 - Diesel Transfer Pump A/B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:2/2 |  | Complete
PS5-71-FIT-0020-CJ01 | T-00254-5462 | I | PS5-71-05 - CFO Transfer Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FXS-0018-CJ01 | T-00254-5463 | I | PS5-71-13 - CFO Service Pump A/B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-FXS-0019-CJ01 | T-00254-5464 | I | PS5-71-21 - Diesel Transfer Pump A/B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-FXS-0020-CJ01 | T-00254-5465 | I | PS5-71-05 - CFO Transfer Pump A/B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:2/2 |  | Complete
PS5-71-FY-0018-CJ01 | T-00254-5466 | I | PS5-71-13 - CFO Service Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FY-0019-CJ01 | T-00254-5467 | I | PS5-71-21 - Diesel Transfer Pump A/B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-FY-0020-CJ01 | T-00254-5468 | I | PS5-71-05 - CFO Transfer Pump A/B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:2/2 |  | Complete
PS5-71-IN-0001-CC01 | T-00254-5469 | I | PS5-71-19 - Diesel Separator Module (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-IN-0001-CC02 | T-00254-5470 | I | PS5-71-19 - Diesel Separator Module (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-IN-0001-CC03 | T-00254-5471 | I | PS5-71-19 - Diesel Separator Module (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-IN-0001-CC04 | T-00254-5472 | I | PS5-71-19 - Diesel Separator Module (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-IN-0001-CC05 | T-00254-5473 | I | PS5-71-19 - Diesel Separator Module (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-IN-0001-CC06 | T-00254-5474 | I | PS5-71-19 - Diesel Separator Module (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-IN-0001-CC07 | T-00254-5475 | I | PS5-71-19 - Diesel Separator Module (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-IN-0002-CC01 | T-00254-5479 | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-IN-0002-CC02 | T-00254-5480 | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0002-CC03 | T-00254-5481 | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-IN-0002-CC04 | T-00254-5482 | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0003-CC01 | T-00254-5486 | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-IN-0003-CC02 | T-00254-5487 | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-IN-0003-CC03 | T-00254-5488 | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0003-CC04 | T-00254-5489 | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0004A-CC01 | T-00254-5493 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004A-CC02 | T-00254-5494 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004A-CC03 | T-00254-5495 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-IN-0004A-CC04 | T-00254-5496 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-IN-0004A-CC05 | T-00254-5497 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-IN-0004A-CC06 | T-00254-5498 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0004A-CC07 | T-00254-5499 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0004A-CC11 | T-00254-5502 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004A-CC13 | T-00254-5504 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004B-CC01 | T-00254-5505 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004B-CC02 | T-00254-5506 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004B-CC03 | T-00254-5507 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004B-CC04 | T-00254-5508 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-IN-0004B-CC05 | T-00254-5509 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-IN-0004B-CC06 | T-00254-5510 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0004B-CC07 | T-00254-5511 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-71-IN-0004B-CC11 | T-00254-5514 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LCV-4101-CC01 | T-00254-5516 | I | PS5-71-04 - CFO Storage Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LI-4201B-CJ01 | T-00254-5517 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-1201-CJ01 | T-00254-5518 | I | PS5-71-20 - Diesel Fuel Day Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-LIT-1202-CJ01 | T-00254-5519 | I | PS5-71-20 - Diesel Fuel Day Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-LIT-4101-CJ01 | T-00254-5520 | I | PS5-71-04 - CFO Storage Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-4102-CJ01 | T-00254-5521 | I | PS5-71-04 - CFO Storage Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-4201-CJ01 | T-00254-5522 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-4202-CJ01 | T-00254-5523 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-4401-CJ01 | T-00254-5524 | I | PS5-71-15 - Diesel Fuel Storage Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-LIT-4402-CJ01 | T-00254-5525 | I | PS5-71-15 - Diesel Fuel Storage Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-LXS-4101-CJ01 | T-00254-5526 | I | PS5-71-04 - CFO Storage Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-LY-4101-CJ01 | T-00254-5527 | I | PS5-71-04 - CFO Storage Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-MOV-0001-CC01 | T-00254-5528 | I | PS5-71-08 - CFO Pre-Pressure Modules | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-MOV-0001-CC02 | T-00254-5529 | I | PS5-71-08 - CFO Pre-Pressure Modules | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-MOV-0002-CC01 | T-00254-5530 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-MOV-0002-CC02 | T-00254-5531 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-MOV-0003-CC01 | T-00254-5532 | I | PS5-71-08 - CFO Pre-Pressure Modules | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-MOV-0003-CC02 | T-00254-5533 | I | PS5-71-08 - CFO Pre-Pressure Modules | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-MOV-0004-CC01 | T-00254-5534 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-MOV-0004-CC02 | T-00254-5535 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-MOV-0007-CC01 | T-00254-5536 | I | PS5-71-08 - CFO Pre-Pressure Modules | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-MOV-0007-CC02 | T-00254-5537 | I | PS5-71-08 - CFO Pre-Pressure Modules | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-MOV-0008-CC01 | T-00254-5538 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-MOV-0008-CC02 | T-00254-5539 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-MOV-0009-CC01 | T-00254-5540 | I | PS5-71-08 - CFO Pre-Pressure Modules | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-MOV-0009-CC02 | T-00254-5541 | I | PS5-71-08 - CFO Pre-Pressure Modules | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-MOV-0010-CC01 | T-00254-5542 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-MOV-0010-CC02 | T-00254-5543 | I | PS5-71-22 - Diesel Fuel Pre Pressure Module | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-PDIT-0030-CJ01 | T-00254-5544 | I | PS5-71-01 - CFO Storage Tank Feed Heater | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PDIT-0056A-CJ01 | T-00254-5545 | I | PS5-71-05 - CFO Transfer Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PDIT-0056B-CJ01 | T-00254-5546 | I | PS5-71-05 - CFO Transfer Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PIT-0001-CJ01 | T-00254-5547 | I | PS5-71-20 - Diesel Fuel Day Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-PIT-0014-CJ01 | T-00254-5548 | I | PS5-71-17 - Diesel Fuel Distribution Header | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-PIT-0018A-CJ01 | T-00254-5549 | I | PS5-71-13 - CFO Service Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PIT-0019A-CJ01 | T-00254-5550 | I | PS5-71-21 - Diesel Transfer Pump A/B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-PIT-0020A-CJ01 | T-00254-5551 | I | PS5-71-05 - CFO Transfer Pump A/B | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PIT-0022-CJ01 | T-00254-5552 | I | PS5-71-04 - CFO Storage Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:2/2 |  | Complete
PS5-71-PIT-0029-CJ01 | T-00254-5553 | I | PS5-71-15 - Diesel Fuel Storage Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-PIT-0039-CJ01 | T-00254-5554 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-PIT-0089-CJ01 | T-00254-5555 | I | PS5-71-04 - CFO Storage Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PIT-0090-CJ01 | T-00254-5556 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PIT-0091-CJ01 | T-00254-5557 | I | PS5-71-18 - Diesel Separator Module | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-PIT-0092-CJ01 | T-00254-5558 | I | PS5-71-20 - Diesel Fuel Day Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-PIT-2402A-CJ01 | T-00254-5559 | I | PS5-71-01 - CFO Storage Tank Feed Heater | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PIT-2402B-CJ01 | T-00254-5560 | I | PS5-71-01 - CFO Storage Tank Feed Heater | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PIT-3301A-CJ01 | T-00254-5561 | I | PS5-71-05 - CFO Transfer Pump A/B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:2/2 |  | Complete
PS5-71-PIT-3301B-CJ01 | T-00254-5562 | I | PS5-71-05 - CFO Transfer Pump A/B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-PIT-3302A-CJ01 | T-00254-5563 | I | PS5-71-05 - CFO Transfer Pump A/B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:2/2 |  | Complete
PS5-71-PIT-3302B-CJ01 | T-00254-5564 | I | PS5-71-05 - CFO Transfer Pump A/B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-PIT-3401A-CJ01 | T-00254-5565 | I | PS5-71-13 - CFO Service Pump A/B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-PIT-3401B-CJ01 | T-00254-5566 | I | PS5-71-13 - CFO Service Pump A/B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-PIT-3402A-CJ01 | T-00254-5567 | I | PS5-71-13 - CFO Service Pump A/B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-PIT-3402B-CJ01 | T-00254-5568 | I | PS5-71-13 - CFO Service Pump A/B | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-PIT-4101A-CJ01 | T-00254-5569 | I | PS5-71-04 - CFO Storage Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SDV-0001-CC01 | T-00254-5570 | I | PS5-71-20 - Diesel Fuel Day Tank | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-SDV-0001-CC02 | T-00254-5571 | I | PS5-71-20 - Diesel Fuel Day Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SDV-0022-CC01 | T-00254-5572 | I | PS5-71-04 - CFO Storage Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SDV-0022-CC02 | T-00254-5573 | I | PS5-71-04 - CFO Storage Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SDV-0029-CC01 | T-00254-5574 | I | PS5-71-15 - Diesel Fuel Storage Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-SDV-0029-CC02 | T-00254-5575 | I | PS5-71-15 - Diesel Fuel Storage Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SDV-0039-CC01 | T-00254-5576 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SDV-0039-CC02 | T-00254-5577 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-SXS-0001-CJ01 | T-00254-5578 | I | PS5-71-20 - Diesel Fuel Day Tank | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-SXS-0022-CJ01 | T-00254-5579 | I | PS5-71-04 - CFO Storage Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-SXS-0029-CJ01 | T-00254-5580 | I | PS5-71-15 - Diesel Fuel Storage Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-SXS-0039-CJ01 | T-00254-5581 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-SY-0001-CJ01 | T-00254-5582 | I | PS5-71-20 - Diesel Fuel Day Tank | TJX10 - Multi/Single-core instrument control cable | Closed | No | No RFI Yet | - |  | Closed but No RFI
PS5-71-SY-0022-CJ01 | T-00254-5583 | I | PS5-71-04 - CFO Storage Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-SY-0029-CJ01 | T-00254-5584 | I | PS5-71-15 - Diesel Fuel Storage Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-SY-0039-CJ01 | T-00254-5585 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-TIT-0003-CJ01 | T-00254-5586 | I | PS5-71-01 - CFO Storage Tank Feed Heater | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-0004-CJ01 | T-00254-5587 | I | PS5-71-01 - CFO Storage Tank Feed Heater | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-0006-CJ01 | T-00254-5588 | I | PS5-71-01 - CFO Storage Tank Feed Heater | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:2/2 |  | Complete
PS5-71-TIT-0007-CJ01 | T-00254-5589 | I | PS5-71-01 - CFO Storage Tank Feed Heater | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:2/2 |  | Complete
PS5-71-TIT-2204-CJ01 | T-00254-5590 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-2301-CJ01 | T-00254-5591 | I | PS5-71-04 - CFO Storage Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-2402AA-CJ01 | T-00254-5592 | I | PS5-71-01 - CFO Storage Tank Feed Heater | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:2/2 |  | Complete
PS5-71-TIT-2402BA-CJ01 | T-00254-5593 | I | PS5-71-01 - CFO Storage Tank Feed Heater | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:2/2 |  | Complete
PS5-71-TIT-4102-CJ01 | T-00254-5596 | I | PS5-71-04 - CFO Storage Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-4103-CJ01 | T-00254-5597 | I | PS5-71-04 - CFO Storage Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-4202-CJ01 | T-00254-5598 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TIT-4203-CJ01 | T-00254-5599 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-XV-0089-CC01 | T-00254-5600 | I | PS5-71-04 - CFO Storage Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-XV-0089-CC02 | T-00254-5601 | I | PS5-71-04 - CFO Storage Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-XV-0090-CC01 | T-00254-5602 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-XV-0090-CC02 | T-00254-5603 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-XV-0091-CC01 | T-00254-5604 | I | PS5-71-18 - Diesel Separator Module | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-XV-0091-CC02 | T-00254-5605 | I | PS5-71-18 - Diesel Separator Module | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-XV-0092-CC01 | T-00254-5606 | I | PS5-71-20 - Diesel Fuel Day Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-XV-0092-CC02 | T-00254-5607 | I | PS5-71-20 - Diesel Fuel Day Tank | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-XXS-0089-CJ01 | T-00254-5608 | I | PS5-71-04 - CFO Storage Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-XXS-0090-CJ01 | T-00254-5609 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-XXS-0091-CJ01 | T-00254-5610 | I | PS5-71-18 - Diesel Separator Module | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-XXS-0092-CJ01 | T-00254-5611 | I | PS5-71-20 - Diesel Fuel Day Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-XY-0089-CJ01 | T-00254-5612 | I | PS5-71-04 - CFO Storage Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-XY-0090-CJ01 | T-00254-5613 | I | PS5-71-12 - CFO Service Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-71-XY-0091-CJ01 | T-00254-5614 | I | PS5-71-18 - Diesel Separator Module | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-71-XY-0092-CJ01 | T-00254-5615 | I | PS5-71-20 - Diesel Fuel Day Tank | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Open | - |  | Closed + Open
PS5-74-PIT-0002-CJ01 | T-00254-5618 | I | PS5-74-04 - Nitrogen Distribution Header | TJX10 - Multi/Single-core instrument control cable | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-03-RMAC-1409-CJ01 | T-00254-9420 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TJX10 - Multi/Single-core instrument control cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FO-0013B | T-00255-0051 | I | PS5-71-16 - Diesel Fuel Supply Pump A/B | TJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-FO-0009A | T-00255-0052 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | TJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-FO-0009B | T-00255-0053 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | TJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-FO-0003 | T-00255-0054 | I | PS5-28-05 - HP Relief Header | TJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-50-FE-0001 | T-00255-0055 | I | PS5-50-03 - Water Pre-Treatment Package | TJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-FO-0002 | T-00255-0056 | I | PS5-60-24 - Cooling Water Tank & Pump | TJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-FO-0005 | T-00255-0057 | I | PS5-28-06 - Relief Drum and Pump | TJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-FO-0001 | T-00255-0058 | I | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | TJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FO-0008 | T-00255-0059 | I | PS5-25-05 - Crude Oil Export Pumps Bypass | TJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FO-0013A | T-00255-0060 | I | PS5-71-16 - Diesel Fuel Supply Pump A/B | TJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-74-FO-0001 | T-00255-0061 | I | PS5-74-04 - Nitrogen Distribution Header | TJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-FO-0002A | T-00255-0062 | I | PS5-28-08 - Open Drain Sump and Pumps | TJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-FO-0002B | T-00255-0063 | I | PS5-28-08 - Open Drain Sump and Pumps | TJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-FO-0004 | T-00255-0064 | I | PS5-28-16 - LP Relief Header | TJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-FO-0006 | T-00255-0065 | I | PS5-28-08 - Open Drain Sump and Pumps | TJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-FO-0007 | T-00255-0066 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | TJX11 - Orifice plate | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-0006-CX01 | T-00256-0023 | I | PS5-09-01 - HVAC for Office and Facilities building | TJX12 - Optical fiber cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-0007-CX01 | T-00256-0024 | I | PS5-09-04 - HVAC for Workshop & Warehouse | TJX12 - Optical fiber cable | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-09-LB-0008-CX01 | T-00256-0025 | I | PS5-09-03 - HVAC for Generator Building | TJX12 - Optical fiber cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-53-LA-0001-CX01 | T-00256-0026 | I | PS5-53-04 - Water Treatment Purification Package | TJX12 - Optical fiber cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-60-IE-0004-CX03 | T-00256-0027 | I | PS5-60-22 - Power Gen Master UCP | TJX12 - Optical fiber cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0004-CX04 | T-00256-0028 | I | PS5-60-22 - Power Gen Master UCP | TJX12 - Optical fiber cable | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-LA-0003-CX01 | T-00256-0029 | I | PS5-60-22 - Power Gen Master UCP | TJX12 - Optical fiber cable | To be completed | Yes | Open | - |  | Open + RFI Submitted
PS5-74-LB-5101-CX01 | T-00256-0030 | I | PS5-74-02 - N2 Generation Skid (UCP) | TJX12 - Optical fiber cable | To be completed | Yes | Accepted with Punch | B:2/2 |  | Open + RFI Submitted
PS5-82-LA-0001-CX01 | T-00256-0031 | I | PS5-82-03 - Sewage Treatment Plant Package (UCP) | TJX12 - Optical fiber cable | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-75-LA-6200-CX01 | T-00256-0085 | I | PS5-75-01 - DRA Injection Package | TJX12 - Optical fiber cable | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-60-LA-0003-CX02 | T-00256-0090 | I | PS5-60-22 - Power Gen Master UCP | TJX12 - Optical fiber cable | To be completed | No | No RFI Yet | A:0/1, B:0/2 | Yes | Not Started
PS5-60-TW-0006G | T-00257-0165 | I | PS5-60-76 - Engine G Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TW-4203 | T-00257-0166 | I | PS5-71-12 - CFO Service Tank | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TW-0007 | T-00257-0167 | I | PS5-71-01 - CFO Storage Tank Feed Heater | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TW-0003 | T-00257-0168 | I | PS5-71-01 - CFO Storage Tank Feed Heater | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0007C | T-00257-0169 | I | PS5-60-72 - Engine C Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TW-0004 | T-00257-0170 | I | PS5-71-01 - CFO Storage Tank Feed Heater | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0005F | T-00257-0171 | I | PS5-60-75 - Engine F Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-TW-1201 | T-00257-0172 | I | PS5-28-06 - Relief Drum and Pump | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0007B | T-00257-0173 | I | PS5-60-71 - Engine B Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0006C | T-00257-0174 | I | PS5-60-72 - Engine C Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0008A | T-00257-0175 | I | PS5-60-70 - Engine A Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0007D | T-00257-0176 | I | PS5-60-73 - Engine D Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0008C | T-00257-0177 | I | PS5-60-72 - Engine C Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-TW-1402 | T-00257-0178 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0005G | T-00257-0179 | I | PS5-60-76 - Engine G Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-TW-1104 | T-00257-0180 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0008E | T-00257-0181 | I | PS5-60-74 - Engine E Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0007A | T-00257-0182 | I | PS5-60-70 - Engine A Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0006D | T-00257-0183 | I | PS5-60-73 - Engine D Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0008B | T-00257-0184 | I | PS5-60-71 - Engine B Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0007E | T-00257-0185 | I | PS5-60-74 - Engine E Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0008D | T-00257-0186 | I | PS5-60-73 - Engine D Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TW-0003B | T-00257-0187 | I | PS5-25-03 - Crude Oil Export Pump B | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TW-4202 | T-00257-0188 | I | PS5-71-12 - CFO Service Tank | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0008F | T-00257-0189 | I | PS5-60-75 - Engine F Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0006E | T-00257-0190 | I | PS5-60-74 - Engine E Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TW-0002A | T-00257-0191 | I | PS5-25-02 - Crude Oil Export Pump A | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TW-0003C | T-00257-0192 | I | PS5-25-04 - Crude Oil Export Pump C | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TW-0006 | T-00257-0193 | I | PS5-71-01 - CFO Storage Tank Feed Heater | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0006B | T-00257-0194 | I | PS5-60-71 - Engine B Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TW-0003A | T-00257-0195 | I | PS5-25-02 - Crude Oil Export Pump A | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TW-4103 | T-00257-0196 | I | PS5-71-04 - CFO Storage Tank | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-TW-1105 | T-00257-0197 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0006A | T-00257-0198 | I | PS5-60-70 - Engine A Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0007F | T-00257-0199 | I | PS5-60-75 - Engine F Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TW-0002B | T-00257-0200 | I | PS5-25-03 - Crude Oil Export Pump B | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TW-0001 | T-00257-0201 | I | PS5-25-01 - Export Pipeline Pig Receiver | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TW-0004 | T-00257-0202 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-TW-0002C | T-00257-0203 | I | PS5-25-04 - Crude Oil Export Pump C | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-TW-4102 | T-00257-0204 | I | PS5-71-04 - CFO Storage Tank | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-74-TW-0001 | T-00257-0205 | I | PS5-74-04 - Nitrogen Distribution Header | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-28-TW-1401 | T-00257-0206 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0005A | T-00257-0207 | I | PS5-60-70 - Engine A Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0005B | T-00257-0208 | I | PS5-60-71 - Engine B Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0005C | T-00257-0209 | I | PS5-60-72 - Engine C Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0005D | T-00257-0210 | I | PS5-60-73 - Engine D Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0005E | T-00257-0211 | I | PS5-60-74 - Engine E Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0006F | T-00257-0212 | I | PS5-60-75 - Engine F Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0007G | T-00257-0213 | I | PS5-60-76 - Engine G Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-TW-0008G | T-00257-0214 | I | PS5-60-76 - Engine G Cooling system | TJX13 - Thermowell | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B-CA02 | T-00275-1945 | T | PS5-60-05 - Power Gen Package B (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B-CA03 | T-00275-1946 | T | PS5-60-05 - Power Gen Package B (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B-CA04 | T-00275-1947 | T | PS5-60-05 - Power Gen Package B (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003B-CA05 | T-00275-1948 | T | PS5-60-05 - Power Gen Package B (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CA02 | T-00275-1949 | T | PS5-60-08 - Power Gen Package C (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CA03 | T-00275-1950 | T | PS5-60-08 - Power Gen Package C (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CA04 | T-00275-1951 | T | PS5-60-08 - Power Gen Package C (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003C-CA05 | T-00275-1952 | T | PS5-60-08 - Power Gen Package C (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CA02 | T-00275-1953 | T | PS5-60-11 - Power Gen Package D (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CA03 | T-00275-1954 | T | PS5-60-11 - Power Gen Package D (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CA04 | T-00275-1955 | T | PS5-60-11 - Power Gen Package D (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003D-CA05 | T-00275-1956 | T | PS5-60-11 - Power Gen Package D (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CA02 | T-00275-1957 | T | PS5-60-14 - Power Gen Package E (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CA03 | T-00275-1958 | T | PS5-60-14 - Power Gen Package E (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CA04 | T-00275-1959 | T | PS5-60-14 - Power Gen Package E (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003E-CA05 | T-00275-1960 | T | PS5-60-14 - Power Gen Package E (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CA02 | T-00275-1961 | T | PS5-60-17 - Power Gen Package F (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CA03 | T-00275-1962 | T | PS5-60-17 - Power Gen Package F (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CA04 | T-00275-1963 | T | PS5-60-17 - Power Gen Package F (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003F-CA05 | T-00275-1964 | T | PS5-60-17 - Power Gen Package F (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CA03 | T-00275-1965 | T | PS5-60-20 - Power Gen Package G (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CA04 | T-00275-1966 | T | PS5-60-20 - Power Gen Package G (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CA05 | T-00275-1967 | T | PS5-60-20 - Power Gen Package G (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CA01 | T-00275-1968 | T | PS5-60-22 - Power Gen Master UCP | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CA07 | T-00275-1969 | T | PS5-60-22 - Power Gen Master UCP | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CA08 | T-00275-1970 | T | PS5-60-22 - Power Gen Master UCP | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CA14 | T-00275-1971 | T | PS5-60-22 - Power Gen Master UCP | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CA15 | T-00275-1972 | T | PS5-60-22 - Power Gen Master UCP | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0004-CA21 | T-00275-1973 | T | PS5-60-22 - Power Gen Master UCP | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001A-CA01 | T-00275-1974 | T | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001B-CA01 | T-00275-1975 | T | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001C-CA01 | T-00275-1976 | T | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001D-CA01 | T-00275-1977 | T | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001E-CA01 | T-00275-1978 | T | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001F-CA01 | T-00275-1979 | T | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IH-0001G-CA01 | T-00275-1980 | T | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001A-CA01 | T-00275-1981 | T | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001B-CA01 | T-00275-1982 | T | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001C-CA01 | T-00275-1983 | T | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001D-CA01 | T-00275-1984 | T | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001E-CA01 | T-00275-1985 | T | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001F-CA01 | T-00275-1986 | T | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0001G-CA01 | T-00275-1987 | T | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002A-CA01 | T-00275-1988 | T | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002B-CA01 | T-00275-1989 | T | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002C-CA01 | T-00275-1990 | T | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002D-CA01 | T-00275-1991 | T | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002E-CA01 | T-00275-1992 | T | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002F-CA01 | T-00275-1993 | T | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IN-0002G-CA01 | T-00275-1994 | T | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B-CA01 | T-00275-1995 | T | PS5-60-10 - Power Generation Package D | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B-CA02 | T-00275-1996 | T | PS5-60-10 - Power Generation Package D | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B-CA03 | T-00275-1997 | T | PS5-60-10 - Power Generation Package D | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B-CA04 | T-00275-1998 | T | PS5-60-10 - Power Generation Package D | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B-CA05 | T-00275-1999 | T | PS5-60-10 - Power Generation Package D | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002B-CA06 | T-00275-2000 | T | PS5-60-10 - Power Generation Package D | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002C-CA01 | T-00275-2001 | T | PS5-60-16 - Power Generation Package F | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002C-CA02 | T-00275-2002 | T | PS5-60-16 - Power Generation Package F | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002C-CA03 | T-00275-2003 | T | PS5-60-16 - Power Generation Package F | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002C-CA04 | T-00275-2004 | T | PS5-60-16 - Power Generation Package F | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002C-CA05 | T-00275-2005 | T | PS5-60-16 - Power Generation Package F | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LA-0002C-CA06 | T-00275-2006 | T | PS5-60-16 - Power Generation Package F | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-SEA-0001-CA01 | T-00275-2007 | T | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0001-CA01 | T-00275-2008 | T | PS5-71-19 - Diesel Separator Module (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0001-CA11 | T-00275-2009 | T | PS5-71-19 - Diesel Separator Module (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0002-CA01 | T-00275-2010 | T | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0003-CA01 | T-00275-2011 | T | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004A-CA01 | T-00275-2012 | T | PS5-71-07 - Crude Fuel Separation Module (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-IN-0004B-CA01 | T-00275-2013 | T | PS5-71-07 - Crude Fuel Separation Module (UCP) | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8451A-CA01 | T-00275-4202 | T | PS5-09-03 - HVAC for Generator Building | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-8451B-CA01 | T-00275-4203 | T | PS5-09-03 - HVAC for Generator Building | TIX01 - RJ45 Cable | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0019 | T-00284-0085 | I | PS5-71-21 - Diesel Transfer Pump A/B | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-50-FIT-0001 | T-00284-0086 | I | PS5-50-03 - Water Pre-Treatment Package | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0018 | T-00284-0087 | I | PS5-71-13 - CFO Service Pump A/B | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0020 | T-00284-0088 | I | PS5-71-05 - CFO Transfer Pump A/B | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0012 | T-00284-0089 | I | PS5-71-17 - Diesel Fuel Distribution Header | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FIT-0005 | T-00284-0090 | I | PS5-71-17 - Diesel Fuel Distribution Header | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-1202 | T-00284-0091 | I | PS5-71-20 - Diesel Fuel Day Tank | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LIT-4401 | T-00284-0092 | I | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-4401 | T-00284-0093 | I | PS5-71-15 - Diesel Fuel Storage Tank | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-LIT-4101 | T-00284-0094 | I | PS5-53-01 - Utility Water / Storage Tank | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-LIT-4301 | T-00284-0095 | I | PS5-60-24 - Cooling Water Tank & Pump | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-1201 | T-00284-0096 | I | PS5-71-20 - Diesel Fuel Day Tank | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LIT-4402 | T-00284-0097 | I | PS5-71-15 - Diesel Fuel Storage Tank | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-LIT-4102 | T-00284-0098 | I | PS5-53-01 - Utility Water / Storage Tank | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PDIT-0034A | T-00284-0099 | I | PS5-25-02 - Crude Oil Export Pump A | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PDIT-0012B | T-00284-0100 | I | PS5-01-03 - Fire Water Pump B | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PDIT-0011A | T-00284-0101 | I | PS5-01-01 - Fire Water Jockey Pump A/B | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PDIT-0050 | T-00284-0102 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PDIT-0034C | T-00284-0103 | I | PS5-25-04 - Crude Oil Export Pump C | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PDIT-0030 | T-00284-0104 | I | PS5-71-01 - CFO Storage Tank Feed Heater | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PDIT-0011B | T-00284-0105 | I | PS5-01-01 - Fire Water Jockey Pump A/B | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PDIT-0056B | T-00284-0106 | I | PS5-71-05 - CFO Transfer Pump A/B | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-PDIT-0056A | T-00284-0107 | I | PS5-71-05 - CFO Transfer Pump A/B | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-PDIT-0012A | T-00284-0108 | I | PS5-01-02 - Fire Water Pump A | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-PDIT-0034B | T-00284-0109 | I | PS5-25-03 - Crude Oil Export Pump B | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FCV-0004B | T-00284-0179 | I | PS5-01-01 - Fire Water Jockey Pump A/B | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FCV-0004 | T-00284-0180 | I | PS5-25-06 - Crude Oil Export Pumps Discharge | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FCV-0003A | T-00284-0181 | I | PS5-01-02 - Fire Water Pump A | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FCV-0003B | T-00284-0182 | I | PS5-01-03 - Fire Water Pump B | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FCV-0018 | T-00284-0183 | I | PS5-71-13 - CFO Service Pump A/B | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FCV-0003B | T-00284-0184 | I | PS5-25-03 - Crude Oil Export Pump B | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-LCV-4101 | T-00284-0185 | I | PS5-71-04 - CFO Storage Tank | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FCV-0019 | T-00284-0186 | I | PS5-71-21 - Diesel Transfer Pump A/B | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-FCV-0020 | T-00284-0187 | I | PS5-71-05 - CFO Transfer Pump A/B | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FCV-0004A | T-00284-0188 | I | PS5-01-01 - Fire Water Jockey Pump A/B | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FCV-0003A | T-00284-0189 | I | PS5-25-02 - Crude Oil Export Pump A | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-25-FCV-0003C | T-00284-0190 | I | PS5-25-04 - Crude Oil Export Pump C | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PDIT-8207 | T-00284-0208 | I | PS5-09-03 - HVAC for Generator Building | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PDIT-8407 | T-00284-0209 | I | PS5-09-03 - HVAC for Generator Building | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PDIT-8408 | T-00284-0210 | I | PS5-09-03 - HVAC for Generator Building | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PDIT-8409 | T-00284-0211 | I | PS5-09-03 - HVAC for Generator Building | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-PDIT-8411 | T-00284-0212 | I | PS5-09-03 - HVAC for Generator Building | TJX06 - Tubing pressure test | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IJ-0001-CL01 | T-00604-0248 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX09a - LV Power Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CL02 | T-00604-0249 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX09a - LV Power Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0010-CL01 | T-00604-0250 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | CPX09a - LV Power Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0011-CL01 | T-00604-0251 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | CPX09a - LV Power Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0001-CG01 | T-00604-0252 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX09a - LV Power Cable (both end by HU CTR) | To be completed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Open + RFI Submitted
PS5-61-IK-0001-CG02 | T-00604-0253 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX09a - LV Power Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:0/2 | Yes | Open + RFI Submitted
PS5-61-IK-0001-CG03 | T-00604-0254 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX09a - LV Power Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0001-CG04 | T-00604-0255 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX09a - LV Power Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0001-CL01 | T-00604-0256 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-61-IK-0001-CL02 | T-00604-0257 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-61-IK-0001-CL03 | T-00604-0258 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-61-IK-0001-CL04 | T-00604-0259 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-61-IK-0001-CL05 | T-00604-0260 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-61-IK-0001-CL06 | T-00604-0261 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-61-IK-0001-CL07 | T-00604-0262 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-61-IK-0001-CL08 | T-00604-0263 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-61-IK-0001-CL09 | T-00604-0264 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted with Punch | B:1/3 | Yes | Closed + Accepted with Punch
PS5-61-IK-0001-CL10 | T-00604-0265 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL11 | T-00604-0266 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL12 | T-00604-0267 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL13 | T-00604-0268 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL14 | T-00604-0269 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL15 | T-00604-0270 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL16 | T-00604-0271 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL17 | T-00604-0272 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-61-IK-0001-CL18 | T-00604-0273 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-61-IK-0001-CL19 | T-00604-0274 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | A:0/2, B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL20 | T-00604-0275 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | A:0/2, B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL21 | T-00604-0276 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | A:0/2, B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL22 | T-00604-0277 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | A:0/2, B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL23 | T-00604-0278 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | A:0/2, B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL24 | T-00604-0279 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | A:0/2, B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL25 | T-00604-0280 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | A:0/2, B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL26 | T-00604-0281 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | A:0/2, B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL27 | T-00604-0282 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | A:0/2, B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL28 | T-00604-0283 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | A:0/2, B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL29 | T-00604-0284 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | A:0/2, B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL30 | T-00604-0285 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | A:0/2, B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL31 | T-00604-0286 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0001-CL32 | T-00604-0287 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IK-0001-CL33 | T-00604-0288 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | A:0/2, B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL34 | T-00604-0289 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | A:0/2, B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL35 | T-00604-0290 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | A:0/2, B:0/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL36 | T-00604-0291 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | A:0/2, B:0/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL44 | T-00604-0292 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | A:0/1, B:1/2 | Yes | Closed + Accepted
PS5-61-IK-0001-CL45 | T-00604-0293 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | A:0/2, B:1/2 | Yes | Closed + Accepted
PS5-61-ISR-0101-CL01 | T-00604-0294 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX09a - LV Power Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-ISR-0102-CL01 | T-00604-0295 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX09a - LV Power Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IU-0010-CL01 | T-00604-0296 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | CPX09a - LV Power Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IU-0010-CL02 | T-00604-0297 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | CPX09a - LV Power Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IU-0011-CL01 | T-00604-0298 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | CPX09a - LV Power Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IU-0011-CL02 | T-00604-0299 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | CPX09a - LV Power Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IV-0001A-CL01 | T-00604-0300 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | B:1/2 | Yes | Closed + Accepted
PS5-61-IV-0001B-CL01 | T-00604-0301 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09a - LV Power Cable (both end by HU CTR) | Closed | Yes | Accepted | B:1/2 | Yes | Closed + Accepted
PS5-61-NER-0010-CL01 | T-00604-0302 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | CPX09a - LV Power Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-NER-0011-CL01 | T-00604-0303 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | CPX09a - LV Power Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-63-IV-0010-CL01 | T-00604-0304 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX09a - LV Power Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-63-IV-0011-CL01 | T-00604-0305 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX09a - LV Power Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-63-NER-0010-CL01 | T-00604-0306 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX09a - LV Power Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-63-NER-0011-CL01 | T-00604-0307 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX09a - LV Power Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IE-0002-CD01 | T-00606-0065 | E | PS5-61-08 - Electrical Control System | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IE-0002-CD02 | T-00606-0066 | E | PS5-61-08 - Electrical Control System | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-61-IE-0002-CD03 | T-00606-0067 | E | PS5-61-08 - Electrical Control System | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IE-0002-CD04 | T-00606-0068 | E | PS5-61-08 - Electrical Control System | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IE-0002-CD05 | T-00606-0069 | E | PS5-61-08 - Electrical Control System | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IE-0002-CD06 | T-00606-0070 | E | PS5-61-08 - Electrical Control System | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:0/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD01 | T-00606-0071 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD03 | T-00606-0072 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | Started (not Completed) | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD33 | T-00606-0073 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | Closed | Yes | Accepted | A:0/2, B:0/2 | Yes | Closed + Accepted
PS5-61-IJ-0001-CD34 | T-00606-0074 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | Closed | Yes | Accepted | A:0/2, B:1/2 | Yes | Closed + Accepted
PS5-61-IJ-0001-CD35 | T-00606-0075 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD36 | T-00606-0076 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IJ-0001-CD37 | T-00606-0077 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD38 | T-00606-0078 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD39 | T-00606-0079 | E | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD40 | T-00606-0080 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD41 | T-00606-0081 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | Closed | Yes | Accepted with Punch | B:1/2 | Yes | Closed + Accepted with Punch
PS5-61-IJ-0001-CD42 | T-00606-0082 | E | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-FIT-0003A-CL01 | T-00608-0350 | E | PS5-01-02 - Fire Water Pump A | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-01-FIT-0003B-CL01 | T-00608-0351 | E | PS5-01-03 - Fire Water Pump B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-01-FIT-0004A-CL01 | T-00608-0352 | E | PS5-01-01 - Fire Water Jockey Pump A/B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-01-FIT-0004B-CL01 | T-00608-0353 | E | PS5-01-01 - Fire Water Jockey Pump A/B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-01-IE-0001A-CL01 | T-00608-0354 | E | PS5-01-05 - Foam Skid | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-01-IE-0001B-CL01 | T-00608-0355 | E | PS5-01-05 - Foam Skid | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-01-IE-0002A-CL01 | T-00608-0356 | E | PS5-01-01 - Fire Water Jockey Pump A/B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-01-IE-0002B-CL01 | T-00608-0357 | E | PS5-01-01 - Fire Water Jockey Pump A/B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-01-IE-0009A-CL01 | T-00608-0358 | E | PS5-01-02 - Fire Water Pump A | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-01-IE-0009B-CL01 | T-00608-0359 | E | PS5-01-03 - Fire Water Pump B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:0/1 | Yes | Open + RFI Submitted
PS5-03-GDLHP-0137-CL01 | T-00608-0360 | E | PS5-03-01 - FZ-01 - Process Area | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-03-GDLHP-0142-CL01 | T-00608-0361 | E | PS5-03-01 - FZ-01 - Process Area | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-03-GDLHP-0143-CL01 | T-00608-0362 | E | PS5-03-01 - FZ-01 - Process Area | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-03-GDLHP-0144-CL01 | T-00608-0363 | E | PS5-03-01 - FZ-01 - Process Area | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-03-GDLHP-0146-CL01 | T-00608-0364 | E | PS5-03-01 - FZ-01 - Process Area | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-03-GDLHP-0147-CL01 | T-00608-0365 | E | PS5-03-01 - FZ-01 - Process Area | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-03-GDLHP-0149-CL01 | T-00608-0366 | E | PS5-03-01 - FZ-01 - Process Area | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-03-GDLHP-0150-CL01 | T-00608-0367 | E | PS5-03-01 - FZ-01 - Process Area | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-03-GDLHP-0401-CL01 | T-00608-0368 | E | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-05-IG-0004-CL01 | T-00608-0369 | E | PS5-62-03 - Outdoor Emergency Lighting DB - PS5-05-IG-0004 | CPX09b - LV Power Cable (One end by HU CTR) | Started (not Completed) | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-05-IG-0006-CL01 | T-00608-0370 | E | PS5-62-04 - Outdoor Emergency Lighting DB - PS5-05-IG-0006 | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-25-DM-3200A-CL01 | T-00608-0371 | E | PS5-25-02 - Crude Oil Export Pump A | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-DM-3200B-CL01 | T-00608-0372 | E | PS5-25-02 - Crude Oil Export Pump A | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-DM-3300A-CL01 | T-00608-0373 | E | PS5-25-03 - Crude Oil Export Pump B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-DM-3300B-CL01 | T-00608-0374 | E | PS5-25-03 - Crude Oil Export Pump B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-DM-3400A-CL01 | T-00608-0375 | E | PS5-25-04 - Crude Oil Export Pump C | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-25-DM-3400B-CL01 | T-00608-0376 | E | PS5-25-04 - Crude Oil Export Pump C | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-DM-6400A-CL01 | T-00608-0377 | E | PS5-25-02 - Crude Oil Export Pump A | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-DM-6400B-CL01 | T-00608-0378 | E | PS5-25-02 - Crude Oil Export Pump A | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-DM-6500A-CL01 | T-00608-0379 | E | PS5-25-03 - Crude Oil Export Pump B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-DM-6500B-CL01 | T-00608-0380 | E | PS5-25-03 - Crude Oil Export Pump B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-DM-6600A-CL01 | T-00608-0381 | E | PS5-25-04 - Crude Oil Export Pump C | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-DM-6600B-CL01 | T-00608-0382 | E | PS5-25-04 - Crude Oil Export Pump C | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-FIT-0001-CL01 | T-00608-0383 | E | PS5-25-01 - Export Pipeline Pig Receiver | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-FIT-0003A-CL01 | T-00608-0384 | E | PS5-25-02 - Crude Oil Export Pump A | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-FIT-0003B-CL01 | T-00608-0385 | E | PS5-25-03 - Crude Oil Export Pump B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-FIT-0003C-CL01 | T-00608-0386 | E | PS5-25-04 - Crude Oil Export Pump C | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-FIT-0004-CL01 | T-00608-0387 | E | PS5-25-06 - Crude Oil Export Pumps Discharge | CPX09b - LV Power Cable (One end by HU CTR) | Started (not Completed) | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-HE-2100-CL01 | T-00608-0388 | E | PS5-25-02 - Crude Oil Export Pump A | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-HE-2200-CL01 | T-00608-0389 | E | PS5-25-03 - Crude Oil Export Pump B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-HE-2300-CL01 | T-00608-0390 | E | PS5-25-04 - Crude Oil Export Pump C | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-UD-3100A-CL01 | T-00608-0391 | E | PS5-25-02 - Crude Oil Export Pump A | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-28-BE-0002A-CL01 | T-00608-0392 | E | PS5-28-17 - Reinjection Pump | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-28-BE-0002B-CL01 | T-00608-0393 | E | PS5-28-17 - Reinjection Pump | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-28-DM-3300-CL01 | T-00608-0394 | E | PS5-28-06 - Relief Drum and Pump | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-28-DM-3400-CL01 | T-00608-0395 | E | PS5-28-03 - Closed Drain Drum and Pump 01 | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-28-DM-3500-CL01 | T-00608-0396 | E | PS5-28-08 - Open Drain Sump and Pumps | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-28-DM-3600A-CL01 | T-00608-0397 | E | PS5-28-08 - Open Drain Sump and Pumps | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-28-DM-3600A-CL02 | T-00608-0398 | E | PS5-28-08 - Open Drain Sump and Pumps | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-28-DM-3600B-CL01 | T-00608-0399 | E | PS5-28-08 - Open Drain Sump and Pumps | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-28-DM-3600B-CL02 | T-00608-0400 | E | PS5-28-08 - Open Drain Sump and Pumps | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-28-DM-3700A-CL01 | T-00608-0401 | E | PS5-28-04 - Closed Drain Drum and Pump 02 | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-28-DM-3700B-CL01 | T-00608-0402 | E | PS5-28-04 - Closed Drain Drum and Pump 02 | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-28-DM-3800A-CL01 | T-00608-0403 | E | PS5-28-13 - Seal Oil Drain Drum & Pump A | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-28-DM-3800B-CL01 | T-00608-0404 | E | PS5-28-14 - Seal Oil Drain Drum & Pump B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-28-DM-3800C-CL01 | T-00608-0405 | E | PS5-28-15 - Seal Oil Drain Drum & Pump C | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-28-DM-3900A-CL01 | T-00608-0406 | E | PS5-28-17 - Reinjection Pump | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/1 | Yes | Open + RFI Submitted
PS5-28-DM-3900B-CL01 | T-00608-0407 | E | PS5-28-17 - Reinjection Pump | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-28-HE-2100-CL01 | T-00608-0408 | E | PS5-28-03 - Closed Drain Drum and Pump 01 | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-28-HE-2200-CL01 | T-00608-0409 | E | PS5-28-04 - Closed Drain Drum and Pump 02 | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-28-ISO-2008-CL01 | T-00608-0410 | E | PS5-28-10 - Oil Skimmer Package | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-50-IE-0001-CL01 | T-00608-0411 | E | PS5-50-01 - Water Well Submersible Pumps (3100) | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-50-IE-0002-CL01 | T-00608-0412 | E | PS5-50-02 - Water Well Submersible Pumps (3200) | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-53-DM-3100A-CL01 | T-00608-0413 | E | PS5-53-02 - Water Distribution Pump A/B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/1 | Yes | Open + RFI Submitted
PS5-53-DM-3100B-CL01 | T-00608-0414 | E | PS5-53-02 - Water Distribution Pump A/B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/1 | Yes | Open + RFI Submitted
PS5-53-IN-0001-CL01 | T-00608-0415 | E | PS5-53-04 - Water Treatment Purification Package | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-60-DM-3300-CL01 | T-00608-0416 | E | PS5-60-24 - Cooling Water Tank & Pump | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-DM-3400-CL01 | T-00608-0417 | E | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IDH-3100A-CL01 | T-00608-0418 | E | PS5-25-02 - Crude Oil Export Pump A | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-61-IDH-3100B-CL01 | T-00608-0419 | E | PS5-25-03 - Crude Oil Export Pump B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-61-IDH-3100C-CL01 | T-00608-0420 | E | PS5-25-04 - Crude Oil Export Pump C | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-61-IG-0006-CL01 | T-00608-0421 | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-61-IG-0007-CL01 | T-00608-0422 | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-61-IG-0012A-CL01 | T-00608-0423 | E | PS5-25-02 - Crude Oil Export Pump A | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IG-0012B-CL01 | T-00608-0424 | E | PS5-25-03 - Crude Oil Export Pump B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IG-0012C-CL01 | T-00608-0425 | E | PS5-25-04 - Crude Oil Export Pump C | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IG-0014-CL01 | T-00608-0426 | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-001 | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-61-IG-0042-CL01 | T-00608-0427 | E | PS5-61-10 - Outdoor Valves Distribution Board - PS5-61-IG-00 | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IG-0043-CL01 | T-00608-0428 | E | PS5-61-11 - Outdoor Valves Distribution Board - PS5-61-IG-00 | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0001-CL37 | T-00608-0429 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09b - LV Power Cable (One end by HU CTR) | Started (not Completed) | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0001-CL38 | T-00608-0430 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0001-CL39 | T-00608-0431 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0001-CL40 | T-00608-0432 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0001-CL41 | T-00608-0433 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0001-CL42 | T-00608-0434 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0001-CL43 | T-00608-0435 | E | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IK-0003-CG01 | T-00608-0436 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0003-CG02 | T-00608-0437 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0003-CG03 | T-00608-0438 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0003-CG04 | T-00608-0439 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0003-CG05 | T-00608-0440 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0003-CG06 | T-00608-0441 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0006-CG01 | T-00608-0442 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0006-CG02 | T-00608-0443 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0006-CG03 | T-00608-0444 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0006-CG04 | T-00608-0445 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IV-0006A-CL01 | T-00608-0446 | E | PS5-25-02 - Crude Oil Export Pump A | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IV-0006B-CL01 | T-00608-0447 | E | PS5-25-03 - Crude Oil Export Pump B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IV-0006C-CL01 | T-00608-0448 | E | PS5-25-04 - Crude Oil Export Pump C | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-71-DM-3100A-CL01 | T-00608-0449 | E | PS5-71-16 - Diesel Fuel Supply Pump A/B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-71-DM-3100B-CL01 | T-00608-0450 | E | PS5-71-16 - Diesel Fuel Supply Pump A/B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-71-DM-3200-CL01 | T-00608-0451 | E | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-71-DM-3300A-CL01 | T-00608-0452 | E | PS5-71-05 - CFO Transfer Pump A/B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-71-DM-3300B-CL01 | T-00608-0453 | E | PS5-71-05 - CFO Transfer Pump A/B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-71-DM-3400A-CL01 | T-00608-0454 | E | PS5-71-13 - CFO Service Pump A/B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-71-DM-3400B-CL01 | T-00608-0455 | E | PS5-71-13 - CFO Service Pump A/B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-71-DM-3500A-CL01 | T-00608-0456 | E | PS5-71-21 - Diesel Transfer Pump A/B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-71-DM-3500B-CL01 | T-00608-0457 | E | PS5-71-21 - Diesel Transfer Pump A/B | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-71-FIT-0011A-CL01 | T-00608-0458 | E | PS5-71-01 - CFO Storage Tank Feed Heater | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-FIT-0011B-CL01 | T-00608-0459 | E | PS5-71-01 - CFO Storage Tank Feed Heater | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-71-HE-2200-CL01 | T-00608-0460 | E | PS5-71-12 - CFO Service Tank | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-71-HE-2300-CL01 | T-00608-0461 | E | PS5-71-04 - CFO Storage Tank | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-74-IG-5101-CL01 | T-00608-0462 | E | PS5-74-01 - N2 Generation Skid | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-75-DM-3100A-CL01 | T-00608-0463 | E | PS5-75-03 - Corrosion Inhibitor Injection Package | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-75-DM-3100B-CL01 | T-00608-0464 | E | PS5-75-03 - Corrosion Inhibitor Injection Package | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-75-DM-3200A-CL01 | T-00608-0465 | E | PS5-75-02 - Biocide Injection Package | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-75-DM-3200B-CL01 | T-00608-0466 | E | PS5-75-02 - Biocide Injection Package | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-75-ISO-0001-CL01 | T-00608-0467 | E | PS5-75-01 - DRA Injection Package | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-75-ISO-0002-CL01 | T-00608-0468 | E | PS5-75-01 - DRA Injection Package | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-79-IV-0001-CL01 | T-00608-0469 | E | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-79-IV-0002-CL01 | T-00608-0470 | E | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-79-IV-0003-CL01 | T-00608-0471 | E | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-79-IV-0004-CL01 | T-00608-0472 | E | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-79-IV-0005-CL01 | T-00608-0473 | E | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-79-IV-0006-CL01 | T-00608-0474 | E | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-79-IV-0007-CL01 | T-00608-0475 | E | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-79-IV-0008-CL01 | T-00608-0476 | E | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-79-IV-0009-CL01 | T-00608-0477 | E | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-79-IV-0010-CL01 | T-00608-0478 | E | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-79-IV-0011-CL01 | T-00608-0479 | E | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-79-IV-0012-CL01 | T-00608-0480 | E | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-82-IN-0001-CL01 | T-00608-0481 | E | PS5-82-02 - Sewage Treatment Plant Package | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-53-IN-0001-CL02 | T-00608-0943 | E | PS5-53-04 - Water Treatment Purification Package | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-53-IN-0001-CL03 | T-00608-0944 | E | PS5-53-04 - Water Treatment Purification Package | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-71-HE-2400A-CL01 | T-00608-1052 | E | PS5-71-01 - CFO Storage Tank Feed Heater | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:2/4 | Yes | Open + RFI Submitted
PS5-71-HE-2400A-CL02 | T-00608-1053 | E | PS5-71-01 - CFO Storage Tank Feed Heater | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | - |  | Open + RFI Submitted
PS5-71-HE-2400A-CL03 | T-00608-1054 | E | PS5-71-01 - CFO Storage Tank Feed Heater | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-HE-2400A-CL04 | T-00608-1055 | E | PS5-71-01 - CFO Storage Tank Feed Heater | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-HE-2400B-CL01 | T-00608-1056 | E | PS5-71-01 - CFO Storage Tank Feed Heater | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-HE-2400B-CL02 | T-00608-1057 | E | PS5-71-01 - CFO Storage Tank Feed Heater | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-HE-2400B-CL03 | T-00608-1058 | E | PS5-71-01 - CFO Storage Tank Feed Heater | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-HE-2400B-CL04 | T-00608-1059 | E | PS5-71-01 - CFO Storage Tank Feed Heater | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-08-52BT-0131-CS01 | T-00608-1068 | E | PS5-08-52 - Process & Security CCTV | CPX09b - LV Power Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD09 | T-00610-0177 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD22 | T-00610-0178 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-05-IE-8100-CD24 | T-00610-0179 | E | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-05-IG-0004-CD01 | T-00610-0180 | E | PS5-62-03 - Outdoor Emergency Lighting DB - PS5-05-IG-0004 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-05-IG-0006-CD01 | T-00610-0181 | E | PS5-62-04 - Outdoor Emergency Lighting DB - PS5-05-IG-0006 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-05-IG-0025-CD01 | T-00610-0182 | E | PS5-62-06 - CRO Generator Building Emergency Lighting DB - | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-05-IG-0026-CD01 | T-00610-0183 | E | PS5-62-07 - CRO Generator Electrical Building Emergency Ligh | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-06-GU-0003A-CD01 | T-00610-0184 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-06-GU-0003B-CD01 | T-00610-0185 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-06-IG-0004A-CD01 | T-00610-0186 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:0/2 | Yes | Not Started
PS5-06-IG-0004B-CD01 | T-00610-0187 | E | PS5-06-02 - AC UPS - Power Generator Building | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-25-HE-2100-CD01 | T-00610-0188 | E | PS5-25-02 - Crude Oil Export Pump A | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-HE-2200-CD01 | T-00610-0189 | E | PS5-25-03 - Crude Oil Export Pump B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-HE-2300-CD01 | T-00610-0190 | E | PS5-25-04 - Crude Oil Export Pump C | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-IES-3200A-CD01 | T-00610-0191 | E | PS5-25-02 - Crude Oil Export Pump A | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/4 | Yes | Closed + Accepted
PS5-25-IES-3200B-CD01 | T-00610-0192 | E | PS5-25-02 - Crude Oil Export Pump A | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/4 | Yes | Closed + Accepted
PS5-25-IES-3300A-CD01 | T-00610-0193 | E | PS5-25-03 - Crude Oil Export Pump B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/4 | Yes | Closed + Accepted
PS5-25-IES-3300B-CD01 | T-00610-0194 | E | PS5-25-03 - Crude Oil Export Pump B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/4 | Yes | Closed + Accepted
PS5-25-IES-3400A-CD01 | T-00610-0195 | E | PS5-25-04 - Crude Oil Export Pump C | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/4 | Yes | Closed + Accepted
PS5-25-IES-3400B-CD01 | T-00610-0196 | E | PS5-25-04 - Crude Oil Export Pump C | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/4 | Yes | Closed + Accepted
PS5-25-IES-6400A-CD01 | T-00610-0197 | E | PS5-25-02 - Crude Oil Export Pump A | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/4 | Yes | Closed + Accepted
PS5-25-IES-6400B-CD01 | T-00610-0198 | E | PS5-25-02 - Crude Oil Export Pump A | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/4 | Yes | Closed + Accepted
PS5-25-IES-6500A-CD01 | T-00610-0199 | E | PS5-25-03 - Crude Oil Export Pump B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/4 | Yes | Closed + Accepted
PS5-25-IES-6500B-CD01 | T-00610-0200 | E | PS5-25-03 - Crude Oil Export Pump B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/4 | Yes | Closed + Accepted
PS5-25-IES-6600A-CD01 | T-00610-0201 | E | PS5-25-04 - Crude Oil Export Pump C | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/4 | Yes | Closed + Accepted
PS5-25-IES-6600B-CD01 | T-00610-0202 | E | PS5-25-04 - Crude Oil Export Pump C | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/4 | Yes | Closed + Accepted
PS5-28-HE-2100-CD01 | T-00610-0203 | E | PS5-28-03 - Closed Drain Drum and Pump 01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-28-HE-2200-CD01 | T-00610-0204 | E | PS5-28-04 - Closed Drain Drum and Pump 02 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-28-IES-2008-CD01 | T-00610-0205 | E | PS5-28-10 - Oil Skimmer Package | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-28-IES-3300-CD01 | T-00610-0206 | E | PS5-28-06 - Relief Drum and Pump | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-28-IES-3400-CD01 | T-00610-0207 | E | PS5-28-03 - Closed Drain Drum and Pump 01 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-28-IES-3500-CD01 | T-00610-0208 | E | PS5-28-08 - Open Drain Sump and Pumps | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-28-IES-3600A-CD01 | T-00610-0209 | E | PS5-28-08 - Open Drain Sump and Pumps | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-28-IES-3600B-CD01 | T-00610-0210 | E | PS5-28-08 - Open Drain Sump and Pumps | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-28-IES-3700A-CD01 | T-00610-0211 | E | PS5-28-04 - Closed Drain Drum and Pump 02 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-28-IES-3700B-CD01 | T-00610-0212 | E | PS5-28-04 - Closed Drain Drum and Pump 02 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-28-IES-3800A-CD01 | T-00610-0213 | E | PS5-28-13 - Seal Oil Drain Drum & Pump A | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-28-IES-3800B-CD01 | T-00610-0214 | E | PS5-28-14 - Seal Oil Drain Drum & Pump B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-28-IES-3800C-CD01 | T-00610-0215 | E | PS5-28-15 - Seal Oil Drain Drum & Pump C | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-28-IES-3900A-CD01 | T-00610-0216 | E | PS5-28-17 - Reinjection Pump | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-28-IES-3900B-CD01 | T-00610-0217 | E | PS5-28-17 - Reinjection Pump | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-53-IES-3100A-CD01 | T-00610-0218 | E | PS5-53-02 - Water Distribution Pump A/B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:0/2 | Yes | Closed + Accepted
PS5-53-IES-3100B-CD01 | T-00610-0219 | E | PS5-53-02 - Water Distribution Pump A/B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:0/2 | Yes | Closed + Accepted
PS5-60-IE-0003A-CD06 | T-00610-0220 | E | PS5-60-01 - Power Generation Package A | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003A-CD08 | T-00610-0221 | E | PS5-60-01 - Power Generation Package A | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003A-CD12 | T-00610-0222 | E | PS5-60-01 - Power Generation Package A | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003B-CD06 | T-00610-0223 | E | PS5-60-04 - Power Generation Package B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003B-CD08 | T-00610-0224 | E | PS5-60-04 - Power Generation Package B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003B-CD12 | T-00610-0225 | E | PS5-60-04 - Power Generation Package B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003C-CD06 | T-00610-0226 | E | PS5-60-07 - Power Generation Package C | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003C-CD08 | T-00610-0227 | E | PS5-60-07 - Power Generation Package C | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003C-CD12 | T-00610-0228 | E | PS5-60-07 - Power Generation Package C | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003D-CD06 | T-00610-0229 | E | PS5-60-10 - Power Generation Package D | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003D-CD08 | T-00610-0230 | E | PS5-60-10 - Power Generation Package D | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003D-CD12 | T-00610-0231 | E | PS5-60-10 - Power Generation Package D | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003E-CD06 | T-00610-0232 | E | PS5-60-13 - Power Generation Package E | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003E-CD08 | T-00610-0233 | E | PS5-60-13 - Power Generation Package E | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003E-CD12 | T-00610-0234 | E | PS5-60-13 - Power Generation Package E | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003F-CD06 | T-00610-0235 | E | PS5-60-16 - Power Generation Package F | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003F-CD08 | T-00610-0236 | E | PS5-60-16 - Power Generation Package F | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003F-CD12 | T-00610-0237 | E | PS5-60-16 - Power Generation Package F | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-60-IE-0003G-CD06 | T-00610-0238 | E | PS5-60-19 - Power Generation Package G | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003G-CD08 | T-00610-0239 | E | PS5-60-19 - Power Generation Package G | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003G-CD12 | T-00610-0240 | E | PS5-60-19 - Power Generation Package G | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0004-CD01 | T-00610-0241 | E | PS5-60-22 - Power Gen Master UCP | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0004-CD02 | T-00610-0242 | E | PS5-60-22 - Power Gen Master UCP | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IES-3300-CD01 | T-00610-0243 | E | PS5-60-24 - Cooling Water Tank & Pump | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IES-3400-CD01 | T-00610-0244 | E | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IDH-3100A-CD01 | T-00610-0245 | E | PS5-25-02 - Crude Oil Export Pump A | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IDH-3100A-CD02 | T-00610-0246 | E | PS5-25-02 - Crude Oil Export Pump A | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IDH-3100B-CD01 | T-00610-0247 | E | PS5-25-03 - Crude Oil Export Pump B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IDH-3100B-CD02 | T-00610-0248 | E | PS5-25-03 - Crude Oil Export Pump B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IDH-3100C-CD01 | T-00610-0249 | E | PS5-25-04 - Crude Oil Export Pump C | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IDH-3100C-CD02 | T-00610-0250 | E | PS5-25-04 - Crude Oil Export Pump C | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IE-0003-CD01 | T-00610-0251 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-61-IG-0006-CD01 | T-00610-0252 | E | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-61-IG-0007-CD01 | T-00610-0253 | E | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-61-IG-0014-CD01 | T-00610-0254 | E | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-001 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-61-IG-0015-CD01 | T-00610-0255 | E | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61- | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-61-IG-0016-CD01 | T-00610-0256 | E | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IG-0042-CD01 | T-00610-0257 | E | PS5-61-10 - Outdoor Valves Distribution Board - PS5-61-IG-00 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IG-0043-CD01 | T-00610-0258 | E | PS5-61-11 - Outdoor Valves Distribution Board - PS5-61-IG-00 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD04 | T-00610-0259 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD05 | T-00610-0260 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD06 | T-00610-0261 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD07 | T-00610-0262 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD24 | T-00610-0263 | E | PS5-25-02 - Crude Oil Export Pump A | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD25 | T-00610-0264 | E | PS5-25-03 - Crude Oil Export Pump B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD26 | T-00610-0265 | E | PS5-25-04 - Crude Oil Export Pump C | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD27 | T-00610-0266 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD28 | T-00610-0267 | E | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD29 | T-00610-0268 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD30 | T-00610-0269 | E | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD31 | T-00610-0270 | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building ( | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IJ-0001-CD32 | T-00610-0271 | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building ( | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0005-CD01 | T-00610-0272 | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building ( | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IK-0005-CD02 | T-00610-0273 | E | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building ( | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-62-IE-0002-CD01 | T-00610-0274 | E | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-71-HE-2200-CD01 | T-00610-0275 | E | PS5-71-12 - CFO Service Tank | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-71-HE-2300-CD01 | T-00610-0276 | E | PS5-71-04 - CFO Storage Tank | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:1/2 | Yes | Open + RFI Submitted
PS5-71-IES-3100A-CD01 | T-00610-0277 | E | PS5-71-16 - Diesel Fuel Supply Pump A/B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-71-IES-3100B-CD01 | T-00610-0278 | E | PS5-71-16 - Diesel Fuel Supply Pump A/B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-71-IES-3200-CD01 | T-00610-0279 | E | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-71-IES-3300A-CD01 | T-00610-0280 | E | PS5-71-05 - CFO Transfer Pump A/B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-71-IES-3300B-CD01 | T-00610-0281 | E | PS5-71-05 - CFO Transfer Pump A/B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-71-IES-3400A-CD01 | T-00610-0282 | E | PS5-71-13 - CFO Service Pump A/B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-71-IES-3400B-CD01 | T-00610-0283 | E | PS5-71-13 - CFO Service Pump A/B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-71-IES-3500A-CD01 | T-00610-0284 | E | PS5-71-21 - Diesel Transfer Pump A/B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-71-IES-3500B-CD01 | T-00610-0285 | E | PS5-71-21 - Diesel Transfer Pump A/B | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-75-IES-3100A-CD01 | T-00610-0286 | E | PS5-75-03 - Corrosion Inhibitor Injection Package | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-75-IES-3100B-CD01 | T-00610-0287 | E | PS5-75-03 - Corrosion Inhibitor Injection Package | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-75-IES-3200A-CD01 | T-00610-0288 | E | PS5-75-02 - Biocide Injection Package | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-75-IES-3200B-CD01 | T-00610-0289 | E | PS5-75-02 - Biocide Injection Package | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0004-CD14 | T-00610-0574 | E | PS5-60-22 - Power Gen Master UCP | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Other | - |  | Open + RFI Submitted
PS5-60-IE-0004-CD15 | T-00610-0575 | E | PS5-60-22 - Power Gen Master UCP | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Other | - |  | Open + RFI Submitted
PS5-60-IE-0004-CD16 | T-00610-0576 | E | PS5-60-22 - Power Gen Master UCP | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Other | - |  | Open + RFI Submitted
PS5-61-IE-0002-CD41 | T-00610-0577 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IE-0002-CD42 | T-00610-0578 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-61-IE-0002-CD43 | T-00610-0579 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-61-IE-0002-CD44 | T-00610-0580 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-61-IE-0003-CD02 | T-00610-0581 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-61-IE-0003-CD03 | T-00610-0582 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-61-IE-0003-CD04 | T-00610-0583 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD61 | T-00610-0584 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD62 | T-00610-0585 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD63 | T-00610-0586 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD64 | T-00610-0587 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD65 | T-00610-0588 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD66 | T-00610-0589 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-61-IJ-0001-CD67 | T-00610-0590 | E | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-61-IE-0002-CD45 | T-00610-0598 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IE-0002-CD46 | T-00610-0599 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IE-0002-CD47 | T-00610-0600 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IE-0002-CD48 | T-00610-0601 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Open + RFI Submitted
PS5-61-IE-0002-CD49 | T-00610-0602 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Open + RFI Submitted
PS5-61-IE-0002-CD50 | T-00610-0603 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Open + RFI Submitted
PS5-61-IE-0002-CD51 | T-00610-0604 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IE-0002-CD52 | T-00610-0605 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IE-0002-CD53 | T-00610-0606 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IE-0002-CD54 | T-00610-0607 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IE-0002-CD55 | T-00610-0608 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-61-IE-0003-CD11 | T-00610-0609 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Open + RFI Submitted
PS5-61-IE-0003-CD12 | T-00610-0610 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Open + RFI Submitted
PS5-61-IE-0003-CD13 | T-00610-0611 | E | PS5-61-08 - Electrical Control System | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | To be completed | Yes | Accepted with Punch | A:0/2, B:0/2 | Yes | Open + RFI Submitted
PS5-01-BI-0001-CC01 | T-00614-0847 | I | PS5-01-05 - Foam Skid | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-01-BI-0002-CC01 | T-00614-0848 | I | PS5-01-10 - Water Mist Package | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-01-BI-0003-CC01 | T-00614-0849 | I | PS5-01-10 - Water Mist Package | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-01-BI-0004-CC01 | T-00614-0850 | I | PS5-01-10 - Water Mist Package | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-01-BI-0005-CC01 | T-00614-0851 | I | PS5-01-05 - Foam Skid | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-01-BI-0006-CC01 | T-00614-0852 | I | PS5-01-05 - Foam Skid | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-01-BI-1117-CC01 | T-00614-0853 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-01-BI-1118-CC01 | T-00614-0854 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-01-BI-1501-CC01 | T-00614-0855 | I | PS5-01-07 - Fire Water Ring Main & Distribution | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-01-BI-1515-CC01 | T-00614-0856 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-01-BI-1520-CC01 | T-00614-0857 | I | PS5-01-10 - Water Mist Package | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-01-BI-1571-CC01 | T-00614-0858 | I | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-01-BI-2110-CC01 | T-00614-0859 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-01-BI-2520-CC01 | T-00614-0860 | I | PS5-01-10 - Water Mist Package | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-01-BI-2571A-CC01 | T-00614-0861 | I | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-01-BI-2571B-CC01 | T-00614-0862 | I | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-01-IE-0002A-CC01 | T-00614-0863 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-01-IE-0002A-CC02 | T-00614-0864 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-01-IE-0002B-CC01 | T-00614-0865 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-01-IE-0002B-CC02 | T-00614-0866 | I | PS5-01-01 - Fire Water Jockey Pump A/B | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-01-IE-0009A-CC01 | T-00614-0867 | I | PS5-01-02 - Fire Water Pump A | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-01-IE-0009A-CC02 | T-00614-0868 | I | PS5-01-02 - Fire Water Pump A | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-IE-0009B-CC01 | T-00614-0869 | I | PS5-01-03 - Fire Water Pump B | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-01-IE-0009B-CC02 | T-00614-0870 | I | PS5-01-03 - Fire Water Pump B | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-01-LB-0004-CC01 | T-00614-0871 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:2/2 |  | Not Started
PS5-01-LB-0004-CC02 | T-00614-0872 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:2/2 |  | Not Started
PS5-01-LB-0004-CC03 | T-00614-0873 | I | PS5-01-11 - Inergen for Power Gen Building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:0/2 | Yes | Not Started
PS5-01-LIT-4201-CJ01 | T-00614-0874 | I | PS5-01-10 - Water Mist Package | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-01-PIT-0014-CJ01 | T-00614-0875 | I | PS5-01-07 - Fire Water Ring Main & Distribution | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-01-PIT-0015-CJ01 | T-00614-0876 | I | PS5-01-07 - Fire Water Ring Main & Distribution | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-01-PIT-0016-CJ01 | T-00614-0877 | I | PS5-01-07 - Fire Water Ring Main & Distribution | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-01-PIT-0017-CJ01 | T-00614-0878 | I | PS5-01-07 - Fire Water Ring Main & Distribution | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-03-BI-1502-CC01 | T-00614-0879 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-03-BI-1503-CC01 | T-00614-0880 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2, C:0/1 | Yes | Open + RFI Submitted
PS5-03-BI-1506-CC01 | T-00614-0881 | I | PS5-03-01 - FZ-01 - Process Area | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-03-BI-1507-CC01 | T-00614-0882 | I | PS5-03-01 - FZ-01 - Process Area | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-03-BI-1508-CC01 | T-00614-0883 | I | PS5-03-01 - FZ-01 - Process Area | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-03-BI-1509-CC01 | T-00614-0884 | I | PS5-03-01 - FZ-01 - Process Area | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/2 | Yes | Closed + Accepted
PS5-03-BI-1510-CC01 | T-00614-0885 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-03-BI-1511-CC01 | T-00614-0886 | I | PS5-03-07 - FZ-07 - Pretreatment Area | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-03-BI-1512-CC01 | T-00614-0887 | I | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-03-BI-1513-CC01 | T-00614-0888 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-03-BI-1514-CC01 | T-00614-0889 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-03-BI-1516-CC01 | T-00614-0890 | I | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | A:0/1, B:1/2 | Yes | Not Started
PS5-03-BI-2501-CC01 | T-00614-0891 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-03-BI-2502-CC01 | T-00614-0892 | I | PS5-03-06 - FZ-06 - Transformer Area | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | Closed | Yes | Accepted | B:2/2, C:0/1 | Yes | Closed + Accepted
PS5-03-BI-2503-CC01 | T-00614-0893 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | Closed | Yes | Accepted | B:0/2, C:0/1 | Yes | Closed + Accepted
PS5-03-BI-2504-CC01 | T-00614-0894 | I | PS5-03-01 - FZ-01 - Process Area | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-03-BI-2505-CC01 | T-00614-0895 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-03-BI-2506-CC01 | T-00614-0896 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-03-BI-2507-CC01 | T-00614-0897 | I | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:0/2 | Yes | Not Started
PS5-03-BI-2508-CC01 | T-00614-0898 | I | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-03-BI-2509-CC01 | T-00614-0899 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-03-BI-2510-CC01 | T-00614-0900 | I | PS5-03-03 - FZ-03 - Buildings Area | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-BI-2511-CC01 | T-00614-0901 | I | PS5-03-01 - FZ-01 - Process Area | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | Closed | Yes | Accepted | B:0/2 | Yes | Closed + Accepted
PS5-03-BI-2512-CC01 | T-00614-0902 | I | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2, C:0/1 | Yes | Open + RFI Submitted
PS5-03-BI-2514-CC01 | T-00614-0903 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-03-BI-2515-CC01 | T-00614-0904 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-03-HS-7002-CJ01 | T-00614-0905 | I | PS5-03-03 - FZ-03 - Buildings Area | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-03-MTX-0001-CC01 | T-00614-0906 | I | PS5-04-02 - Office Building SIS/FGS System | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-MTX-0001-CC02 | T-00614-0907 | I | PS5-04-02 - Office Building SIS/FGS System | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-MTX-0001-CC03 | T-00614-0908 | I | PS5-04-02 - Office Building SIS/FGS System | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-MTX-0001-CC04 | T-00614-0909 | I | PS5-04-02 - Office Building SIS/FGS System | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-MTX-0001-CC05 | T-00614-0910 | I | PS5-04-02 - Office Building SIS/FGS System | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-MTX-0001-CC06 | T-00614-0911 | I | PS5-04-02 - Office Building SIS/FGS System | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-MTX-0001-CC07 | T-00614-0912 | I | PS5-04-02 - Office Building SIS/FGS System | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-MTX-0001-CC08 | T-00614-0913 | I | PS5-04-02 - Office Building SIS/FGS System | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-NMR-0801-CJ01 | T-00614-0914 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-03-NMR-0802-CJ01 | T-00614-0915 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-03-NMR-0803-CJ01 | T-00614-0916 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-03-NMR-0804-CJ01 | T-00614-0917 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-03-RMAC-0120-CJ01 | T-00614-0918 | I | PS5-03-01 - FZ-01 - Process Area | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:0/2 | Yes | Not Started
PS5-03-RMAC-0824-CJ01 | T-00614-0919 | I | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-03-SEA-0002-CC01 | T-00614-0920 | I | PS5-03-22 - FZ-G1 - Guard House | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-03-SEA-0002-CJ01 | T-00614-0921 | I | PS5-03-22 - FZ-G1 - Guard House | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | A:0/1, B:1/2 | Yes | Not Started
PS5-03-SEA-0003-CC01 | T-00614-0922 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-03-SEA-0003-CJ01 | T-00614-0923 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-03-SEA-0005-CC01 | T-00614-0924 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-SEA-0005-CJ01 | T-00614-0925 | I | PS5-03-24 - FZ - Office and Facilities Building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-03-SEA-0006-CC01 | T-00614-0926 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-03-SEA-0006-CJ01 | T-00614-0927 | I | PS5-03-25 - FZ - Workshop & Warehouse | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | A:0/1, B:1/2 | Yes | Not Started
PS5-05-BI-0002-CC11 | T-00614-0928 | I | PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-05-BI-0002-CC12 | T-00614-0929 | I | PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-05-IE-8100-CC01 | T-00614-0930 | I | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-05-IE-8100-CC02 | T-00614-0931 | I | PS5-05-02 - Emergency Diesel Generator Package (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-06-GU-0003A-CC01 | T-00614-0932 | I | PS5-06-02 - AC UPS - Power Generator Building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:2/2 |  | Not Started
PS5-06-GU-0003B-CC01 | T-00614-0933 | I | PS5-06-02 - AC UPS - Power Generator Building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-09-BI-2501-CC01 | T-00614-0934 | I | PS5-09-04 - HVAC for Workshop & Warehouse | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | A:0/1, B:0/2 | Yes | Not Started
PS5-09-BI-2502-CC01 | T-00614-0935 | I | PS5-09-01 - HVAC for Office and Facilities building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-BI-2503-CC01 | T-00614-0936 | I | PS5-09-03 - HVAC for Generator Building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-09-LB-0006-CC01 | T-00614-0937 | I | PS5-09-01 - HVAC for Office and Facilities building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-0006-CC02 | T-00614-0938 | I | PS5-09-01 - HVAC for Office and Facilities building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-0006-CC03 | T-00614-0939 | I | PS5-09-01 - HVAC for Office and Facilities building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-0006-CC04 | T-00614-0940 | I | PS5-09-01 - HVAC for Office and Facilities building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-0007-CC01 | T-00614-0941 | I | PS5-09-04 - HVAC for Workshop & Warehouse | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | A:0/1, B:1/2 | Yes | Not Started
PS5-09-LB-0007-CC02 | T-00614-0942 | I | PS5-09-04 - HVAC for Workshop & Warehouse | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-09-LB-0007-CC03 | T-00614-0943 | I | PS5-09-04 - HVAC for Workshop & Warehouse | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-09-LB-0007-CC04 | T-00614-0944 | I | PS5-09-04 - HVAC for Workshop & Warehouse | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | A:0/1, B:1/2 | Yes | Not Started
PS5-09-LB-0008-CC01 | T-00614-0945 | I | PS5-09-03 - HVAC for Generator Building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | A:0/1, B:1/2 | Yes | Not Started
PS5-09-LB-0008-CC02 | T-00614-0946 | I | PS5-09-03 - HVAC for Generator Building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | A:0/1, B:0/2 | Yes | Not Started
PS5-09-LB-0008-CC03 | T-00614-0947 | I | PS5-09-03 - HVAC for Generator Building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-09-LB-0008-CC04 | T-00614-0948 | I | PS5-09-03 - HVAC for Generator Building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-09-LB-0008-CC05 | T-00614-0949 | I | PS5-09-03 - HVAC for Generator Building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:0/2 | Yes | Not Started
PS5-09-LB-0008-CC06 | T-00614-0950 | I | PS5-09-03 - HVAC for Generator Building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | A:0/1, B:1/2 | Yes | Not Started
PS5-09-LB-0008-CC07 | T-00614-0951 | I | PS5-09-03 - HVAC for Generator Building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-09-LB-0008-CC08 | T-00614-0952 | I | PS5-09-03 - HVAC for Generator Building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-25-BI-1101-CC01 | T-00614-0953 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-25-BI-1102-CC01 | T-00614-0954 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-25-BI-1103-CC01 | T-00614-0955 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/3, C:0/1 | Yes | Closed + Accepted
PS5-25-BI-1104-CC01 | T-00614-0956 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-25-BI-1115-CC01 | T-00614-0957 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-25-BI-1174A-CC01 | T-00614-0958 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-1174B-CC01 | T-00614-0959 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-1174C-CC01 | T-00614-0960 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-1201-CC01 | T-00614-0961 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-25-BI-1274A-CC01 | T-00614-0962 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-1274B-CC01 | T-00614-0963 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-1274C-CC01 | T-00614-0964 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-25-BI-1301-CC01 | T-00614-0965 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-25-BI-1302-CC01 | T-00614-0966 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-25-BI-1310-CC01 | T-00614-0967 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | Started (not Completed) | No | No RFI Yet | B:0/2 | Yes | Not Started
PS5-25-BI-1801A-CC01 | T-00614-0968 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-1801B-CC01 | T-00614-0969 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-1801C-CC01 | T-00614-0970 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-1802A-CC02 | T-00614-0971 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-1802B-CC02 | T-00614-0972 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-1802C-CC02 | T-00614-0973 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-1803A-CC01 | T-00614-0974 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-1803A-CC02 | T-00614-0975 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-25-BI-1803B-CC01 | T-00614-0976 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-1803B-CC02 | T-00614-0977 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-1803C-CC01 | T-00614-0978 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-1803C-CC02 | T-00614-0979 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-2101-CC01 | T-00614-0980 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-2102-CC01 | T-00614-0981 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-2103-CC01 | T-00614-0982 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-2104-CC01 | T-00614-0983 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-25-BI-2105-CC01 | T-00614-0984 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-25-BI-2106-CC01 | T-00614-0985 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-25-BI-2108-CC01 | T-00614-0986 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-25-BI-2109-CC01 | T-00614-0987 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/2 | Yes | Closed + Accepted
PS5-25-BI-2201-CC01 | T-00614-0988 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-25-BI-2203-CC01 | T-00614-0989 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-2205-CC01 | T-00614-0990 | I | PS5-25-01 - Export Pipeline Pig Receiver | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-BI-2301-CC01 | T-00614-0991 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-25-BI-2302-CC01 | T-00614-0992 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-25-BI-2305-CC01 | T-00614-0993 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-25-BI-2308-CC01 | T-00614-0994 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/2 | Yes | Closed + Accepted
PS5-25-BI-2309-CC01 | T-00614-0995 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-25-BI-2312-CC01 | T-00614-0996 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/2 | Yes | Closed + Accepted
PS5-25-BI-2315-CC01 | T-00614-0997 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/2 | Yes | Closed + Accepted
PS5-25-BI-2316-CC01 | T-00614-0998 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-25-MXS-3101AA-CJ01 | T-00614-0999 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-MXS-3101AB-CJ01 | T-00614-1000 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-25-MXS-3101BA-CJ01 | T-00614-1001 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-MXS-3101BB-CJ01 | T-00614-1002 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-25-MXS-3101CA-CJ01 | T-00614-1003 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-MXS-3101CB-CJ01 | T-00614-1004 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | Accepted | B:1/2 | Yes | Not Started
PS5-25-PIT-0052-CJ01 | T-00614-1005 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-PIT-0071A-CJ01 | T-00614-1006 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-PIT-0071B-CJ01 | T-00614-1007 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-PIT-0071C-CJ01 | T-00614-1008 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-SDV-0052-CC01 | T-00614-1009 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-SDV-0052-CJ01 | T-00614-1010 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-25-SHSR-0052-CJ01 | T-00614-1011 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-25-SXS-0052-CJ01 | T-00614-1012 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-25-SY-0052A-CJ01 | T-00614-1013 | I | PS5-25-07 - Export Pipeline Pig Launcher | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-28-BI-1105-CC01 | T-00614-1014 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-28-BI-1106-CC01 | T-00614-1015 | I | PS5-28-06 - Relief Drum and Pump | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-28-BI-1114-CC01 | T-00614-1016 | I | PS5-28-04 - Closed Drain Drum and Pump 02 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-28-BI-1303-CC01 | T-00614-1017 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-28-BI-1307-CC01 | T-00614-1018 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-28-BI-2304-CC01 | T-00614-1019 | I | PS5-28-17 - Reinjection Pump | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-28-HXA-1101-CJ01 | T-00614-1020 | I | PS5-28-03 - Closed Drain Drum and Pump 01 | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | A:0/1, B:0/2 | Yes | Not Started
PS5-28-LB-8200-CC01 | T-00614-1021 | I | PS5-28-11 - Open Drain Interceptor | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-28-LB-8200-CJ01 | T-00614-1022 | I | PS5-28-11 - Open Drain Interceptor | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-50-BI-1107-CC01 | T-00614-1023 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-50-IE-0001-CC01 | T-00614-1024 | I | PS5-50-01 - Water Well Submersible Pumps (3100) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-50-IE-0001-CC02 | T-00614-1025 | I | PS5-50-01 - Water Well Submersible Pumps (3100) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:0/2 | Yes | Open + RFI Submitted
PS5-50-IE-0002-CC01 | T-00614-1026 | I | PS5-50-02 - Water Well Submersible Pumps (3200) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-50-IE-0002-CC02 | T-00614-1027 | I | PS5-50-02 - Water Well Submersible Pumps (3200) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:1/1 | Yes | Open + RFI Submitted
PS5-50-LIT-0001-CJ01 | T-00614-1028 | I | PS5-50-01 - Water Well Submersible Pumps (3100) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-50-LIT-0002-CJ01 | T-00614-1029 | I | PS5-50-02 - Water Well Submersible Pumps (3200) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-53-BI-1108-CC01 | T-00614-1030 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-53-BI-1304-CC01 | T-00614-1031 | I | PS5-53-01 - Utility Water / Storage Tank | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | Closed | Yes | Accepted | C:0/1 | Yes | Closed + Accepted
PS5-53-LA-0001-CC01 | T-00614-1032 | I | PS5-53-04 - Water Treatment Purification Package | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-53-LA-0001-CC02 | T-00614-1033 | I | PS5-53-04 - Water Treatment Purification Package | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003A-CC21 | T-00614-1034 | I | PS5-60-02 - Power Gen Package A (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:2/2 |  | Not Started
PS5-60-IE-0003A-CC22 | T-00614-1035 | I | PS5-60-02 - Power Gen Package A (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:2/2 |  | Not Started
PS5-60-IE-0003A-CC23 | T-00614-1036 | I | PS5-60-02 - Power Gen Package A (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:2/2 |  | Not Started
PS5-60-IE-0003A-CC24 | T-00614-1037 | I | PS5-60-02 - Power Gen Package A (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:2/2 |  | Not Started
PS5-60-IE-0003B-CC21 | T-00614-1038 | I | PS5-60-05 - Power Gen Package B (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:2/2 |  | Not Started
PS5-60-IE-0003B-CC22 | T-00614-1039 | I | PS5-60-05 - Power Gen Package B (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-60-IE-0003B-CC23 | T-00614-1040 | I | PS5-60-05 - Power Gen Package B (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-60-IE-0003B-CC24 | T-00614-1041 | I | PS5-60-05 - Power Gen Package B (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:2/2 |  | Not Started
PS5-60-IE-0003C-CC21 | T-00614-1042 | I | PS5-60-08 - Power Gen Package C (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | A:0/1, B:1/2 | Yes | Not Started
PS5-60-IE-0003C-CC22 | T-00614-1043 | I | PS5-60-08 - Power Gen Package C (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | A:0/1, B:1/2 | Yes | Not Started
PS5-60-IE-0003C-CC23 | T-00614-1044 | I | PS5-60-08 - Power Gen Package C (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003C-CC24 | T-00614-1045 | I | PS5-60-08 - Power Gen Package C (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:0/2 | Yes | Not Started
PS5-60-IE-0003D-CC21 | T-00614-1046 | I | PS5-60-11 - Power Gen Package D (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | A:0/1, B:1/2 | Yes | Not Started
PS5-60-IE-0003D-CC22 | T-00614-1047 | I | PS5-60-11 - Power Gen Package D (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | A:0/1, B:1/2 | Yes | Not Started
PS5-60-IE-0003D-CC23 | T-00614-1048 | I | PS5-60-11 - Power Gen Package D (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:0/2 | Yes | Not Started
PS5-60-IE-0003D-CC24 | T-00614-1049 | I | PS5-60-11 - Power Gen Package D (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003E-CC21 | T-00614-1050 | I | PS5-60-14 - Power Gen Package E (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | A:0/1, B:1/2 | Yes | Not Started
PS5-60-IE-0003E-CC22 | T-00614-1051 | I | PS5-60-14 - Power Gen Package E (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | A:0/2, B:2/4 | Yes | Not Started
PS5-60-IE-0003E-CC23 | T-00614-1052 | I | PS5-60-14 - Power Gen Package E (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003E-CC24 | T-00614-1053 | I | PS5-60-14 - Power Gen Package E (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-60-IE-0003F-CC21 | T-00614-1054 | I | PS5-60-17 - Power Gen Package F (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | Accepted | A:0/1, B:1/4 | Yes | Not Started
PS5-60-IE-0003F-CC22 | T-00614-1055 | I | PS5-60-17 - Power Gen Package F (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-60-IE-0003F-CC23 | T-00614-1056 | I | PS5-60-17 - Power Gen Package F (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-60-IE-0003F-CC24 | T-00614-1057 | I | PS5-60-17 - Power Gen Package F (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-60-IE-0003G-CC21 | T-00614-1058 | I | PS5-60-20 - Power Gen Package G (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-60-IE-0003G-CC22 | T-00614-1059 | I | PS5-60-20 - Power Gen Package G (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-60-IE-0003G-CC23 | T-00614-1060 | I | PS5-60-20 - Power Gen Package G (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-60-IE-0003G-CC24 | T-00614-1061 | I | PS5-60-20 - Power Gen Package G (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:0/2 | Yes | Not Started
PS5-60-IE-0004-CC08 | T-00614-1062 | I | PS5-60-22 - Power Gen Master UCP | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:0/2 | Yes | Not Started
PS5-60-IE-0004-CC11 | T-00614-1063 | I | PS5-60-22 - Power Gen Master UCP | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-60-IE-0004-CC12 | T-00614-1064 | I | PS5-60-22 - Power Gen Master UCP | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-60-SEA-0001-CC18 | T-00614-1065 | I | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-61-IDH-3100A-CC01 | T-00614-1066 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IDH-3100A-CC02 | T-00614-1067 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IDH-3100A-CC03 | T-00614-1068 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IDH-3100B-CC01 | T-00614-1069 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IDH-3100B-CC02 | T-00614-1070 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IDH-3100B-CC03 | T-00614-1071 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IDH-3100C-CC01 | T-00614-1072 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IDH-3100C-CC02 | T-00614-1073 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-61-IDH-3100C-CC03 | T-00614-1074 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0001-CC01 | T-00614-1075 | I | PS5-71-02 - CFO Allocation Metering Package | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-71-BI-0021-CC01 | T-00614-1076 | I | PS5-71-02 - CFO Allocation Metering Package | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-71-BI-0021-CC02 | T-00614-1077 | I | PS5-71-02 - CFO Allocation Metering Package | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:0/2 | Yes | Not Started
PS5-71-BI-1109-CC01 | T-00614-1078 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/4 | Yes | Open + RFI Submitted
PS5-71-BI-1110-CC01 | T-00614-1079 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-71-BI-1111-CC01 | T-00614-1080 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-71-BI-1112-CC01 | T-00614-1081 | I | PS5-71-17 - Diesel Fuel Distribution Header | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-71-BI-1113-CC01 | T-00614-1082 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-71-BI-1116-CC01 | T-00614-1083 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-71-BI-1117-CC01 | T-00614-1084 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-71-BI-2101-CC01 | T-00614-1085 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | Closed | No | No RFI Yet | B:1/2 | Yes | Closed but No RFI
PS5-71-BI-1305-CC01 | T-00614-1086 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-71-BI-1306-CC01 | T-00614-1087 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/3 | Yes | Closed + Accepted
PS5-71-BI-1308-CC01 | T-00614-1088 | I | PS5-71-15 - Diesel Fuel Storage Tank | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2, C:0/1 | Yes | Open + RFI Submitted
PS5-71-BI-2107-CC01 | T-00614-1089 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-71-BI-2113-CC01 | T-00614-1090 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-71-BI-2114-CC01 | T-00614-1091 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-71-BI-2115-CC01 | T-00614-1092 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-71-BI-2116-CC01 | T-00614-1093 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-71-BI-2118-CC01 | T-00614-1094 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-71-BI-2119-CC01 | T-00614-1095 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-71-BI-2120-CC01 | T-00614-1096 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-71-BI-2121-CC01 | T-00614-1097 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-71-BI-2122-CC01 | T-00614-1098 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-71-BI-2123-CC01 | T-00614-1099 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/3 | Yes | Not Started
PS5-71-BI-2124-CC01 | T-00614-1100 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-71-BI-2125-CC01 | T-00614-1101 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-71-BI-2306-CC01 | T-00614-1102 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/3 | Yes | Open + RFI Submitted
PS5-71-BI-2307-CC01 | T-00614-1103 | I | PS5-71-15 - Diesel Fuel Storage Tank | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2, C:0/1 | Yes | Open + RFI Submitted
PS5-71-BI-2310-CC01 | T-00614-1104 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-71-BI-2313-CC01 | T-00614-1105 | I | PS5-71-15 - Diesel Fuel Storage Tank | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2, C:0/1 | Yes | Not Started
PS5-71-BI-2314-CC01 | T-00614-1106 | I | PS5-91-01 - Multicore cables & JB | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | Closed | Yes | Accepted | A:0/1, B:2/4, C:0/1 | Yes | Closed + Accepted
PS5-71-BI-2317-CC01 | T-00614-1107 | I | PS5-71-15 - Diesel Fuel Storage Tank | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | Closed | Yes | Accepted | B:1/2, C:0/1 | Yes | Closed + Accepted
PS5-71-IN-0001-CC08 | T-00614-1108 | I | PS5-71-19 - Diesel Separator Module (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-71-IN-0001-CC09 | T-00614-1109 | I | PS5-71-19 - Diesel Separator Module (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-71-IN-0001-CC10 | T-00614-1110 | I | PS5-71-19 - Diesel Separator Module (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-71-IN-0002-CC05 | T-00614-1111 | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-71-IN-0002-CC06 | T-00614-1112 | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-71-IN-0002-CC07 | T-00614-1113 | I | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-71-IN-0003-CC05 | T-00614-1114 | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-71-IN-0003-CC06 | T-00614-1115 | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-71-IN-0003-CC07 | T-00614-1116 | I | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-71-IN-0004A-CC08 | T-00614-1117 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-71-IN-0004A-CC09 | T-00614-1118 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-71-IN-0004A-CC12 | T-00614-1119 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-71-IN-0004B-CC08 | T-00614-1120 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-71-IN-0004B-CC09 | T-00614-1121 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-71-IN-0004B-CC12 | T-00614-1122 | I | PS5-71-07 - Crude Fuel Separation Module (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:0/2 | Yes | Not Started
PS5-71-TIT-2403A-CJ01 | T-00614-1123 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-71-TIT-2403B-CJ01 | T-00614-1124 | I | PS5-71-01 - CFO Storage Tank Feed Heater | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-74-LB-5101-CC01 | T-00614-1125 | I | PS5-74-02 - N2 Generation Skid (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-74-LB-5101-CJ01 | T-00614-1126 | I | PS5-74-02 - N2 Generation Skid (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:2/2 |  | Open + RFI Submitted
PS5-75-BI-1177-CC01 | T-00614-1127 | I | PS5-75-02 - Biocide Injection Package | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-75-BI-1178-CC01 | T-00614-1128 | I | PS5-75-03 - Corrosion Inhibitor Injection Package | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-75-BI-1371-CC01 | T-00614-1129 | I | PS5-75-02 - Biocide Injection Package | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-75-BI-1372-CC01 | T-00614-1130 | I | PS5-75-03 - Corrosion Inhibitor Injection Package | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-75-BI-0001-CC01 | T-00614-1131 | I | PS5-75-01 - DRA Injection Package | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/1 | Yes | Open + RFI Submitted
PS5-75-BI-0002-CC01 | T-00614-1132 | I | PS5-75-01 - DRA Injection Package | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-75-BI-0002-CC02 | T-00614-1133 | I | PS5-75-01 - DRA Injection Package | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/1 | Yes | Open + RFI Submitted
PS5-75-BI-0002-CC03 | T-00614-1134 | I | PS5-75-01 - DRA Injection Package | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:0/2 | Yes | Open + RFI Submitted
PS5-75-MOV-0001-CC01 | T-00614-1135 | I | PS5-28-07 - Open Drains (OD2) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-75-MOV-0001-CC02 | T-00614-1136 | I | PS5-28-07 - Open Drains (OD2) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | A:0/1, B:1/2 | Yes | Open + RFI Submitted
PS5-79-IG-0001-CJ01 | T-00614-1137 | I | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-79-IG-0002-CJ01 | T-00614-1138 | I | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-79-IG-0003-CJ01 | T-00614-1139 | I | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-79-IG-0004-CJ01 | T-00614-1140 | I | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-79-IG-0005-CJ01 | T-00614-1141 | I | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-79-IG-0006-CJ01 | T-00614-1142 | I | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-79-IG-0007-CJ01 | T-00614-1143 | I | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-79-IG-0008-CJ01 | T-00614-1144 | I | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-79-IG-0009-CJ01 | T-00614-1145 | I | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-79-IG-0010-CJ01 | T-00614-1146 | I | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-79-IG-0011-CJ01 | T-00614-1147 | I | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-79-IG-0012-CJ01 | T-00614-1148 | I | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-83-EHO-0001A-CC01 | T-00614-1149 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-83-EHO-0001A-CJ01 | T-00614-1150 | I | PS5-25-02 - Crude Oil Export Pump A | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-83-EHO-0001B-CC01 | T-00614-1151 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-83-EHO-0001B-CJ01 | T-00614-1152 | I | PS5-25-03 - Crude Oil Export Pump B | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-83-EHO-0001C-CC01 | T-00614-1153 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-83-EHO-0001C-CJ01 | T-00614-1154 | I | PS5-25-04 - Crude Oil Export Pump C | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | Yes | Accepted | B:1/2 | Yes | Open + RFI Submitted
PS5-09-BI-2504-CC01 | T-00614-2626 | I | PS5-09-01 - HVAC for Office and Facilities building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-09-LB-0006-CC05 | T-00614-2627 | I | PS5-09-01 - HVAC for Office and Facilities building | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-50-IE-0001-CJ01 | T-00614-2628 | I | PS5-50-01 - Water Well Submersible Pumps (3100) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-50-IE-0002-CJ01 | T-00614-2629 | I | PS5-50-02 - Water Well Submersible Pumps (3200) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | A:0/2, B:0/1 | Yes | Not Started
PS5-74-LB-5101-CC02 | T-00614-2630 | I | PS5-74-02 - N2 Generation Skid (UCP) | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | To be completed | No | No RFI Yet | B:1/2 | Yes | Not Started
PS5-08-11CB-1201-CX01 | T-00618-0217 | T | PS5-08-11 - Corporate LAN (SIE) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-11CB-1501-CX01 | T-00618-0218 | T | PS5-08-11 - Corporate LAN (SIE) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-11CB-1601-CX01 | T-00618-0219 | T | PS5-08-11 - Corporate LAN (SIE) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-11CB-1901-CX01 | T-00618-0220 | T | PS5-08-11 - Corporate LAN (SIE) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12BT-0001-CX01 | T-00618-0221 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12BT-0104-CX01 | T-00618-0222 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12BT-0105-CX01 | T-00618-0223 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12BT-0106-CX01 | T-00618-0224 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12BT-0107-CX01 | T-00618-0225 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-08-12BT-0108-CX01 | T-00618-0226 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-08-12BT-0109-CX01 | T-00618-0227 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12BT-1903-CX01 | T-00618-0228 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12BT-1904-CX01 | T-00618-0229 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-15CP-0001-CX01 | T-00618-0230 | T | PS5-08-15 - Security Data Network (SII SP3 SEC) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-15CP-0002-CX01 | T-00618-0231 | T | PS5-08-15 - Security Data Network (SII SP3 SEC) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-15CP-0003-CX01 | T-00618-0232 | T | PS5-08-15 - Security Data Network (SII SP3 SEC) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-15CP-0004-CX01 | T-00618-0233 | T | PS5-08-15 - Security Data Network (SII SP3 SEC) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-15CP-0005-CX01 | T-00618-0234 | T | PS5-08-15 - Security Data Network (SII SP3 SEC) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-15CP-0005-CX02 | T-00618-0235 | T | PS5-08-15 - Security Data Network (SII SP3 SEC) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-15CP-0006-CX01 | T-00618-0236 | T | PS5-08-15 - Security Data Network (SII SP3 SEC) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-15CP-0007-CX01 | T-00618-0237 | T | PS5-08-15 - Security Data Network (SII SP3 SEC) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-15CP-0008-CX01 | T-00618-0238 | T | PS5-08-15 - Security Data Network (SII SP3 SEC) | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-36SP-0101-CX02 | T-00618-0239 | T | PS5-08-36 - Pipeline FO Cable & EPRS | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-36SP-0102-CX02 | T-00618-0240 | T | PS5-08-36 - Pipeline FO Cable & EPRS | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0131-CX01 | T-00618-0241 | T | PS5-08-52 - Process & Security CCTV | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | B:0/2 | Yes | Not Started
PS5-08-52CM-0132-CX01 | T-00618-0242 | T | PS5-08-52 - Process & Security CCTV | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | A:0/1, B:0/2 | Yes | Not Started
PS5-08-52CM-0133-CX01 | T-00618-0243 | T | PS5-08-52 - Process & Security CCTV | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | B:0/1 | Yes | Not Started
PS5-08-52CM-0135-CX01 | T-00618-0244 | T | PS5-08-52 - Process & Security CCTV | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0136-CX01 | T-00618-0245 | T | PS5-08-52 - Process & Security CCTV | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0138-CX01 | T-00618-0246 | T | PS5-08-52 - Process & Security CCTV | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0139-CX01 | T-00618-0247 | T | PS5-08-52 - Process & Security CCTV | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-83SP-0001-CX01 | T-00618-0248 | T | PS5-08-83 - Perimeter & Pipeline intrusion detection system | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-83SP-0001-CX02 | T-00618-0249 | T | PS5-08-83 - Perimeter & Pipeline intrusion detection system | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85CP-0024-CX01 | T-00618-0250 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85CP-0024-CX02 | T-00618-0251 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85CP-0025-CX01 | T-00618-0252 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85CP-0025-CX02 | T-00618-0253 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX55a - Fiber Optic Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-0001-CR01 | T-00621-2796 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-0001-CR02 | T-00621-2797 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-0002-CR01 | T-00621-2798 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-0002-CR02 | T-00621-2799 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-0003-CR01 | T-00621-2800 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-0003-CR02 | T-00621-2801 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-0004-CR01 | T-00621-2802 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-0004-CR02 | T-00621-2803 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1201-CN01 | T-00621-2804 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1201-CR01 | T-00621-2805 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1201-CR02 | T-00621-2806 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1201-CR03 | T-00621-2807 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1202-CN01 | T-00621-2808 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1202-CR01 | T-00621-2809 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1202-CR02 | T-00621-2810 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1202-CR03 | T-00621-2811 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1203-CJ01 | T-00621-2812 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1203-CJ02 | T-00621-2813 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1203-CN01 | T-00621-2814 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1203-CN02 | T-00621-2815 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1501-CR01 | T-00621-2816 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1501-CR02 | T-00621-2817 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1502-CR01 | T-00621-2818 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1502-CR02 | T-00621-2819 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1503-CJ01 | T-00621-2820 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1503-CJ02 | T-00621-2821 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1503-CN01 | T-00621-2822 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1503-CN02 | T-00621-2823 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1601-CR01 | T-00621-2824 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1601-CR02 | T-00621-2825 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1602-CR01 | T-00621-2826 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1602-CR02 | T-00621-2827 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1901-CR01 | T-00621-2828 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1901-CR02 | T-00621-2829 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Open | B:0/1 | Yes | Open + RFI Submitted
PS5-08-01BT-1902-CR01 | T-00621-2830 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01BT-1902-CR02 | T-00621-2831 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-08-01BT-1903-CR01 | T-00621-2832 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-08-01BT-1904-CR01 | T-00621-2833 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-08-01LS-0101-CR01 | T-00621-2834 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-08-01LS-0102-CR01 | T-00621-2835 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0103-CR01 | T-00621-2836 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0104-CR01 | T-00621-2837 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0105-CR01 | T-00621-2838 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0106-CR01 | T-00621-2839 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0107-CR01 | T-00621-2840 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0108-CR01 | T-00621-2841 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0109-CR01 | T-00621-2842 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0110-CR01 | T-00621-2843 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0110-CR02 | T-00621-2844 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0201-CR01 | T-00621-2845 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-08-01LS-0202-CR01 | T-00621-2846 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0203-CR01 | T-00621-2847 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0204-CR01 | T-00621-2848 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0205-CR01 | T-00621-2849 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0206-CR01 | T-00621-2850 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0207-CR01 | T-00621-2851 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0208-CR01 | T-00621-2852 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0209-CR01 | T-00621-2853 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0210-CR01 | T-00621-2854 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0211-CR01 | T-00621-2855 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0211-CR02 | T-00621-2856 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0301-CR01 | T-00621-2857 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0302-CR01 | T-00621-2858 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/2, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0303-CR01 | T-00621-2859 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0304-CR01 | T-00621-2860 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0305-CR01 | T-00621-2861 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0306-CR01 | T-00621-2862 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0307-CR01 | T-00621-2863 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Open | B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0308-CR01 | T-00621-2864 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0309-CR01 | T-00621-2865 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0310-CR01 | T-00621-2866 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0310-CR02 | T-00621-2867 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0318-CR02 | T-00621-2868 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0401-CR01 | T-00621-2869 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-08-01LS-0402-CR01 | T-00621-2870 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-08-01LS-0403-CR01 | T-00621-2871 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0404-CR01 | T-00621-2872 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Open | B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0405-CR01 | T-00621-2873 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Accepted with Punch | B:0/1 | Yes | Closed + Accepted with Punch
PS5-08-01LS-0406-CR01 | T-00621-2874 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0407-CR01 | T-00621-2875 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0408-CR01 | T-00621-2876 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0409-CR01 | T-00621-2877 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0410-CR01 | T-00621-2878 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0411-CR01 | T-00621-2879 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0411-CR02 | T-00621-2880 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted with Punch | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-01LS-0418-CR02 | T-00621-2881 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0501-CR01 | T-00621-2882 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0502-CR01 | T-00621-2883 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0503-CR01 | T-00621-2884 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0504-CR01 | T-00621-2885 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0505-CR01 | T-00621-2886 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0506-CR01 | T-00621-2887 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0507-CR01 | T-00621-2888 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0508-CR01 | T-00621-2889 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0509-CR01 | T-00621-2890 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0510-CR01 | T-00621-2891 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0511-CR01 | T-00621-2892 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0512-CR01 | T-00621-2893 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0517-CR01 | T-00621-2894 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0518-CR01 | T-00621-2895 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0519-CR01 | T-00621-2896 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0520-CR01 | T-00621-2897 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0521-CR01 | T-00621-2898 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0522-CR01 | T-00621-2899 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0522-CR02 | T-00621-2900 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0523-CR01 | T-00621-2901 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0524-CR01 | T-00621-2902 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0525-CR01 | T-00621-2903 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0526-CR01 | T-00621-2904 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0527-CR01 | T-00621-2905 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0528-CR01 | T-00621-2906 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0529-CR01 | T-00621-2907 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0530-CR01 | T-00621-2908 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0530-CR02 | T-00621-2909 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0601-CR01 | T-00621-2910 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0602-CR01 | T-00621-2911 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0603-CR01 | T-00621-2912 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0604-CR01 | T-00621-2913 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0605-CR01 | T-00621-2914 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0606-CR01 | T-00621-2915 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0607-CR01 | T-00621-2916 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0608-CR01 | T-00621-2917 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0609-CR01 | T-00621-2918 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0610-CR01 | T-00621-2919 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0611-CR01 | T-00621-2920 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0612-CR01 | T-00621-2921 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0617-CR01 | T-00621-2922 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0618-CR01 | T-00621-2923 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0619-CR01 | T-00621-2924 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0620-CR01 | T-00621-2925 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0621-CR01 | T-00621-2926 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0621-CR02 | T-00621-2927 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0622-CR01 | T-00621-2928 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0623-CR01 | T-00621-2929 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0624-CR01 | T-00621-2930 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0625-CR01 | T-00621-2931 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0626-CR01 | T-00621-2932 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0627-CR01 | T-00621-2933 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0628-CR01 | T-00621-2934 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0629-CR01 | T-00621-2935 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0629-CR02 | T-00621-2936 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0701-CR01 | T-00621-2937 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0702-CR01 | T-00621-2938 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0703-CR01 | T-00621-2939 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0704-CR01 | T-00621-2940 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0705-CR01 | T-00621-2941 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0706-CR01 | T-00621-2942 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0707-CR01 | T-00621-2943 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0708-CR01 | T-00621-2944 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0709-CR01 | T-00621-2945 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0710-CR01 | T-00621-2946 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0711-CR01 | T-00621-2947 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0712-CR01 | T-00621-2948 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0713-CR01 | T-00621-2949 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0714-CR01 | T-00621-2950 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0715-CR01 | T-00621-2951 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0716-CR01 | T-00621-2952 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0716-CR02 | T-00621-2953 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0717-CR01 | T-00621-2954 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0718-CR01 | T-00621-2955 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0719-CR01 | T-00621-2956 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0720-CR01 | T-00621-2957 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0721-CR01 | T-00621-2958 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0722-CR01 | T-00621-2959 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0723-CR01 | T-00621-2960 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0724-CR01 | T-00621-2961 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0725-CR01 | T-00621-2962 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0726-CR01 | T-00621-2963 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0727-CR01 | T-00621-2964 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0728-CR01 | T-00621-2965 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0729-CR01 | T-00621-2966 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0730-CR01 | T-00621-2967 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0731-CR01 | T-00621-2968 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0732-CR01 | T-00621-2969 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0733-CR01 | T-00621-2970 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0733-CR02 | T-00621-2971 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0801-CR01 | T-00621-2972 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0802-CR01 | T-00621-2973 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0803-CR01 | T-00621-2974 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0804-CR01 | T-00621-2975 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0805-CR01 | T-00621-2976 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0806-CR01 | T-00621-2977 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0807-CR01 | T-00621-2978 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0808-CR01 | T-00621-2979 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0809-CR01 | T-00621-2980 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0810-CR01 | T-00621-2981 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0811-CR01 | T-00621-2982 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0812-CR01 | T-00621-2983 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0813-CR01 | T-00621-2984 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0814-CR01 | T-00621-2985 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0815-CR01 | T-00621-2986 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0816-CR01 | T-00621-2987 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0816-CR02 | T-00621-2988 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0817-CR01 | T-00621-2989 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0818-CR01 | T-00621-2990 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0819-CR01 | T-00621-2991 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0820-CR01 | T-00621-2992 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0821-CR01 | T-00621-2993 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0822-CR01 | T-00621-2994 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0823-CR01 | T-00621-2995 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0824-CR01 | T-00621-2996 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0825-CR01 | T-00621-2997 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0826-CR01 | T-00621-2998 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0827-CR01 | T-00621-2999 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0828-CR01 | T-00621-3000 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0829-CR01 | T-00621-3001 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0830-CR01 | T-00621-3002 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0831-CR01 | T-00621-3003 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0832-CR01 | T-00621-3004 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0833-CR01 | T-00621-3005 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0834-CR01 | T-00621-3006 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01LS-0834-CR02 | T-00621-3007 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01MP-0001-CC01 | T-00621-3008 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-08-01MP-0001-CC02 | T-00621-3009 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-08-01MP-0001-CC03 | T-00621-3010 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-08-01MP-0001-CC04 | T-00621-3011 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-08-01OC-0001-CJ01 | T-00621-3012 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01OC-0001-CJ02 | T-00621-3013 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01OC-0001-CN01 | T-00621-3014 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01OC-0001-CN02 | T-00621-3015 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01OC-0002-CJ01 | T-00621-3016 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01OC-0002-CJ02 | T-00621-3017 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01OC-0002-CN01 | T-00621-3018 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01OC-0002-CN02 | T-00621-3019 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01PA-1201-CA01 | T-00621-3020 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01PA-1201-CC01 | T-00621-3021 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01PA-1501-CA01 | T-00621-3022 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01PA-1501-CC01 | T-00621-3023 | T | PS5-08-01 - PAGA | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-03TP-0001-CJ01 | T-00621-3024 | T | PS5-08-03 - Telephone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-08-03TP-0001-CJ02 | T-00621-3025 | T | PS5-08-03 - Telephone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-03TP-0002-CJ01 | T-00621-3026 | T | PS5-08-03 - Telephone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-03TP-0002-CJ02 | T-00621-3027 | T | PS5-08-03 - Telephone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-03TP-0003-CJ01 | T-00621-3028 | T | PS5-08-03 - Telephone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-03TP-0003-CJ02 | T-00621-3029 | T | PS5-08-03 - Telephone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-03TP-0004-CJ01 | T-00621-3030 | T | PS5-08-03 - Telephone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-03TP-0004-CJ02 | T-00621-3031 | T | PS5-08-03 - Telephone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-03TP-0101-CJ01 | T-00621-3032 | T | PS5-08-03 - Telephone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-03TP-0101-CJ02 | T-00621-3033 | T | PS5-08-03 - Telephone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-03TP-0102-CJ01 | T-00621-3034 | T | PS5-08-03 - Telephone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-03TP-0102-CJ02 | T-00621-3035 | T | PS5-08-03 - Telephone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-03TP-0103-CJ01 | T-00621-3036 | T | PS5-08-03 - Telephone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Accepted | - |  | Complete
PS5-08-03TP-0103-CJ02 | T-00621-3037 | T | PS5-08-03 - Telephone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-03TP-1903-CJ01 | T-00621-3038 | T | PS5-08-03 - Telephone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-03TP-1903-CJ02 | T-00621-3039 | T | PS5-08-03 - Telephone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-03TP-1904-CJ01 | T-00621-3040 | T | PS5-08-03 - Telephone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-03TP-1904-CJ02 | T-00621-3041 | T | PS5-08-03 - Telephone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-05IN-0001-CA01 | T-00621-3042 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-08-05IN-0002-CA01 | T-00621-3043 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-08-05IN-0003-CA01 | T-00621-3044 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-08-05IN-0004-CA01 | T-00621-3045 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-08-05IN-0005-CA01 | T-00621-3046 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | B:0/1 | Yes | Closed + Open
PS5-08-12AP-0001-CN01 | T-00621-3047 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12AP-0002-CA01 | T-00621-3048 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12AP-0003-CA01 | T-00621-3049 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12AP-0101-CA01 | T-00621-3050 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12AP-0103-CA01 | T-00621-3051 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12AP-0104-CN01 | T-00621-3052 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12AP-0105-CN01 | T-00621-3053 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12AP-0106-CN01 | T-00621-3054 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12AP-0107-CN01 | T-00621-3055 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12AP-0108-CN01 | T-00621-3056 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12AP-0109-CN01 | T-00621-3057 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12AP-1903-CN01 | T-00621-3058 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12AP-1904-CN01 | T-00621-3059 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12BT-0002-CA01 | T-00621-3060 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12BT-0003-CA01 | T-00621-3061 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12BT-0101-CA01 | T-00621-3062 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Open | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-12BT-0103-CA01 | T-00621-3063 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-13CB-1201-CA01 | T-00621-3064 | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-13CB-1201-CA02 | T-00621-3065 | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-13CB-1201-CA03 | T-00621-3066 | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-13CB-1201-CA04 | T-00621-3067 | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-13CB-1201-CA05 | T-00621-3068 | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-13CB-1201-CA06 | T-00621-3069 | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-13CB-1201-CC01 | T-00621-3070 | T | PS5-08-93 - Telecom Monitoring System | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-13CB-1201-CJ01 | T-00621-3071 | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-14CB-1201-CA01 | T-00621-3072 | T | PS5-08-14 - Industrial Data Network (SII SP1) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-14CB-1201-CA02 | T-00621-3073 | T | PS5-08-14 - Industrial Data Network (SII SP1) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-14CB-1201-CA03 | T-00621-3074 | T | PS5-08-14 - Industrial Data Network (SII SP1) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-14CB-1201-CA04 | T-00621-3075 | T | PS5-08-14 - Industrial Data Network (SII SP1) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-14CB-1201-CA05 | T-00621-3076 | T | PS5-08-14 - Industrial Data Network (SII SP1) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-14CB-1201-CA06 | T-00621-3077 | T | PS5-08-14 - Industrial Data Network (SII SP1) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-23AN-0001-CV01 | T-00621-3078 | T | PS5-08-23 - VHF Trunk Radio System | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-23AN-0002-CV01 | T-00621-3079 | T | PS5-08-23 - VHF Trunk Radio System | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-23AN-0003-CV01 | T-00621-3080 | T | PS5-08-23 - VHF Trunk Radio System | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-23AN-0005-CV01 | T-00621-3081 | T | PS5-08-23 - VHF Trunk Radio System | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-23AN-0901-CV01 | T-00621-3082 | T | PS5-08-23 - VHF Trunk Radio System | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-23AN-1201-CV01 | T-00621-3083 | T | PS5-08-23 - VHF Trunk Radio System | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-23AN-1601-CV01 | T-00621-3084 | T | PS5-08-23 - VHF Trunk Radio System | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-23AN-1901-CV01 | T-00621-3085 | T | PS5-08-23 - VHF Trunk Radio System | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-23LA-1201-CV01 | T-00621-3086 | T | PS5-08-23 - VHF Trunk Radio System | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-23LA-1202-CV01 | T-00621-3087 | T | PS5-08-23 - VHF Trunk Radio System | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-23LA-1501-CV01 | T-00621-3088 | T | PS5-08-23 - VHF Trunk Radio System | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-34AN-0001-CV01 | T-00621-3089 | T | PS5-08-34 - Satphone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-34AN-0002-CV01 | T-00621-3090 | T | PS5-08-34 - Satphone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-34LA-1201-CV01 | T-00621-3091 | T | PS5-08-34 - Satphone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-34LA-1501-CV01 | T-00621-3092 | T | PS5-08-34 - Satphone | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-51AN-0001-CV01 | T-00621-3093 | T | PS5-08-51 - Entertainment | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-51AN-0001-CV02 | T-00621-3094 | T | PS5-08-51 - Entertainment | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-51AN-0001-CV03 | T-00621-3095 | T | PS5-08-51 - Entertainment | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-51AN-0001-CV04 | T-00621-3096 | T | PS5-08-51 - Entertainment | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-51LA-1201-CV01 | T-00621-3097 | T | PS5-08-51 - Entertainment | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-51LA-1202-CV01 | T-00621-3098 | T | PS5-08-51 - Entertainment | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-51LA-1203-CV01 | T-00621-3099 | T | PS5-08-51 - Entertainment | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-51LA-1204-CV01 | T-00621-3100 | T | PS5-08-51 - Entertainment | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-51SK-1201-CV01 | T-00621-3101 | T | PS5-08-51 - Entertainment | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-51SK-1202-CV01 | T-00621-3102 | T | PS5-08-51 - Entertainment | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-51SK-1203-CV01 | T-00621-3103 | T | PS5-08-51 - Entertainment | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-51SK-1204-CV01 | T-00621-3104 | T | PS5-08-51 - Entertainment | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-51SK-1205-CV01 | T-00621-3105 | T | PS5-08-51 - Entertainment | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-51SK-1206-CV01 | T-00621-3106 | T | PS5-08-51 - Entertainment | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-51SK-1207-CV01 | T-00621-3107 | T | PS5-08-51 - Entertainment | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-51SK-1208-CV01 | T-00621-3108 | T | PS5-08-51 - Entertainment | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-51SK-1209-CV01 | T-00621-3109 | T | PS5-08-51 - Entertainment | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-51SK-1210-CV01 | T-00621-3110 | T | PS5-08-51 - Entertainment | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0001-CA01 | T-00621-3111 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0002-CA01 | T-00621-3112 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0003-CA01 | T-00621-3113 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0004-CA01 | T-00621-3114 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0005-CA01 | T-00621-3115 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0031-CA01 | T-00621-3116 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0032-CA01 | T-00621-3117 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0033-CA01 | T-00621-3118 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0034-CA01 | T-00621-3119 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0071-CA01 | T-00621-3120 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0072-CA01 | T-00621-3121 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0073-CA01 | T-00621-3122 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0074-CA01 | T-00621-3123 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0075-CA01 | T-00621-3124 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0076-CA01 | T-00621-3125 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0077-CA01 | T-00621-3126 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0078-CA01 | T-00621-3127 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0134-CA01 | T-00621-3128 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0137-CA01 | T-00621-3129 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0140-CA01 | T-00621-3130 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0931-CA01 | T-00621-3131 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-1201-CA01 | T-00621-3132 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-1202-CA01 | T-00621-3133 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-1901-CA01 | T-00621-3134 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-1902-CA01 | T-00621-3135 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-1903-CA01 | T-00621-3136 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52TK-0031-CC01 | T-00621-3137 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52TK-0032-CC01 | T-00621-3138 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52TK-0033-CC01 | T-00621-3139 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52TK-0131-CC01 | T-00621-3140 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52TK-0132-CC01 | T-00621-3141 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52TK-0133-CC01 | T-00621-3142 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52TK-0134-CC01 | T-00621-3143 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52TK-0135-CC01 | T-00621-3144 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52TK-0136-CC01 | T-00621-3145 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52TK-0137-CC01 | T-00621-3146 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52TK-0138-CC01 | T-00621-3147 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52TK-0139-CC01 | T-00621-3148 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52TK-0140-CC01 | T-00621-3149 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52TK-0931-CC01 | T-00621-3150 | T | PS5-08-52 - Process & Security CCTV | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-61BT-0001-CC01 | T-00621-3151 | T | PS5-08-61 - Meteocean | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-61BT-0001-CC02 | T-00621-3152 | T | PS5-08-61 - Meteocean | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-61BT-0001-CN01 | T-00621-3153 | T | PS5-08-61 - Meteocean | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-61BT-0002-CC01 | T-00621-3154 | T | PS5-08-61 - Meteocean | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-61BT-0901-CC01 | T-00621-3155 | T | PS5-08-61 - Meteocean | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-61SN-0003-CZ01 | T-00621-3156 | T | PS5-08-61 - Meteocean | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-61SN-0004-CZ01 | T-00621-3157 | T | PS5-08-61 - Meteocean | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-61SN-0005-CZ01 | T-00621-3158 | T | PS5-08-61 - Meteocean | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-61SN-0005-CZ02 | T-00621-3159 | T | PS5-08-61 - Meteocean | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-61SN-0901-CZ01 | T-00621-3160 | T | PS5-08-61 - Meteocean | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1201-CA01 | T-00621-3161 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1202-CA01 | T-00621-3162 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1203-CA01 | T-00621-3163 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1204-CA01 | T-00621-3164 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1205-CA01 | T-00621-3165 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1206A-CA01 | T-00621-3166 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1206B-CA01 | T-00621-3167 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1207-CA01 | T-00621-3168 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1208-CA01 | T-00621-3169 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1209-CA01 | T-00621-3170 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1210-CA01 | T-00621-3171 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1211-CA01 | T-00621-3172 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1212A-CA01 | T-00621-3173 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1212B-CA01 | T-00621-3174 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1213-CA01 | T-00621-3175 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1214A-CA01 | T-00621-3176 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1214B-CA01 | T-00621-3177 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1214C-CA01 | T-00621-3178 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1214D-CA01 | T-00621-3179 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1215A-CA01 | T-00621-3180 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1215B-CA01 | T-00621-3181 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1216A-CA01 | T-00621-3182 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1216B-CA01 | T-00621-3183 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1217A-CA01 | T-00621-3184 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1217B-CA01 | T-00621-3185 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1218A-CA01 | T-00621-3186 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1218B-CA01 | T-00621-3187 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1219A-CA01 | T-00621-3188 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1219B-CA01 | T-00621-3189 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1220A-CA01 | T-00621-3190 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1220B-CA01 | T-00621-3191 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1221A-CA01 | T-00621-3192 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1221B-CA01 | T-00621-3193 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1222A-CA01 | T-00621-3194 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1222B-CA01 | T-00621-3195 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1223A-CA01 | T-00621-3196 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1223B-CA01 | T-00621-3197 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1224A-CA01 | T-00621-3198 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1224B-CA01 | T-00621-3199 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1225A-CA01 | T-00621-3200 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1225B-CA01 | T-00621-3201 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1226A-CA01 | T-00621-3202 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1226B-CA01 | T-00621-3203 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1227A-CA01 | T-00621-3204 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1227B-CA01 | T-00621-3205 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1228A-CA01 | T-00621-3206 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1228B-CA01 | T-00621-3207 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1229-CA01 | T-00621-3208 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1230A-CA01 | T-00621-3209 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1230B-CA01 | T-00621-3210 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1231-CA01 | T-00621-3211 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1232A-CA01 | T-00621-3212 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1232B-CA01 | T-00621-3213 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1233A-CA01 | T-00621-3214 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1233B-CA01 | T-00621-3215 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1234-CA01 | T-00621-3216 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1235-CA01 | T-00621-3217 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1236A-CA01 | T-00621-3218 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1236B-CA01 | T-00621-3219 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1237-CA01 | T-00621-3220 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1238-CA01 | T-00621-3221 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1239-CA01 | T-00621-3222 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1240-CA01 | T-00621-3223 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1241A-CA01 | T-00621-3224 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1241B-CA01 | T-00621-3225 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1242A-CA01 | T-00621-3226 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1242B-CA01 | T-00621-3227 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1243A-CA01 | T-00621-3228 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1243B-CA01 | T-00621-3229 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1244A-CA01 | T-00621-3230 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1244B-CA01 | T-00621-3231 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1245A-CA01 | T-00621-3232 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1245B-CA01 | T-00621-3233 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1246A-CA01 | T-00621-3234 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1246B-CA01 | T-00621-3235 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1247-CA01 | T-00621-3236 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1248-CA01 | T-00621-3237 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1249A-CA01 | T-00621-3238 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1249B-CA01 | T-00621-3239 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1249C-CA01 | T-00621-3240 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1249D-CA01 | T-00621-3241 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1250A-CA01 | T-00621-3242 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1250B-CA01 | T-00621-3243 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1501A-CA01 | T-00621-3244 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1501B-CA01 | T-00621-3245 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1502A-CA01 | T-00621-3246 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1502B-CA01 | T-00621-3247 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1503A-CA01 | T-00621-3248 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1503B-CA01 | T-00621-3249 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1504A-CA01 | T-00621-3250 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1504B-CA01 | T-00621-3251 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1505-CA01 | T-00621-3252 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1506-CA01 | T-00621-3253 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1507-CA01 | T-00621-3254 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1508-CA01 | T-00621-3255 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1509-CA01 | T-00621-3256 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1510A-CA01 | T-00621-3257 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1510B-CA01 | T-00621-3258 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1511A-CA01 | T-00621-3259 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1511B-CA01 | T-00621-3260 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1512-CA01 | T-00621-3261 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1513-CA01 | T-00621-3262 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1601A-CA01 | T-00621-3263 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1601B-CA01 | T-00621-3264 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1602A-CA01 | T-00621-3265 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1602B-CA01 | T-00621-3266 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1603A-CA01 | T-00621-3267 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1603B-CA01 | T-00621-3268 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1604A-CA01 | T-00621-3269 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1604B-CA01 | T-00621-3270 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1605A-CA01 | T-00621-3271 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1605B-CA01 | T-00621-3272 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1606-CA01 | T-00621-3273 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1607-CA01 | T-00621-3274 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1608-CA01 | T-00621-3275 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1609-CA01 | T-00621-3276 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1610-CA01 | T-00621-3277 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1611-CA01 | T-00621-3278 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1901-CA01 | T-00621-3279 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1903A-CA01 | T-00621-3280 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1903B-CA01 | T-00621-3281 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1904A-CA01 | T-00621-3282 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1904B-CA01 | T-00621-3283 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1905A-CA01 | T-00621-3284 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1905B-CA01 | T-00621-3285 | T | PS5-08-71 - Structured Cabling (CAT6) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BG-1201-CC01 | T-00621-3286 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BG-1202-CC01 | T-00621-3287 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BG-1203-CC01 | T-00621-3288 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BG-1204-CC01 | T-00621-3289 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BG-1501-CC01 | T-00621-3290 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BG-1601-CC01 | T-00621-3291 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BG-1602-CC01 | T-00621-3292 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BG-1603-CC01 | T-00621-3293 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BG-1604-CC01 | T-00621-3294 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BG-1605-CC01 | T-00621-3295 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BG-1901-CC01 | T-00621-3296 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BG-1902-CC01 | T-00621-3297 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BR-0001-CC01 | T-00621-3298 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | A:0/1, B:0/1 | Yes | Closed + Open
PS5-08-85BR-0002-CC01 | T-00621-3299 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | A:0/1, B:0/1 | Yes | Closed + Open
PS5-08-85BR-0003-CC01 | T-00621-3300 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | A:0/1, B:0/1 | Yes | Closed + Open
PS5-08-85BR-0004-CC01 | T-00621-3301 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | A:0/1, B:0/1 | Yes | Closed + Open
PS5-08-85BR-0005-CC01 | T-00621-3302 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | A:0/1, B:0/1 | Yes | Closed + Open
PS5-08-85BR-0006-CC01 | T-00621-3303 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | A:0/1, B:0/1 | Yes | Closed + Open
PS5-08-85BR-0007-CC01 | T-00621-3304 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | A:0/1, B:0/1 | Yes | Closed + Open
PS5-08-85BR-0008-CC01 | T-00621-3305 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | A:0/1, B:0/1 | Yes | Closed + Open
PS5-08-85BR-0009-CC01 | T-00621-3306 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BR-0010-CC01 | T-00621-3307 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BR-0011-CC01 | T-00621-3308 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BR-0012-CC01 | T-00621-3309 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BR-1201-CC01 | T-00621-3310 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BR-1202-CC01 | T-00621-3311 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BR-1203-CC01 | T-00621-3312 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BR-1204-CC01 | T-00621-3313 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BR-1205-CC01 | T-00621-3314 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BR-1206-CC01 | T-00621-3315 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BR-1501-CC01 | T-00621-3316 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BR-1502-CC01 | T-00621-3317 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BR-1601-CC01 | T-00621-3318 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BR-1602-CC01 | T-00621-3319 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BR-1603-CC01 | T-00621-3320 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BR-1604-CC01 | T-00621-3321 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BR-1605-CC01 | T-00621-3322 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BR-1901-CC01 | T-00621-3323 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BR-1902-CC01 | T-00621-3324 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-0001-CJ01 | T-00621-3325 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-0002-CJ01 | T-00621-3326 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-08-85BT-0003-CJ01 | T-00621-3327 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-08-85BT-0004-CJ01 | T-00621-3328 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-0005-CJ01 | T-00621-3329 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-08-85BT-0006-CJ01 | T-00621-3330 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-0007-CJ01 | T-00621-3331 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-08-85BT-0008-CJ01 | T-00621-3332 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-0009-CJ01 | T-00621-3333 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-0010-CJ01 | T-00621-3334 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-08-85BT-0011-CJ01 | T-00621-3335 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-0012-CJ01 | T-00621-3336 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-0013-CJ01 | T-00621-3337 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-08-85BT-0014-CJ01 | T-00621-3338 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-08-85BT-0015-CJ01 | T-00621-3339 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Accepted | - |  | Open + RFI Submitted
PS5-08-85BT-0016-CJ01 | T-00621-3340 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | Yes | Open | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-85BT-0017-CC01 | T-00621-3341 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | A:0/1, B:0/1 | Yes | Closed + Open
PS5-08-85BT-0017-CN01 | T-00621-3342 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-08-85BT-0018-CJ01 | T-00621-3343 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-0019-CC01 | T-00621-3344 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | A:0/1, B:0/1 | Yes | Closed + Open
PS5-08-85BT-0020-CC01 | T-00621-3345 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | A:0/1, B:0/1 | Yes | Closed + Open
PS5-08-85BT-0021-CC01 | T-00621-3346 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | A:0/1, B:0/1 | Yes | Closed + Open
PS5-08-85BT-0022-CC01 | T-00621-3347 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | A:0/1, B:0/1 | Yes | Closed + Open
PS5-08-85BT-0023-CC01 | T-00621-3348 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | A:0/1, B:0/1 | Yes | Closed + Open
PS5-08-85BT-0024-CJ01 | T-00621-3349 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-08-85BT-0025-CJ01 | T-00621-3350 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-08-85BT-0026-CJ01 | T-00621-3351 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | Closed | Yes | Open | B:0/2 | Yes | Closed + Open
PS5-08-85BT-0027-CA01 | T-00621-3352 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-0028-CA01 | T-00621-3353 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1201-CC01 | T-00621-3354 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1201-CN01 | T-00621-3355 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1202-CC01 | T-00621-3356 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1202-CN01 | T-00621-3357 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1203-CC01 | T-00621-3358 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1203-CN01 | T-00621-3359 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1204-CJ01 | T-00621-3360 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1205-CC01 | T-00621-3361 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1205-CN01 | T-00621-3362 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1501-CJ01 | T-00621-3363 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1502-CJ01 | T-00621-3364 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1503-CC01 | T-00621-3365 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1503-CN01 | T-00621-3366 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1601-CJ01 | T-00621-3367 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1602-CJ01 | T-00621-3368 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1603-CC01 | T-00621-3369 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1603-CN01 | T-00621-3370 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1604-CJ01 | T-00621-3371 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1605-CC01 | T-00621-3372 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1605-CN01 | T-00621-3373 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1606-CC01 | T-00621-3374 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1606-CN01 | T-00621-3375 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1607-CC01 | T-00621-3376 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1607-CN01 | T-00621-3377 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1608-CC01 | T-00621-3378 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1608-CN01 | T-00621-3379 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1609-CJ01 | T-00621-3380 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1610-CJ01 | T-00621-3381 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1611-CJ01 | T-00621-3382 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1612-CJ01 | T-00621-3383 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1613-CJ01 | T-00621-3384 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1614-CJ01 | T-00621-3385 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1901-CC01 | T-00621-3386 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1901-CN01 | T-00621-3387 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1902-CC01 | T-00621-3388 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1902-CN01 | T-00621-3389 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1903-CJ01 | T-00621-3390 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1904-CJ01 | T-00621-3391 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1905-CJ01 | T-00621-3392 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1906-CJ01 | T-00621-3393 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1907-CJ01 | T-00621-3394 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1908-CJ01 | T-00621-3395 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-1909-CJ01 | T-00621-3396 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85CP-1201-CA01 | T-00621-3397 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85CP-1202-CA01 | T-00621-3398 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85CP-1501-CA01 | T-00621-3399 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85CP-1601-CA01 | T-00621-3400 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85CP-1901-CA01 | T-00621-3401 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0001-CJ01 | T-00621-3402 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0002-CJ01 | T-00621-3403 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0003-CJ01 | T-00621-3404 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0004-CJ01 | T-00621-3405 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0005-CJ01 | T-00621-3406 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0006-CJ01 | T-00621-3407 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0007-CJ01 | T-00621-3408 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0008-CJ01 | T-00621-3409 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0009-CJ01 | T-00621-3410 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0010-CJ01 | T-00621-3411 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0011-CJ01 | T-00621-3412 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0012-CJ01 | T-00621-3413 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0013-CJ01 | T-00621-3414 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0014-CJ01 | T-00621-3415 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0015-CJ01 | T-00621-3416 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0016-CJ01 | T-00621-3417 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0017-CJ01 | T-00621-3418 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0018-CJ01 | T-00621-3419 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0019-CJ01 | T-00621-3420 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0021-CJ01 | T-00621-3421 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0022-CJ01 | T-00621-3422 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0023-CJ01 | T-00621-3423 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0024-CJ01 | T-00621-3424 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0025-CJ01 | T-00621-3425 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0026-CJ01 | T-00621-3426 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0027-CJ01 | T-00621-3427 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-0028-CJ01 | T-00621-3428 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1201-CJ01 | T-00621-3429 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1202-CJ01 | T-00621-3430 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1203-CJ01 | T-00621-3431 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1204-CJ01 | T-00621-3432 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1205-CJ01 | T-00621-3433 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1206-CJ01 | T-00621-3434 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1207-CJ01 | T-00621-3435 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1501-CJ01 | T-00621-3436 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1502-CJ01 | T-00621-3437 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1503-CJ01 | T-00621-3438 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1601-CJ01 | T-00621-3439 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1602-CJ01 | T-00621-3440 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1603-CJ01 | T-00621-3441 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1604-CJ01 | T-00621-3442 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1605-CJ01 | T-00621-3443 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1606-CJ01 | T-00621-3444 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1607-CJ01 | T-00621-3445 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1608-CJ01 | T-00621-3446 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1609-CJ01 | T-00621-3447 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1610-CJ01 | T-00621-3448 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1611-CJ01 | T-00621-3449 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1612-CJ01 | T-00621-3450 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1613-CJ01 | T-00621-3451 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1614-CJ01 | T-00621-3452 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1615-CJ01 | T-00621-3453 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1616-CJ01 | T-00621-3454 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1617-CJ01 | T-00621-3455 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1618-CJ01 | T-00621-3456 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1901-CJ01 | T-00621-3457 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1902-CJ01 | T-00621-3458 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1903-CJ01 | T-00621-3459 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1904-CJ01 | T-00621-3460 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1905-CJ01 | T-00621-3461 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1906-CJ01 | T-00621-3462 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1907-CJ01 | T-00621-3463 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1908-CJ01 | T-00621-3464 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1909-CJ01 | T-00621-3465 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1910-CJ01 | T-00621-3466 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1911-CJ01 | T-00621-3467 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1912-CJ01 | T-00621-3468 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1913-CJ01 | T-00621-3469 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1914-CJ01 | T-00621-3470 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1915-CJ01 | T-00621-3471 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85DC-1916-CJ01 | T-00621-3472 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85ML-0001-CN01 | T-00621-3473 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85ML-1201-CN01 | T-00621-3474 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85ML-1202-CN01 | T-00621-3475 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85ML-1203-CN01 | T-00621-3476 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85ML-1204-CN01 | T-00621-3477 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85ML-1501-CN01 | T-00621-3478 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85ML-1601-CN01 | T-00621-3479 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85ML-1602-CN01 | T-00621-3480 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85ML-1603-CN01 | T-00621-3481 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85ML-1604-CN01 | T-00621-3482 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85ML-1605-CN01 | T-00621-3483 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85ML-1901-CN01 | T-00621-3484 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85ML-1902-CN01 | T-00621-3485 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85PB-0001-CJ01 | T-00621-3486 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85PB-1201-CJ01 | T-00621-3487 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85PB-1202-CJ01 | T-00621-3488 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85PB-1203-CJ01 | T-00621-3489 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85PB-1204-CJ01 | T-00621-3490 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85PB-1501-CJ01 | T-00621-3491 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85PB-1601-CJ01 | T-00621-3492 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85PB-1602-CJ01 | T-00621-3493 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85PB-1603-CJ01 | T-00621-3494 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85PB-1604-CJ01 | T-00621-3495 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85PB-1605-CJ01 | T-00621-3496 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85PB-1901-CJ01 | T-00621-3497 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85PB-1902-CJ01 | T-00621-3498 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-MBA-0001-CC01 | T-00621-3499 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-MBA-0002-CC01 | T-00621-3500 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-MBA-0003-CC01 | T-00621-3501 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-MGV-0002-CC01 | T-00621-3502 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-82-MTL-0001-CC01 | T-00621-3503 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-13CB-1201-CX01 | T-00621-5357 | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-14CB-1201-CX01 | T-00621-5358 | T | PS5-08-14 - Industrial Data Network (SII SP1) | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85AP-0001-CA01 | T-00621-5359 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85AP-0002-CA01 | T-00621-5360 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85AP-0003-CA01 | T-00621-5361 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85AP-0004-CA01 | T-00621-5362 | T | PS5-08-85 - Access Control, POB & e-Mustering | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01PA-1201-CA01 | T-00624-0767 | T | PS5-08-01 - PAGA | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-01PA-1501-CA01 | T-00624-0768 | T | PS5-08-01 - PAGA | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-05IN-0001-CA01 | T-00624-0769 | T | PS5-08-85 - Access Control, POB & e-Mustering | TIX01a - RJ45 Cable (Both end by EITS) | Started (not Completed) | Yes | Open | B:0/1 | Yes | Open + RFI Submitted
PS5-08-05IN-0002-CA01 | T-00624-0770 | T | PS5-08-85 - Access Control, POB & e-Mustering | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | Yes | Open | B:0/1 | Yes | Open + RFI Submitted
PS5-08-05IN-0003-CA01 | T-00624-0771 | T | PS5-08-85 - Access Control, POB & e-Mustering | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | Yes | Open | B:0/1 | Yes | Open + RFI Submitted
PS5-08-05IN-0004-CA01 | T-00624-0772 | T | PS5-08-85 - Access Control, POB & e-Mustering | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | Yes | Open | B:0/1 | Yes | Open + RFI Submitted
PS5-08-05IN-0005-CA01 | T-00624-0773 | T | PS5-08-85 - Access Control, POB & e-Mustering | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | Yes | Open | B:0/1 | Yes | Open + RFI Submitted
PS5-08-12AP-0002-CA01 | T-00624-0774 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12AP-0003-CA01 | T-00624-0775 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12AP-0101-CA01 | T-00624-0776 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12AP-0103-CA01 | T-00624-0777 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12BT-0002-CA01 | T-00624-0778 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12BT-0003-CA01 | T-00624-0779 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-12BT-0101-CA01 | T-00624-0780 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | TIX01a - RJ45 Cable (Both end by EITS) | Started (not Completed) | Yes | Open | A:0/1, B:0/1 | Yes | Open + RFI Submitted
PS5-08-12BT-0103-CA01 | T-00624-0781 | T | PS5-08-12 - Corporate Wireless LAN (SIE) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-13CB-1201-CA01 | T-00624-0782 | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-13CB-1201-CA02 | T-00624-0783 | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-13CB-1201-CA03 | T-00624-0784 | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-13CB-1201-CA04 | T-00624-0785 | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-13CB-1201-CA05 | T-00624-0786 | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-13CB-1201-CA06 | T-00624-0787 | T | PS5-08-13 - Safety Data Network (SII SP3 SAF) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-14CB-1201-CA01 | T-00624-0788 | T | PS5-08-14 - Industrial Data Network (SII SP1) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-14CB-1201-CA02 | T-00624-0789 | T | PS5-08-14 - Industrial Data Network (SII SP1) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-14CB-1201-CA03 | T-00624-0790 | T | PS5-08-14 - Industrial Data Network (SII SP1) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-14CB-1201-CA04 | T-00624-0791 | T | PS5-08-14 - Industrial Data Network (SII SP1) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-14CB-1201-CA05 | T-00624-0792 | T | PS5-08-14 - Industrial Data Network (SII SP1) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-14CB-1201-CA06 | T-00624-0793 | T | PS5-08-14 - Industrial Data Network (SII SP1) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0001-CA01 | T-00624-0794 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0002-CA01 | T-00624-0795 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0003-CA01 | T-00624-0796 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0004-CA01 | T-00624-0797 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0005-CA01 | T-00624-0798 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0031-CA01 | T-00624-0799 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0032-CA01 | T-00624-0800 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0033-CA01 | T-00624-0801 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0034-CA01 | T-00624-0802 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0071-CA01 | T-00624-0803 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0072-CA01 | T-00624-0804 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0073-CA01 | T-00624-0805 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0074-CA01 | T-00624-0806 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0075-CA01 | T-00624-0807 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0076-CA01 | T-00624-0808 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0077-CA01 | T-00624-0809 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0078-CA01 | T-00624-0810 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0134-CA01 | T-00624-0811 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0137-CA01 | T-00624-0812 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0140-CA01 | T-00624-0813 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-0931-CA01 | T-00624-0814 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-1201-CA01 | T-00624-0815 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-1202-CA01 | T-00624-0816 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-1901-CA01 | T-00624-0817 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-1902-CA01 | T-00624-0818 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-52CM-1903-CA01 | T-00624-0819 | T | PS5-08-52 - Process & Security CCTV | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1201-CA01 | T-00624-0820 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1202-CA01 | T-00624-0821 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1203-CA01 | T-00624-0822 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1204-CA01 | T-00624-0823 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1205-CA01 | T-00624-0824 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1206A-CA01 | T-00624-0825 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1206B-CA01 | T-00624-0826 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1207-CA01 | T-00624-0827 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1208-CA01 | T-00624-0828 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1209-CA01 | T-00624-0829 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1210-CA01 | T-00624-0830 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1211-CA01 | T-00624-0831 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1212A-CA01 | T-00624-0832 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1212B-CA01 | T-00624-0833 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1213-CA01 | T-00624-0834 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1214A-CA01 | T-00624-0835 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1214B-CA01 | T-00624-0836 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1214C-CA01 | T-00624-0837 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1214D-CA01 | T-00624-0838 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1215A-CA01 | T-00624-0839 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1215B-CA01 | T-00624-0840 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1216A-CA01 | T-00624-0841 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1216B-CA01 | T-00624-0842 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1217A-CA01 | T-00624-0843 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1217B-CA01 | T-00624-0844 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1218A-CA01 | T-00624-0845 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1218B-CA01 | T-00624-0846 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1219A-CA01 | T-00624-0847 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1219B-CA01 | T-00624-0848 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1220A-CA01 | T-00624-0849 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1220B-CA01 | T-00624-0850 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1221A-CA01 | T-00624-0851 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1221B-CA01 | T-00624-0852 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1222A-CA01 | T-00624-0853 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1222B-CA01 | T-00624-0854 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1223A-CA01 | T-00624-0855 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1223B-CA01 | T-00624-0856 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1224A-CA01 | T-00624-0857 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1224B-CA01 | T-00624-0858 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1225A-CA01 | T-00624-0859 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1225B-CA01 | T-00624-0860 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1226A-CA01 | T-00624-0861 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1226B-CA01 | T-00624-0862 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1227A-CA01 | T-00624-0863 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1227B-CA01 | T-00624-0864 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1228A-CA01 | T-00624-0865 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1228B-CA01 | T-00624-0866 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1229-CA01 | T-00624-0867 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1230A-CA01 | T-00624-0868 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1230B-CA01 | T-00624-0869 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1231-CA01 | T-00624-0870 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1232A-CA01 | T-00624-0871 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1232B-CA01 | T-00624-0872 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1233A-CA01 | T-00624-0873 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1233B-CA01 | T-00624-0874 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1234-CA01 | T-00624-0875 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1235-CA01 | T-00624-0876 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1236A-CA01 | T-00624-0877 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1236B-CA01 | T-00624-0878 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1237-CA01 | T-00624-0879 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1238-CA01 | T-00624-0880 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1239-CA01 | T-00624-0881 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1240-CA01 | T-00624-0882 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1241A-CA01 | T-00624-0883 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1241B-CA01 | T-00624-0884 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1242A-CA01 | T-00624-0885 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1242B-CA01 | T-00624-0886 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1243A-CA01 | T-00624-0887 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1243B-CA01 | T-00624-0888 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1244A-CA01 | T-00624-0889 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1244B-CA01 | T-00624-0890 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1245A-CA01 | T-00624-0891 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1245B-CA01 | T-00624-0892 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1246A-CA01 | T-00624-0893 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1246B-CA01 | T-00624-0894 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1247-CA01 | T-00624-0895 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1248-CA01 | T-00624-0896 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1249A-CA01 | T-00624-0897 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1249B-CA01 | T-00624-0898 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1249C-CA01 | T-00624-0899 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1249D-CA01 | T-00624-0900 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1250A-CA01 | T-00624-0901 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1250B-CA01 | T-00624-0902 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1501A-CA01 | T-00624-0903 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1501B-CA01 | T-00624-0904 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1502A-CA01 | T-00624-0905 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1502B-CA01 | T-00624-0906 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1503A-CA01 | T-00624-0907 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1503B-CA01 | T-00624-0908 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1504A-CA01 | T-00624-0909 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1504B-CA01 | T-00624-0910 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1505-CA01 | T-00624-0911 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1506-CA01 | T-00624-0912 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1507-CA01 | T-00624-0913 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1508-CA01 | T-00624-0914 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1509-CA01 | T-00624-0915 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1510A-CA01 | T-00624-0916 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1510B-CA01 | T-00624-0917 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1511A-CA01 | T-00624-0918 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1511B-CA01 | T-00624-0919 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1512-CA01 | T-00624-0920 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1513-CA01 | T-00624-0921 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1601A-CA01 | T-00624-0922 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1601B-CA01 | T-00624-0923 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1602A-CA01 | T-00624-0924 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1602B-CA01 | T-00624-0925 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1603A-CA01 | T-00624-0926 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1603B-CA01 | T-00624-0927 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1604A-CA01 | T-00624-0928 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1604B-CA01 | T-00624-0929 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1605A-CA01 | T-00624-0930 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1605B-CA01 | T-00624-0931 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1606-CA01 | T-00624-0932 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1607-CA01 | T-00624-0933 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1608-CA01 | T-00624-0934 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1609-CA01 | T-00624-0935 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1610-CA01 | T-00624-0936 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1611-CA01 | T-00624-0937 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1901-CA01 | T-00624-0938 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1903A-CA01 | T-00624-0939 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1903B-CA01 | T-00624-0940 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1904A-CA01 | T-00624-0941 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1904B-CA01 | T-00624-0942 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1905A-CA01 | T-00624-0943 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-71SK-1905B-CA01 | T-00624-0944 | T | PS5-08-71 - Structured Cabling (CAT6) | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-0027-CA01 | T-00624-0945 | T | PS5-08-85 - Access Control, POB & e-Mustering | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85BT-0028-CA01 | T-00624-0946 | T | PS5-08-85 - Access Control, POB & e-Mustering | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85CP-1201-CA01 | T-00624-0947 | T | PS5-08-85 - Access Control, POB & e-Mustering | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85CP-1202-CA01 | T-00624-0948 | T | PS5-08-85 - Access Control, POB & e-Mustering | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85CP-1501-CA01 | T-00624-0949 | T | PS5-08-85 - Access Control, POB & e-Mustering | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85CP-1601-CA01 | T-00624-0950 | T | PS5-08-85 - Access Control, POB & e-Mustering | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started
PS5-08-85CP-1901-CA01 | T-00624-0951 | T | PS5-08-85 - Access Control, POB & e-Mustering | TIX01a - RJ45 Cable (Both end by EITS) | To be completed | No | No RFI Yet | - |  | Not Started

## By Variation
Variation | Count
Closed + Accepted | 144
Closed + Accepted with Punch | 493
Closed + Hold by EACOP | 26
Closed + Open | 315
Closed + Other | 23
Closed but No RFI | 430
Complete | 384
Not Started | 5706
Open + RFI Submitted | 1706
Submitted No RFI | 17

## By Discipline
Discipline | Closed + Accepted | Closed + Accepted with Punch | Closed + Hold by EACOP | Closed + Open | Closed + Other | Closed but No RFI | Complete | Not Started | Open + RFI Submitted | Submitted No RFI | Total
E | 124 | 334 | 26 | 46 | 23 | 376 | 266 | 1574 | 783 | 17 | 3569
I | 20 | 156 | 0 | 234 | 0 | 54 | 117 | 3133 | 883 | 0 | 4597
T | 0 | 3 | 0 | 35 | 0 | 0 | 1 | 999 | 40 | 0 | 1078

## By Subsystem
Subsystem | Closed + Accepted | Closed + Accepted with Punch | Closed + Hold by EACOP | Closed + Open | Closed + Other | Closed but No RFI | Complete | Not Started | Open + RFI Submitted | Submitted No RFI | Total
PS5-09-03 - HVAC for Generator Building | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 982 | 6 | 0 | 1004
PS5-08-71 - Structured Cabling (CAT6) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 250
PS5-08-85 - Access Control, POB & e-Mustering | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 212 | 12 | 0 | 249
PS5-08-01 - PAGA | 0 | 3 | 0 | 9 | 0 | 0 | 0 | 192 | 26 | 0 | 230
PS5-25-02 - Crude Oil Export Pump A | 6 | 22 | 0 | 6 | 0 | 1 | 46 | 51 | 58 | 0 | 190
PS5-25-04 - Crude Oil Export Pump C | 6 | 15 | 0 | 0 | 0 | 1 | 46 | 74 | 45 | 0 | 187
PS5-25-03 - Crude Oil Export Pump B | 6 | 18 | 0 | 7 | 0 | 1 | 46 | 55 | 54 | 0 | 187
PS5-60-10 - Power Generation Package D | 0 | 7 | 0 | 4 | 0 | 31 | 14 | 90 | 22 | 0 | 168
PS5-60-16 - Power Generation Package F | 0 | 5 | 1 | 10 | 0 | 27 | 14 | 83 | 28 | 0 | 168
PS5-60-01 - Power Generation Package A | 10 | 17 | 0 | 3 | 1 | 19 | 14 | 58 | 40 | 0 | 162
PS5-03-01 - FZ-01 - Process Area | 4 | 17 | 0 | 0 | 0 | 0 | 17 | 61 | 52 | 0 | 151
PS5-60-07 - Power Generation Package C | 0 | 9 | 1 | 4 | 0 | 21 | 14 | 67 | 25 | 0 | 141
PS5-60-13 - Power Generation Package E | 0 | 6 | 2 | 4 | 0 | 20 | 14 | 70 | 25 | 0 | 141
PS5-60-19 - Power Generation Package G | 0 | 6 | 0 | 4 | 0 | 26 | 14 | 72 | 19 | 0 | 141
PS5-60-04 - Power Generation Package B | 13 | 14 | 0 | 3 | 1 | 9 | 14 | 43 | 42 | 0 | 139
PS5-91-01 - Multicore cables & JB | 13 | 16 | 0 | 0 | 0 | 1 | 48 | 3 | 47 | 0 | 128
PS5-03-25 - FZ - Workshop & Warehouse | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 120
PS5-03-24 - FZ - Office and Facilities Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 120
PS5-60-22 - Power Gen Master UCP | 1 | 3 | 0 | 3 | 0 | 18 | 0 | 74 | 20 | 0 | 119
PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5- | 0 | 48 | 0 | 0 | 2 | 7 | 0 | 15 | 44 | 0 | 116
PS5-71-07 - Crude Fuel Separation Module (UCP) | 0 | 2 | 2 | 5 | 0 | 2 | 0 | 84 | 17 | 0 | 112
PS5-05-01 - Emergency Diesel Generator Package | 11 | 24 | 0 | 0 | 0 | 0 | 1 | 3 | 67 | 0 | 106
PS5-25-01 - Export Pipeline Pig Receiver | 0 | 15 | 0 | 10 | 0 | 0 | 1 | 46 | 27 | 0 | 99
PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5- | 3 | 41 | 0 | 0 | 0 | 4 | 0 | 10 | 36 | 0 | 94
PS5-71-12 - CFO Service Tank | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 65 | 15 | 0 | 93
PS5-25-07 - Export Pipeline Pig Launcher | 0 | 9 | 0 | 5 | 0 | 0 | 1 | 45 | 25 | 0 | 85
PS5-01-11 - Inergen for Power Gen Building | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 54 | 25 | 0 | 81
PS5-71-04 - CFO Storage Tank | 0 | 11 | 0 | 0 | 0 | 0 | 1 | 54 | 14 | 0 | 80
PS5-03-14 - FZ-14 - Power Generation Building - Switchgear R | 0 | 0 | 0 | 13 | 0 | 2 | 0 | 46 | 15 | 0 | 76
PS5-08-52 - Process & Security CCTV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 1 | 0 | 74
PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | 0 | 0 | 2 | 0 | 4 | 0 | 12 | 15 | 41 | 0 | 74
PS5-63-01 - Electrical Earthing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 16 | 68
PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | 41 | 3 | 0 | 0 | 1 | 0 | 12 | 0 | 8 | 0 | 65
PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 61 | 1 | 0 | 64
PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 46 | 16 | 0 | 64
PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 44 | 17 | 0 | 62
PS5-03-06 - FZ-06 - Transformer Area | 1 | 1 | 0 | 3 | 0 | 3 | 7 | 29 | 18 | 0 | 62
PS5-71-01 - CFO Storage Tank Feed Heater | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 44 | 14 | 0 | 62
PS5-06-02 - AC UPS - Power Generator Building | 0 | 0 | 0 | 17 | 1 | 0 | 0 | 19 | 21 | 0 | 58
PS5-71-08 - CFO Pre-Pressure Modules | 0 | 7 | 0 | 1 | 0 | 12 | 0 | 28 | 8 | 0 | 56
PS5-05-02 - Emergency Diesel Generator Package (UCP) | 0 | 13 | 0 | 0 | 0 | 3 | 0 | 5 | 32 | 0 | 53
PS5-28-17 - Reinjection Pump | 1 | 7 | 0 | 4 | 0 | 1 | 1 | 22 | 17 | 0 | 53
PS5-60-11 - Power Gen Package D (UCP) | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 36 | 12 | 0 | 52
PS5-60-05 - Power Gen Package B (UCP) | 0 | 0 | 0 | 4 | 0 | 7 | 0 | 29 | 12 | 0 | 52
PS5-60-14 - Power Gen Package E (UCP) | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 32 | 14 | 0 | 52
PS5-01-01 - Fire Water Jockey Pump A/B | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 40 | 10 | 0 | 52
PS5-60-17 - Power Gen Package F (UCP) | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 37 | 10 | 0 | 52
PS5-28-04 - Closed Drain Drum and Pump 02 | 0 | 1 | 0 | 6 | 0 | 0 | 1 | 30 | 14 | 0 | 52
PS5-60-08 - Power Gen Package C (UCP) | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 36 | 12 | 0 | 52
PS5-60-20 - Power Gen Package G (UCP) | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 34 | 11 | 0 | 50
PS5-01-10 - Water Mist Package | 0 | 2 | 0 | 0 | 0 | 1 | 3 | 21 | 22 | 0 | 49
PS5-03-08 - FZ-08 - Utilities - Power Generation Area - Exte | 0 | 3 | 0 | 3 | 0 | 0 | 1 | 28 | 12 | 0 | 47
PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 31 | 0 | 0 | 46
PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 36 | 0 | 0 | 46
PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2 | 0 | 0 | 0 | 0 | 14 | 0 | 28 | 2 | 0 | 46
PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 0 | 0 | 0 | 13 | 3 | 2 | 0 | 12 | 16 | 0 | 46
PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 0 | 1 | 0 | 13 | 3 | 1 | 0 | 11 | 17 | 0 | 46
PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 38 | 0 | 0 | 46
PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 39 | 0 | 0 | 46
PS5-28-03 - Closed Drain Drum and Pump 01 | 0 | 3 | 0 | 5 | 0 | 0 | 0 | 25 | 12 | 0 | 45
PS5-71-05 - CFO Transfer Pump A/B | 2 | 3 | 0 | 0 | 0 | 0 | 4 | 27 | 9 | 0 | 45
PS5-60-02 - Power Gen Package A (UCP) | 0 | 0 | 0 | 4 | 0 | 7 | 0 | 19 | 14 | 0 | 44
PS5-25-05 - Crude Oil Export Pumps Bypass | 0 | 7 | 1 | 2 | 0 | 1 | 0 | 18 | 10 | 0 | 39
PS5-71-19 - Diesel Separator Module (UCP) | 0 | 1 | 0 | 7 | 0 | 2 | 0 | 16 | 11 | 0 | 37
PS5-71-13 - CFO Service Pump A/B | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 21 | 9 | 0 | 37
PS5-25-06 - Crude Oil Export Pumps Discharge | 0 | 2 | 0 | 5 | 0 | 1 | 0 | 21 | 8 | 0 | 37
PS5-71-22 - Diesel Fuel Pre Pressure Module | 0 | 3 | 0 | 3 | 0 | 8 | 0 | 16 | 6 | 0 | 36
PS5-71-06 - Crude Fuel Separation Module | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 34 | 0 | 0 | 36
PS5-71-21 - Diesel Transfer Pump A/B | 2 | 1 | 0 | 4 | 0 | 0 | 1 | 19 | 8 | 0 | 35
PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 2 | 0 | 35
PS5-71-15 - Diesel Fuel Storage Tank | 1 | 2 | 0 | 6 | 0 | 0 | 4 | 12 | 10 | 0 | 35
PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 30 | 2 | 0 | 35
PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 28 | 2 | 0 | 34
PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 24 | 4 | 0 | 34
PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | 0 | 3 | 0 | 2 | 0 | 4 | 0 | 20 | 5 | 0 | 34
PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | 0 | 3 | 0 | 4 | 0 | 1 | 0 | 19 | 7 | 0 | 34
PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 26 | 4 | 0 | 34
PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 24 | 4 | 0 | 34
PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 23 | 4 | 0 | 34
PS5-71-20 - Diesel Fuel Day Tank | 0 | 2 | 0 | 7 | 0 | 3 | 0 | 13 | 9 | 0 | 34
PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 24 | 4 | 0 | 34
PS5-08-12 - Corporate Wireless LAN (SIE) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 2 | 0 | 34
PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps A | 0 | 2 | 0 | 2 | 0 | 0 | 7 | 11 | 12 | 0 | 34
PS5-01-02 - Fire Water Pump A | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 22 | 10 | 0 | 33
PS5-28-08 - Open Drain Sump and Pumps | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 20 | 10 | 0 | 32
PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - E | 0 | 2 | 0 | 0 | 0 | 0 | 6 | 5 | 19 | 0 | 32
PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - E | 0 | 2 | 0 | 0 | 0 | 0 | 6 | 6 | 18 | 0 | 32
PS5-71-18 - Diesel Separator Module | 0 | 0 | 0 | 5 | 0 | 1 | 0 | 20 | 5 | 0 | 31
PS5-28-15 - Seal Oil Drain Drum & Pump C | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 26 | 3 | 0 | 30
PS5-28-13 - Seal Oil Drain Drum & Pump A | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 18 | 8 | 0 | 30
PS5-28-14 - Seal Oil Drain Drum & Pump B | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 18 | 8 | 0 | 30
PS5-01-03 - Fire Water Pump B | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 22 | 6 | 0 | 29
PS5-61-08 - Electrical Control System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 20 | 0 | 28
PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 1 | 0 | 0 | 3 | 0 | 2 | 0 | 8 | 11 | 0 | 25
PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & D | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 20 | 1 | 0 | 24
PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & D | 0 | 0 | 1 | 0 | 0 | 5 | 0 | 17 | 1 | 0 | 24
PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & D | 0 | 5 | 1 | 0 | 0 | 1 | 0 | 11 | 6 | 0 | 24
PS5-28-06 - Relief Drum and Pump | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 18 | 4 | 0 | 24
PS5-60-75 - Engine F Cooling system | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 21 | 1 | 0 | 24
PS5-60-73 - Engine D Cooling system | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 18 | 2 | 0 | 24
PS5-60-76 - Engine G Cooling system | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 21 | 1 | 0 | 24
PS5-60-72 - Engine C Cooling system | 0 | 0 | 1 | 0 | 0 | 4 | 0 | 18 | 1 | 0 | 24
PS5-60-71 - Engine B Cooling system | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 19 | 0 | 0 | 24
PS5-60-70 - Engine A Cooling system | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 19 | 0 | 0 | 24
PS5-60-74 - Engine E Cooling system | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 21 | 1 | 0 | 24
PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & D | 0 | 0 | 4 | 0 | 0 | 3 | 0 | 13 | 4 | 0 | 24
PS5-03-07 - FZ-07 - Pretreatment Area | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 21 | 1 | 0 | 23
PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & D | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 12 | 4 | 0 | 22
PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & D | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 16 | 0 | 0 | 22
PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & D | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 21 | 0 | 0 | 22
PS5-71-09 - CFO Pre-Pressure Modules (UCP) | 0 | 0 | 0 | 2 | 0 | 3 | 0 | 12 | 4 | 0 | 21
PS5-08-03 - Telephone | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 16 | 0 | 0 | 18
PS5-08-51 - Entertainment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 18
PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 0 | 1 | 0 | 3 | 0 | 2 | 0 | 8 | 4 | 0 | 18
PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | 0 | 2 | 0 | 3 | 0 | 2 | 0 | 6 | 5 | 0 | 18
PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | 0 | 2 | 0 | 3 | 0 | 3 | 0 | 5 | 5 | 0 | 18
PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | 0 | 2 | 0 | 3 | 0 | 2 | 0 | 6 | 5 | 0 | 18
PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | 0 | 2 | 0 | 3 | 0 | 2 | 0 | 6 | 5 | 0 | 18
PS5-61-04 - 0.4kV Switchboard Office & Facilities Building ( | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 18
PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | 0 | 2 | 0 | 3 | 0 | 2 | 0 | 6 | 5 | 0 | 18
PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 0 | 1 | 0 | 3 | 0 | 2 | 0 | 8 | 4 | 0 | 18
PS5-71-16 - Diesel Fuel Supply Pump A/B | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 2 | 0 | 18
PS5-01-05 - Foam Skid | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 7 | 6 | 0 | 16
PS5-03-03 - FZ-03 - Buildings Area | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 1 | 0 | 16
PS5-53-01 - Utility Water / Storage Tank | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 0 | 16
PS5-01-07 - Fire Water Ring Main & Distribution | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 6 | 8 | 0 | 16
PS5-53-02 - Water Distribution Pump A/B | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 2 | 0 | 15
PS5-08-13 - Safety Data Network (SII SP3 SAF) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 14
PS5-75-01 - DRA Injection Package | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 0 | 14
PS5-71-17 - Diesel Fuel Distribution Header | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 7 | 3 | 0 | 13
PS5-08-14 - Industrial Data Network (SII SP1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 13
PS5-60-36 - Injector Tip Cooling Module B | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 5 | 2 | 0 | 12
PS5-60-24 - Cooling Water Tank & Pump | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 8 | 3 | 0 | 12
PS5-50-01 - Water Well Submersible Pumps (3100) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 3 | 0 | 12
PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 8 | 3 | 0 | 12
PS5-08-11 - Corporate LAN (SIE) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 11 | 0 | 0 | 12
PS5-50-02 - Water Well Submersible Pumps (3200) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 3 | 0 | 12
PS5-03-13 - FZ-13 - Power Generation Building - Instrument A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 12
PS5-60-35 - Injector Tip Cooling Module A | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 5 | 2 | 0 | 12
PS5-60-26 - Instrument Air Compressor Skid | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 2 | 5 | 0 | 12
PS5-60-39 - Injector Tip Cooling Module E | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 8 | 1 | 0 | 12
PS5-60-40 - Injector Tip Cooling Module F | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 8 | 1 | 0 | 12
PS5-60-41 - Injector Tip Cooling Module G | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 7 | 2 | 0 | 12
PS5-60-37 - Injector Tip Cooling Module C | 0 | 0 | 3 | 0 | 0 | 2 | 0 | 4 | 3 | 0 | 12
PS5-60-38 - Injector Tip Cooling Module D | 2 | 1 | 0 | 0 | 0 | 2 | 0 | 4 | 3 | 0 | 12
PS5-08-23 - VHF Trunk Radio System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 11
PS5-03-22 - FZ-G1 - Guard House | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0 | 11
PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 2 | 0 | 11
PS5-79-04 - Electrical Heat Tracing Transformer/Distribution | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 10
PS5-79-11 - Electrical Heat Tracing Transformer/Distribution | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 10
PS5-79-12 - Electrical Heat Tracing Transformer/Distribution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 2 | 0 | 10
PS5-79-02 - Electrical Heat Tracing Transformer/Distribution | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 0 | 10
PS5-79-10 - Electrical Heat Tracing Transformer/Distribution | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 10
PS5-79-06 - Electrical Heat Tracing Transformer/Distribution | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 10
PS5-79-03 - Electrical Heat Tracing Transformer/Distribution | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 10
PS5-79-09 - Electrical Heat Tracing Transformer/Distribution | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 10
PS5-79-05 - Electrical Heat Tracing Transformer/Distribution | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 10
PS5-79-01 - Electrical Heat Tracing Transformer/Distribution | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 10
PS5-79-07 - Electrical Heat Tracing Transformer/Distribution | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 10
PS5-79-08 - Electrical Heat Tracing Transformer/Distribution | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 10
PS5-60-27 - Compressed Air Starting Skid | 0 | 0 | 0 | 1 | 3 | 1 | 0 | 1 | 4 | 0 | 10
PS5-09-01 - HVAC for Office and Facilities building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10
PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 4 | 0 | 10
PS5-08-61 - Meteocean | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10
PS5-04-02 - Office Building SIS/FGS System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9
PS5-03-15 - FZ-15 - Power Generation Building - Generator Ro | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9
PS5-53-04 - Water Treatment Purification Package | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 0 | 9
PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9
PS5-03-18 - FZ-18 - Power Generation Building - Generator Ro | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9
PS5-03-21 - FZ-21 - Power Generation Building - Air Handling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9
PS5-03-16 - FZ-16 - Power Generation Building - Generator Ro | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9
PS5-28-10 - Oil Skimmer Package | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 | 0 | 9
PS5-08-15 - Security Data Network (SII SP3 SEC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9
PS5-03-17 - FZ-17 - Power Generation Building - Generator Ro | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9
PS5-74-02 - N2 Generation Skid (UCP) | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 0 | 9
PS5-09-04 - HVAC for Workshop & Warehouse | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 0 | 8
PS5-50-03 - Water Pre-Treatment Package | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 0 | 8
PS5-78-01 - Lifting and handling equipment | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 5 | 0 | 0 | 8
PS5-75-03 - Corrosion Inhibitor Injection Package | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 8
PS5-75-02 - Biocide Injection Package | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 8
PS5-63-05 - Electrical Earthing - Guard Hut A & B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8
PS5-74-04 - Nitrogen Distribution Header | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 0 | 8
PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 1 | 0 | 6
PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 1 | 0 | 6
PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 1 | 0 | 6
PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 0 | 6
PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 1 | 0 | 6
PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3 | 1 | 0 | 6
PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3 | 1 | 0 | 6
PS5-71-02 - CFO Allocation Metering Package | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 5
PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 5
PS5-28-07 - Open Drains (OD2) | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 5
PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 5
PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61- | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 1 | 0 | 5
PS5-74-01 - N2 Generation Skid | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 5
PS5-62-07 - CRO Generator Electrical Building Emergency Ligh | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 5
PS5-62-06 - CRO Generator Building Emergency Lighting DB - | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 5
PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-001 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4
PS5-61-10 - Outdoor Valves Distribution Board - PS5-61-IG-00 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4
PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4
PS5-62-04 - Outdoor Emergency Lighting DB - PS5-05-IG-0006 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4
PS5-09-02 - HVAC for Guard House | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4
PS5-28-11 - Open Drain Interceptor | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4
PS5-60-28 - Air Receiver A & Air Regulator A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4
PS5-60-29 - Air Receiver B & Air Regulator B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4
PS5-02-01 - Miscellaneous Safety equipment | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 4
PS5-08-34 - Satphone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4
PS5-60-32 - Air Receiver E & Air Regulator E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4
PS5-60-30 - Air Receiver C & Air Regulator C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4
PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4
PS5-63-03 - Electrical Earthing - Generator Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4
PS5-61-11 - Outdoor Valves Distribution Board - PS5-61-IG-00 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4
PS5-62-03 - Outdoor Emergency Lighting DB - PS5-05-IG-0004 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4
PS5-63-07 - Electrical Earthing - Workshop & Warehouse | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4
PS5-63-02 - Electrical Earthing - Office and Facilities buil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4
PS5-63-06 - Electrical Earthing - Guard House | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4
PS5-60-31 - Air Receiver D & Air Regulator D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4
PS5-60-34 - Air Receiver G & Air Regulator G | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 4
PS5-60-33 - Air Receiver F & Air Regulator F | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 4
PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4
PS5-99-04 - Area Completion for Process area | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3
PS5-82-02 - Sewage Treatment Plant Package | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 3
PS5-74-03 - Nitrogen Receiver | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3
PS5-06-04 - AC UPS - Guard House | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
PS5-08-36 - Pipeline FO Cable & EPRS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
PS5-99-01 - Area Completion for Building area | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
PS5-53-03 - Water Softener Package | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
PS5-28-16 - LP Relief Header | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
PS5-08-83 - Perimeter & Pipeline intrusion detection system | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
PS5-28-05 - HP Relief Header | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
PS5-82-03 - Sewage Treatment Plant Package (UCP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2
PS5-82-05 - Office and Facilities building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
PS5-84-01 - Generator Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
PS5-82-06 - Guard House Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
PS5-08-93 - Telecom Monitoring System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
PS5-83-01 - EITS Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
PS5-99-02 - Area Completion for Utility area | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
PS5-99-03 - Area Completion for Power Distribution area | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
PS5-99-05 - Area Completion for CFO area | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
PS5-99-06 - Area Completion for Power Generation area | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1

## Construction vs RFI
Construction | No | Yes | Total
Closed | 430 | 1385 | 1815
Completed (not Closed) | 0 | 6 | 6
Started (not Completed) | 7 | 9 | 16
Submitted | 17 | 0 | 17
To be completed | 5699 | 1691 | 7390