## CHECKSHEET
Pre-commissioning Preliminary Check List - Walkdown (PS4/PS5)
Sr. no | Item / Activity | Check Point for attendance at site | Power Gen | PS-4 Sub-system No. | PS-5 Sub-system No. | Comments
1 | Injector tip Cooling Module (Repeated for All Skids) |  | PG | PS4-60-35/36/37/38/39/40/41 | PS5-60-35/36/37/38/39/40/41 |  | Milestone B | Milestone D | Milestone E
2 | Alternator bearing cooling skid (Repeated for All Skids) |  | PG | PS4-60-01/04/07/10/13/16/19 | PS5-60-01/04/07/10/13/16/19 |  | Milestone B | Milestone D | Milestone E
3 | Lube oil separator module (Repeated for All Skids) |  | PG | PS4-60-49/50/51/52/53/54/55 | PS5-60-49/50/51/52/53/54/55 |  | Milestone B | Milestone D | Milestone E
4 | Oil mist eliminator (Vent Purifier) (Repeated for All Units) |  | PG | PS4-60-42/43/44/45/46/47/48 | PS5-60-42/43/44/45/46/47/48 |  | Milestone B | Milestone D | Milestone E
5 | External Cooler Skid (Repeated for All Skids) |  | PG | PS4-60-35/36/37/38/39/40/41 | PS5-60-35/36/37/38/39/40/41 |  | Milestone B | Milestone D | Milestone E
6 | Engine Cooling Radiator (Repeated for All Skids) |  | PG | PS4-60-70/71/72/73/74/75/76 | PS5-60-70/71/72/73/74/75/76 |  | Milestone B | Milestone D | Milestone E
7 | Cooling water expansion Tank(s) (Repeated for All Skids) |  | PG | PS4-60-70/71/72/73/74/75/76 | PS5-60-70/71/72/73/74/75/76 |  | Milestone B | Milestone D | Milestone E
8 | Fuel Conditioning module unit (FCU) (Repeated for All Skids) |  | PG | PS4-60-56/58/60/62/64/66/68 | PS5-60-56/58/60/62/64/66/68 |  | Milestone B | Milestone D | Milestone E
9 | Starting Compressed air skid |  | PG | PS4-60-27 | PS5-60-27 |  | Milestone B
10 | Starting Compressed air Bottles |  | PG | PS4-60-27 | PS5-60-27 |  | Milestone B
11 | Instrument Air Compressor Skid |  | PG | PS4-60-26 | PS5-60-26 |  | Milestone B
12 | Crude separator module (A/B) |  | PG | PS4-71-06 | PS5-71-06 |  | Milestone H
13 | Diesel oil separator module |  | PG | PS4-71-22 | PS5-71-22 |  | Milestone B
14 | Crude pre-pressure module |  | PG | PS4-71-08 | PS5-71-08 |  | Milestone H
15 | Diesel oil pre-pressure module |  | PG | PS4-71-22 | PS5-71-22 |  | Milestone B
16 | Self supporting exhaust Chimney (repeated) |  | PG | PS4-60-35/36/37/38/39/40/41 | PS5-60-35/36/37/38/39/40/41 |  | Milestone B | Milestone D | Milestone E
17 | Exhaust gas silencer (Repeated) |  | PG | PS4-60-35/36/37/38/39/40/41 | PS5-60-35/36/37/38/39/40/41 |  | Milestone B | Milestone D | Milestone E
18 | Exhaust Line ducting (Repeated) |  | PG | PS4-60-35/36/37/38/39/40/41 | PS5-60-35/36/37/38/39/40/41 |  | Milestone B | Milestone D | Milestone E
19 | Air Intake ducting (Repeated) |  | PG | PS4-60-35/36/37/38/39/40/41 | PS5-60-35/36/37/38/39/40/41 |  | Milestone B | Milestone D | Milestone E
20 | Engine MCC - CRO Generator set |  | PG | PS4-60-03/06/09/12/15/18/21 | PS5-60-03/06/09/12/15/18/21 |  | Milestone B | Milestone D | Milestone E
21 | Power Generation Common/Treatment MCC |  | PG | PS4-60-22 | PS5-60-22 |  | Milestone B
22 | Local display panel LDP Generator set |  | PG | PS4-60-01/04/07/10/13/16/19 | PS5-60-01/04/07/10/13/16/19 |  | Milestone B | Milestone D | Milestone E
23 | GCP Generator Set |  | PG | PS4-60-02/05/08/11/14/17/20 | PS5-60-02/05/08/11/14/17/20 |  | Milestone B | Milestone D | Milestone E
24 | Master Control panel |  | PG | PS4-60-22 | PS5-60-22 |  | Milestone B
25 | VTMS Vibration and temperature monitoring System |  | PG | PS4-60-01/10/16 | PS5-60-01/10/16 |  | Milestone B | Milestone D
26 | RAP remote access panel |  | PG | PS4-60-22 | PS5-60-22 |  | Milestone B
27 | Gas detection panel |  | PG | PS4-03-14 | PS5-03-14 |  | Milestone E
28 | Power Step-up Transformer (PS4/PS5 only) |  | PG | PS4-60-01/04/07/10/13/16/19 | PS5-60-01/04/07/10/13/16/19 |  | Milestone B | Milestone D | Milestone E
29 | Crude oil CFO- Separator Control Panel |  | PG | PS4-71-09 | PS5-71-09 |  | Milestone H
30 | Diesel Fuel oil DFO Control Panels |  | PG | PS4-71-23 | PS5-71-23 |  | Milestone B
31 | FCU Control Panel |  | PG | PS4-60-57/59/61/63/65/67/69 | PS5-60-57/59/61/63/65/67/69 |  | Milestone B | Milestone D | Milestone E
32 | NGRs (PS4/PS5 only) |  | PG | PS4-60-01/04/07/10/13/16/19 | PS5-60-01/04/07/10/13/16/19 |  | Milestone B | Milestone D | Milestone E
PS5-05-01,02

## ITR SUMMARY
Responsible Company : CPP AGI-VENDOR-MANTRAC CHECKLIST SUMMERY
Discipline | Total | Closed | % | Open |  | CUT OFF DATE-03-JULY-2026
[6 empty] | 27 June | 28 June | 29 June | 30 June | 1 July | 2 July | 3 July | TOTAL | MONTH | TOTAL NO SS | RFC SIGNED | TOTAL ITRS | TOTAL CLOSED | BALANCE | % COMPLETION | ITR CLOSED THIS WEEK
CPP | [13 empty] | JUNE | 10 | 0 | #REF! | #REF! | #REF! | #REF! | 29
Mechanical | 202 | 202 | 100% | 0 |  |  |  |  | 14 |  |  |  | 14 | SEPTEMBER | 53 | 0 | #REF! | #REF! | #REF! | #REF! | 1
Piping & Vessel | 995 | 578 | 58.09% | 417 |  | 1 |  |  | 9 | 4 | 19 | 8 | 41 | OCTOBER | 7 | 0 | #REF! | #REF! | #REF! | #REF! | 0
Total | 1197 | 780 | 65.16% | 417 | 0 | 1 | 0 | 0 | 23 | 4 | 19 | 8 | 55
EIT | [13 empty] | MONTH | TOTAL NO SS | RFC SIGNED | TOTAL ITRS | TOTAL CLOSED | BALANCE | % COMPLETION | ITR CLOSED THIS WEEK
Electrical | 1451 | 300 | 20.68% | 1151 |  | 15 |  |  |  | 35 |  | 8 | 58 | JUNE | 9 | 0 | 437 | 47 | 390 | 0.10755 | 29
Instrumentation | 1366 | 18 | 1.318% | 1348 | [5 empty] | 18 |  |  | 18 | JULY | 48 | 0 | 2705 | 306 | 2399 | 0.11312 | 33
Telecom | 130 | 0 | 0% | 130 | [8 empty] | 0 | AUGUST | 129 | 0 | 6505 | 874 | 5631 | 0.13436 | 35
Total | 2947 | 318 | 10.79% | 2629 | 0 | 15 | 0 | 0 | 0 | 53 | 0 | 8 | 76 | SEPTEMBER | 53 | 0 | 1930 | 270 | 1660 | 0.1399 | 1
Grand Total | 4144 | 1098 | 26.5% | 3046 | 0 | 16 | 0 | 0 | 23 | 57 | 19 | 16 | 131 | OCTOBER | 7 | 0 | 1183 | 2 | 1181 | 0.0016906 | 0
*Note: This report was generated based on Hexagon data as of- July 3 2026 at 7.00 AM | [13 empty] | Grand Total | 248 | 0 | 12763 | 1501 | 11262 | 0.11761 | 98
-56

## DETAILED ITR LIST
Task ID | Asset - Tag | Asset Pack ID | Cable Pack ID | Pipe Pack ID | Loop Name | Description | Category (Summary) | Discipline | Task Type (Name) | Discipline (Summary) | Asset - Description | Systemization - Process Plant ID | Responsible Company (Summary) | Actual Duration | Scheduled Duration | Task Duration | Title - Actual MH/Person | Title - Planned MH/Person | Field005 (Custom) | Physical Location - Area (Summary) | Systemization - Subsystem (Summary) | Closing Date | Subsystem ID | Priority | Priority | Test Form - Description | Asset Discipline | Task State | Priority | RFC
T-00018-0192 | PS5-61-IU-0001A |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 16 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Power Transformer | E | To be completed | PS5 - Milestone B
T-00018-0193 | PS5-61-IU-0001B |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 16 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Power Transformer | E | To be completed | PS5 - Milestone B
T-00018-0194 | PS5-61-IU-0001C |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 16 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Power Transformer | E | To be completed | PS5 - Milestone D
T-00018-0195 | PS5-61-IU-0001D |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 16 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Power Transformer | E | To be completed | PS5 - Milestone D
T-00018-0196 | PS5-61-IU-0001E |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 16 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Power Transformer | E | To be completed | PS5 - Milestone D
T-00018-0197 | PS5-61-IU-0001F |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 16 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Power Transformer | E | To be completed | PS5 - Milestone D
T-00018-0198 | PS5-61-IU-0001G |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 16 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Power Transformer | E | To be completed | PS5 - Milestone E
T-00022-3334 | PS5-60-IJ-0001A-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-60-IJ-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-03-07 11:29 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00022-3335 | PS5-60-IJ-0001B-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-60-IJ-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-03-07 11:36 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00022-3336 | PS5-60-IJ-0001C-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100C TO PS5-60-IJ-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-03-07 11:39 | PS5-60-07 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3337 | PS5-60-IJ-0001D-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100D TO PS5-60-IJ-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-03-07 11:42 | PS5-60-10 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3338 | PS5-60-IJ-0001E-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100E TO PS5-60-IJ-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-03-07 11:46 | PS5-60-13 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3339 | PS5-60-IJ-0001F-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100F TO PS5-60-IJ-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-03-07 11:49 | PS5-60-16 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3340 | PS5-60-IJ-0001G-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100G TO PS5-60-IJ-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-03-07 11:51 | PS5-60-19 |  |  | HV Power Cable | E | Closed | PS5 - Milestone E
T-00022-3377 | PS5-61-IJ-0001-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-24 08:12 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00022-3378 | PS5-61-IJ-0001-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-24 12:59 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00022-3379 | PS5-61-IJ-0001-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-24 13:00 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00022-3380 | PS5-61-IJ-0001-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-24 13:01 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00022-3381 | PS5-61-IJ-0001-CH05 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-24 13:01 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00022-3382 | PS5-61-IJ-0001-CH06 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-24 13:48 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00022-3383 | PS5-61-IJ-0001-CH07 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001C TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-24 13:48 | PS5-60-07 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3384 | PS5-61-IJ-0001-CH08 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001C TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-24 13:49 | PS5-60-07 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3385 | PS5-61-IJ-0001-CH09 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001C TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-24 08:14 | PS5-60-07 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3386 | PS5-61-IJ-0001-CH10 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001D TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-24 08:15 | PS5-60-10 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3387 | PS5-61-IJ-0001-CH11 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001D TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-24 08:15 | PS5-60-10 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3388 | PS5-61-IJ-0001-CH12 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001D TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-24 08:17 | PS5-60-10 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3389 | PS5-61-IJ-0001-CH13 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001E TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-04-24 08:17 | PS5-60-13 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3390 | PS5-61-IJ-0001-CH14 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001E TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-04-24 08:24 | PS5-60-13 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3391 | PS5-61-IJ-0001-CH15 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001E TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-04-24 08:32 | PS5-60-13 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3392 | PS5-61-IJ-0001-CH16 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001F TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-04-24 08:33 | PS5-60-16 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3393 | PS5-61-IJ-0001-CH17 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001F TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-04-24 08:33 | PS5-60-16 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3394 | PS5-61-IJ-0001-CH18 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001F TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-04-24 08:34 | PS5-60-16 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3395 | PS5-61-IJ-0001-CH19 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001G TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-04-24 08:34 | PS5-60-19 |  |  | HV Power Cable | E | Closed | PS5 - Milestone E
T-00022-3396 | PS5-61-IJ-0001-CH20 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001G TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-04-24 08:34 | PS5-60-19 |  |  | HV Power Cable | E | Closed | PS5 - Milestone E
T-00022-3397 | PS5-61-IJ-0001-CH21 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001G TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-04-24 08:35 | PS5-60-19 |  |  | HV Power Cable | E | Closed | PS5 - Milestone E
T-00022-3410 | PS5-61-IU-0001A-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-18 12:59 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00022-3411 | PS5-61-IU-0001A-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-18 13:03 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00022-3412 | PS5-61-IU-0001A-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-18 13:06 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00022-3413 | PS5-61-IU-0001B-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-18 13:09 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00022-3414 | PS5-61-IU-0001B-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-18 13:11 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00022-3415 | PS5-61-IU-0001B-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-18 13:13 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00022-3416 | PS5-61-IU-0001C-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100C TO PS5-61-IU-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-02-19 12:39 | PS5-60-07 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3417 | PS5-61-IU-0001C-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100C TO PS5-61-IU-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-02-19 12:40 | PS5-60-07 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3418 | PS5-61-IU-0001C-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100C TO PS5-61-IU-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-02-19 12:45 | PS5-60-07 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3419 | PS5-61-IU-0001D-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100D TO PS5-61-IU-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-02-19 12:46 | PS5-60-10 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3420 | PS5-61-IU-0001D-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100D TO PS5-61-IU-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-02-19 12:48 | PS5-60-10 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3421 | PS5-61-IU-0001D-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100D TO PS5-61-IU-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-02-19 12:50 | PS5-60-10 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3422 | PS5-61-IU-0001E-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100E TO PS5-61-IU-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-02-19 12:52 | PS5-60-13 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3423 | PS5-61-IU-0001E-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100E TO PS5-61-IU-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-02-19 12:53 | PS5-60-13 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3424 | PS5-61-IU-0001E-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100E TO PS5-61-IU-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-02-19 12:54 | PS5-60-13 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3425 | PS5-61-IU-0001F-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100F TO PS5-61-IU-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-02-19 12:56 | PS5-60-16 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3426 | PS5-61-IU-0001F-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100F TO PS5-61-IU-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-02-19 12:57 | PS5-60-16 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3427 | PS5-61-IU-0001F-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100F TO PS5-61-IU-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-02-19 12:59 | PS5-60-16 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00022-3428 | PS5-61-IU-0001G-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100G TO PS5-61-IU-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-02-22 11:16 | PS5-60-19 |  |  | HV Power Cable | E | Closed | PS5 - Milestone E
T-00022-3429 | PS5-61-IU-0001G-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100G TO PS5-61-IU-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-02-22 11:18 | PS5-60-19 |  |  | HV Power Cable | E | Closed | PS5 - Milestone E
T-00022-3430 | PS5-61-IU-0001G-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100G TO PS5-61-IU-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-02-22 11:20 | PS5-60-19 |  |  | HV Power Cable | E | Closed | PS5 - Milestone E
T-00023-10536 | PS5-60-IN-0002A-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-10537 | PS5-60-IN-0002B-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-10538 | PS5-60-IN-0002C-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-10539 | PS5-60-IN-0002D-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-10540 | PS5-60-IN-0002E-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-10541 | PS5-60-IN-0002F-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-10542 | PS5-60-IN-0002G-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-10593 | PS5-60-IH-0001A-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-10594 | PS5-60-IH-0001B-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-10595 | PS5-60-IH-0001C-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-10596 | PS5-60-IH-0001D-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-10597 | PS5-60-IH-0001E-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001E | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-10598 | PS5-60-IH-0001F-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001F | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-10599 | PS5-60-IH-0001G-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001G | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-10600 | PS5-60-IH-0002-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-10601 | PS5-60-IH-0002-CG02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-10887 | PS5-60-BE-0007A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-10888 | PS5-60-BE-0007A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-10889 | PS5-60-BE-0007B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-10890 | PS5-60-BE-0007B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-10891 | PS5-60-BE-0007C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0007C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-10892 | PS5-60-BE-0007C-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0007C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-10893 | PS5-60-BE-0007D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0007D | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-10894 | PS5-60-BE-0007D-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0007D | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-10895 | PS5-60-BE-0007E-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BE-0007E | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-10896 | PS5-60-BE-0007E-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BE-0007E | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-10897 | PS5-60-BE-0007F-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BE-0007F | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-10898 | PS5-60-BE-0007F-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BE-0007F | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-10899 | PS5-60-BE-0007G-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BE-0007G | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-10900 | PS5-60-BE-0007G-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BE-0007G | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-10901 | PS5-60-ISO-62800A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-ISO-62800A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-10902 | PS5-60-ISO-62800C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-ISO-62800C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-10903 | PS5-60-ISO-62800E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-ISO-62800E | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-10904 | PS5-60-ISO-62800G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-ISO-62800G | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-4725 | PS5-03-SEA-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-03-SEA-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-4978 | PS5-60-BE-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-4979 | PS5-60-BE-0001-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-4981 | PS5-60-BE-0001-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-4982 | PS5-60-BE-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-4983 | PS5-60-BE-0002-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-4984 | PS5-60-BE-0002-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-4986 | PS5-60-BE-0002-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-4987 | PS5-60-BE-0003A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0003A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-4988 | PS5-60-BE-0003B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-4989 | PS5-60-BE-0003C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0003C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-4990 | PS5-60-BE-0003D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0003D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-4991 | PS5-60-BE-0003E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0003E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-4992 | PS5-60-BE-0003F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0003F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-4993 | PS5-60-BE-0003G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0003G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-4994 | PS5-60-BE-0004A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0004A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-4995 | PS5-60-BE-0004B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0004B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-4996 | PS5-60-BE-0004C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0004C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-4997 | PS5-60-BE-0004D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0004D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-4998 | PS5-60-BE-0004E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0004E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-4999 | PS5-60-BE-0004F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0004F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5000 | PS5-60-BE-0004G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0004G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5001 | PS5-60-BE-0005A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0005A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5002 | PS5-60-BE-0005B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0005B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5003 | PS5-60-BE-0005C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0005C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5004 | PS5-60-BE-0005D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0005D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5005 | PS5-60-BE-0005E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0005E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5006 | PS5-60-BE-0005F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0005F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5007 | PS5-60-BE-0005G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0005G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5008 | PS5-60-BE-0011A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5009 | PS5-60-BE-0011A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5010 | PS5-60-BE-0011A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5011 | PS5-60-BE-0011A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5012 | PS5-60-BE-0011A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5013 | PS5-60-BE-0011A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5014 | PS5-60-BE-0011B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5015 | PS5-60-BE-0011B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5016 | PS5-60-BE-0011B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5017 | PS5-60-BE-0011B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5018 | PS5-60-BE-0011B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5019 | PS5-60-BE-0011B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5020 | PS5-60-BE-0012A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5021 | PS5-60-BE-0012A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5022 | PS5-60-BE-0012A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5023 | PS5-60-BE-0012A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5024 | PS5-60-BE-0012A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5025 | PS5-60-BE-0012A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5026 | PS5-60-BE-0012B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5027 | PS5-60-BE-0012B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5028 | PS5-60-BE-0012B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5029 | PS5-60-BE-0012B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5030 | PS5-60-BE-0012B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5031 | PS5-60-BE-0012B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5032 | PS5-60-BE-0013A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5033 | PS5-60-BE-0013A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5034 | PS5-60-BE-0013A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5035 | PS5-60-BE-0013A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5036 | PS5-60-BE-0013A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5037 | PS5-60-BE-0013A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5038 | PS5-60-BE-0013B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5039 | PS5-60-BE-0013B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5040 | PS5-60-BE-0013B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5041 | PS5-60-BE-0013B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5042 | PS5-60-BE-0013B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5043 | PS5-60-BE-0013B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5044 | PS5-60-BE-0014A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5045 | PS5-60-BE-0014A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5046 | PS5-60-BE-0014A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5047 | PS5-60-BE-0014A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5048 | PS5-60-BE-0014A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5049 | PS5-60-BE-0014A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5050 | PS5-60-BE-0014B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5051 | PS5-60-BE-0014B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5052 | PS5-60-BE-0014B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5053 | PS5-60-BE-0014B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5054 | PS5-60-BE-0014B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5055 | PS5-60-BE-0014B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5056 | PS5-60-BE-0015A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5057 | PS5-60-BE-0015A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5058 | PS5-60-BE-0015A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5059 | PS5-60-BE-0015A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5060 | PS5-60-BE-0015A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5061 | PS5-60-BE-0015A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5062 | PS5-60-BE-0015B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5063 | PS5-60-BE-0015B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5064 | PS5-60-BE-0015B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5065 | PS5-60-BE-0015B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5066 | PS5-60-BE-0015B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5067 | PS5-60-BE-0015B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5068 | PS5-60-BE-0016A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5069 | PS5-60-BE-0016A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5070 | PS5-60-BE-0016A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5071 | PS5-60-BE-0016A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5072 | PS5-60-BE-0016A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5073 | PS5-60-BE-0016A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5074 | PS5-60-BE-0016B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5075 | PS5-60-BE-0016B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5076 | PS5-60-BE-0016B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5077 | PS5-60-BE-0016B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5078 | PS5-60-BE-0016B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5079 | PS5-60-BE-0016B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5080 | PS5-60-BE-0017A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5081 | PS5-60-BE-0017A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5082 | PS5-60-BE-0017A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5083 | PS5-60-BE-0017A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5084 | PS5-60-BE-0017A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5085 | PS5-60-BE-0017A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5086 | PS5-60-BE-0017B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5087 | PS5-60-BE-0017B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5088 | PS5-60-BE-0017B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5089 | PS5-60-BE-0017B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5090 | PS5-60-BE-0017B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5091 | PS5-60-BE-0017B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5092 | PS5-60-BE-0021A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0021A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5093 | PS5-60-BE-0021B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0021B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5094 | PS5-60-BE-0024A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0024A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5095 | PS5-60-BE-0024A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0024A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5096 | PS5-60-BE-0024B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0024B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5097 | PS5-60-BE-0024B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0024B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5098 | PS5-60-BE-0024C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0024C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5099 | PS5-60-BE-0024C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0024C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5100 | PS5-60-BE-0024D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0024D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5101 | PS5-60-BE-0024D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0024D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5102 | PS5-60-BE-0024E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0024E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5103 | PS5-60-BE-0024E-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0024E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5104 | PS5-60-BE-0024F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0024F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F |  | PS5-60-40 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5105 | PS5-60-BE-0024F-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0024F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F |  | PS5-60-40 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5106 | PS5-60-BE-0024G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0024G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5107 | PS5-60-BE-0024G-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0024G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5108 | PS5-60-BE-0025A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0025A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5109 | PS5-60-BE-0025B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0025B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5110 | PS5-60-BE-0025C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0025C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5111 | PS5-60-BE-0025D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0025D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5112 | PS5-60-BE-0025E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0025E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5113 | PS5-60-BE-0025F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0025F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F |  | PS5-60-40 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5114 | PS5-60-BE-0025G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0025G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5115 | PS5-60-BE-0026A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0026A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5116 | PS5-60-BE-0026A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0026A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5117 | PS5-60-BE-0026B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0026B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5118 | PS5-60-BE-0026B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0026B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5119 | PS5-60-BE-0026C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0026C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5120 | PS5-60-BE-0026C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0026C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5121 | PS5-60-BE-0026D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0026D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5122 | PS5-60-BE-0026D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0026D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5123 | PS5-60-BE-0026E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0026E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5124 | PS5-60-BE-0026E-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0026E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5125 | PS5-60-BE-0026F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0026F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5126 | PS5-60-BE-0026F-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0026F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5127 | PS5-60-BE-0026G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0026G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5128 | PS5-60-BE-0026G-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0026G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5129 | PS5-60-BI-0005A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0005A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5130 | PS5-60-BI-0005B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0005B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5131 | PS5-60-BI-0005C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0005C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5132 | PS5-60-BI-0005D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0005D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5133 | PS5-60-BI-0005E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0005E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5134 | PS5-60-BI-0005F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0005F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5135 | PS5-60-BI-0005G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0005G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5136 | PS5-60-BI-0015A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5137 | PS5-60-BI-0015A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5138 | PS5-60-BI-0015A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5139 | PS5-60-BI-0015B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5140 | PS5-60-BI-0015B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5141 | PS5-60-BI-0015B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5142 | PS5-60-BI-0015C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0015C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5143 | PS5-60-BI-0015C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0015C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5144 | PS5-60-BI-0015C-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0015C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5145 | PS5-60-BI-0015D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0015D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5146 | PS5-60-BI-0015D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0015D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5147 | PS5-60-BI-0015D-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0015D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5148 | PS5-60-BI-0015E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0015E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5149 | PS5-60-BI-0015E-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0015E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5150 | PS5-60-BI-0015E-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0015E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5151 | PS5-60-BI-0015F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0015F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5152 | PS5-60-BI-0015F-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0015F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5153 | PS5-60-BI-0015F-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0015F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5154 | PS5-60-BI-0015G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0015G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5155 | PS5-60-BI-0015G-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0015G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5156 | PS5-60-BI-0015G-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0015G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5157 | PS5-60-DD-62800A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-DD-62800A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5159 | PS5-60-DD-62800C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-DD-62800C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5161 | PS5-60-DD-62800E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-DD-62800E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5163 | PS5-60-DD-62800G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-DD-62800G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5166 | PS5-60-IE-0002A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5167 | PS5-60-IE-0002A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5168 | PS5-60-IE-0002A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5169 | PS5-60-IE-0002B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5170 | PS5-60-IE-0002B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5171 | PS5-60-IE-0002B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5172 | PS5-60-IE-0002C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5173 | PS5-60-IE-0002C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5174 | PS5-60-IE-0002C-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5175 | PS5-60-IE-0002D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5176 | PS5-60-IE-0002D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5177 | PS5-60-IE-0002D-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5178 | PS5-60-IE-0002E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5179 | PS5-60-IE-0002E-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5180 | PS5-60-IE-0002E-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0002E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5181 | PS5-60-IE-0002F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5182 | PS5-60-IE-0002F-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5183 | PS5-60-IE-0002F-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0002F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5184 | PS5-60-IE-0002G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5185 | PS5-60-IE-0002G-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5186 | PS5-60-IE-0002G-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0002G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5187 | PS5-60-IE-0003A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5188 | PS5-60-IE-0003A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5189 | PS5-60-IE-0003B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5190 | PS5-60-IE-0003B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5191 | PS5-60-IE-0003C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5192 | PS5-60-IE-0003C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5193 | PS5-60-IE-0003D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5194 | PS5-60-IE-0003D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5195 | PS5-60-IE-0003E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5196 | PS5-60-IE-0003E-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5197 | PS5-60-IE-0003F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5198 | PS5-60-IE-0003F-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5199 | PS5-60-IE-0003G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5200 | PS5-60-IE-0003G-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5201 | PS5-60-IE-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5202 | PS5-60-IE-0004-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5204 | PS5-60-IH-0001A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5205 | PS5-60-IH-0001A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5206 | PS5-60-IH-0001A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5207 | PS5-60-IH-0001A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5208 | PS5-60-IH-0001A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5209 | PS5-60-IH-0001A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5211 | PS5-60-IH-0001B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5212 | PS5-60-IH-0001B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5213 | PS5-60-IH-0001B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5214 | PS5-60-IH-0001B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5215 | PS5-60-IH-0001B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5216 | PS5-60-IH-0001B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5218 | PS5-60-IH-0001C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5219 | PS5-60-IH-0001C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5220 | PS5-60-IH-0001C-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5221 | PS5-60-IH-0001C-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5222 | PS5-60-IH-0001C-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5223 | PS5-60-IH-0001C-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5225 | PS5-60-IH-0001D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5226 | PS5-60-IH-0001D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5227 | PS5-60-IH-0001D-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5228 | PS5-60-IH-0001D-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5229 | PS5-60-IH-0001D-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5230 | PS5-60-IH-0001D-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5232 | PS5-60-IH-0001E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5233 | PS5-60-IH-0001E-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5234 | PS5-60-IH-0001E-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5235 | PS5-60-IH-0001E-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5236 | PS5-60-IH-0001E-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5237 | PS5-60-IH-0001E-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5239 | PS5-60-IH-0001F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5240 | PS5-60-IH-0001F-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5241 | PS5-60-IH-0001F-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5242 | PS5-60-IH-0001F-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5243 | PS5-60-IH-0001F-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5244 | PS5-60-IH-0001F-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5246 | PS5-60-IH-0001G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5247 | PS5-60-IH-0001G-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5248 | PS5-60-IH-0001G-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5249 | PS5-60-IH-0001G-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5250 | PS5-60-IH-0001G-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5251 | PS5-60-IH-0001G-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5254 | PS5-60-IH-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5255 | PS5-60-IH-0002-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5256 | PS5-60-IH-0002-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5257 | PS5-60-IH-0002-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5258 | PS5-60-IH-0002-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5259 | PS5-60-IH-0002-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5260 | PS5-60-IH-0002-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5261 | PS5-60-IH-0002-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5262 | PS5-60-IH-0002-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5263 | PS5-60-IH-0002-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5264 | PS5-60-IN-0001A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5265 | PS5-60-IN-0001B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5266 | PS5-60-IN-0001C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5267 | PS5-60-IN-0001D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5268 | PS5-60-IN-0001E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-IN-0001E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5269 | PS5-60-IN-0001F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-IN-0001F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5270 | PS5-60-IN-0001G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-IN-0001G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5271 | PS5-60-IN-0002A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5272 | PS5-60-IN-0002A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5273 | PS5-60-IN-0002A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5274 | PS5-60-IN-0002B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5275 | PS5-60-IN-0002B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5276 | PS5-60-IN-0002B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5277 | PS5-60-IN-0002C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5278 | PS5-60-IN-0002C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5279 | PS5-60-IN-0002C-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5280 | PS5-60-IN-0002D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5281 | PS5-60-IN-0002D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5282 | PS5-60-IN-0002D-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5283 | PS5-60-IN-0002E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5284 | PS5-60-IN-0002E-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5285 | PS5-60-IN-0002E-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5286 | PS5-60-IN-0002F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5287 | PS5-60-IN-0002F-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5288 | PS5-60-IN-0002F-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5289 | PS5-60-IN-0002G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5290 | PS5-60-IN-0002G-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5291 | PS5-60-IN-0002G-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5292 | PS5-60-IWK-0001A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5293 | PS5-60-IWK-0001A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5294 | PS5-60-IWK-0001B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5295 | PS5-60-IWK-0001B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5296 | PS5-60-IWK-0001C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5297 | PS5-60-IWK-0001C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5298 | PS5-60-LA-0002A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5299 | PS5-60-LA-0002A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5300 | PS5-60-LA-0002B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5301 | PS5-60-LA-0002B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5302 | PS5-60-LA-0002C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5303 | PS5-60-LA-0002C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5304 | PS5-60-LA-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5305 | PS5-60-LA-0003-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5310 | PS5-60-SEA-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5311 | PS5-60-SEA-0001-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5312 | PS5-60-VS-9100A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-VS-9100A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5313 | PS5-60-VS-9100B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-VS-9100B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5314 | PS5-60-VS-9100C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-VS-9100C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C |  | PS5-60-44 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5315 | PS5-60-VS-9100D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-VS-9100D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D |  | PS5-60-45 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5316 | PS5-60-VS-9100E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-VS-9100E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E |  | PS5-60-46 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5317 | PS5-60-VS-9100F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-VS-9100F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F |  | PS5-60-47 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5318 | PS5-60-VS-9100G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-VS-9100G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G |  | PS5-60-48 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5319 | PS5-61-BI-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5320 | PS5-61-BI-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5321 | PS5-61-BI-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-61-BI-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5322 | PS5-61-BI-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-61-BI-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5323 | PS5-61-BI-0005-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-61-BI-0005 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5324 | PS5-61-BI-0006-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-61-BI-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-5325 | PS5-61-BI-0007-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-61-BI-0007 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-5581 | PS5-71-IN-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00023-5582 | PS5-71-IN-0002-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00023-5583 | PS5-71-IN-0002-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00023-5584 | PS5-71-IN-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5585 | PS5-71-IN-0003-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5586 | PS5-71-IN-0003-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5594 | PS5-71-MOV-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00023-5595 | PS5-71-MOV-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5596 | PS5-71-MOV-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00023-5597 | PS5-71-MOV-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-5599 | PS5-71-MOV-0008-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0008 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00023-5601 | PS5-71-MOV-0010-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0010 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00023-9131 | PS5-60-BE-0007A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9132 | PS5-60-BE-0007B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9133 | PS5-60-BE-0007C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0007C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9134 | PS5-60-BE-0007D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0007D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9135 | PS5-60-BE-0007E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BE-0007E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9136 | PS5-60-BE-0007F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BE-0007F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9137 | PS5-60-BE-0007G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BE-0007G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-9138 | PS5-60-BE-0027A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0027A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9139 | PS5-60-BE-0027B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0027B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9140 | PS5-60-BE-0027C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0027C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9141 | PS5-60-BE-0027D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0027D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9142 | PS5-60-BE-0027E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BE-0027E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9143 | PS5-60-BE-0027F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BE-0027F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9144 | PS5-60-BE-0027G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BE-0027G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-9145 | PS5-60-BE-0028A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0028A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9146 | PS5-60-BE-0028B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0028B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9147 | PS5-60-BE-0028C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0028C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9148 | PS5-60-BE-0028D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0028D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9149 | PS5-60-BE-0028E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BE-0028E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9150 | PS5-60-BE-0028F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BE-0028F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9151 | PS5-60-BE-0028G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BE-0028G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-9152 | PS5-60-BI-0006A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9153 | PS5-60-BI-0006A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9154 | PS5-60-BI-0006A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9155 | PS5-60-BI-0006A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9156 | PS5-60-BI-0006A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9157 | PS5-60-BI-0006A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9158 | PS5-60-BI-0006A-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9159 | PS5-60-BI-0006A-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9160 | PS5-60-BI-0006A-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9161 | PS5-60-BI-0006A-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9162 | PS5-60-BI-0006A-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9163 | PS5-60-BI-0006B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9164 | PS5-60-BI-0006B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9165 | PS5-60-BI-0006B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9166 | PS5-60-BI-0006B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9167 | PS5-60-BI-0006B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9168 | PS5-60-BI-0006B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9169 | PS5-60-BI-0006B-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9170 | PS5-60-BI-0006B-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9171 | PS5-60-BI-0006B-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9172 | PS5-60-BI-0006B-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9173 | PS5-60-BI-0006B-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9174 | PS5-60-BI-0006C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9175 | PS5-60-BI-0006C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9176 | PS5-60-BI-0006C-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9177 | PS5-60-BI-0006C-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9178 | PS5-60-BI-0006C-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9179 | PS5-60-BI-0006C-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9180 | PS5-60-BI-0006C-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9181 | PS5-60-BI-0006C-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9182 | PS5-60-BI-0006C-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9183 | PS5-60-BI-0006C-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9184 | PS5-60-BI-0006C-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9185 | PS5-60-BI-0006D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9186 | PS5-60-BI-0006D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9187 | PS5-60-BI-0006D-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9188 | PS5-60-BI-0006D-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9189 | PS5-60-BI-0006D-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9190 | PS5-60-BI-0006D-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9191 | PS5-60-BI-0006D-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9192 | PS5-60-BI-0006D-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9193 | PS5-60-BI-0006D-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9194 | PS5-60-BI-0006D-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9195 | PS5-60-BI-0006D-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9196 | PS5-60-BI-0006E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9197 | PS5-60-BI-0006E-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9198 | PS5-60-BI-0006E-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9199 | PS5-60-BI-0006E-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9200 | PS5-60-BI-0006E-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9201 | PS5-60-BI-0006E-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9202 | PS5-60-BI-0006E-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9203 | PS5-60-BI-0006E-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9204 | PS5-60-BI-0006E-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9205 | PS5-60-BI-0006E-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9206 | PS5-60-BI-0006E-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9207 | PS5-60-BI-0006F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9208 | PS5-60-BI-0006F-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9209 | PS5-60-BI-0006F-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9210 | PS5-60-BI-0006F-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9211 | PS5-60-BI-0006F-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9212 | PS5-60-BI-0006F-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9213 | PS5-60-BI-0006F-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9214 | PS5-60-BI-0006F-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9215 | PS5-60-BI-0006F-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9216 | PS5-60-BI-0006F-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9217 | PS5-60-BI-0006F-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9218 | PS5-60-BI-0006G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-9219 | PS5-60-BI-0006G-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-9220 | PS5-60-BI-0006G-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-9221 | PS5-60-BI-0006G-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-9222 | PS5-60-BI-0006G-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-9223 | PS5-60-BI-0006G-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-9224 | PS5-60-BI-0006G-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-9225 | PS5-60-BI-0006G-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-9226 | PS5-60-BI-0006G-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-9227 | PS5-60-BI-0006G-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-9228 | PS5-60-BI-0006G-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-9229 | PS5-60-BI-0017A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0017A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9230 | PS5-60-BI-0017B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0017B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9231 | PS5-60-BI-0017C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0017C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9232 | PS5-60-BI-0017D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0017D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9233 | PS5-60-BI-0017E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0017E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9234 | PS5-60-BI-0017F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0017F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9235 | PS5-60-BI-0017G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0017G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-9236 | PS5-60-EA-2900A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-EA-2900A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9237 | PS5-60-EA-2900B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-EA-2900B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9238 | PS5-60-EA-2900C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-EA-2900C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9239 | PS5-60-EA-2900D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-EA-2900D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9240 | PS5-60-EA-2900E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-EA-2900E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9241 | PS5-60-EA-2900F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-EA-2900F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00023-9242 | PS5-60-EA-2900G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-EA-2900G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00023-9244 | PS5-71-BE-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00023-9245 | PS5-71-BE-0004-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00023-9246 | PS5-71-BE-0004-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00023-9247 | PS5-71-BI-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00023-9248 | PS5-71-BI-0003-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00023-9249 | PS5-71-BI-0003-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00023-9250 | PS5-71-BI-0003-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00023-9251 | PS5-71-BI-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00023-9252 | PS5-71-BI-0005-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9253 | PS5-71-BI-0005-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9254 | PS5-71-BI-0005-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00023-9255 | PS5-71-BI-0006-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0006 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00024-2101 | PS5-60-IE-0002A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00024-2102 | PS5-60-IE-0002A-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00024-2103 | PS5-60-IE-0002A-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00024-2104 | PS5-60-IE-0002B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00024-2105 | PS5-60-IE-0002B-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00024-2106 | PS5-60-IE-0002B-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00024-2107 | PS5-60-IE-0002C-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2108 | PS5-60-IE-0002C-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2109 | PS5-60-IE-0002C-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2110 | PS5-60-IE-0002D-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2111 | PS5-60-IE-0002D-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2112 | PS5-60-IE-0002D-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2113 | PS5-60-IE-0002E-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2114 | PS5-60-IE-0002E-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2115 | PS5-60-IE-0002E-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2116 | PS5-60-IE-0002F-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2117 | PS5-60-IE-0002F-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2118 | PS5-60-IE-0002F-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2119 | PS5-60-IE-0002G-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone E
T-00024-2120 | PS5-60-IE-0002G-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone E
T-00024-2121 | PS5-60-IE-0002G-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone E
T-00024-2123 | PS5-60-IE-0003A-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00024-2124 | PS5-60-IE-0003A-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00024-2125 | PS5-60-IE-0003A-CD04 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0005A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00024-2126 | PS5-60-IE-0003A-CD05 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00024-2135 | PS5-60-IE-0003A-CD14 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00024-2136 | PS5-60-IE-0003A-CD15 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00024-2138 | PS5-60-IE-0003B-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00024-2139 | PS5-60-IE-0003B-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00024-2140 | PS5-60-IE-0003B-CD04 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0005B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00024-2141 | PS5-60-IE-0003B-CD05 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00024-2150 | PS5-60-IE-0003B-CD14 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00024-2151 | PS5-60-IE-0003B-CD15 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00024-2153 | PS5-60-IE-0003C-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2154 | PS5-60-IE-0003C-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2155 | PS5-60-IE-0003C-CD04 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0005C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2156 | PS5-60-IE-0003C-CD05 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2165 | PS5-60-IE-0003C-CD14 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2166 | PS5-60-IE-0003C-CD15 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2168 | PS5-60-IE-0003D-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2169 | PS5-60-IE-0003D-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2170 | PS5-60-IE-0003D-CD04 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0005D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2171 | PS5-60-IE-0003D-CD05 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2180 | PS5-60-IE-0003D-CD14 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2181 | PS5-60-IE-0003D-CD15 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2183 | PS5-60-IE-0003E-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2184 | PS5-60-IE-0003E-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2185 | PS5-60-IE-0003E-CD04 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0005E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2186 | PS5-60-IE-0003E-CD05 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2195 | PS5-60-IE-0003E-CD14 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2196 | PS5-60-IE-0003E-CD15 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2198 | PS5-60-IE-0003F-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2199 | PS5-60-IE-0003F-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2200 | PS5-60-IE-0003F-CD04 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0005F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2201 | PS5-60-IE-0003F-CD05 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2210 | PS5-60-IE-0003F-CD14 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2211 | PS5-60-IE-0003F-CD15 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00024-2213 | PS5-60-IE-0003G-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone E
T-00024-2214 | PS5-60-IE-0003G-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone E
T-00024-2215 | PS5-60-IE-0003G-CD04 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0005G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone E
T-00024-2216 | PS5-60-IE-0003G-CD05 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone E
T-00024-2225 | PS5-60-IE-0003G-CD14 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone E
T-00024-2226 | PS5-60-IE-0003G-CD15 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone E
T-00034-0059 | PS5-60-IJ-0001A |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Neutral Grounding resistor for Generator set 1 (A) | EACOP | CPP AGI |  |  | 8 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone B
T-00034-0060 | PS5-60-IJ-0001B |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Neutral Grounding resistor for Generator set 2 (B) | EACOP | CPP AGI |  |  | 8 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone B
T-00034-0061 | PS5-60-IJ-0001C |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Neutral Grounding resistor for Generator set 3 (C) | EACOP | CPP AGI |  |  | 8 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone D
T-00034-0062 | PS5-60-IJ-0001D |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Neutral Grounding resistor for Generator set 4 (D) | EACOP | CPP AGI |  |  | 8 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone D
T-00034-0063 | PS5-60-IJ-0001E |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Neutral Grounding resistor for Generator set 5 (E) | EACOP | CPP AGI |  |  | 8 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone D
T-00034-0064 | PS5-60-IJ-0001F |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Neutral Grounding resistor for Generator set 6 (F) | EACOP | CPP AGI |  |  | 8 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone D
T-00034-0065 | PS5-60-IJ-0001G |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Neutral Grounding resistor for Generator set 7 (G) | EACOP | CPP AGI |  |  | 8 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone E
T-00044-0090 | PS5-60-IE-0003A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GCP G-1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B
T-00044-0091 | PS5-60-IE-0003B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GCP G-2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B
T-00044-0092 | PS5-60-IE-0003C |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GCP G-3 (C) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone D
T-00044-0093 | PS5-60-IE-0003D |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GCP G-4 (D) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone D
T-00044-0094 | PS5-60-IE-0003E |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GCP G-5 (E) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone D
T-00044-0095 | PS5-60-IE-0003F |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GCP G-6 (F) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone D
T-00044-0096 | PS5-60-IE-0003G |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GCP G-7 (G) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone E
T-00044-0097 | PS5-60-IE-0004 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | MCP- MASTER CONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B
T-00044-0098 | PS5-60-IH-0001A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENSET MCC -1 - G1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B
T-00044-0099 | PS5-60-IH-0001B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENSET MCC -2 - G2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B
T-00044-0100 | PS5-60-IH-0001C |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENSET MCC -3 - G3 (C) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone D
T-00044-0101 | PS5-60-IH-0001D |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENSET MCC -4 - G4 (D) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone D
T-00044-0102 | PS5-60-IH-0001E |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENSET MCC -5 - G5 (E) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone D
T-00044-0103 | PS5-60-IH-0001F |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENSET MCC -6 - G6 (F) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone D
T-00044-0104 | PS5-60-IH-0001G |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENSET MCC -7 - G7 (G) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone E
T-00044-0105 | PS5-60-IH-0002 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COMMON / TREATMENT MCC | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B
T-00044-0106 | PS5-60-IE-0002A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B
T-00044-0107 | PS5-60-IE-0002B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B
T-00044-0108 | PS5-60-IE-0002C |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone D
T-00044-0109 | PS5-60-IE-0002D |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone D
T-00044-0110 | PS5-60-IE-0002E |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone D
T-00044-0111 | PS5-60-IE-0002F |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone D
T-00044-0112 | PS5-60-IE-0002G |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone E
T-00044-0185 | PS5-60-IN-0002A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B
T-00044-0186 | PS5-60-IN-0002B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B
T-00044-0187 | PS5-60-IN-0002C |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone D
T-00044-0188 | PS5-60-IN-0002D |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone D
T-00044-0189 | PS5-60-IN-0002E |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone D
T-00044-0190 | PS5-60-IN-0002F |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone D
T-00044-0191 | PS5-60-IN-0002G |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone E
T-00044-0198 | PS5-71-IN-0002 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRO-PRE PRESSURECONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone H
T-00044-0199 | PS5-71-IN-0003 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | DFO- PRE PRESSURE CONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B
T-00046-0291 | PS5-60-UR-8100A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION PACKAGE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0292 | PS5-60-UR-8100B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION PACKAGE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0293 | PS5-60-UR-8100C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION PACKAGE C | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0294 | PS5-60-UR-8100D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION PACKAGE D | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0295 | PS5-60-UR-8100E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION PACKAGE E | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0296 | PS5-60-UR-8100F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION PACKAGE F | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0297 | PS5-60-UR-8100G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION PACKAGE G | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00046-0300 | PS5-60-UA-5100 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COMPRESSOR AIR STARTING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135128 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0301 | PS5-60-UO-81100A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0302 | PS5-60-UO-81100B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0303 | PS5-60-UO-81100C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0304 | PS5-60-UO-81100D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0305 | PS5-60-UO-81100E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0306 | PS5-60-UO-81100F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0307 | PS5-60-UO-81100G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00046-0308 | PS5-60-UZ-8200A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0309 | PS5-60-UZ-8200B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0310 | PS5-60-UZ-8200C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0311 | PS5-60-UZ-8200D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0312 | PS5-60-UZ-8200E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0313 | PS5-60-UZ-8200F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F |  | PS5-60-40 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0314 | PS5-60-VS-9100A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0315 | PS5-60-VS-9100B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0316 | PS5-60-VS-9100C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C |  | PS5-60-44 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0317 | PS5-60-VS-9100D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D |  | PS5-60-45 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0318 | PS5-60-VS-9100E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E |  | PS5-60-46 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0319 | PS5-60-VS-9100F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F |  | PS5-60-47 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0320 | PS5-60-VS-9100G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G |  | PS5-60-48 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00046-0322 | PS5-71-UZ-6800A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE FUEL SEPARATOR MODULE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135002 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Package | M | To be completed | PS5 - Milestone H
T-00046-0323 | PS5-71-UZ-6800B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE FUEL SEPARATOR MODULE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135002 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Package | M | To be completed | PS5 - Milestone H
T-00046-0327 | PS5-60-EA-2100A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0328 | PS5-60-EA-2100B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0329 | PS5-60-EA-21100A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0330 | PS5-60-EA-21100B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0331 | PS5-60-EA-21100C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0332 | PS5-60-EA-21100D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0333 | PS5-60-EA-21100E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0334 | PS5-60-EA-21100F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0335 | PS5-60-EA-21100G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00046-0336 | PS5-60-EA-21200A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0337 | PS5-60-EA-21200B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0338 | PS5-60-EA-21200C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0339 | PS5-60-EA-21200D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0340 | PS5-60-EA-21200E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0341 | PS5-60-EA-21200F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0342 | PS5-60-EA-21200G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00046-0343 | PS5-60-EA-2200A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0344 | PS5-60-EA-2200B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0345 | PS5-60-EA-2300A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0346 | PS5-60-EA-2300B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0347 | PS5-60-EA-2400A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0348 | PS5-60-EA-2400B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0349 | PS5-60-EA-2500A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0350 | PS5-60-EA-2500B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0351 | PS5-60-EA-2600A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0352 | PS5-60-EA-2600B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0353 | PS5-60-EA-2700A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00046-0354 | PS5-60-EA-2700B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00046-0355 | PS5-60-EA-2800A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0356 | PS5-60-EA-2800B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0357 | PS5-60-EA-2800C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0358 | PS5-60-EA-2800D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0359 | PS5-60-EA-2800E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0360 | PS5-60-EA-2800F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F |  | PS5-60-40 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0361 | PS5-60-EA-2800G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00046-0362 | PS5-60-EA-2900A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0363 | PS5-60-EA-2900B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0364 | PS5-60-EA-2900C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0365 | PS5-60-EA-2900D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0366 | PS5-60-EA-2900E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0367 | PS5-60-EA-2900F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0368 | PS5-60-EA-2900G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00046-0369 | PS5-60-TCV-0001A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0370 | PS5-60-TCV-0001B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0371 | PS5-60-TCV-0001C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0372 | PS5-60-TCV-0001D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0373 | PS5-60-TCV-0001E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0374 | PS5-60-TCV-0001F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0375 | PS5-60-TCV-0001G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00046-0376 | PS5-60-TCV-0002A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0377 | PS5-60-TCV-0002B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0378 | PS5-60-TCV-0002C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0379 | PS5-60-TCV-0002D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0380 | PS5-60-TCV-0002E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0381 | PS5-60-TCV-0002F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0382 | PS5-60-TCV-0002G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00046-0383 | PS5-60-UA-5200 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INSTRUMENT AIR COMPRESSOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135127 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0384 | PS5-60-UR-8200A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0385 | PS5-60-UR-8200B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0386 | PS5-60-UR-8200C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0387 | PS5-60-UR-8200D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0388 | PS5-60-UR-8200E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0389 | PS5-60-UR-8200F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0390 | PS5-60-UR-8200G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00046-0391 | PS5-60-UZ-8200G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00046-0392 | PS5-60-UZ-8900A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0393 | PS5-60-UZ-8900B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0394 | PS5-60-UZ-8900C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0395 | PS5-60-UZ-8900D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0396 | PS5-60-UZ-8900E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0397 | PS5-60-UZ-8900F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0398 | PS5-60-UZ-8900G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00046-0400 | PS5-71-UZ-6400 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135004 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Package | M | To be completed | PS5 - Milestone H
T-00046-0401 | PS5-71-UZ-6700 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | DIESEL FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135126 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0552 | PS5-60-UR-8300A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0553 | PS5-60-UR-8300B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00046-0554 | PS5-60-UR-8300C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0555 | PS5-60-UR-8300D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0556 | PS5-60-UR-8300E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0557 | PS5-60-UR-8300F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F |  | PS5-60-40 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00046-0558 | PS5-60-UR-8300G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00067-0659 | PS5-03-RMAC-1409 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Electrical Instrument | I | To be completed | PS5 - Milestone E
T-00067-0660 | PS5-03-RMAC-1410 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Electrical Instrument | I | To be completed | PS5 - Milestone E
T-00067-0661 | PS5-03-RMAC-1411 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Electrical Instrument | I | To be completed | PS5 - Milestone E
T-00069-12948 | PS5-60-BI-0001A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-12949 | PS5-60-BI-0001B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-12950 | PS5-60-BI-0001C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-BI-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12951 | PS5-60-BI-0001D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-BI-0001D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12952 | PS5-60-BI-0001E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-BI-0001E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12953 | PS5-60-BI-0001F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001F TO PS5-60-BI-0001F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12954 | PS5-60-BI-0001G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001G TO PS5-60-BI-0001G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-12955 | PS5-60-BI-0003-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-12956 | PS5-60-IE-0002A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-12957 | PS5-60-IE-0002A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-12958 | PS5-60-IE-0002A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-12959 | PS5-60-IE-0002B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-12960 | PS5-60-IE-0002B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-12961 | PS5-60-IE-0002B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-12962 | PS5-60-IE-0002C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12963 | PS5-60-IE-0002C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12964 | PS5-60-IE-0002C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12965 | PS5-60-IE-0002D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12966 | PS5-60-IE-0002D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12967 | PS5-60-IE-0002D-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12968 | PS5-60-IE-0002E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12969 | PS5-60-IE-0002E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12970 | PS5-60-IE-0002E-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12971 | PS5-60-IE-0002F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001F TO PS5-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12972 | PS5-60-IE-0002F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001F TO PS5-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12973 | PS5-60-IE-0002F-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001F TO PS5-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12974 | PS5-60-IE-0002G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001G TO PS5-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-12975 | PS5-60-IE-0002G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001G TO PS5-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-12976 | PS5-60-IE-0002G-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001G TO PS5-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-12977 | PS5-60-IH-0001A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-12978 | PS5-60-IH-0001A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-12979 | PS5-60-IH-0001B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-12980 | PS5-60-IH-0001B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-12981 | PS5-60-IH-0001C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12982 | PS5-60-IH-0001C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12983 | PS5-60-IH-0001D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12984 | PS5-60-IH-0001D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12985 | PS5-60-IH-0001E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12986 | PS5-60-IH-0001E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12987 | PS5-60-IH-0001F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12988 | PS5-60-IH-0001F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12989 | PS5-60-IH-0001G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-12990 | PS5-60-IH-0001G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-12991 | PS5-60-IH-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-12992 | PS5-60-IH-0002-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-12993 | PS5-60-LA-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-12994 | PS5-60-LA-0003-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-12995 | PS5-60-PIT-8113A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BE-0027A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-12996 | PS5-60-PIT-8113B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BE-0027B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-12997 | PS5-60-PIT-8113C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-BE-0027C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12998 | PS5-60-PIT-8113D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-BE-0027D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-12999 | PS5-60-PIT-8113E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-BE-0027E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-13000 | PS5-60-PIT-8113F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001F TO PS5-60-BE-0027F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-13001 | PS5-60-PIT-8113G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001G TO PS5-60-BE-0027G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-13002 | PS5-60-PIT-8114A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BE-0027A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-13003 | PS5-60-PIT-8114B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BE-0027B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-13004 | PS5-60-PIT-8114C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-BE-0027C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-13005 | PS5-60-PIT-8114D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-BE-0027D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-13006 | PS5-60-PIT-8114E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-BE-0027E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-13007 | PS5-60-PIT-8114F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001F TO PS5-60-BE-0027F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-13008 | PS5-60-PIT-8114G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001G TO PS5-60-BE-0027G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4487 | PS5-03-RDOS-1401-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-RMAC-1411 TO PS5-03-RDOS-1401 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4488 | PS5-03-RDOS-1402-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-RDOS-1401 TO PS5-03-RDOS-1402 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4489 | PS5-03-RDOS-1403-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-RDOS-1402 TO PS5-03-RDOS-1403 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4490 | PS5-03-RDOS-1404-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-RDOS-1403 TO PS5-03-RDOS-1404 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4491 | PS5-03-RDOS-1405-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-RDOS-1404 TO PS5-03-RDOS-1405 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4492 | PS5-03-RDOS-1406-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-RDOS-1503 TO PS5-03-RDOS-1406 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4493 | PS5-03-RDOS-1407-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-RDOS-1405 TO PS5-03-RDOS-1407 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4494 | PS5-03-RDOS-1408-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-RDOS-1407 TO PS5-03-RDOS-1408 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4540 | PS5-03-RMAC-1410-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-RDOS-2103 TO PS5-03-RMAC-1410 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4541 | PS5-03-RMAC-1411-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-RDOS-1406 TO PS5-03-RMAC-1411 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4888 | PS5-60-BE-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4889 | PS5-60-BE-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4890 | PS5-60-BE-0004A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0001A TO PS5-60-BE-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4891 | PS5-60-BE-0004B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0001B TO PS5-60-BE-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4892 | PS5-60-BE-0004C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0001C TO PS5-60-BE-0004C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4893 | PS5-60-BE-0004D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0001D TO PS5-60-BE-0004D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4894 | PS5-60-BE-0004E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0001E TO PS5-60-BE-0004E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4895 | PS5-60-BE-0004F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0001F TO PS5-60-BE-0004F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4896 | PS5-60-BE-0004G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0001G TO PS5-60-BE-0004G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4897 | PS5-60-BI-0001A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4898 | PS5-60-BI-0001A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4899 | PS5-60-BI-0001B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4900 | PS5-60-BI-0001B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4901 | PS5-60-BI-0001C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4902 | PS5-60-BI-0001C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4903 | PS5-60-BI-0001D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4904 | PS5-60-BI-0001D-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4905 | PS5-60-BI-0001E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0001E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4906 | PS5-60-BI-0001E-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0001E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4907 | PS5-60-BI-0001F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0001F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4908 | PS5-60-BI-0001F-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0001F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4909 | PS5-60-BI-0001G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0001G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4910 | PS5-60-BI-0001G-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0001G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4911 | PS5-60-BI-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4912 | PS5-60-BI-0002-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4913 | PS5-60-BI-0002-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4914 | PS5-60-BI-0002-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4915 | PS5-60-BI-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4916 | PS5-60-BI-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4917 | PS5-60-BI-0004A-CCO1 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4918 | PS5-60-BI-0004B-CCO1 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4919 | PS5-60-BI-0004C-CCO1 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-BI-0004C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4920 | PS5-60-BI-0004D-CCO1 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-BI-0004D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4921 | PS5-60-BI-0004E-CCO1 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-BI-0004E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4922 | PS5-60-BI-0004F-CCO1 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001F TO PS5-60-BI-0004F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4923 | PS5-60-BI-0004G-CCO1 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001G TO PS5-60-BI-0004G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4924 | PS5-60-BI-0005A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0005A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4925 | PS5-60-BI-0005A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0005A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4926 | PS5-60-BI-0005B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0005B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4927 | PS5-60-BI-0005B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0005B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4928 | PS5-60-BI-0005C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0005C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4929 | PS5-60-BI-0005C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0005C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4930 | PS5-60-BI-0005D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0005D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4931 | PS5-60-BI-0005D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0005D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4932 | PS5-60-BI-0005E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0005E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4933 | PS5-60-BI-0005E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0005E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4934 | PS5-60-BI-0005F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0005F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4935 | PS5-60-BI-0005F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0005F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4936 | PS5-60-BI-0005G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0005G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4937 | PS5-60-BI-0005G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0005G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4938 | PS5-60-BI-0006A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4939 | PS5-60-BI-0006A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4940 | PS5-60-BI-0006A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4941 | PS5-60-BI-0006A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4942 | PS5-60-BI-0006A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4943 | PS5-60-BI-0006A-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4944 | PS5-60-BI-0006B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4945 | PS5-60-BI-0006B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4946 | PS5-60-BI-0006B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4947 | PS5-60-BI-0006B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4948 | PS5-60-BI-0006B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4949 | PS5-60-BI-0006B-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4950 | PS5-60-BI-0006C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4951 | PS5-60-BI-0006C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4952 | PS5-60-BI-0006C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4953 | PS5-60-BI-0006C-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4954 | PS5-60-BI-0006C-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4955 | PS5-60-BI-0006C-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4956 | PS5-60-BI-0006D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4957 | PS5-60-BI-0006D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4958 | PS5-60-BI-0006D-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4959 | PS5-60-BI-0006D-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4960 | PS5-60-BI-0006D-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4961 | PS5-60-BI-0006D-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4962 | PS5-60-BI-0006E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4963 | PS5-60-BI-0006E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4964 | PS5-60-BI-0006E-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4965 | PS5-60-BI-0006E-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4966 | PS5-60-BI-0006E-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4967 | PS5-60-BI-0006E-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4968 | PS5-60-BI-0006F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4969 | PS5-60-BI-0006F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4970 | PS5-60-BI-0006F-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4971 | PS5-60-BI-0006F-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4972 | PS5-60-BI-0006F-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4973 | PS5-60-BI-0006F-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4974 | PS5-60-BI-0006G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4975 | PS5-60-BI-0006G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4976 | PS5-60-BI-0006G-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4977 | PS5-60-BI-0006G-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4978 | PS5-60-BI-0006G-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4979 | PS5-60-BI-0006G-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-4980 | PS5-60-BI-0008A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4981 | PS5-60-BI-0008A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4982 | PS5-60-BI-0008B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4983 | PS5-60-BI-0008B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4984 | PS5-60-BI-0009A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0009A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4985 | PS5-60-BI-0009A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0009A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4986 | PS5-60-BI-0009B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0009B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4987 | PS5-60-BI-0009B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0009B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-4988 | PS5-60-BI-0010A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0010A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4989 | PS5-60-BI-0010A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0010A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4990 | PS5-60-BI-0010B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0010B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4991 | PS5-60-BI-0010B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0010B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4992 | PS5-60-BI-0011A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4993 | PS5-60-BI-0011A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4994 | PS5-60-BI-0011B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4995 | PS5-60-BI-0011B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4996 | PS5-60-BI-0012A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0012A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4997 | PS5-60-BI-0012A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0012A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4998 | PS5-60-BI-0012B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0012B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-4999 | PS5-60-BI-0012B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0012B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5000 | PS5-60-BI-0013A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0013A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5001 | PS5-60-BI-0013A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0013A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5002 | PS5-60-BI-0013B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0013B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5003 | PS5-60-BI-0013B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0013B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5004 | PS5-60-BI-0014A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0014A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5005 | PS5-60-BI-0014A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0014A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5006 | PS5-60-BI-0014B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0014B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5007 | PS5-60-BI-0014B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0014B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5008 | PS5-60-BI-0016A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5009 | PS5-60-BI-0016A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5010 | PS5-60-BI-0016A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5011 | PS5-60-BI-0016A-CCO4 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5012 | PS5-60-BI-0016B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5013 | PS5-60-BI-0016B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5014 | PS5-60-BI-0016B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5015 | PS5-60-BI-0016B-CCO4 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5016 | PS5-60-BI-0016C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5017 | PS5-60-BI-0016C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5018 | PS5-60-BI-0016C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5019 | PS5-60-BI-0016C-CCO4 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5020 | PS5-60-BI-0016D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5021 | PS5-60-BI-0016D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5022 | PS5-60-BI-0016D-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5023 | PS5-60-BI-0016D-CCO4 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5024 | PS5-60-BI-0016E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0016E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5025 | PS5-60-BI-0016E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0016E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5026 | PS5-60-BI-0016E-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0016E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5027 | PS5-60-BI-0016E-CCO4 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-BI-0016E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5028 | PS5-60-BI-0016F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0016F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5029 | PS5-60-BI-0016F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0016F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5030 | PS5-60-BI-0016F-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0016F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5031 | PS5-60-BI-0016F-CCO4 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001F TO PS5-60-BI-0016F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5032 | PS5-60-BI-0016G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0016G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5033 | PS5-60-BI-0016G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0016G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5034 | PS5-60-BI-0016G-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0016G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5035 | PS5-60-BI-0016G-CCO4 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001G TO PS5-60-BI-0016G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5036 | PS5-60-BI-0017A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0017A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5037 | PS5-60-BI-0017B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0017B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5038 | PS5-60-BI-0017C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0017C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5039 | PS5-60-BI-0017D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0017D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5040 | PS5-60-BI-0017E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0017E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5041 | PS5-60-BI-0017F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0017F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5042 | PS5-60-BI-0017G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0017G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5043 | PS5-60-BI-0019A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0019A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5044 | PS5-60-BI-0019A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0019A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5045 | PS5-60-BI-0019B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0019B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5046 | PS5-60-BI-0019B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0019B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5047 | PS5-60-BI-0019C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0019C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5048 | PS5-60-BI-0019C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0019C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5049 | PS5-60-BI-0019D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0019D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5050 | PS5-60-BI-0019D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0019D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5051 | PS5-60-BI-0019E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0019E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5052 | PS5-60-BI-0019E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0019E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5053 | PS5-60-BI-0019F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0019F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5054 | PS5-60-BI-0019F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0019F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5055 | PS5-60-BI-0019G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0019G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5056 | PS5-60-BI-0019G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0019G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5057 | PS5-60-IE-0002B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5058 | PS5-60-IE-0002C-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5059 | PS5-60-IE-0002D-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5060 | PS5-60-IE-0002E-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5061 | PS5-60-IE-0002F-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5062 | PS5-60-IE-0002G-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5063 | PS5-60-IE-0003A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5064 | PS5-60-IE-0003A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5065 | PS5-60-IE-0003A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5066 | PS5-60-IE-0003A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5067 | PS5-60-IE-0003A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5068 | PS5-60-IE-0003A-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5069 | PS5-60-IE-0003A-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5070 | PS5-60-IE-0003A-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5071 | PS5-60-IE-0003A-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5072 | PS5-60-IE-0003A-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5073 | PS5-60-IE-0003A-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5074 | PS5-60-IE-0003A-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5075 | PS5-60-IE-0003A-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5076 | PS5-60-IE-0003A-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5081 | PS5-60-IE-0003A-CC25 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41100A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5082 | PS5-60-IE-0003A-CC26 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41100B TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5083 | PS5-60-IE-0003B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5084 | PS5-60-IE-0003B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5085 | PS5-60-IE-0003B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5086 | PS5-60-IE-0003B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5087 | PS5-60-IE-0003B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5088 | PS5-60-IE-0003B-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5089 | PS5-60-IE-0003B-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5090 | PS5-60-IE-0003B-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5091 | PS5-60-IE-0003B-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5092 | PS5-60-IE-0003B-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5093 | PS5-60-IE-0003B-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5094 | PS5-60-IE-0003B-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5095 | PS5-60-IE-0003B-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5096 | PS5-60-IE-0003B-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5101 | PS5-60-IE-0003B-CC25 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41200A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5102 | PS5-60-IE-0003B-CC26 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41200B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5103 | PS5-60-IE-0003C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5104 | PS5-60-IE-0003C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5105 | PS5-60-IE-0003C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5106 | PS5-60-IE-0003C-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5107 | PS5-60-IE-0003C-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5108 | PS5-60-IE-0003C-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5109 | PS5-60-IE-0003C-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5110 | PS5-60-IE-0003C-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5111 | PS5-60-IE-0003C-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5112 | PS5-60-IE-0003C-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5113 | PS5-60-IE-0003C-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5114 | PS5-60-IE-0003C-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5115 | PS5-60-IE-0003C-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5116 | PS5-60-IE-0003C-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5121 | PS5-60-IE-0003C-CC25 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41300A TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5122 | PS5-60-IE-0003C-CC26 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41300B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5123 | PS5-60-IE-0003D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5124 | PS5-60-IE-0003D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5125 | PS5-60-IE-0003D-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5126 | PS5-60-IE-0003D-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5127 | PS5-60-IE-0003D-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5128 | PS5-60-IE-0003D-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5129 | PS5-60-IE-0003D-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5130 | PS5-60-IE-0003D-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5131 | PS5-60-IE-0003D-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5132 | PS5-60-IE-0003D-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5133 | PS5-60-IE-0003D-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5134 | PS5-60-IE-0003D-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5135 | PS5-60-IE-0003D-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5136 | PS5-60-IE-0003D-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5141 | PS5-60-IE-0003D-CC25 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41400A TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5142 | PS5-60-IE-0003D-CC26 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41400B TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5143 | PS5-60-IE-0003E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5144 | PS5-60-IE-0003E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5145 | PS5-60-IE-0003E-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5146 | PS5-60-IE-0003E-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5147 | PS5-60-IE-0003E-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5148 | PS5-60-IE-0003E-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5149 | PS5-60-IE-0003E-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5150 | PS5-60-IE-0003E-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5151 | PS5-60-IE-0003E-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5152 | PS5-60-IE-0003E-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5153 | PS5-60-IE-0003E-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5154 | PS5-60-IE-0003E-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5155 | PS5-60-IE-0003E-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5156 | PS5-60-IE-0003E-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5161 | PS5-60-IE-0003E-CC25 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41500A TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5162 | PS5-60-IE-0003E-CC26 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41500B TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5163 | PS5-60-IE-0003F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IF-0001F TO PS5-60-IF-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5164 | PS5-60-IE-0003F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IF-0001F TO PS5-60-IF-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5165 | PS5-60-IE-0003F-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5166 | PS5-60-IE-0003F-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IF-0001F TO PS5-60-IF-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5167 | PS5-60-IE-0003F-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001F TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5168 | PS5-60-IE-0003F-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5169 | PS5-60-IE-0003F-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5170 | PS5-60-IE-0003F-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5171 | PS5-60-IE-0003F-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5172 | PS5-60-IE-0003F-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5173 | PS5-60-IE-0003F-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5174 | PS5-60-IE-0003F-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5175 | PS5-60-IE-0003F-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5176 | PS5-60-IE-0003F-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5181 | PS5-60-IE-0003F-CC25 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41600A TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5182 | PS5-60-IE-0003F-CC26 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41600B TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5183 | PS5-60-IE-0003G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IG-0001G TO PS5-60-IG-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5184 | PS5-60-IE-0003G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IG-0001G TO PS5-60-IG-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5185 | PS5-60-IE-0003G-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5186 | PS5-60-IE-0003G-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IG-0001G TO PS5-60-IG-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5187 | PS5-60-IE-0003G-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001G TO PS5-60-IE-0003H | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5188 | PS5-60-IE-0003G-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5189 | PS5-60-IE-0003G-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5190 | PS5-60-IE-0003G-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5191 | PS5-60-IE-0003G-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5192 | PS5-60-IE-0003G-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5193 | PS5-60-IE-0003G-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5194 | PS5-60-IE-0003G-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5195 | PS5-60-IE-0003G-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5196 | PS5-60-IE-0003G-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5201 | PS5-60-IE-0003G-CC25 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41700A TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5202 | PS5-60-IE-0003G-CC26 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41700B TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5203 | PS5-60-IE-0004-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5204 | PS5-60-IE-0004-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5205 | PS5-60-IE-0004-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5206 | PS5-60-IE-0004-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5207 | PS5-60-IE-0004-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5208 | PS5-60-IE-0004-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5209 | PS5-60-IE-0004-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5213 | PS5-60-IN-0001A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5214 | PS5-60-IN-0001A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5215 | PS5-60-IN-0001A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5216 | PS5-60-IN-0001A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5217 | PS5-60-IN-0001B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5218 | PS5-60-IN-0001B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5219 | PS5-60-IN-0001B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5220 | PS5-60-IN-0001B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5221 | PS5-60-IN-0001C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5222 | PS5-60-IN-0001C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5223 | PS5-60-IN-0001C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5224 | PS5-60-IN-0001C-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5225 | PS5-60-IN-0001D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5226 | PS5-60-IN-0001D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5227 | PS5-60-IN-0001D-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5228 | PS5-60-IN-0001D-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5229 | PS5-60-IN-0001E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0001E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5230 | PS5-60-IN-0001E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0001E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5231 | PS5-60-IN-0001E-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0001E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5232 | PS5-60-IN-0001E-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0001E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5233 | PS5-60-IN-0001F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0001F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5234 | PS5-60-IN-0001F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0001F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5235 | PS5-60-IN-0001F-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0001F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5236 | PS5-60-IN-0001F-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0001F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5237 | PS5-60-IN-0001G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0001G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5238 | PS5-60-IN-0001G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0001G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5239 | PS5-60-IN-0001G-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0001G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5240 | PS5-60-IN-0001G-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0001G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5241 | PS5-60-IN-0002A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5242 | PS5-60-IN-0002A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5243 | PS5-60-IN-0002A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5244 | PS5-60-IN-0002A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5245 | PS5-60-IN-0002A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5246 | PS5-60-IN-0002A-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5247 | PS5-60-IN-0002B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5248 | PS5-60-IN-0002B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5249 | PS5-60-IN-0002B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5250 | PS5-60-IN-0002B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5251 | PS5-60-IN-0002B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5252 | PS5-60-IN-0002B-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5253 | PS5-60-IN-0002C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5254 | PS5-60-IN-0002C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5255 | PS5-60-IN-0002C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5256 | PS5-60-IN-0002C-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5257 | PS5-60-IN-0002C-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5258 | PS5-60-IN-0002C-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5259 | PS5-60-IN-0002D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5260 | PS5-60-IN-0002D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5261 | PS5-60-IN-0002D-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5262 | PS5-60-IN-0002D-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5263 | PS5-60-IN-0002D-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5264 | PS5-60-IN-0002D-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5265 | PS5-60-IN-0002E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5266 | PS5-60-IN-0002E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5267 | PS5-60-IN-0002E-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5268 | PS5-60-IN-0002E-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5269 | PS5-60-IN-0002E-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5270 | PS5-60-IN-0002E-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5271 | PS5-60-IN-0002F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5272 | PS5-60-IN-0002F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5273 | PS5-60-IN-0002F-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5274 | PS5-60-IN-0002F-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5275 | PS5-60-IN-0002F-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5276 | PS5-60-IN-0002F-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5277 | PS5-60-IN-0002G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5278 | PS5-60-IN-0002G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5279 | PS5-60-IN-0002G-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5280 | PS5-60-IN-0002G-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5281 | PS5-60-IN-0002G-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5282 | PS5-60-IN-0002G-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5284 | PS5-60-LA-0002A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5285 | PS5-60-LA-0002A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5286 | PS5-60-LA-0002A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5287 | PS5-60-LA-0002A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5288 | PS5-60-LA-0002A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5289 | PS5-60-LA-0002A-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5290 | PS5-60-LA-0002A-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5291 | PS5-60-LA-0002A-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5292 | PS5-60-LA-0002A-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5293 | PS5-60-LA-0002B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5294 | PS5-60-LA-0002B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5295 | PS5-60-LA-0002B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5296 | PS5-60-LA-0002B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5297 | PS5-60-LA-0002B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5298 | PS5-60-LA-0002B-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5299 | PS5-60-LA-0002C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5300 | PS5-60-LA-0002C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5301 | PS5-60-LA-0002C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5302 | PS5-60-LA-0002C-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5303 | PS5-60-LA-0002C-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5304 | PS5-60-LA-0002C-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5305 | PS5-60-LA-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5316 | PS5-60-SEA-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5317 | PS5-60-SEA-0001-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5318 | PS5-60-SEA-0001-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5319 | PS5-60-SEA-0001-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5320 | PS5-60-SEA-0001-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5321 | PS5-60-SEA-0001-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5322 | PS5-60-SEA-0001-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5323 | PS5-60-SEA-0001-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5324 | PS5-60-SEA-0001-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5325 | PS5-60-SEA-0001-CC12 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5326 | PS5-60-SEA-0001-CC13 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5327 | PS5-60-SEA-0001-CC14 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5328 | PS5-60-SEA-0001-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5329 | PS5-60-SEA-0001-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5330 | PS5-60-SEA-0001-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5339 | PS5-60-VS-9101A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-VS-9101A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5340 | PS5-60-VS-9101B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-VS-9101B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5341 | PS5-60-VS-9101C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-VS-9101C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C |  | PS5-60-44 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5342 | PS5-60-VS-9101D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-VS-9101D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D |  | PS5-60-45 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5343 | PS5-60-VS-9101E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-VS-9101E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E |  | PS5-60-46 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5344 | PS5-60-VS-9101F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-VS-9101F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F |  | PS5-60-47 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5345 | PS5-60-VS-9101G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-VS-9101G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G |  | PS5-60-48 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5346 | PS5-61-BI-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5347 | PS5-61-BI-0001-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5348 | PS5-61-BI-0001-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-61-TE-0003A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5349 | PS5-61-BI-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5350 | PS5-61-BI-0002-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5351 | PS5-61-BI-0002-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-61-TE-0003B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5352 | PS5-61-BI-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-61-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5353 | PS5-61-BI-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-61-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5354 | PS5-61-BI-0003-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-61-TE-0003C TO PS5-61-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5355 | PS5-61-BI-0004-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-61-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5356 | PS5-61-BI-0004-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-61-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5357 | PS5-61-BI-0004-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-61-TE-0003D TO PS5-61-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5358 | PS5-61-BI-0005-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-61-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5359 | PS5-61-BI-0005-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-61-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5360 | PS5-61-BI-0005-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-61-TE-0003E TO PS5-61-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5361 | PS5-61-BI-0006-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-61-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5362 | PS5-61-BI-0006-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-61-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5363 | PS5-61-BI-0006-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-61-TE-0003F TO PS5-61-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00069-5364 | PS5-61-BI-0007-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-61-BI-0007 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5365 | PS5-61-BI-0007-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-61-BI-0007 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5366 | PS5-61-BI-0007-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-61-TE-0003G TO PS5-61-BI-0007 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00069-5378 | PS5-71-BI-0001A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5379 | PS5-71-BI-0001B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5382 | PS5-71-BI-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5383 | PS5-71-BI-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5384 | PS5-71-BI-0003-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5385 | PS5-71-BI-0003-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5386 | PS5-71-BI-0004-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5387 | PS5-71-BI-0005-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5388 | PS5-71-BI-0005-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5389 | PS5-71-BI-0006-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5390 | PS5-71-BI-0008A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5391 | PS5-71-BI-0008A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5392 | PS5-71-BI-0008B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5393 | PS5-71-BI-0008B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5399 | PS5-71-BI-0011A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5400 | PS5-71-BI-0011A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5401 | PS5-71-BI-0011A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5402 | PS5-71-BI-0011A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5403 | PS5-71-BI-0011A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5404 | PS5-71-BI-0011B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5405 | PS5-71-BI-0011B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5406 | PS5-71-BI-0011B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5407 | PS5-71-BI-0011B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5408 | PS5-71-BI-0011B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5467 | PS5-71-IN-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5468 | PS5-71-IN-0002-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5469 | PS5-71-IN-0002-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5470 | PS5-71-IN-0002-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5474 | PS5-71-IN-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5475 | PS5-71-IN-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5476 | PS5-71-IN-0003-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5477 | PS5-71-IN-0003-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5516 | PS5-71-MOV-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2120 TO PS5-71-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5517 | PS5-71-MOV-0001-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2124 TO PS5-71-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5518 | PS5-71-MOV-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2120 TO PS5-71-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5519 | PS5-71-MOV-0002-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2124 TO PS5-71-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5520 | PS5-71-MOV-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2121 TO PS5-71-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5521 | PS5-71-MOV-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2125 TO PS5-71-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5522 | PS5-71-MOV-0004-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2121 TO PS5-71-MOV-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5523 | PS5-71-MOV-0004-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2125 TO PS5-71-MOV-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5524 | PS5-71-MOV-0007-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2118 TO PS5-71-MOV-0007 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5525 | PS5-71-MOV-0007-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2122 TO PS5-71-MOV-0007 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5526 | PS5-71-MOV-0008-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2118 TO PS5-71-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5527 | PS5-71-MOV-0008-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2122 TO PS5-71-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5528 | PS5-71-MOV-0009-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2119 TO PS5-71-MOV-0009 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5529 | PS5-71-MOV-0009-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2123 TO PS5-71-MOV-0009 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00069-5530 | PS5-71-MOV-0010-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2119 TO PS5-71-MOV-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-5531 | PS5-71-MOV-0010-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2123 TO PS5-71-MOV-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00069-9408 | PS5-03-RMAC-1409-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SEA-0003 TO PS5-03-RMAC-1409 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00071-0027 | PS5-60-IE-0004-CX03 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-SSF1-161401 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B
T-00071-0028 | PS5-60-IE-0004-CX04 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-SSF1-161401 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B
T-00071-0029 | PS5-60-LA-0003-CX01 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-SSF1-161401 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B
T-00071-0090 | PS5-60-LA-0003-CX02 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B
T-00072-0165 | PS5-60-TW-0006G |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Thermowell | I | To be completed | PS5 - Milestone E
T-00072-0169 | PS5-60-TW-0007C |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00072-0171 | PS5-60-TW-0005F |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00072-0173 | PS5-60-TW-0007B |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Thermowell | I | To be completed | PS5 - Milestone B
T-00072-0174 | PS5-60-TW-0006C |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00072-0175 | PS5-60-TW-0008A |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Thermowell | I | To be completed | PS5 - Milestone B
T-00072-0176 | PS5-60-TW-0007D |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00072-0177 | PS5-60-TW-0008C |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00072-0179 | PS5-60-TW-0005G |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Thermowell | I | To be completed | PS5 - Milestone E
T-00072-0181 | PS5-60-TW-0008E |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00072-0182 | PS5-60-TW-0007A |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Thermowell | I | To be completed | PS5 - Milestone B
T-00072-0183 | PS5-60-TW-0006D |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00072-0184 | PS5-60-TW-0008B |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Thermowell | I | To be completed | PS5 - Milestone B
T-00072-0185 | PS5-60-TW-0007E |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00072-0186 | PS5-60-TW-0008D |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00072-0189 | PS5-60-TW-0008F |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00072-0190 | PS5-60-TW-0006E |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00072-0194 | PS5-60-TW-0006B |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Thermowell | I | To be completed | PS5 - Milestone B
T-00072-0198 | PS5-60-TW-0006A |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Thermowell | I | To be completed | PS5 - Milestone B
T-00072-0199 | PS5-60-TW-0007F |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00072-0207 | PS5-60-TW-0005A |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Thermowell | I | To be completed | PS5 - Milestone B
T-00072-0208 | PS5-60-TW-0005B |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Thermowell | I | To be completed | PS5 - Milestone B
T-00072-0209 | PS5-60-TW-0005C |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00072-0210 | PS5-60-TW-0005D |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00072-0211 | PS5-60-TW-0005E |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00072-0212 | PS5-60-TW-0006F |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00072-0213 | PS5-60-TW-0007G |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Thermowell | I | To be completed | PS5 - Milestone E
T-00072-0214 | PS5-60-TW-0008G |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Thermowell | I | To be completed | PS5 - Milestone E
T-00075-0200 | PS5-60-TG-0005C |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D
T-00075-0202 | PS5-60-TG-0006F |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D
T-00075-0204 | PS5-60-TG-0005E |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D
T-00075-0205 | PS5-60-TG-0008D |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D
T-00075-0211 | PS5-60-TG-0005A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B
T-00075-0215 | PS5-60-TG-0007G |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone E
T-00075-0216 | PS5-60-TG-0005F |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D
T-00075-0217 | PS5-60-TG-0006G |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone E
T-00075-0218 | PS5-60-TG-0008A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B
T-00075-0224 | PS5-60-TG-0008C |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D
T-00075-0229 | PS5-60-TG-0007D |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D
T-00075-0234 | PS5-60-TG-0008E |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D
T-00075-0239 | PS5-60-TG-0007A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B
T-00075-0242 | PS5-60-TG-0008F |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D
T-00075-0244 | PS5-60-TG-0007C |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D
T-00075-0250 | PS5-60-TG-0005G |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone E
T-00075-0251 | PS5-60-TG-0006D |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D
T-00075-0252 | PS5-60-TG-0007E |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D
T-00075-0264 | PS5-60-TG-0005D |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D
T-00075-0265 | PS5-60-TG-0006A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B
T-00075-0266 | PS5-60-TG-0006C |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D
T-00075-0267 | PS5-60-TG-0006E |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D
T-00075-0268 | PS5-60-TG-0007F |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone D
T-00075-0269 | PS5-60-TG-0008G |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone E
T-00075-0270 | PS5-60-TG-0006B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B
T-00075-0271 | PS5-60-TG-0005B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B
T-00075-0272 | PS5-60-TG-0007B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B
T-00075-0273 | PS5-60-TG-0008B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B
T-00078-0140 | PS5-71-MOV-0007 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone H
T-00078-0143 | PS5-71-MOV-0010 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone B
T-00078-0144 | PS5-71-MOV-0003 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone H
T-00078-0147 | PS5-71-MOV-0004 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone B
T-00078-0149 | PS5-71-MOV-0001 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone H
T-00078-0151 | PS5-71-MOV-0002 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone B
T-00078-0152 | PS5-71-MOV-0008 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone B
T-00078-0153 | PS5-71-MOV-0009 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone H
T-00083-0865 | PS5-03-RDOS-1401 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E
T-00083-0866 | PS5-03-RDOS-1402 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E
T-00083-0867 | PS5-03-RDOS-1403 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E
T-00083-0868 | PS5-03-RDOS-1404 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E
T-00083-0869 | PS5-03-RDOS-1405 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E
T-00083-0870 | PS5-03-RDOS-1406 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E
T-00083-0871 | PS5-03-RDOS-1407 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E
T-00083-0872 | PS5-03-RDOS-1408 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Gas/Smoke Detector | I | To be completed | PS5 - Milestone E
T-00087-0103 | PS5-03-SEA-0003 |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FIRE ALARM CONTROL PANEL | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121133 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Indoor Cabinet/Panel | I | To be completed | PS5 - Milestone E
T-00087-0105 | PS5-60-SEA-0001 |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTION PANEL | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Indoor Cabinet/Panel | I | To be completed | PS5 - Milestone E
T-00087-0500 | PS5-60-LA-0002A |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | VTMS VIBRATION AND TEMPERATURE MONITORING SYSTEM | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Indoor Cabinet/Panel | I | To be completed | PS5 - Milestone B
T-00087-0501 | PS5-60-LA-0002B |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | VTMS VIBRATION AND TEMPERATURE MONITORING SYSTEM | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Indoor Cabinet/Panel | I | To be completed | PS5 - Milestone D
T-00087-0502 | PS5-60-LA-0002C |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | VTMS VIBRATION AND TEMPERATURE MONITORING SYSTEM | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Indoor Cabinet/Panel | I | To be completed | PS5 - Milestone D
T-00087-0528 | PS5-60-LA-0003 |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Remote Access Panel | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Indoor Cabinet/Panel | I | To be completed | PS5 - Milestone B
T-00090-0179 | PS5-60-UR-8100A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION PACKAGE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0180 | PS5-60-UR-8100B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION PACKAGE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0181 | PS5-60-UR-8100C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION PACKAGE C | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0182 | PS5-60-UR-8100D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION PACKAGE D | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0183 | PS5-60-UR-8100E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION PACKAGE E | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0184 | PS5-60-UR-8100F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION PACKAGE F | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0185 | PS5-60-UR-8100G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION PACKAGE G | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00090-0188 | PS5-60-UA-5100 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COMPRESSOR AIR STARTING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135128 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0189 | PS5-60-UO-81100A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0190 | PS5-60-UO-81100B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0191 | PS5-60-UO-81100C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0192 | PS5-60-UO-81100D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0193 | PS5-60-UO-81100E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0194 | PS5-60-UO-81100F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0195 | PS5-60-UO-81100G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00090-0196 | PS5-60-UZ-8200A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0197 | PS5-60-UZ-8200B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0198 | PS5-60-UZ-8200C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0199 | PS5-60-UZ-8200D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0200 | PS5-60-UZ-8200E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0201 | PS5-60-UZ-8200F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F |  | PS5-60-40 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0202 | PS5-60-VS-9100A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0203 | PS5-60-VS-9100B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0204 | PS5-60-VS-9100C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C |  | PS5-60-44 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0205 | PS5-60-VS-9100D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D |  | PS5-60-45 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0206 | PS5-60-VS-9100E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E |  | PS5-60-46 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0207 | PS5-60-VS-9100F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F |  | PS5-60-47 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0208 | PS5-60-VS-9100G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G |  | PS5-60-48 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00090-0210 | PS5-71-UZ-6800A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CRUDE FUEL SEPARATOR MODULE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135002 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Package | M | To be completed | PS5 - Milestone H
T-00090-0211 | PS5-71-UZ-6800B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CRUDE FUEL SEPARATOR MODULE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135002 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Package | M | To be completed | PS5 - Milestone H
T-00090-0215 | PS5-60-EA-2100A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0216 | PS5-60-EA-2100B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0217 | PS5-60-EA-21100A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0218 | PS5-60-EA-21100B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0219 | PS5-60-EA-21100C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0220 | PS5-60-EA-21100D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0221 | PS5-60-EA-21100E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0222 | PS5-60-EA-21100F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0223 | PS5-60-EA-21100G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00090-0224 | PS5-60-EA-21200A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0225 | PS5-60-EA-21200B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0226 | PS5-60-EA-21200C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0227 | PS5-60-EA-21200D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0228 | PS5-60-EA-21200E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0229 | PS5-60-EA-21200F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0230 | PS5-60-EA-21200G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00090-0231 | PS5-60-EA-2200A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0232 | PS5-60-EA-2200B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0233 | PS5-60-EA-2300A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0234 | PS5-60-EA-2300B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0235 | PS5-60-EA-2400A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0236 | PS5-60-EA-2400B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0237 | PS5-60-EA-2500A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0238 | PS5-60-EA-2500B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0239 | PS5-60-EA-2600A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0240 | PS5-60-EA-2600B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0241 | PS5-60-EA-2700A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00090-0242 | PS5-60-EA-2700B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00090-0243 | PS5-60-EA-2800A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0244 | PS5-60-EA-2800B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0245 | PS5-60-EA-2800C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0246 | PS5-60-EA-2800D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0247 | PS5-60-EA-2800E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0248 | PS5-60-EA-2800F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F |  | PS5-60-40 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0249 | PS5-60-EA-2800G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00090-0250 | PS5-60-EA-2900A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0251 | PS5-60-EA-2900B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0252 | PS5-60-EA-2900C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0253 | PS5-60-EA-2900D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0254 | PS5-60-EA-2900E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0255 | PS5-60-EA-2900F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0256 | PS5-60-EA-2900G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00090-0257 | PS5-60-TCV-0001A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0258 | PS5-60-TCV-0001B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0259 | PS5-60-TCV-0001C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0260 | PS5-60-TCV-0001D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0261 | PS5-60-TCV-0001E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0262 | PS5-60-TCV-0001F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0263 | PS5-60-TCV-0001G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00090-0264 | PS5-60-TCV-0002A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0265 | PS5-60-TCV-0002B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0266 | PS5-60-TCV-0002C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0267 | PS5-60-TCV-0002D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0268 | PS5-60-TCV-0002E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0269 | PS5-60-TCV-0002F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0270 | PS5-60-TCV-0002G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00090-0271 | PS5-60-UA-5200 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INSTRUMENT AIR COMPRESSOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135127 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0272 | PS5-60-UR-8200A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0273 | PS5-60-UR-8200B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0274 | PS5-60-UR-8200C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0275 | PS5-60-UR-8200D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0276 | PS5-60-UR-8200E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0277 | PS5-60-UR-8200F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0278 | PS5-60-UR-8200G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00090-0279 | PS5-60-UZ-8200G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00090-0280 | PS5-60-UZ-8900A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0281 | PS5-60-UZ-8900B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0282 | PS5-60-UZ-8900C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0283 | PS5-60-UZ-8900D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0284 | PS5-60-UZ-8900E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0285 | PS5-60-UZ-8900F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0286 | PS5-60-UZ-8900G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00090-0288 | PS5-71-UZ-6400 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CRUDE FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135004 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Package | M | To be completed | PS5 - Milestone H
T-00090-0289 | PS5-71-UZ-6700 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DIESEL FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135126 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0436 | PS5-60-UR-8300A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0437 | PS5-60-UR-8300B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Package | M | To be completed | PS5 - Milestone B
T-00090-0438 | PS5-60-UR-8300C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0439 | PS5-60-UR-8300D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0440 | PS5-60-UR-8300E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0441 | PS5-60-UR-8300F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F |  | PS5-60-40 |  |  | Package | M | To be completed | PS5 - Milestone D
T-00090-0442 | PS5-60-UR-8300G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | Package | M | To be completed | PS5 - Milestone E
T-00115-0006 | PS5-60-YF-1700A |  |  |  |  | CHX01 - Strainer / Filter | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL FITLER SE - LOOSE / REMOTE MOUNTED | EACOP | CPP AGI |  |  | 5 |  |  | TZ-MID-68-WPR2-135134 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-03-30 12:07 | PS5-60-56 |  |  | Strainer/Filter | M | Closed | PS5 - Milestone B
T-00115-0007 | PS5-60-YF-1700B |  |  |  |  | CHX01 - Strainer / Filter | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL FITLER SE - LOOSE / REMOTE MOUNTED | EACOP | CPP AGI |  |  | 5 |  |  | TZ-MID-68-WPR2-135134 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-03-30 12:08 | PS5-60-58 |  |  | Strainer/Filter | M | Closed | PS5 - Milestone B
T-00115-0008 | PS5-60-YF-1700C |  |  |  |  | CHX01 - Strainer / Filter | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL FITLER SE - LOOSE / REMOTE MOUNTED | EACOP | CPP AGI |  |  | 5 |  |  | TZ-MID-68-WPR2-135134 | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 2026-03-30 12:08 | PS5-60-60 |  |  | Strainer/Filter | M | Closed | PS5 - Milestone D
T-00115-0009 | PS5-60-YF-1700D |  |  |  |  | CHX01 - Strainer / Filter | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL FITLER SE - LOOSE / REMOTE MOUNTED | EACOP | CPP AGI |  |  | 5 |  |  | TZ-MID-68-WPR2-135134 | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2026-03-30 12:08 | PS5-60-62 |  |  | Strainer/Filter | M | Closed | PS5 - Milestone D
T-00115-0010 | PS5-60-YF-1700E |  |  |  |  | CHX01 - Strainer / Filter | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL FITLER SE - LOOSE / REMOTE MOUNTED | EACOP | CPP AGI |  |  | 5 |  |  | TZ-MID-68-WPR2-135134 | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | 2026-04-05 11:30 | PS5-60-64 |  |  | Strainer/Filter | M | Closed | PS5 - Milestone D
T-00115-0011 | PS5-60-YF-1700F |  |  |  |  | CHX01 - Strainer / Filter | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL FITLER SE - LOOSE / REMOTE MOUNTED | EACOP | CPP AGI |  |  | 5 |  |  | TZ-MID-68-WPR2-135134 | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | 2026-03-30 12:11 | PS5-60-66 |  |  | Strainer/Filter | M | Closed | PS5 - Milestone D
T-00115-0012 | PS5-60-YF-1700G |  |  |  |  | CHX01 - Strainer / Filter | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL FITLER SE - LOOSE / REMOTE MOUNTED | EACOP | CPP AGI |  |  | 5 |  |  | TZ-MID-68-WPR2-135134 | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | 2026-03-30 12:12 | PS5-60-68 |  |  | Strainer/Filter | M | Closed | PS5 - Milestone E
T-00135-0220 | PS5-60-UR-8100A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-14 05:32 | PS5-60-01 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0221 | PS5-60-UR-8100B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-14 05:33 | PS5-60-04 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0222 | PS5-60-UR-8100C |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE C | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-02-14 05:33 | PS5-60-07 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0223 | PS5-60-UR-8100D |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE D | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-02-14 05:34 | PS5-60-10 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0224 | PS5-60-UR-8100E |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE E | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-02-14 05:34 | PS5-60-13 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0225 | PS5-60-UR-8100F |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE F | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-02-14 05:37 | PS5-60-16 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0226 | PS5-60-UR-8100G |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE G | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-02-14 05:37 | PS5-60-19 |  |  | Package | M | Closed | PS5 - Milestone E
T-00135-0229 | PS5-60-UA-5100 |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COMPRESSOR AIR STARTING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135128 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-04-13 06:58 | PS5-60-27 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0230 | PS5-60-UO-81100A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2026-01-24 12:49 | PS5-60-49 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0231 | PS5-60-UO-81100B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2026-01-24 12:50 | PS5-60-50 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0232 | PS5-60-UO-81100C |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | 2026-01-24 12:51 | PS5-60-51 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0233 | PS5-60-UO-81100D |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | 2026-01-24 12:52 | PS5-60-52 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0234 | PS5-60-UO-81100E |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | 2026-01-24 12:53 | PS5-60-53 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0235 | PS5-60-UO-81100F |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | 2026-01-24 12:54 | PS5-60-54 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0236 | PS5-60-UO-81100G |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | 2026-01-24 12:54 | PS5-60-55 |  |  | Package | M | Closed | PS5 - Milestone E
T-00135-0237 | PS5-60-UZ-8200A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-01-24 12:55 | PS5-60-35 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0238 | PS5-60-UZ-8200B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-01-24 12:55 | PS5-60-36 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0239 | PS5-60-UZ-8200C |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C | 2026-01-24 13:09 | PS5-60-37 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0240 | PS5-60-UZ-8200D |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D | 2026-01-24 13:09 | PS5-60-38 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0241 | PS5-60-UZ-8200E |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E | 2026-01-24 13:10 | PS5-60-39 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0242 | PS5-60-UZ-8200F |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F | 2026-01-24 12:56 | PS5-60-40 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0243 | PS5-60-VS-9100A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-03-30 11:55 | PS5-60-42 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0244 | PS5-60-VS-9100B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-03-30 11:57 | PS5-60-43 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0245 | PS5-60-VS-9100C |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | 2026-03-30 12:01 | PS5-60-44 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0246 | PS5-60-VS-9100D |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | 2026-03-30 12:02 | PS5-60-45 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0247 | PS5-60-VS-9100E |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | 2026-03-30 12:01 | PS5-60-46 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0248 | PS5-60-VS-9100F |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | 2026-03-30 12:00 | PS5-60-47 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0249 | PS5-60-VS-9100G |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | 2026-03-30 11:59 | PS5-60-48 |  |  | Package | M | Closed | PS5 - Milestone E
T-00135-0251 | PS5-71-UZ-6800A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | CRUDE FUEL SEPARATOR MODULE A | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135002 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-04-23 10:29 | PS5-71-06 |  |  | Package | M | Closed | PS5 - Milestone H
T-00135-0252 | PS5-71-UZ-6800B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | CRUDE FUEL SEPARATOR MODULE B | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135002 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-04-23 10:29 | PS5-71-06 |  |  | Package | M | Closed | PS5 - Milestone H
T-00135-0256 | PS5-60-EA-2100A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-30 13:48 | PS5-60-70 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0257 | PS5-60-EA-2100B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-30 13:49 | PS5-60-70 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0258 | PS5-60-EA-21100A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-04 07:38 | PS5-60-01 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0259 | PS5-60-EA-21100B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-04 10:58 | PS5-60-04 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0260 | PS5-60-EA-21100C |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-04 10:59 | PS5-60-07 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0261 | PS5-60-EA-21100D |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-05 11:19 | PS5-60-10 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0262 | PS5-60-EA-21100E |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-04-05 11:19 | PS5-60-13 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0263 | PS5-60-EA-21100F |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-04-05 11:20 | PS5-60-16 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0264 | PS5-60-EA-21100G |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-04-05 11:21 | PS5-60-19 |  |  | Package | M | Closed | PS5 - Milestone E
T-00135-0265 | PS5-60-EA-21200A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-05 11:22 | PS5-60-01 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0266 | PS5-60-EA-21200B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-05 11:22 | PS5-60-04 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0267 | PS5-60-EA-21200C |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-05 11:22 | PS5-60-07 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0268 | PS5-60-EA-21200D |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-05 11:23 | PS5-60-10 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0269 | PS5-60-EA-21200E |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-04-05 11:23 | PS5-60-13 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0270 | PS5-60-EA-21200F |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-04-05 11:24 | PS5-60-16 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0271 | PS5-60-EA-21200G |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-04-05 11:24 | PS5-60-19 |  |  | Package | M | Closed | PS5 - Milestone E
T-00135-0272 | PS5-60-EA-2200A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-30 13:50 | PS5-60-71 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0273 | PS5-60-EA-2200B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-30 13:51 | PS5-60-71 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0274 | PS5-60-EA-2300A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-30 13:52 | PS5-60-72 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0275 | PS5-60-EA-2300B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-30 13:55 | PS5-60-72 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0276 | PS5-60-EA-2400A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-30 13:56 | PS5-60-73 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0277 | PS5-60-EA-2400B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-30 13:57 | PS5-60-73 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0278 | PS5-60-EA-2500A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-06-30 13:57 | PS5-60-74 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0279 | PS5-60-EA-2500B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-06-30 13:57 | PS5-60-74 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0280 | PS5-60-EA-2600A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-06-30 13:58 | PS5-60-75 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0281 | PS5-60-EA-2600B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-06-30 13:58 | PS5-60-75 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0282 | PS5-60-EA-2700A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-06-30 13:59 | PS5-60-76 |  |  | Package | M | Closed | PS5 - Milestone E
T-00135-0283 | PS5-60-EA-2700B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-06-30 13:59 | PS5-60-76 |  |  | Package | M | Closed | PS5 - Milestone E
T-00135-0284 | PS5-60-EA-2800A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-04-25 08:26 | PS5-60-35 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0285 | PS5-60-EA-2800B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-04-25 08:27 | PS5-60-36 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0286 | PS5-60-EA-2800C |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C | 2026-04-25 08:27 | PS5-60-37 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0287 | PS5-60-EA-2800D |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D | 2026-04-25 08:28 | PS5-60-38 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0288 | PS5-60-EA-2800E |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E | 2026-04-25 08:28 | PS5-60-39 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0289 | PS5-60-EA-2800F |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F | 2026-04-25 08:28 | PS5-60-40 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0290 | PS5-60-EA-2800G |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G | 2026-04-25 08:29 | PS5-60-41 |  |  | Package | M | Closed | PS5 - Milestone E
T-00135-0291 | PS5-60-EA-2900A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-04-05 11:24 | PS5-60-56 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0292 | PS5-60-EA-2900B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-04-05 11:25 | PS5-60-58 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0293 | PS5-60-EA-2900C |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 2026-04-05 11:25 | PS5-60-60 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0294 | PS5-60-EA-2900D |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2026-04-05 11:25 | PS5-60-62 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0295 | PS5-60-EA-2900E |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | 2026-04-05 11:26 | PS5-60-64 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0296 | PS5-60-EA-2900F |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | 2026-04-05 11:27 | PS5-60-66 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0297 | PS5-60-EA-2900G |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | 2026-04-05 11:29 | PS5-60-68 |  |  | Package | M | Closed | PS5 - Milestone E
T-00135-0298 | PS5-60-TCV-0001A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-14 10:24 | PS5-60-70 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0299 | PS5-60-TCV-0001B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-05-14 10:25 | PS5-60-71 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0300 | PS5-60-TCV-0001C |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-05 11:44 | PS5-60-72 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0301 | PS5-60-TCV-0001D |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-05-14 10:26 | PS5-60-73 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0302 | PS5-60-TCV-0001E |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-06-05 11:45 | PS5-60-74 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0303 | PS5-60-TCV-0001F |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-05-14 10:26 | PS5-60-75 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0304 | PS5-60-TCV-0001G |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-05-14 10:27 | PS5-60-76 |  |  | Package | M | Closed | PS5 - Milestone E
T-00135-0305 | PS5-60-TCV-0002A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-14 10:27 | PS5-60-70 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0306 | PS5-60-TCV-0002B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-05-14 10:28 | PS5-60-71 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0307 | PS5-60-TCV-0002C |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-05-14 10:28 | PS5-60-72 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0308 | PS5-60-TCV-0002D |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-05-14 10:29 | PS5-60-73 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0309 | PS5-60-TCV-0002E |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-05-14 10:29 | PS5-60-74 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0310 | PS5-60-TCV-0002F |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-05-14 10:30 | PS5-60-75 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0311 | PS5-60-TCV-0002G |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-05-14 13:24 | PS5-60-76 |  |  | Package | M | Closed | PS5 - Milestone E
T-00135-0312 | PS5-60-UA-5200 |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INSTRUMENT AIR COMPRESSOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135127 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-04-13 06:59 | PS5-60-26 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0313 | PS5-60-UR-8200A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-13 07:07 | PS5-60-01 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0314 | PS5-60-UR-8200B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-13 07:08 | PS5-60-04 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0315 | PS5-60-UR-8200C |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-17 14:26 | PS5-60-07 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0316 | PS5-60-UR-8200D |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-17 14:27 | PS5-60-10 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0317 | PS5-60-UR-8200E |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-04-17 14:28 | PS5-60-13 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0318 | PS5-60-UR-8200F |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-04-17 14:28 | PS5-60-16 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0319 | PS5-60-UR-8200G |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-04-17 14:28 | PS5-60-19 |  |  | Package | M | Closed | PS5 - Milestone E
T-00135-0320 | PS5-60-UZ-8200G |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G | 2026-01-24 12:59 | PS5-60-41 |  |  | Package | M | Closed | PS5 - Milestone E
T-00135-0321 | PS5-60-UZ-8900A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-03-28 07:29 | PS5-60-56 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0322 | PS5-60-UZ-8900B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-01-24 12:59 | PS5-60-58 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0323 | PS5-60-UZ-8900C |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 2026-01-24 13:00 | PS5-60-60 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0324 | PS5-60-UZ-8900D |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2026-01-24 13:00 | PS5-60-62 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0325 | PS5-60-UZ-8900E |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | 2026-01-24 13:04 | PS5-60-64 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0326 | PS5-60-UZ-8900F |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | 2026-01-24 13:11 | PS5-60-66 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0327 | PS5-60-UZ-8900G |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | 2026-01-24 13:12 | PS5-60-68 |  |  | Package | M | Closed | PS5 - Milestone E
T-00135-0329 | PS5-71-UZ-6400 |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | CRUDE FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135004 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-04-23 10:30 | PS5-71-08 |  |  | Package | M | Closed | PS5 - Milestone H
T-00135-0330 | PS5-71-UZ-6700 |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | DIESEL FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135126 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-04-23 10:30 | PS5-71-22 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0465 | PS5-60-UR-8300A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-04-18 05:28 | PS5-60-35 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0466 | PS5-60-UR-8300B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-04-18 05:28 | PS5-60-36 |  |  | Package | M | Closed | PS5 - Milestone B
T-00135-0467 | PS5-60-UR-8300C |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C | 2026-04-18 07:21 | PS5-60-37 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0468 | PS5-60-UR-8300D |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D | 2026-04-18 05:32 | PS5-60-38 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0469 | PS5-60-UR-8300E |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E | 2026-04-18 05:32 | PS5-60-39 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0470 | PS5-60-UR-8300F |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F | 2026-04-18 05:34 | PS5-60-40 |  |  | Package | M | Closed | PS5 - Milestone D
T-00135-0471 | PS5-60-UR-8300G |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G | 2026-04-18 05:33 | PS5-60-41 |  |  | Package | M | Closed | PS5 - Milestone E
T-00140-0065 | PS5-60-TX-41100A |  |  |  |  | CDX01 - Storage tank | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING WATER EXPANSION TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-68-WPR2-135131 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Storage Tank | P | Started (not Completed) | PS5 - Milestone B
T-00140-0066 | PS5-60-TX-41100B |  |  |  |  | CDX01 - Storage tank | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING WATER EXPANSION TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-68-WPR2-135132 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Storage Tank | P | To be completed | PS5 - Milestone B
T-00140-0067 | PS5-60-TX-41200A |  |  |  |  | CDX01 - Storage tank | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING WATER EXPANSION TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-68-WPR2-135131 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Storage Tank | P | To be completed | PS5 - Milestone B
T-00140-0068 | PS5-60-TX-41200B |  |  |  |  | CDX01 - Storage tank | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING WATER EXPANSION TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-68-WPR2-135132 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Storage Tank | P | To be completed | PS5 - Milestone B
T-00140-0069 | PS5-60-TX-41300A |  |  |  |  | CDX01 - Storage tank | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING WATER EXPANSION TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-68-WPR2-135131 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Storage Tank | P | To be completed | PS5 - Milestone D
T-00140-0070 | PS5-60-TX-41300B |  |  |  |  | CDX01 - Storage tank | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING WATER EXPANSION TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-68-WPR2-135132 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Storage Tank | P | To be completed | PS5 - Milestone D
T-00140-0071 | PS5-60-TX-41400A |  |  |  |  | CDX01 - Storage tank | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING WATER EXPANSION TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-68-WPR2-135131 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Storage Tank | P | To be completed | PS5 - Milestone D
T-00140-0072 | PS5-60-TX-41400B |  |  |  |  | CDX01 - Storage tank | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING WATER EXPANSION TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-68-WPR2-135132 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Storage Tank | P | To be completed | PS5 - Milestone D
T-00140-0073 | PS5-60-TX-41500A |  |  |  |  | CDX01 - Storage tank | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING WATER EXPANSION TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-68-WPR2-135131 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Storage Tank | P | To be completed | PS5 - Milestone D
T-00140-0074 | PS5-60-TX-41500B |  |  |  |  | CDX01 - Storage tank | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING WATER EXPANSION TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-68-WPR2-135132 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Storage Tank | P | To be completed | PS5 - Milestone D
T-00140-0075 | PS5-60-TX-41600A |  |  |  |  | CDX01 - Storage tank | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING WATER EXPANSION TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-68-WPR2-135131 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Storage Tank | P | To be completed | PS5 - Milestone D
T-00140-0076 | PS5-60-TX-41600B |  |  |  |  | CDX01 - Storage tank | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING WATER EXPANSION TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-68-WPR2-135132 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Storage Tank | P | To be completed | PS5 - Milestone D
T-00140-0077 | PS5-60-TX-41700A |  |  |  |  | CDX01 - Storage tank | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING WATER EXPANSION TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-68-WPR2-135131 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Storage Tank | P | To be completed | PS5 - Milestone E
T-00140-0078 | PS5-60-TX-41700B |  |  |  |  | CDX01 - Storage tank | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING WATER EXPANSION TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-68-WPR2-135132 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Storage Tank | P | To be completed | PS5 - Milestone E
T-00141-0132 | PS5-60-01_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Pipework | P | To be completed | PS5 - Milestone B
T-00141-0133 | PS5-60-04_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Pipework | P | To be completed | PS5 - Milestone B
T-00141-0134 | PS5-60-07_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0135 | PS5-60-10_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0136 | PS5-60-13_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0137 | PS5-60-16_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0138 | PS5-60-19_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Pipework | P | To be completed | PS5 - Milestone E
T-00141-0142 | PS5-60-26_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | Pipework | P | To be completed | PS5 - Milestone B
T-00141-0143 | PS5-60-27_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Pipework | P | To be completed | PS5 - Milestone B
T-00141-0151 | PS5-60-35_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Pipework | P | To be completed | PS5 - Milestone B
T-00141-0152 | PS5-60-36_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Pipework | P | To be completed | PS5 - Milestone B
T-00141-0153 | PS5-60-37_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0154 | PS5-60-38_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0155 | PS5-60-39_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0156 | PS5-60-40_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F |  | PS5-60-40 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0157 | PS5-60-41_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | Pipework | P | To be completed | PS5 - Milestone E
T-00141-0158 | PS5-60-42_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Pipework | P | To be completed | PS5 - Milestone B
T-00141-0159 | PS5-60-43_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Pipework | P | To be completed | PS5 - Milestone B
T-00141-0160 | PS5-60-44_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C |  | PS5-60-44 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0161 | PS5-60-45_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D |  | PS5-60-45 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0162 | PS5-60-46_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E |  | PS5-60-46 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0163 | PS5-60-47_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F |  | PS5-60-47 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0164 | PS5-60-48_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G |  | PS5-60-48 |  |  | Pipework | P | To be completed | PS5 - Milestone E
T-00141-0165 | PS5-60-49_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Pipework | P | To be completed | PS5 - Milestone B
T-00141-0166 | PS5-60-50_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Pipework | P | To be completed | PS5 - Milestone B
T-00141-0167 | PS5-60-51_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0168 | PS5-60-52_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0169 | PS5-60-53_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0170 | PS5-60-54_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0171 | PS5-60-55_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | Pipework | P | To be completed | PS5 - Milestone E
T-00141-0172 | PS5-60-56_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Pipework | P | To be completed | PS5 - Milestone B
T-00141-0173 | PS5-60-58_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Pipework | P | To be completed | PS5 - Milestone B
T-00141-0174 | PS5-60-60_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0175 | PS5-60-62_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0176 | PS5-60-64_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0177 | PS5-60-66_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0178 | PS5-60-68_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | Pipework | P | To be completed | PS5 - Milestone E
T-00141-0179 | PS5-60-70_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Pipework | P | To be completed | PS5 - Milestone B
T-00141-0180 | PS5-60-71_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Pipework | P | To be completed | PS5 - Milestone B
T-00141-0181 | PS5-60-72_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0182 | PS5-60-73_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0183 | PS5-60-74_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0184 | PS5-60-75_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Pipework | P | To be completed | PS5 - Milestone D
T-00141-0185 | PS5-60-76_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Pipework | P | To be completed | PS5 - Milestone E
T-00141-0190 | PS5-71-06_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Pipework | P | To be completed | PS5 - Milestone H
T-00141-0191 | PS5-71-08_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Pipework | P | To be completed | PS5 - Milestone H
T-00141-0201 | PS5-71-22_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Pipework | P | To be completed | PS5 - Milestone B
T-00146-0173 | PS5-60-UR-8100A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION PACKAGE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-09 11:47 | PS5-60-01 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0174 | PS5-60-UR-8100B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION PACKAGE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-09 11:51 | PS5-60-04 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0175 | PS5-60-UR-8100C |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION PACKAGE C | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-06-11 08:00 | PS5-60-07 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0176 | PS5-60-UR-8100D |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION PACKAGE D | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-11 08:00 | PS5-60-10 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0177 | PS5-60-UR-8100E |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION PACKAGE E | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-06-11 08:01 | PS5-60-13 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0178 | PS5-60-UR-8100F |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION PACKAGE F | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-06-11 08:02 | PS5-60-16 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0179 | PS5-60-UR-8100G |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION PACKAGE G | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-06-11 12:35 | PS5-60-19 |  |  | Package | M | Closed | PS5 - Milestone E
T-00146-0182 | PS5-60-UA-5100 |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COMPRESSOR AIR STARTING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135128 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-06-09 11:52 | PS5-60-27 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0183 | PS5-60-UO-81100A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2026-06-09 11:53 | PS5-60-49 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0184 | PS5-60-UO-81100B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2026-06-09 11:56 | PS5-60-50 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0185 | PS5-60-UO-81100C |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | 2026-06-11 07:57 | PS5-60-51 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0186 | PS5-60-UO-81100D |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | 2026-06-11 07:58 | PS5-60-52 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0187 | PS5-60-UO-81100E |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | 2026-06-11 07:58 | PS5-60-53 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0188 | PS5-60-UO-81100F |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | 2026-06-11 07:59 | PS5-60-54 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0189 | PS5-60-UO-81100G |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | 2026-06-11 12:34 | PS5-60-55 |  |  | Package | M | Closed | PS5 - Milestone E
T-00146-0190 | PS5-60-UZ-8200A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-06-09 11:57 | PS5-60-35 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0191 | PS5-60-UZ-8200B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-06-09 11:58 | PS5-60-36 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0192 | PS5-60-UZ-8200C |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C | 2026-06-11 08:10 | PS5-60-37 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0193 | PS5-60-UZ-8200D |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D | 2026-06-11 08:11 | PS5-60-38 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0194 | PS5-60-UZ-8200E |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E | 2026-06-11 08:12 | PS5-60-39 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0195 | PS5-60-UZ-8200F |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F | 2026-06-11 08:12 | PS5-60-40 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0196 | PS5-60-VS-9100A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-06-09 11:58 | PS5-60-42 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0197 | PS5-60-VS-9100B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-06-09 11:59 | PS5-60-43 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0198 | PS5-60-VS-9100C |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | 2026-06-11 08:16 | PS5-60-44 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0199 | PS5-60-VS-9100D |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | 2026-06-11 08:17 | PS5-60-45 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0200 | PS5-60-VS-9100E |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | 2026-06-11 08:18 | PS5-60-46 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0201 | PS5-60-VS-9100F |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | 2026-06-11 08:19 | PS5-60-47 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0202 | PS5-60-VS-9100G |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | 2026-06-11 12:38 | PS5-60-48 |  |  | Package | M | Closed | PS5 - Milestone E
T-00146-0204 | PS5-71-UZ-6800A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | CRUDE FUEL SEPARATOR MODULE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135002 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-06-12 10:53 | PS5-71-06 |  |  | Package | M | Closed | PS5 - Milestone H
T-00146-0205 | PS5-71-UZ-6800B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | CRUDE FUEL SEPARATOR MODULE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135002 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-06-12 10:54 | PS5-71-06 |  |  | Package | M | Closed | PS5 - Milestone H
T-00146-0209 | PS5-60-EA-2100A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-07-02 11:47 | PS5-60-70 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0210 | PS5-60-EA-2100B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-07-02 11:49 | PS5-60-70 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0211 | PS5-60-EA-21100A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-09 11:59 | PS5-60-01 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0212 | PS5-60-EA-21100B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-09 12:00 | PS5-60-04 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0213 | PS5-60-EA-21100C |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-06-11 07:37 | PS5-60-07 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0214 | PS5-60-EA-21100D |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-11 07:38 | PS5-60-10 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0215 | PS5-60-EA-21100E |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-06-11 07:39 | PS5-60-13 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0216 | PS5-60-EA-21100F |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-06-11 07:39 | PS5-60-16 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0217 | PS5-60-EA-21100G |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-06-11 12:30 | PS5-60-19 |  |  | Package | M | Closed | PS5 - Milestone E
T-00146-0218 | PS5-60-EA-21200A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-09 12:01 | PS5-60-01 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0219 | PS5-60-EA-21200B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-09 12:02 | PS5-60-04 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0220 | PS5-60-EA-21200C |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-06-11 07:40 | PS5-60-07 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0221 | PS5-60-EA-21200D |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-11 07:41 | PS5-60-10 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0222 | PS5-60-EA-21200E |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-06-11 07:42 | PS5-60-13 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0223 | PS5-60-EA-21200F |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-06-11 07:43 | PS5-60-16 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0224 | PS5-60-EA-21200G |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-06-11 12:30 | PS5-60-19 |  |  | Package | M | Closed | PS5 - Milestone E
T-00146-0225 | PS5-60-EA-2200A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-07-02 11:50 | PS5-60-71 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0226 | PS5-60-EA-2200B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-07-02 11:51 | PS5-60-71 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0227 | PS5-60-EA-2300A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-07-02 11:52 | PS5-60-72 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0228 | PS5-60-EA-2300B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-07-02 11:53 | PS5-60-72 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0229 | PS5-60-EA-2400A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-07-02 11:54 | PS5-60-73 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0230 | PS5-60-EA-2400B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-07-02 11:55 | PS5-60-73 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0231 | PS5-60-EA-2500A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-07-02 12:06 | PS5-60-74 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0232 | PS5-60-EA-2500B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-07-02 12:07 | PS5-60-74 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0233 | PS5-60-EA-2600A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-07-02 12:09 | PS5-60-75 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0234 | PS5-60-EA-2600B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-07-02 12:19 | PS5-60-75 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0235 | PS5-60-EA-2700A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-07-02 12:20 | PS5-60-76 |  |  | Package | M | Closed | PS5 - Milestone E
T-00146-0236 | PS5-60-EA-2700B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-07-02 12:21 | PS5-60-76 |  |  | Package | M | Closed | PS5 - Milestone E
T-00146-0237 | PS5-60-EA-2800A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-06-09 12:02 | PS5-60-35 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0238 | PS5-60-EA-2800B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-06-09 12:03 | PS5-60-36 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0239 | PS5-60-EA-2800C |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C | 2026-06-11 07:43 | PS5-60-37 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0240 | PS5-60-EA-2800D |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D | 2026-06-11 07:44 | PS5-60-38 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0241 | PS5-60-EA-2800E |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E | 2026-06-11 07:45 | PS5-60-39 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0242 | PS5-60-EA-2800F |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F | 2026-06-11 07:46 | PS5-60-40 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0243 | PS5-60-EA-2800G |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G | 2026-06-11 12:31 | PS5-60-41 |  |  | Package | M | Closed | PS5 - Milestone E
T-00146-0244 | PS5-60-EA-2900A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-06-09 12:03 | PS5-60-56 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0245 | PS5-60-EA-2900B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-06-09 12:08 | PS5-60-58 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0246 | PS5-60-EA-2900C |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 2026-06-11 07:46 | PS5-60-60 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0247 | PS5-60-EA-2900D |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2026-06-11 07:48 | PS5-60-62 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0248 | PS5-60-EA-2900E |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | 2026-06-11 07:48 | PS5-60-64 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0249 | PS5-60-EA-2900F |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | 2026-06-11 07:49 | PS5-60-66 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0250 | PS5-60-EA-2900G |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | 2026-06-11 12:31 | PS5-60-68 |  |  | Package | M | Closed | PS5 - Milestone E
T-00146-0251 | PS5-60-TCV-0001A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-09 12:09 | PS5-60-70 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0252 | PS5-60-TCV-0001B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-09 12:11 | PS5-60-71 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0253 | PS5-60-TCV-0001C |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-11 07:50 | PS5-60-72 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0254 | PS5-60-TCV-0001D |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-11 07:50 | PS5-60-73 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0255 | PS5-60-TCV-0001E |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-06-11 07:51 | PS5-60-74 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0256 | PS5-60-TCV-0001F |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-06-11 07:52 | PS5-60-75 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0257 | PS5-60-TCV-0001G |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-06-11 12:32 | PS5-60-76 |  |  | Package | M | Closed | PS5 - Milestone E
T-00146-0258 | PS5-60-TCV-0002A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-09 12:12 | PS5-60-70 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0259 | PS5-60-TCV-0002B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-09 12:13 | PS5-60-71 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0260 | PS5-60-TCV-0002C |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-11 07:53 | PS5-60-72 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0261 | PS5-60-TCV-0002D |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-11 07:54 | PS5-60-73 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0262 | PS5-60-TCV-0002E |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-06-11 07:55 | PS5-60-74 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0263 | PS5-60-TCV-0002F |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-06-11 07:56 | PS5-60-75 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0264 | PS5-60-TCV-0002G |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-06-11 12:33 | PS5-60-76 |  |  | Package | M | Closed | PS5 - Milestone E
T-00146-0265 | PS5-60-UA-5200 |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | INSTRUMENT AIR COMPRESSOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135127 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-09 12:13 | PS5-60-26 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0266 | PS5-60-UR-8200A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-09 12:14 | PS5-60-01 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0267 | PS5-60-UR-8200B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-09 12:15 | PS5-60-04 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0268 | PS5-60-UR-8200C |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-06-11 08:02 | PS5-60-07 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0269 | PS5-60-UR-8200D |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-11 08:03 | PS5-60-10 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0270 | PS5-60-UR-8200E |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-06-11 08:04 | PS5-60-13 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0271 | PS5-60-UR-8200F |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-06-11 08:04 | PS5-60-16 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0272 | PS5-60-UR-8200G |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-06-11 12:36 | PS5-60-19 |  |  | Package | M | Closed | PS5 - Milestone E
T-00146-0273 | PS5-60-UZ-8200G |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G | 2026-06-11 12:37 | PS5-60-41 |  |  | Package | M | Closed | PS5 - Milestone E
T-00146-0274 | PS5-60-UZ-8900A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-06-09 12:15 | PS5-60-56 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0275 | PS5-60-UZ-8900B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-06-09 12:16 | PS5-60-58 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0276 | PS5-60-UZ-8900C |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 2026-06-11 08:13 | PS5-60-60 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0277 | PS5-60-UZ-8900D |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2026-06-11 08:14 | PS5-60-62 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0278 | PS5-60-UZ-8900E |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | 2026-06-11 08:15 | PS5-60-64 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0279 | PS5-60-UZ-8900F |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | 2026-06-11 08:16 | PS5-60-66 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0280 | PS5-60-UZ-8900G |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | 2026-06-11 12:38 | PS5-60-68 |  |  | Package | M | Closed | PS5 - Milestone E
T-00146-0282 | PS5-71-UZ-6400 |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | CRUDE FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135004 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-06-12 10:50 | PS5-71-08 |  |  | Package | M | Closed | PS5 - Milestone H
T-00146-0283 | PS5-71-UZ-6700 |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | DIESEL FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135126 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-06-09 12:16 | PS5-71-22 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0418 | PS5-60-UR-8300A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-06-09 12:17 | PS5-60-35 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0419 | PS5-60-UR-8300B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-06-09 12:18 | PS5-60-36 |  |  | Package | M | Closed | PS5 - Milestone B
T-00146-0420 | PS5-60-UR-8300C |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C | 2026-06-11 08:05 | PS5-60-37 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0421 | PS5-60-UR-8300D |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D | 2026-06-11 08:06 | PS5-60-38 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0422 | PS5-60-UR-8300E |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E | 2026-06-11 08:07 | PS5-60-39 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0423 | PS5-60-UR-8300F |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F | 2026-06-11 08:08 | PS5-60-40 |  |  | Package | M | Closed | PS5 - Milestone D
T-00146-0424 | PS5-60-UR-8300G |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G | 2026-06-11 12:36 | PS5-60-41 |  |  | Package | M | Closed | PS5 - Milestone E
T-00146-0449 | PS5-60-SPZQ-0081A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Sample Connection - Type 5 | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135134 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Package | P | To be completed | PS5 - Milestone B
T-00146-0450 | PS5-60-SPZQ-0081B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Sample Connection - Type 5 | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135134 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Package | P | To be completed | PS5 - Milestone B
T-00146-0451 | PS5-60-SPZQ-0081C |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Sample Connection - Type 5 | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135134 | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | Package | P | To be completed | PS5 - Milestone D
T-00146-0452 | PS5-60-SPZQ-0081D |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Sample Connection - Type 5 | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135134 | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | Package | P | To be completed | PS5 - Milestone D
T-00146-0453 | PS5-60-SPZQ-0081E |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Sample Connection - Type 5 | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135134 | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | Package | P | To be completed | PS5 - Milestone D
T-00146-0454 | PS5-60-SPZQ-0081F |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Sample Connection - Type 5 | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135134 | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | Package | P | To be completed | PS5 - Milestone D
T-00146-0455 | PS5-60-SPZQ-0081G |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Sample Connection - Type 5 | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135134 | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | Package | P | To be completed | PS5 - Milestone E
T-00146-0461 | PS5-71-SPZQ-0070 |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Sample Connection - Type 4 | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135010 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Package | P | To be completed | PS5 - Milestone H
T-00171-4342 | PS5-60-IE-0003B-CA02 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B
T-00171-4343 | PS5-60-IE-0003B-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B
T-00171-4344 | PS5-60-IE-0003B-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B
T-00171-4345 | PS5-60-IE-0003B-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B
T-00171-4346 | PS5-60-IE-0003C-CA02 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4347 | PS5-60-IE-0003C-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4348 | PS5-60-IE-0003C-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4349 | PS5-60-IE-0003C-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4350 | PS5-60-IE-0003D-CA02 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4351 | PS5-60-IE-0003D-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4352 | PS5-60-IE-0003D-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4353 | PS5-60-IE-0003D-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4354 | PS5-60-IE-0003E-CA02 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4355 | PS5-60-IE-0003E-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4356 | PS5-60-IE-0003E-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4357 | PS5-60-IE-0003E-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4358 | PS5-60-IE-0003F-CA02 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4359 | PS5-60-IE-0003F-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4360 | PS5-60-IE-0003F-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4361 | PS5-60-IE-0003F-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4362 | PS5-60-IE-0003G-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003F TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone E
T-00171-4363 | PS5-60-IE-0003G-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003F TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone E
T-00171-4364 | PS5-60-IE-0003G-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003F TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone E
T-00171-4365 | PS5-60-IE-0004-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B
T-00171-4366 | PS5-60-IE-0004-CA07 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B
T-00171-4367 | PS5-60-IE-0004-CA08 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B
T-00171-4368 | PS5-60-IE-0004-CA14 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B
T-00171-4369 | PS5-60-IE-0004-CA15 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B
T-00171-4370 | PS5-60-IE-0004-CA21 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B
T-00171-4371 | PS5-60-IH-0001A-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B
T-00171-4372 | PS5-60-IH-0001B-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0001B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B
T-00171-4373 | PS5-60-IH-0001C-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0001C TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4374 | PS5-60-IH-0001D-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0001D TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4375 | PS5-60-IH-0001E-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0001E TO PS5-60-IH-0001E | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4376 | PS5-60-IH-0001F-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0001F TO PS5-60-IH-0001F | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4377 | PS5-60-IH-0001G-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0001G TO PS5-60-IH-0001G | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone E
T-00171-4378 | PS5-60-IN-0001A-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B
T-00171-4379 | PS5-60-IN-0001B-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B
T-00171-4380 | PS5-60-IN-0001C-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4381 | PS5-60-IN-0001D-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4382 | PS5-60-IN-0001E-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0001E | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4383 | PS5-60-IN-0001F-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0001F | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4384 | PS5-60-IN-0001G-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0001G | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone E
T-00171-4385 | PS5-60-IN-0002A-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B
T-00171-4386 | PS5-60-IN-0002B-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B
T-00171-4387 | PS5-60-IN-0002C-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4388 | PS5-60-IN-0002D-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4389 | PS5-60-IN-0002E-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4390 | PS5-60-IN-0002F-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4391 | PS5-60-IN-0002G-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone E
T-00171-4392 | PS5-60-LA-0002B-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4393 | PS5-60-LA-0002B-CA02 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4394 | PS5-60-LA-0002B-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4395 | PS5-60-LA-0002B-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4396 | PS5-60-LA-0002B-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002C TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4397 | PS5-60-LA-0002B-CA06 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002C TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4398 | PS5-60-LA-0002C-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4399 | PS5-60-LA-0002C-CA02 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4400 | PS5-60-LA-0002C-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4401 | PS5-60-LA-0002C-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4402 | PS5-60-LA-0002C-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002B TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4403 | PS5-60-LA-0002C-CA06 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002B TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D
T-00171-4404 | PS5-60-SEA-0001-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone E
T-00171-4407 | PS5-71-IN-0002-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone H
T-00171-4408 | PS5-71-IN-0003-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B
T-00214-0231 |  | EACOP-PS5-60-01-0151 |  | EACOP-PS5-60-01-0151 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-25 06:52 | PS5-60-01 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0232 |  | EACOP-PS5-60-01-0152 |  | EACOP-PS5-60-01-0152 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-25 06:54 | PS5-60-01 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0233 |  | EACOP-PS5-60-01-0153 |  | EACOP-PS5-60-01-0153 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-25 06:56 | PS5-60-01 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0234 |  | EACOP-PS5-60-04-0154 |  | EACOP-PS5-60-04-0154 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-25 06:59 | PS5-60-04 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0235 |  | EACOP-PS5-60-04-0155 |  | EACOP-PS5-60-04-0155 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-25 07:01 | PS5-60-04 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0236 |  | EACOP-PS5-60-04-0156 |  | EACOP-PS5-60-04-0156 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-25 07:03 | PS5-60-04 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0237 |  | EACOP-PS5-60-07-0157 |  | EACOP-PS5-60-07-0157 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-05-19 06:26 | PS5-60-07 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0238 |  | EACOP-PS5-60-07-0158 |  | EACOP-PS5-60-07-0158 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-05-19 06:29 | PS5-60-07 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0239 |  | EACOP-PS5-60-07-0159 |  | EACOP-PS5-60-07-0159 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-05-19 06:31 | PS5-60-07 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0240 |  | EACOP-PS5-60-10-0160 |  | EACOP-PS5-60-10-0160 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-05-19 08:27 | PS5-60-10 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0241 |  | EACOP-PS5-60-10-0161 |  | EACOP-PS5-60-10-0161 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-05-19 08:27 | PS5-60-10 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0242 |  | EACOP-PS5-60-10-0162 |  | EACOP-PS5-60-10-0162 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-05-19 08:29 | PS5-60-10 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0243 |  | EACOP-PS5-60-13-0163 |  | EACOP-PS5-60-13-0163 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-05-19 08:28 | PS5-60-13 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0244 |  | EACOP-PS5-60-13-0164 |  | EACOP-PS5-60-13-0164 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-05-19 08:25 | PS5-60-13 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0245 |  | EACOP-PS5-60-13-0165 |  | EACOP-PS5-60-13-0165 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-05-19 08:24 | PS5-60-13 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0246 |  | EACOP-PS5-60-16-0166 |  | EACOP-PS5-60-16-0166 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-05-19 08:23 | PS5-60-16 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0247 |  | EACOP-PS5-60-16-0167 |  | EACOP-PS5-60-16-0167 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-05-19 08:26 | PS5-60-16 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0248 |  | EACOP-PS5-60-16-0168 |  | EACOP-PS5-60-16-0168 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-05-19 08:22 | PS5-60-16 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0249 |  | EACOP-PS5-60-19-0169 |  | EACOP-PS5-60-19-0169 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-05-19 08:29 | PS5-60-19 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone E
T-00214-0250 |  | EACOP-PS5-60-19-0170 |  | EACOP-PS5-60-19-0170 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-06-18 06:33 | PS5-60-19 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone E
T-00214-0251 |  | EACOP-PS5-60-19-0171 |  | EACOP-PS5-60-19-0171 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-06-18 06:34 | PS5-60-19 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone E
T-00214-0267 |  | EACOP-PS5-60-26-0183 |  | EACOP-PS5-60-26-0183 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-05-15 06:23 | PS5-60-26 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0268 |  | EACOP-PS5-60-26-0184 |  | EACOP-PS5-60-26-0184 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-04-04 06:12 | PS5-60-26 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0269 |  | EACOP-PS5-60-27-0185 |  | EACOP-PS5-60-27-0185 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-04-04 06:08 | PS5-60-27 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0270 |  | EACOP-PS5-60-27-0186 |  | EACOP-PS5-60-27-0186 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-04-26 04:39 | PS5-60-27 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0278 |  | EACOP-PS5-60-35-0194 |  | EACOP-PS5-60-35-0194 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-04-26 04:54 | PS5-60-35 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0279 |  | EACOP-PS5-60-35-0195 |  | EACOP-PS5-60-35-0195 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-04-26 04:55 | PS5-60-35 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0280 |  | EACOP-PS5-60-36-0196 |  | EACOP-PS5-60-36-0196 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-05-15 06:25 | PS5-60-36 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0281 |  | EACOP-PS5-60-36-0197 |  | EACOP-PS5-60-36-0197 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-04-04 06:11 | PS5-60-36 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0282 |  | EACOP-PS5-60-37-0198 |  | EACOP-PS5-60-37-0198 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C | 2026-04-26 04:57 | PS5-60-37 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0283 |  | EACOP-PS5-60-37-0199 |  | EACOP-PS5-60-37-0199 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C | 2026-04-26 04:58 | PS5-60-37 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0284 |  | EACOP-PS5-60-38-0200 |  | EACOP-PS5-60-38-0200 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D | 2026-04-26 05:05 | PS5-60-38 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0285 |  | EACOP-PS5-60-38-0201 |  | EACOP-PS5-60-38-0201 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D | 2026-04-26 05:07 | PS5-60-38 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0286 |  | EACOP-PS5-60-39-0202 |  | EACOP-PS5-60-39-0202 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E | 2026-04-26 05:09 | PS5-60-39 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0287 |  | EACOP-PS5-60-39-0203 |  | EACOP-PS5-60-39-0203 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E | 2026-04-26 05:10 | PS5-60-39 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0288 |  | EACOP-PS5-60-40-0204 |  | EACOP-PS5-60-40-0204 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F | 2026-04-26 05:11 | PS5-60-40 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0289 |  | EACOP-PS5-60-40-0205 |  | EACOP-PS5-60-40-0205 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F | 2026-04-26 05:13 | PS5-60-40 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0290 |  | EACOP-PS5-60-41-0206 |  | EACOP-PS5-60-41-0206 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G | 2026-04-26 05:14 | PS5-60-41 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone E
T-00214-0291 |  | EACOP-PS5-60-41-0207 |  | EACOP-PS5-60-41-0207 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G | 2026-04-26 05:16 | PS5-60-41 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone E
T-00214-0292 |  | EACOP-PS5-60-42-0208 |  | EACOP-PS5-60-42-0208 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-05-15 06:26 | PS5-60-42 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0293 |  | EACOP-PS5-60-42-0209 |  | EACOP-PS5-60-42-0209 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-04-26 06:12 | PS5-60-42 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0294 |  | EACOP-PS5-60-43-0210 |  | EACOP-PS5-60-43-0210 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-04-26 06:13 | PS5-60-43 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0295 |  | EACOP-PS5-60-43-0211 |  | EACOP-PS5-60-43-0211 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-04-26 06:14 | PS5-60-43 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0296 |  | EACOP-PS5-60-44-0212 |  | EACOP-PS5-60-44-0212 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | 2026-04-26 06:16 | PS5-60-44 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0297 |  | EACOP-PS5-60-44-0213 |  | EACOP-PS5-60-44-0213 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | 2026-04-26 06:17 | PS5-60-44 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0298 |  | EACOP-PS5-60-45-0214 |  | EACOP-PS5-60-45-0214 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | 2026-05-19 08:21 | PS5-60-45 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0299 |  | EACOP-PS5-60-45-0215 |  | EACOP-PS5-60-45-0215 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | 2026-04-26 06:18 | PS5-60-45 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0300 |  | EACOP-PS5-60-46-0216 |  | EACOP-PS5-60-46-0216 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | 2026-04-26 06:19 | PS5-60-46 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0301 |  | EACOP-PS5-60-46-0217 |  | EACOP-PS5-60-46-0217 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | 2026-04-26 06:21 | PS5-60-46 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0302 |  | EACOP-PS5-60-47-0218 |  | EACOP-PS5-60-47-0218 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | 2026-05-19 08:20 | PS5-60-47 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0303 |  | EACOP-PS5-60-47-0219 |  | EACOP-PS5-60-47-0219 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | 2026-04-26 06:23 | PS5-60-47 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0304 |  | EACOP-PS5-60-48-0220 |  | EACOP-PS5-60-48-0220 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | 2026-04-26 06:24 | PS5-60-48 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone E
T-00214-0305 |  | EACOP-PS5-60-48-0221 |  | EACOP-PS5-60-48-0221 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | 2026-05-22 05:44 | PS5-60-48 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone E
T-00214-0306 |  | EACOP-PS5-60-49-0222 |  | EACOP-PS5-60-49-0222 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2026-05-15 06:27 | PS5-60-49 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0307 |  | EACOP-PS5-60-49-0223 |  | EACOP-PS5-60-49-0223 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2026-05-15 06:28 | PS5-60-49 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0308 |  | EACOP-PS5-60-50-0224 |  | EACOP-PS5-60-50-0224 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2026-05-15 06:29 | PS5-60-50 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0309 |  | EACOP-PS5-60-50-0225 |  | EACOP-PS5-60-50-0225 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2026-05-15 06:30 | PS5-60-50 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0310 |  | EACOP-PS5-60-51-0226 |  | EACOP-PS5-60-51-0226 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | 2026-05-19 08:18 | PS5-60-51 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0311 |  | EACOP-PS5-60-51-0227 |  | EACOP-PS5-60-51-0227 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | 2026-05-19 08:16 | PS5-60-51 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0312 |  | EACOP-PS5-60-52-0228 |  | EACOP-PS5-60-52-0228 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | 2026-05-19 08:14 | PS5-60-52 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0313 |  | EACOP-PS5-60-52-0229 |  | EACOP-PS5-60-52-0229 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | 2026-05-19 08:12 | PS5-60-52 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0314 |  | EACOP-PS5-60-53-0230 |  | EACOP-PS5-60-53-0230 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | 2026-05-19 08:10 | PS5-60-53 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0315 |  | EACOP-PS5-60-53-0231 |  | EACOP-PS5-60-53-0231 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | 2026-05-19 08:08 | PS5-60-53 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0316 |  | EACOP-PS5-60-54-0232 |  | EACOP-PS5-60-54-0232 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | 2026-05-19 08:07 | PS5-60-54 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0317 |  | EACOP-PS5-60-54-0233 |  | EACOP-PS5-60-54-0233 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | 2026-05-19 08:05 | PS5-60-54 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0318 |  | EACOP-PS5-60-55-0234 |  | EACOP-PS5-60-55-0234 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | 2026-06-18 06:37 | PS5-60-55 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone E
T-00214-0319 |  | EACOP-PS5-60-55-0235 |  | EACOP-PS5-60-55-0235 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | 2026-06-18 06:38 | PS5-60-55 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone E
T-00214-0320 |  | EACOP-PS5-60-56-0236 |  | EACOP-PS5-60-56-0236 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-04-22 13:38 | PS5-60-56 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0321 |  | EACOP-PS5-60-56-0237 |  | EACOP-PS5-60-56-0237 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-04-04 06:06 | PS5-60-56 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0322 |  | EACOP-PS5-60-58-0238 |  | EACOP-PS5-60-58-0238 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-04-04 06:14 | PS5-60-58 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0323 |  | EACOP-PS5-60-58-0239 |  | EACOP-PS5-60-58-0239 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-04-04 06:00 | PS5-60-58 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0324 |  | EACOP-PS5-60-60-0240 |  | EACOP-PS5-60-60-0240 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 2026-04-17 17:41 | PS5-60-60 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0325 |  | EACOP-PS5-60-60-0241 |  | EACOP-PS5-60-60-0241 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 2026-05-14 11:07 | PS5-60-60 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0326 |  | EACOP-PS5-60-62-0242 |  | EACOP-PS5-60-62-0242 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2026-04-15 08:48 | PS5-60-62 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0327 |  | EACOP-PS5-60-62-0243 |  | EACOP-PS5-60-62-0243 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2026-05-19 06:26 | PS5-60-62 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0328 |  | EACOP-PS5-60-64-0244 |  | EACOP-PS5-60-64-0244 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | 2026-04-24 17:35 | PS5-60-64 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0329 |  | EACOP-PS5-60-64-0245 |  | EACOP-PS5-60-64-0245 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | 2026-05-19 06:29 | PS5-60-64 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0330 |  | EACOP-PS5-60-66-0246 |  | EACOP-PS5-60-66-0246 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | 2026-05-09 05:27 | PS5-60-66 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0331 |  | EACOP-PS5-60-66-0247 |  | EACOP-PS5-60-66-0247 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | 2026-05-19 06:31 | PS5-60-66 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0332 |  | EACOP-PS5-60-68-0248 |  | EACOP-PS5-60-68-0248 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | 2026-04-26 07:09 | PS5-60-68 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone E
T-00214-0333 |  | EACOP-PS5-60-68-0249 |  | EACOP-PS5-60-68-0249 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | 2026-05-19 06:32 | PS5-60-68 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone E
T-00214-0334 |  | EACOP-PS5-60-70-0250 |  | EACOP-PS5-60-70-0250 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-15 06:32 | PS5-60-70 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0335 |  | EACOP-PS5-60-70-0251 |  | EACOP-PS5-60-70-0251 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-02 18:22 | PS5-60-70 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0336 |  | EACOP-PS5-60-70-0252 |  | EACOP-PS5-60-70-0252 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-15 06:33 | PS5-60-70 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0337 |  | EACOP-PS5-60-70-0253 |  | EACOP-PS5-60-70-0253 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-15 06:34 | PS5-60-70 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0338 |  | EACOP-PS5-60-70-0254 |  | EACOP-PS5-60-70-0254 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-15 06:35 | PS5-60-70 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0339 |  | EACOP-PS5-60-70-0255 |  | EACOP-PS5-60-70-0255 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-15 06:37 | PS5-60-70 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0340 |  | EACOP-PS5-60-71-0256 |  | EACOP-PS5-60-71-0256 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-05-15 06:38 | PS5-60-71 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0341 |  | EACOP-PS5-60-71-0257 |  | EACOP-PS5-60-71-0257 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-05-06 05:23 | PS5-60-71 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0342 |  | EACOP-PS5-60-71-0258 |  | EACOP-PS5-60-71-0258 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-05-15 06:39 | PS5-60-71 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0343 |  | EACOP-PS5-60-71-0259 |  | EACOP-PS5-60-71-0259 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-05-15 06:40 | PS5-60-71 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0344 |  | EACOP-PS5-60-71-0260 |  | EACOP-PS5-60-71-0260 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-05-15 06:41 | PS5-60-71 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0345 |  | EACOP-PS5-60-71-0261 |  | EACOP-PS5-60-71-0261 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-05-15 06:42 | PS5-60-71 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0346 |  | EACOP-PS5-60-72-0262 |  | EACOP-PS5-60-72-0262 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-05-16 05:47 | PS5-60-72 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0347 |  | EACOP-PS5-60-72-0263 |  | EACOP-PS5-60-72-0263 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-05-12 19:46 | PS5-60-72 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0348 |  | EACOP-PS5-60-72-0264 |  | EACOP-PS5-60-72-0264 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-05-16 05:46 | PS5-60-72 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0349 |  | EACOP-PS5-60-72-0265 |  | EACOP-PS5-60-72-0265 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-05-16 05:45 | PS5-60-72 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0350 |  | EACOP-PS5-60-72-0266 |  | EACOP-PS5-60-72-0266 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-05-19 08:01 | PS5-60-72 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0351 |  | EACOP-PS5-60-72-0267 |  | EACOP-PS5-60-72-0267 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-05-16 05:44 | PS5-60-72 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0352 |  | EACOP-PS5-60-73-0268 |  | EACOP-PS5-60-73-0268 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-05-16 05:43 | PS5-60-73 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0353 |  | EACOP-PS5-60-73-0269 |  | EACOP-PS5-60-73-0269 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-05-16 04:52 | PS5-60-73 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0354 |  | EACOP-PS5-60-73-0270 |  | EACOP-PS5-60-73-0270 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-05-16 05:42 | PS5-60-73 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0355 |  | EACOP-PS5-60-73-0271 |  | EACOP-PS5-60-73-0271 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-05-16 05:49 | PS5-60-73 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0356 |  | EACOP-PS5-60-73-0272 |  | EACOP-PS5-60-73-0272 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-05-16 05:51 | PS5-60-73 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0357 |  | EACOP-PS5-60-73-0273 |  | EACOP-PS5-60-73-0273 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-05-16 05:52 | PS5-60-73 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0358 |  | EACOP-PS5-60-74-0274 |  | EACOP-PS5-60-74-0274 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-05-16 05:53 | PS5-60-74 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0359 |  | EACOP-PS5-60-74-0275 |  | EACOP-PS5-60-74-0275 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-05-16 05:17 | PS5-60-74 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0360 |  | EACOP-PS5-60-74-0276 |  | EACOP-PS5-60-74-0276 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-04-29 06:38 | PS5-60-74 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0361 |  | EACOP-PS5-60-74-0277 |  | EACOP-PS5-60-74-0277 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-04-29 06:36 | PS5-60-74 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0362 |  | EACOP-PS5-60-74-0278 |  | EACOP-PS5-60-74-0278 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-04-29 06:34 | PS5-60-74 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0363 |  | EACOP-PS5-60-74-0279 |  | EACOP-PS5-60-74-0279 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-04-29 06:32 | PS5-60-74 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0364 |  | EACOP-PS5-60-75-0280 |  | EACOP-PS5-60-75-0280 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-04-29 06:29 | PS5-60-75 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0365 |  | EACOP-PS5-60-75-0281 |  | EACOP-PS5-60-75-0281 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-04-29 06:27 | PS5-60-75 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0366 |  | EACOP-PS5-60-75-0282 |  | EACOP-PS5-60-75-0282 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-04-29 06:26 | PS5-60-75 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0367 |  | EACOP-PS5-60-75-0283 |  | EACOP-PS5-60-75-0283 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-04-29 06:24 | PS5-60-75 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0368 |  | EACOP-PS5-60-75-0284 |  | EACOP-PS5-60-75-0284 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-04-29 06:23 | PS5-60-75 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0369 |  | EACOP-PS5-60-75-0285 |  | EACOP-PS5-60-75-0285 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-04-29 06:22 | PS5-60-75 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0370 |  | EACOP-PS5-60-76-0286 |  | EACOP-PS5-60-76-0286 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-04-28 19:01 | PS5-60-76 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone E
T-00214-0371 |  | EACOP-PS5-60-76-0287 |  | EACOP-PS5-60-76-0287 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-04-28 18:49 | PS5-60-76 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone E
T-00214-0372 |  | EACOP-PS5-60-76-0288 |  | EACOP-PS5-60-76-0288 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-04-28 18:47 | PS5-60-76 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone E
T-00214-0373 |  | EACOP-PS5-60-76-0289 |  | EACOP-PS5-60-76-0289 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-04-28 18:46 | PS5-60-76 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone E
T-00214-0374 |  | EACOP-PS5-60-76-0290 |  | EACOP-PS5-60-76-0290 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-04-28 18:44 | PS5-60-76 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone E
T-00214-0375 |  | EACOP-PS5-60-76-0291 |  | EACOP-PS5-60-76-0291 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-04-28 18:41 | PS5-60-76 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone E
T-00214-0391 |  | EACOP-PS5-71-06-0307 |  | EACOP-PS5-71-06-0307 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-02-25 06:31 | PS5-71-06 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone H
T-00214-0392 |  | EACOP-PS5-71-06-0308 |  | EACOP-PS5-71-06-0308 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-05-16 05:40 | PS5-71-06 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone H
T-00214-0393 |  | EACOP-PS5-71-06-0378 |  | EACOP-PS5-71-06-0378 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-03-26 18:35 | PS5-71-06 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone H
T-00214-0394 |  | EACOP-PS5-71-08-0309 |  | EACOP-PS5-71-08-0309 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-02-25 06:33 | PS5-71-08 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone H
T-00214-0395 |  | EACOP-PS5-71-08-0310 |  | EACOP-PS5-71-08-0310 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-04-28 14:46 | PS5-71-08 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone H
T-00214-0418 |  | EACOP-PS5-71-22-0333 |  | EACOP-PS5-71-22-0333 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  | 40 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-04-28 18:16 | PS5-71-22 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0419 |  | EACOP-PS5-71-22-0334 |  | EACOP-PS5-71-22-0334 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-04-26 07:08 | PS5-71-22 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0420 |  | EACOP-PS5-71-22-0335 |  | EACOP-PS5-71-22-0335 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-04-28 18:17 | PS5-71-22 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0421 |  | EACOP-PS5-71-22-0336 |  | EACOP-PS5-71-22-0336 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-03-07 07:21 | PS5-71-22 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0422 |  | EACOP-PS5-71-22-0337 |  | EACOP-PS5-71-22-0337 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-03-07 07:19 | PS5-71-22 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0512 |  | EACOP-PS5-60-42-0046 |  | EACOP-PS5-60-42-0046 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-05-07 05:42 | PS5-60-42 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0513 |  | EACOP-PS5-60-43-0091 |  | EACOP-PS5-60-43-0091 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-05-07 05:58 | PS5-60-43 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B
T-00214-0514 |  | EACOP-PS5-60-44-0421 |  | EACOP-PS5-60-44-0421 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | 2026-05-07 06:08 | PS5-60-44 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0515 |  | EACOP-PS5-60-45-0422 |  | EACOP-PS5-60-45-0422 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | 2026-05-07 06:13 | PS5-60-45 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0516 |  | EACOP-PS5-60-46-0423 |  | EACOP-PS5-60-46-0423 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | 2026-05-07 10:38 | PS5-60-46 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0517 |  | EACOP-PS5-60-47-0424 |  | EACOP-PS5-60-47-0424 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | 2026-05-07 10:46 | PS5-60-47 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone D
T-00214-0518 |  | EACOP-PS5-60-48-0065 |  | EACOP-PS5-60-48-0065 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | 2026-05-07 05:49 | PS5-60-48 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone E
T-00215-0231 |  | EACOP-PS5-60-01-0151 |  | EACOP-PS5-60-01-0151 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-07 17:32 | PS5-60-01 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0232 |  | EACOP-PS5-60-01-0152 |  | EACOP-PS5-60-01-0152 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-03 14:40 | PS5-60-01 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0233 |  | EACOP-PS5-60-01-0153 |  | EACOP-PS5-60-01-0153 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-07 17:37 | PS5-60-01 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0234 |  | EACOP-PS5-60-04-0154 |  | EACOP-PS5-60-04-0154 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-03 14:43 | PS5-60-04 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0235 |  | EACOP-PS5-60-04-0155 |  | EACOP-PS5-60-04-0155 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-10 14:54 | PS5-60-04 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0236 |  | EACOP-PS5-60-04-0156 |  | EACOP-PS5-60-04-0156 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-10 14:58 | PS5-60-04 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0237 |  | EACOP-PS5-60-07-0157 |  | EACOP-PS5-60-07-0157 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-06-10 15:00 | PS5-60-07 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0238 |  | EACOP-PS5-60-07-0158 |  | EACOP-PS5-60-07-0158 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-06-17 06:04 | PS5-60-07 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0239 |  | EACOP-PS5-60-07-0159 |  | EACOP-PS5-60-07-0159 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-06-12 06:50 | PS5-60-07 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0240 |  | EACOP-PS5-60-10-0160 |  | EACOP-PS5-60-10-0160 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-12 06:52 | PS5-60-10 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0241 |  | EACOP-PS5-60-10-0161 |  | EACOP-PS5-60-10-0161 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-23 04:54 | PS5-60-10 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0242 |  | EACOP-PS5-60-10-0162 |  | EACOP-PS5-60-10-0162 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-23 04:56 | PS5-60-10 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0243 |  | EACOP-PS5-60-13-0163 |  | EACOP-PS5-60-13-0163 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-06-23 04:59 | PS5-60-13 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0244 |  | EACOP-PS5-60-13-0164 |  | EACOP-PS5-60-13-0164 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-06-23 05:01 | PS5-60-13 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0245 |  | EACOP-PS5-60-13-0165 |  | EACOP-PS5-60-13-0165 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-06-23 05:03 | PS5-60-13 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0246 |  | EACOP-PS5-60-16-0166 |  | EACOP-PS5-60-16-0166 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-06-23 05:04 | PS5-60-16 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0247 |  | EACOP-PS5-60-16-0167 |  | EACOP-PS5-60-16-0167 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-06-25 19:01 | PS5-60-16 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0248 |  | EACOP-PS5-60-16-0168 |  | EACOP-PS5-60-16-0168 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-06-25 19:03 | PS5-60-16 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0249 |  | EACOP-PS5-60-19-0169 |  | EACOP-PS5-60-19-0169 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-06-26 05:08 | PS5-60-19 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone E
T-00215-0250 |  | EACOP-PS5-60-19-0170 |  | EACOP-PS5-60-19-0170 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-07-02 11:35 | PS5-60-19 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone E
T-00215-0251 |  | EACOP-PS5-60-19-0171 |  | EACOP-PS5-60-19-0171 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-07-02 11:36 | PS5-60-19 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone E
T-00215-0267 |  | EACOP-PS5-60-26-0183 |  | EACOP-PS5-60-26-0183 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-03 14:45 | PS5-60-26 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0268 |  | EACOP-PS5-60-26-0184 |  | EACOP-PS5-60-26-0184 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-05-07 14:08 | PS5-60-26 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0269 |  | EACOP-PS5-60-27-0185 |  | EACOP-PS5-60-27-0185 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-05-07 14:27 | PS5-60-27 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0270 |  | EACOP-PS5-60-27-0186 |  | EACOP-PS5-60-27-0186 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone B
T-00215-0278 |  | EACOP-PS5-60-35-0194 |  | EACOP-PS5-60-35-0194 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone B
T-00215-0279 |  | EACOP-PS5-60-35-0195 |  | EACOP-PS5-60-35-0195 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-05-04 08:39 | PS5-60-35 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0280 |  | EACOP-PS5-60-36-0196 |  | EACOP-PS5-60-36-0196 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone B
T-00215-0281 |  | EACOP-PS5-60-36-0197 |  | EACOP-PS5-60-36-0197 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-05-24 12:50 | PS5-60-36 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0282 |  | EACOP-PS5-60-37-0198 |  | EACOP-PS5-60-37-0198 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone D
T-00215-0283 |  | EACOP-PS5-60-37-0199 |  | EACOP-PS5-60-37-0199 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C | 2026-05-24 13:51 | PS5-60-37 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0284 |  | EACOP-PS5-60-38-0200 |  | EACOP-PS5-60-38-0200 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone D
T-00215-0285 |  | EACOP-PS5-60-38-0201 |  | EACOP-PS5-60-38-0201 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D | 2026-06-07 17:43 | PS5-60-38 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0286 |  | EACOP-PS5-60-39-0202 |  | EACOP-PS5-60-39-0202 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone D
T-00215-0287 |  | EACOP-PS5-60-39-0203 |  | EACOP-PS5-60-39-0203 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E | 2026-06-25 19:14 | PS5-60-39 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0288 |  | EACOP-PS5-60-40-0204 |  | EACOP-PS5-60-40-0204 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F |  | PS5-60-40 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone D
T-00215-0289 |  | EACOP-PS5-60-40-0205 |  | EACOP-PS5-60-40-0205 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F | 2026-06-07 17:46 | PS5-60-40 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0290 |  | EACOP-PS5-60-41-0206 |  | EACOP-PS5-60-41-0206 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone E
T-00215-0291 |  | EACOP-PS5-60-41-0207 |  | EACOP-PS5-60-41-0207 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G | 2026-07-02 11:38 | PS5-60-41 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone E
T-00215-0292 |  | EACOP-PS5-60-42-0208 |  | EACOP-PS5-60-42-0208 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone B
T-00215-0293 |  | EACOP-PS5-60-42-0209 |  | EACOP-PS5-60-42-0209 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-06-07 18:03 | PS5-60-42 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0294 |  | EACOP-PS5-60-43-0210 |  | EACOP-PS5-60-43-0210 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone B
T-00215-0295 |  | EACOP-PS5-60-43-0211 |  | EACOP-PS5-60-43-0211 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-05-24 11:07 | PS5-60-43 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0296 |  | EACOP-PS5-60-44-0212 |  | EACOP-PS5-60-44-0212 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C |  | PS5-60-44 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone D
T-00215-0297 |  | EACOP-PS5-60-44-0213 |  | EACOP-PS5-60-44-0213 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | 2026-05-24 12:43 | PS5-60-44 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0298 |  | EACOP-PS5-60-45-0214 |  | EACOP-PS5-60-45-0214 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D |  | PS5-60-45 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone D
T-00215-0299 |  | EACOP-PS5-60-45-0215 |  | EACOP-PS5-60-45-0215 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | 2026-05-24 12:59 | PS5-60-45 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0300 |  | EACOP-PS5-60-46-0216 |  | EACOP-PS5-60-46-0216 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  | 12 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E |  | PS5-60-46 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone D
T-00215-0301 |  | EACOP-PS5-60-46-0217 |  | EACOP-PS5-60-46-0217 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | 2026-05-24 13:58 | PS5-60-46 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0302 |  | EACOP-PS5-60-47-0218 |  | EACOP-PS5-60-47-0218 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F |  | PS5-60-47 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone D
T-00215-0303 |  | EACOP-PS5-60-47-0219 |  | EACOP-PS5-60-47-0219 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | 2026-05-24 14:06 | PS5-60-47 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0304 |  | EACOP-PS5-60-48-0220 |  | EACOP-PS5-60-48-0220 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G |  | PS5-60-48 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone E
T-00215-0305 |  | EACOP-PS5-60-48-0221 |  | EACOP-PS5-60-48-0221 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | 2026-05-24 14:09 | PS5-60-48 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone E
T-00215-0306 |  | EACOP-PS5-60-49-0222 |  | EACOP-PS5-60-49-0222 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone B
T-00215-0307 |  | EACOP-PS5-60-49-0223 |  | EACOP-PS5-60-49-0223 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2026-06-07 18:06 | PS5-60-49 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0308 |  | EACOP-PS5-60-50-0224 |  | EACOP-PS5-60-50-0224 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone B
T-00215-0309 |  | EACOP-PS5-60-50-0225 |  | EACOP-PS5-60-50-0225 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2026-06-03 14:50 | PS5-60-50 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0310 |  | EACOP-PS5-60-51-0226 |  | EACOP-PS5-60-51-0226 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone D
T-00215-0311 |  | EACOP-PS5-60-51-0227 |  | EACOP-PS5-60-51-0227 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | 2026-06-17 05:49 | PS5-60-51 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0312 |  | EACOP-PS5-60-52-0228 |  | EACOP-PS5-60-52-0228 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone D
T-00215-0313 |  | EACOP-PS5-60-52-0229 |  | EACOP-PS5-60-52-0229 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | 2026-06-23 05:41 | PS5-60-52 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0314 |  | EACOP-PS5-60-53-0230 |  | EACOP-PS5-60-53-0230 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone D
T-00215-0315 |  | EACOP-PS5-60-53-0231 |  | EACOP-PS5-60-53-0231 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | 2026-06-23 05:44 | PS5-60-53 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0316 |  | EACOP-PS5-60-54-0232 |  | EACOP-PS5-60-54-0232 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone D
T-00215-0317 |  | EACOP-PS5-60-54-0233 |  | EACOP-PS5-60-54-0233 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | 2026-06-25 19:17 | PS5-60-54 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0318 |  | EACOP-PS5-60-55-0234 |  | EACOP-PS5-60-55-0234 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone E
T-00215-0319 |  | EACOP-PS5-60-55-0235 |  | EACOP-PS5-60-55-0235 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | 2026-07-02 11:42 | PS5-60-55 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone E
T-00215-0320 |  | EACOP-PS5-60-56-0236 |  | EACOP-PS5-60-56-0236 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-04-22 13:41 | PS5-60-56 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0321 |  | EACOP-PS5-60-56-0237 |  | EACOP-PS5-60-56-0237 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-06-07 18:09 | PS5-60-56 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0322 |  | EACOP-PS5-60-58-0238 |  | EACOP-PS5-60-58-0238 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-04-22 13:59 | PS5-60-58 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0323 |  | EACOP-PS5-60-58-0239 |  | EACOP-PS5-60-58-0239 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-05-24 11:11 | PS5-60-58 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0324 |  | EACOP-PS5-60-60-0240 |  | EACOP-PS5-60-60-0240 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 2026-04-22 14:03 | PS5-60-60 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0325 |  | EACOP-PS5-60-60-0241 |  | EACOP-PS5-60-60-0241 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 2026-05-24 14:13 | PS5-60-60 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0326 |  | EACOP-PS5-60-62-0242 |  | EACOP-PS5-60-62-0242 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2026-04-15 10:41 | PS5-60-62 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0327 |  | EACOP-PS5-60-62-0243 |  | EACOP-PS5-60-62-0243 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2026-05-24 14:15 | PS5-60-62 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0328 |  | EACOP-PS5-60-64-0244 |  | EACOP-PS5-60-64-0244 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | 2026-04-26 18:13 | PS5-60-64 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0329 |  | EACOP-PS5-60-64-0245 |  | EACOP-PS5-60-64-0245 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | 2026-06-03 14:54 | PS5-60-64 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0330 |  | EACOP-PS5-60-66-0246 |  | EACOP-PS5-60-66-0246 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | 2026-05-24 13:01 | PS5-60-66 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0331 |  | EACOP-PS5-60-66-0247 |  | EACOP-PS5-60-66-0247 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | 2026-06-07 18:13 | PS5-60-66 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0332 |  | EACOP-PS5-60-68-0248 |  | EACOP-PS5-60-68-0248 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | 2026-06-07 18:16 | PS5-60-68 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone E
T-00215-0333 |  | EACOP-PS5-60-68-0249 |  | EACOP-PS5-60-68-0249 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | 2026-07-02 11:44 | PS5-60-68 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone E
T-00215-0334 |  | EACOP-PS5-60-70-0250 |  | EACOP-PS5-60-70-0250 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-03 15:00 | PS5-60-70 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0335 |  | EACOP-PS5-60-70-0251 |  | EACOP-PS5-60-70-0251 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-04 08:42 | PS5-60-70 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0336 |  | EACOP-PS5-60-70-0252 |  | EACOP-PS5-60-70-0252 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-03 15:04 | PS5-60-70 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0337 |  | EACOP-PS5-60-70-0253 |  | EACOP-PS5-60-70-0253 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-03 15:07 | PS5-60-70 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0338 |  | EACOP-PS5-60-70-0254 |  | EACOP-PS5-60-70-0254 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-03 15:10 | PS5-60-70 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0339 |  | EACOP-PS5-60-70-0255 |  | EACOP-PS5-60-70-0255 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-07 18:19 | PS5-60-70 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0340 |  | EACOP-PS5-60-71-0256 |  | EACOP-PS5-60-71-0256 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-10 15:05 | PS5-60-71 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0341 |  | EACOP-PS5-60-71-0257 |  | EACOP-PS5-60-71-0257 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-05-24 11:13 | PS5-60-71 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0342 |  | EACOP-PS5-60-71-0258 |  | EACOP-PS5-60-71-0258 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-03 17:02 | PS5-60-71 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0343 |  | EACOP-PS5-60-71-0259 |  | EACOP-PS5-60-71-0259 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-03 17:04 | PS5-60-71 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0344 |  | EACOP-PS5-60-71-0260 |  | EACOP-PS5-60-71-0260 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-03 17:07 | PS5-60-71 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0345 |  | EACOP-PS5-60-71-0261 |  | EACOP-PS5-60-71-0261 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-03 17:10 | PS5-60-71 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0346 |  | EACOP-PS5-60-72-0262 |  | EACOP-PS5-60-72-0262 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-19 05:29 | PS5-60-72 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0347 |  | EACOP-PS5-60-72-0263 |  | EACOP-PS5-60-72-0263 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-05-24 13:04 | PS5-60-72 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0348 |  | EACOP-PS5-60-72-0264 |  | EACOP-PS5-60-72-0264 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-10 16:55 | PS5-60-72 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0349 |  | EACOP-PS5-60-72-0265 |  | EACOP-PS5-60-72-0265 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-10 16:58 | PS5-60-72 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0350 |  | EACOP-PS5-60-72-0266 |  | EACOP-PS5-60-72-0266 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-10 17:07 | PS5-60-72 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0351 |  | EACOP-PS5-60-72-0267 |  | EACOP-PS5-60-72-0267 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-10 17:10 | PS5-60-72 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0352 |  | EACOP-PS5-60-73-0268 |  | EACOP-PS5-60-73-0268 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-17 05:57 | PS5-60-73 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0353 |  | EACOP-PS5-60-73-0269 |  | EACOP-PS5-60-73-0269 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-05-24 14:46 | PS5-60-73 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0354 |  | EACOP-PS5-60-73-0270 |  | EACOP-PS5-60-73-0270 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-12 06:54 | PS5-60-73 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0355 |  | EACOP-PS5-60-73-0271 |  | EACOP-PS5-60-73-0271 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-12 06:56 | PS5-60-73 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0356 |  | EACOP-PS5-60-73-0272 |  | EACOP-PS5-60-73-0272 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-12 06:58 | PS5-60-73 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0357 |  | EACOP-PS5-60-73-0273 |  | EACOP-PS5-60-73-0273 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-12 06:59 | PS5-60-73 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0358 |  | EACOP-PS5-60-74-0274 |  | EACOP-PS5-60-74-0274 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-06-23 05:46 | PS5-60-74 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0359 |  | EACOP-PS5-60-74-0275 |  | EACOP-PS5-60-74-0275 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-05-24 14:49 | PS5-60-74 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0360 |  | EACOP-PS5-60-74-0276 |  | EACOP-PS5-60-74-0276 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-06-23 05:48 | PS5-60-74 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0361 |  | EACOP-PS5-60-74-0277 |  | EACOP-PS5-60-74-0277 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-06-23 05:50 | PS5-60-74 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0362 |  | EACOP-PS5-60-74-0278 |  | EACOP-PS5-60-74-0278 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-06-23 05:52 | PS5-60-74 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0363 |  | EACOP-PS5-60-74-0279 |  | EACOP-PS5-60-74-0279 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-06-23 05:54 | PS5-60-74 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0364 |  | EACOP-PS5-60-75-0280 |  | EACOP-PS5-60-75-0280 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-06-26 04:59 | PS5-60-75 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0365 |  | EACOP-PS5-60-75-0281 |  | EACOP-PS5-60-75-0281 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-06-07 18:35 | PS5-60-75 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0366 |  | EACOP-PS5-60-75-0282 |  | EACOP-PS5-60-75-0282 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-06-26 05:01 | PS5-60-75 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0367 |  | EACOP-PS5-60-75-0283 |  | EACOP-PS5-60-75-0283 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-06-26 05:03 | PS5-60-75 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0368 |  | EACOP-PS5-60-75-0284 |  | EACOP-PS5-60-75-0284 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-06-26 05:04 | PS5-60-75 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0369 |  | EACOP-PS5-60-75-0285 |  | EACOP-PS5-60-75-0285 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-06-26 05:05 | PS5-60-75 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0370 |  | EACOP-PS5-60-76-0286 |  | EACOP-PS5-60-76-0286 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-06-26 05:09 | PS5-60-76 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone E
T-00215-0371 |  | EACOP-PS5-60-76-0287 |  | EACOP-PS5-60-76-0287 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-06-07 18:37 | PS5-60-76 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone E
T-00215-0372 |  | EACOP-PS5-60-76-0288 |  | EACOP-PS5-60-76-0288 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-06-26 05:18 | PS5-60-76 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone E
T-00215-0373 |  | EACOP-PS5-60-76-0289 |  | EACOP-PS5-60-76-0289 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-06-26 05:21 | PS5-60-76 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone E
T-00215-0374 |  | EACOP-PS5-60-76-0290 |  | EACOP-PS5-60-76-0290 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-06-26 05:25 | PS5-60-76 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone E
T-00215-0375 |  | EACOP-PS5-60-76-0291 |  | EACOP-PS5-60-76-0291 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-06-26 05:26 | PS5-60-76 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone E
T-00215-0391 |  | EACOP-PS5-71-06-0307 |  | EACOP-PS5-71-06-0307 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-04-02 12:16 | PS5-71-06 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone H
T-00215-0392 |  | EACOP-PS5-71-06-0308 |  | EACOP-PS5-71-06-0308 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-05-24 14:51 | PS5-71-06 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone H
T-00215-0393 |  | EACOP-PS5-71-06-0378 |  | EACOP-PS5-71-06-0378 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-03-26 18:37 | PS5-71-06 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone H
T-00215-0394 |  | EACOP-PS5-71-08-0309 |  | EACOP-PS5-71-08-0309 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-04-02 12:28 | PS5-71-08 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone H
T-00215-0395 |  | EACOP-PS5-71-08-0310 |  | EACOP-PS5-71-08-0310 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-06-26 05:14 | PS5-71-08 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone H
T-00215-0418 |  | EACOP-PS5-71-22-0333 |  | EACOP-PS5-71-22-0333 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-05-24 14:54 | PS5-71-22 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0419 |  | EACOP-PS5-71-22-0334 |  | EACOP-PS5-71-22-0334 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-04-26 18:21 | PS5-71-22 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0420 |  | EACOP-PS5-71-22-0335 |  | EACOP-PS5-71-22-0335 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-05-04 08:47 | PS5-71-22 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0421 |  | EACOP-PS5-71-22-0336 |  | EACOP-PS5-71-22-0336 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  | 12 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-05-24 12:21 | PS5-71-22 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0422 |  | EACOP-PS5-71-22-0337 |  | EACOP-PS5-71-22-0337 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-06-07 18:48 | PS5-71-22 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0512 |  | EACOP-PS5-60-42-0046 |  | EACOP-PS5-60-42-0046 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-05-07 13:57 | PS5-60-42 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0513 |  | EACOP-PS5-60-43-0091 |  | EACOP-PS5-60-43-0091 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-05-07 14:04 | PS5-60-43 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B
T-00215-0514 |  | EACOP-PS5-60-44-0421 |  | EACOP-PS5-60-44-0421 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | 2026-05-07 14:31 | PS5-60-44 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0515 |  | EACOP-PS5-60-45-0422 |  | EACOP-PS5-60-45-0422 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | 2026-05-07 14:32 | PS5-60-45 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0516 |  | EACOP-PS5-60-46-0423 |  | EACOP-PS5-60-46-0423 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | 2026-05-07 14:33 | PS5-60-46 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0517 |  | EACOP-PS5-60-47-0424 |  | EACOP-PS5-60-47-0424 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | 2026-05-07 14:34 | PS5-60-47 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone D
T-00215-0518 |  | EACOP-PS5-60-48-0065 |  | EACOP-PS5-60-48-0065 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | 2026-05-07 14:03 | PS5-60-48 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone E
T-00216-0231 |  | EACOP-PS5-60-01-0151 |  | EACOP-PS5-60-01-0151 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0232 |  | EACOP-PS5-60-01-0152 |  | EACOP-PS5-60-01-0152 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0233 |  | EACOP-PS5-60-01-0153 |  | EACOP-PS5-60-01-0153 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0234 |  | EACOP-PS5-60-04-0154 |  | EACOP-PS5-60-04-0154 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0235 |  | EACOP-PS5-60-04-0155 |  | EACOP-PS5-60-04-0155 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0236 |  | EACOP-PS5-60-04-0156 |  | EACOP-PS5-60-04-0156 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0237 |  | EACOP-PS5-60-07-0157 |  | EACOP-PS5-60-07-0157 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0238 |  | EACOP-PS5-60-07-0158 |  | EACOP-PS5-60-07-0158 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0239 |  | EACOP-PS5-60-07-0159 |  | EACOP-PS5-60-07-0159 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0240 |  | EACOP-PS5-60-10-0160 |  | EACOP-PS5-60-10-0160 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0241 |  | EACOP-PS5-60-10-0161 |  | EACOP-PS5-60-10-0161 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0242 |  | EACOP-PS5-60-10-0162 |  | EACOP-PS5-60-10-0162 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0243 |  | EACOP-PS5-60-13-0163 |  | EACOP-PS5-60-13-0163 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0244 |  | EACOP-PS5-60-13-0164 |  | EACOP-PS5-60-13-0164 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0245 |  | EACOP-PS5-60-13-0165 |  | EACOP-PS5-60-13-0165 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0246 |  | EACOP-PS5-60-16-0166 |  | EACOP-PS5-60-16-0166 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0247 |  | EACOP-PS5-60-16-0167 |  | EACOP-PS5-60-16-0167 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0248 |  | EACOP-PS5-60-16-0168 |  | EACOP-PS5-60-16-0168 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0249 |  | EACOP-PS5-60-19-0169 |  | EACOP-PS5-60-19-0169 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone E
T-00216-0250 |  | EACOP-PS5-60-19-0170 |  | EACOP-PS5-60-19-0170 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone E
T-00216-0251 |  | EACOP-PS5-60-19-0171 |  | EACOP-PS5-60-19-0171 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone E
T-00216-0267 |  | EACOP-PS5-60-26-0183 |  | EACOP-PS5-60-26-0183 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0268 |  | EACOP-PS5-60-26-0184 |  | EACOP-PS5-60-26-0184 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0269 |  | EACOP-PS5-60-27-0185 |  | EACOP-PS5-60-27-0185 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0270 |  | EACOP-PS5-60-27-0186 |  | EACOP-PS5-60-27-0186 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0278 |  | EACOP-PS5-60-35-0194 |  | EACOP-PS5-60-35-0194 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0279 |  | EACOP-PS5-60-35-0195 |  | EACOP-PS5-60-35-0195 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0280 |  | EACOP-PS5-60-36-0196 |  | EACOP-PS5-60-36-0196 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0281 |  | EACOP-PS5-60-36-0197 |  | EACOP-PS5-60-36-0197 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0282 |  | EACOP-PS5-60-37-0198 |  | EACOP-PS5-60-37-0198 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0283 |  | EACOP-PS5-60-37-0199 |  | EACOP-PS5-60-37-0199 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0284 |  | EACOP-PS5-60-38-0200 |  | EACOP-PS5-60-38-0200 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0285 |  | EACOP-PS5-60-38-0201 |  | EACOP-PS5-60-38-0201 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0286 |  | EACOP-PS5-60-39-0202 |  | EACOP-PS5-60-39-0202 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0287 |  | EACOP-PS5-60-39-0203 |  | EACOP-PS5-60-39-0203 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0288 |  | EACOP-PS5-60-40-0204 |  | EACOP-PS5-60-40-0204 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F |  | PS5-60-40 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0289 |  | EACOP-PS5-60-40-0205 |  | EACOP-PS5-60-40-0205 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F |  | PS5-60-40 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0290 |  | EACOP-PS5-60-41-0206 |  | EACOP-PS5-60-41-0206 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone E
T-00216-0291 |  | EACOP-PS5-60-41-0207 |  | EACOP-PS5-60-41-0207 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone E
T-00216-0292 |  | EACOP-PS5-60-42-0208 |  | EACOP-PS5-60-42-0208 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0293 |  | EACOP-PS5-60-42-0209 |  | EACOP-PS5-60-42-0209 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0294 |  | EACOP-PS5-60-43-0210 |  | EACOP-PS5-60-43-0210 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0295 |  | EACOP-PS5-60-43-0211 |  | EACOP-PS5-60-43-0211 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0296 |  | EACOP-PS5-60-44-0212 |  | EACOP-PS5-60-44-0212 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C |  | PS5-60-44 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0297 |  | EACOP-PS5-60-44-0213 |  | EACOP-PS5-60-44-0213 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C |  | PS5-60-44 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0298 |  | EACOP-PS5-60-45-0214 |  | EACOP-PS5-60-45-0214 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D |  | PS5-60-45 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0299 |  | EACOP-PS5-60-45-0215 |  | EACOP-PS5-60-45-0215 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D |  | PS5-60-45 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0300 |  | EACOP-PS5-60-46-0216 |  | EACOP-PS5-60-46-0216 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E |  | PS5-60-46 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0301 |  | EACOP-PS5-60-46-0217 |  | EACOP-PS5-60-46-0217 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E |  | PS5-60-46 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0302 |  | EACOP-PS5-60-47-0218 |  | EACOP-PS5-60-47-0218 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F |  | PS5-60-47 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0303 |  | EACOP-PS5-60-47-0219 |  | EACOP-PS5-60-47-0219 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F |  | PS5-60-47 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0304 |  | EACOP-PS5-60-48-0220 |  | EACOP-PS5-60-48-0220 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G |  | PS5-60-48 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone E
T-00216-0305 |  | EACOP-PS5-60-48-0221 |  | EACOP-PS5-60-48-0221 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G |  | PS5-60-48 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone E
T-00216-0306 |  | EACOP-PS5-60-49-0222 |  | EACOP-PS5-60-49-0222 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0307 |  | EACOP-PS5-60-49-0223 |  | EACOP-PS5-60-49-0223 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0308 |  | EACOP-PS5-60-50-0224 |  | EACOP-PS5-60-50-0224 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0309 |  | EACOP-PS5-60-50-0225 |  | EACOP-PS5-60-50-0225 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0310 |  | EACOP-PS5-60-51-0226 |  | EACOP-PS5-60-51-0226 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0311 |  | EACOP-PS5-60-51-0227 |  | EACOP-PS5-60-51-0227 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0312 |  | EACOP-PS5-60-52-0228 |  | EACOP-PS5-60-52-0228 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0313 |  | EACOP-PS5-60-52-0229 |  | EACOP-PS5-60-52-0229 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0314 |  | EACOP-PS5-60-53-0230 |  | EACOP-PS5-60-53-0230 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0315 |  | EACOP-PS5-60-53-0231 |  | EACOP-PS5-60-53-0231 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0316 |  | EACOP-PS5-60-54-0232 |  | EACOP-PS5-60-54-0232 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0317 |  | EACOP-PS5-60-54-0233 |  | EACOP-PS5-60-54-0233 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0318 |  | EACOP-PS5-60-55-0234 |  | EACOP-PS5-60-55-0234 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone E
T-00216-0319 |  | EACOP-PS5-60-55-0235 |  | EACOP-PS5-60-55-0235 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone E
T-00216-0320 |  | EACOP-PS5-60-56-0236 |  | EACOP-PS5-60-56-0236 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0321 |  | EACOP-PS5-60-56-0237 |  | EACOP-PS5-60-56-0237 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0322 |  | EACOP-PS5-60-58-0238 |  | EACOP-PS5-60-58-0238 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0323 |  | EACOP-PS5-60-58-0239 |  | EACOP-PS5-60-58-0239 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0324 |  | EACOP-PS5-60-60-0240 |  | EACOP-PS5-60-60-0240 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0325 |  | EACOP-PS5-60-60-0241 |  | EACOP-PS5-60-60-0241 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0326 |  | EACOP-PS5-60-62-0242 |  | EACOP-PS5-60-62-0242 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0327 |  | EACOP-PS5-60-62-0243 |  | EACOP-PS5-60-62-0243 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0328 |  | EACOP-PS5-60-64-0244 |  | EACOP-PS5-60-64-0244 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0329 |  | EACOP-PS5-60-64-0245 |  | EACOP-PS5-60-64-0245 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0330 |  | EACOP-PS5-60-66-0246 |  | EACOP-PS5-60-66-0246 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0331 |  | EACOP-PS5-60-66-0247 |  | EACOP-PS5-60-66-0247 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0332 |  | EACOP-PS5-60-68-0248 |  | EACOP-PS5-60-68-0248 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone E
T-00216-0333 |  | EACOP-PS5-60-68-0249 |  | EACOP-PS5-60-68-0249 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone E
T-00216-0334 |  | EACOP-PS5-60-70-0250 |  | EACOP-PS5-60-70-0250 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0335 |  | EACOP-PS5-60-70-0251 |  | EACOP-PS5-60-70-0251 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0336 |  | EACOP-PS5-60-70-0252 |  | EACOP-PS5-60-70-0252 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0337 |  | EACOP-PS5-60-70-0253 |  | EACOP-PS5-60-70-0253 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0338 |  | EACOP-PS5-60-70-0254 |  | EACOP-PS5-60-70-0254 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0339 |  | EACOP-PS5-60-70-0255 |  | EACOP-PS5-60-70-0255 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0340 |  | EACOP-PS5-60-71-0256 |  | EACOP-PS5-60-71-0256 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0341 |  | EACOP-PS5-60-71-0257 |  | EACOP-PS5-60-71-0257 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0342 |  | EACOP-PS5-60-71-0258 |  | EACOP-PS5-60-71-0258 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0343 |  | EACOP-PS5-60-71-0259 |  | EACOP-PS5-60-71-0259 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0344 |  | EACOP-PS5-60-71-0260 |  | EACOP-PS5-60-71-0260 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0345 |  | EACOP-PS5-60-71-0261 |  | EACOP-PS5-60-71-0261 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0346 |  | EACOP-PS5-60-72-0262 |  | EACOP-PS5-60-72-0262 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0347 |  | EACOP-PS5-60-72-0263 |  | EACOP-PS5-60-72-0263 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0348 |  | EACOP-PS5-60-72-0264 |  | EACOP-PS5-60-72-0264 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0349 |  | EACOP-PS5-60-72-0265 |  | EACOP-PS5-60-72-0265 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0350 |  | EACOP-PS5-60-72-0266 |  | EACOP-PS5-60-72-0266 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0351 |  | EACOP-PS5-60-72-0267 |  | EACOP-PS5-60-72-0267 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0352 |  | EACOP-PS5-60-73-0268 |  | EACOP-PS5-60-73-0268 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0353 |  | EACOP-PS5-60-73-0269 |  | EACOP-PS5-60-73-0269 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0354 |  | EACOP-PS5-60-73-0270 |  | EACOP-PS5-60-73-0270 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0355 |  | EACOP-PS5-60-73-0271 |  | EACOP-PS5-60-73-0271 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0356 |  | EACOP-PS5-60-73-0272 |  | EACOP-PS5-60-73-0272 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0357 |  | EACOP-PS5-60-73-0273 |  | EACOP-PS5-60-73-0273 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0358 |  | EACOP-PS5-60-74-0274 |  | EACOP-PS5-60-74-0274 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0359 |  | EACOP-PS5-60-74-0275 |  | EACOP-PS5-60-74-0275 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0360 |  | EACOP-PS5-60-74-0276 |  | EACOP-PS5-60-74-0276 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0361 |  | EACOP-PS5-60-74-0277 |  | EACOP-PS5-60-74-0277 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0362 |  | EACOP-PS5-60-74-0278 |  | EACOP-PS5-60-74-0278 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0363 |  | EACOP-PS5-60-74-0279 |  | EACOP-PS5-60-74-0279 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0364 |  | EACOP-PS5-60-75-0280 |  | EACOP-PS5-60-75-0280 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0365 |  | EACOP-PS5-60-75-0281 |  | EACOP-PS5-60-75-0281 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0366 |  | EACOP-PS5-60-75-0282 |  | EACOP-PS5-60-75-0282 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0367 |  | EACOP-PS5-60-75-0283 |  | EACOP-PS5-60-75-0283 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0368 |  | EACOP-PS5-60-75-0284 |  | EACOP-PS5-60-75-0284 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0369 |  | EACOP-PS5-60-75-0285 |  | EACOP-PS5-60-75-0285 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0370 |  | EACOP-PS5-60-76-0286 |  | EACOP-PS5-60-76-0286 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone E
T-00216-0371 |  | EACOP-PS5-60-76-0287 |  | EACOP-PS5-60-76-0287 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone E
T-00216-0372 |  | EACOP-PS5-60-76-0288 |  | EACOP-PS5-60-76-0288 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone E
T-00216-0373 |  | EACOP-PS5-60-76-0289 |  | EACOP-PS5-60-76-0289 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone E
T-00216-0374 |  | EACOP-PS5-60-76-0290 |  | EACOP-PS5-60-76-0290 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone E
T-00216-0375 |  | EACOP-PS5-60-76-0291 |  | EACOP-PS5-60-76-0291 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone E
T-00216-0391 |  | EACOP-PS5-71-06-0307 |  | EACOP-PS5-71-06-0307 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone H
T-00216-0392 |  | EACOP-PS5-71-06-0308 |  | EACOP-PS5-71-06-0308 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone H
T-00216-0393 |  | EACOP-PS5-71-06-0378 |  | EACOP-PS5-71-06-0378 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone H
T-00216-0394 |  | EACOP-PS5-71-08-0309 |  | EACOP-PS5-71-08-0309 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone H
T-00216-0395 |  | EACOP-PS5-71-08-0310 |  | EACOP-PS5-71-08-0310 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone H
T-00216-0418 |  | EACOP-PS5-71-22-0333 |  | EACOP-PS5-71-22-0333 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0419 |  | EACOP-PS5-71-22-0334 |  | EACOP-PS5-71-22-0334 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0420 |  | EACOP-PS5-71-22-0335 |  | EACOP-PS5-71-22-0335 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0421 |  | EACOP-PS5-71-22-0336 |  | EACOP-PS5-71-22-0336 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0422 |  | EACOP-PS5-71-22-0337 |  | EACOP-PS5-71-22-0337 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0512 |  | EACOP-PS5-60-42-0046 |  | EACOP-PS5-60-42-0046 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0513 |  | EACOP-PS5-60-43-0091 |  | EACOP-PS5-60-43-0091 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B
T-00216-0514 |  | EACOP-PS5-60-44-0421 |  | EACOP-PS5-60-44-0421 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C |  | PS5-60-44 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0515 |  | EACOP-PS5-60-45-0422 |  | EACOP-PS5-60-45-0422 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D |  | PS5-60-45 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0516 |  | EACOP-PS5-60-46-0423 |  | EACOP-PS5-60-46-0423 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E |  | PS5-60-46 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0517 |  | EACOP-PS5-60-47-0424 |  | EACOP-PS5-60-47-0424 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F |  | PS5-60-47 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone D
T-00216-0518 |  | EACOP-PS5-60-48-0065 |  | EACOP-PS5-60-48-0065 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G |  | PS5-60-48 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone E
T-00218-0097 | PS5-60-01_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Painting Line | P | To be completed | PS5 - Milestone B
T-00218-0098 | PS5-60-04_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Painting Line | P | To be completed | PS5 - Milestone B
T-00218-0099 | PS5-60-07_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0100 | PS5-60-10_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0101 | PS5-60-13_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0102 | PS5-60-16_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0103 | PS5-60-19_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Painting Line | P | To be completed | PS5 - Milestone E
T-00218-0107 | PS5-60-26_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | Painting Line | P | To be completed | PS5 - Milestone B
T-00218-0108 | PS5-60-27_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Painting Line | P | To be completed | PS5 - Milestone B
T-00218-0116 | PS5-60-35_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Painting Line | P | To be completed | PS5 - Milestone B
T-00218-0117 | PS5-60-36_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Painting Line | P | To be completed | PS5 - Milestone B
T-00218-0118 | PS5-60-37_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0119 | PS5-60-38_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0120 | PS5-60-39_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0121 | PS5-60-40_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F |  | PS5-60-40 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0122 | PS5-60-41_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | Painting Line | P | To be completed | PS5 - Milestone E
T-00218-0123 | PS5-60-42_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Painting Line | P | To be completed | PS5 - Milestone B
T-00218-0124 | PS5-60-43_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Painting Line | P | To be completed | PS5 - Milestone B
T-00218-0125 | PS5-60-44_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C |  | PS5-60-44 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0126 | PS5-60-45_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D |  | PS5-60-45 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0127 | PS5-60-46_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E |  | PS5-60-46 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0128 | PS5-60-47_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F |  | PS5-60-47 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0129 | PS5-60-48_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G |  | PS5-60-48 |  |  | Painting Line | P | To be completed | PS5 - Milestone E
T-00218-0130 | PS5-60-49_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Painting Line | P | To be completed | PS5 - Milestone B
T-00218-0131 | PS5-60-50_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Painting Line | P | To be completed | PS5 - Milestone B
T-00218-0132 | PS5-60-51_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0133 | PS5-60-52_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0134 | PS5-60-53_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0135 | PS5-60-54_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0136 | PS5-60-55_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | Painting Line | P | To be completed | PS5 - Milestone E
T-00218-0137 | PS5-60-56_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Painting Line | P | To be completed | PS5 - Milestone B
T-00218-0138 | PS5-60-58_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Painting Line | P | To be completed | PS5 - Milestone B
T-00218-0139 | PS5-60-60_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0140 | PS5-60-62_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0141 | PS5-60-64_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0142 | PS5-60-66_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0143 | PS5-60-68_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | Painting Line | P | To be completed | PS5 - Milestone E
T-00218-0144 | PS5-60-70_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Painting Line | P | To be completed | PS5 - Milestone B
T-00218-0145 | PS5-60-71_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Painting Line | P | To be completed | PS5 - Milestone B
T-00218-0146 | PS5-60-72_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0147 | PS5-60-73_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0148 | PS5-60-74_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0149 | PS5-60-75_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Painting Line | P | To be completed | PS5 - Milestone D
T-00218-0150 | PS5-60-76_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Painting Line | P | To be completed | PS5 - Milestone E
T-00218-0155 | PS5-71-06_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Painting Line | P | To be completed | PS5 - Milestone H
T-00218-0156 | PS5-71-08_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Painting Line | P | To be completed | PS5 - Milestone H
T-00218-0166 | PS5-71-22_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Painting Line | P | To be completed | PS5 - Milestone B
T-00220-0008 | PS5-60-35_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone B
T-00220-0009 | PS5-60-36_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone B
T-00220-0010 | PS5-60-37_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone D
T-00220-0011 | PS5-60-38_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone D
T-00220-0012 | PS5-60-39_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone D
T-00220-0013 | PS5-60-40_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F |  | PS5-60-40 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone D
T-00220-0014 | PS5-60-41_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone E
T-00220-0015 | PS5-60-49_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone B
T-00220-0016 | PS5-60-50_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone B
T-00220-0017 | PS5-60-51_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone D
T-00220-0018 | PS5-60-52_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone D
T-00220-0019 | PS5-60-53_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone D
T-00220-0020 | PS5-60-54_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone D
T-00220-0021 | PS5-60-55_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone E
T-00220-0022 | PS5-60-70_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone B
T-00220-0023 | PS5-60-71_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone B
T-00220-0024 | PS5-60-72_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone D
T-00220-0025 | PS5-60-73_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone D
T-00220-0026 | PS5-60-74_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone D
T-00220-0027 | PS5-60-75_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone D
T-00220-0028 | PS5-60-76_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone E
T-00221-0231 |  | EACOP-PS5-60-01-0151 |  | EACOP-PS5-60-01-0151 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-03 11:35 | PS5-60-01 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0232 |  | EACOP-PS5-60-01-0152 |  | EACOP-PS5-60-01-0152 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-03 11:36 | PS5-60-01 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0233 |  | EACOP-PS5-60-01-0153 |  | EACOP-PS5-60-01-0153 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-05 13:00 | PS5-60-01 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0234 |  | EACOP-PS5-60-04-0154 |  | EACOP-PS5-60-04-0154 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-08 12:18 | PS5-60-04 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0235 |  | EACOP-PS5-60-04-0155 |  | EACOP-PS5-60-04-0155 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-17 11:54 | PS5-60-04 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0236 |  | EACOP-PS5-60-04-0156 |  | EACOP-PS5-60-04-0156 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-17 12:04 | PS5-60-04 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0237 |  | EACOP-PS5-60-07-0157 |  | EACOP-PS5-60-07-0157 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-06-17 11:10 | PS5-60-07 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0238 |  | EACOP-PS5-60-07-0158 |  | EACOP-PS5-60-07-0158 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-06-18 11:27 | PS5-60-07 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0239 |  | EACOP-PS5-60-07-0159 |  | EACOP-PS5-60-07-0159 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-06-17 11:16 | PS5-60-07 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0240 |  | EACOP-PS5-60-10-0160 |  | EACOP-PS5-60-10-0160 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-17 12:10 | PS5-60-10 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0241 |  | EACOP-PS5-60-10-0161 |  | EACOP-PS5-60-10-0161 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-23 12:39 | PS5-60-10 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0242 |  | EACOP-PS5-60-10-0162 |  | EACOP-PS5-60-10-0162 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-23 12:41 | PS5-60-10 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0243 |  | EACOP-PS5-60-13-0163 |  | EACOP-PS5-60-13-0163 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-06-24 11:28 | PS5-60-13 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0244 |  | EACOP-PS5-60-13-0164 |  | EACOP-PS5-60-13-0164 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-06-24 11:28 | PS5-60-13 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0245 |  | EACOP-PS5-60-13-0165 |  | EACOP-PS5-60-13-0165 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-06-24 11:29 | PS5-60-13 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0246 |  | EACOP-PS5-60-16-0166 |  | EACOP-PS5-60-16-0166 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-06-24 11:30 | PS5-60-16 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0247 |  | EACOP-PS5-60-16-0167 |  | EACOP-PS5-60-16-0167 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-06-24 11:31 | PS5-60-16 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0248 |  | EACOP-PS5-60-16-0168 |  | EACOP-PS5-60-16-0168 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-06-24 11:32 | PS5-60-16 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0249 |  | EACOP-PS5-60-19-0169 |  | EACOP-PS5-60-19-0169 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-06-30 08:57 | PS5-60-19 |  |  | Pressure Test |  | Closed | PS5 - Milestone E
T-00221-0250 |  | EACOP-PS5-60-19-0170 |  | EACOP-PS5-60-19-0170 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Pressure Test |  | Completed (not Closed) | PS5 - Milestone E
T-00221-0251 |  | EACOP-PS5-60-19-0171 |  | EACOP-PS5-60-19-0171 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Pressure Test |  | Completed (not Closed) | PS5 - Milestone E
T-00221-0267 |  | EACOP-PS5-60-26-0183 |  | EACOP-PS5-60-26-0183 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-24 11:36 | PS5-60-26 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0268 |  | EACOP-PS5-60-26-0184 |  | EACOP-PS5-60-26-0184 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-01 05:52 | PS5-60-26 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0269 |  | EACOP-PS5-60-27-0185 |  | EACOP-PS5-60-27-0185 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-06-01 05:54 | PS5-60-27 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0270 |  | EACOP-PS5-60-27-0186 |  | EACOP-PS5-60-27-0186 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Pressure Test |  | To be completed | PS5 - Milestone B
T-00221-0278 |  | EACOP-PS5-60-35-0194 |  | EACOP-PS5-60-35-0194 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Pressure Test |  | To be completed | PS5 - Milestone B
T-00221-0279 |  | EACOP-PS5-60-35-0195 |  | EACOP-PS5-60-35-0195 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-05-09 10:32 | PS5-60-35 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0280 |  | EACOP-PS5-60-36-0196 |  | EACOP-PS5-60-36-0196 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Pressure Test |  | To be completed | PS5 - Milestone B
T-00221-0281 |  | EACOP-PS5-60-36-0197 |  | EACOP-PS5-60-36-0197 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-06-01 05:55 | PS5-60-36 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0282 |  | EACOP-PS5-60-37-0198 |  | EACOP-PS5-60-37-0198 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 |  |  | Pressure Test |  | To be completed | PS5 - Milestone D
T-00221-0283 |  | EACOP-PS5-60-37-0199 |  | EACOP-PS5-60-37-0199 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C | 2026-06-01 05:51 | PS5-60-37 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0284 |  | EACOP-PS5-60-38-0200 |  | EACOP-PS5-60-38-0200 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 |  |  | Pressure Test |  | To be completed | PS5 - Milestone D
T-00221-0285 |  | EACOP-PS5-60-38-0201 |  | EACOP-PS5-60-38-0201 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D | 2026-06-01 05:43 | PS5-60-38 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0286 |  | EACOP-PS5-60-39-0202 |  | EACOP-PS5-60-39-0202 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  | Pressure Test |  | To be completed | PS5 - Milestone D
T-00221-0287 |  | EACOP-PS5-60-39-0203 |  | EACOP-PS5-60-39-0203 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E | 2026-06-24 11:34 | PS5-60-39 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0288 |  | EACOP-PS5-60-40-0204 |  | EACOP-PS5-60-40-0204 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F |  | PS5-60-40 |  |  | Pressure Test |  | To be completed | PS5 - Milestone D
T-00221-0289 |  | EACOP-PS5-60-40-0205 |  | EACOP-PS5-60-40-0205 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F | 2026-06-03 11:36 | PS5-60-40 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0290 |  | EACOP-PS5-60-41-0206 |  | EACOP-PS5-60-41-0206 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | Pressure Test |  | To be completed | PS5 - Milestone E
T-00221-0291 |  | EACOP-PS5-60-41-0207 |  | EACOP-PS5-60-41-0207 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | Pressure Test |  | Completed (not Closed) | PS5 - Milestone E
T-00221-0292 |  | EACOP-PS5-60-42-0208 |  | EACOP-PS5-60-42-0208 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Pressure Test |  | To be completed | PS5 - Milestone B
T-00221-0293 |  | EACOP-PS5-60-42-0209 |  | EACOP-PS5-60-42-0209 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-06-03 11:38 | PS5-60-42 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0294 |  | EACOP-PS5-60-43-0210 |  | EACOP-PS5-60-43-0210 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Pressure Test |  | To be completed | PS5 - Milestone B
T-00221-0295 |  | EACOP-PS5-60-43-0211 |  | EACOP-PS5-60-43-0211 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-06-03 11:40 | PS5-60-43 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0296 |  | EACOP-PS5-60-44-0212 |  | EACOP-PS5-60-44-0212 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C |  | PS5-60-44 |  |  | Pressure Test |  | To be completed | PS5 - Milestone D
T-00221-0297 |  | EACOP-PS5-60-44-0213 |  | EACOP-PS5-60-44-0213 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | 2026-06-03 11:41 | PS5-60-44 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0298 |  | EACOP-PS5-60-45-0214 |  | EACOP-PS5-60-45-0214 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D |  | PS5-60-45 |  |  | Pressure Test |  | To be completed | PS5 - Milestone D
T-00221-0299 |  | EACOP-PS5-60-45-0215 |  | EACOP-PS5-60-45-0215 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | 2026-06-03 11:43 | PS5-60-45 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0300 |  | EACOP-PS5-60-46-0216 |  | EACOP-PS5-60-46-0216 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E |  | PS5-60-46 |  |  | Pressure Test |  | To be completed | PS5 - Milestone D
T-00221-0301 |  | EACOP-PS5-60-46-0217 |  | EACOP-PS5-60-46-0217 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | 2026-06-03 11:46 | PS5-60-46 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0302 |  | EACOP-PS5-60-47-0218 |  | EACOP-PS5-60-47-0218 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F |  | PS5-60-47 |  |  | Pressure Test |  | To be completed | PS5 - Milestone D
T-00221-0303 |  | EACOP-PS5-60-47-0219 |  | EACOP-PS5-60-47-0219 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | 2026-06-03 11:56 | PS5-60-47 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0304 |  | EACOP-PS5-60-48-0220 |  | EACOP-PS5-60-48-0220 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G |  | PS5-60-48 |  |  | Pressure Test |  | To be completed | PS5 - Milestone E
T-00221-0305 |  | EACOP-PS5-60-48-0221 |  | EACOP-PS5-60-48-0221 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | 2026-06-03 11:57 | PS5-60-48 |  |  | Pressure Test |  | Closed | PS5 - Milestone E
T-00221-0306 |  | EACOP-PS5-60-49-0222 |  | EACOP-PS5-60-49-0222 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Pressure Test |  | To be completed | PS5 - Milestone B
T-00221-0307 |  | EACOP-PS5-60-49-0223 |  | EACOP-PS5-60-49-0223 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2026-06-05 13:03 | PS5-60-49 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0308 |  | EACOP-PS5-60-50-0224 |  | EACOP-PS5-60-50-0224 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Pressure Test |  | To be completed | PS5 - Milestone B
T-00221-0309 |  | EACOP-PS5-60-50-0225 |  | EACOP-PS5-60-50-0225 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2026-06-08 12:19 | PS5-60-50 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0310 |  | EACOP-PS5-60-51-0226 |  | EACOP-PS5-60-51-0226 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | Pressure Test |  | To be completed | PS5 - Milestone D
T-00221-0311 |  | EACOP-PS5-60-51-0227 |  | EACOP-PS5-60-51-0227 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | 2026-06-17 11:20 | PS5-60-51 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0312 |  | EACOP-PS5-60-52-0228 |  | EACOP-PS5-60-52-0228 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | Pressure Test |  | To be completed | PS5 - Milestone D
T-00221-0313 |  | EACOP-PS5-60-52-0229 |  | EACOP-PS5-60-52-0229 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | Pressure Test |  | Completed (not Closed) | PS5 - Milestone D
T-00221-0314 |  | EACOP-PS5-60-53-0230 |  | EACOP-PS5-60-53-0230 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | Pressure Test |  | To be completed | PS5 - Milestone D
T-00221-0315 |  | EACOP-PS5-60-53-0231 |  | EACOP-PS5-60-53-0231 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | 2026-06-30 09:09 | PS5-60-53 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0316 |  | EACOP-PS5-60-54-0232 |  | EACOP-PS5-60-54-0232 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | Pressure Test |  | To be completed | PS5 - Milestone D
T-00221-0317 |  | EACOP-PS5-60-54-0233 |  | EACOP-PS5-60-54-0233 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | 2026-07-01 06:18 | PS5-60-54 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0318 |  | EACOP-PS5-60-55-0234 |  | EACOP-PS5-60-55-0234 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | Pressure Test |  | To be completed | PS5 - Milestone E
T-00221-0319 |  | EACOP-PS5-60-55-0235 |  | EACOP-PS5-60-55-0235 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | 2026-07-03 06:47 | PS5-60-55 |  |  | Pressure Test |  | Closed | PS5 - Milestone E
T-00221-0320 |  | EACOP-PS5-60-56-0236 |  | EACOP-PS5-60-56-0236 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-04-30 09:33 | PS5-60-56 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0321 |  | EACOP-PS5-60-56-0237 |  | EACOP-PS5-60-56-0237 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-04-30 09:48 | PS5-60-56 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0322 |  | EACOP-PS5-60-58-0238 |  | EACOP-PS5-60-58-0238 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-05-09 11:00 | PS5-60-58 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0323 |  | EACOP-PS5-60-58-0239 |  | EACOP-PS5-60-58-0239 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-05-09 10:37 | PS5-60-58 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0324 |  | EACOP-PS5-60-60-0240 |  | EACOP-PS5-60-60-0240 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 2026-04-24 07:20 | PS5-60-60 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0325 |  | EACOP-PS5-60-60-0241 |  | EACOP-PS5-60-60-0241 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 2026-06-01 05:39 | PS5-60-60 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0326 |  | EACOP-PS5-60-62-0242 |  | EACOP-PS5-60-62-0242 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2026-04-27 11:05 | PS5-60-62 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0327 |  | EACOP-PS5-60-62-0243 |  | EACOP-PS5-60-62-0243 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2026-06-01 05:46 | PS5-60-62 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0328 |  | EACOP-PS5-60-64-0244 |  | EACOP-PS5-60-64-0244 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | 2026-04-30 09:41 | PS5-60-64 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0329 |  | EACOP-PS5-60-64-0245 |  | EACOP-PS5-60-64-0245 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | 2026-06-03 11:58 | PS5-60-64 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0330 |  | EACOP-PS5-60-66-0246 |  | EACOP-PS5-60-66-0246 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | 2026-06-01 05:41 | PS5-60-66 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0331 |  | EACOP-PS5-60-66-0247 |  | EACOP-PS5-60-66-0247 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | 2026-06-03 11:59 | PS5-60-66 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0332 |  | EACOP-PS5-60-68-0248 |  | EACOP-PS5-60-68-0248 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | 2026-04-30 09:47 | PS5-60-68 |  |  | Pressure Test |  | Closed | PS5 - Milestone E
T-00221-0333 |  | EACOP-PS5-60-68-0249 |  | EACOP-PS5-60-68-0249 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | Pressure Test |  | Completed (not Closed) | PS5 - Milestone E
T-00221-0334 |  | EACOP-PS5-60-70-0250 |  | EACOP-PS5-60-70-0250 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-05 12:45 | PS5-60-70 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0335 |  | EACOP-PS5-60-70-0251 |  | EACOP-PS5-60-70-0251 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-20 11:33 | PS5-60-70 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0336 |  | EACOP-PS5-60-70-0252 |  | EACOP-PS5-60-70-0252 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-05 12:41 | PS5-60-70 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0337 |  | EACOP-PS5-60-70-0253 |  | EACOP-PS5-60-70-0253 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-05 12:43 | PS5-60-70 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0338 |  | EACOP-PS5-60-70-0254 |  | EACOP-PS5-60-70-0254 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-03 12:00 | PS5-60-70 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0339 |  | EACOP-PS5-60-70-0255 |  | EACOP-PS5-60-70-0255 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-03 12:01 | PS5-60-70 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0340 |  | EACOP-PS5-60-71-0256 |  | EACOP-PS5-60-71-0256 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-17 11:17 | PS5-60-71 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0341 |  | EACOP-PS5-60-71-0257 |  | EACOP-PS5-60-71-0257 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-03 12:07 | PS5-60-71 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0342 |  | EACOP-PS5-60-71-0258 |  | EACOP-PS5-60-71-0258 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-05 12:53 | PS5-60-71 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0343 |  | EACOP-PS5-60-71-0259 |  | EACOP-PS5-60-71-0259 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-05 12:56 | PS5-60-71 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0344 |  | EACOP-PS5-60-71-0260 |  | EACOP-PS5-60-71-0260 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-05 12:57 | PS5-60-71 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0345 |  | EACOP-PS5-60-71-0261 |  | EACOP-PS5-60-71-0261 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-05 12:58 | PS5-60-71 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0346 |  | EACOP-PS5-60-72-0262 |  | EACOP-PS5-60-72-0262 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-23 12:50 | PS5-60-72 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0347 |  | EACOP-PS5-60-72-0263 |  | EACOP-PS5-60-72-0263 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-03 12:07 | PS5-60-72 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0348 |  | EACOP-PS5-60-72-0264 |  | EACOP-PS5-60-72-0264 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-18 11:33 | PS5-60-72 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0349 |  | EACOP-PS5-60-72-0265 |  | EACOP-PS5-60-72-0265 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-18 11:35 | PS5-60-72 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0350 |  | EACOP-PS5-60-72-0266 |  | EACOP-PS5-60-72-0266 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-18 11:36 | PS5-60-72 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0351 |  | EACOP-PS5-60-72-0267 |  | EACOP-PS5-60-72-0267 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-18 11:28 | PS5-60-72 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0352 |  | EACOP-PS5-60-73-0268 |  | EACOP-PS5-60-73-0268 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-23 12:50 | PS5-60-73 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0353 |  | EACOP-PS5-60-73-0269 |  | EACOP-PS5-60-73-0269 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-03 12:08 | PS5-60-73 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0354 |  | EACOP-PS5-60-73-0270 |  | EACOP-PS5-60-73-0270 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-17 11:19 | PS5-60-73 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0355 |  | EACOP-PS5-60-73-0271 |  | EACOP-PS5-60-73-0271 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-17 12:09 | PS5-60-73 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0356 |  | EACOP-PS5-60-73-0272 |  | EACOP-PS5-60-73-0272 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-17 11:40 | PS5-60-73 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0357 |  | EACOP-PS5-60-73-0273 |  | EACOP-PS5-60-73-0273 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-18 11:25 | PS5-60-73 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0358 |  | EACOP-PS5-60-74-0274 |  | EACOP-PS5-60-74-0274 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-06-24 11:39 | PS5-60-74 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0359 |  | EACOP-PS5-60-74-0275 |  | EACOP-PS5-60-74-0275 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-06-03 12:09 | PS5-60-74 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0360 |  | EACOP-PS5-60-74-0276 |  | EACOP-PS5-60-74-0276 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-06-24 11:40 | PS5-60-74 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0361 |  | EACOP-PS5-60-74-0277 |  | EACOP-PS5-60-74-0277 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-06-24 11:42 | PS5-60-74 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0362 |  | EACOP-PS5-60-74-0278 |  | EACOP-PS5-60-74-0278 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-06-24 11:41 | PS5-60-74 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0363 |  | EACOP-PS5-60-74-0279 |  | EACOP-PS5-60-74-0279 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-06-24 11:42 | PS5-60-74 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0364 |  | EACOP-PS5-60-75-0280 |  | EACOP-PS5-60-75-0280 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-06-30 09:10 | PS5-60-75 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0365 |  | EACOP-PS5-60-75-0281 |  | EACOP-PS5-60-75-0281 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-06-01 05:45 | PS5-60-75 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0366 |  | EACOP-PS5-60-75-0282 |  | EACOP-PS5-60-75-0282 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-06-30 09:12 | PS5-60-75 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0367 |  | EACOP-PS5-60-75-0283 |  | EACOP-PS5-60-75-0283 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-06-30 09:12 | PS5-60-75 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0368 |  | EACOP-PS5-60-75-0284 |  | EACOP-PS5-60-75-0284 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-06-30 09:13 | PS5-60-75 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0369 |  | EACOP-PS5-60-75-0285 |  | EACOP-PS5-60-75-0285 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-06-30 09:14 | PS5-60-75 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0370 |  | EACOP-PS5-60-76-0286 |  | EACOP-PS5-60-76-0286 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-07-01 06:16 | PS5-60-76 |  |  | Pressure Test |  | Closed | PS5 - Milestone E
T-00221-0371 |  | EACOP-PS5-60-76-0287 |  | EACOP-PS5-60-76-0287 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-06-03 12:10 | PS5-60-76 |  |  | Pressure Test |  | Closed | PS5 - Milestone E
T-00221-0372 |  | EACOP-PS5-60-76-0288 |  | EACOP-PS5-60-76-0288 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-06-30 08:58 | PS5-60-76 |  |  | Pressure Test |  | Closed | PS5 - Milestone E
T-00221-0373 |  | EACOP-PS5-60-76-0289 |  | EACOP-PS5-60-76-0289 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-06-30 08:59 | PS5-60-76 |  |  | Pressure Test |  | Closed | PS5 - Milestone E
T-00221-0374 |  | EACOP-PS5-60-76-0290 |  | EACOP-PS5-60-76-0290 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-07-01 06:17 | PS5-60-76 |  |  | Pressure Test |  | Closed | PS5 - Milestone E
T-00221-0375 |  | EACOP-PS5-60-76-0291 |  | EACOP-PS5-60-76-0291 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-07-01 06:18 | PS5-60-76 |  |  | Pressure Test |  | Closed | PS5 - Milestone E
T-00221-0391 |  | EACOP-PS5-71-06-0307 |  | EACOP-PS5-71-06-0307 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-05-02 05:49 | PS5-71-06 |  |  | Pressure Test |  | Closed | PS5 - Milestone H
T-00221-0392 |  | EACOP-PS5-71-06-0308 |  | EACOP-PS5-71-06-0308 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-06-01 05:34 | PS5-71-06 |  |  | Pressure Test |  | Closed | PS5 - Milestone H
T-00221-0393 |  | EACOP-PS5-71-06-0378 |  | EACOP-PS5-71-06-0378 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-04-13 11:37 | PS5-71-06 |  |  | Pressure Test |  | Closed | PS5 - Milestone H
T-00221-0394 |  | EACOP-PS5-71-08-0309 |  | EACOP-PS5-71-08-0309 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-05-05 11:14 | PS5-71-08 |  |  | Pressure Test |  | Closed | PS5 - Milestone H
T-00221-0395 |  | EACOP-PS5-71-08-0310 |  | EACOP-PS5-71-08-0310 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Pressure Test |  | Completed (not Closed) | PS5 - Milestone H
T-00221-0418 |  | EACOP-PS5-71-22-0333 |  | EACOP-PS5-71-22-0333 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-06-01 05:50 | PS5-71-22 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0419 |  | EACOP-PS5-71-22-0334 |  | EACOP-PS5-71-22-0334 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-04-30 09:49 | PS5-71-22 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0420 |  | EACOP-PS5-71-22-0335 |  | EACOP-PS5-71-22-0335 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-05-09 10:31 | PS5-71-22 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0421 |  | EACOP-PS5-71-22-0336 |  | EACOP-PS5-71-22-0336 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-05-09 10:36 | PS5-71-22 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0422 |  | EACOP-PS5-71-22-0337 |  | EACOP-PS5-71-22-0337 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-05-09 10:34 | PS5-71-22 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0512 |  | EACOP-PS5-60-42-0046 |  | EACOP-PS5-60-42-0046 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-05-09 10:37 | PS5-60-42 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0513 |  | EACOP-PS5-60-43-0091 |  | EACOP-PS5-60-43-0091 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-05-09 10:38 | PS5-60-43 |  |  | Pressure Test |  | Closed | PS5 - Milestone B
T-00221-0514 |  | EACOP-PS5-60-44-0421 |  | EACOP-PS5-60-44-0421 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | 2026-05-09 10:39 | PS5-60-44 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0515 |  | EACOP-PS5-60-45-0422 |  | EACOP-PS5-60-45-0422 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | 2026-05-09 10:39 | PS5-60-45 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0516 |  | EACOP-PS5-60-46-0423 |  | EACOP-PS5-60-46-0423 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | 2026-05-09 10:40 | PS5-60-46 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0517 |  | EACOP-PS5-60-47-0424 |  | EACOP-PS5-60-47-0424 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | 2026-05-09 10:40 | PS5-60-47 |  |  | Pressure Test |  | Closed | PS5 - Milestone D
T-00221-0518 |  | EACOP-PS5-60-48-0065 |  | EACOP-PS5-60-48-0065 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | 2026-05-09 10:38 | PS5-60-48 |  |  | Pressure Test |  | Closed | PS5 - Milestone E
T-00223-0231 |  | EACOP-PS5-60-01-0151 |  | EACOP-PS5-60-01-0151 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-01 07:41 | PS5-60-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0232 |  | EACOP-PS5-60-01-0152 |  | EACOP-PS5-60-01-0152 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-06 11:25 | PS5-60-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0233 |  | EACOP-PS5-60-01-0153 |  | EACOP-PS5-60-01-0153 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-06 11:40 | PS5-60-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0234 |  | EACOP-PS5-60-04-0154 |  | EACOP-PS5-60-04-0154 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-06 11:36 | PS5-60-04 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0235 |  | EACOP-PS5-60-04-0155 |  | EACOP-PS5-60-04-0155 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 11:36 | PS5-60-04 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0236 |  | EACOP-PS5-60-04-0156 |  | EACOP-PS5-60-04-0156 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 14:30 | PS5-60-04 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0237 |  | EACOP-PS5-60-07-0157 |  | EACOP-PS5-60-07-0157 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-06-19 11:33 | PS5-60-07 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0238 |  | EACOP-PS5-60-07-0158 |  | EACOP-PS5-60-07-0158 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-06-19 14:22 | PS5-60-07 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0239 |  | EACOP-PS5-60-07-0159 |  | EACOP-PS5-60-07-0159 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-06-19 14:13 | PS5-60-07 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0240 |  | EACOP-PS5-60-10-0160 |  | EACOP-PS5-60-10-0160 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-19 14:12 | PS5-60-10 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0241 |  | EACOP-PS5-60-10-0161 |  | EACOP-PS5-60-10-0161 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-23 09:16 | PS5-60-10 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0242 |  | EACOP-PS5-60-10-0162 |  | EACOP-PS5-60-10-0162 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-23 09:17 | PS5-60-10 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0243 |  | EACOP-PS5-60-13-0163 |  | EACOP-PS5-60-13-0163 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-06-24 05:51 | PS5-60-13 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0244 |  | EACOP-PS5-60-13-0164 |  | EACOP-PS5-60-13-0164 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-06-24 05:54 | PS5-60-13 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0245 |  | EACOP-PS5-60-13-0165 |  | EACOP-PS5-60-13-0165 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-06-24 05:55 | PS5-60-13 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0246 |  | EACOP-PS5-60-16-0166 |  | EACOP-PS5-60-16-0166 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-06-24 06:01 | PS5-60-16 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0247 |  | EACOP-PS5-60-16-0167 |  | EACOP-PS5-60-16-0167 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-07-03 07:32 | PS5-60-16 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0248 |  | EACOP-PS5-60-16-0168 |  | EACOP-PS5-60-16-0168 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-07-03 07:35 | PS5-60-16 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0249 |  | EACOP-PS5-60-19-0169 |  | EACOP-PS5-60-19-0169 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-07-03 07:12 | PS5-60-19 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone E
T-00223-0250 |  | EACOP-PS5-60-19-0170 |  | EACOP-PS5-60-19-0170 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-07-03 07:15 | PS5-60-19 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone E
T-00223-0251 |  | EACOP-PS5-60-19-0171 |  | EACOP-PS5-60-19-0171 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-07-03 07:20 | PS5-60-19 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone E
T-00223-0267 |  | EACOP-PS5-60-26-0183 |  | EACOP-PS5-60-26-0183 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-23 08:44 | PS5-60-26 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0268 |  | EACOP-PS5-60-26-0184 |  | EACOP-PS5-60-26-0184 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-01 13:43 | PS5-60-26 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0269 |  | EACOP-PS5-60-27-0185 |  | EACOP-PS5-60-27-0185 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-06-01 13:45 | PS5-60-27 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0270 |  | EACOP-PS5-60-27-0186 |  | EACOP-PS5-60-27-0186 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  |  |  | To be completed | PS5 - Milestone B
T-00223-0278 |  | EACOP-PS5-60-35-0194 |  | EACOP-PS5-60-35-0194 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  |  |  | To be completed | PS5 - Milestone B
T-00223-0279 |  | EACOP-PS5-60-35-0195 |  | EACOP-PS5-60-35-0195 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-05-05 11:42 | PS5-60-35 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0280 |  | EACOP-PS5-60-36-0196 |  | EACOP-PS5-60-36-0196 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  |  |  | To be completed | PS5 - Milestone B
T-00223-0281 |  | EACOP-PS5-60-36-0197 |  | EACOP-PS5-60-36-0197 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-05-25 17:54 | PS5-60-36 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0282 |  | EACOP-PS5-60-37-0198 |  | EACOP-PS5-60-37-0198 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 |  |  |  |  | To be completed | PS5 - Milestone D
T-00223-0283 |  | EACOP-PS5-60-37-0199 |  | EACOP-PS5-60-37-0199 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C | 2026-06-01 13:41 | PS5-60-37 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0284 |  | EACOP-PS5-60-38-0200 |  | EACOP-PS5-60-38-0200 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 |  |  |  |  | To be completed | PS5 - Milestone D
T-00223-0285 |  | EACOP-PS5-60-38-0201 |  | EACOP-PS5-60-38-0201 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D | 2026-05-29 04:39 | PS5-60-38 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0286 |  | EACOP-PS5-60-39-0202 |  | EACOP-PS5-60-39-0202 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  |  |  | To be completed | PS5 - Milestone D
T-00223-0287 |  | EACOP-PS5-60-39-0203 |  | EACOP-PS5-60-39-0203 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Submitted | PS5 - Milestone D
T-00223-0288 |  | EACOP-PS5-60-40-0204 |  | EACOP-PS5-60-40-0204 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F |  | PS5-60-40 |  |  |  |  | To be completed | PS5 - Milestone D
T-00223-0289 |  | EACOP-PS5-60-40-0205 |  | EACOP-PS5-60-40-0205 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F | 2026-05-29 04:38 | PS5-60-40 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0290 |  | EACOP-PS5-60-41-0206 |  | EACOP-PS5-60-41-0206 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  |  |  | To be completed | PS5 - Milestone E
T-00223-0291 |  | EACOP-PS5-60-41-0207 |  | EACOP-PS5-60-41-0207 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Submitted | PS5 - Milestone E
T-00223-0292 |  | EACOP-PS5-60-42-0208 |  | EACOP-PS5-60-42-0208 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  |  |  | To be completed | PS5 - Milestone B
T-00223-0293 |  | EACOP-PS5-60-42-0209 |  | EACOP-PS5-60-42-0209 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-05-29 08:59 | PS5-60-42 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0294 |  | EACOP-PS5-60-43-0210 |  | EACOP-PS5-60-43-0210 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  |  |  | To be completed | PS5 - Milestone B
T-00223-0295 |  | EACOP-PS5-60-43-0211 |  | EACOP-PS5-60-43-0211 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-05-29 09:01 | PS5-60-43 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0296 |  | EACOP-PS5-60-44-0212 |  | EACOP-PS5-60-44-0212 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C |  | PS5-60-44 |  |  |  |  | To be completed | PS5 - Milestone D
T-00223-0297 |  | EACOP-PS5-60-44-0213 |  | EACOP-PS5-60-44-0213 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | 2026-05-29 09:04 | PS5-60-44 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0298 |  | EACOP-PS5-60-45-0214 |  | EACOP-PS5-60-45-0214 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D |  | PS5-60-45 |  |  |  |  | To be completed | PS5 - Milestone D
T-00223-0299 |  | EACOP-PS5-60-45-0215 |  | EACOP-PS5-60-45-0215 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | 2026-05-29 09:06 | PS5-60-45 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0300 |  | EACOP-PS5-60-46-0216 |  | EACOP-PS5-60-46-0216 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E |  | PS5-60-46 |  |  |  |  | To be completed | PS5 - Milestone D
T-00223-0301 |  | EACOP-PS5-60-46-0217 |  | EACOP-PS5-60-46-0217 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | 2026-05-29 09:10 | PS5-60-46 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0302 |  | EACOP-PS5-60-47-0218 |  | EACOP-PS5-60-47-0218 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F |  | PS5-60-47 |  |  |  |  | To be completed | PS5 - Milestone D
T-00223-0303 |  | EACOP-PS5-60-47-0219 |  | EACOP-PS5-60-47-0219 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | 2026-05-29 09:12 | PS5-60-47 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0304 |  | EACOP-PS5-60-48-0220 |  | EACOP-PS5-60-48-0220 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G |  | PS5-60-48 |  |  |  |  | To be completed | PS5 - Milestone E
T-00223-0305 |  | EACOP-PS5-60-48-0221 |  | EACOP-PS5-60-48-0221 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | 2026-06-01 07:15 | PS5-60-48 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone E
T-00223-0306 |  | EACOP-PS5-60-49-0222 |  | EACOP-PS5-60-49-0222 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  |  |  | To be completed | PS5 - Milestone B
T-00223-0307 |  | EACOP-PS5-60-49-0223 |  | EACOP-PS5-60-49-0223 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2026-06-06 11:42 | PS5-60-49 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0308 |  | EACOP-PS5-60-50-0224 |  | EACOP-PS5-60-50-0224 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  |  |  | To be completed | PS5 - Milestone B
T-00223-0309 |  | EACOP-PS5-60-50-0225 |  | EACOP-PS5-60-50-0225 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2026-06-27 07:52 | PS5-60-50 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0310 |  | EACOP-PS5-60-51-0226 |  | EACOP-PS5-60-51-0226 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  |  |  | To be completed | PS5 - Milestone D
T-00223-0311 |  | EACOP-PS5-60-51-0227 |  | EACOP-PS5-60-51-0227 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | 2026-06-19 14:23 | PS5-60-51 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0312 |  | EACOP-PS5-60-52-0228 |  | EACOP-PS5-60-52-0228 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  |  |  | To be completed | PS5 - Milestone D
T-00223-0313 |  | EACOP-PS5-60-52-0229 |  | EACOP-PS5-60-52-0229 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | 2026-06-23 09:20 | PS5-60-52 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0314 |  | EACOP-PS5-60-53-0230 |  | EACOP-PS5-60-53-0230 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  |  |  | To be completed | PS5 - Milestone D
T-00223-0315 |  | EACOP-PS5-60-53-0231 |  | EACOP-PS5-60-53-0231 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Submitted | PS5 - Milestone D
T-00223-0316 |  | EACOP-PS5-60-54-0232 |  | EACOP-PS5-60-54-0232 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  |  |  | To be completed | PS5 - Milestone D
T-00223-0317 |  | EACOP-PS5-60-54-0233 |  | EACOP-PS5-60-54-0233 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | 2026-07-03 07:41 | PS5-60-54 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0318 |  | EACOP-PS5-60-55-0234 |  | EACOP-PS5-60-55-0234 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  |  |  | To be completed | PS5 - Milestone E
T-00223-0319 |  | EACOP-PS5-60-55-0235 |  | EACOP-PS5-60-55-0235 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Submitted | PS5 - Milestone E
T-00223-0320 |  | EACOP-PS5-60-56-0236 |  | EACOP-PS5-60-56-0236 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-04-26 08:14 | PS5-60-56 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0321 |  | EACOP-PS5-60-56-0237 |  | EACOP-PS5-60-56-0237 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-04-29 05:09 | PS5-60-56 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0322 |  | EACOP-PS5-60-58-0238 |  | EACOP-PS5-60-58-0238 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-04-26 12:29 | PS5-60-58 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0323 |  | EACOP-PS5-60-58-0239 |  | EACOP-PS5-60-58-0239 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-05-25 17:47 | PS5-60-58 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0324 |  | EACOP-PS5-60-60-0240 |  | EACOP-PS5-60-60-0240 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 2026-04-26 10:05 | PS5-60-60 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0325 |  | EACOP-PS5-60-60-0241 |  | EACOP-PS5-60-60-0241 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 2026-05-25 17:51 | PS5-60-60 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0326 |  | EACOP-PS5-60-62-0242 |  | EACOP-PS5-60-62-0242 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  | 50 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2026-04-27 10:11 | PS5-60-62 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0327 |  | EACOP-PS5-60-62-0243 |  | EACOP-PS5-60-62-0243 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2026-05-25 17:39 | PS5-60-62 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0328 |  | EACOP-PS5-60-64-0244 |  | EACOP-PS5-60-64-0244 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | 2026-04-26 08:08 | PS5-60-64 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0329 |  | EACOP-PS5-60-64-0245 |  | EACOP-PS5-60-64-0245 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | 2026-06-23 08:46 | PS5-60-64 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0330 |  | EACOP-PS5-60-66-0246 |  | EACOP-PS5-60-66-0246 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | 2026-06-01 08:36 | PS5-60-66 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0331 |  | EACOP-PS5-60-66-0247 |  | EACOP-PS5-60-66-0247 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | 2026-06-01 07:17 | PS5-60-66 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0332 |  | EACOP-PS5-60-68-0248 |  | EACOP-PS5-60-68-0248 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | 2026-04-28 07:19 | PS5-60-68 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone E
T-00223-0333 |  | EACOP-PS5-60-68-0249 |  | EACOP-PS5-60-68-0249 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | 2026-07-03 07:26 | PS5-60-68 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone E
T-00223-0334 |  | EACOP-PS5-60-70-0250 |  | EACOP-PS5-60-70-0250 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-06 11:30 | PS5-60-70 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0335 |  | EACOP-PS5-60-70-0251 |  | EACOP-PS5-60-70-0251 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-05 11:54 | PS5-60-70 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0336 |  | EACOP-PS5-60-70-0252 |  | EACOP-PS5-60-70-0252 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-06 11:31 | PS5-60-70 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0337 |  | EACOP-PS5-60-70-0253 |  | EACOP-PS5-60-70-0253 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-06 11:32 | PS5-60-70 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0338 |  | EACOP-PS5-60-70-0254 |  | EACOP-PS5-60-70-0254 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-06 11:26 | PS5-60-70 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0339 |  | EACOP-PS5-60-70-0255 |  | EACOP-PS5-60-70-0255 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-06 11:27 | PS5-60-70 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0340 |  | EACOP-PS5-60-71-0256 |  | EACOP-PS5-60-71-0256 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-19 11:37 | PS5-60-71 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0341 |  | EACOP-PS5-60-71-0257 |  | EACOP-PS5-60-71-0257 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-03 04:46 | PS5-60-71 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0342 |  | EACOP-PS5-60-71-0258 |  | EACOP-PS5-60-71-0258 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-19 11:29 | PS5-60-71 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0343 |  | EACOP-PS5-60-71-0259 |  | EACOP-PS5-60-71-0259 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-19 11:29 | PS5-60-71 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0344 |  | EACOP-PS5-60-71-0260 |  | EACOP-PS5-60-71-0260 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-19 11:30 | PS5-60-71 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0345 |  | EACOP-PS5-60-71-0261 |  | EACOP-PS5-60-71-0261 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-19 11:32 | PS5-60-71 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0346 |  | EACOP-PS5-60-72-0262 |  | EACOP-PS5-60-72-0262 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-25 08:37 | PS5-60-72 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0347 |  | EACOP-PS5-60-72-0263 |  | EACOP-PS5-60-72-0263 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-01 08:28 | PS5-60-72 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0348 |  | EACOP-PS5-60-72-0264 |  | EACOP-PS5-60-72-0264 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-19 14:08 | PS5-60-72 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0349 |  | EACOP-PS5-60-72-0265 |  | EACOP-PS5-60-72-0265 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-19 14:09 | PS5-60-72 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0350 |  | EACOP-PS5-60-72-0266 |  | EACOP-PS5-60-72-0266 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-19 14:10 | PS5-60-72 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0351 |  | EACOP-PS5-60-72-0267 |  | EACOP-PS5-60-72-0267 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-19 14:11 | PS5-60-72 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0352 |  | EACOP-PS5-60-73-0268 |  | EACOP-PS5-60-73-0268 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  | 50 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-20 06:56 | PS5-60-73 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0353 |  | EACOP-PS5-60-73-0269 |  | EACOP-PS5-60-73-0269 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-23 08:15 | PS5-60-73 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0354 |  | EACOP-PS5-60-73-0270 |  | EACOP-PS5-60-73-0270 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-20 04:51 | PS5-60-73 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0355 |  | EACOP-PS5-60-73-0271 |  | EACOP-PS5-60-73-0271 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-20 04:50 | PS5-60-73 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0356 |  | EACOP-PS5-60-73-0272 |  | EACOP-PS5-60-73-0272 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-20 04:49 | PS5-60-73 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0357 |  | EACOP-PS5-60-73-0273 |  | EACOP-PS5-60-73-0273 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-20 04:49 | PS5-60-73 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0358 |  | EACOP-PS5-60-74-0274 |  | EACOP-PS5-60-74-0274 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Submitted | PS5 - Milestone D
T-00223-0359 |  | EACOP-PS5-60-74-0275 |  | EACOP-PS5-60-74-0275 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-06-01 08:31 | PS5-60-74 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0360 |  | EACOP-PS5-60-74-0276 |  | EACOP-PS5-60-74-0276 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Submitted | PS5 - Milestone D
T-00223-0361 |  | EACOP-PS5-60-74-0277 |  | EACOP-PS5-60-74-0277 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Submitted | PS5 - Milestone D
T-00223-0362 |  | EACOP-PS5-60-74-0278 |  | EACOP-PS5-60-74-0278 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Submitted | PS5 - Milestone D
T-00223-0363 |  | EACOP-PS5-60-74-0279 |  | EACOP-PS5-60-74-0279 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Submitted | PS5 - Milestone D
T-00223-0364 |  | EACOP-PS5-60-75-0280 |  | EACOP-PS5-60-75-0280 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Submitted | PS5 - Milestone D
T-00223-0365 |  | EACOP-PS5-60-75-0281 |  | EACOP-PS5-60-75-0281 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-06-01 08:25 | PS5-60-75 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0366 |  | EACOP-PS5-60-75-0282 |  | EACOP-PS5-60-75-0282 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Submitted | PS5 - Milestone D
T-00223-0367 |  | EACOP-PS5-60-75-0283 |  | EACOP-PS5-60-75-0283 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Submitted | PS5 - Milestone D
T-00223-0368 |  | EACOP-PS5-60-75-0284 |  | EACOP-PS5-60-75-0284 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Submitted | PS5 - Milestone D
T-00223-0369 |  | EACOP-PS5-60-75-0285 |  | EACOP-PS5-60-75-0285 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Submitted | PS5 - Milestone D
T-00223-0370 |  | EACOP-PS5-60-76-0286 |  | EACOP-PS5-60-76-0286 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  |  |  | To be completed | PS5 - Milestone E
T-00223-0371 |  | EACOP-PS5-60-76-0287 |  | EACOP-PS5-60-76-0287 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-06-01 07:43 | PS5-60-76 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone E
T-00223-0372 |  | EACOP-PS5-60-76-0288 |  | EACOP-PS5-60-76-0288 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  |  |  | To be completed | PS5 - Milestone E
T-00223-0373 |  | EACOP-PS5-60-76-0289 |  | EACOP-PS5-60-76-0289 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  |  |  | To be completed | PS5 - Milestone E
T-00223-0374 |  | EACOP-PS5-60-76-0290 |  | EACOP-PS5-60-76-0290 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  |  |  | To be completed | PS5 - Milestone E
T-00223-0375 |  | EACOP-PS5-60-76-0291 |  | EACOP-PS5-60-76-0291 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  |  |  | To be completed | PS5 - Milestone E
T-00223-0391 |  | EACOP-PS5-71-06-0307 |  | EACOP-PS5-71-06-0307 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-04-27 08:28 | PS5-71-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone H
T-00223-0392 |  | EACOP-PS5-71-06-0308 |  | EACOP-PS5-71-06-0308 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-05-29 08:52 | PS5-71-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone H
T-00223-0393 |  | EACOP-PS5-71-06-0378 |  | EACOP-PS5-71-06-0378 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-04-04 12:14 | PS5-71-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone H
T-00223-0394 |  | EACOP-PS5-71-08-0309 |  | EACOP-PS5-71-08-0309 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-04-27 08:26 | PS5-71-08 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone H
T-00223-0395 |  | EACOP-PS5-71-08-0310 |  | EACOP-PS5-71-08-0310 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  |  |  | To be completed | PS5 - Milestone H
T-00223-0418 |  | EACOP-PS5-71-22-0333 |  | EACOP-PS5-71-22-0333 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Submitted | PS5 - Milestone B
T-00223-0419 |  | EACOP-PS5-71-22-0334 |  | EACOP-PS5-71-22-0334 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-04-28 07:18 | PS5-71-22 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0420 |  | EACOP-PS5-71-22-0335 |  | EACOP-PS5-71-22-0335 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-05-05 12:29 | PS5-71-22 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0421 |  | EACOP-PS5-71-22-0336 |  | EACOP-PS5-71-22-0336 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-05-25 17:46 | PS5-71-22 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0422 |  | EACOP-PS5-71-22-0337 |  | EACOP-PS5-71-22-0337 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-06-03 04:48 | PS5-71-22 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0512 |  | EACOP-PS5-60-42-0046 |  | EACOP-PS5-60-42-0046 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-05-25 18:11 | PS5-60-42 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0513 |  | EACOP-PS5-60-43-0091 |  | EACOP-PS5-60-43-0091 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-05-25 18:13 | PS5-60-43 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B
T-00223-0514 |  | EACOP-PS5-60-44-0421 |  | EACOP-PS5-60-44-0421 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | 2026-05-26 19:45 | PS5-60-44 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0515 |  | EACOP-PS5-60-45-0422 |  | EACOP-PS5-60-45-0422 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | 2026-05-26 19:41 | PS5-60-45 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0516 |  | EACOP-PS5-60-46-0423 |  | EACOP-PS5-60-46-0423 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | 2026-05-26 19:43 | PS5-60-46 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0517 |  | EACOP-PS5-60-47-0424 |  | EACOP-PS5-60-47-0424 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | 2026-05-26 19:47 | PS5-60-47 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone D
T-00223-0518 |  | EACOP-PS5-60-48-0065 |  | EACOP-PS5-60-48-0065 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | 2026-05-25 18:12 | PS5-60-48 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone E
T-00224-0120 | PS5-60-01_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B
T-00224-0121 | PS5-60-04_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B
T-00224-0122 | PS5-60-07_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0123 | PS5-60-10_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0124 | PS5-60-13_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0125 | PS5-60-16_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0126 | PS5-60-19_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone E
T-00224-0130 | PS5-60-26_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B
T-00224-0131 | PS5-60-27_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B
T-00224-0139 | PS5-60-35_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B
T-00224-0140 | PS5-60-36_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B
T-00224-0141 | PS5-60-37_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0142 | PS5-60-38_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D |  | PS5-60-38 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0143 | PS5-60-39_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0144 | PS5-60-40_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F |  | PS5-60-40 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0145 | PS5-60-41_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone E
T-00224-0146 | PS5-60-42_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B
T-00224-0147 | PS5-60-43_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B
T-00224-0148 | PS5-60-44_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C |  | PS5-60-44 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0149 | PS5-60-45_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D |  | PS5-60-45 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0150 | PS5-60-46_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E |  | PS5-60-46 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0151 | PS5-60-47_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F |  | PS5-60-47 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0152 | PS5-60-48_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G |  | PS5-60-48 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone E
T-00224-0153 | PS5-60-49_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B
T-00224-0154 | PS5-60-50_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B
T-00224-0155 | PS5-60-51_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0156 | PS5-60-52_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0157 | PS5-60-53_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0158 | PS5-60-54_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0159 | PS5-60-55_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone E
T-00224-0160 | PS5-60-56_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B
T-00224-0161 | PS5-60-58_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B
T-00224-0162 | PS5-60-60_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0163 | PS5-60-62_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0164 | PS5-60-64_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0165 | PS5-60-66_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0166 | PS5-60-68_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone E
T-00224-0167 | PS5-60-70_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B
T-00224-0168 | PS5-60-71_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B
T-00224-0169 | PS5-60-72_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0170 | PS5-60-73_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0171 | PS5-60-74_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0172 | PS5-60-75_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone D
T-00224-0173 | PS5-60-76_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone E
T-00224-0178 | PS5-71-06_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone H
T-00224-0179 | PS5-71-08_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone H
T-00224-0189 | PS5-71-22_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B
T-00227-0133 | PS5-61-IU-0001A |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 24 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Power Transformer | E | To be completed | PS5 - Milestone B
T-00227-0134 | PS5-61-IU-0001B |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 24 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Power Transformer | E | To be completed | PS5 - Milestone B
T-00227-0135 | PS5-61-IU-0001C |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 24 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Power Transformer | E | To be completed | PS5 - Milestone D
T-00227-0136 | PS5-61-IU-0001D |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 24 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Power Transformer | E | To be completed | PS5 - Milestone D
T-00227-0137 | PS5-61-IU-0001E |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 24 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Power Transformer | E | To be completed | PS5 - Milestone D
T-00227-0138 | PS5-61-IU-0001F |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 24 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Power Transformer | E | To be completed | PS5 - Milestone D
T-00227-0139 | PS5-61-IU-0001G |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 24 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Power Transformer | E | To be completed | PS5 - Milestone E
T-00232-0970 | PS5-60-IJ-0001A-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-60-IJ-0001A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-03-14 04:26 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00232-0971 | PS5-60-IJ-0001B-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-60-IJ-0001B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-03-14 04:27 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00232-0972 | PS5-60-IJ-0001C-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100C TO PS5-60-IJ-0001C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-03-14 04:28 | PS5-60-07 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-0973 | PS5-60-IJ-0001D-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100D TO PS5-60-IJ-0001D | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-03-14 04:28 | PS5-60-10 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-0974 | PS5-60-IJ-0001E-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100E TO PS5-60-IJ-0001E | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-03-14 04:29 | PS5-60-13 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-0975 | PS5-60-IJ-0001F-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100F TO PS5-60-IJ-0001F | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-03-14 04:29 | PS5-60-16 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-0976 | PS5-60-IJ-0001G-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100G TO PS5-60-IJ-0001G | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-03-14 04:31 | PS5-60-19 |  |  | HV Power Cable | E | Closed | PS5 - Milestone E
T-00232-1013 | PS5-61-IJ-0001-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-13 05:39 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00232-1014 | PS5-61-IJ-0001-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-13 05:42 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00232-1015 | PS5-61-IJ-0001-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-13 05:42 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00232-1016 | PS5-61-IJ-0001-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-13 05:43 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00232-1017 | PS5-61-IJ-0001-CH05 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-13 05:44 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00232-1018 | PS5-61-IJ-0001-CH06 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-13 05:44 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00232-1019 | PS5-61-IJ-0001-CH07 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001C TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-13 05:45 | PS5-60-07 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1020 | PS5-61-IJ-0001-CH08 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001C TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-13 05:45 | PS5-60-07 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1021 | PS5-61-IJ-0001-CH09 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001C TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-13 05:46 | PS5-60-07 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1022 | PS5-61-IJ-0001-CH10 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001D TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-13 05:46 | PS5-60-10 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1023 | PS5-61-IJ-0001-CH11 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001D TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-13 05:47 | PS5-60-10 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1024 | PS5-61-IJ-0001-CH12 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001D TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-13 05:47 | PS5-60-10 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1025 | PS5-61-IJ-0001-CH13 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001E TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-04-13 05:48 | PS5-60-13 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1026 | PS5-61-IJ-0001-CH14 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001E TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-04-13 05:49 | PS5-60-13 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1027 | PS5-61-IJ-0001-CH15 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001E TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-04-13 05:50 | PS5-60-13 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1028 | PS5-61-IJ-0001-CH16 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001F TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-04-13 05:50 | PS5-60-16 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1029 | PS5-61-IJ-0001-CH17 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001F TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-04-13 05:51 | PS5-60-16 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1030 | PS5-61-IJ-0001-CH18 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001F TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-04-13 05:51 | PS5-60-16 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1031 | PS5-61-IJ-0001-CH19 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001G TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-04-13 05:53 | PS5-60-19 |  |  | HV Power Cable | E | Closed | PS5 - Milestone E
T-00232-1032 | PS5-61-IJ-0001-CH20 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001G TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-04-13 05:53 | PS5-60-19 |  |  | HV Power Cable | E | Closed | PS5 - Milestone E
T-00232-1033 | PS5-61-IJ-0001-CH21 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001G TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-04-13 05:54 | PS5-60-19 |  |  | HV Power Cable | E | Closed | PS5 - Milestone E
T-00232-1046 | PS5-61-IU-0001A-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-17 05:50 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00232-1047 | PS5-61-IU-0001A-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-17 05:50 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00232-1048 | PS5-61-IU-0001A-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-17 05:51 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00232-1049 | PS5-61-IU-0001B-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-17 05:51 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00232-1050 | PS5-61-IU-0001B-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-17 05:52 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00232-1051 | PS5-61-IU-0001B-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-17 05:52 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B
T-00232-1052 | PS5-61-IU-0001C-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100C TO PS5-61-IU-0001C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-17 05:53 | PS5-60-07 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1053 | PS5-61-IU-0001C-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100C TO PS5-61-IU-0001C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-17 05:53 | PS5-60-07 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1054 | PS5-61-IU-0001C-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100C TO PS5-61-IU-0001C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-04-17 05:54 | PS5-60-07 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1055 | PS5-61-IU-0001D-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100D TO PS5-61-IU-0001D | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-17 05:55 | PS5-60-10 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1056 | PS5-61-IU-0001D-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100D TO PS5-61-IU-0001D | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-17 05:55 | PS5-60-10 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1057 | PS5-61-IU-0001D-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100D TO PS5-61-IU-0001D | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-04-17 05:56 | PS5-60-10 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1058 | PS5-61-IU-0001E-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100E TO PS5-61-IU-0001E | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-04-17 05:57 | PS5-60-13 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1059 | PS5-61-IU-0001E-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100E TO PS5-61-IU-0001E | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-04-17 05:57 | PS5-60-13 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1060 | PS5-61-IU-0001E-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100E TO PS5-61-IU-0001E | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-04-17 05:57 | PS5-60-13 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1061 | PS5-61-IU-0001F-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100F TO PS5-61-IU-0001F | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-04-17 05:58 | PS5-60-16 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1062 | PS5-61-IU-0001F-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100F TO PS5-61-IU-0001F | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-04-17 05:58 | PS5-60-16 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1063 | PS5-61-IU-0001F-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100F TO PS5-61-IU-0001F | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-04-17 05:59 | PS5-60-16 |  |  | HV Power Cable | E | Closed | PS5 - Milestone D
T-00232-1064 | PS5-61-IU-0001G-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100G TO PS5-61-IU-0001G | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-04-17 05:59 | PS5-60-19 |  |  | HV Power Cable | E | Closed | PS5 - Milestone E
T-00232-1065 | PS5-61-IU-0001G-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100G TO PS5-61-IU-0001G | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-04-17 06:00 | PS5-60-19 |  |  | HV Power Cable | E | Closed | PS5 - Milestone E
T-00232-1066 | PS5-61-IU-0001G-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100G TO PS5-61-IU-0001G | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-04-17 06:00 | PS5-60-19 |  |  | HV Power Cable | E | Closed | PS5 - Milestone E
T-00233-10536 | PS5-60-IN-0002A-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00233-10537 | PS5-60-IN-0002B-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00233-10538 | PS5-60-IN-0002C-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-10539 | PS5-60-IN-0002D-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-10540 | PS5-60-IN-0002E-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-10541 | PS5-60-IN-0002F-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-10542 | PS5-60-IN-0002G-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-10593 | PS5-60-IH-0001A-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00233-10594 | PS5-60-IH-0001B-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00233-10595 | PS5-60-IH-0001C-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-10596 | PS5-60-IH-0001D-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-10597 | PS5-60-IH-0001E-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-10598 | PS5-60-IH-0001F-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-10599 | PS5-60-IH-0001G-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-10600 | PS5-60-IH-0002-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:17 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-10601 | PS5-60-IH-0002-CG02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:17 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-10890 | PS5-60-BE-0007A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-06-27 08:59 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-10891 | PS5-60-BE-0007A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-06-27 09:04 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-10892 | PS5-60-BE-0007B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-06-27 09:24 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-10893 | PS5-60-BE-0007B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-06-27 09:25 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-10894 | PS5-60-BE-0007C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0007C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-10895 | PS5-60-BE-0007C-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0007C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-10896 | PS5-60-BE-0007D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0007D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2026-06-11 05:19 | PS5-60-62 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-10897 | PS5-60-BE-0007D-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0007D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2026-06-11 05:19 | PS5-60-62 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-10898 | PS5-60-BE-0007E-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BE-0007E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-10899 | PS5-60-BE-0007E-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BE-0007E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-10900 | PS5-60-BE-0007F-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BE-0007F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-10901 | PS5-60-BE-0007F-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BE-0007F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-10902 | PS5-60-BE-0007G-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BE-0007G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | Started (not Completed) | PS5 - Milestone E
T-00233-10903 | PS5-60-BE-0007G-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BE-0007G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-10904 | PS5-60-ISO-62800A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-ISO-62800A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00233-10905 | PS5-60-ISO-62800C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-ISO-62800C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-10906 | PS5-60-ISO-62800E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-ISO-62800E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-10907 | PS5-60-ISO-62800G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-ISO-62800G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-4725 | PS5-03-SEA-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-03-SEA-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-4978 | PS5-60-BE-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-06-27 09:27 | PS5-60-27 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-4979 | PS5-60-BE-0001-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-06-27 09:28 | PS5-60-27 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-4981 | PS5-60-BE-0001-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-06-27 08:44 | PS5-60-27 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-4982 | PS5-60-BE-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-27 08:53 | PS5-60-26 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-4983 | PS5-60-BE-0002-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-27 08:55 | PS5-60-26 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-4984 | PS5-60-BE-0002-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-27 09:29 | PS5-60-26 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-4986 | PS5-60-BE-0002-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-27 08:52 | PS5-60-26 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-4987 | PS5-60-BE-0003A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 04:41 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-4988 | PS5-60-BE-0003B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 04:42 | PS5-60-04 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-4989 | PS5-60-BE-0003C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-4990 | PS5-60-BE-0003D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-4991 | PS5-60-BE-0003E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-4992 | PS5-60-BE-0003F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-4993 | PS5-60-BE-0003G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-4994 | PS5-60-BE-0004A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0004A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00233-4995 | PS5-60-BE-0004B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0004B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00233-4996 | PS5-60-BE-0004C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0004C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-4997 | PS5-60-BE-0004D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0004D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-4998 | PS5-60-BE-0004E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0004E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-4999 | PS5-60-BE-0004F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0004F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5000 | PS5-60-BE-0004G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0004G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5001 | PS5-60-BE-0005A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0005A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-11 05:20 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5002 | PS5-60-BE-0005B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0005B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B
T-00233-5003 | PS5-60-BE-0005C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0005C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5004 | PS5-60-BE-0005D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0005D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-19 05:12 | PS5-60-10 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5005 | PS5-60-BE-0005E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0005E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5006 | PS5-60-BE-0005F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0005F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5007 | PS5-60-BE-0005G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0005G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5008 | PS5-60-BE-0011A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-05 07:47 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5009 | PS5-60-BE-0011A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-05 07:49 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5010 | PS5-60-BE-0011A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B
T-00233-5011 | PS5-60-BE-0011A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-06 04:42 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5012 | PS5-60-BE-0011A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B
T-00233-5013 | PS5-60-BE-0011A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B
T-00233-5014 | PS5-60-BE-0011B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B
T-00233-5015 | PS5-60-BE-0011B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B
T-00233-5016 | PS5-60-BE-0011B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B
T-00233-5017 | PS5-60-BE-0011B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B
T-00233-5018 | PS5-60-BE-0011B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B
T-00233-5019 | PS5-60-BE-0011B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B
T-00233-5020 | PS5-60-BE-0012A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B
T-00233-5021 | PS5-60-BE-0012A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B
T-00233-5022 | PS5-60-BE-0012A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B
T-00233-5023 | PS5-60-BE-0012A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B
T-00233-5024 | PS5-60-BE-0012A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B
T-00233-5025 | PS5-60-BE-0012A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B
T-00233-5026 | PS5-60-BE-0012B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B
T-00233-5027 | PS5-60-BE-0012B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B
T-00233-5028 | PS5-60-BE-0012B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B
T-00233-5029 | PS5-60-BE-0012B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B
T-00233-5030 | PS5-60-BE-0012B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B
T-00233-5031 | PS5-60-BE-0012B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 04:43 | PS5-60-04 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5032 | PS5-60-BE-0013A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5033 | PS5-60-BE-0013A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5034 | PS5-60-BE-0013A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5035 | PS5-60-BE-0013A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5036 | PS5-60-BE-0013A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5037 | PS5-60-BE-0013A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5038 | PS5-60-BE-0013B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5039 | PS5-60-BE-0013B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5040 | PS5-60-BE-0013B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5041 | PS5-60-BE-0013B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5042 | PS5-60-BE-0013B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5043 | PS5-60-BE-0013B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0013B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5044 | PS5-60-BE-0014A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5045 | PS5-60-BE-0014A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5046 | PS5-60-BE-0014A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5047 | PS5-60-BE-0014A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5048 | PS5-60-BE-0014A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5049 | PS5-60-BE-0014A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5050 | PS5-60-BE-0014B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5051 | PS5-60-BE-0014B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5052 | PS5-60-BE-0014B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5053 | PS5-60-BE-0014B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5054 | PS5-60-BE-0014B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5055 | PS5-60-BE-0014B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0014B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5056 | PS5-60-BE-0015A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5057 | PS5-60-BE-0015A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5058 | PS5-60-BE-0015A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5059 | PS5-60-BE-0015A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5060 | PS5-60-BE-0015A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5061 | PS5-60-BE-0015A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5062 | PS5-60-BE-0015B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5063 | PS5-60-BE-0015B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5064 | PS5-60-BE-0015B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5065 | PS5-60-BE-0015B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5066 | PS5-60-BE-0015B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5067 | PS5-60-BE-0015B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5068 | PS5-60-BE-0016A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5069 | PS5-60-BE-0016A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5070 | PS5-60-BE-0016A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5071 | PS5-60-BE-0016A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5072 | PS5-60-BE-0016A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5073 | PS5-60-BE-0016A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5074 | PS5-60-BE-0016B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5075 | PS5-60-BE-0016B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5076 | PS5-60-BE-0016B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5077 | PS5-60-BE-0016B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5078 | PS5-60-BE-0016B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5079 | PS5-60-BE-0016B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0016B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5080 | PS5-60-BE-0017A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5081 | PS5-60-BE-0017A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5082 | PS5-60-BE-0017A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5083 | PS5-60-BE-0017A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5084 | PS5-60-BE-0017A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5085 | PS5-60-BE-0017A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5086 | PS5-60-BE-0017B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5087 | PS5-60-BE-0017B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5088 | PS5-60-BE-0017B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5089 | PS5-60-BE-0017B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5090 | PS5-60-BE-0017B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5091 | PS5-60-BE-0017B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0017B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5092 | PS5-60-BE-0021A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0021A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-06 04:42 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5093 | PS5-60-BE-0021B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0021B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 08:29 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5094 | PS5-60-BE-0024A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0024A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-06-11 10:41 | PS5-60-35 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5095 | PS5-60-BE-0024A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0024A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-06-11 10:42 | PS5-60-35 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5096 | PS5-60-BE-0024B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0024B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-06-11 10:43 | PS5-60-36 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5097 | PS5-60-BE-0024B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0024B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-06-11 10:43 | PS5-60-36 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5098 | PS5-60-BE-0024C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0024C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5099 | PS5-60-BE-0024C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0024C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5100 | PS5-60-BE-0024D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0024D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D | 2026-06-11 10:44 | PS5-60-38 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5101 | PS5-60-BE-0024D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0024D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D | 2026-06-11 10:45 | PS5-60-38 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5102 | PS5-60-BE-0024E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0024E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5103 | PS5-60-BE-0024E-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0024E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5104 | PS5-60-BE-0024F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0024F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F |  | PS5-60-40 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5105 | PS5-60-BE-0024F-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0024F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F |  | PS5-60-40 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5106 | PS5-60-BE-0024G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0024G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5107 | PS5-60-BE-0024G-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0024G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5108 | PS5-60-BE-0025A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0025A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-06-19 04:43 | PS5-60-35 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5109 | PS5-60-BE-0025B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0025B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-06-19 04:44 | PS5-60-36 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5110 | PS5-60-BE-0025C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0025C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C |  | PS5-60-37 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5111 | PS5-60-BE-0025D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0025D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D | 2026-06-19 08:35 | PS5-60-38 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5112 | PS5-60-BE-0025E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0025E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E |  | PS5-60-39 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5113 | PS5-60-BE-0025F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0025F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F |  | PS5-60-40 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5114 | PS5-60-BE-0025G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0025G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G |  | PS5-60-41 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5115 | PS5-60-BE-0026A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0026A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-19 04:45 | PS5-60-70 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5116 | PS5-60-BE-0026A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0026A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-19 04:45 | PS5-60-70 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5117 | PS5-60-BE-0026B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0026B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-19 04:45 | PS5-60-71 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5118 | PS5-60-BE-0026B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0026B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-19 04:46 | PS5-60-71 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5119 | PS5-60-BE-0026C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0026C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5120 | PS5-60-BE-0026C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BE-0026C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2026-06-19 04:46 | PS5-60-72 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5121 | PS5-60-BE-0026D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0026D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-11 10:45 | PS5-60-73 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5122 | PS5-60-BE-0026D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BE-0026D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2026-06-11 10:46 | PS5-60-73 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5123 | PS5-60-BE-0026E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0026E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5124 | PS5-60-BE-0026E-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BE-0026E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2026-06-11 10:47 | PS5-60-74 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5125 | PS5-60-BE-0026F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0026F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5126 | PS5-60-BE-0026F-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BE-0026F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2026-06-11 10:47 | PS5-60-75 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5127 | PS5-60-BE-0026G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0026G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5128 | PS5-60-BE-0026G-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BE-0026G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2026-06-19 04:47 | PS5-60-76 |  |  | LV Power Cable | E | Closed | PS5 - Milestone E
T-00233-5129 | PS5-60-BI-0005A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0005A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-05 07:51 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5130 | PS5-60-BI-0005B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0005B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-05 07:52 | PS5-60-04 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5131 | PS5-60-BI-0005C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0005C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-06-05 07:52 | PS5-60-07 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5132 | PS5-60-BI-0005D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0005D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-06 04:43 | PS5-60-10 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5133 | PS5-60-BI-0005E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0005E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-06-05 07:54 | PS5-60-13 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5134 | PS5-60-BI-0005F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0005F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-06-06 04:44 | PS5-60-16 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5135 | PS5-60-BI-0005G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0005G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-06-05 07:56 | PS5-60-19 |  |  | LV Power Cable | E | Closed | PS5 - Milestone E
T-00233-5136 | PS5-60-BI-0015A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00233-5137 | PS5-60-BI-0015A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 04:48 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5138 | PS5-60-BI-0015A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 04:48 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5139 | PS5-60-BI-0015B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00233-5140 | PS5-60-BI-0015B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 04:48 | PS5-60-04 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5141 | PS5-60-BI-0015B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 04:49 | PS5-60-04 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5142 | PS5-60-BI-0015C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0015C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5143 | PS5-60-BI-0015C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0015C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5144 | PS5-60-BI-0015C-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0015C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5145 | PS5-60-BI-0015D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0015D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5146 | PS5-60-BI-0015D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0015D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-19 04:50 | PS5-60-10 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5147 | PS5-60-BI-0015D-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0015D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-19 04:51 | PS5-60-10 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5148 | PS5-60-BI-0015E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0015E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5149 | PS5-60-BI-0015E-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0015E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5150 | PS5-60-BI-0015E-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0015E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5151 | PS5-60-BI-0015F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0015F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5152 | PS5-60-BI-0015F-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0015F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5153 | PS5-60-BI-0015F-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0015F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5154 | PS5-60-BI-0015G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0015G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5155 | PS5-60-BI-0015G-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0015G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5156 | PS5-60-BI-0015G-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0015G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5157 | PS5-60-DD-62800A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-DD-62800A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00233-5159 | PS5-60-DD-62800C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-DD-62800C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5161 | PS5-60-DD-62800E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-DD-62800E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5163 | PS5-60-DD-62800G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-DD-62800G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5166 | PS5-60-IE-0002A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:28 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5167 | PS5-60-IE-0002A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:31 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5168 | PS5-60-IE-0002A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:31 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5169 | PS5-60-IE-0002B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-06 04:44 | PS5-60-04 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5170 | PS5-60-IE-0002B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-06 04:45 | PS5-60-04 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5171 | PS5-60-IE-0002B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:31 | PS5-60-04 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5172 | PS5-60-IE-0002C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5173 | PS5-60-IE-0002C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5174 | PS5-60-IE-0002C-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5175 | PS5-60-IE-0002D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-19 04:23 | PS5-60-10 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5176 | PS5-60-IE-0002D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-19 04:23 | PS5-60-10 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5177 | PS5-60-IE-0002D-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5178 | PS5-60-IE-0002E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5179 | PS5-60-IE-0002E-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5180 | PS5-60-IE-0002E-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5181 | PS5-60-IE-0002F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5182 | PS5-60-IE-0002F-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5183 | PS5-60-IE-0002F-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5184 | PS5-60-IE-0002G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5185 | PS5-60-IE-0002G-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5186 | PS5-60-IE-0002G-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5187 | PS5-60-IE-0003A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) | 2026-06-19 04:25 | PS5-60-02 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5188 | PS5-60-IE-0003A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) | 2026-06-19 04:26 | PS5-60-02 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5189 | PS5-60-IE-0003B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) | 2026-06-19 04:26 | PS5-60-05 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5190 | PS5-60-IE-0003B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) | 2026-06-19 04:27 | PS5-60-05 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5191 | PS5-60-IE-0003C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5192 | PS5-60-IE-0003C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5193 | PS5-60-IE-0003D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5194 | PS5-60-IE-0003D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) | 2026-06-19 04:27 | PS5-60-11 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5195 | PS5-60-IE-0003E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5196 | PS5-60-IE-0003E-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5197 | PS5-60-IE-0003F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5198 | PS5-60-IE-0003F-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5199 | PS5-60-IE-0003G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5200 | PS5-60-IE-0003G-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5201 | PS5-60-IE-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:28 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5202 | PS5-60-IE-0004-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:28 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5204 | PS5-60-IH-0001A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-19 08:23 | PS5-60-03 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5205 | PS5-60-IH-0001A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-19 08:24 | PS5-60-03 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5206 | PS5-60-IH-0001A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-19 08:25 | PS5-60-03 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5207 | PS5-60-IH-0001A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-19 08:26 | PS5-60-03 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5208 | PS5-60-IH-0001A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-19 08:31 | PS5-60-03 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5209 | PS5-60-IH-0001A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-19 04:28 | PS5-60-03 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5211 | PS5-60-IH-0001B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-19 08:28 | PS5-60-06 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5212 | PS5-60-IH-0001B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-19 08:28 | PS5-60-06 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5213 | PS5-60-IH-0001B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-19 08:28 | PS5-60-06 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5214 | PS5-60-IH-0001B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-19 08:29 | PS5-60-06 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5215 | PS5-60-IH-0001B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-19 04:29 | PS5-60-06 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5216 | PS5-60-IH-0001B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-19 04:32 | PS5-60-06 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5218 | PS5-60-IH-0001C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5219 | PS5-60-IH-0001C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5220 | PS5-60-IH-0001C-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5221 | PS5-60-IH-0001C-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5222 | PS5-60-IH-0001C-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5223 | PS5-60-IH-0001C-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5225 | PS5-60-IH-0001D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5226 | PS5-60-IH-0001D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5227 | PS5-60-IH-0001D-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5228 | PS5-60-IH-0001D-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5229 | PS5-60-IH-0001D-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | 2026-06-19 04:33 | PS5-60-12 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5230 | PS5-60-IH-0001D-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5232 | PS5-60-IH-0001E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5233 | PS5-60-IH-0001E-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5234 | PS5-60-IH-0001E-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5235 | PS5-60-IH-0001E-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5236 | PS5-60-IH-0001E-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5237 | PS5-60-IH-0001E-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5239 | PS5-60-IH-0001F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5240 | PS5-60-IH-0001F-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5241 | PS5-60-IH-0001F-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5242 | PS5-60-IH-0001F-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5243 | PS5-60-IH-0001F-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5244 | PS5-60-IH-0001F-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5246 | PS5-60-IH-0001G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5247 | PS5-60-IH-0001G-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5248 | PS5-60-IH-0001G-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5249 | PS5-60-IH-0001G-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5250 | PS5-60-IH-0001G-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5251 | PS5-60-IH-0001G-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5254 | PS5-60-IH-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:33 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5255 | PS5-60-IH-0002-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:33 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5256 | PS5-60-IH-0002-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:18 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5257 | PS5-60-IH-0002-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:20 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5258 | PS5-60-IH-0002-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:20 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5259 | PS5-60-IH-0002-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:20 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5260 | PS5-60-IH-0002-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:21 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5261 | PS5-60-IH-0002-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:21 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5262 | PS5-60-IH-0002-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:21 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5263 | PS5-60-IH-0002-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:20 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5264 | PS5-60-IN-0001A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2026-06-19 04:51 | PS5-60-49 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5265 | PS5-60-IN-0001B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2026-06-19 04:51 | PS5-60-50 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5266 | PS5-60-IN-0001C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5267 | PS5-60-IN-0001D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | 2026-06-19 04:50 | PS5-60-52 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5268 | PS5-60-IN-0001E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-IN-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5269 | PS5-60-IN-0001F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-IN-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5270 | PS5-60-IN-0001G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-IN-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5271 | PS5-60-IN-0002A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | 2026-06-19 08:35 | PS5-60-57 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5272 | PS5-60-IN-0002A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | 2026-06-19 08:31 | PS5-60-57 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5273 | PS5-60-IN-0002A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | 2026-06-19 08:31 | PS5-60-57 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5274 | PS5-60-IN-0002B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | 2026-06-19 08:35 | PS5-60-59 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5275 | PS5-60-IN-0002B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | 2026-06-19 08:31 | PS5-60-59 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5276 | PS5-60-IN-0002B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | 2026-06-19 08:33 | PS5-60-59 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5277 | PS5-60-IN-0002C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5278 | PS5-60-IN-0002C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5279 | PS5-60-IN-0002C-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5280 | PS5-60-IN-0002D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | 2026-06-19 04:53 | PS5-60-63 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5281 | PS5-60-IN-0002D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | 2026-06-19 04:32 | PS5-60-63 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5282 | PS5-60-IN-0002D-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | 2026-06-19 04:32 | PS5-60-63 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5283 | PS5-60-IN-0002E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5284 | PS5-60-IN-0002E-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5285 | PS5-60-IN-0002E-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5286 | PS5-60-IN-0002F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5287 | PS5-60-IN-0002F-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5288 | PS5-60-IN-0002F-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5289 | PS5-60-IN-0002G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5290 | PS5-60-IN-0002G-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5291 | PS5-60-IN-0002G-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5292 | PS5-60-IWK-0001A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00233-5293 | PS5-60-IWK-0001A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00233-5294 | PS5-60-IWK-0001B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:32 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5295 | PS5-60-IWK-0001B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:32 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5296 | PS5-60-IWK-0001C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:34 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5297 | PS5-60-IWK-0001C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:34 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5298 | PS5-60-LA-0002A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 04:34 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5299 | PS5-60-LA-0002A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 04:34 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5300 | PS5-60-LA-0002B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5301 | PS5-60-LA-0002B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5302 | PS5-60-LA-0002C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5303 | PS5-60-LA-0002C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5304 | PS5-60-LA-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 08:33 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5305 | PS5-60-LA-0003-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 08:32 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5310 | PS5-60-SEA-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5311 | PS5-60-SEA-0001-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5312 | PS5-60-VS-9100A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-VS-9100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-06-19 04:53 | PS5-60-42 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5313 | PS5-60-VS-9100B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-VS-9100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-06-19 04:53 | PS5-60-43 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5314 | PS5-60-VS-9100C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-60-VS-9100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C |  | PS5-60-44 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5315 | PS5-60-VS-9100D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-60-VS-9100D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | 2026-06-19 04:54 | PS5-60-45 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5316 | PS5-60-VS-9100E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-60-VS-9100E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E |  | PS5-60-46 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5317 | PS5-60-VS-9100F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-60-VS-9100F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F |  | PS5-60-47 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-5318 | PS5-60-VS-9100G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-60-VS-9100G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G |  | PS5-60-48 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-5319 | PS5-61-BI-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-05-25 17:35 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5320 | PS5-61-BI-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-05-25 17:35 | PS5-60-04 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5321 | PS5-61-BI-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001C TO PS5-61-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-05-29 14:43 | PS5-60-07 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5322 | PS5-61-BI-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001D TO PS5-61-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-05-29 14:42 | PS5-60-10 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5323 | PS5-61-BI-0005-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001E TO PS5-61-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-05-29 14:42 | PS5-60-13 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5324 | PS5-61-BI-0006-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001F TO PS5-61-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-05-29 14:41 | PS5-60-16 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-5325 | PS5-61-BI-0007-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001G TO PS5-61-BI-0007 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-05-25 17:37 | PS5-60-19 |  |  | LV Power Cable | E | Closed | PS5 - Milestone E
T-00233-5581 | PS5-71-IN-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00233-5582 | PS5-71-IN-0002-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00233-5583 | PS5-71-IN-0002-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00233-5584 | PS5-71-IN-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-06-19 04:37 | PS5-71-23 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5585 | PS5-71-IN-0003-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-06-19 04:38 | PS5-71-23 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5586 | PS5-71-IN-0003-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-06-06 04:50 | PS5-71-23 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5594 | PS5-71-MOV-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-06-11 04:56 | PS5-71-08 |  |  | LV Power Cable | E | Closed | PS5 - Milestone H
T-00233-5595 | PS5-71-MOV-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-06-04 17:59 | PS5-71-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5596 | PS5-71-MOV-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-06-11 04:56 | PS5-71-08 |  |  | LV Power Cable | E | Closed | PS5 - Milestone H
T-00233-5597 | PS5-71-MOV-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-06-04 18:00 | PS5-71-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-5599 | PS5-71-MOV-0008-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-06-04 18:01 | PS5-71-08 |  |  | LV Power Cable | E | Closed | PS5 - Milestone H
T-00233-5601 | PS5-71-MOV-0010-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-06-11 04:57 | PS5-71-08 |  |  | LV Power Cable | E | Closed | PS5 - Milestone H
T-00233-9131 | PS5-60-BE-0007A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-06-27 08:56 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9132 | PS5-60-BE-0007B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-06-27 09:13 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9133 | PS5-60-BE-0007C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0007C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9134 | PS5-60-BE-0007D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0007D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2026-06-19 04:22 | PS5-60-62 |  |  | LV Power Cable | E | Closed | PS5 - Milestone D
T-00233-9135 | PS5-60-BE-0007E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BE-0007E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9136 | PS5-60-BE-0007F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BE-0007F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9137 | PS5-60-BE-0007G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BE-0007G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-9138 | PS5-60-BE-0027A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0027A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:40 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9139 | PS5-60-BE-0027B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0027B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00233-9140 | PS5-60-BE-0027C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0027C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9141 | PS5-60-BE-0027D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0027D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9142 | PS5-60-BE-0027E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BE-0027E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9143 | PS5-60-BE-0027F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BE-0027F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9144 | PS5-60-BE-0027G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BE-0027G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-9145 | PS5-60-BE-0028A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0028A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:39 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9146 | PS5-60-BE-0028B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0028B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 13:25 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9147 | PS5-60-BE-0028C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BE-0028C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9148 | PS5-60-BE-0028D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BE-0028D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9149 | PS5-60-BE-0028E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BE-0028E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9150 | PS5-60-BE-0028F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BE-0028F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9151 | PS5-60-BE-0028G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BE-0028G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-9152 | PS5-60-BI-0006A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:38 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9153 | PS5-60-BI-0006A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 14:12 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9154 | PS5-60-BI-0006A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 13:28 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9155 | PS5-60-BI-0006A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:36 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9156 | PS5-60-BI-0006A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:34 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9157 | PS5-60-BI-0006A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:33 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9158 | PS5-60-BI-0006A-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:33 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9159 | PS5-60-BI-0006A-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:32 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9160 | PS5-60-BI-0006A-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 13:29 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9161 | PS5-60-BI-0006A-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:32 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9162 | PS5-60-BI-0006A-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:30 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9163 | PS5-60-BI-0006B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:29 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9164 | PS5-60-BI-0006B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 13:31 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9165 | PS5-60-BI-0006B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 13:32 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9166 | PS5-60-BI-0006B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:28 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9167 | PS5-60-BI-0006B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:28 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9168 | PS5-60-BI-0006B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:27 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9169 | PS5-60-BI-0006B-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:26 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9170 | PS5-60-BI-0006B-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:25 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9171 | PS5-60-BI-0006B-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:25 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9172 | PS5-60-BI-0006B-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:24 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9173 | PS5-60-BI-0006B-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:24 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9174 | PS5-60-BI-0006C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9175 | PS5-60-BI-0006C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9176 | PS5-60-BI-0006C-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9177 | PS5-60-BI-0006C-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9178 | PS5-60-BI-0006C-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9179 | PS5-60-BI-0006C-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9180 | PS5-60-BI-0006C-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9181 | PS5-60-BI-0006C-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9182 | PS5-60-BI-0006C-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9183 | PS5-60-BI-0006C-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9184 | PS5-60-BI-0006C-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9185 | PS5-60-BI-0006D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9186 | PS5-60-BI-0006D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9187 | PS5-60-BI-0006D-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9188 | PS5-60-BI-0006D-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9189 | PS5-60-BI-0006D-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9190 | PS5-60-BI-0006D-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9191 | PS5-60-BI-0006D-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9192 | PS5-60-BI-0006D-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9193 | PS5-60-BI-0006D-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9194 | PS5-60-BI-0006D-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9195 | PS5-60-BI-0006D-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9196 | PS5-60-BI-0006E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9197 | PS5-60-BI-0006E-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9198 | PS5-60-BI-0006E-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9199 | PS5-60-BI-0006E-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9200 | PS5-60-BI-0006E-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9201 | PS5-60-BI-0006E-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9202 | PS5-60-BI-0006E-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9203 | PS5-60-BI-0006E-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9204 | PS5-60-BI-0006E-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9205 | PS5-60-BI-0006E-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9206 | PS5-60-BI-0006E-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9207 | PS5-60-BI-0006F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9208 | PS5-60-BI-0006F-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9209 | PS5-60-BI-0006F-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9210 | PS5-60-BI-0006F-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9211 | PS5-60-BI-0006F-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9212 | PS5-60-BI-0006F-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9213 | PS5-60-BI-0006F-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9214 | PS5-60-BI-0006F-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9215 | PS5-60-BI-0006F-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9216 | PS5-60-BI-0006F-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9217 | PS5-60-BI-0006F-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9218 | PS5-60-BI-0006G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-9219 | PS5-60-BI-0006G-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-9220 | PS5-60-BI-0006G-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-9221 | PS5-60-BI-0006G-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-9222 | PS5-60-BI-0006G-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-9223 | PS5-60-BI-0006G-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-9224 | PS5-60-BI-0006G-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-9225 | PS5-60-BI-0006G-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-9226 | PS5-60-BI-0006G-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-9227 | PS5-60-BI-0006G-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-9228 | PS5-60-BI-0006G-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-9229 | PS5-60-BI-0017A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0017A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:23 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9230 | PS5-60-BI-0017B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0017B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:23 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9231 | PS5-60-BI-0017C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0017C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9232 | PS5-60-BI-0017D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0017D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9233 | PS5-60-BI-0017E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0017E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9234 | PS5-60-BI-0017F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0017F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9235 | PS5-60-BI-0017G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0017G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-9236 | PS5-60-EA-2900A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-EA-2900A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00233-9237 | PS5-60-EA-2900B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-EA-2900B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B
T-00233-9238 | PS5-60-EA-2900C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002C TO PS5-60-EA-2900C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9239 | PS5-60-EA-2900D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002D TO PS5-60-EA-2900D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9240 | PS5-60-EA-2900E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002E TO PS5-60-EA-2900E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9241 | PS5-60-EA-2900F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002F TO PS5-60-EA-2900F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D
T-00233-9242 | PS5-60-EA-2900G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002G TO PS5-60-EA-2900G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E
T-00233-9244 | PS5-71-BE-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-07-03 09:19 | PS5-71-08 |  |  | LV Power Cable | E | Closed | PS5 - Milestone H
T-00233-9245 | PS5-71-BE-0004-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00233-9246 | PS5-71-BE-0004-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-07-03 09:21 | PS5-71-08 |  |  | LV Power Cable | E | Closed | PS5 - Milestone H
T-00233-9247 | PS5-71-BI-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-07-03 09:24 | PS5-71-08 |  |  | LV Power Cable | E | Closed | PS5 - Milestone H
T-00233-9248 | PS5-71-BI-0003-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00233-9249 | PS5-71-BI-0003-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00233-9250 | PS5-71-BI-0003-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00233-9251 | PS5-71-BI-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H
T-00233-9252 | PS5-71-BI-0005-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-01 12:21 | PS5-71-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9253 | PS5-71-BI-0005-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-01 12:19 | PS5-71-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9254 | PS5-71-BI-0005-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-01 14:11 | PS5-71-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00233-9255 | PS5-71-BI-0006-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-01 12:17 | PS5-71-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B
T-00234-2101 | PS5-60-IE-0002A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:36 | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B
T-00234-2102 | PS5-60-IE-0002A-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:36 | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B
T-00234-2103 | PS5-60-IE-0002A-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:37 | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B
T-00234-2104 | PS5-60-IE-0002B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:37 | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B
T-00234-2105 | PS5-60-IE-0002B-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:36 | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B
T-00234-2106 | PS5-60-IE-0002B-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:39 | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B
T-00234-2107 | PS5-60-IE-0002C-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-03 08:45 | PS5-60-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D
T-00234-2108 | PS5-60-IE-0002C-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-03 08:50 | PS5-60-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D
T-00234-2109 | PS5-60-IE-0002C-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-03 08:52 | PS5-60-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D
T-00234-2110 | PS5-60-IE-0002D-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-07-03 08:57 | PS5-60-10 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D
T-00234-2111 | PS5-60-IE-0002D-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-07-03 09:01 | PS5-60-10 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D
T-00234-2112 | PS5-60-IE-0002D-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2113 | PS5-60-IE-0002E-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2114 | PS5-60-IE-0002E-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2115 | PS5-60-IE-0002E-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2116 | PS5-60-IE-0002F-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2117 | PS5-60-IE-0002F-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2118 | PS5-60-IE-0002F-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2119 | PS5-60-IE-0002G-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone E
T-00234-2120 | PS5-60-IE-0002G-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone E
T-00234-2121 | PS5-60-IE-0002G-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone E
T-00234-2123 | PS5-60-IE-0003A-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 04:54 | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B
T-00234-2124 | PS5-60-IE-0003A-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:37 | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B
T-00234-2125 | PS5-60-IE-0003A-CD04 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0005A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 04:38 | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B
T-00234-2126 | PS5-60-IE-0003A-CD05 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:39 | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B
T-00234-2135 | PS5-60-IE-0003A-CD14 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:38 | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B
T-00234-2136 | PS5-60-IE-0003A-CD15 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-27 09:30 | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B
T-00234-2138 | PS5-60-IE-0003B-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:39 | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B
T-00234-2139 | PS5-60-IE-0003B-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:40 | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B
T-00234-2140 | PS5-60-IE-0003B-CD04 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0005B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:34 | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B
T-00234-2141 | PS5-60-IE-0003B-CD05 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 04:55 | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B
T-00234-2150 | PS5-60-IE-0003B-CD14 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:40 | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B
T-00234-2151 | PS5-60-IE-0003B-CD15 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-27 09:31 | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B
T-00234-2153 | PS5-60-IE-0003C-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2154 | PS5-60-IE-0003C-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2155 | PS5-60-IE-0003C-CD04 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0005C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-01 14:12 | PS5-60-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D
T-00234-2156 | PS5-60-IE-0003C-CD05 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2165 | PS5-60-IE-0003C-CD14 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2166 | PS5-60-IE-0003C-CD15 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2168 | PS5-60-IE-0003D-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2169 | PS5-60-IE-0003D-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-19 04:56 | PS5-60-10 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D
T-00234-2170 | PS5-60-IE-0003D-CD04 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0005D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-19 04:41 | PS5-60-10 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D
T-00234-2171 | PS5-60-IE-0003D-CD05 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-19 04:56 | PS5-60-10 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D
T-00234-2180 | PS5-60-IE-0003D-CD14 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-06-19 04:57 | PS5-60-10 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D
T-00234-2181 | PS5-60-IE-0003D-CD15 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2183 | PS5-60-IE-0003E-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2184 | PS5-60-IE-0003E-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2185 | PS5-60-IE-0003E-CD04 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0005E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-07-01 14:13 | PS5-60-13 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D
T-00234-2186 | PS5-60-IE-0003E-CD05 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2195 | PS5-60-IE-0003E-CD14 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2196 | PS5-60-IE-0003E-CD15 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2198 | PS5-60-IE-0003F-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2199 | PS5-60-IE-0003F-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2200 | PS5-60-IE-0003F-CD04 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0005F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-07-01 14:13 | PS5-60-16 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone D
T-00234-2201 | PS5-60-IE-0003F-CD05 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2210 | PS5-60-IE-0003F-CD14 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2211 | PS5-60-IE-0003F-CD15 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00234-2213 | PS5-60-IE-0003G-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone E
T-00234-2214 | PS5-60-IE-0003G-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone E
T-00234-2215 | PS5-60-IE-0003G-CD04 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0005G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-07-01 14:14 | PS5-60-19 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone E
T-00234-2216 | PS5-60-IE-0003G-CD05 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone E
T-00234-2225 | PS5-60-IE-0003G-CD14 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone E
T-00234-2226 | PS5-60-IE-0003G-CD15 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone E
T-00238-0457 | PS5-60-IE-0003A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GCP G-1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B
T-00238-0458 | PS5-60-IE-0003B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GCP G-2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B
T-00238-0459 | PS5-60-IE-0003C |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GCP G-3 (C) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D
T-00238-0460 | PS5-60-IE-0003D |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GCP G-4 (D) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D
T-00238-0461 | PS5-60-IE-0003E |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GCP G-5 (E) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D
T-00238-0462 | PS5-60-IE-0003F |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GCP G-6 (F) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D
T-00238-0463 | PS5-60-IE-0003G |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GCP G-7 (G) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone E
T-00238-0464 | PS5-60-IE-0004 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | MCP- MASTER CONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B
T-00238-0465 | PS5-60-IH-0001A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GENSET MCC -1 - G1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B
T-00238-0466 | PS5-60-IH-0001B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GENSET MCC -2 - G2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B
T-00238-0467 | PS5-60-IH-0001C |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GENSET MCC -3 - G3 (C) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D
T-00238-0468 | PS5-60-IH-0001D |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GENSET MCC -4 - G4 (D) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D
T-00238-0469 | PS5-60-IH-0001E |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GENSET MCC -5 - G5 (E) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D
T-00238-0470 | PS5-60-IH-0001F |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GENSET MCC -6 - G6 (F) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D
T-00238-0471 | PS5-60-IH-0001G |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GENSET MCC -7 - G7 (G) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone E
T-00238-0472 | PS5-60-IH-0002 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | COMMON / TREATMENT MCC | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B
T-00238-0473 | PS5-60-IE-0002A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B
T-00238-0474 | PS5-60-IE-0002B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B
T-00238-0475 | PS5-60-IE-0002C |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D
T-00238-0476 | PS5-60-IE-0002D |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D
T-00238-0477 | PS5-60-IE-0002E |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D
T-00238-0478 | PS5-60-IE-0002F |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D
T-00238-0479 | PS5-60-IE-0002G |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone E
T-00238-0552 | PS5-60-IN-0002A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B
T-00238-0553 | PS5-60-IN-0002B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B
T-00238-0554 | PS5-60-IN-0002C |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D
T-00238-0555 | PS5-60-IN-0002D |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D
T-00238-0556 | PS5-60-IN-0002E |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D
T-00238-0557 | PS5-60-IN-0002F |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone D
T-00238-0558 | PS5-60-IN-0002G |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone E
T-00238-0565 | PS5-71-IN-0002 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | CRO-PRE PRESSURECONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone H
T-00238-0566 | PS5-71-IN-0003 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | DFO- PRE PRESSURE CONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B
T-00243-0059 | PS5-60-IJ-0001A |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Neutral Grounding resistor for Generator set 1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone B
T-00243-0060 | PS5-60-IJ-0001B |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Neutral Grounding resistor for Generator set 2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone B
T-00243-0061 | PS5-60-IJ-0001C |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Neutral Grounding resistor for Generator set 3 (C) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone D
T-00243-0062 | PS5-60-IJ-0001D |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Neutral Grounding resistor for Generator set 4 (D) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone D
T-00243-0063 | PS5-60-IJ-0001E |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Neutral Grounding resistor for Generator set 5 (E) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone D
T-00243-0064 | PS5-60-IJ-0001F |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Neutral Grounding resistor for Generator set 6 (F) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone D
T-00243-0065 | PS5-60-IJ-0001G |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Neutral Grounding resistor for Generator set 7 (G) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone E
T-00254-12960 | PS5-60-BI-0001A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-12961 | PS5-60-BI-0001B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-12962 | PS5-60-BI-0001C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-BI-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12963 | PS5-60-BI-0001D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-BI-0001D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12964 | PS5-60-BI-0001E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-BI-0001E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12965 | PS5-60-BI-0001F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001F TO PS5-60-BI-0001F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12966 | PS5-60-BI-0001G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001G TO PS5-60-BI-0001G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-12967 | PS5-60-BI-0003-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-12968 | PS5-60-IE-0002A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-12969 | PS5-60-IE-0002A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-12970 | PS5-60-IE-0002A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-12971 | PS5-60-IE-0002B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-12972 | PS5-60-IE-0002B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-12973 | PS5-60-IE-0002B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-12974 | PS5-60-IE-0002C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12975 | PS5-60-IE-0002C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12976 | PS5-60-IE-0002C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12977 | PS5-60-IE-0002D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12978 | PS5-60-IE-0002D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12979 | PS5-60-IE-0002D-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12980 | PS5-60-IE-0002E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12981 | PS5-60-IE-0002E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12982 | PS5-60-IE-0002E-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12983 | PS5-60-IE-0002F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001F TO PS5-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12984 | PS5-60-IE-0002F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001F TO PS5-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12985 | PS5-60-IE-0002F-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001F TO PS5-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12986 | PS5-60-IE-0002G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001G TO PS5-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-12987 | PS5-60-IE-0002G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001G TO PS5-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-12988 | PS5-60-IE-0002G-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001G TO PS5-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-12989 | PS5-60-IH-0001A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-12990 | PS5-60-IH-0001A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-12991 | PS5-60-IH-0001B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-12992 | PS5-60-IH-0001B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-12993 | PS5-60-IH-0001C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12994 | PS5-60-IH-0001C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12995 | PS5-60-IH-0001D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12996 | PS5-60-IH-0001D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12997 | PS5-60-IH-0001E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12998 | PS5-60-IH-0001E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-12999 | PS5-60-IH-0001F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-13000 | PS5-60-IH-0001F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-13001 | PS5-60-IH-0001G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-13002 | PS5-60-IH-0001G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-13003 | PS5-60-IH-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-13004 | PS5-60-IH-0002-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-13005 | PS5-60-LA-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-13006 | PS5-60-LA-0003-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-13007 | PS5-60-PIT-8113A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BE-0027A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-13008 | PS5-60-PIT-8113B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BE-0027B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-13009 | PS5-60-PIT-8113C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-BE-0027C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-13010 | PS5-60-PIT-8113D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-BE-0027D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-13011 | PS5-60-PIT-8113E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-BE-0027E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-13012 | PS5-60-PIT-8113F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001F TO PS5-60-BE-0027F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-13013 | PS5-60-PIT-8113G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001G TO PS5-60-BE-0027G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-13014 | PS5-60-PIT-8114A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BE-0027A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-13015 | PS5-60-PIT-8114B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BE-0027B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-13016 | PS5-60-PIT-8114C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-BE-0027C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-13017 | PS5-60-PIT-8114D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-BE-0027D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-13018 | PS5-60-PIT-8114E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-BE-0027E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-13019 | PS5-60-PIT-8114F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001F TO PS5-60-BE-0027F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-13020 | PS5-60-PIT-8114G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001G TO PS5-60-BE-0027G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4499 | PS5-03-RDOS-1401-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-RMAC-1411 TO PS5-03-RDOS-1401 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4500 | PS5-03-RDOS-1402-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-RDOS-1401 TO PS5-03-RDOS-1402 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4501 | PS5-03-RDOS-1403-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-RDOS-1402 TO PS5-03-RDOS-1403 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4502 | PS5-03-RDOS-1404-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-RDOS-1403 TO PS5-03-RDOS-1404 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4503 | PS5-03-RDOS-1405-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-RDOS-1404 TO PS5-03-RDOS-1405 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4504 | PS5-03-RDOS-1406-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-RDOS-1503 TO PS5-03-RDOS-1406 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4505 | PS5-03-RDOS-1407-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-RDOS-1405 TO PS5-03-RDOS-1407 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4506 | PS5-03-RDOS-1408-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-RDOS-1407 TO PS5-03-RDOS-1408 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4552 | PS5-03-RMAC-1410-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-RDOS-2103 TO PS5-03-RMAC-1410 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4553 | PS5-03-RMAC-1411-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-RDOS-1406 TO PS5-03-RMAC-1411 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4900 | PS5-60-BE-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4901 | PS5-60-BE-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4902 | PS5-60-BE-0004A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0001A TO PS5-60-BE-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4903 | PS5-60-BE-0004B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0001B TO PS5-60-BE-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4904 | PS5-60-BE-0004C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0001C TO PS5-60-BE-0004C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4905 | PS5-60-BE-0004D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0001D TO PS5-60-BE-0004D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4906 | PS5-60-BE-0004E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0001E TO PS5-60-BE-0004E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4907 | PS5-60-BE-0004F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0001F TO PS5-60-BE-0004F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4908 | PS5-60-BE-0004G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0001G TO PS5-60-BE-0004G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4909 | PS5-60-BI-0001A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4910 | PS5-60-BI-0001A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4911 | PS5-60-BI-0001B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4912 | PS5-60-BI-0001B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4913 | PS5-60-BI-0001C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4914 | PS5-60-BI-0001C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4915 | PS5-60-BI-0001D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4916 | PS5-60-BI-0001D-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4917 | PS5-60-BI-0001E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0001E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4918 | PS5-60-BI-0001E-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0001E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4919 | PS5-60-BI-0001F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0001F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4920 | PS5-60-BI-0001F-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0001F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4921 | PS5-60-BI-0001G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0001G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4922 | PS5-60-BI-0001G-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0001G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4923 | PS5-60-BI-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4924 | PS5-60-BI-0002-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4925 | PS5-60-BI-0002-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4926 | PS5-60-BI-0002-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4927 | PS5-60-BI-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4928 | PS5-60-BI-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4929 | PS5-60-BI-0004A-CCO1 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4930 | PS5-60-BI-0004B-CCO1 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4931 | PS5-60-BI-0004C-CCO1 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-BI-0004C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4932 | PS5-60-BI-0004D-CCO1 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-BI-0004D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4933 | PS5-60-BI-0004E-CCO1 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-BI-0004E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4934 | PS5-60-BI-0004F-CCO1 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001F TO PS5-60-BI-0004F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4935 | PS5-60-BI-0004G-CCO1 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001G TO PS5-60-BI-0004G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4936 | PS5-60-BI-0005A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0005A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4937 | PS5-60-BI-0005A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0005A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4938 | PS5-60-BI-0005B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0005B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4939 | PS5-60-BI-0005B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0005B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4940 | PS5-60-BI-0005C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0005C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4941 | PS5-60-BI-0005C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0005C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4942 | PS5-60-BI-0005D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0005D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4943 | PS5-60-BI-0005D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0005D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4944 | PS5-60-BI-0005E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0005E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4945 | PS5-60-BI-0005E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0005E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4946 | PS5-60-BI-0005F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0005F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4947 | PS5-60-BI-0005F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0005F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4948 | PS5-60-BI-0005G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0005G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4949 | PS5-60-BI-0005G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0005G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4950 | PS5-60-BI-0006A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4951 | PS5-60-BI-0006A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4952 | PS5-60-BI-0006A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4953 | PS5-60-BI-0006A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4954 | PS5-60-BI-0006A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4955 | PS5-60-BI-0006A-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4956 | PS5-60-BI-0006B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4957 | PS5-60-BI-0006B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4958 | PS5-60-BI-0006B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4959 | PS5-60-BI-0006B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4960 | PS5-60-BI-0006B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4961 | PS5-60-BI-0006B-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4962 | PS5-60-BI-0006C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4963 | PS5-60-BI-0006C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4964 | PS5-60-BI-0006C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4965 | PS5-60-BI-0006C-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4966 | PS5-60-BI-0006C-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4967 | PS5-60-BI-0006C-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4968 | PS5-60-BI-0006D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4969 | PS5-60-BI-0006D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4970 | PS5-60-BI-0006D-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4971 | PS5-60-BI-0006D-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4972 | PS5-60-BI-0006D-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4973 | PS5-60-BI-0006D-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4974 | PS5-60-BI-0006E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4975 | PS5-60-BI-0006E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4976 | PS5-60-BI-0006E-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4977 | PS5-60-BI-0006E-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4978 | PS5-60-BI-0006E-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4979 | PS5-60-BI-0006E-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4980 | PS5-60-BI-0006F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4981 | PS5-60-BI-0006F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4982 | PS5-60-BI-0006F-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4983 | PS5-60-BI-0006F-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4984 | PS5-60-BI-0006F-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4985 | PS5-60-BI-0006F-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-4986 | PS5-60-BI-0006G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4987 | PS5-60-BI-0006G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4988 | PS5-60-BI-0006G-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4989 | PS5-60-BI-0006G-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4990 | PS5-60-BI-0006G-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4991 | PS5-60-BI-0006G-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-4992 | PS5-60-BI-0008A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4993 | PS5-60-BI-0008A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4994 | PS5-60-BI-0008B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4995 | PS5-60-BI-0008B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4996 | PS5-60-BI-0009A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0009A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4997 | PS5-60-BI-0009A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0009A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4998 | PS5-60-BI-0009B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0009B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-4999 | PS5-60-BI-0009B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0009B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5000 | PS5-60-BI-0010A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0010A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5001 | PS5-60-BI-0010A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0010A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5002 | PS5-60-BI-0010B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0010B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5003 | PS5-60-BI-0010B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001C TO PS5-60-BI-0010B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5004 | PS5-60-BI-0011A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5005 | PS5-60-BI-0011A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5006 | PS5-60-BI-0011B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5007 | PS5-60-BI-0011B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001D TO PS5-60-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5008 | PS5-60-BI-0012A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0012A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5009 | PS5-60-BI-0012A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0012A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5010 | PS5-60-BI-0012B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0012B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5011 | PS5-60-BI-0012B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001E TO PS5-60-BI-0012B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5012 | PS5-60-BI-0013A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0013A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5013 | PS5-60-BI-0013A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0013A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5014 | PS5-60-BI-0013B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0013B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5015 | PS5-60-BI-0013B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001F TO PS5-60-BI-0013B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5016 | PS5-60-BI-0014A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0014A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5017 | PS5-60-BI-0014A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0014A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5018 | PS5-60-BI-0014B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0014B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5019 | PS5-60-BI-0014B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001G TO PS5-60-BI-0014B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5020 | PS5-60-BI-0016A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5021 | PS5-60-BI-0016A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5022 | PS5-60-BI-0016A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-07-01 13:12 | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B
T-00254-5023 | PS5-60-BI-0016A-CCO4 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5024 | PS5-60-BI-0016B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5025 | PS5-60-BI-0016B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5026 | PS5-60-BI-0016B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-01 13:13 | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B
T-00254-5027 | PS5-60-BI-0016B-CCO4 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5028 | PS5-60-BI-0016C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5029 | PS5-60-BI-0016C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5030 | PS5-60-BI-0016C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-07-01 13:14 | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D
T-00254-5031 | PS5-60-BI-0016C-CCO4 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5032 | PS5-60-BI-0016D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5033 | PS5-60-BI-0016D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5034 | PS5-60-BI-0016D-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-07-01 13:15 | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D
T-00254-5035 | PS5-60-BI-0016D-CCO4 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5036 | PS5-60-BI-0016E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0016E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5037 | PS5-60-BI-0016E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0016E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5038 | PS5-60-BI-0016E-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0016E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-07-01 13:16 | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D
T-00254-5039 | PS5-60-BI-0016E-CCO4 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-BI-0016E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5040 | PS5-60-BI-0016F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0016F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5041 | PS5-60-BI-0016F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0016F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5042 | PS5-60-BI-0016F-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0016F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5043 | PS5-60-BI-0016F-CCO4 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001F TO PS5-60-BI-0016F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5044 | PS5-60-BI-0016G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0016G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5045 | PS5-60-BI-0016G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0016G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5046 | PS5-60-BI-0016G-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0016G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-07-01 13:17 | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone E
T-00254-5047 | PS5-60-BI-0016G-CCO4 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001G TO PS5-60-BI-0016G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5048 | PS5-60-BI-0017A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0017A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5049 | PS5-60-BI-0017B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0017B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5050 | PS5-60-BI-0017C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002C TO PS5-60-BI-0017C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C |  | PS5-60-60 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5051 | PS5-60-BI-0017D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002D TO PS5-60-BI-0017D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D |  | PS5-60-62 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5052 | PS5-60-BI-0017E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002E TO PS5-60-BI-0017E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E |  | PS5-60-64 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5053 | PS5-60-BI-0017F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002F TO PS5-60-BI-0017F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F |  | PS5-60-66 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5054 | PS5-60-BI-0017G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002G TO PS5-60-BI-0017G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G |  | PS5-60-68 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5055 | PS5-60-BI-0019A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0019A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5056 | PS5-60-BI-0019A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0019A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5057 | PS5-60-BI-0019B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0019B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5058 | PS5-60-BI-0019B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0019B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5059 | PS5-60-BI-0019C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0019C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5060 | PS5-60-BI-0019C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-BI-0019C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5061 | PS5-60-BI-0019D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0019D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5062 | PS5-60-BI-0019D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-BI-0019D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5063 | PS5-60-BI-0019E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0019E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5064 | PS5-60-BI-0019E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-BI-0019E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5065 | PS5-60-BI-0019F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0019F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5066 | PS5-60-BI-0019F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-BI-0019F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5067 | PS5-60-BI-0019G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0019G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5068 | PS5-60-BI-0019G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-BI-0019G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5069 | PS5-60-IE-0002B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5070 | PS5-60-IE-0002C-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5071 | PS5-60-IE-0002D-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5072 | PS5-60-IE-0002E-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5073 | PS5-60-IE-0002F-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5074 | PS5-60-IE-0002G-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5075 | PS5-60-IE-0003A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5076 | PS5-60-IE-0003A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5077 | PS5-60-IE-0003A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5078 | PS5-60-IE-0003A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5079 | PS5-60-IE-0003A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5080 | PS5-60-IE-0003A-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5081 | PS5-60-IE-0003A-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5082 | PS5-60-IE-0003A-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5083 | PS5-60-IE-0003A-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5084 | PS5-60-IE-0003A-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5085 | PS5-60-IE-0003A-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5086 | PS5-60-IE-0003A-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5087 | PS5-60-IE-0003A-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5088 | PS5-60-IE-0003A-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5093 | PS5-60-IE-0003A-CC25 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41100A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5094 | PS5-60-IE-0003A-CC26 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41100B TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5095 | PS5-60-IE-0003B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5096 | PS5-60-IE-0003B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5097 | PS5-60-IE-0003B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5098 | PS5-60-IE-0003B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5099 | PS5-60-IE-0003B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5100 | PS5-60-IE-0003B-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5101 | PS5-60-IE-0003B-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5102 | PS5-60-IE-0003B-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5103 | PS5-60-IE-0003B-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5104 | PS5-60-IE-0003B-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5105 | PS5-60-IE-0003B-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5106 | PS5-60-IE-0003B-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5107 | PS5-60-IE-0003B-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5108 | PS5-60-IE-0003B-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5113 | PS5-60-IE-0003B-CC25 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41200A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5114 | PS5-60-IE-0003B-CC26 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41200B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5115 | PS5-60-IE-0003C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5116 | PS5-60-IE-0003C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5117 | PS5-60-IE-0003C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5118 | PS5-60-IE-0003C-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5119 | PS5-60-IE-0003C-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5120 | PS5-60-IE-0003C-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5121 | PS5-60-IE-0003C-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5122 | PS5-60-IE-0003C-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5123 | PS5-60-IE-0003C-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5124 | PS5-60-IE-0003C-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5125 | PS5-60-IE-0003C-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5126 | PS5-60-IE-0003C-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5127 | PS5-60-IE-0003C-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5128 | PS5-60-IE-0003C-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002C TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5133 | PS5-60-IE-0003C-CC25 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41300A TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5134 | PS5-60-IE-0003C-CC26 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41300B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5135 | PS5-60-IE-0003D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5136 | PS5-60-IE-0003D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5137 | PS5-60-IE-0003D-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5138 | PS5-60-IE-0003D-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5139 | PS5-60-IE-0003D-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5140 | PS5-60-IE-0003D-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5141 | PS5-60-IE-0003D-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5142 | PS5-60-IE-0003D-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5143 | PS5-60-IE-0003D-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5144 | PS5-60-IE-0003D-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5145 | PS5-60-IE-0003D-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5146 | PS5-60-IE-0003D-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5147 | PS5-60-IE-0003D-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5148 | PS5-60-IE-0003D-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002D TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5153 | PS5-60-IE-0003D-CC25 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41400A TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5154 | PS5-60-IE-0003D-CC26 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41400B TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5155 | PS5-60-IE-0003E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5156 | PS5-60-IE-0003E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5157 | PS5-60-IE-0003E-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5158 | PS5-60-IE-0003E-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5159 | PS5-60-IE-0003E-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001E TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5160 | PS5-60-IE-0003E-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5161 | PS5-60-IE-0003E-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5162 | PS5-60-IE-0003E-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5163 | PS5-60-IE-0003E-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5164 | PS5-60-IE-0003E-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5165 | PS5-60-IE-0003E-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5166 | PS5-60-IE-0003E-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5167 | PS5-60-IE-0003E-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5168 | PS5-60-IE-0003E-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002E TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5173 | PS5-60-IE-0003E-CC25 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41500A TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5174 | PS5-60-IE-0003E-CC26 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41500B TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5175 | PS5-60-IE-0003F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IF-0001F TO PS5-60-IF-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5176 | PS5-60-IE-0003F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IF-0001F TO PS5-60-IF-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5177 | PS5-60-IE-0003F-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5178 | PS5-60-IE-0003F-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IF-0001F TO PS5-60-IF-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5179 | PS5-60-IE-0003F-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001F TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5180 | PS5-60-IE-0003F-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5181 | PS5-60-IE-0003F-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5182 | PS5-60-IE-0003F-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5183 | PS5-60-IE-0003F-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5184 | PS5-60-IE-0003F-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5185 | PS5-60-IE-0003F-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5186 | PS5-60-IE-0003F-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5187 | PS5-60-IE-0003F-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5188 | PS5-60-IE-0003F-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002F TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5193 | PS5-60-IE-0003F-CC25 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41600A TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5194 | PS5-60-IE-0003F-CC26 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41600B TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5195 | PS5-60-IE-0003G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IG-0001G TO PS5-60-IG-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5196 | PS5-60-IE-0003G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IG-0001G TO PS5-60-IG-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5197 | PS5-60-IE-0003G-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5198 | PS5-60-IE-0003G-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IG-0001G TO PS5-60-IG-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5199 | PS5-60-IE-0003G-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001G TO PS5-60-IE-0003H | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5200 | PS5-60-IE-0003G-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5201 | PS5-60-IE-0003G-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5202 | PS5-60-IE-0003G-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5203 | PS5-60-IE-0003G-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5204 | PS5-60-IE-0003G-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5205 | PS5-60-IE-0003G-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5206 | PS5-60-IE-0003G-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5207 | PS5-60-IE-0003G-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5208 | PS5-60-IE-0003G-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002G TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5213 | PS5-60-IE-0003G-CC25 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41700A TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5214 | PS5-60-IE-0003G-CC26 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41700B TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5215 | PS5-60-IE-0004-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5216 | PS5-60-IE-0004-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5217 | PS5-60-IE-0004-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5218 | PS5-60-IE-0004-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5219 | PS5-60-IE-0004-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5220 | PS5-60-IE-0004-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5221 | PS5-60-IE-0004-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5225 | PS5-60-IN-0001A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5226 | PS5-60-IN-0001A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5227 | PS5-60-IN-0001A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5228 | PS5-60-IN-0001A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2026-07-01 13:18 | PS5-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B
T-00254-5229 | PS5-60-IN-0001B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5230 | PS5-60-IN-0001B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5231 | PS5-60-IN-0001B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5232 | PS5-60-IN-0001B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2026-07-01 13:18 | PS5-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B
T-00254-5233 | PS5-60-IN-0001C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5234 | PS5-60-IN-0001C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | 2026-07-01 13:19 | PS5-60-51 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D
T-00254-5235 | PS5-60-IN-0001C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5236 | PS5-60-IN-0001C-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | 2026-07-01 13:19 | PS5-60-51 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D
T-00254-5237 | PS5-60-IN-0001D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5238 | PS5-60-IN-0001D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | 2026-07-01 13:20 | PS5-60-52 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D
T-00254-5239 | PS5-60-IN-0001D-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5240 | PS5-60-IN-0001D-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | 2026-07-01 13:21 | PS5-60-52 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D
T-00254-5241 | PS5-60-IN-0001E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0001E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5242 | PS5-60-IN-0001E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0001E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | 2026-07-01 13:21 | PS5-60-53 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D
T-00254-5243 | PS5-60-IN-0001E-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0001E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5244 | PS5-60-IN-0001E-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0001E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | 2026-07-01 13:22 | PS5-60-53 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D
T-00254-5245 | PS5-60-IN-0001F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0001F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5246 | PS5-60-IN-0001F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0001F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | 2026-07-01 13:22 | PS5-60-54 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D
T-00254-5247 | PS5-60-IN-0001F-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0001F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5248 | PS5-60-IN-0001F-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0001F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | 2026-07-01 13:23 | PS5-60-54 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone D
T-00254-5249 | PS5-60-IN-0001G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0001G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5250 | PS5-60-IN-0001G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0001G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | 2026-07-01 13:23 | PS5-60-55 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone E
T-00254-5251 | PS5-60-IN-0001G-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0001G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5252 | PS5-60-IN-0001G-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0001G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | 2026-07-01 13:24 | PS5-60-55 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone E
T-00254-5253 | PS5-60-IN-0002A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5254 | PS5-60-IN-0002A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5255 | PS5-60-IN-0002A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5256 | PS5-60-IN-0002A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5257 | PS5-60-IN-0002A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5258 | PS5-60-IN-0002A-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5259 | PS5-60-IN-0002B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5260 | PS5-60-IN-0002B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5261 | PS5-60-IN-0002B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5262 | PS5-60-IN-0002B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5263 | PS5-60-IN-0002B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5264 | PS5-60-IN-0002B-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5265 | PS5-60-IN-0002C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5266 | PS5-60-IN-0002C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5267 | PS5-60-IN-0002C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5268 | PS5-60-IN-0002C-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5269 | PS5-60-IN-0002C-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5270 | PS5-60-IN-0002C-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5271 | PS5-60-IN-0002D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5272 | PS5-60-IN-0002D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5273 | PS5-60-IN-0002D-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5274 | PS5-60-IN-0002D-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5275 | PS5-60-IN-0002D-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5276 | PS5-60-IN-0002D-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5277 | PS5-60-IN-0002E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5278 | PS5-60-IN-0002E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5279 | PS5-60-IN-0002E-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5280 | PS5-60-IN-0002E-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5281 | PS5-60-IN-0002E-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5282 | PS5-60-IN-0002E-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5283 | PS5-60-IN-0002F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5284 | PS5-60-IN-0002F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5285 | PS5-60-IN-0002F-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5286 | PS5-60-IN-0002F-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5287 | PS5-60-IN-0002F-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5288 | PS5-60-IN-0002F-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5289 | PS5-60-IN-0002G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5290 | PS5-60-IN-0002G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5291 | PS5-60-IN-0002G-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5292 | PS5-60-IN-0002G-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5293 | PS5-60-IN-0002G-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5294 | PS5-60-IN-0002G-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5296 | PS5-60-LA-0002A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5297 | PS5-60-LA-0002A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5298 | PS5-60-LA-0002A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5299 | PS5-60-LA-0002A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5300 | PS5-60-LA-0002A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5301 | PS5-60-LA-0002A-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5302 | PS5-60-LA-0002A-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5303 | PS5-60-LA-0002A-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5304 | PS5-60-LA-0002A-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5305 | PS5-60-LA-0002B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5306 | PS5-60-LA-0002B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5307 | PS5-60-LA-0002B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5308 | PS5-60-LA-0002B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5309 | PS5-60-LA-0002B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5310 | PS5-60-LA-0002B-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5311 | PS5-60-LA-0002C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5312 | PS5-60-LA-0002C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5313 | PS5-60-LA-0002C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5314 | PS5-60-LA-0002C-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5315 | PS5-60-LA-0002C-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5316 | PS5-60-LA-0002C-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5317 | PS5-60-LA-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5328 | PS5-60-SEA-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5329 | PS5-60-SEA-0001-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5330 | PS5-60-SEA-0001-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5331 | PS5-60-SEA-0001-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5332 | PS5-60-SEA-0001-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5333 | PS5-60-SEA-0001-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5334 | PS5-60-SEA-0001-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5335 | PS5-60-SEA-0001-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5336 | PS5-60-SEA-0001-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5337 | PS5-60-SEA-0001-CC12 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5338 | PS5-60-SEA-0001-CC13 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5339 | PS5-60-SEA-0001-CC14 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5340 | PS5-60-SEA-0001-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5341 | PS5-60-SEA-0001-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5342 | PS5-60-SEA-0001-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5351 | PS5-60-VS-9101A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-VS-9101A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5352 | PS5-60-VS-9101B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-VS-9101B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5353 | PS5-60-VS-9101C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-VS-9101C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C |  | PS5-60-44 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5354 | PS5-60-VS-9101D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-VS-9101D | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D |  | PS5-60-45 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5355 | PS5-60-VS-9101E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-VS-9101E | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E |  | PS5-60-46 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5356 | PS5-60-VS-9101F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-VS-9101F | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F |  | PS5-60-47 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5357 | PS5-60-VS-9101G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-VS-9101G | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G |  | PS5-60-48 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5358 | PS5-61-BI-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5359 | PS5-61-BI-0001-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5360 | PS5-61-BI-0001-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-61-TE-0003A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5361 | PS5-61-BI-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5362 | PS5-61-BI-0002-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5363 | PS5-61-BI-0002-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-61-TE-0003B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5364 | PS5-61-BI-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-61-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5365 | PS5-61-BI-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-61-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5366 | PS5-61-BI-0003-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-61-TE-0003C TO PS5-61-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5367 | PS5-61-BI-0004-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-61-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5368 | PS5-61-BI-0004-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-61-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5369 | PS5-61-BI-0004-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-61-TE-0003D TO PS5-61-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5370 | PS5-61-BI-0005-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-61-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5371 | PS5-61-BI-0005-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-61-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5372 | PS5-61-BI-0005-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-61-TE-0003E TO PS5-61-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5373 | PS5-61-BI-0006-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-61-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5374 | PS5-61-BI-0006-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-61-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5375 | PS5-61-BI-0006-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-61-TE-0003F TO PS5-61-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D
T-00254-5376 | PS5-61-BI-0007-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-61-BI-0007 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5377 | PS5-61-BI-0007-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-61-BI-0007 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5378 | PS5-61-BI-0007-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-61-TE-0003G TO PS5-61-BI-0007 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00254-5390 | PS5-71-BI-0001A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5391 | PS5-71-BI-0001B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5394 | PS5-71-BI-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5395 | PS5-71-BI-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5396 | PS5-71-BI-0003-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5397 | PS5-71-BI-0003-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5398 | PS5-71-BI-0004-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5399 | PS5-71-BI-0005-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5400 | PS5-71-BI-0005-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5401 | PS5-71-BI-0006-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5402 | PS5-71-BI-0008A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5403 | PS5-71-BI-0008A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5404 | PS5-71-BI-0008B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5405 | PS5-71-BI-0008B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5411 | PS5-71-BI-0011A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5412 | PS5-71-BI-0011A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5413 | PS5-71-BI-0011A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5414 | PS5-71-BI-0011A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5415 | PS5-71-BI-0011A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5416 | PS5-71-BI-0011B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5417 | PS5-71-BI-0011B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5418 | PS5-71-BI-0011B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5419 | PS5-71-BI-0011B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5420 | PS5-71-BI-0011B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5479 | PS5-71-IN-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5480 | PS5-71-IN-0002-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5481 | PS5-71-IN-0002-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5482 | PS5-71-IN-0002-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5486 | PS5-71-IN-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5487 | PS5-71-IN-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5488 | PS5-71-IN-0003-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5489 | PS5-71-IN-0003-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5528 | PS5-71-MOV-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2120 TO PS5-71-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5529 | PS5-71-MOV-0001-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2124 TO PS5-71-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5530 | PS5-71-MOV-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2120 TO PS5-71-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5531 | PS5-71-MOV-0002-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2124 TO PS5-71-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5532 | PS5-71-MOV-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2121 TO PS5-71-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5533 | PS5-71-MOV-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2125 TO PS5-71-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5534 | PS5-71-MOV-0004-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2121 TO PS5-71-MOV-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5535 | PS5-71-MOV-0004-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2125 TO PS5-71-MOV-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5536 | PS5-71-MOV-0007-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2118 TO PS5-71-MOV-0007 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5537 | PS5-71-MOV-0007-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2122 TO PS5-71-MOV-0007 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5538 | PS5-71-MOV-0008-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2118 TO PS5-71-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5539 | PS5-71-MOV-0008-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2122 TO PS5-71-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5540 | PS5-71-MOV-0009-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2119 TO PS5-71-MOV-0009 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5541 | PS5-71-MOV-0009-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2123 TO PS5-71-MOV-0009 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H
T-00254-5542 | PS5-71-MOV-0010-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2119 TO PS5-71-MOV-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-5543 | PS5-71-MOV-0010-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2123 TO PS5-71-MOV-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B
T-00254-9420 | PS5-03-RMAC-1409-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-03-SEA-0003 TO PS5-03-RMAC-1409 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E
T-00256-0027 | PS5-60-IE-0004-CX03 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-SSF1-161401 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B
T-00256-0028 | PS5-60-IE-0004-CX04 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-SSF1-161401 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B
T-00256-0029 | PS5-60-LA-0003-CX01 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-SSF1-161401 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B
T-00256-0090 | PS5-60-LA-0003-CX02 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B
T-00257-0165 | PS5-60-TW-0006G |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Thermowell | I | To be completed | PS5 - Milestone E
T-00257-0169 | PS5-60-TW-0007C |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00257-0171 | PS5-60-TW-0005F |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00257-0173 | PS5-60-TW-0007B |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Thermowell | I | To be completed | PS5 - Milestone B
T-00257-0174 | PS5-60-TW-0006C |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00257-0175 | PS5-60-TW-0008A |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Thermowell | I | To be completed | PS5 - Milestone B
T-00257-0176 | PS5-60-TW-0007D |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00257-0177 | PS5-60-TW-0008C |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00257-0179 | PS5-60-TW-0005G |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Thermowell | I | To be completed | PS5 - Milestone E
T-00257-0181 | PS5-60-TW-0008E |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00257-0182 | PS5-60-TW-0007A |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Thermowell | I | To be completed | PS5 - Milestone B
T-00257-0183 | PS5-60-TW-0006D |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00257-0184 | PS5-60-TW-0008B |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Thermowell | I | To be completed | PS5 - Milestone B
T-00257-0185 | PS5-60-TW-0007E |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00257-0186 | PS5-60-TW-0008D |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00257-0189 | PS5-60-TW-0008F |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00257-0190 | PS5-60-TW-0006E |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00257-0194 | PS5-60-TW-0006B |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Thermowell | I | To be completed | PS5 - Milestone B
T-00257-0198 | PS5-60-TW-0006A |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Thermowell | I | To be completed | PS5 - Milestone B
T-00257-0199 | PS5-60-TW-0007F |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00257-0207 | PS5-60-TW-0005A |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Thermowell | I | To be completed | PS5 - Milestone B
T-00257-0208 | PS5-60-TW-0005B |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Thermowell | I | To be completed | PS5 - Milestone B
T-00257-0209 | PS5-60-TW-0005C |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system |  | PS5-60-72 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00257-0210 | PS5-60-TW-0005D |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system |  | PS5-60-73 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00257-0211 | PS5-60-TW-0005E |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system |  | PS5-60-74 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00257-0212 | PS5-60-TW-0006F |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system |  | PS5-60-75 |  |  | Thermowell | I | To be completed | PS5 - Milestone D
T-00257-0213 | PS5-60-TW-0007G |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Thermowell | I | To be completed | PS5 - Milestone E
T-00257-0214 | PS5-60-TW-0008G |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system |  | PS5-60-76 |  |  | Thermowell | I | To be completed | PS5 - Milestone E
T-00275-1945 | PS5-60-IE-0003B-CA02 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B
T-00275-1946 | PS5-60-IE-0003B-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B
T-00275-1947 | PS5-60-IE-0003B-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B
T-00275-1948 | PS5-60-IE-0003B-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B
T-00275-1949 | PS5-60-IE-0003C-CA02 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1950 | PS5-60-IE-0003C-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1951 | PS5-60-IE-0003C-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1952 | PS5-60-IE-0003C-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1953 | PS5-60-IE-0003D-CA02 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1954 | PS5-60-IE-0003D-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1955 | PS5-60-IE-0003D-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1956 | PS5-60-IE-0003D-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1957 | PS5-60-IE-0003E-CA02 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1958 | PS5-60-IE-0003E-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1959 | PS5-60-IE-0003E-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1960 | PS5-60-IE-0003E-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1961 | PS5-60-IE-0003F-CA02 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1962 | PS5-60-IE-0003F-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1963 | PS5-60-IE-0003F-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1964 | PS5-60-IE-0003F-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1965 | PS5-60-IE-0003G-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003F TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone E
T-00275-1966 | PS5-60-IE-0003G-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003F TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone E
T-00275-1967 | PS5-60-IE-0003G-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003F TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone E
T-00275-1968 | PS5-60-IE-0004-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B
T-00275-1969 | PS5-60-IE-0004-CA07 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B
T-00275-1970 | PS5-60-IE-0004-CA08 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B
T-00275-1971 | PS5-60-IE-0004-CA14 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B
T-00275-1972 | PS5-60-IE-0004-CA15 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B
T-00275-1973 | PS5-60-IE-0004-CA21 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B
T-00275-1974 | PS5-60-IH-0001A-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B
T-00275-1975 | PS5-60-IH-0001B-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0001B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B
T-00275-1976 | PS5-60-IH-0001C-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0001C TO PS5-60-IH-0001C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS5-60-09 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1977 | PS5-60-IH-0001D-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0001D TO PS5-60-IH-0001D | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS5-60-12 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1978 | PS5-60-IH-0001E-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0001E TO PS5-60-IH-0001E | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS5-60-15 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1979 | PS5-60-IH-0001F-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0001F TO PS5-60-IH-0001F | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS5-60-18 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1980 | PS5-60-IH-0001G-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0001G TO PS5-60-IH-0001G | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS5-60-21 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone E
T-00275-1981 | PS5-60-IN-0001A-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B
T-00275-1982 | PS5-60-IN-0001B-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B
T-00275-1983 | PS5-60-IN-0001C-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0001C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C |  | PS5-60-51 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1984 | PS5-60-IN-0001D-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0001D | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D |  | PS5-60-52 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1985 | PS5-60-IN-0001E-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0001E | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E |  | PS5-60-53 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1986 | PS5-60-IN-0001F-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0001F | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F |  | PS5-60-54 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1987 | PS5-60-IN-0001G-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0001G | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G |  | PS5-60-55 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone E
T-00275-1988 | PS5-60-IN-0002A-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B
T-00275-1989 | PS5-60-IN-0002B-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B
T-00275-1990 | PS5-60-IN-0002C-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003C TO PS5-60-IN-0002C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) |  | PS5-60-61 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1991 | PS5-60-IN-0002D-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003D TO PS5-60-IN-0002D | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) |  | PS5-60-63 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1992 | PS5-60-IN-0002E-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003E TO PS5-60-IN-0002E | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) |  | PS5-60-65 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1993 | PS5-60-IN-0002F-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003F TO PS5-60-IN-0002F | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) |  | PS5-60-67 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1994 | PS5-60-IN-0002G-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IN-0002G | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) |  | PS5-60-69 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone E
T-00275-1995 | PS5-60-LA-0002B-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1996 | PS5-60-LA-0002B-CA02 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1997 | PS5-60-LA-0002B-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1998 | PS5-60-LA-0002B-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-1999 | PS5-60-LA-0002B-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002C TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-2000 | PS5-60-LA-0002B-CA06 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002C TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-2001 | PS5-60-LA-0002C-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-2002 | PS5-60-LA-0002C-CA02 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-2003 | PS5-60-LA-0002C-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-2004 | PS5-60-LA-0002C-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-2005 | PS5-60-LA-0002C-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002B TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-2006 | PS5-60-LA-0002C-CA06 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002B TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D
T-00275-2007 | PS5-60-SEA-0001-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone E
T-00275-2010 | PS5-71-IN-0002-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone H
T-00275-2011 | PS5-71-IN-0003-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B
T-00525-0026 | PS5-60-UR-8100A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE A | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2024-09-05 05:20 | PS5-60-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B
T-00525-0027 | PS5-60-UR-8100B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE B | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2024-09-05 05:21 | PS5-60-04 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B
T-00525-0028 | PS5-60-UR-8100C |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE C | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2024-09-05 05:21 | PS5-60-07 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0029 | PS5-60-UR-8100D |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE D | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2024-09-05 05:22 | PS5-60-10 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0030 | PS5-60-UR-8100E |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE E | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2024-10-08 10:58 | PS5-60-13 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0031 | PS5-60-UR-8100F |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE F | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2024-10-08 10:59 | PS5-60-16 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0032 | PS5-60-UR-8100G |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE G | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2024-09-05 05:23 | PS5-60-19 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone E
T-00525-0219 | PS5-60-UA-5100 |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COMPRESSOR AIR STARTING SKID | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2025-03-28 12:28 | PS5-60-27 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B
T-00525-0220 | PS5-60-UO-81100A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2025-03-28 12:29 | PS5-60-49 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B
T-00525-0221 | PS5-60-UO-81100B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2025-03-28 12:29 | PS5-60-50 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B
T-00525-0222 | PS5-60-UO-81100C |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | 2025-03-28 12:31 | PS5-60-51 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0223 | PS5-60-UO-81100D |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | 2025-03-28 13:09 | PS5-60-52 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0224 | PS5-60-UO-81100E |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | 2025-03-28 13:10 | PS5-60-53 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0225 | PS5-60-UO-81100F |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | 2025-03-28 13:10 | PS5-60-54 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0226 | PS5-60-UO-81100G |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | 2025-03-28 13:10 | PS5-60-55 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone E
T-00525-0227 | PS5-60-UZ-8200A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2025-05-05 12:03 | PS5-60-35 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B
T-00525-0228 | PS5-60-UZ-8200B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2025-03-28 13:12 | PS5-60-36 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B
T-00525-0229 | PS5-60-UZ-8200C |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C | 2025-03-28 13:12 | PS5-60-37 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0230 | PS5-60-UZ-8200D |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D | 2025-02-26 08:45 | PS5-60-38 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0231 | PS5-60-UZ-8200E |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-39 - Injector Tip Cooling Module E | 2025-02-26 08:45 | PS5-60-39 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0232 | PS5-60-UZ-8200F |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F | 2025-02-26 08:44 | PS5-60-40 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0233 | PS5-60-VS-9100A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2025-02-26 08:44 | PS5-60-42 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B
T-00525-0234 | PS5-60-VS-9100B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2025-02-26 08:43 | PS5-60-43 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B
T-00525-0235 | PS5-60-VS-9100C |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | 2025-02-26 08:43 | PS5-60-44 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0236 | PS5-60-VS-9100D |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | 2025-02-26 08:42 | PS5-60-45 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0237 | PS5-60-VS-9100E |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | 2025-02-26 08:41 | PS5-60-46 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0238 | PS5-60-VS-9100F |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | 2025-02-26 08:41 | PS5-60-47 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0239 | PS5-60-VS-9100G |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | 2025-02-26 08:41 | PS5-60-48 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone E
T-00525-0241 | PS5-71-UZ-6800A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | CRUDE FUEL SEPARATOR MODULE A | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2025-02-26 08:32 | PS5-71-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone H
T-00525-0242 | PS5-71-UZ-6800B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | CRUDE FUEL SEPARATOR MODULE B | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2025-02-26 08:31 | PS5-71-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone H
T-00525-0276 | PS5-60-UZ-8200G |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G | 2025-02-26 08:30 | PS5-60-41 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone E
T-00525-0278 | PS5-60-UR-8100A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE A | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2025-02-26 08:28 | PS5-60-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B
T-00525-0279 | PS5-60-UR-8100B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE B | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2025-02-26 08:09 | PS5-60-04 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B
T-00525-0280 | PS5-60-UR-8100C |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE C | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-135106 | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2025-02-26 08:25 | PS5-60-07 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0281 | PS5-60-UR-8100D |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE D | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-135109 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2025-02-26 08:24 | PS5-60-10 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0282 | PS5-60-UR-8100E |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE E | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-135112 | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2025-02-26 08:23 | PS5-60-13 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0283 | PS5-60-UR-8100G |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE G | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-135118 | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2025-02-26 08:22 | PS5-60-19 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone E
T-00525-0284 | PS5-60-UR-8100F |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE F | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-135115 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2025-02-26 08:21 | PS5-60-16 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0458 | PS5-60-EA-2500A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2025-06-27 13:58 | PS5-60-74 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0459 | PS5-60-EA-2500B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-74 - Engine E Cooling system | 2025-06-27 13:59 | PS5-60-74 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0460 | PS5-60-EA-2600A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2025-06-27 14:00 | PS5-60-75 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0461 | PS5-60-EA-2600B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-75 - Engine F Cooling system | 2025-07-15 10:44 | PS5-60-75 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0462 | PS5-60-EA-2700A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2025-06-27 14:01 | PS5-60-76 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone E
T-00525-0463 | PS5-60-EA-2700B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-76 - Engine G Cooling system | 2025-06-27 14:02 | PS5-60-76 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone E
T-00525-0464 | PS5-60-EA-2400A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2025-06-27 14:02 | PS5-60-73 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0465 | PS5-60-EA-2400B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-73 - Engine D Cooling system | 2025-06-27 14:03 | PS5-60-73 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0466 | PS5-60-EA-2100A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2025-06-27 14:03 | PS5-60-70 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B
T-00525-0467 | PS5-60-EA-2100B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2025-06-27 14:04 | PS5-60-70 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B
T-00525-0468 | PS5-60-EA-2200A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2025-06-27 14:05 | PS5-60-71 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B
T-00525-0469 | PS5-60-EA-2200B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2025-06-27 14:05 | PS5-60-71 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B
T-00525-0546 | PS5-60-UZ-8900B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2025-07-15 10:49 | PS5-60-58 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B
T-00525-0547 | PS5-60-UZ-8900C |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 2025-07-15 10:49 | PS5-60-60 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0548 | PS5-60-UZ-8900D |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 2025-07-15 11:01 | PS5-60-62 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0549 | PS5-60-UZ-8900E |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | 2025-07-15 11:03 | PS5-60-64 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0550 | PS5-60-UZ-8900F |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | 2025-07-15 11:04 | PS5-60-66 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0551 | PS5-60-UZ-8900G |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | 2025-07-15 11:04 | PS5-60-68 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone E
T-00525-0552 | PS5-61-IU-0001F |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2025-07-15 11:05 | PS5-60-16 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS5 - Milestone D
T-00525-0553 | PS5-61-IU-0001G |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2025-07-15 11:06 | PS5-60-19 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS5 - Milestone E
T-00525-0560 | PS5-71-UZ-6400 |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | CRUDE FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2025-07-16 08:17 | PS5-71-08 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone H
T-00525-0561 | PS5-60-UR-8200A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2025-07-16 08:18 | PS5-60-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B
T-00525-0562 | PS5-60-UR-8200F |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2025-07-16 08:19 | PS5-60-16 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0563 | PS5-60-UR-8200E |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2025-07-16 08:19 | PS5-60-13 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0564 | PS5-60-UR-8200D |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2025-07-16 08:20 | PS5-60-10 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0565 | PS5-60-UR-8200C |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2025-07-16 08:21 | PS5-60-07 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0566 | PS5-60-UR-8200B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2025-07-16 08:21 | PS5-60-04 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B
T-00525-0567 | PS5-60-UR-8300C |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-37 - Injector Tip Cooling Module C | 2025-07-16 08:22 | PS5-60-37 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0568 | PS5-60-UR-8300F |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-40 - Injector Tip Cooling Module F | 2025-07-16 08:23 | PS5-60-40 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0569 | PS5-60-UR-8300D |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-38 - Injector Tip Cooling Module D | 2025-07-16 08:24 | PS5-60-38 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0570 | PS5-60-LA-0002A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | VTMS VIBRATION AND TEMPERATURE MONITORING SYSTEM | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2025-07-16 08:24 | PS5-60-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone B
T-00525-0571 | PS5-60-EA-2300A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2025-08-11 12:22 | PS5-60-72 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0572 | PS5-60-EA-2300B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-72 - Engine C Cooling system | 2025-08-11 12:23 | PS5-60-72 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone D
T-00525-0573 | PS5-60-SEA-0001 |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | GAS DETECTION PANEL | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2025-08-11 12:24 | PS5-03-14 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone E
T-00525-0574 | PS5-60-UR-8300G |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-41 - Injector Tip Cooling Module G | 2025-08-11 12:29 | PS5-60-41 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone E
T-00525-0575 | PS5-60-UR-8200G |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2025-08-11 12:40 | PS5-60-19 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone E
T-00525-0576 | PS5-61-IU-0001D |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2025-08-11 12:41 | PS5-60-10 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS5 - Milestone D
T-00525-0583 | PS5-60-UA-5200 |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INSTRUMENT AIR COMPRESSOR MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-04-18 05:35 | PS5-60-26 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B
T-00525-0609 | PS5-61-IU-0001B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2025-09-11 06:52 | PS5-60-04 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS5 - Milestone B
T-00525-0899 | PS5-60-IJ-0001A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | Neutral Grounding resistor for Generator set 1 (A) | EACOP | CPP AGI |  |  | 10 |  | 10 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-05-22 10:05 | PS5-60-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS5 - Milestone B
T-00525-0900 | PS5-60-IJ-0001B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | Neutral Grounding resistor for Generator set 2 (B) | EACOP | CPP AGI |  |  | 10 |  | 10 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-05-22 10:06 | PS5-60-04 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS5 - Milestone B
T-00525-0901 | PS5-60-IJ-0001C |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | Neutral Grounding resistor for Generator set 3 (C) | EACOP | CPP AGI |  |  | 10 |  | 10 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C | 2026-05-22 10:06 | PS5-60-07 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS5 - Milestone D
T-00525-0902 | PS5-60-IJ-0001D |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | Neutral Grounding resistor for Generator set 4 (D) | EACOP | CPP AGI |  |  | 10 |  | 10 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D | 2026-05-22 10:07 | PS5-60-10 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS5 - Milestone D
T-00525-0903 | PS5-60-IJ-0001E |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | Neutral Grounding resistor for Generator set 5 (E) | EACOP | CPP AGI |  |  | 10 |  | 10 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E | 2026-05-22 10:08 | PS5-60-13 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS5 - Milestone D
T-00525-0904 | PS5-60-IJ-0001F |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | Neutral Grounding resistor for Generator set 6 (F) | EACOP | CPP AGI |  |  | 10 |  | 10 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F | 2026-05-22 10:08 | PS5-60-16 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS5 - Milestone D
T-00525-0905 | PS5-60-IJ-0001G |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | Neutral Grounding resistor for Generator set 7 (G) | EACOP | CPP AGI |  |  | 10 |  | 10 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G | 2026-05-22 10:09 | PS5-60-19 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS5 - Milestone E
T-00610-0220 | PS5-60-IE-0003A-CD06 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00610-0221 | PS5-60-IE-0003A-CD08 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00610-0222 | PS5-60-IE-0003A-CD12 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00610-0223 | PS5-60-IE-0003B-CD06 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00610-0224 | PS5-60-IE-0003B-CD08 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00610-0225 | PS5-60-IE-0003B-CD12 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00610-0226 | PS5-60-IE-0003C-CD06 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00610-0227 | PS5-60-IE-0003C-CD08 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00610-0228 | PS5-60-IE-0003C-CD12 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-07 - Power Generation Package C |  | PS5-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00610-0229 | PS5-60-IE-0003D-CD06 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00610-0230 | PS5-60-IE-0003D-CD08 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00610-0231 | PS5-60-IE-0003D-CD12 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00610-0232 | PS5-60-IE-0003E-CD06 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00610-0233 | PS5-60-IE-0003E-CD08 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00610-0234 | PS5-60-IE-0003E-CD12 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-13 - Power Generation Package E |  | PS5-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00610-0235 | PS5-60-IE-0003F-CD06 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00610-0236 | PS5-60-IE-0003F-CD08 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00610-0237 | PS5-60-IE-0003F-CD12 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone D
T-00610-0238 | PS5-60-IE-0003G-CD06 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone E
T-00610-0239 | PS5-60-IE-0003G-CD08 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone E
T-00610-0240 | PS5-60-IE-0003G-CD12 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-19 - Power Generation Package G |  | PS5-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone E
T-00610-0241 | PS5-60-IE-0004-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00610-0242 | PS5-60-IE-0004-CD02 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00610-0574 | PS5-60-IE-0004-CD14 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00610-0575 | PS5-60-IE-0004-CD15 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00610-0576 | PS5-60-IE-0004-CD16 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B
T-00614-0922 | PS5-03-SEA-0003-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0010 TO PS5-03-SEA-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  |  | I | To be completed | PS5 - Milestone E
T-00614-0923 | PS5-03-SEA-0003-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-03-SEA-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  |  | I | To be completed | PS5 - Milestone E
T-00614-1034 | PS5-60-IE-0003A-CC21 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  |  | I | To be completed | PS5 - Milestone B
T-00614-1035 | PS5-60-IE-0003A-CC22 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  |  | I | To be completed | PS5 - Milestone B
T-00614-1036 | PS5-60-IE-0003A-CC23 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0003 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  |  | I | To be completed | PS5 - Milestone B
T-00614-1037 | PS5-60-IE-0003A-CC24 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  |  | I | To be completed | PS5 - Milestone B
T-00614-1038 | PS5-60-IE-0003B-CC21 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  |  | I | To be completed | PS5 - Milestone B
T-00614-1039 | PS5-60-IE-0003B-CC22 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  |  | I | To be completed | PS5 - Milestone B
T-00614-1040 | PS5-60-IE-0003B-CC23 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0003 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  |  | I | To be completed | PS5 - Milestone B
T-00614-1041 | PS5-60-IE-0003B-CC24 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  |  | I | To be completed | PS5 - Milestone B
T-00614-1042 | PS5-60-IE-0003C-CC21 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  |  | I | To be completed | PS5 - Milestone D
T-00614-1043 | PS5-60-IE-0003C-CC22 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  |  | I | To be completed | PS5 - Milestone D
T-00614-1044 | PS5-60-IE-0003C-CC23 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0003 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  |  | I | To be completed | PS5 - Milestone D
T-00614-1045 | PS5-60-IE-0003C-CC24 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0006 TO PS5-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-08 - Power Gen Package C (UCP) |  | PS5-60-08 |  |  |  | I | To be completed | PS5 - Milestone D
T-00614-1046 | PS5-60-IE-0003D-CC21 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  |  | I | To be completed | PS5 - Milestone D
T-00614-1047 | PS5-60-IE-0003D-CC22 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  |  | I | To be completed | PS5 - Milestone D
T-00614-1048 | PS5-60-IE-0003D-CC23 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0003 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  |  | I | To be completed | PS5 - Milestone D
T-00614-1049 | PS5-60-IE-0003D-CC24 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-11 - Power Gen Package D (UCP) |  | PS5-60-11 |  |  |  | I | To be completed | PS5 - Milestone D
T-00614-1050 | PS5-60-IE-0003E-CC21 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  |  | I | To be completed | PS5 - Milestone D
T-00614-1051 | PS5-60-IE-0003E-CC22 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  |  | I | To be completed | PS5 - Milestone D
T-00614-1052 | PS5-60-IE-0003E-CC23 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0003 TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  |  | I | To be completed | PS5 - Milestone D
T-00614-1053 | PS5-60-IE-0003E-CC24 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-14 - Power Gen Package E (UCP) |  | PS5-60-14 |  |  |  | I | To be completed | PS5 - Milestone D
T-00614-1054 | PS5-60-IE-0003F-CC21 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  |  | I | To be completed | PS5 - Milestone D
T-00614-1055 | PS5-60-IE-0003F-CC22 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  |  | I | To be completed | PS5 - Milestone D
T-00614-1056 | PS5-60-IE-0003F-CC23 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0004 TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  |  | I | To be completed | PS5 - Milestone D
T-00614-1057 | PS5-60-IE-0003F-CC24 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0006 TO PS5-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-17 - Power Gen Package F (UCP) |  | PS5-60-17 |  |  |  | I | To be completed | PS5 - Milestone D
T-00614-1058 | PS5-60-IE-0003G-CC21 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  |  | I | To be completed | PS5 - Milestone E
T-00614-1059 | PS5-60-IE-0003G-CC22 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  |  | I | To be completed | PS5 - Milestone E
T-00614-1060 | PS5-60-IE-0003G-CC23 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0004 TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  |  | I | To be completed | PS5 - Milestone E
T-00614-1061 | PS5-60-IE-0003G-CC24 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0006 TO PS5-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-20 - Power Gen Package G (UCP) |  | PS5-60-20 |  |  |  | I | To be completed | PS5 - Milestone E
T-00614-1062 | PS5-60-IE-0004-CC08 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  |  | I | To be completed | PS5 - Milestone B
T-00614-1063 | PS5-60-IE-0004-CC11 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0004 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  |  | I | To be completed | PS5 - Milestone B
T-00614-1064 | PS5-60-IE-0004-CC12 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  |  | I | To be completed | PS5 - Milestone B
T-00614-1065 | PS5-60-SEA-0001-CC18 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0009 TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  |  | I | To be completed | PS5 - Milestone E
T-00614-1111 | PS5-71-IN-0002-CC05 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  |  | I | To be completed | PS5 - Milestone H
T-00614-1112 | PS5-71-IN-0002-CC06 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  |  | I | To be completed | PS5 - Milestone H
T-00614-1113 | PS5-71-IN-0002-CC07 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0006 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  |  | I | To be completed | PS5 - Milestone H
T-00614-1114 | PS5-71-IN-0003-CC05 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  |  | I | To be completed | PS5 - Milestone B
T-00614-1115 | PS5-71-IN-0003-CC06 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  |  | I | To be completed | PS5 - Milestone B
T-00614-1116 | PS5-71-IN-0003-CC07 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0006 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  |  | I | To be completed | PS5 - Milestone B

## PRELIMINARY -MILESTONES
SUBSYSTEM | SUBSYTEM DESCRIPTIONS | Priority | REMARKS
PS5-60-22 | PS5-60-22 - Power Gen Master UCP | PS5 - Milestone B
PS5-60-26 | PS5-60-26 - Instrument Air Compressor Skid | PS5 - Milestone B
PS5-60-27 | PS5-60-27 - Compressed Air Starting Skid | PS5 - Milestone B
PS5-60-02 | PS5-60-02 - Power Gen Package A (UCP) | PS5 - Milestone B
PS5-60-03 | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | PS5 - Milestone B
PS5-71-23 | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | PS5 - Milestone B
PS5-60-70 | PS5-60-70 - Engine A Cooling system | PS5 - Milestone B
PS5-60-57 | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | PS5 - Milestone B
PS5-60-05 | PS5-60-05 - Power Gen Package B (UCP) | PS5 - Milestone B
PS5-60-06 | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | PS5 - Milestone B
PS5-60-35 | PS5-60-35 - Injector Tip Cooling Module A | PS5 - Milestone B
PS5-60-42 | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | PS5 - Milestone B
PS5-60-49 | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | PS5 - Milestone B
PS5-71-22 | PS5-71-22 - Diesel Fuel Pre Pressure Module | PS5 - Milestone B
PS5-60-01 | PS5-60-01 - Power Generation Package A | PS5 - Milestone B
PS5-60-56 | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | PS5 - Milestone B
PS5-60-59 | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | PS5 - Milestone B
PS5-60-71 | PS5-60-71 - Engine B Cooling system | PS5 - Milestone B
PS5-60-36 | PS5-60-36 - Injector Tip Cooling Module B | PS5 - Milestone B
PS5-60-43 | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | PS5 - Milestone B
PS5-60-04 | PS5-60-04 - Power Generation Package B | PS5 - Milestone B
PS5-60-50 | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | PS5 - Milestone B
PS5-60-58 | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | PS5 - Milestone B
PS5-60-08 | PS5-60-08 - Power Gen Package C (UCP) | PS5 - Milestone D
PS5-60-09 | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | PS5 - Milestone D
PS5-60-61 | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | PS5 - Milestone D
PS5-60-72 | PS5-60-72 - Engine C Cooling system | PS5 - Milestone D
PS5-60-11 | PS5-60-11 - Power Gen Package D (UCP) | PS5 - Milestone D
PS5-60-12 | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | PS5 - Milestone D
PS5-60-37 | PS5-60-37 - Injector Tip Cooling Module C | PS5 - Milestone D
PS5-60-44 | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | PS5 - Milestone D
PS5-60-51 | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | PS5 - Milestone D
PS5-60-07 | PS5-60-07 - Power Generation Package C | PS5 - Milestone D
PS5-60-60 | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | PS5 - Milestone D
PS5-60-63 | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | PS5 - Milestone D
PS5-60-73 | PS5-60-73 - Engine D Cooling system | PS5 - Milestone D
PS5-60-14 | PS5-60-14 - Power Gen Package E (UCP) | PS5 - Milestone D
PS5-60-15 | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | PS5 - Milestone D
PS5-60-38 | PS5-60-38 - Injector Tip Cooling Module D | PS5 - Milestone D
PS5-60-45 | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | PS5 - Milestone D
PS5-60-52 | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | PS5 - Milestone D
PS5-60-10 | PS5-60-10 - Power Generation Package D | PS5 - Milestone D
PS5-60-62 | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | PS5 - Milestone D
PS5-60-65 | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | PS5 - Milestone D
PS5-60-74 | PS5-60-74 - Engine E Cooling system | PS5 - Milestone D
PS5-60-17 | PS5-60-17 - Power Gen Package F (UCP) | PS5 - Milestone D
PS5-60-18 | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | PS5 - Milestone D
PS5-60-39 | PS5-60-39 - Injector Tip Cooling Module E | PS5 - Milestone D
PS5-60-46 | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | PS5 - Milestone D
PS5-60-53 | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | PS5 - Milestone D
PS5-60-13 | PS5-60-13 - Power Generation Package E | PS5 - Milestone D
PS5-60-64 | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | PS5 - Milestone D
PS5-60-67 | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | PS5 - Milestone D
PS5-60-75 | PS5-60-75 - Engine F Cooling system | PS5 - Milestone D
PS5-60-40 | PS5-60-40 - Injector Tip Cooling Module F | PS5 - Milestone D
PS5-60-47 | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | PS5 - Milestone D
PS5-60-54 | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | PS5 - Milestone D
PS5-60-16 | PS5-60-16 - Power Generation Package F | PS5 - Milestone D
PS5-60-66 | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | PS5 - Milestone D
PS5-60-20 | PS5-60-20 - Power Gen Package G (UCP) | PS5 - Milestone E
PS5-60-21 | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | PS5 - Milestone E
PS5-60-69 | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | PS5 - Milestone E
PS5-60-76 | PS5-60-76 - Engine G Cooling system | PS5 - Milestone E
PS5-60-41 | PS5-60-41 - Injector Tip Cooling Module G | PS5 - Milestone E
PS5-60-48 | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | PS5 - Milestone E
PS5-60-55 | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | PS5 - Milestone E
PS5-60-19 | PS5-60-19 - Power Generation Package G | PS5 - Milestone E
PS5-60-68 | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | PS5 - Milestone E
PS5-03-14 | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | PS5 - Milestone E
PS5-71-06 | PS5-71-06 - Crude Fuel Separation Module | PS5 - Milestone H
PS5-71-08 | PS5-71-08 - CFO Pre-Pressure Modules | PS5 - Milestone H
PS5-71-09 | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | PS5 - Milestone H

## MILESTONE & DIS.
Responsible Company : CPP AGI-VENDOR-MANTRAC CHECKLIST SUMMERY
Milestone & Discipline | Subsystem Total | ITR Total | ITR EACOP Approved | ITR Open |  | CUT OFF DATE-19-JUNE-2026
[6 empty] | 27 June | 28 June | 29 June | 30 June | 1 July | 2 July | 3 July | TOTAL
PS5 - Milestone B | 23 | 1298 | 429 | 869 | [8 empty] | 33.05%
E - Electrical |  | 470 | 176 | 294 |  | 15 |  |  |  | 31 |  |  | 46 | MILESTONES-CPP AGI STATUS
I - Instrumentation |  | 421 | 4 | 417 | [5 empty] | 4 |  |  | 4 | MILESTONES | TOTAL ITRs | CLOSED | REMAIINING | % | CUT OFF-19-JUNE
M - Mechanical |  | 58 | 58 | 0 |  |  |  |  | 4 |  |  |  | 4 | PS5 - Milestone B | 1298 | 429 | 869 | 33.05% | 59
P - Piping & Vessel |  | 315 | 191 | 124 |  | 1 |  |  |  |  | 4 |  | 5 | PS5 - Milestone D | 2103 | 518 | 1585 | 24.63% | 45
T - Telecom |  | 34 | 0 | 34 | [8 empty] | 0 | PS5 - Milestone E | 589 | 117 | 472 | 19.86% | 22
PS5 - Milestone D | 36 | 2103 | 518 | 1585 | [8 empty] | 24.63% | PS5 - Milestone H | 154 | 34 | 120 | 22.08% | 5
E - Electrical |  | 752 | 99 | 653 | [5 empty] | 3 |  | 5 | 8 | TOTAL | 4144 | 1098 | 3046 | 26.5% | 131
I - Instrumentation |  | 646 | 11 | 635 | [5 empty] | 11 |  |  | 11
M - Mechanical |  | 109 | 109 | 0 |  |  |  |  | 8 |  |  |  | 8 | HYDROTEST-ITRs STATUS
P - Piping & Vessel |  | 516 | 299 | 217 |  |  |  |  | 6 | 1 | 8 | 3 | 18 | MILESTONES | TOTAL ITRs | CLOSED | REMAIINING | %
T - Telecom |  | 80 | 0 | 80 | [8 empty] | 0 | PS5 - Milestone B | 225 | 158 | 67 | 70.22%
PS5 - Milestone E | 10 | 589 | 117 | 472 | [8 empty] | 19.86% | PS5 - Milestone D | 360 | 239 | 121 | 66.39%
E - Electrical |  | 194 | 18 | 176 | [5 empty] | 1 |  |  | 1 | PS5 - Milestone E | 90 | 52 | 38 | 57.78%
I - Instrumentation |  | 223 | 3 | 220 | [5 empty] | 3 |  |  | 3 | PS5 - Milestone H | 25 | 18 | 7 | 72%
M - Mechanical |  | 29 | 29 | 0 | [8 empty] | 0 | GRAND TOTAL | 700 | 467 | 233 | 66.71%
P - Piping & Vessel |  | 129 | 67 | 62 |  |  |  |  | 3 | 3 | 7 | 5 | 18
T - Telecom |  | 14 | 0 | 14 | [8 empty] | 0
PS5 - Milestone H | 3 | 154 | 34 | 120 | [8 empty] | 22.08%
E - Electrical |  | 35 | 7 | 28 | [7 empty] | 3 | 3
I - Instrumentation |  | 76 | 0 | 76 | [8 empty] | 0
M - Mechanical |  | 6 | 6 | 0 |  |  |  |  | 2 |  |  |  | 2
P - Piping & Vessel |  | 35 | 21 | 14 | [8 empty] | 0
T - Telecom |  | 2 | 0 | 2 | [8 empty] | 0
Grand Total | 72 | 4144 | 1098 | 3046 | 0 | 16 | 0 | 0 | 23 | 57 | 19 | 16 | 131

## 1ST PRIORITY MANTRAC
TASK ID | Asset - Tag | Asset Pack ID | Cable Pack ID | Pipe Pack ID | Loop Name | Description | Category (Summary) | Discipline | Task Type (Name) | Discipline (Summary) | Asset - Description | Systemization - Process Plant ID | Responsible Company (Summary) | Actual Duration | Scheduled Duration | Task Duration | Title - Actual MH/Person | Title - Planned MH/Person | Field005 (Custom) | Physical Location - Area (Summary) | Systemization - Subsystem (Summary) | Closing Date | Subsystem ID | Priority | Priority | Test Form - Description | Asset Discipline | Task State | Priority | RFC | P-1,2,3
T-00018-0192 | PS5-61-IU-0001A |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 16 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Power Transformer | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00018-0193 | PS5-61-IU-0001B |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 16 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Power Transformer | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00022-3334 | PS5-60-IJ-0001A-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-60-IJ-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-03-07 11:29 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00022-3335 | PS5-60-IJ-0001B-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-60-IJ-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-03-07 11:36 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00022-3377 | PS5-61-IJ-0001-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-24 08:12 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00022-3378 | PS5-61-IJ-0001-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-24 12:59 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00022-3379 | PS5-61-IJ-0001-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-24 13:00 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00022-3380 | PS5-61-IJ-0001-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-24 13:01 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00022-3381 | PS5-61-IJ-0001-CH05 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-24 13:01 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00022-3382 | PS5-61-IJ-0001-CH06 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-24 13:48 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00022-3410 | PS5-61-IU-0001A-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-18 12:59 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00022-3411 | PS5-61-IU-0001A-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-18 13:03 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00022-3412 | PS5-61-IU-0001A-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-18 13:06 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00022-3413 | PS5-61-IU-0001B-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-18 13:09 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00022-3414 | PS5-61-IU-0001B-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-18 13:11 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00022-3415 | PS5-61-IU-0001B-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-18 13:13 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-10536 | PS5-60-IN-0002A-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-10537 | PS5-60-IN-0002B-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-10593 | PS5-60-IH-0001A-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-10594 | PS5-60-IH-0001B-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-10600 | PS5-60-IH-0002-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-10601 | PS5-60-IH-0002-CG02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-10887 | PS5-60-BE-0007A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-10888 | PS5-60-BE-0007A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-10889 | PS5-60-BE-0007B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-10890 | PS5-60-BE-0007B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-10901 | PS5-60-ISO-62800A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-ISO-62800A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-4978 | PS5-60-BE-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-4979 | PS5-60-BE-0001-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-4981 | PS5-60-BE-0001-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-4982 | PS5-60-BE-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-4983 | PS5-60-BE-0002-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-4984 | PS5-60-BE-0002-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-4986 | PS5-60-BE-0002-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-4987 | PS5-60-BE-0003A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0003A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-4988 | PS5-60-BE-0003B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-4994 | PS5-60-BE-0004A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0004A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-4995 | PS5-60-BE-0004B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0004B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5001 | PS5-60-BE-0005A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0005A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5002 | PS5-60-BE-0005B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0005B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5008 | PS5-60-BE-0011A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5009 | PS5-60-BE-0011A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5010 | PS5-60-BE-0011A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5011 | PS5-60-BE-0011A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5012 | PS5-60-BE-0011A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5013 | PS5-60-BE-0011A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5014 | PS5-60-BE-0011B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5015 | PS5-60-BE-0011B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5016 | PS5-60-BE-0011B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5017 | PS5-60-BE-0011B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5018 | PS5-60-BE-0011B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5019 | PS5-60-BE-0011B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5020 | PS5-60-BE-0012A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5021 | PS5-60-BE-0012A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5022 | PS5-60-BE-0012A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5023 | PS5-60-BE-0012A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5024 | PS5-60-BE-0012A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5025 | PS5-60-BE-0012A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5026 | PS5-60-BE-0012B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5027 | PS5-60-BE-0012B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5028 | PS5-60-BE-0012B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5029 | PS5-60-BE-0012B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5030 | PS5-60-BE-0012B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5031 | PS5-60-BE-0012B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5092 | PS5-60-BE-0021A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0021A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5093 | PS5-60-BE-0021B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0021B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5094 | PS5-60-BE-0024A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0024A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5095 | PS5-60-BE-0024A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0024A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5096 | PS5-60-BE-0024B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0024B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5097 | PS5-60-BE-0024B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0024B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5108 | PS5-60-BE-0025A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0025A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5109 | PS5-60-BE-0025B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0025B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5115 | PS5-60-BE-0026A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0026A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5116 | PS5-60-BE-0026A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0026A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5117 | PS5-60-BE-0026B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0026B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5118 | PS5-60-BE-0026B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0026B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5129 | PS5-60-BI-0005A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0005A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5130 | PS5-60-BI-0005B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0005B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5136 | PS5-60-BI-0015A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5137 | PS5-60-BI-0015A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5138 | PS5-60-BI-0015A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5139 | PS5-60-BI-0015B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5140 | PS5-60-BI-0015B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5141 | PS5-60-BI-0015B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5157 | PS5-60-DD-62800A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-DD-62800A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5166 | PS5-60-IE-0002A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5167 | PS5-60-IE-0002A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5168 | PS5-60-IE-0002A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5169 | PS5-60-IE-0002B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5170 | PS5-60-IE-0002B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5171 | PS5-60-IE-0002B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5187 | PS5-60-IE-0003A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5188 | PS5-60-IE-0003A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5189 | PS5-60-IE-0003B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5190 | PS5-60-IE-0003B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5201 | PS5-60-IE-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5202 | PS5-60-IE-0004-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5204 | PS5-60-IH-0001A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5205 | PS5-60-IH-0001A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5206 | PS5-60-IH-0001A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5207 | PS5-60-IH-0001A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5208 | PS5-60-IH-0001A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5209 | PS5-60-IH-0001A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5211 | PS5-60-IH-0001B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5212 | PS5-60-IH-0001B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5213 | PS5-60-IH-0001B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5214 | PS5-60-IH-0001B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5215 | PS5-60-IH-0001B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5216 | PS5-60-IH-0001B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5254 | PS5-60-IH-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5255 | PS5-60-IH-0002-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5256 | PS5-60-IH-0002-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5257 | PS5-60-IH-0002-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5258 | PS5-60-IH-0002-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5259 | PS5-60-IH-0002-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5260 | PS5-60-IH-0002-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5261 | PS5-60-IH-0002-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5262 | PS5-60-IH-0002-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5263 | PS5-60-IH-0002-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5264 | PS5-60-IN-0001A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5265 | PS5-60-IN-0001B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5271 | PS5-60-IN-0002A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5272 | PS5-60-IN-0002A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5273 | PS5-60-IN-0002A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5274 | PS5-60-IN-0002B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-5275 | PS5-60-IN-0002B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-5276 | PS5-60-IN-0002B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-5292 | PS5-60-IWK-0001A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5293 | PS5-60-IWK-0001A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5294 | PS5-60-IWK-0001B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5295 | PS5-60-IWK-0001B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5296 | PS5-60-IWK-0001C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5297 | PS5-60-IWK-0001C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5298 | PS5-60-LA-0002A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5299 | PS5-60-LA-0002A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5302 | PS5-60-LA-0002C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00023-5303 | PS5-60-LA-0002C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00023-5304 | PS5-60-LA-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5305 | PS5-60-LA-0003-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5310 | PS5-60-SEA-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00023-5311 | PS5-60-SEA-0001-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00023-5312 | PS5-60-VS-9100A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-VS-9100A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5313 | PS5-60-VS-9100B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-VS-9100B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5319 | PS5-61-BI-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00023-5320 | PS5-61-BI-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-5581 | PS5-71-IN-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00023-5582 | PS5-71-IN-0002-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00023-5583 | PS5-71-IN-0002-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00023-5584 | PS5-71-IN-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00023-5585 | PS5-71-IN-0003-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00023-5586 | PS5-71-IN-0003-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00023-5594 | PS5-71-MOV-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00023-5595 | PS5-71-MOV-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00023-5596 | PS5-71-MOV-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00023-5597 | PS5-71-MOV-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00023-5599 | PS5-71-MOV-0008-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0008 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00023-5601 | PS5-71-MOV-0010-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0010 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00023-9131 | PS5-60-BE-0007A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-9132 | PS5-60-BE-0007B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-9138 | PS5-60-BE-0027A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0027A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-9139 | PS5-60-BE-0027B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0027B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-9145 | PS5-60-BE-0028A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0028A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-9146 | PS5-60-BE-0028B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0028B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-9152 | PS5-60-BI-0006A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-9153 | PS5-60-BI-0006A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-9154 | PS5-60-BI-0006A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-9155 | PS5-60-BI-0006A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-9156 | PS5-60-BI-0006A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-9157 | PS5-60-BI-0006A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-9158 | PS5-60-BI-0006A-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-9159 | PS5-60-BI-0006A-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-9160 | PS5-60-BI-0006A-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-9161 | PS5-60-BI-0006A-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-9162 | PS5-60-BI-0006A-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-9163 | PS5-60-BI-0006B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-9164 | PS5-60-BI-0006B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-9165 | PS5-60-BI-0006B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-9166 | PS5-60-BI-0006B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-9167 | PS5-60-BI-0006B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-9168 | PS5-60-BI-0006B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-9169 | PS5-60-BI-0006B-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-9170 | PS5-60-BI-0006B-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-9171 | PS5-60-BI-0006B-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-9172 | PS5-60-BI-0006B-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-9173 | PS5-60-BI-0006B-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-9229 | PS5-60-BI-0017A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0017A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-9230 | PS5-60-BI-0017B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0017B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-9236 | PS5-60-EA-2900A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-EA-2900A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00023-9237 | PS5-60-EA-2900B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-EA-2900B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00023-9244 | PS5-71-BE-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00023-9245 | PS5-71-BE-0004-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00023-9246 | PS5-71-BE-0004-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00023-9247 | PS5-71-BI-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00023-9248 | PS5-71-BI-0003-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00023-9249 | PS5-71-BI-0003-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00023-9250 | PS5-71-BI-0003-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00023-9251 | PS5-71-BI-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00023-9252 | PS5-71-BI-0005-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00023-9253 | PS5-71-BI-0005-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00023-9254 | PS5-71-BI-0005-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00023-9255 | PS5-71-BI-0006-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0006 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00024-2101 | PS5-60-IE-0002A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00024-2102 | PS5-60-IE-0002A-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00024-2103 | PS5-60-IE-0002A-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00024-2104 | PS5-60-IE-0002B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00024-2105 | PS5-60-IE-0002B-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00024-2106 | PS5-60-IE-0002B-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00024-2123 | PS5-60-IE-0003A-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00024-2124 | PS5-60-IE-0003A-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00024-2125 | PS5-60-IE-0003A-CD04 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0005A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00024-2126 | PS5-60-IE-0003A-CD05 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00024-2135 | PS5-60-IE-0003A-CD14 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00024-2136 | PS5-60-IE-0003A-CD15 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00024-2138 | PS5-60-IE-0003B-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00024-2139 | PS5-60-IE-0003B-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00024-2140 | PS5-60-IE-0003B-CD04 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0005B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00024-2141 | PS5-60-IE-0003B-CD05 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00024-2150 | PS5-60-IE-0003B-CD14 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00024-2151 | PS5-60-IE-0003B-CD15 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00034-0059 | PS5-60-IJ-0001A |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Neutral Grounding resistor for Generator set 1 (A) | EACOP | CPP AGI |  |  | 8 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00034-0060 | PS5-60-IJ-0001B |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Neutral Grounding resistor for Generator set 2 (B) | EACOP | CPP AGI |  |  | 8 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00039-0295 | PS5 - POWER DISTRIBUTION AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  | 10 | TZ-MID-68-WPR2-151148 | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 |  |  | Earthing System | E | Submitted | PS5 - Milestone A | 2026-07-20 | Priority-1
T-00039-0296 | PS5 - POWER GENERATION BUILDING AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-151152 | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 |  |  | Earthing System | E | Submitted | PS5 - Milestone A | 2026-07-20 | Priority-1
T-00039-0297 | PS5 - POWER GENERATION COOLING TOWER AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-151154 | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 |  |  | Earthing System | E | Submitted | PS5 - Milestone A | 2026-07-20 | Priority-1
T-00039-0309 | PS5-84-OB-0005_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing for Generator Electrical Building | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-151181 | PS5 - TZA - PS5 - Tanzania | PS5-63-03 - Electrical Earthing - Generator Building |  | PS5-63-03 |  |  | Earthing System | E | To be completed | PS5 - Milestone B | 2026-06-21 | Priority-1
T-00044-0090 | PS5-60-IE-0003A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GCP G-1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00044-0091 | PS5-60-IE-0003B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GCP G-2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00044-0097 | PS5-60-IE-0004 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | MCP- MASTER CONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00044-0098 | PS5-60-IH-0001A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENSET MCC -1 - G1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00044-0099 | PS5-60-IH-0001B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENSET MCC -2 - G2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00044-0105 | PS5-60-IH-0002 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COMMON / TREATMENT MCC | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00044-0106 | PS5-60-IE-0002A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00044-0107 | PS5-60-IE-0002B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00044-0185 | PS5-60-IN-0002A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00044-0186 | PS5-60-IN-0002B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00044-0198 | PS5-71-IN-0002 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRO-PRE PRESSURECONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00044-0199 | PS5-71-IN-0003 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | DFO- PRE PRESSURE CONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Console / Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00046-0291 | PS5-60-UR-8100A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION PACKAGE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00046-0292 | PS5-60-UR-8100B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION PACKAGE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00046-0300 | PS5-60-UA-5100 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COMPRESSOR AIR STARTING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135128 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00046-0301 | PS5-60-UO-81100A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00046-0302 | PS5-60-UO-81100B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00046-0308 | PS5-60-UZ-8200A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00046-0309 | PS5-60-UZ-8200B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00046-0314 | PS5-60-VS-9100A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00046-0315 | PS5-60-VS-9100B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00046-0322 | PS5-71-UZ-6800A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE FUEL SEPARATOR MODULE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135002 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Package | M | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00046-0323 | PS5-71-UZ-6800B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE FUEL SEPARATOR MODULE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135002 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Package | M | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00046-0327 | PS5-60-EA-2100A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00046-0328 | PS5-60-EA-2100B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00046-0329 | PS5-60-EA-21100A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00046-0330 | PS5-60-EA-21100B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00046-0336 | PS5-60-EA-21200A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00046-0337 | PS5-60-EA-21200B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00046-0343 | PS5-60-EA-2200A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00046-0344 | PS5-60-EA-2200B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00046-0355 | PS5-60-EA-2800A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00046-0356 | PS5-60-EA-2800B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00046-0362 | PS5-60-EA-2900A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00046-0363 | PS5-60-EA-2900B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00046-0369 | PS5-60-TCV-0001A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00046-0370 | PS5-60-TCV-0001B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00046-0376 | PS5-60-TCV-0002A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00046-0377 | PS5-60-TCV-0002B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00046-0383 | PS5-60-UA-5200 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INSTRUMENT AIR COMPRESSOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135127 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00046-0384 | PS5-60-UR-8200A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00046-0385 | PS5-60-UR-8200B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00046-0392 | PS5-60-UZ-8900A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00046-0393 | PS5-60-UZ-8900B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00046-0400 | PS5-71-UZ-6400 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135004 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Package | M | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00046-0401 | PS5-71-UZ-6700 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | DIESEL FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135126 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00046-0552 | PS5-60-UR-8300A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00046-0553 | PS5-60-UR-8300B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-12948 | PS5-60-BI-0001A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-12949 | PS5-60-BI-0001B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-12955 | PS5-60-BI-0003-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-12956 | PS5-60-IE-0002A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-12957 | PS5-60-IE-0002A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-12958 | PS5-60-IE-0002A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-12959 | PS5-60-IE-0002B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-12960 | PS5-60-IE-0002B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-12961 | PS5-60-IE-0002B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-12977 | PS5-60-IH-0001A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-12978 | PS5-60-IH-0001A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-12979 | PS5-60-IH-0001B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-12980 | PS5-60-IH-0001B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-12991 | PS5-60-IH-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-12992 | PS5-60-IH-0002-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-12993 | PS5-60-LA-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-12994 | PS5-60-LA-0003-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-12995 | PS5-60-PIT-8113A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BE-0027A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-12996 | PS5-60-PIT-8113B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BE-0027B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00069-13002 | PS5-60-PIT-8114A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BE-0027A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-13003 | PS5-60-PIT-8114B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BE-0027B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00069-4888 | PS5-60-BE-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-4889 | PS5-60-BE-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-4890 | PS5-60-BE-0004A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0001A TO PS5-60-BE-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-4891 | PS5-60-BE-0004B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0001B TO PS5-60-BE-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-4897 | PS5-60-BI-0001A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-4898 | PS5-60-BI-0001A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-4899 | PS5-60-BI-0001B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-4900 | PS5-60-BI-0001B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-4911 | PS5-60-BI-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-4912 | PS5-60-BI-0002-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-4913 | PS5-60-BI-0002-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-4914 | PS5-60-BI-0002-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-4915 | PS5-60-BI-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-4916 | PS5-60-BI-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-4917 | PS5-60-BI-0004A-CCO1 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-4918 | PS5-60-BI-0004B-CCO1 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-4924 | PS5-60-BI-0005A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0005A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-4925 | PS5-60-BI-0005A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0005A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-4926 | PS5-60-BI-0005B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0005B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-4927 | PS5-60-BI-0005B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0005B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-4938 | PS5-60-BI-0006A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-4939 | PS5-60-BI-0006A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-4940 | PS5-60-BI-0006A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-4941 | PS5-60-BI-0006A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-4942 | PS5-60-BI-0006A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-4943 | PS5-60-BI-0006A-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-4944 | PS5-60-BI-0006B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-4945 | PS5-60-BI-0006B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00069-4946 | PS5-60-BI-0006B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00069-4947 | PS5-60-BI-0006B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00069-4948 | PS5-60-BI-0006B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00069-4949 | PS5-60-BI-0006B-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00069-4980 | PS5-60-BI-0008A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-4981 | PS5-60-BI-0008A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-4982 | PS5-60-BI-0008B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-4983 | PS5-60-BI-0008B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-4984 | PS5-60-BI-0009A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0009A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-4985 | PS5-60-BI-0009A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0009A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-4986 | PS5-60-BI-0009B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0009B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-4987 | PS5-60-BI-0009B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0009B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5008 | PS5-60-BI-0016A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5009 | PS5-60-BI-0016A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5010 | PS5-60-BI-0016A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5011 | PS5-60-BI-0016A-CCO4 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5012 | PS5-60-BI-0016B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5013 | PS5-60-BI-0016B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5014 | PS5-60-BI-0016B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5015 | PS5-60-BI-0016B-CCO4 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5036 | PS5-60-BI-0017A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0017A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5037 | PS5-60-BI-0017B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0017B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00069-5043 | PS5-60-BI-0019A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0019A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5044 | PS5-60-BI-0019A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0019A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5045 | PS5-60-BI-0019B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0019B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5046 | PS5-60-BI-0019B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0019B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5057 | PS5-60-IE-0002B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5063 | PS5-60-IE-0003A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5064 | PS5-60-IE-0003A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5065 | PS5-60-IE-0003A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5066 | PS5-60-IE-0003A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5067 | PS5-60-IE-0003A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5068 | PS5-60-IE-0003A-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5069 | PS5-60-IE-0003A-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5070 | PS5-60-IE-0003A-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5071 | PS5-60-IE-0003A-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5072 | PS5-60-IE-0003A-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5073 | PS5-60-IE-0003A-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5074 | PS5-60-IE-0003A-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5075 | PS5-60-IE-0003A-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5076 | PS5-60-IE-0003A-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5081 | PS5-60-IE-0003A-CC25 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41100A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5082 | PS5-60-IE-0003A-CC26 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41100B TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5083 | PS5-60-IE-0003B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5084 | PS5-60-IE-0003B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5085 | PS5-60-IE-0003B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5086 | PS5-60-IE-0003B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5087 | PS5-60-IE-0003B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5088 | PS5-60-IE-0003B-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5089 | PS5-60-IE-0003B-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5090 | PS5-60-IE-0003B-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5091 | PS5-60-IE-0003B-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5092 | PS5-60-IE-0003B-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5093 | PS5-60-IE-0003B-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5094 | PS5-60-IE-0003B-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5095 | PS5-60-IE-0003B-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5096 | PS5-60-IE-0003B-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5101 | PS5-60-IE-0003B-CC25 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41200A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5102 | PS5-60-IE-0003B-CC26 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-TX-41200B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5203 | PS5-60-IE-0004-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5204 | PS5-60-IE-0004-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5205 | PS5-60-IE-0004-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5206 | PS5-60-IE-0004-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5207 | PS5-60-IE-0004-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5208 | PS5-60-IE-0004-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5209 | PS5-60-IE-0004-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5213 | PS5-60-IN-0001A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5214 | PS5-60-IN-0001A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5215 | PS5-60-IN-0001A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5216 | PS5-60-IN-0001A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5217 | PS5-60-IN-0001B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5218 | PS5-60-IN-0001B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5219 | PS5-60-IN-0001B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5220 | PS5-60-IN-0001B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5241 | PS5-60-IN-0002A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5242 | PS5-60-IN-0002A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5243 | PS5-60-IN-0002A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5244 | PS5-60-IN-0002A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5245 | PS5-60-IN-0002A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5246 | PS5-60-IN-0002A-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5247 | PS5-60-IN-0002B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00069-5248 | PS5-60-IN-0002B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00069-5249 | PS5-60-IN-0002B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00069-5250 | PS5-60-IN-0002B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00069-5251 | PS5-60-IN-0002B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00069-5252 | PS5-60-IN-0002B-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00069-5284 | PS5-60-LA-0002A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5285 | PS5-60-LA-0002A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5286 | PS5-60-LA-0002A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5287 | PS5-60-LA-0002A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5288 | PS5-60-LA-0002A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5289 | PS5-60-LA-0002A-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5290 | PS5-60-LA-0002A-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5291 | PS5-60-LA-0002A-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5292 | PS5-60-LA-0002A-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5299 | PS5-60-LA-0002C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00069-5300 | PS5-60-LA-0002C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00069-5301 | PS5-60-LA-0002C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00069-5302 | PS5-60-LA-0002C-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00069-5303 | PS5-60-LA-0002C-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00069-5304 | PS5-60-LA-0002C-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00069-5305 | PS5-60-LA-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5316 | PS5-60-SEA-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00069-5317 | PS5-60-SEA-0001-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00069-5318 | PS5-60-SEA-0001-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00069-5319 | PS5-60-SEA-0001-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00069-5320 | PS5-60-SEA-0001-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00069-5321 | PS5-60-SEA-0001-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00069-5322 | PS5-60-SEA-0001-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00069-5323 | PS5-60-SEA-0001-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00069-5324 | PS5-60-SEA-0001-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00069-5325 | PS5-60-SEA-0001-CC12 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00069-5326 | PS5-60-SEA-0001-CC13 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00069-5327 | PS5-60-SEA-0001-CC14 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00069-5328 | PS5-60-SEA-0001-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00069-5329 | PS5-60-SEA-0001-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00069-5330 | PS5-60-SEA-0001-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00069-5339 | PS5-60-VS-9101A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-VS-9101A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5340 | PS5-60-VS-9101B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-VS-9101B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5346 | PS5-61-BI-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5347 | PS5-61-BI-0001-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5348 | PS5-61-BI-0001-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-61-TE-0003A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00069-5349 | PS5-61-BI-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5350 | PS5-61-BI-0002-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5351 | PS5-61-BI-0002-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-61-TE-0003B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00069-5378 | PS5-71-BI-0001A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5379 | PS5-71-BI-0001B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5382 | PS5-71-BI-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5383 | PS5-71-BI-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5384 | PS5-71-BI-0003-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5385 | PS5-71-BI-0003-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5386 | PS5-71-BI-0004-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5387 | PS5-71-BI-0005-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00069-5388 | PS5-71-BI-0005-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00069-5389 | PS5-71-BI-0006-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00069-5390 | PS5-71-BI-0008A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5391 | PS5-71-BI-0008A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5392 | PS5-71-BI-0008B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5393 | PS5-71-BI-0008B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5399 | PS5-71-BI-0011A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5400 | PS5-71-BI-0011A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5401 | PS5-71-BI-0011A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5402 | PS5-71-BI-0011A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5403 | PS5-71-BI-0011A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5404 | PS5-71-BI-0011B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5405 | PS5-71-BI-0011B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5406 | PS5-71-BI-0011B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5407 | PS5-71-BI-0011B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5408 | PS5-71-BI-0011B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5467 | PS5-71-IN-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5468 | PS5-71-IN-0002-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5469 | PS5-71-IN-0002-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5470 | PS5-71-IN-0002-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5474 | PS5-71-IN-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00069-5475 | PS5-71-IN-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00069-5476 | PS5-71-IN-0003-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00069-5477 | PS5-71-IN-0003-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00069-5516 | PS5-71-MOV-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2120 TO PS5-71-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5517 | PS5-71-MOV-0001-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2124 TO PS5-71-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5518 | PS5-71-MOV-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2120 TO PS5-71-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00069-5519 | PS5-71-MOV-0002-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2124 TO PS5-71-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00069-5520 | PS5-71-MOV-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2121 TO PS5-71-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5521 | PS5-71-MOV-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2125 TO PS5-71-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5522 | PS5-71-MOV-0004-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2121 TO PS5-71-MOV-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00069-5523 | PS5-71-MOV-0004-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2125 TO PS5-71-MOV-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00069-5524 | PS5-71-MOV-0007-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2118 TO PS5-71-MOV-0007 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5525 | PS5-71-MOV-0007-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2122 TO PS5-71-MOV-0007 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5526 | PS5-71-MOV-0008-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2118 TO PS5-71-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00069-5527 | PS5-71-MOV-0008-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2122 TO PS5-71-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00069-5528 | PS5-71-MOV-0009-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2119 TO PS5-71-MOV-0009 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5529 | PS5-71-MOV-0009-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2123 TO PS5-71-MOV-0009 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00069-5530 | PS5-71-MOV-0010-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2119 TO PS5-71-MOV-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00069-5531 | PS5-71-MOV-0010-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-71-BI-2123 TO PS5-71-MOV-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00071-0027 | PS5-60-IE-0004-CX03 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-SSF1-161401 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00071-0028 | PS5-60-IE-0004-CX04 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-SSF1-161401 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00071-0029 | PS5-60-LA-0003-CX01 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-SSF1-161401 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00071-0090 | PS5-60-LA-0003-CX02 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00072-0173 | PS5-60-TW-0007B |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Thermowell | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00072-0175 | PS5-60-TW-0008A |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Thermowell | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00072-0182 | PS5-60-TW-0007A |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Thermowell | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00072-0184 | PS5-60-TW-0008B |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Thermowell | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00072-0194 | PS5-60-TW-0006B |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Thermowell | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00072-0198 | PS5-60-TW-0006A |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Thermowell | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00072-0207 | PS5-60-TW-0005A |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Thermowell | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00072-0208 | PS5-60-TW-0005B |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Thermowell | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00075-0211 | PS5-60-TG-0005A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00075-0218 | PS5-60-TG-0008A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00075-0239 | PS5-60-TG-0007A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00075-0265 | PS5-60-TG-0006A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00075-0270 | PS5-60-TG-0006B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00075-0271 | PS5-60-TG-0005B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00075-0272 | PS5-60-TG-0007B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00075-0273 | PS5-60-TG-0008B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Local Gauge/Indicator | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00078-0140 | PS5-71-MOV-0007 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00078-0143 | PS5-71-MOV-0010 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00078-0144 | PS5-71-MOV-0003 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00078-0147 | PS5-71-MOV-0004 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00078-0149 | PS5-71-MOV-0001 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00078-0151 | PS5-71-MOV-0002 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00078-0152 | PS5-71-MOV-0008 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00078-0153 | PS5-71-MOV-0009 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135138 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Actuated on/off Valve | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00082-0460 | PS5-01-BI-1117 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 07:55 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0461 | PS5-01-BI-1118 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 07:56 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0463 | PS5-01-BI-1515 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 07:57 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0466 | PS5-01-BI-2110 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 07:58 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0484 | PS5-03-BI-2503 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-19 04:59 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0487 | PS5-03-BI-2506 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  | 1 | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-19 05:03 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0490 | PS5-03-BI-2509 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:00 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0494 | PS5-03-BI-2514 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-19 05:04 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0495 | PS5-03-BI-2515 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:01 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0500 | PS5-25-BI-1101 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:01 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0501 | PS5-25-BI-1102 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:02 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0502 | PS5-25-BI-1103 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:38 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0503 | PS5-25-BI-1104 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:16 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0504 | PS5-25-BI-1115 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:41 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0508 | PS5-25-BI-1201 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:41 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0512 | PS5-25-BI-1301 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:42 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0513 | PS5-25-BI-1302 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:16 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0514 | PS5-25-BI-1310 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:17 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0517 | PS5-25-BI-2103 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:03 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0518 | PS5-25-BI-2104 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  | Junction and Marshalling Box | I | Submitted | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0519 | PS5-25-BI-2105 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:42 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0520 | PS5-25-BI-2106 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:18 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0521 | PS5-25-BI-2108 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:19 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0522 | PS5-25-BI-2109 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:19 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0523 | PS5-25-BI-2201 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-05-30 12:03 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0524 | PS5-25-BI-2203 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-05-30 12:02 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0526 | PS5-25-BI-2301 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:43 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0527 | PS5-25-BI-2302 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:44 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0528 | PS5-25-BI-2305 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:20 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0529 | PS5-25-BI-2308 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:21 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0530 | PS5-25-BI-2309 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:44 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0531 | PS5-25-BI-2312 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:21 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0532 | PS5-25-BI-2315 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:20 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0533 | PS5-25-BI-2316 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:19 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0534 | PS5-28-BI-1105 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-19 04:59 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0537 | PS5-28-BI-1303 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:05 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0538 | PS5-28-BI-1307 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:05 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0540 | PS5-50-BI-1107 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:07 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0541 | PS5-53-BI-1108 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  | Junction and Marshalling Box | I | Submitted | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0543 | PS5-71-BI-1109 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-05-30 12:05 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0544 | PS5-71-BI-1110 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:45 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0545 | PS5-71-BI-1111 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:18 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0547 | PS5-71-BI-1113 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:17 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0548 | PS5-71-BI-1116 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:16 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0549 | PS5-71-BI-1117 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:46 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0550 | PS5-71-BI-1305 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-05-30 12:04 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0551 | PS5-71-BI-1306 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:15 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0553 | PS5-71-BI-2101 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:46 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0554 | PS5-71-BI-2107 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:48 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0555 | PS5-71-BI-2113 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:13 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0556 | PS5-71-BI-2114 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:12 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0557 | PS5-71-BI-2115 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:12 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0558 | PS5-71-BI-2116 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:07 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0559 | PS5-71-BI-2118 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:10 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0560 | PS5-71-BI-2119 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:08 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0561 | PS5-71-BI-2120 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:08 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0562 | PS5-71-BI-2121 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-19 05:05 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0563 | PS5-71-BI-2122 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:09 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0564 | PS5-71-BI-2123 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:09 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0565 | PS5-71-BI-2124 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:09 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0566 | PS5-71-BI-2125 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-19 05:05 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0567 | PS5-71-BI-2306 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-01 13:23 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0569 | PS5-71-BI-2310 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-12 08:10 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00082-0571 | PS5-71-BI-2314 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-04 17:49 | PS5-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00087-0105 | PS5-60-SEA-0001 |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTION PANEL | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-121106 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Indoor Cabinet/Panel | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00087-0500 | PS5-60-LA-0002A |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | VTMS VIBRATION AND TEMPERATURE MONITORING SYSTEM | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Indoor Cabinet/Panel | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00087-0501 | PS5-60-LA-0002B |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | VTMS VIBRATION AND TEMPERATURE MONITORING SYSTEM | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Indoor Cabinet/Panel | I | To be completed | PS5 - Milestone D | 2026-07-30 | Priority-1
T-00087-0502 | PS5-60-LA-0002C |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | VTMS VIBRATION AND TEMPERATURE MONITORING SYSTEM | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Indoor Cabinet/Panel | I | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00087-0528 | PS5-60-LA-0003 |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Remote Access Panel | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Indoor Cabinet/Panel | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00090-0179 | PS5-60-UR-8100A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION PACKAGE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00090-0180 | PS5-60-UR-8100B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION PACKAGE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00090-0188 | PS5-60-UA-5100 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COMPRESSOR AIR STARTING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135128 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00090-0189 | PS5-60-UO-81100A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00090-0190 | PS5-60-UO-81100B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00090-0196 | PS5-60-UZ-8200A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00090-0197 | PS5-60-UZ-8200B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00090-0202 | PS5-60-VS-9100A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00090-0203 | PS5-60-VS-9100B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00090-0210 | PS5-71-UZ-6800A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CRUDE FUEL SEPARATOR MODULE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135002 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Package | M | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00090-0211 | PS5-71-UZ-6800B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CRUDE FUEL SEPARATOR MODULE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135002 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Package | M | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00090-0215 | PS5-60-EA-2100A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00090-0216 | PS5-60-EA-2100B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00090-0217 | PS5-60-EA-21100A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00090-0218 | PS5-60-EA-21100B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00090-0224 | PS5-60-EA-21200A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00090-0225 | PS5-60-EA-21200B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00090-0231 | PS5-60-EA-2200A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00090-0232 | PS5-60-EA-2200B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00090-0243 | PS5-60-EA-2800A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00090-0244 | PS5-60-EA-2800B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00090-0250 | PS5-60-EA-2900A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00090-0251 | PS5-60-EA-2900B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00090-0257 | PS5-60-TCV-0001A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00090-0258 | PS5-60-TCV-0001B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00090-0264 | PS5-60-TCV-0002A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00090-0265 | PS5-60-TCV-0002B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00090-0271 | PS5-60-UA-5200 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INSTRUMENT AIR COMPRESSOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135127 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00090-0272 | PS5-60-UR-8200A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00090-0273 | PS5-60-UR-8200B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00090-0280 | PS5-60-UZ-8900A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00090-0281 | PS5-60-UZ-8900B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00090-0288 | PS5-71-UZ-6400 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CRUDE FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135004 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Package | M | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00090-0289 | PS5-71-UZ-6700 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DIESEL FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135126 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00090-0436 | PS5-60-UR-8300A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00090-0437 | PS5-60-UR-8300B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Package | M | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00115-0006 | PS5-60-YF-1700A |  |  |  |  | CHX01 - Strainer / Filter | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL FITLER SE - LOOSE / REMOTE MOUNTED | EACOP | CPP AGI |  |  | 5 |  |  | TZ-MID-68-WPR2-135134 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-03-30 12:07 | PS5-60-56 |  |  | Strainer/Filter | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00115-0007 | PS5-60-YF-1700B |  |  |  |  | CHX01 - Strainer / Filter | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL FITLER SE - LOOSE / REMOTE MOUNTED | EACOP | CPP AGI |  |  | 5 |  |  | TZ-MID-68-WPR2-135134 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-03-30 12:08 | PS5-60-58 |  |  | Strainer/Filter | M | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00135-0220 | PS5-60-UR-8100A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-14 05:32 | PS5-60-01 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00135-0221 | PS5-60-UR-8100B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-14 05:33 | PS5-60-04 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00135-0229 | PS5-60-UA-5100 |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COMPRESSOR AIR STARTING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135128 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-04-13 06:58 | PS5-60-27 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00135-0230 | PS5-60-UO-81100A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2026-01-24 12:49 | PS5-60-49 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00135-0231 | PS5-60-UO-81100B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2026-01-24 12:50 | PS5-60-50 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00135-0237 | PS5-60-UZ-8200A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-01-24 12:55 | PS5-60-35 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00135-0238 | PS5-60-UZ-8200B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-01-24 12:55 | PS5-60-36 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00135-0243 | PS5-60-VS-9100A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-03-30 11:55 | PS5-60-42 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00135-0244 | PS5-60-VS-9100B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-03-30 11:57 | PS5-60-43 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00135-0251 | PS5-71-UZ-6800A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | CRUDE FUEL SEPARATOR MODULE A | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135002 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-04-23 10:29 | PS5-71-06 |  |  | Package | M | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00135-0252 | PS5-71-UZ-6800B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | CRUDE FUEL SEPARATOR MODULE B | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135002 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-04-23 10:29 | PS5-71-06 |  |  | Package | M | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00135-0256 | PS5-60-EA-2100A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-30 13:48 | PS5-60-70 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00135-0257 | PS5-60-EA-2100B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-30 13:49 | PS5-60-70 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00135-0258 | PS5-60-EA-21100A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-04 07:38 | PS5-60-01 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00135-0259 | PS5-60-EA-21100B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-04 10:58 | PS5-60-04 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00135-0265 | PS5-60-EA-21200A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-05 11:22 | PS5-60-01 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00135-0266 | PS5-60-EA-21200B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-05 11:22 | PS5-60-04 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00135-0272 | PS5-60-EA-2200A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-30 13:50 | PS5-60-71 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00135-0273 | PS5-60-EA-2200B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-30 13:51 | PS5-60-71 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00135-0284 | PS5-60-EA-2800A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-04-25 08:26 | PS5-60-35 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00135-0285 | PS5-60-EA-2800B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-04-25 08:27 | PS5-60-36 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00135-0291 | PS5-60-EA-2900A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-04-05 11:24 | PS5-60-56 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00135-0292 | PS5-60-EA-2900B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-04-05 11:25 | PS5-60-58 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00135-0298 | PS5-60-TCV-0001A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-14 10:24 | PS5-60-70 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00135-0299 | PS5-60-TCV-0001B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-05-14 10:25 | PS5-60-71 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00135-0305 | PS5-60-TCV-0002A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-14 10:27 | PS5-60-70 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00135-0306 | PS5-60-TCV-0002B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-05-14 10:28 | PS5-60-71 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00135-0312 | PS5-60-UA-5200 |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INSTRUMENT AIR COMPRESSOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135127 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-04-13 06:59 | PS5-60-26 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00135-0313 | PS5-60-UR-8200A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-13 07:07 | PS5-60-01 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00135-0314 | PS5-60-UR-8200B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-13 07:08 | PS5-60-04 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00135-0321 | PS5-60-UZ-8900A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-03-28 07:29 | PS5-60-56 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00135-0322 | PS5-60-UZ-8900B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-01-24 12:59 | PS5-60-58 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00135-0329 | PS5-71-UZ-6400 |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | CRUDE FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135004 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-04-23 10:30 | PS5-71-08 |  |  | Package | M | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00135-0330 | PS5-71-UZ-6700 |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | DIESEL FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135126 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-04-23 10:30 | PS5-71-22 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00135-0465 | PS5-60-UR-8300A |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-04-18 05:28 | PS5-60-35 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00135-0466 | PS5-60-UR-8300B |  |  |  |  | CZX01M - Package | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-04-18 05:28 | PS5-60-36 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00140-0065 | PS5-60-TX-41100A |  |  |  |  | CDX01 - Storage tank | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING WATER EXPANSION TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-68-WPR2-135131 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Storage Tank | P | Started (not Completed) | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00140-0066 | PS5-60-TX-41100B |  |  |  |  | CDX01 - Storage tank | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING WATER EXPANSION TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-68-WPR2-135132 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Storage Tank | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00140-0067 | PS5-60-TX-41200A |  |  |  |  | CDX01 - Storage tank | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING WATER EXPANSION TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-68-WPR2-135131 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Storage Tank | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00140-0068 | PS5-60-TX-41200B |  |  |  |  | CDX01 - Storage tank | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING WATER EXPANSION TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-68-WPR2-135132 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Storage Tank | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00141-0132 | PS5-60-01_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Pipework | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00141-0133 | PS5-60-04_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Pipework | P | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00141-0142 | PS5-60-26_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | Pipework | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00141-0143 | PS5-60-27_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Pipework | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00141-0151 | PS5-60-35_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Pipework | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00141-0152 | PS5-60-36_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Pipework | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00141-0158 | PS5-60-42_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Pipework | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00141-0159 | PS5-60-43_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Pipework | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00141-0165 | PS5-60-49_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Pipework | P | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00141-0166 | PS5-60-50_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Pipework | P | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00141-0172 | PS5-60-56_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Pipework | P | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00141-0173 | PS5-60-58_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Pipework | P | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00141-0179 | PS5-60-70_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Pipework | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00141-0180 | PS5-60-71_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Pipework | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00141-0190 | PS5-71-06_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Pipework | P | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00141-0191 | PS5-71-08_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Pipework | P | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00141-0201 | PS5-71-22_SS_ALL_LINES |  |  |  |  | CLX02 - Pipework | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Pipework | P | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00146-0173 | PS5-60-UR-8100A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION PACKAGE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-09 11:47 | PS5-60-01 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0174 | PS5-60-UR-8100B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION PACKAGE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-09 11:51 | PS5-60-04 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00146-0182 | PS5-60-UA-5100 |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COMPRESSOR AIR STARTING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135128 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-06-09 11:52 | PS5-60-27 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0183 | PS5-60-UO-81100A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2026-06-09 11:53 | PS5-60-49 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00146-0184 | PS5-60-UO-81100B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135124 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2026-06-09 11:56 | PS5-60-50 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00146-0190 | PS5-60-UZ-8200A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-06-09 11:57 | PS5-60-35 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0191 | PS5-60-UZ-8200B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-06-09 11:58 | PS5-60-36 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0196 | PS5-60-VS-9100A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-06-09 11:58 | PS5-60-42 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0197 | PS5-60-VS-9100B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135130 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-06-09 11:59 | PS5-60-43 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0204 | PS5-71-UZ-6800A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | CRUDE FUEL SEPARATOR MODULE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135002 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-06-12 10:53 | PS5-71-06 |  |  | Package | M | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00146-0205 | PS5-71-UZ-6800B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | CRUDE FUEL SEPARATOR MODULE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135002 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-06-12 10:54 | PS5-71-06 |  |  | Package | M | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00146-0209 | PS5-60-EA-2100A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-07-02 11:47 | PS5-60-70 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0210 | PS5-60-EA-2100B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-07-02 11:49 | PS5-60-70 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0211 | PS5-60-EA-21100A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-09 11:59 | PS5-60-01 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0212 | PS5-60-EA-21100B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-09 12:00 | PS5-60-04 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00146-0218 | PS5-60-EA-21200A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-09 12:01 | PS5-60-01 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0219 | PS5-60-EA-21200B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-09 12:02 | PS5-60-04 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00146-0225 | PS5-60-EA-2200A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-07-02 11:50 | PS5-60-71 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0226 | PS5-60-EA-2200B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135122 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-07-02 11:51 | PS5-60-71 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0237 | PS5-60-EA-2800A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-06-09 12:02 | PS5-60-35 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0238 | PS5-60-EA-2800B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-06-09 12:03 | PS5-60-36 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0244 | PS5-60-EA-2900A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-06-09 12:03 | PS5-60-56 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00146-0245 | PS5-60-EA-2900B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | COOLING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-06-09 12:08 | PS5-60-58 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00146-0251 | PS5-60-TCV-0001A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-09 12:09 | PS5-60-70 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0252 | PS5-60-TCV-0001B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135136 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-09 12:11 | PS5-60-71 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0258 | PS5-60-TCV-0002A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-09 12:12 | PS5-60-70 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0259 | PS5-60-TCV-0002B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135137 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-09 12:13 | PS5-60-71 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0265 | PS5-60-UA-5200 |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | INSTRUMENT AIR COMPRESSOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135127 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-09 12:13 | PS5-60-26 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0266 | PS5-60-UR-8200A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-09 12:14 | PS5-60-01 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0267 | PS5-60-UR-8200B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-09 12:15 | PS5-60-04 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00146-0274 | PS5-60-UZ-8900A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-06-09 12:15 | PS5-60-56 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00146-0275 | PS5-60-UZ-8900B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135123 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-06-09 12:16 | PS5-60-58 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00146-0282 | PS5-71-UZ-6400 |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | CRUDE FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135004 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-06-12 10:50 | PS5-71-08 |  |  | Package | M | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00146-0283 | PS5-71-UZ-6700 |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | DIESEL FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135126 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-06-09 12:16 | PS5-71-22 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00146-0418 | PS5-60-UR-8300A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-06-09 12:17 | PS5-60-35 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0419 | PS5-60-UR-8300B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-68-WPR2-135129 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-06-09 12:18 | PS5-60-36 |  |  | Package | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00146-0449 | PS5-60-SPZQ-0081A |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Sample Connection - Type 5 | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135134 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Package | P | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00146-0450 | PS5-60-SPZQ-0081B |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Sample Connection - Type 5 | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135134 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Package | P | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00146-0461 | PS5-71-SPZQ-0070 |  |  |  |  | CZX01P - Package | PCOM - Precommissioning | P | Conformity Check | P - Piping & Vessel | Sample Connection - Type 4 | EACOP | CPP AGI |  |  | 20 |  | 20 | TZ-MID-68-WPR2-135010 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Package | P | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00171-4342 | PS5-60-IE-0003B-CA02 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00171-4343 | PS5-60-IE-0003B-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00171-4344 | PS5-60-IE-0003B-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00171-4345 | PS5-60-IE-0003B-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00171-4365 | PS5-60-IE-0004-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00171-4366 | PS5-60-IE-0004-CA07 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00171-4367 | PS5-60-IE-0004-CA08 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00171-4368 | PS5-60-IE-0004-CA14 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00171-4369 | PS5-60-IE-0004-CA15 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00171-4370 | PS5-60-IE-0004-CA21 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00171-4371 | PS5-60-IH-0001A-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00171-4372 | PS5-60-IH-0001B-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0001B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00171-4378 | PS5-60-IN-0001A-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00171-4379 | PS5-60-IN-0001B-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00171-4385 | PS5-60-IN-0002A-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00171-4386 | PS5-60-IN-0002B-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00171-4393 | PS5-60-LA-0002B-CA02 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | 2026-07-30 | Priority-1
T-00171-4394 | PS5-60-LA-0002B-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | 2026-07-30 | Priority-1
T-00171-4395 | PS5-60-LA-0002B-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | 2026-07-30 | Priority-1
T-00171-4398 | PS5-60-LA-0002C-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00171-4399 | PS5-60-LA-0002C-CA02 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00171-4400 | PS5-60-LA-0002C-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00171-4401 | PS5-60-LA-0002C-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00171-4402 | PS5-60-LA-0002C-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002B TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00171-4403 | PS5-60-LA-0002C-CA06 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-LA-0002B TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00171-4404 | PS5-60-SEA-0001-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00171-4407 | PS5-71-IN-0002-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00171-4408 | PS5-71-IN-0003-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 1 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00214-0231 |  | EACOP-PS5-60-01-0151 |  | EACOP-PS5-60-01-0151 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-25 06:52 | PS5-60-01 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0232 |  | EACOP-PS5-60-01-0152 |  | EACOP-PS5-60-01-0152 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-25 06:54 | PS5-60-01 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0233 |  | EACOP-PS5-60-01-0153 |  | EACOP-PS5-60-01-0153 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-02-25 06:56 | PS5-60-01 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0234 |  | EACOP-PS5-60-04-0154 |  | EACOP-PS5-60-04-0154 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-25 06:59 | PS5-60-04 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00214-0235 |  | EACOP-PS5-60-04-0155 |  | EACOP-PS5-60-04-0155 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-25 07:01 | PS5-60-04 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00214-0236 |  | EACOP-PS5-60-04-0156 |  | EACOP-PS5-60-04-0156 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-02-25 07:03 | PS5-60-04 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00214-0267 |  | EACOP-PS5-60-26-0183 |  | EACOP-PS5-60-26-0183 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-05-15 06:23 | PS5-60-26 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0268 |  | EACOP-PS5-60-26-0184 |  | EACOP-PS5-60-26-0184 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-04-04 06:12 | PS5-60-26 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0269 |  | EACOP-PS5-60-27-0185 |  | EACOP-PS5-60-27-0185 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-04-04 06:08 | PS5-60-27 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0270 |  | EACOP-PS5-60-27-0186 |  | EACOP-PS5-60-27-0186 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-04-26 04:39 | PS5-60-27 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0278 |  | EACOP-PS5-60-35-0194 |  | EACOP-PS5-60-35-0194 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-04-26 04:54 | PS5-60-35 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0279 |  | EACOP-PS5-60-35-0195 |  | EACOP-PS5-60-35-0195 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-04-26 04:55 | PS5-60-35 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0280 |  | EACOP-PS5-60-36-0196 |  | EACOP-PS5-60-36-0196 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-05-15 06:25 | PS5-60-36 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0281 |  | EACOP-PS5-60-36-0197 |  | EACOP-PS5-60-36-0197 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-04-04 06:11 | PS5-60-36 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0292 |  | EACOP-PS5-60-42-0208 |  | EACOP-PS5-60-42-0208 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-05-15 06:26 | PS5-60-42 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0293 |  | EACOP-PS5-60-42-0209 |  | EACOP-PS5-60-42-0209 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-04-26 06:12 | PS5-60-42 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0294 |  | EACOP-PS5-60-43-0210 |  | EACOP-PS5-60-43-0210 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-04-26 06:13 | PS5-60-43 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0295 |  | EACOP-PS5-60-43-0211 |  | EACOP-PS5-60-43-0211 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-04-26 06:14 | PS5-60-43 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0306 |  | EACOP-PS5-60-49-0222 |  | EACOP-PS5-60-49-0222 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2026-05-15 06:27 | PS5-60-49 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00214-0307 |  | EACOP-PS5-60-49-0223 |  | EACOP-PS5-60-49-0223 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2026-05-15 06:28 | PS5-60-49 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00214-0308 |  | EACOP-PS5-60-50-0224 |  | EACOP-PS5-60-50-0224 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2026-05-15 06:29 | PS5-60-50 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00214-0309 |  | EACOP-PS5-60-50-0225 |  | EACOP-PS5-60-50-0225 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2026-05-15 06:30 | PS5-60-50 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00214-0320 |  | EACOP-PS5-60-56-0236 |  | EACOP-PS5-60-56-0236 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-04-22 13:38 | PS5-60-56 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00214-0321 |  | EACOP-PS5-60-56-0237 |  | EACOP-PS5-60-56-0237 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-04-04 06:06 | PS5-60-56 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00214-0322 |  | EACOP-PS5-60-58-0238 |  | EACOP-PS5-60-58-0238 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-04-04 06:14 | PS5-60-58 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00214-0323 |  | EACOP-PS5-60-58-0239 |  | EACOP-PS5-60-58-0239 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-04-04 06:00 | PS5-60-58 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00214-0334 |  | EACOP-PS5-60-70-0250 |  | EACOP-PS5-60-70-0250 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-15 06:32 | PS5-60-70 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0335 |  | EACOP-PS5-60-70-0251 |  | EACOP-PS5-60-70-0251 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-02 18:22 | PS5-60-70 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0336 |  | EACOP-PS5-60-70-0252 |  | EACOP-PS5-60-70-0252 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-15 06:33 | PS5-60-70 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0337 |  | EACOP-PS5-60-70-0253 |  | EACOP-PS5-60-70-0253 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-15 06:34 | PS5-60-70 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0338 |  | EACOP-PS5-60-70-0254 |  | EACOP-PS5-60-70-0254 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-15 06:35 | PS5-60-70 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0339 |  | EACOP-PS5-60-70-0255 |  | EACOP-PS5-60-70-0255 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-15 06:37 | PS5-60-70 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0340 |  | EACOP-PS5-60-71-0256 |  | EACOP-PS5-60-71-0256 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-05-15 06:38 | PS5-60-71 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0341 |  | EACOP-PS5-60-71-0257 |  | EACOP-PS5-60-71-0257 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-05-06 05:23 | PS5-60-71 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0342 |  | EACOP-PS5-60-71-0258 |  | EACOP-PS5-60-71-0258 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-05-15 06:39 | PS5-60-71 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0343 |  | EACOP-PS5-60-71-0259 |  | EACOP-PS5-60-71-0259 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-05-15 06:40 | PS5-60-71 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0344 |  | EACOP-PS5-60-71-0260 |  | EACOP-PS5-60-71-0260 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-05-15 06:41 | PS5-60-71 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0345 |  | EACOP-PS5-60-71-0261 |  | EACOP-PS5-60-71-0261 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-05-15 06:42 | PS5-60-71 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0391 |  | EACOP-PS5-71-06-0307 |  | EACOP-PS5-71-06-0307 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-02-25 06:31 | PS5-71-06 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00214-0392 |  | EACOP-PS5-71-06-0308 |  | EACOP-PS5-71-06-0308 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-05-16 05:40 | PS5-71-06 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00214-0393 |  | EACOP-PS5-71-06-0378 |  | EACOP-PS5-71-06-0378 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-03-26 18:35 | PS5-71-06 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00214-0394 |  | EACOP-PS5-71-08-0309 |  | EACOP-PS5-71-08-0309 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-02-25 06:33 | PS5-71-08 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00214-0395 |  | EACOP-PS5-71-08-0310 |  | EACOP-PS5-71-08-0310 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-04-28 14:46 | PS5-71-08 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00214-0418 |  | EACOP-PS5-71-22-0333 |  | EACOP-PS5-71-22-0333 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  | 40 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-04-28 18:16 | PS5-71-22 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00214-0419 |  | EACOP-PS5-71-22-0334 |  | EACOP-PS5-71-22-0334 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-04-26 07:08 | PS5-71-22 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00214-0420 |  | EACOP-PS5-71-22-0335 |  | EACOP-PS5-71-22-0335 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-04-28 18:17 | PS5-71-22 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00214-0421 |  | EACOP-PS5-71-22-0336 |  | EACOP-PS5-71-22-0336 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-03-07 07:21 | PS5-71-22 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00214-0422 |  | EACOP-PS5-71-22-0337 |  | EACOP-PS5-71-22-0337 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-03-07 07:19 | PS5-71-22 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00214-0512 |  | EACOP-PS5-60-42-0046 |  | EACOP-PS5-60-42-0046 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-05-07 05:42 | PS5-60-42 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00214-0513 |  | EACOP-PS5-60-43-0091 |  | EACOP-PS5-60-43-0091 | TP | CLX01 - Pipework Test Pack composition | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 40 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-05-07 05:58 | PS5-60-43 |  |  | Pipework Test Pack Composition |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0231 |  | EACOP-PS5-60-01-0151 |  | EACOP-PS5-60-01-0151 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-07 17:32 | PS5-60-01 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0232 |  | EACOP-PS5-60-01-0152 |  | EACOP-PS5-60-01-0152 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-03 14:40 | PS5-60-01 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0233 |  | EACOP-PS5-60-01-0153 |  | EACOP-PS5-60-01-0153 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-07 17:37 | PS5-60-01 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0234 |  | EACOP-PS5-60-04-0154 |  | EACOP-PS5-60-04-0154 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-03 14:43 | PS5-60-04 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00215-0235 |  | EACOP-PS5-60-04-0155 |  | EACOP-PS5-60-04-0155 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-10 14:54 | PS5-60-04 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00215-0236 |  | EACOP-PS5-60-04-0156 |  | EACOP-PS5-60-04-0156 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-10 14:58 | PS5-60-04 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00215-0267 |  | EACOP-PS5-60-26-0183 |  | EACOP-PS5-60-26-0183 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-03 14:45 | PS5-60-26 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0268 |  | EACOP-PS5-60-26-0184 |  | EACOP-PS5-60-26-0184 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-05-07 14:08 | PS5-60-26 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0269 |  | EACOP-PS5-60-27-0185 |  | EACOP-PS5-60-27-0185 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-05-07 14:27 | PS5-60-27 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0270 |  | EACOP-PS5-60-27-0186 |  | EACOP-PS5-60-27-0186 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0278 |  | EACOP-PS5-60-35-0194 |  | EACOP-PS5-60-35-0194 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0279 |  | EACOP-PS5-60-35-0195 |  | EACOP-PS5-60-35-0195 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-05-04 08:39 | PS5-60-35 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0280 |  | EACOP-PS5-60-36-0196 |  | EACOP-PS5-60-36-0196 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0281 |  | EACOP-PS5-60-36-0197 |  | EACOP-PS5-60-36-0197 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-05-24 12:50 | PS5-60-36 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0292 |  | EACOP-PS5-60-42-0208 |  | EACOP-PS5-60-42-0208 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0293 |  | EACOP-PS5-60-42-0209 |  | EACOP-PS5-60-42-0209 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-06-07 18:03 | PS5-60-42 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0294 |  | EACOP-PS5-60-43-0210 |  | EACOP-PS5-60-43-0210 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0295 |  | EACOP-PS5-60-43-0211 |  | EACOP-PS5-60-43-0211 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-05-24 11:07 | PS5-60-43 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0306 |  | EACOP-PS5-60-49-0222 |  | EACOP-PS5-60-49-0222 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00215-0307 |  | EACOP-PS5-60-49-0223 |  | EACOP-PS5-60-49-0223 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2026-06-07 18:06 | PS5-60-49 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00215-0308 |  | EACOP-PS5-60-50-0224 |  | EACOP-PS5-60-50-0224 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Pipework Before Test |  | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00215-0309 |  | EACOP-PS5-60-50-0225 |  | EACOP-PS5-60-50-0225 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2026-06-03 14:50 | PS5-60-50 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00215-0320 |  | EACOP-PS5-60-56-0236 |  | EACOP-PS5-60-56-0236 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-04-22 13:41 | PS5-60-56 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00215-0321 |  | EACOP-PS5-60-56-0237 |  | EACOP-PS5-60-56-0237 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-06-07 18:09 | PS5-60-56 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00215-0322 |  | EACOP-PS5-60-58-0238 |  | EACOP-PS5-60-58-0238 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-04-22 13:59 | PS5-60-58 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00215-0323 |  | EACOP-PS5-60-58-0239 |  | EACOP-PS5-60-58-0239 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-05-24 11:11 | PS5-60-58 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00215-0334 |  | EACOP-PS5-60-70-0250 |  | EACOP-PS5-60-70-0250 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-03 15:00 | PS5-60-70 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0335 |  | EACOP-PS5-60-70-0251 |  | EACOP-PS5-60-70-0251 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-04 08:42 | PS5-60-70 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0336 |  | EACOP-PS5-60-70-0252 |  | EACOP-PS5-60-70-0252 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-03 15:04 | PS5-60-70 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0337 |  | EACOP-PS5-60-70-0253 |  | EACOP-PS5-60-70-0253 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-03 15:07 | PS5-60-70 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0338 |  | EACOP-PS5-60-70-0254 |  | EACOP-PS5-60-70-0254 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-03 15:10 | PS5-60-70 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0339 |  | EACOP-PS5-60-70-0255 |  | EACOP-PS5-60-70-0255 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-07 18:19 | PS5-60-70 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0340 |  | EACOP-PS5-60-71-0256 |  | EACOP-PS5-60-71-0256 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-10 15:05 | PS5-60-71 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0341 |  | EACOP-PS5-60-71-0257 |  | EACOP-PS5-60-71-0257 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-05-24 11:13 | PS5-60-71 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0342 |  | EACOP-PS5-60-71-0258 |  | EACOP-PS5-60-71-0258 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-03 17:02 | PS5-60-71 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0343 |  | EACOP-PS5-60-71-0259 |  | EACOP-PS5-60-71-0259 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-03 17:04 | PS5-60-71 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0344 |  | EACOP-PS5-60-71-0260 |  | EACOP-PS5-60-71-0260 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-03 17:07 | PS5-60-71 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0345 |  | EACOP-PS5-60-71-0261 |  | EACOP-PS5-60-71-0261 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-03 17:10 | PS5-60-71 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0391 |  | EACOP-PS5-71-06-0307 |  | EACOP-PS5-71-06-0307 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-04-02 12:16 | PS5-71-06 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00215-0392 |  | EACOP-PS5-71-06-0308 |  | EACOP-PS5-71-06-0308 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-05-24 14:51 | PS5-71-06 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00215-0393 |  | EACOP-PS5-71-06-0378 |  | EACOP-PS5-71-06-0378 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-03-26 18:37 | PS5-71-06 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00215-0394 |  | EACOP-PS5-71-08-0309 |  | EACOP-PS5-71-08-0309 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-04-02 12:28 | PS5-71-08 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00215-0395 |  | EACOP-PS5-71-08-0310 |  | EACOP-PS5-71-08-0310 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-06-26 05:14 | PS5-71-08 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00215-0418 |  | EACOP-PS5-71-22-0333 |  | EACOP-PS5-71-22-0333 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-05-24 14:54 | PS5-71-22 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00215-0419 |  | EACOP-PS5-71-22-0334 |  | EACOP-PS5-71-22-0334 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-04-26 18:21 | PS5-71-22 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00215-0420 |  | EACOP-PS5-71-22-0335 |  | EACOP-PS5-71-22-0335 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-05-04 08:47 | PS5-71-22 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00215-0421 |  | EACOP-PS5-71-22-0336 |  | EACOP-PS5-71-22-0336 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  | 12 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-05-24 12:21 | PS5-71-22 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00215-0422 |  | EACOP-PS5-71-22-0337 |  | EACOP-PS5-71-22-0337 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-06-07 18:48 | PS5-71-22 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00215-0512 |  | EACOP-PS5-60-42-0046 |  | EACOP-PS5-60-42-0046 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-05-07 13:57 | PS5-60-42 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00215-0513 |  | EACOP-PS5-60-43-0091 |  | EACOP-PS5-60-43-0091 | TP | CLX02A - Pipework before test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-05-07 14:04 | PS5-60-43 |  |  | Pipework Before Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0231 |  | EACOP-PS5-60-01-0151 |  | EACOP-PS5-60-01-0151 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0232 |  | EACOP-PS5-60-01-0152 |  | EACOP-PS5-60-01-0152 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0233 |  | EACOP-PS5-60-01-0153 |  | EACOP-PS5-60-01-0153 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0234 |  | EACOP-PS5-60-04-0154 |  | EACOP-PS5-60-04-0154 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00216-0235 |  | EACOP-PS5-60-04-0155 |  | EACOP-PS5-60-04-0155 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00216-0236 |  | EACOP-PS5-60-04-0156 |  | EACOP-PS5-60-04-0156 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00216-0267 |  | EACOP-PS5-60-26-0183 |  | EACOP-PS5-60-26-0183 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0268 |  | EACOP-PS5-60-26-0184 |  | EACOP-PS5-60-26-0184 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0269 |  | EACOP-PS5-60-27-0185 |  | EACOP-PS5-60-27-0185 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0270 |  | EACOP-PS5-60-27-0186 |  | EACOP-PS5-60-27-0186 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0278 |  | EACOP-PS5-60-35-0194 |  | EACOP-PS5-60-35-0194 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0279 |  | EACOP-PS5-60-35-0195 |  | EACOP-PS5-60-35-0195 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0280 |  | EACOP-PS5-60-36-0196 |  | EACOP-PS5-60-36-0196 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0281 |  | EACOP-PS5-60-36-0197 |  | EACOP-PS5-60-36-0197 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0292 |  | EACOP-PS5-60-42-0208 |  | EACOP-PS5-60-42-0208 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0293 |  | EACOP-PS5-60-42-0209 |  | EACOP-PS5-60-42-0209 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0294 |  | EACOP-PS5-60-43-0210 |  | EACOP-PS5-60-43-0210 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0295 |  | EACOP-PS5-60-43-0211 |  | EACOP-PS5-60-43-0211 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0306 |  | EACOP-PS5-60-49-0222 |  | EACOP-PS5-60-49-0222 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00216-0307 |  | EACOP-PS5-60-49-0223 |  | EACOP-PS5-60-49-0223 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00216-0308 |  | EACOP-PS5-60-50-0224 |  | EACOP-PS5-60-50-0224 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00216-0309 |  | EACOP-PS5-60-50-0225 |  | EACOP-PS5-60-50-0225 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00216-0320 |  | EACOP-PS5-60-56-0236 |  | EACOP-PS5-60-56-0236 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00216-0321 |  | EACOP-PS5-60-56-0237 |  | EACOP-PS5-60-56-0237 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00216-0322 |  | EACOP-PS5-60-58-0238 |  | EACOP-PS5-60-58-0238 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00216-0323 |  | EACOP-PS5-60-58-0239 |  | EACOP-PS5-60-58-0239 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00216-0334 |  | EACOP-PS5-60-70-0250 |  | EACOP-PS5-60-70-0250 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0335 |  | EACOP-PS5-60-70-0251 |  | EACOP-PS5-60-70-0251 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0336 |  | EACOP-PS5-60-70-0252 |  | EACOP-PS5-60-70-0252 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0337 |  | EACOP-PS5-60-70-0253 |  | EACOP-PS5-60-70-0253 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0338 |  | EACOP-PS5-60-70-0254 |  | EACOP-PS5-60-70-0254 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0339 |  | EACOP-PS5-60-70-0255 |  | EACOP-PS5-60-70-0255 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0340 |  | EACOP-PS5-60-71-0256 |  | EACOP-PS5-60-71-0256 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0341 |  | EACOP-PS5-60-71-0257 |  | EACOP-PS5-60-71-0257 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0342 |  | EACOP-PS5-60-71-0258 |  | EACOP-PS5-60-71-0258 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0343 |  | EACOP-PS5-60-71-0259 |  | EACOP-PS5-60-71-0259 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0344 |  | EACOP-PS5-60-71-0260 |  | EACOP-PS5-60-71-0260 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0345 |  | EACOP-PS5-60-71-0261 |  | EACOP-PS5-60-71-0261 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0391 |  | EACOP-PS5-71-06-0307 |  | EACOP-PS5-71-06-0307 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00216-0392 |  | EACOP-PS5-71-06-0308 |  | EACOP-PS5-71-06-0308 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00216-0393 |  | EACOP-PS5-71-06-0378 |  | EACOP-PS5-71-06-0378 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00216-0394 |  | EACOP-PS5-71-08-0309 |  | EACOP-PS5-71-08-0309 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00216-0395 |  | EACOP-PS5-71-08-0310 |  | EACOP-PS5-71-08-0310 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00216-0418 |  | EACOP-PS5-71-22-0333 |  | EACOP-PS5-71-22-0333 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00216-0419 |  | EACOP-PS5-71-22-0334 |  | EACOP-PS5-71-22-0334 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00216-0420 |  | EACOP-PS5-71-22-0335 |  | EACOP-PS5-71-22-0335 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00216-0421 |  | EACOP-PS5-71-22-0336 |  | EACOP-PS5-71-22-0336 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00216-0422 |  | EACOP-PS5-71-22-0337 |  | EACOP-PS5-71-22-0337 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00216-0512 |  | EACOP-PS5-60-42-0046 |  | EACOP-PS5-60-42-0046 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00216-0513 |  | EACOP-PS5-60-43-0091 |  | EACOP-PS5-60-43-0091 | TP | CLX02B - Pipework after test (Reinstatement) | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 12 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Pipework After Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00218-0097 | PS5-60-01_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Painting Line | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00218-0098 | PS5-60-04_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Painting Line | P | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00218-0107 | PS5-60-26_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | Painting Line | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00218-0108 | PS5-60-27_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Painting Line | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00218-0116 | PS5-60-35_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Painting Line | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00218-0117 | PS5-60-36_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Painting Line | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00218-0123 | PS5-60-42_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Painting Line | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00218-0124 | PS5-60-43_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Painting Line | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00218-0130 | PS5-60-49_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Painting Line | P | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00218-0131 | PS5-60-50_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Painting Line | P | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00218-0137 | PS5-60-56_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Painting Line | P | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00218-0138 | PS5-60-58_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Painting Line | P | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00218-0144 | PS5-60-70_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Painting Line | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00218-0145 | PS5-60-71_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Painting Line | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00218-0155 | PS5-71-06_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Painting Line | P | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00218-0156 | PS5-71-08_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Painting Line | P | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00218-0166 | PS5-71-22_SS_ALL_LINES |  |  |  |  | CXX02 - Painting line | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Painting Line | P | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00220-0008 | PS5-60-35_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00220-0009 | PS5-60-36_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00220-0015 | PS5-60-49_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00220-0016 | PS5-60-50_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00220-0022 | PS5-60-70_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00220-0023 | PS5-60-71_SS_ALL_LINES |  |  |  |  | CXX05 - Personnel protection | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Subsystem all lines | EACOP | CPP AGI |  |  | 1 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Personnel Protection | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0231 |  | EACOP-PS5-60-01-0151 |  | EACOP-PS5-60-01-0151 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-03 11:35 | PS5-60-01 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0232 |  | EACOP-PS5-60-01-0152 |  | EACOP-PS5-60-01-0152 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-03 11:36 | PS5-60-01 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0233 |  | EACOP-PS5-60-01-0153 |  | EACOP-PS5-60-01-0153 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-05 13:00 | PS5-60-01 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0234 |  | EACOP-PS5-60-04-0154 |  | EACOP-PS5-60-04-0154 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-08 12:18 | PS5-60-04 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00221-0235 |  | EACOP-PS5-60-04-0155 |  | EACOP-PS5-60-04-0155 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-17 11:54 | PS5-60-04 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00221-0236 |  | EACOP-PS5-60-04-0156 |  | EACOP-PS5-60-04-0156 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-17 12:04 | PS5-60-04 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00221-0267 |  | EACOP-PS5-60-26-0183 |  | EACOP-PS5-60-26-0183 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-24 11:36 | PS5-60-26 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0268 |  | EACOP-PS5-60-26-0184 |  | EACOP-PS5-60-26-0184 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-01 05:52 | PS5-60-26 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0269 |  | EACOP-PS5-60-27-0185 |  | EACOP-PS5-60-27-0185 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-06-01 05:54 | PS5-60-27 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0270 |  | EACOP-PS5-60-27-0186 |  | EACOP-PS5-60-27-0186 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Pressure Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0278 |  | EACOP-PS5-60-35-0194 |  | EACOP-PS5-60-35-0194 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Pressure Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0279 |  | EACOP-PS5-60-35-0195 |  | EACOP-PS5-60-35-0195 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-05-09 10:32 | PS5-60-35 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0280 |  | EACOP-PS5-60-36-0196 |  | EACOP-PS5-60-36-0196 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Pressure Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0281 |  | EACOP-PS5-60-36-0197 |  | EACOP-PS5-60-36-0197 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-06-01 05:55 | PS5-60-36 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0292 |  | EACOP-PS5-60-42-0208 |  | EACOP-PS5-60-42-0208 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Pressure Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0293 |  | EACOP-PS5-60-42-0209 |  | EACOP-PS5-60-42-0209 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-06-03 11:38 | PS5-60-42 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0294 |  | EACOP-PS5-60-43-0210 |  | EACOP-PS5-60-43-0210 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Pressure Test |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0295 |  | EACOP-PS5-60-43-0211 |  | EACOP-PS5-60-43-0211 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-06-03 11:40 | PS5-60-43 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0306 |  | EACOP-PS5-60-49-0222 |  | EACOP-PS5-60-49-0222 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Pressure Test |  | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00221-0307 |  | EACOP-PS5-60-49-0223 |  | EACOP-PS5-60-49-0223 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2026-06-05 13:03 | PS5-60-49 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00221-0308 |  | EACOP-PS5-60-50-0224 |  | EACOP-PS5-60-50-0224 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Pressure Test |  | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00221-0309 |  | EACOP-PS5-60-50-0225 |  | EACOP-PS5-60-50-0225 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2026-06-08 12:19 | PS5-60-50 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00221-0320 |  | EACOP-PS5-60-56-0236 |  | EACOP-PS5-60-56-0236 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-04-30 09:33 | PS5-60-56 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00221-0321 |  | EACOP-PS5-60-56-0237 |  | EACOP-PS5-60-56-0237 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-04-30 09:48 | PS5-60-56 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00221-0322 |  | EACOP-PS5-60-58-0238 |  | EACOP-PS5-60-58-0238 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-05-09 11:00 | PS5-60-58 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00221-0323 |  | EACOP-PS5-60-58-0239 |  | EACOP-PS5-60-58-0239 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-05-09 10:37 | PS5-60-58 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00221-0334 |  | EACOP-PS5-60-70-0250 |  | EACOP-PS5-60-70-0250 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-05 12:45 | PS5-60-70 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0335 |  | EACOP-PS5-60-70-0251 |  | EACOP-PS5-60-70-0251 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-20 11:33 | PS5-60-70 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0336 |  | EACOP-PS5-60-70-0252 |  | EACOP-PS5-60-70-0252 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-05 12:41 | PS5-60-70 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0337 |  | EACOP-PS5-60-70-0253 |  | EACOP-PS5-60-70-0253 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-05 12:43 | PS5-60-70 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0338 |  | EACOP-PS5-60-70-0254 |  | EACOP-PS5-60-70-0254 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-03 12:00 | PS5-60-70 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0339 |  | EACOP-PS5-60-70-0255 |  | EACOP-PS5-60-70-0255 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-03 12:01 | PS5-60-70 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0340 |  | EACOP-PS5-60-71-0256 |  | EACOP-PS5-60-71-0256 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-17 11:17 | PS5-60-71 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0341 |  | EACOP-PS5-60-71-0257 |  | EACOP-PS5-60-71-0257 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-03 12:07 | PS5-60-71 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0342 |  | EACOP-PS5-60-71-0258 |  | EACOP-PS5-60-71-0258 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-05 12:53 | PS5-60-71 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0343 |  | EACOP-PS5-60-71-0259 |  | EACOP-PS5-60-71-0259 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-05 12:56 | PS5-60-71 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0344 |  | EACOP-PS5-60-71-0260 |  | EACOP-PS5-60-71-0260 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-05 12:57 | PS5-60-71 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0345 |  | EACOP-PS5-60-71-0261 |  | EACOP-PS5-60-71-0261 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-05 12:58 | PS5-60-71 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0391 |  | EACOP-PS5-71-06-0307 |  | EACOP-PS5-71-06-0307 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-05-02 05:49 | PS5-71-06 |  |  | Pressure Test |  | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00221-0392 |  | EACOP-PS5-71-06-0308 |  | EACOP-PS5-71-06-0308 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-06-01 05:34 | PS5-71-06 |  |  | Pressure Test |  | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00221-0393 |  | EACOP-PS5-71-06-0378 |  | EACOP-PS5-71-06-0378 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-04-13 11:37 | PS5-71-06 |  |  | Pressure Test |  | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00221-0394 |  | EACOP-PS5-71-08-0309 |  | EACOP-PS5-71-08-0309 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-05-05 11:14 | PS5-71-08 |  |  | Pressure Test |  | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00221-0395 |  | EACOP-PS5-71-08-0310 |  | EACOP-PS5-71-08-0310 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Pressure Test |  | Completed (not Closed) | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00221-0418 |  | EACOP-PS5-71-22-0333 |  | EACOP-PS5-71-22-0333 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-06-01 05:50 | PS5-71-22 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00221-0419 |  | EACOP-PS5-71-22-0334 |  | EACOP-PS5-71-22-0334 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-04-30 09:49 | PS5-71-22 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00221-0420 |  | EACOP-PS5-71-22-0335 |  | EACOP-PS5-71-22-0335 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-05-09 10:31 | PS5-71-22 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00221-0421 |  | EACOP-PS5-71-22-0336 |  | EACOP-PS5-71-22-0336 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-05-09 10:36 | PS5-71-22 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00221-0422 |  | EACOP-PS5-71-22-0337 |  | EACOP-PS5-71-22-0337 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-05-09 10:34 | PS5-71-22 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00221-0512 |  | EACOP-PS5-60-42-0046 |  | EACOP-PS5-60-42-0046 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-05-09 10:37 | PS5-60-42 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00221-0513 |  | EACOP-PS5-60-43-0091 |  | EACOP-PS5-60-43-0091 | TP | TMX05 - Pressure test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 20 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-05-09 10:38 | PS5-60-43 |  |  | Pressure Test |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0231 |  | EACOP-PS5-60-01-0151 |  | EACOP-PS5-60-01-0151 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-01 07:41 | PS5-60-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0232 |  | EACOP-PS5-60-01-0152 |  | EACOP-PS5-60-01-0152 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-06 11:25 | PS5-60-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0233 |  | EACOP-PS5-60-01-0153 |  | EACOP-PS5-60-01-0153 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-06 11:40 | PS5-60-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0234 |  | EACOP-PS5-60-04-0154 |  | EACOP-PS5-60-04-0154 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-06 11:36 | PS5-60-04 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00223-0235 |  | EACOP-PS5-60-04-0155 |  | EACOP-PS5-60-04-0155 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 11:36 | PS5-60-04 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00223-0236 |  | EACOP-PS5-60-04-0156 |  | EACOP-PS5-60-04-0156 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 14:30 | PS5-60-04 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00223-0267 |  | EACOP-PS5-60-26-0183 |  | EACOP-PS5-60-26-0183 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-23 08:44 | PS5-60-26 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0268 |  | EACOP-PS5-60-26-0184 |  | EACOP-PS5-60-26-0184 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-01 13:43 | PS5-60-26 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0269 |  | EACOP-PS5-60-27-0185 |  | EACOP-PS5-60-27-0185 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-06-01 13:45 | PS5-60-27 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0270 |  | EACOP-PS5-60-27-0186 |  | EACOP-PS5-60-27-0186 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  |  |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0278 |  | EACOP-PS5-60-35-0194 |  | EACOP-PS5-60-35-0194 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  |  |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0279 |  | EACOP-PS5-60-35-0195 |  | EACOP-PS5-60-35-0195 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-05-05 11:42 | PS5-60-35 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0280 |  | EACOP-PS5-60-36-0196 |  | EACOP-PS5-60-36-0196 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  |  |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0281 |  | EACOP-PS5-60-36-0197 |  | EACOP-PS5-60-36-0197 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-05-25 17:54 | PS5-60-36 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0292 |  | EACOP-PS5-60-42-0208 |  | EACOP-PS5-60-42-0208 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  |  |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0293 |  | EACOP-PS5-60-42-0209 |  | EACOP-PS5-60-42-0209 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-05-29 08:59 | PS5-60-42 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0294 |  | EACOP-PS5-60-43-0210 |  | EACOP-PS5-60-43-0210 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  |  |  | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0295 |  | EACOP-PS5-60-43-0211 |  | EACOP-PS5-60-43-0211 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-05-29 09:01 | PS5-60-43 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0306 |  | EACOP-PS5-60-49-0222 |  | EACOP-PS5-60-49-0222 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  |  |  | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00223-0307 |  | EACOP-PS5-60-49-0223 |  | EACOP-PS5-60-49-0223 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2026-06-06 11:42 | PS5-60-49 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00223-0308 |  | EACOP-PS5-60-50-0224 |  | EACOP-PS5-60-50-0224 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  |  |  | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00223-0309 |  | EACOP-PS5-60-50-0225 |  | EACOP-PS5-60-50-0225 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2026-06-27 07:52 | PS5-60-50 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00223-0320 |  | EACOP-PS5-60-56-0236 |  | EACOP-PS5-60-56-0236 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-04-26 08:14 | PS5-60-56 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00223-0321 |  | EACOP-PS5-60-56-0237 |  | EACOP-PS5-60-56-0237 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-04-29 05:09 | PS5-60-56 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00223-0322 |  | EACOP-PS5-60-58-0238 |  | EACOP-PS5-60-58-0238 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-04-26 12:29 | PS5-60-58 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00223-0323 |  | EACOP-PS5-60-58-0239 |  | EACOP-PS5-60-58-0239 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-05-25 17:47 | PS5-60-58 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00223-0334 |  | EACOP-PS5-60-70-0250 |  | EACOP-PS5-60-70-0250 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-06 11:30 | PS5-60-70 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0335 |  | EACOP-PS5-60-70-0251 |  | EACOP-PS5-60-70-0251 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-05-05 11:54 | PS5-60-70 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0336 |  | EACOP-PS5-60-70-0252 |  | EACOP-PS5-60-70-0252 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-06 11:31 | PS5-60-70 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0337 |  | EACOP-PS5-60-70-0253 |  | EACOP-PS5-60-70-0253 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-06 11:32 | PS5-60-70 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0338 |  | EACOP-PS5-60-70-0254 |  | EACOP-PS5-60-70-0254 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-06 11:26 | PS5-60-70 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0339 |  | EACOP-PS5-60-70-0255 |  | EACOP-PS5-60-70-0255 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-06 11:27 | PS5-60-70 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0340 |  | EACOP-PS5-60-71-0256 |  | EACOP-PS5-60-71-0256 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-19 11:37 | PS5-60-71 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0341 |  | EACOP-PS5-60-71-0257 |  | EACOP-PS5-60-71-0257 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-03 04:46 | PS5-60-71 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0342 |  | EACOP-PS5-60-71-0258 |  | EACOP-PS5-60-71-0258 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-19 11:29 | PS5-60-71 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0343 |  | EACOP-PS5-60-71-0259 |  | EACOP-PS5-60-71-0259 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-19 11:29 | PS5-60-71 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0344 |  | EACOP-PS5-60-71-0260 |  | EACOP-PS5-60-71-0260 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-19 11:30 | PS5-60-71 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0345 |  | EACOP-PS5-60-71-0261 |  | EACOP-PS5-60-71-0261 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-19 11:32 | PS5-60-71 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0391 |  | EACOP-PS5-71-06-0307 |  | EACOP-PS5-71-06-0307 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-04-27 08:28 | PS5-71-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00223-0392 |  | EACOP-PS5-71-06-0308 |  | EACOP-PS5-71-06-0308 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-05-29 08:52 | PS5-71-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00223-0393 |  | EACOP-PS5-71-06-0378 |  | EACOP-PS5-71-06-0378 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2026-04-04 12:14 | PS5-71-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00223-0394 |  | EACOP-PS5-71-08-0309 |  | EACOP-PS5-71-08-0309 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-04-27 08:26 | PS5-71-08 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00223-0395 |  | EACOP-PS5-71-08-0310 |  | EACOP-PS5-71-08-0310 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  |  |  | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00223-0418 |  | EACOP-PS5-71-22-0333 |  | EACOP-PS5-71-22-0333 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Submitted | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00223-0419 |  | EACOP-PS5-71-22-0334 |  | EACOP-PS5-71-22-0334 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-04-28 07:18 | PS5-71-22 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00223-0420 |  | EACOP-PS5-71-22-0335 |  | EACOP-PS5-71-22-0335 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-05-05 12:29 | PS5-71-22 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00223-0421 |  | EACOP-PS5-71-22-0336 |  | EACOP-PS5-71-22-0336 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-05-25 17:46 | PS5-71-22 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00223-0422 |  | EACOP-PS5-71-22-0337 |  | EACOP-PS5-71-22-0337 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-06-03 04:48 | PS5-71-22 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00223-0512 |  | EACOP-PS5-60-42-0046 |  | EACOP-PS5-60-42-0046 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-05-25 18:11 | PS5-60-42 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00223-0513 |  | EACOP-PS5-60-43-0091 |  | EACOP-PS5-60-43-0091 | TP | TMX03 - Cleaning | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel |  | EACOP | CPP AGI |  |  | 50 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-05-25 18:13 | PS5-60-43 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) |  | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00224-0120 | PS5-60-01_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00224-0121 | PS5-60-04_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00224-0130 | PS5-60-26_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00224-0131 | PS5-60-27_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00224-0139 | PS5-60-35_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A |  | PS5-60-35 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00224-0140 | PS5-60-36_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B |  | PS5-60-36 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00224-0146 | PS5-60-42_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00224-0147 | PS5-60-43_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00224-0153 | PS5-60-49_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00224-0154 | PS5-60-50_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00224-0160 | PS5-60-56_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00224-0161 | PS5-60-58_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00224-0167 | PS5-60-70_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00224-0168 | PS5-60-71_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00224-0178 | PS5-71-06_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00224-0179 | PS5-71-08_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00224-0189 | PS5-71-22_GALT |  |  |  |  | TMX25 - Gross air leak test | PCOM - Precommissioning | P | Piping Test Preparations | P - Piping & Vessel | Gross Air Leak Test | EACOP | CPP AGI |  |  | 30 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Gross Air Leak Test | P | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00227-0133 | PS5-61-IU-0001A |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 24 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Power Transformer | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00227-0134 | PS5-61-IU-0001B |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 24 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Power Transformer | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00232-0970 | PS5-60-IJ-0001A-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-60-IJ-0001A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-03-14 04:26 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00232-0971 | PS5-60-IJ-0001B-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-60-IJ-0001B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-03-14 04:27 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00232-1013 | PS5-61-IJ-0001-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-13 05:39 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00232-1014 | PS5-61-IJ-0001-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-13 05:42 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00232-1015 | PS5-61-IJ-0001-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001A TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-13 05:42 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00232-1016 | PS5-61-IJ-0001-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-13 05:43 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00232-1017 | PS5-61-IJ-0001-CH05 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-13 05:44 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00232-1018 | PS5-61-IJ-0001-CH06 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IU-0001B TO PS5-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-13 05:44 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00232-1046 | PS5-61-IU-0001A-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-17 05:50 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00232-1047 | PS5-61-IU-0001A-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-17 05:50 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00232-1048 | PS5-61-IU-0001A-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100A TO PS5-61-IU-0001A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-04-17 05:51 | PS5-60-01 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00232-1049 | PS5-61-IU-0001B-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-17 05:51 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00232-1050 | PS5-61-IU-0001B-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-17 05:52 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00232-1051 | PS5-61-IU-0001B-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-GE-8100B TO PS5-61-IU-0001B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-04-17 05:52 | PS5-60-04 |  |  | HV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-10536 | PS5-60-IN-0002A-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-10537 | PS5-60-IN-0002B-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-10593 | PS5-60-IH-0001A-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-10594 | PS5-60-IH-0001B-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-10600 | PS5-60-IH-0002-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:17 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-10601 | PS5-60-IH-0002-CG02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:17 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-10890 | PS5-60-BE-0007A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-06-27 08:59 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-10891 | PS5-60-BE-0007A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-06-27 09:04 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-10892 | PS5-60-BE-0007B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-06-27 09:24 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-10893 | PS5-60-BE-0007B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-06-27 09:25 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-10904 | PS5-60-ISO-62800A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-ISO-62800A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-4978 | PS5-60-BE-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-06-27 09:27 | PS5-60-27 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-4979 | PS5-60-BE-0001-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-06-27 09:28 | PS5-60-27 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-4981 | PS5-60-BE-0001-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2026-06-27 08:44 | PS5-60-27 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-4982 | PS5-60-BE-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-27 08:53 | PS5-60-26 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-4983 | PS5-60-BE-0002-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-27 08:55 | PS5-60-26 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-4984 | PS5-60-BE-0002-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-27 09:29 | PS5-60-26 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-4986 | PS5-60-BE-0002-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-06-27 08:52 | PS5-60-26 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-4987 | PS5-60-BE-0003A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 04:41 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-4988 | PS5-60-BE-0003B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 04:42 | PS5-60-04 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-4994 | PS5-60-BE-0004A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0004A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-4995 | PS5-60-BE-0004B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0004B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5001 | PS5-60-BE-0005A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0005A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-11 05:20 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5002 | PS5-60-BE-0005B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0005B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5008 | PS5-60-BE-0011A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-05 07:47 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5009 | PS5-60-BE-0011A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-05 07:49 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5010 | PS5-60-BE-0011A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5011 | PS5-60-BE-0011A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-06 04:42 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5012 | PS5-60-BE-0011A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5013 | PS5-60-BE-0011A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5014 | PS5-60-BE-0011B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5015 | PS5-60-BE-0011B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5016 | PS5-60-BE-0011B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5017 | PS5-60-BE-0011B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5018 | PS5-60-BE-0011B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5019 | PS5-60-BE-0011B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5020 | PS5-60-BE-0012A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5021 | PS5-60-BE-0012A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5022 | PS5-60-BE-0012A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5023 | PS5-60-BE-0012A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5024 | PS5-60-BE-0012A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5025 | PS5-60-BE-0012A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5026 | PS5-60-BE-0012B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5027 | PS5-60-BE-0012B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5028 | PS5-60-BE-0012B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5029 | PS5-60-BE-0012B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5030 | PS5-60-BE-0012B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | Submitted | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5031 | PS5-60-BE-0012B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 04:43 | PS5-60-04 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5092 | PS5-60-BE-0021A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0021A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-06 04:42 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5093 | PS5-60-BE-0021B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-60-BE-0021B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 08:29 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5094 | PS5-60-BE-0024A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0024A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-06-11 10:41 | PS5-60-35 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5095 | PS5-60-BE-0024A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0024A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-06-11 10:42 | PS5-60-35 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5096 | PS5-60-BE-0024B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0024B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-06-11 10:43 | PS5-60-36 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5097 | PS5-60-BE-0024B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0024B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-06-11 10:43 | PS5-60-36 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5108 | PS5-60-BE-0025A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0025A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2026-06-19 04:43 | PS5-60-35 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5109 | PS5-60-BE-0025B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0025B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2026-06-19 04:44 | PS5-60-36 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5115 | PS5-60-BE-0026A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0026A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-19 04:45 | PS5-60-70 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5116 | PS5-60-BE-0026A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BE-0026A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2026-06-19 04:45 | PS5-60-70 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5117 | PS5-60-BE-0026B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0026B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-19 04:45 | PS5-60-71 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5118 | PS5-60-BE-0026B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BE-0026B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2026-06-19 04:46 | PS5-60-71 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5129 | PS5-60-BI-0005A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0005A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-05 07:51 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5130 | PS5-60-BI-0005B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0005B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-05 07:52 | PS5-60-04 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5136 | PS5-60-BI-0015A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5137 | PS5-60-BI-0015A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 04:48 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5138 | PS5-60-BI-0015A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 04:48 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5139 | PS5-60-BI-0015B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5140 | PS5-60-BI-0015B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 04:48 | PS5-60-04 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5141 | PS5-60-BI-0015B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 04:49 | PS5-60-04 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5157 | PS5-60-DD-62800A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-DD-62800A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5166 | PS5-60-IE-0002A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:28 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5167 | PS5-60-IE-0002A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:31 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5168 | PS5-60-IE-0002A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:31 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5169 | PS5-60-IE-0002B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-06 04:44 | PS5-60-04 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5170 | PS5-60-IE-0002B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-06 04:45 | PS5-60-04 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5171 | PS5-60-IE-0002B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:31 | PS5-60-04 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5187 | PS5-60-IE-0003A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) | 2026-06-19 04:25 | PS5-60-02 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5188 | PS5-60-IE-0003A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) | 2026-06-19 04:26 | PS5-60-02 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5189 | PS5-60-IE-0003B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) | 2026-06-19 04:26 | PS5-60-05 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5190 | PS5-60-IE-0003B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) | 2026-06-19 04:27 | PS5-60-05 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5201 | PS5-60-IE-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:28 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5202 | PS5-60-IE-0004-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:28 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5204 | PS5-60-IH-0001A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-19 08:23 | PS5-60-03 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5205 | PS5-60-IH-0001A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-19 08:24 | PS5-60-03 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5206 | PS5-60-IH-0001A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-19 08:25 | PS5-60-03 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5207 | PS5-60-IH-0001A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-19 08:26 | PS5-60-03 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5208 | PS5-60-IH-0001A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-19 08:31 | PS5-60-03 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5209 | PS5-60-IH-0001A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-19 04:28 | PS5-60-03 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5211 | PS5-60-IH-0001B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-19 08:28 | PS5-60-06 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5212 | PS5-60-IH-0001B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-19 08:28 | PS5-60-06 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5213 | PS5-60-IH-0001B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-19 08:28 | PS5-60-06 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5214 | PS5-60-IH-0001B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-19 08:29 | PS5-60-06 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5215 | PS5-60-IH-0001B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-19 04:29 | PS5-60-06 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5216 | PS5-60-IH-0001B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-19 04:32 | PS5-60-06 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5254 | PS5-60-IH-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:33 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5255 | PS5-60-IH-0002-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:33 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5256 | PS5-60-IH-0002-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:18 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5257 | PS5-60-IH-0002-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:20 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5258 | PS5-60-IH-0002-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:20 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5259 | PS5-60-IH-0002-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:20 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5260 | PS5-60-IH-0002-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:21 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5261 | PS5-60-IH-0002-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:21 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5262 | PS5-60-IH-0002-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:21 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5263 | PS5-60-IH-0002-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IK-0003 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:20 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5264 | PS5-60-IN-0001A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2026-06-19 04:51 | PS5-60-49 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5265 | PS5-60-IN-0001B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2026-06-19 04:51 | PS5-60-50 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5271 | PS5-60-IN-0002A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | 2026-06-19 08:35 | PS5-60-57 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5272 | PS5-60-IN-0002A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | 2026-06-19 08:31 | PS5-60-57 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5273 | PS5-60-IN-0002A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | 2026-06-19 08:31 | PS5-60-57 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5274 | PS5-60-IN-0002B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | 2026-06-19 08:35 | PS5-60-59 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-5275 | PS5-60-IN-0002B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | 2026-06-19 08:31 | PS5-60-59 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-5276 | PS5-60-IN-0002B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | 2026-06-19 08:33 | PS5-60-59 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-5292 | PS5-60-IWK-0001A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5293 | PS5-60-IWK-0001A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5294 | PS5-60-IWK-0001B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:32 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5295 | PS5-60-IWK-0001B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:32 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5296 | PS5-60-IWK-0001C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-IWK-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:34 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5297 | PS5-60-IWK-0001C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-IWK-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 04:34 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5298 | PS5-60-LA-0002A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 04:34 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5299 | PS5-60-LA-0002A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 04:34 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5302 | PS5-60-LA-0002C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00233-5303 | PS5-60-LA-0002C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00233-5304 | PS5-60-LA-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 08:33 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5305 | PS5-60-LA-0003-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP | 2026-06-19 08:32 | PS5-60-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5310 | PS5-60-SEA-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00233-5311 | PS5-60-SEA-0001-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00233-5312 | PS5-60-VS-9100A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-60-VS-9100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2026-06-19 04:53 | PS5-60-42 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5313 | PS5-60-VS-9100B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-60-VS-9100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2026-06-19 04:53 | PS5-60-43 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5319 | PS5-61-BI-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-05-25 17:35 | PS5-60-01 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00233-5320 | PS5-61-BI-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0001B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-05-25 17:35 | PS5-60-04 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-5581 | PS5-71-IN-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00233-5582 | PS5-71-IN-0002-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00233-5583 | PS5-71-IN-0002-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00233-5584 | PS5-71-IN-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004A TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-06-19 04:37 | PS5-71-23 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00233-5585 | PS5-71-IN-0003-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-06-IG-0004B TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-06-19 04:38 | PS5-71-23 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00233-5586 | PS5-71-IN-0003-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IH-0002 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-06-06 04:50 | PS5-71-23 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00233-5594 | PS5-71-MOV-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-06-11 04:56 | PS5-71-08 |  |  | LV Power Cable | E | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00233-5595 | PS5-71-MOV-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-06-04 17:59 | PS5-71-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00233-5596 | PS5-71-MOV-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-06-11 04:56 | PS5-71-08 |  |  | LV Power Cable | E | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00233-5597 | PS5-71-MOV-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-06-04 18:00 | PS5-71-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00233-5599 | PS5-71-MOV-0008-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-06-04 18:01 | PS5-71-08 |  |  | LV Power Cable | E | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00233-5601 | PS5-71-MOV-0010-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-61-IG-0042 TO PS5-71-MOV-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-06-11 04:57 | PS5-71-08 |  |  | LV Power Cable | E | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00233-9131 | PS5-60-BE-0007A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0007A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-06-27 08:56 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-9132 | PS5-60-BE-0007B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0007B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-06-27 09:13 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-9138 | PS5-60-BE-0027A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0027A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:40 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-9139 | PS5-60-BE-0027B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0027B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-9145 | PS5-60-BE-0028A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BE-0028A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:39 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-9146 | PS5-60-BE-0028B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BE-0028B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 13:25 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-9152 | PS5-60-BI-0006A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:38 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-9153 | PS5-60-BI-0006A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 14:12 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-9154 | PS5-60-BI-0006A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 13:28 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-9155 | PS5-60-BI-0006A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:36 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-9156 | PS5-60-BI-0006A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:34 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-9157 | PS5-60-BI-0006A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:33 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-9158 | PS5-60-BI-0006A-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:33 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-9159 | PS5-60-BI-0006A-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:32 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-9160 | PS5-60-BI-0006A-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 13:29 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-9161 | PS5-60-BI-0006A-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:32 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-9162 | PS5-60-BI-0006A-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:30 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-9163 | PS5-60-BI-0006B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:29 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-9164 | PS5-60-BI-0006B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 13:31 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-9165 | PS5-60-BI-0006B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 13:32 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-9166 | PS5-60-BI-0006B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:28 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-9167 | PS5-60-BI-0006B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:28 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-9168 | PS5-60-BI-0006B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:27 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-9169 | PS5-60-BI-0006B-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:26 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-9170 | PS5-60-BI-0006B-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:25 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-9171 | PS5-60-BI-0006B-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:25 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-9172 | PS5-60-BI-0006B-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:24 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-9173 | PS5-60-BI-0006B-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:24 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-9229 | PS5-60-BI-0017A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0017A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 2026-07-01 12:23 | PS5-60-56 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-9230 | PS5-60-BI-0017B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0017B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2026-07-01 12:23 | PS5-60-58 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-9236 | PS5-60-EA-2900A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002A TO PS5-60-EA-2900A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00233-9237 | PS5-60-EA-2900B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IN-0002B TO PS5-60-EA-2900B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00233-9244 | PS5-71-BE-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-07-03 09:19 | PS5-71-08 |  |  | LV Power Cable | E | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00233-9245 | PS5-71-BE-0004-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00233-9246 | PS5-71-BE-0004-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-07-03 09:21 | PS5-71-08 |  |  | LV Power Cable | E | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00233-9247 | PS5-71-BI-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2026-07-03 09:24 | PS5-71-08 |  |  | LV Power Cable | E | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00233-9248 | PS5-71-BI-0003-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00233-9249 | PS5-71-BI-0003-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00233-9250 | PS5-71-BI-0003-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00233-9251 | PS5-71-BI-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | LV Power Cable | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00233-9252 | PS5-71-BI-0005-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-01 12:21 | PS5-71-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00233-9253 | PS5-71-BI-0005-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-01 12:19 | PS5-71-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00233-9254 | PS5-71-BI-0005-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-01 14:11 | PS5-71-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00233-9255 | PS5-71-BI-0006-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-01 12:17 | PS5-71-22 |  |  | LV Power Cable | E | Closed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00234-2101 | PS5-60-IE-0002A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:36 | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00234-2102 | PS5-60-IE-0002A-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:36 | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00234-2103 | PS5-60-IE-0002A-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:37 | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00234-2104 | PS5-60-IE-0002B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:37 | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00234-2105 | PS5-60-IE-0002B-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:36 | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00234-2106 | PS5-60-IE-0002B-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:39 | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00234-2123 | PS5-60-IE-0003A-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 04:54 | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00234-2124 | PS5-60-IE-0003A-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:37 | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00234-2125 | PS5-60-IE-0003A-CD04 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0005A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 04:38 | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00234-2126 | PS5-60-IE-0003A-CD05 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:39 | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00234-2135 | PS5-60-IE-0003A-CD14 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-19 08:38 | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00234-2136 | PS5-60-IE-0003A-CD15 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-06-27 09:30 | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00234-2138 | PS5-60-IE-0003B-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:39 | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00234-2139 | PS5-60-IE-0003B-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:40 | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00234-2140 | PS5-60-IE-0003B-CD04 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0005B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:34 | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00234-2141 | PS5-60-IE-0003B-CD05 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-BI-0015B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 04:55 | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00234-2150 | PS5-60-IE-0003B-CD14 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-19 08:40 | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00234-2151 | PS5-60-IE-0003B-CD15 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-150101 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-06-27 09:31 | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00238-0457 | PS5-60-IE-0003A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GCP G-1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00238-0458 | PS5-60-IE-0003B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GCP G-2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00238-0464 | PS5-60-IE-0004 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | MCP- MASTER CONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00238-0465 | PS5-60-IH-0001A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GENSET MCC -1 - G1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00238-0466 | PS5-60-IH-0001B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | GENSET MCC -2 - G2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00238-0472 | PS5-60-IH-0002 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | COMMON / TREATMENT MCC | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00238-0473 | PS5-60-IE-0002A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00238-0474 | PS5-60-IE-0002B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | LOCAL DISPLAY PANEL LDP GENERATOR SET | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00238-0552 | PS5-60-IN-0002A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00238-0553 | PS5-60-IN-0002B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00238-0565 | PS5-71-IN-0002 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | CRO-PRE PRESSURECONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00238-0566 | PS5-71-IN-0003 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | DFO- PRE PRESSURE CONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00243-0059 | PS5-60-IJ-0001A |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Neutral Grounding resistor for Generator set 1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00243-0060 | PS5-60-IJ-0001B |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Neutral Grounding resistor for Generator set 2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Neutral Earthing Resistor | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00247-0146 | PS5 - POWER DISTRIBUTION AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-151148 | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 |  |  | Earthing System | E | To be completed | PS5 - Milestone A | 2026-07-20 | Priority-1
T-00247-0147 | PS5 - POWER GENERATION BUILDING AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-151152 | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 |  |  | Earthing System | E | To be completed | PS5 - Milestone A | 2026-07-20 | Priority-1
T-00247-0148 | PS5 - POWER GENERATION COOLING TOWER AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-151154 | PS5 - TZA - PS5 - Tanzania | PS5-63-01 - Electrical Earthing |  | PS5-63-01 |  |  | Earthing System | E | To be completed | PS5 - Milestone A | 2026-07-20 | Priority-1
T-00247-0160 | PS5-84-OB-0005_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing for Generator Electrical Building | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-151181 | PS5 - TZA - PS5 - Tanzania | PS5-63-03 - Electrical Earthing - Generator Building |  | PS5-63-03 |  |  | Earthing System | E | To be completed | PS5 - Milestone B | 2026-06-21 | Priority-1
T-00254-12960 | PS5-60-BI-0001A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-12961 | PS5-60-BI-0001B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-12967 | PS5-60-BI-0003-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-12968 | PS5-60-IE-0002A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-12969 | PS5-60-IE-0002A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-12970 | PS5-60-IE-0002A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-12971 | PS5-60-IE-0002B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-12972 | PS5-60-IE-0002B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-12973 | PS5-60-IE-0002B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-12989 | PS5-60-IH-0001A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-12990 | PS5-60-IH-0001A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-12991 | PS5-60-IH-0001B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-12992 | PS5-60-IH-0001B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-13003 | PS5-60-IH-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-13004 | PS5-60-IH-0002-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-13005 | PS5-60-LA-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-13006 | PS5-60-LA-0003-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-13007 | PS5-60-PIT-8113A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BE-0027A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-13008 | PS5-60-PIT-8113B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BE-0027B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00254-13014 | PS5-60-PIT-8114A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BE-0027A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-13015 | PS5-60-PIT-8114B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BE-0027B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00254-4900 | PS5-60-BE-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid |  | PS5-60-27 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-4901 | PS5-60-BE-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid |  | PS5-60-26 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-4902 | PS5-60-BE-0004A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0001A TO PS5-60-BE-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-4903 | PS5-60-BE-0004B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0001B TO PS5-60-BE-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-4909 | PS5-60-BI-0001A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-4910 | PS5-60-BI-0001A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-4911 | PS5-60-BI-0001B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-4912 | PS5-60-BI-0001B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-4923 | PS5-60-BI-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-4924 | PS5-60-BI-0002-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-4925 | PS5-60-BI-0002-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-4926 | PS5-60-BI-0002-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-4927 | PS5-60-BI-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-4928 | PS5-60-BI-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-4929 | PS5-60-BI-0004A-CCO1 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0004A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-4930 | PS5-60-BI-0004B-CCO1 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0004B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-4936 | PS5-60-BI-0005A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0005A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-4937 | PS5-60-BI-0005A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0005A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-4938 | PS5-60-BI-0005B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0005B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-4939 | PS5-60-BI-0005B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0005B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-4950 | PS5-60-BI-0006A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-4951 | PS5-60-BI-0006A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-4952 | PS5-60-BI-0006A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-4953 | PS5-60-BI-0006A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-4954 | PS5-60-BI-0006A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-4955 | PS5-60-BI-0006A-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-4956 | PS5-60-BI-0006B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-4957 | PS5-60-BI-0006B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00254-4958 | PS5-60-BI-0006B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00254-4959 | PS5-60-BI-0006B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00254-4960 | PS5-60-BI-0006B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00254-4961 | PS5-60-BI-0006B-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00254-4992 | PS5-60-BI-0008A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-4993 | PS5-60-BI-0008A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-4994 | PS5-60-BI-0008B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-4995 | PS5-60-BI-0008B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001A TO PS5-60-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-4996 | PS5-60-BI-0009A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0009A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-4997 | PS5-60-BI-0009A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0009A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-4998 | PS5-60-BI-0009B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0009B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-4999 | PS5-60-BI-0009B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IH-0001B TO PS5-60-BI-0009B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5020 | PS5-60-BI-0016A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5021 | PS5-60-BI-0016A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5022 | PS5-60-BI-0016A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-07-01 13:12 | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5023 | PS5-60-BI-0016A-CCO4 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5024 | PS5-60-BI-0016B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5025 | PS5-60-BI-0016B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5026 | PS5-60-BI-0016B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-07-01 13:13 | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5027 | PS5-60-BI-0016B-CCO4 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5048 | PS5-60-BI-0017A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002A TO PS5-60-BI-0017A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A |  | PS5-60-56 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5049 | PS5-60-BI-0017B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IN-0002B TO PS5-60-BI-0017B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B |  | PS5-60-58 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00254-5055 | PS5-60-BI-0019A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0019A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5056 | PS5-60-BI-0019A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-BI-0019A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5057 | PS5-60-BI-0019B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0019B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5058 | PS5-60-BI-0019B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-BI-0019B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5069 | PS5-60-IE-0002B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5075 | PS5-60-IE-0003A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5076 | PS5-60-IE-0003A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5077 | PS5-60-IE-0003A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5078 | PS5-60-IE-0003A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5079 | PS5-60-IE-0003A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5080 | PS5-60-IE-0003A-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5081 | PS5-60-IE-0003A-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5082 | PS5-60-IE-0003A-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5083 | PS5-60-IE-0003A-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5084 | PS5-60-IE-0003A-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5085 | PS5-60-IE-0003A-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5086 | PS5-60-IE-0003A-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5087 | PS5-60-IE-0003A-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5088 | PS5-60-IE-0003A-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5093 | PS5-60-IE-0003A-CC25 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41100A TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5094 | PS5-60-IE-0003A-CC26 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41100B TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5095 | PS5-60-IE-0003B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5096 | PS5-60-IE-0003B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5097 | PS5-60-IE-0003B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5098 | PS5-60-IE-0003B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5099 | PS5-60-IE-0003B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0001B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5100 | PS5-60-IE-0003B-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5101 | PS5-60-IE-0003B-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5102 | PS5-60-IE-0003B-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5103 | PS5-60-IE-0003B-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5104 | PS5-60-IE-0003B-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5105 | PS5-60-IE-0003B-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5106 | PS5-60-IE-0003B-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5107 | PS5-60-IE-0003B-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5108 | PS5-60-IE-0003B-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0002B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5113 | PS5-60-IE-0003B-CC25 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41200A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5114 | PS5-60-IE-0003B-CC26 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-TX-41200B TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5215 | PS5-60-IE-0004-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5216 | PS5-60-IE-0004-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5217 | PS5-60-IE-0004-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5218 | PS5-60-IE-0004-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5219 | PS5-60-IE-0004-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5220 | PS5-60-IE-0004-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5221 | PS5-60-IE-0004-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5225 | PS5-60-IN-0001A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5226 | PS5-60-IN-0001A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5227 | PS5-60-IN-0001A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5228 | PS5-60-IN-0001A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2026-07-01 13:18 | PS5-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5229 | PS5-60-IN-0001B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5230 | PS5-60-IN-0001B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5231 | PS5-60-IN-0001B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5232 | PS5-60-IN-0001B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2026-07-01 13:18 | PS5-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5253 | PS5-60-IN-0002A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5254 | PS5-60-IN-0002A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5255 | PS5-60-IN-0002A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5256 | PS5-60-IN-0002A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5257 | PS5-60-IN-0002A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5258 | PS5-60-IN-0002A-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5259 | PS5-60-IN-0002B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00254-5260 | PS5-60-IN-0002B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00254-5261 | PS5-60-IN-0002B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00254-5262 | PS5-60-IN-0002B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00254-5263 | PS5-60-IN-0002B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00254-5264 | PS5-60-IN-0002B-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00254-5296 | PS5-60-LA-0002A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5297 | PS5-60-LA-0002A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5298 | PS5-60-LA-0002A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5299 | PS5-60-LA-0002A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5300 | PS5-60-LA-0002A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5301 | PS5-60-LA-0002A-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5302 | PS5-60-LA-0002A-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5303 | PS5-60-LA-0002A-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5304 | PS5-60-LA-0002A-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5311 | PS5-60-LA-0002C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00254-5312 | PS5-60-LA-0002C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00254-5313 | PS5-60-LA-0002C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00254-5314 | PS5-60-LA-0002C-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00254-5315 | PS5-60-LA-0002C-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00254-5316 | PS5-60-LA-0002C-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00254-5317 | PS5-60-LA-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5328 | PS5-60-SEA-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00254-5329 | PS5-60-SEA-0001-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00254-5330 | PS5-60-SEA-0001-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00254-5331 | PS5-60-SEA-0001-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00254-5332 | PS5-60-SEA-0001-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00254-5333 | PS5-60-SEA-0001-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00254-5334 | PS5-60-SEA-0001-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00254-5335 | PS5-60-SEA-0001-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00254-5336 | PS5-60-SEA-0001-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00254-5337 | PS5-60-SEA-0001-CC12 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00254-5338 | PS5-60-SEA-0001-CC13 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003C TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00254-5339 | PS5-60-SEA-0001-CC14 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003D TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00254-5340 | PS5-60-SEA-0001-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003E TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00254-5341 | PS5-60-SEA-0001-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003F TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00254-5342 | PS5-60-SEA-0001-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003G TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00254-5351 | PS5-60-VS-9101A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-60-VS-9101A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A |  | PS5-60-42 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5352 | PS5-60-VS-9101B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-60-VS-9101B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B |  | PS5-60-43 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5358 | PS5-61-BI-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5359 | PS5-61-BI-0001-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5360 | PS5-61-BI-0001-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-61-TE-0003A TO PS5-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00254-5361 | PS5-61-BI-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5362 | PS5-61-BI-0002-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0003B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5363 | PS5-61-BI-0002-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-61-TE-0003B TO PS5-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00254-5390 | PS5-71-BI-0001A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5391 | PS5-71-BI-0001B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5394 | PS5-71-BI-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5395 | PS5-71-BI-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5396 | PS5-71-BI-0003-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5397 | PS5-71-BI-0003-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5398 | PS5-71-BI-0004-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0002 TO PS5-71-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5399 | PS5-71-BI-0005-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00254-5400 | PS5-71-BI-0005-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00254-5401 | PS5-71-BI-0006-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0003 TO PS5-71-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00254-5402 | PS5-71-BI-0008A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5403 | PS5-71-BI-0008A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5404 | PS5-71-BI-0008B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5405 | PS5-71-BI-0008B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5411 | PS5-71-BI-0011A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5412 | PS5-71-BI-0011A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5413 | PS5-71-BI-0011A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5414 | PS5-71-BI-0011A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5415 | PS5-71-BI-0011A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5416 | PS5-71-BI-0011B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5417 | PS5-71-BI-0011B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5418 | PS5-71-BI-0011B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5419 | PS5-71-BI-0011B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5420 | PS5-71-BI-0011B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-IN-0004A TO PS5-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module |  | PS5-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5479 | PS5-71-IN-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5480 | PS5-71-IN-0002-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5481 | PS5-71-IN-0002-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5482 | PS5-71-IN-0002-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5486 | PS5-71-IN-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00254-5487 | PS5-71-IN-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00254-5488 | PS5-71-IN-0003-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00254-5489 | PS5-71-IN-0003-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00254-5528 | PS5-71-MOV-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2120 TO PS5-71-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5529 | PS5-71-MOV-0001-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2124 TO PS5-71-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5530 | PS5-71-MOV-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2120 TO PS5-71-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00254-5531 | PS5-71-MOV-0002-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2124 TO PS5-71-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00254-5532 | PS5-71-MOV-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2121 TO PS5-71-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5533 | PS5-71-MOV-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2125 TO PS5-71-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5534 | PS5-71-MOV-0004-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2121 TO PS5-71-MOV-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00254-5535 | PS5-71-MOV-0004-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2125 TO PS5-71-MOV-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00254-5536 | PS5-71-MOV-0007-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2118 TO PS5-71-MOV-0007 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5537 | PS5-71-MOV-0007-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2122 TO PS5-71-MOV-0007 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5538 | PS5-71-MOV-0008-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2118 TO PS5-71-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00254-5539 | PS5-71-MOV-0008-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2122 TO PS5-71-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00254-5540 | PS5-71-MOV-0009-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2119 TO PS5-71-MOV-0009 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5541 | PS5-71-MOV-0009-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2123 TO PS5-71-MOV-0009 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules |  | PS5-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00254-5542 | PS5-71-MOV-0010-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2119 TO PS5-71-MOV-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00254-5543 | PS5-71-MOV-0010-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-71-BI-2123 TO PS5-71-MOV-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-68-WPR2-161503 | PS5 - TZA - PS5 - Tanzania | PS5-71-22 - Diesel Fuel Pre Pressure Module |  | PS5-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00256-0027 | PS5-60-IE-0004-CX03 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-SSF1-161401 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00256-0028 | PS5-60-IE-0004-CX04 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-SSF1-161401 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00256-0029 | PS5-60-LA-0003-CX01 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-SSF1-161401 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00256-0090 | PS5-60-LA-0003-CX02 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS5-04-PNC-0001 TO PS5-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00257-0173 | PS5-60-TW-0007B |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Thermowell | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00257-0175 | PS5-60-TW-0008A |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Thermowell | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00257-0182 | PS5-60-TW-0007A |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Thermowell | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00257-0184 | PS5-60-TW-0008B |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Thermowell | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00257-0194 | PS5-60-TW-0006B |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Thermowell | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00257-0198 | PS5-60-TW-0006A |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Thermowell | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00257-0207 | PS5-60-TW-0005A |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system |  | PS5-60-70 |  |  | Thermowell | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00257-0208 | PS5-60-TW-0005B |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system |  | PS5-60-71 |  |  | Thermowell | I | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00275-1945 | PS5-60-IE-0003B-CA02 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00275-1946 | PS5-60-IE-0003B-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00275-1947 | PS5-60-IE-0003B-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00275-1948 | PS5-60-IE-0003B-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00275-1968 | PS5-60-IE-0004-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00275-1969 | PS5-60-IE-0004-CA07 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00275-1970 | PS5-60-IE-0004-CA08 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00275-1971 | PS5-60-IE-0004-CA14 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00275-1972 | PS5-60-IE-0004-CA15 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00275-1973 | PS5-60-IE-0004-CA21 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00275-1974 | PS5-60-IH-0001A-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003G TO PS5-60-IH-0001A | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS5-60-03 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00275-1975 | PS5-60-IH-0001B-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0001B TO PS5-60-IH-0001B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS5-60-06 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00275-1981 | PS5-60-IN-0001A-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0001A | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A |  | PS5-60-49 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00275-1982 | PS5-60-IN-0001B-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0001B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B |  | PS5-60-50 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00275-1988 | PS5-60-IN-0002A-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003A TO PS5-60-IN-0002A | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) |  | PS5-60-57 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00275-1989 | PS5-60-IN-0002B-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0003B TO PS5-60-IN-0002B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) |  | PS5-60-59 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00275-1996 | PS5-60-LA-0002B-CA02 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | 2026-07-30 | Priority-1
T-00275-1997 | PS5-60-LA-0002B-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | 2026-07-30 | Priority-1
T-00275-1998 | PS5-60-LA-0002B-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002B | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-10 - Power Generation Package D |  | PS5-60-10 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | 2026-07-30 | Priority-1
T-00275-2001 | PS5-60-LA-0002C-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00275-2002 | PS5-60-LA-0002C-CA02 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00275-2003 | PS5-60-LA-0002C-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00275-2004 | PS5-60-LA-0002C-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002A TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00275-2005 | PS5-60-LA-0002C-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002B TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00275-2006 | PS5-60-LA-0002C-CA06 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-LA-0002B TO PS5-60-LA-0002C | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-60-16 - Power Generation Package F |  | PS5-60-16 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone D | 2026-07-31 | Priority-1
T-00275-2007 | PS5-60-SEA-0001-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00275-2010 | PS5-71-IN-0002-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00275-2011 | PS5-71-IN-0003-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS5-60-IE-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 6 |  |  | 0 | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  | RJ45 Cable | T | To be completed | PS5 - Milestone B | 2026-07-21 | Priority-1
T-00525-0026 | PS5-60-UR-8100A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE A | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2024-09-05 05:20 | PS5-60-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00525-0027 | PS5-60-UR-8100B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE B | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2024-09-05 05:21 | PS5-60-04 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00525-0219 | PS5-60-UA-5100 |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | COMPRESSOR AIR STARTING SKID | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-27 - Compressed Air Starting Skid | 2025-03-28 12:28 | PS5-60-27 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00525-0220 | PS5-60-UO-81100A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 2025-03-28 12:29 | PS5-60-49 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00525-0221 | PS5-60-UO-81100B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 2025-03-28 12:29 | PS5-60-50 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00525-0227 | PS5-60-UZ-8200A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-35 - Injector Tip Cooling Module A | 2025-05-05 12:03 | PS5-60-35 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00525-0228 | PS5-60-UZ-8200B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-36 - Injector Tip Cooling Module B | 2025-03-28 13:12 | PS5-60-36 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00525-0233 | PS5-60-VS-9100A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 2025-02-26 08:44 | PS5-60-42 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00525-0234 | PS5-60-VS-9100B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 2025-02-26 08:43 | PS5-60-43 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00525-0241 | PS5-71-UZ-6800A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | CRUDE FUEL SEPARATOR MODULE A | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2025-02-26 08:32 | PS5-71-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00525-0242 | PS5-71-UZ-6800B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | CRUDE FUEL SEPARATOR MODULE B | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-06 - Crude Fuel Separation Module | 2025-02-26 08:31 | PS5-71-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00525-0278 | PS5-60-UR-8100A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE A | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-135100 | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2025-02-26 08:28 | PS5-60-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00525-0279 | PS5-60-UR-8100B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION PACKAGE B | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-68-WPR2-135103 | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2025-02-26 08:09 | PS5-60-04 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00525-0466 | PS5-60-EA-2100A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2025-06-27 14:03 | PS5-60-70 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00525-0467 | PS5-60-EA-2100B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-70 - Engine A Cooling system | 2025-06-27 14:04 | PS5-60-70 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00525-0468 | PS5-60-EA-2200A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2025-06-27 14:05 | PS5-60-71 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00525-0469 | PS5-60-EA-2200B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-71 - Engine B Cooling system | 2025-06-27 14:05 | PS5-60-71 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00525-0546 | PS5-60-UZ-8900B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 2025-07-15 10:49 | PS5-60-58 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00525-0560 | PS5-71-UZ-6400 |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | CRUDE FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-71-08 - CFO Pre-Pressure Modules | 2025-07-16 08:17 | PS5-71-08 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00525-0561 | PS5-60-UR-8200A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2025-07-16 08:18 | PS5-60-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00525-0566 | PS5-60-UR-8200B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2025-07-16 08:21 | PS5-60-04 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00525-0570 | PS5-60-LA-0002A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | VTMS VIBRATION AND TEMPERATURE MONITORING SYSTEM | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2025-07-16 08:24 | PS5-60-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00525-0573 | PS5-60-SEA-0001 |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | GAS DETECTION PANEL | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2025-08-11 12:24 | PS5-03-14 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00525-0583 | PS5-60-UA-5200 |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | INSTRUMENT AIR COMPRESSOR MODULE | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-26 - Instrument Air Compressor Skid | 2026-04-18 05:35 | PS5-60-26 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | M | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00525-0609 | PS5-61-IU-0001B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 10 |  |  |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2025-09-11 06:52 | PS5-60-04 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00525-0899 | PS5-60-IJ-0001A |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | Neutral Grounding resistor for Generator set 1 (A) | EACOP | CPP AGI |  |  | 10 |  | 10 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A | 2026-05-22 10:05 | PS5-60-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00525-0900 | PS5-60-IJ-0001B |  |  |  |  | CZX01R - Package receiving inspection | PCOM - Precommissioning | M | Conformity Check | M - Mechanical | Neutral Grounding resistor for Generator set 2 (B) | EACOP | CPP AGI |  |  | 10 |  | 10 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B | 2026-05-22 10:06 | PS5-60-04 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00610-0220 | PS5-60-IE-0003A-CD06 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00610-0221 | PS5-60-IE-0003A-CD08 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00610-0222 | PS5-60-IE-0003A-CD12 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-01 - Power Generation Package A |  | PS5-60-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-17 | Priority-1
T-00610-0223 | PS5-60-IE-0003B-CD06 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00610-0224 | PS5-60-IE-0003B-CD08 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00610-0225 | PS5-60-IE-0003B-CD12 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-04 - Power Generation Package B |  | PS5-60-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00610-0241 | PS5-60-IE-0004-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00610-0242 | PS5-60-IE-0004-CD02 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00610-0574 | PS5-60-IE-0004-CD14 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00610-0575 | PS5-60-IE-0004-CD15 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00610-0576 | PS5-60-IE-0004-CD16 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS5-61-IJ-0001 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  | Multicore Electrical Control Cable | E | To be completed | PS5 - Milestone B | 2026-07-30 | Priority-1
T-00614-0853 | PS5-01-BI-1117-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0002 TO PS5-01-BI-1117 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00614-0854 | PS5-01-BI-1118-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0001 TO PS5-01-BI-1118 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00614-0856 | PS5-01-BI-1515-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0008 TO PS5-01-BI-1515 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00614-0859 | PS5-01-BI-2110-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0006 TO PS5-01-BI-2110 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00614-0893 | PS5-03-BI-2503-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2503 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00614-0896 | PS5-03-BI-2506-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0010 TO PS5-03-BI-2506 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00614-0899 | PS5-03-BI-2509-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0010 TO PS5-03-BI-2509 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00614-0903 | PS5-03-BI-2514-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2514 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00614-0904 | PS5-03-BI-2515-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0009 TO PS5-03-BI-2515 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-06-25 | Priority-1
T-00614-0953 | PS5-25-BI-1101-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0001 TO PS5-25-BI-1101 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0954 | PS5-25-BI-1102-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0002 TO PS5-25-BI-1102 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0955 | PS5-25-BI-1103-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0001 TO PS5-25-BI-1103 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:36 | PS5-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0956 | PS5-25-BI-1104-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0002 TO PS5-25-BI-1104 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:33 | PS5-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0957 | PS5-25-BI-1115-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0002 TO PS5-25-BI-1115 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0961 | PS5-25-BI-1201-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0001 TO PS5-25-BI-1201 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0965 | PS5-25-BI-1301-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0002 TO PS5-25-BI-1301 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0966 | PS5-25-BI-1302-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0002 TO PS5-25-BI-1302 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0967 | PS5-25-BI-1310-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0002 TO PS5-25-BI-1310 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0982 | PS5-25-BI-2103-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0006 TO PS5-25-BI-2103 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0983 | PS5-25-BI-2104-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0003 TO PS5-25-BI-2104 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0984 | PS5-25-BI-2105-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0006 TO PS5-25-BI-2105 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0985 | PS5-25-BI-2106-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0006 TO PS5-25-BI-2106 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0986 | PS5-25-BI-2108-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-25-BI-2108 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:27 | PS5-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0987 | PS5-25-BI-2109-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-25-BI-2109 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:29 | PS5-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0988 | PS5-25-BI-2201-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0001 TO PS5-25-BI-2201 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0989 | PS5-25-BI-2203-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0001 TO PS5-25-BI-2203 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0991 | PS5-25-BI-2301-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0003 TO PS5-25-BI-2301 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0992 | PS5-25-BI-2302-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0004 TO PS5-25-BI-2302 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0993 | PS5-25-BI-2305-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0003 TO PS5-25-BI-2305 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0994 | PS5-25-BI-2308-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0005 TO PS5-25-BI-2308 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:26 | PS5-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0995 | PS5-25-BI-2309-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0005 TO PS5-25-BI-2309 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0996 | PS5-25-BI-2312-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0003 TO PS5-25-BI-2312 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:32 | PS5-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0997 | PS5-25-BI-2315-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0003 TO PS5-25-BI-2315 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:28 | PS5-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-0998 | PS5-25-BI-2316-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0006 TO PS5-25-BI-2316 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:30 | PS5-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1014 | PS5-28-BI-1105-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0001 TO PS5-28-BI-1105 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1017 | PS5-28-BI-1303-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0001 TO PS5-28-BI-1303 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1018 | PS5-28-BI-1307-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0001 TO PS5-28-BI-1307 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1023 | PS5-50-BI-1107-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0002 TO PS5-50-BI-1107 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1030 | PS5-53-BI-1108-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0002 TO PS5-53-BI-1108 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1034 | PS5-60-IE-0003A-CC21 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  |  | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00614-1035 | PS5-60-IE-0003A-CC22 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  |  | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00614-1036 | PS5-60-IE-0003A-CC23 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0003 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  |  | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00614-1037 | PS5-60-IE-0003A-CC24 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-02 - Power Gen Package A (UCP) |  | PS5-60-02 |  |  |  | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00614-1038 | PS5-60-IE-0003B-CC21 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  |  | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00614-1039 | PS5-60-IE-0003B-CC22 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0005 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  |  | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00614-1040 | PS5-60-IE-0003B-CC23 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0003 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  |  | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00614-1041 | PS5-60-IE-0003B-CC24 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-05 - Power Gen Package B (UCP) |  | PS5-60-05 |  |  |  | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00614-1062 | PS5-60-IE-0004-CC08 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  |  | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00614-1063 | PS5-60-IE-0004-CC11 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0004 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  |  | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00614-1064 | PS5-60-IE-0004-CC12 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0005 TO PS5-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-60-22 - Power Gen Master UCP |  | PS5-60-22 |  |  |  | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00614-1065 | PS5-60-SEA-0001-CC18 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0009 TO PS5-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS5-03-14 |  |  |  | I | To be completed | PS5 - Milestone E | 2026-07-31 | Priority-1
T-00614-1078 | PS5-71-BI-1109-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0002 TO PS5-71-BI-1109 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1079 | PS5-71-BI-1110-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0001 TO PS5-71-BI-1110 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:22 | PS5-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1080 | PS5-71-BI-1111-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0002 TO PS5-71-BI-1111 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1082 | PS5-71-BI-1113-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0002 TO PS5-71-BI-1113 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1083 | PS5-71-BI-1116-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0002 TO PS5-71-BI-1116 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:23 | PS5-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1084 | PS5-71-BI-1117-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0001 TO PS5-71-BI-1117 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1085 | PS5-71-BI-2101-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-71-BI-2101 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | Started (not Completed) | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1086 | PS5-71-BI-1305-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0002 TO PS5-71-BI-1305 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1087 | PS5-71-BI-1306-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0002 TO PS5-71-BI-1306 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:25 | PS5-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1089 | PS5-71-BI-2107-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0006 TO PS5-71-BI-2107 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1090 | PS5-71-BI-2113-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0003 TO PS5-71-BI-2113 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1091 | PS5-71-BI-2114-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0006 TO PS5-71-BI-2114 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1092 | PS5-71-BI-2115-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-71-BI-2115 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1093 | PS5-71-BI-2116-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0003 TO PS5-71-BI-2116 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1094 | PS5-71-BI-2118-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0005 TO PS5-71-BI-2118 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1095 | PS5-71-BI-2119-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0005 TO PS5-71-BI-2119 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1096 | PS5-71-BI-2120-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0005 TO PS5-71-BI-2120 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1097 | PS5-71-BI-2121-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0005 TO PS5-71-BI-2121 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1098 | PS5-71-BI-2122-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-71-BI-2122 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1099 | PS5-71-BI-2123-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0006 TO PS5-71-BI-2123 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1100 | PS5-71-BI-2124-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0006 TO PS5-71-BI-2124 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1101 | PS5-71-BI-2125-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0006 TO PS5-71-BI-2125 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1102 | PS5-71-BI-2306-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0004 TO PS5-71-BI-2306 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1104 | PS5-71-BI-2310-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0006 TO PS5-71-BI-2310 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB |  | PS5-91-01 |  |  |  | I | To be completed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1106 | PS5-71-BI-2314-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0004 TO PS5-71-BI-2314 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-91-01 - Multicore cables & JB | 2026-06-27 08:39 | PS5-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS5 - Milestone A | 2026-07-31 | Priority-1
T-00614-1111 | PS5-71-IN-0002-CC05 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  |  | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00614-1112 | PS5-71-IN-0002-CC06 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0004 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  |  | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00614-1113 | PS5-71-IN-0002-CC07 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0006 TO PS5-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-09 - CFO Pre-Pressure Modules (UCP) |  | PS5-71-09 |  |  |  | I | To be completed | PS5 - Milestone H | 2026-07-31 | Priority-2
T-00614-1114 | PS5-71-IN-0003-CC05 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  |  | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00614-1115 | PS5-71-IN-0003-CC06 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0004 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  |  | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1
T-00614-1116 | PS5-71-IN-0003-CC07 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-03-SFMC-0006 TO PS5-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS5 - TZA - PS5 - Tanzania | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS5-71-23 |  |  |  | I | To be completed | PS5 - Milestone B | 2026-07-31 | Priority-1

## SUMMERY
PRIORITY 1 & PRIORITY 2 | [6 empty] | PRIORITY 1 & PRIORITY 2 |  |  |  |  | TASK ID | RFC | P-1,2,3
DATES | EIT MONTHLY PLAN |  |  | MECH & PIPING MONTHLY PLAN |  |  | Discipline | Total | Closed | % | Open | T-00018-0192 | 2026-07-17 | Priority-1
| PLAN | ACTUAL | BACKLOG | PLAN | ACTUAL | BACKLOG | [5 empty] | T-00018-0193 | 2026-07-30 | Priority-1
2026-07-01 | 34 | 35 | -1 | 4 | 0 | 4 | CPP |  |  |  |  | T-00022-3334 | 2026-07-17 | Priority-1
2026-07-02 | 33 | 0 | 33 | 9 | 4 | 5 | Mechanical | 65 | 65 | 100% | 0 | T-00022-3335 | 2026-07-30 | Priority-1
2026-07-03 | 66 | 3 | 63 | 10 | 0 | 10 | Piping & Vessel | 350 | 212 | 60.57% | 138 | T-00022-3377 | 2026-07-17 | Priority-1
2026-07-04 | 96 |  |  | 15 |  |  | Total | 415 | 277 | 66.75% | 138 | T-00022-3378 | 2026-07-17 | Priority-1
2026-07-05 | 33 |  |  | 5 |  |  | EIT |  |  |  |  | T-00022-3379 | 2026-07-17 | Priority-1
2026-07-06 | 33 |  |  | 5 |  |  | Electrical | 521 | 183 | 35.12% | 338 | T-00022-3380 | 2026-07-30 | Priority-1
2026-07-07 | 33 |  |  | 5 |  |  | Instrumentation | 671 | 78 | 11.62% | 593 | T-00022-3381 | 2026-07-30 | Priority-1
2026-07-08 | 33 |  |  | 5 |  |  | Telecom | 56 | 0 | 0% | 56 | T-00022-3382 | 2026-07-30 | Priority-1
2026-07-09 | 33 |  |  | 5 |  |  | Total | 1248 | 261 | 20.91% | 987 | T-00022-3410 | 2026-07-17 | Priority-1
2026-07-10 | 33 |  |  | 5 |  |  | Grand Total | 1663 | 538 | 32.35% | 1125 | T-00022-3411 | 2026-07-17 | Priority-1
2026-07-11 | 33 |  |  | 4 | [7 empty] | T-00022-3412 | 2026-07-17 | Priority-1
2026-07-12 | 33 |  |  | 5 | [7 empty] | T-00022-3413 | 2026-07-30 | Priority-1
2026-07-13 | 33 |  |  | 4 |  |  | PRIORITY 1 |  |  |  |  | T-00022-3414 | 2026-07-30 | Priority-1
2026-07-14 | 33 |  |  | 5 |  |  | DISCIPILINE | TOTAL TASK IDs | TOTAL CLOSED | BALANCE | % | T-00022-3415 | 2026-07-30 | Priority-1
2026-07-15 | 33 |  |  | 4 |  |  | EIT | 1135 | 254 | 881 | 22.38% | T-00023-10536 | 2026-07-17 | Priority-1
2026-07-16 | 33 |  |  | 5 |  |  | PIPING ANG MECH | 374 | 250 | 124 | 66.84% | T-00023-10537 | 2026-07-31 | Priority-1
2026-07-17 | 33 |  |  | 4 | [7 empty] | T-00023-10593 | 2026-07-17 | Priority-1
2026-07-18 | 33 |  |  | 5 |  |  | PRIORITY 2 |  |  |  |  | T-00023-10594 | 2026-07-30 | Priority-1
2026-07-19 | 33 |  |  | 4 |  |  | DISCIPILINE | TOTAL TASK IDs | TOTAL CLOSED | BALANCE | % | T-00023-10600 | 2026-07-30 | Priority-1
2026-07-20 | 33 |  |  | 5 |  |  | EIT | 113 | 7 | 106 | 6.195% | T-00023-10601 | 2026-07-30 | Priority-1
2026-07-21 | 33 |  |  | 4 |  |  | PIPING ANG MECH | 41 | 27 | 14 | 65.85% | T-00023-10887 | 2026-07-30 | Priority-1
2026-07-22 | 33 |  |  | 5 | [7 empty] | T-00023-10888 | 2026-07-30 | Priority-1
2026-07-23 | 33 |  |  | 4 | [7 empty] | T-00023-10889 | 2026-07-31 | Priority-1
2026-07-24 | 33 |  |  | 5 | [7 empty] | T-00023-10890 | 2026-07-31 | Priority-1
2026-07-25 | 33 |  |  | 4 | [7 empty] | T-00023-10901 | 2026-07-17 | Priority-1
2026-07-26 | 33 |  |  | 5 | [7 empty] | T-00023-4978 | 2026-07-17 | Priority-1
2026-07-27 | 33 |  |  | 5 | [7 empty] | T-00023-4979 | 2026-07-17 | Priority-1
2026-07-28 | 33 |  |  | 5 | [7 empty] | T-00023-4981 | 2026-07-17 | Priority-1
2026-07-29 | 33 |  |  | 5 | [7 empty] | T-00023-4982 | 2026-07-17 | Priority-1
2026-07-30 | 33 |  |  | 5 | [7 empty] | T-00023-4983 | 2026-07-17 | Priority-1
2026-07-31 | 33 |  |  | 5 | [7 empty] | T-00023-4984 | 2026-07-17 | Priority-1
TOTAL | [11 empty] | T-00023-4986 | 2026-07-17 | Priority-1
[12 empty] | T-00023-4987 | 2026-07-17 | Priority-1
[12 empty] | T-00023-4988 | 2026-07-30 | Priority-1
[12 empty] | T-00023-4994 | 2026-07-30 | Priority-1
[12 empty] | T-00023-4995 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5001 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5002 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5008 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5009 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5010 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5011 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5012 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5013 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5014 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5015 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5016 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5017 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5018 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5019 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5020 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5021 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5022 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5023 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5024 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5025 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5026 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5027 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5028 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5029 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5030 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5031 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5092 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5093 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5094 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5095 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5096 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5097 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5108 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5109 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5115 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5116 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5117 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5118 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5129 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5130 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5136 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5137 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5138 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5139 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5140 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5141 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5157 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5166 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5167 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5168 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5169 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5170 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5171 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5187 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5188 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5189 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5190 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5201 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5202 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5204 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5205 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5206 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5207 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5208 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5209 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5211 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5212 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5213 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5214 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5215 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5216 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5254 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5255 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5256 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5257 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5258 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5259 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5260 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5261 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5262 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5263 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5264 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5265 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5271 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5272 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5273 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5274 | 2026-07-31 | Priority-1
[12 empty] | T-00023-5275 | 2026-07-31 | Priority-1
[12 empty] | T-00023-5276 | 2026-07-31 | Priority-1
[12 empty] | T-00023-5292 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5293 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5294 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5295 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5296 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5297 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5298 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5299 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5302 | 2026-07-31 | Priority-1
[12 empty] | T-00023-5303 | 2026-07-31 | Priority-1
[12 empty] | T-00023-5304 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5305 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5310 | 2026-07-31 | Priority-1
[12 empty] | T-00023-5311 | 2026-07-31 | Priority-1
[12 empty] | T-00023-5312 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5313 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5319 | 2026-07-17 | Priority-1
[12 empty] | T-00023-5320 | 2026-07-30 | Priority-1
[12 empty] | T-00023-5581 | 2026-07-31 | Priority-2
[12 empty] | T-00023-5582 | 2026-07-31 | Priority-2
[12 empty] | T-00023-5583 | 2026-07-31 | Priority-2
[12 empty] | T-00023-5584 | 2026-07-21 | Priority-1
[12 empty] | T-00023-5585 | 2026-07-21 | Priority-1
[12 empty] | T-00023-5586 | 2026-07-21 | Priority-1
[12 empty] | T-00023-5594 | 2026-07-31 | Priority-2
[12 empty] | T-00023-5595 | 2026-07-21 | Priority-1
[12 empty] | T-00023-5596 | 2026-07-31 | Priority-2
[12 empty] | T-00023-5597 | 2026-07-21 | Priority-1
[12 empty] | T-00023-5599 | 2026-07-31 | Priority-2
[12 empty] | T-00023-5601 | 2026-07-31 | Priority-2
[12 empty] | T-00023-9131 | 2026-07-30 | Priority-1
[12 empty] | T-00023-9132 | 2026-07-31 | Priority-1
[12 empty] | T-00023-9138 | 2026-07-30 | Priority-1
[12 empty] | T-00023-9139 | 2026-07-31 | Priority-1
[12 empty] | T-00023-9145 | 2026-07-30 | Priority-1
[12 empty] | T-00023-9146 | 2026-07-31 | Priority-1
[12 empty] | T-00023-9152 | 2026-07-30 | Priority-1
[12 empty] | T-00023-9153 | 2026-07-30 | Priority-1
[12 empty] | T-00023-9154 | 2026-07-30 | Priority-1
[12 empty] | T-00023-9155 | 2026-07-30 | Priority-1
[12 empty] | T-00023-9156 | 2026-07-30 | Priority-1
[12 empty] | T-00023-9157 | 2026-07-30 | Priority-1
[12 empty] | T-00023-9158 | 2026-07-30 | Priority-1
[12 empty] | T-00023-9159 | 2026-07-30 | Priority-1
[12 empty] | T-00023-9160 | 2026-07-30 | Priority-1
[12 empty] | T-00023-9161 | 2026-07-30 | Priority-1
[12 empty] | T-00023-9162 | 2026-07-30 | Priority-1
[12 empty] | T-00023-9163 | 2026-07-31 | Priority-1
[12 empty] | T-00023-9164 | 2026-07-31 | Priority-1
[12 empty] | T-00023-9165 | 2026-07-31 | Priority-1
[12 empty] | T-00023-9166 | 2026-07-31 | Priority-1
[12 empty] | T-00023-9167 | 2026-07-31 | Priority-1
[12 empty] | T-00023-9168 | 2026-07-31 | Priority-1
[12 empty] | T-00023-9169 | 2026-07-31 | Priority-1
[12 empty] | T-00023-9170 | 2026-07-31 | Priority-1
[12 empty] | T-00023-9171 | 2026-07-31 | Priority-1
[12 empty] | T-00023-9172 | 2026-07-31 | Priority-1
[12 empty] | T-00023-9173 | 2026-07-31 | Priority-1
[12 empty] | T-00023-9229 | 2026-07-30 | Priority-1
[12 empty] | T-00023-9230 | 2026-07-31 | Priority-1
[12 empty] | T-00023-9236 | 2026-07-30 | Priority-1
[12 empty] | T-00023-9237 | 2026-07-31 | Priority-1
[12 empty] | T-00023-9244 | 2026-07-31 | Priority-2
[12 empty] | T-00023-9245 | 2026-07-31 | Priority-2
[12 empty] | T-00023-9246 | 2026-07-31 | Priority-2
[12 empty] | T-00023-9247 | 2026-07-31 | Priority-2
[12 empty] | T-00023-9248 | 2026-07-31 | Priority-2
[12 empty] | T-00023-9249 | 2026-07-31 | Priority-2
[12 empty] | T-00023-9250 | 2026-07-31 | Priority-2
[12 empty] | T-00023-9251 | 2026-07-31 | Priority-2
[12 empty] | T-00023-9252 | 2026-07-21 | Priority-1
[12 empty] | T-00023-9253 | 2026-07-21 | Priority-1
[12 empty] | T-00023-9254 | 2026-07-21 | Priority-1
[12 empty] | T-00023-9255 | 2026-07-21 | Priority-1
[12 empty] | T-00024-2101 | 2026-07-17 | Priority-1
[12 empty] | T-00024-2102 | 2026-07-17 | Priority-1
[12 empty] | T-00024-2103 | 2026-07-17 | Priority-1
[12 empty] | T-00024-2104 | 2026-07-30 | Priority-1
[12 empty] | T-00024-2105 | 2026-07-30 | Priority-1
[12 empty] | T-00024-2106 | 2026-07-30 | Priority-1
[12 empty] | T-00024-2123 | 2026-07-17 | Priority-1
[12 empty] | T-00024-2124 | 2026-07-17 | Priority-1
[12 empty] | T-00024-2125 | 2026-07-17 | Priority-1
[12 empty] | T-00024-2126 | 2026-07-17 | Priority-1
[12 empty] | T-00024-2135 | 2026-07-17 | Priority-1
[12 empty] | T-00024-2136 | 2026-07-17 | Priority-1
[12 empty] | T-00024-2138 | 2026-07-30 | Priority-1
[12 empty] | T-00024-2139 | 2026-07-30 | Priority-1
[12 empty] | T-00024-2140 | 2026-07-30 | Priority-1
[12 empty] | T-00024-2141 | 2026-07-30 | Priority-1
[12 empty] | T-00024-2150 | 2026-07-30 | Priority-1
[12 empty] | T-00024-2151 | 2026-07-30 | Priority-1
[12 empty] | T-00034-0059 | 2026-07-17 | Priority-1
[12 empty] | T-00034-0060 | 2026-07-30 | Priority-1
[12 empty] | T-00039-0295 | 2026-07-20 | Priority-1
[12 empty] | T-00039-0296 | 2026-07-20 | Priority-1
[12 empty] | T-00039-0297 | 2026-07-20 | Priority-1
[12 empty] | T-00039-0309 | 2026-06-21 | Priority-1
[12 empty] | T-00044-0090 | 2026-07-17 | Priority-1
[12 empty] | T-00044-0091 | 2026-07-30 | Priority-1
[12 empty] | T-00044-0097 | 2026-07-30 | Priority-1
[12 empty] | T-00044-0098 | 2026-07-17 | Priority-1
[12 empty] | T-00044-0099 | 2026-07-30 | Priority-1
[12 empty] | T-00044-0105 | 2026-07-30 | Priority-1
[12 empty] | T-00044-0106 | 2026-07-17 | Priority-1
[12 empty] | T-00044-0107 | 2026-07-30 | Priority-1
[12 empty] | T-00044-0185 | 2026-07-17 | Priority-1
[12 empty] | T-00044-0186 | 2026-07-31 | Priority-1
[12 empty] | T-00044-0198 | 2026-07-31 | Priority-2
[12 empty] | T-00044-0199 | 2026-07-21 | Priority-1
[12 empty] | T-00046-0291 | 2026-07-17 | Priority-1
[12 empty] | T-00046-0292 | 2026-07-30 | Priority-1
[12 empty] | T-00046-0300 | 2026-07-17 | Priority-1
[12 empty] | T-00046-0301 | 2026-07-30 | Priority-1
[12 empty] | T-00046-0302 | 2026-07-30 | Priority-1
[12 empty] | T-00046-0308 | 2026-07-17 | Priority-1
[12 empty] | T-00046-0309 | 2026-07-17 | Priority-1
[12 empty] | T-00046-0314 | 2026-07-17 | Priority-1
[12 empty] | T-00046-0315 | 2026-07-17 | Priority-1
[12 empty] | T-00046-0322 | 2026-07-31 | Priority-2
[12 empty] | T-00046-0323 | 2026-07-31 | Priority-2
[12 empty] | T-00046-0327 | 2026-07-17 | Priority-1
[12 empty] | T-00046-0328 | 2026-07-17 | Priority-1
[12 empty] | T-00046-0329 | 2026-07-17 | Priority-1
[12 empty] | T-00046-0330 | 2026-07-30 | Priority-1
[12 empty] | T-00046-0336 | 2026-07-17 | Priority-1
[12 empty] | T-00046-0337 | 2026-07-30 | Priority-1
[12 empty] | T-00046-0343 | 2026-07-17 | Priority-1
[12 empty] | T-00046-0344 | 2026-07-17 | Priority-1
[12 empty] | T-00046-0355 | 2026-07-17 | Priority-1
[12 empty] | T-00046-0356 | 2026-07-17 | Priority-1
[12 empty] | T-00046-0362 | 2026-07-30 | Priority-1
[12 empty] | T-00046-0363 | 2026-07-31 | Priority-1
[12 empty] | T-00046-0369 | 2026-07-17 | Priority-1
[12 empty] | T-00046-0370 | 2026-07-17 | Priority-1
[12 empty] | T-00046-0376 | 2026-07-17 | Priority-1
[12 empty] | T-00046-0377 | 2026-07-17 | Priority-1
[12 empty] | T-00046-0383 | 2026-07-17 | Priority-1
[12 empty] | T-00046-0384 | 2026-07-17 | Priority-1
[12 empty] | T-00046-0385 | 2026-07-30 | Priority-1
[12 empty] | T-00046-0392 | 2026-07-30 | Priority-1
[12 empty] | T-00046-0393 | 2026-07-31 | Priority-1
[12 empty] | T-00046-0400 | 2026-07-31 | Priority-2
[12 empty] | T-00046-0401 | 2026-07-21 | Priority-1
[12 empty] | T-00046-0552 | 2026-07-17 | Priority-1
[12 empty] | T-00046-0553 | 2026-07-17 | Priority-1
[12 empty] | T-00069-12948 | 2026-07-17 | Priority-1
[12 empty] | T-00069-12949 | 2026-07-30 | Priority-1
[12 empty] | T-00069-12955 | 2026-07-30 | Priority-1
[12 empty] | T-00069-12956 | 2026-07-17 | Priority-1
[12 empty] | T-00069-12957 | 2026-07-17 | Priority-1
[12 empty] | T-00069-12958 | 2026-07-17 | Priority-1
[12 empty] | T-00069-12959 | 2026-07-30 | Priority-1
[12 empty] | T-00069-12960 | 2026-07-30 | Priority-1
[12 empty] | T-00069-12961 | 2026-07-30 | Priority-1
[12 empty] | T-00069-12977 | 2026-07-17 | Priority-1
[12 empty] | T-00069-12978 | 2026-07-17 | Priority-1
[12 empty] | T-00069-12979 | 2026-07-30 | Priority-1
[12 empty] | T-00069-12980 | 2026-07-30 | Priority-1
[12 empty] | T-00069-12991 | 2026-07-30 | Priority-1
[12 empty] | T-00069-12992 | 2026-07-30 | Priority-1
[12 empty] | T-00069-12993 | 2026-07-30 | Priority-1
[12 empty] | T-00069-12994 | 2026-07-30 | Priority-1
[12 empty] | T-00069-12995 | 2026-07-30 | Priority-1
[12 empty] | T-00069-12996 | 2026-07-31 | Priority-1
[12 empty] | T-00069-13002 | 2026-07-30 | Priority-1
[12 empty] | T-00069-13003 | 2026-07-31 | Priority-1
[12 empty] | T-00069-4888 | 2026-07-17 | Priority-1
[12 empty] | T-00069-4889 | 2026-07-17 | Priority-1
[12 empty] | T-00069-4890 | 2026-07-30 | Priority-1
[12 empty] | T-00069-4891 | 2026-07-30 | Priority-1
[12 empty] | T-00069-4897 | 2026-07-17 | Priority-1
[12 empty] | T-00069-4898 | 2026-07-17 | Priority-1
[12 empty] | T-00069-4899 | 2026-07-30 | Priority-1
[12 empty] | T-00069-4900 | 2026-07-30 | Priority-1
[12 empty] | T-00069-4911 | 2026-07-30 | Priority-1
[12 empty] | T-00069-4912 | 2026-07-30 | Priority-1
[12 empty] | T-00069-4913 | 2026-07-30 | Priority-1
[12 empty] | T-00069-4914 | 2026-07-30 | Priority-1
[12 empty] | T-00069-4915 | 2026-07-30 | Priority-1
[12 empty] | T-00069-4916 | 2026-07-30 | Priority-1
[12 empty] | T-00069-4917 | 2026-07-17 | Priority-1
[12 empty] | T-00069-4918 | 2026-07-30 | Priority-1
[12 empty] | T-00069-4924 | 2026-07-17 | Priority-1
[12 empty] | T-00069-4925 | 2026-07-17 | Priority-1
[12 empty] | T-00069-4926 | 2026-07-30 | Priority-1
[12 empty] | T-00069-4927 | 2026-07-30 | Priority-1
[12 empty] | T-00069-4938 | 2026-07-17 | Priority-1
[12 empty] | T-00069-4939 | 2026-07-17 | Priority-1
[12 empty] | T-00069-4940 | 2026-07-17 | Priority-1
[12 empty] | T-00069-4941 | 2026-07-17 | Priority-1
[12 empty] | T-00069-4942 | 2026-07-17 | Priority-1
[12 empty] | T-00069-4943 | 2026-07-17 | Priority-1
[12 empty] | T-00069-4944 | 2026-07-30 | Priority-1
[12 empty] | T-00069-4945 | 2026-07-31 | Priority-1
[12 empty] | T-00069-4946 | 2026-07-31 | Priority-1
[12 empty] | T-00069-4947 | 2026-07-31 | Priority-1
[12 empty] | T-00069-4948 | 2026-07-31 | Priority-1
[12 empty] | T-00069-4949 | 2026-07-31 | Priority-1
[12 empty] | T-00069-4980 | 2026-07-17 | Priority-1
[12 empty] | T-00069-4981 | 2026-07-17 | Priority-1
[12 empty] | T-00069-4982 | 2026-07-17 | Priority-1
[12 empty] | T-00069-4983 | 2026-07-17 | Priority-1
[12 empty] | T-00069-4984 | 2026-07-30 | Priority-1
[12 empty] | T-00069-4985 | 2026-07-30 | Priority-1
[12 empty] | T-00069-4986 | 2026-07-30 | Priority-1
[12 empty] | T-00069-4987 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5008 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5009 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5010 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5011 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5012 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5013 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5014 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5015 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5036 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5037 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5043 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5044 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5045 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5046 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5057 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5063 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5064 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5065 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5066 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5067 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5068 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5069 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5070 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5071 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5072 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5073 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5074 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5075 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5076 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5081 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5082 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5083 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5084 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5085 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5086 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5087 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5088 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5089 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5090 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5091 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5092 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5093 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5094 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5095 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5096 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5101 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5102 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5203 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5204 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5205 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5206 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5207 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5208 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5209 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5213 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5214 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5215 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5216 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5217 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5218 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5219 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5220 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5241 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5242 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5243 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5244 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5245 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5246 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5247 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5248 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5249 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5250 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5251 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5252 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5284 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5285 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5286 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5287 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5288 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5289 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5290 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5291 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5292 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5299 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5300 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5301 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5302 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5303 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5304 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5305 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5316 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5317 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5318 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5319 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5320 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5321 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5322 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5323 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5324 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5325 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5326 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5327 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5328 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5329 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5330 | 2026-07-31 | Priority-1
[12 empty] | T-00069-5339 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5340 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5346 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5347 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5348 | 2026-07-17 | Priority-1
[12 empty] | T-00069-5349 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5350 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5351 | 2026-07-30 | Priority-1
[12 empty] | T-00069-5378 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5379 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5382 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5383 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5384 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5385 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5386 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5387 | 2026-07-21 | Priority-1
[12 empty] | T-00069-5388 | 2026-07-21 | Priority-1
[12 empty] | T-00069-5389 | 2026-07-21 | Priority-1
[12 empty] | T-00069-5390 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5391 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5392 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5393 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5399 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5400 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5401 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5402 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5403 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5404 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5405 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5406 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5407 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5408 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5467 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5468 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5469 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5470 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5474 | 2026-07-21 | Priority-1
[12 empty] | T-00069-5475 | 2026-07-21 | Priority-1
[12 empty] | T-00069-5476 | 2026-07-21 | Priority-1
[12 empty] | T-00069-5477 | 2026-07-21 | Priority-1
[12 empty] | T-00069-5516 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5517 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5518 | 2026-07-21 | Priority-1
[12 empty] | T-00069-5519 | 2026-07-21 | Priority-1
[12 empty] | T-00069-5520 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5521 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5522 | 2026-07-21 | Priority-1
[12 empty] | T-00069-5523 | 2026-07-21 | Priority-1
[12 empty] | T-00069-5524 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5525 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5526 | 2026-07-21 | Priority-1
[12 empty] | T-00069-5527 | 2026-07-21 | Priority-1
[12 empty] | T-00069-5528 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5529 | 2026-07-31 | Priority-2
[12 empty] | T-00069-5530 | 2026-07-21 | Priority-1
[12 empty] | T-00069-5531 | 2026-07-21 | Priority-1
[12 empty] | T-00071-0027 | 2026-07-30 | Priority-1
[12 empty] | T-00071-0028 | 2026-07-30 | Priority-1
[12 empty] | T-00071-0029 | 2026-07-30 | Priority-1
[12 empty] | T-00071-0090 | 2026-07-30 | Priority-1
[12 empty] | T-00072-0173 | 2026-07-17 | Priority-1
[12 empty] | T-00072-0175 | 2026-07-17 | Priority-1
[12 empty] | T-00072-0182 | 2026-07-17 | Priority-1
[12 empty] | T-00072-0184 | 2026-07-17 | Priority-1
[12 empty] | T-00072-0194 | 2026-07-17 | Priority-1
[12 empty] | T-00072-0198 | 2026-07-17 | Priority-1
[12 empty] | T-00072-0207 | 2026-07-17 | Priority-1
[12 empty] | T-00072-0208 | 2026-07-17 | Priority-1
[12 empty] | T-00075-0211 | 2026-07-17 | Priority-1
[12 empty] | T-00075-0218 | 2026-07-17 | Priority-1
[12 empty] | T-00075-0239 | 2026-07-17 | Priority-1
[12 empty] | T-00075-0265 | 2026-07-17 | Priority-1
[12 empty] | T-00075-0270 | 2026-07-17 | Priority-1
[12 empty] | T-00075-0271 | 2026-07-17 | Priority-1
[12 empty] | T-00075-0272 | 2026-07-17 | Priority-1
[12 empty] | T-00075-0273 | 2026-07-17 | Priority-1
[12 empty] | T-00078-0140 | 2026-07-31 | Priority-2
[12 empty] | T-00078-0143 | 2026-07-21 | Priority-1
[12 empty] | T-00078-0144 | 2026-07-31 | Priority-2
[12 empty] | T-00078-0147 | 2026-07-21 | Priority-1
[12 empty] | T-00078-0149 | 2026-07-31 | Priority-2
[12 empty] | T-00078-0151 | 2026-07-21 | Priority-1
[12 empty] | T-00078-0152 | 2026-07-21 | Priority-1
[12 empty] | T-00078-0153 | 2026-07-31 | Priority-2
[12 empty] | T-00082-0460 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0461 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0463 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0466 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0484 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0487 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0490 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0494 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0495 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0500 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0501 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0502 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0503 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0504 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0508 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0512 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0513 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0514 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0517 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0518 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0519 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0520 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0521 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0522 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0523 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0524 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0526 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0527 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0528 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0529 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0530 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0531 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0532 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0533 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0534 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0537 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0538 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0540 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0541 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0543 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0544 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0545 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0547 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0548 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0549 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0550 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0551 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0553 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0554 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0555 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0556 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0557 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0558 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0559 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0560 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0561 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0562 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0563 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0564 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0565 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0566 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0567 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0569 | 2026-06-25 | Priority-1
[12 empty] | T-00082-0571 | 2026-06-25 | Priority-1
[12 empty] | T-00087-0105 | 2026-07-31 | Priority-1
[12 empty] | T-00087-0500 | 2026-07-17 | Priority-1
[12 empty] | T-00087-0501 | 2026-07-30 | Priority-1
[12 empty] | T-00087-0502 | 2026-07-31 | Priority-1
[12 empty] | T-00087-0528 | 2026-07-30 | Priority-1
[12 empty] | T-00090-0179 | 2026-07-17 | Priority-1
[12 empty] | T-00090-0180 | 2026-07-30 | Priority-1
[12 empty] | T-00090-0188 | 2026-07-17 | Priority-1
[12 empty] | T-00090-0189 | 2026-07-30 | Priority-1
[12 empty] | T-00090-0190 | 2026-07-30 | Priority-1
[12 empty] | T-00090-0196 | 2026-07-17 | Priority-1
[12 empty] | T-00090-0197 | 2026-07-17 | Priority-1
[12 empty] | T-00090-0202 | 2026-07-17 | Priority-1
[12 empty] | T-00090-0203 | 2026-07-17 | Priority-1
[12 empty] | T-00090-0210 | 2026-07-31 | Priority-2
[12 empty] | T-00090-0211 | 2026-07-31 | Priority-2
[12 empty] | T-00090-0215 | 2026-07-17 | Priority-1
[12 empty] | T-00090-0216 | 2026-07-17 | Priority-1
[12 empty] | T-00090-0217 | 2026-07-17 | Priority-1
[12 empty] | T-00090-0218 | 2026-07-30 | Priority-1
[12 empty] | T-00090-0224 | 2026-07-17 | Priority-1
[12 empty] | T-00090-0225 | 2026-07-30 | Priority-1
[12 empty] | T-00090-0231 | 2026-07-17 | Priority-1
[12 empty] | T-00090-0232 | 2026-07-17 | Priority-1
[12 empty] | T-00090-0243 | 2026-07-17 | Priority-1
[12 empty] | T-00090-0244 | 2026-07-17 | Priority-1
[12 empty] | T-00090-0250 | 2026-07-30 | Priority-1
[12 empty] | T-00090-0251 | 2026-07-31 | Priority-1
[12 empty] | T-00090-0257 | 2026-07-17 | Priority-1
[12 empty] | T-00090-0258 | 2026-07-17 | Priority-1
[12 empty] | T-00090-0264 | 2026-07-17 | Priority-1
[12 empty] | T-00090-0265 | 2026-07-17 | Priority-1
[12 empty] | T-00090-0271 | 2026-07-17 | Priority-1
[12 empty] | T-00090-0272 | 2026-07-17 | Priority-1
[12 empty] | T-00090-0273 | 2026-07-30 | Priority-1
[12 empty] | T-00090-0280 | 2026-07-30 | Priority-1
[12 empty] | T-00090-0281 | 2026-07-31 | Priority-1
[12 empty] | T-00090-0288 | 2026-07-31 | Priority-2
[12 empty] | T-00090-0289 | 2026-07-21 | Priority-1
[12 empty] | T-00090-0436 | 2026-07-17 | Priority-1
[12 empty] | T-00090-0437 | 2026-07-17 | Priority-1
[12 empty] | T-00115-0006 | 2026-07-30 | Priority-1
[12 empty] | T-00115-0007 | 2026-07-31 | Priority-1
[12 empty] | T-00135-0220 | 2026-07-17 | Priority-1
[12 empty] | T-00135-0221 | 2026-07-30 | Priority-1
[12 empty] | T-00135-0229 | 2026-07-17 | Priority-1
[12 empty] | T-00135-0230 | 2026-07-30 | Priority-1
[12 empty] | T-00135-0231 | 2026-07-30 | Priority-1
[12 empty] | T-00135-0237 | 2026-07-17 | Priority-1
[12 empty] | T-00135-0238 | 2026-07-17 | Priority-1
[12 empty] | T-00135-0243 | 2026-07-17 | Priority-1
[12 empty] | T-00135-0244 | 2026-07-17 | Priority-1
[12 empty] | T-00135-0251 | 2026-07-31 | Priority-2
[12 empty] | T-00135-0252 | 2026-07-31 | Priority-2
[12 empty] | T-00135-0256 | 2026-07-17 | Priority-1
[12 empty] | T-00135-0257 | 2026-07-17 | Priority-1
[12 empty] | T-00135-0258 | 2026-07-17 | Priority-1
[12 empty] | T-00135-0259 | 2026-07-30 | Priority-1
[12 empty] | T-00135-0265 | 2026-07-17 | Priority-1
[12 empty] | T-00135-0266 | 2026-07-30 | Priority-1
[12 empty] | T-00135-0272 | 2026-07-17 | Priority-1
[12 empty] | T-00135-0273 | 2026-07-17 | Priority-1
[12 empty] | T-00135-0284 | 2026-07-17 | Priority-1
[12 empty] | T-00135-0285 | 2026-07-17 | Priority-1
[12 empty] | T-00135-0291 | 2026-07-30 | Priority-1
[12 empty] | T-00135-0292 | 2026-07-31 | Priority-1
[12 empty] | T-00135-0298 | 2026-07-17 | Priority-1
[12 empty] | T-00135-0299 | 2026-07-17 | Priority-1
[12 empty] | T-00135-0305 | 2026-07-17 | Priority-1
[12 empty] | T-00135-0306 | 2026-07-17 | Priority-1
[12 empty] | T-00135-0312 | 2026-07-17 | Priority-1
[12 empty] | T-00135-0313 | 2026-07-17 | Priority-1
[12 empty] | T-00135-0314 | 2026-07-30 | Priority-1
[12 empty] | T-00135-0321 | 2026-07-30 | Priority-1
[12 empty] | T-00135-0322 | 2026-07-31 | Priority-1
[12 empty] | T-00135-0329 | 2026-07-31 | Priority-2
[12 empty] | T-00135-0330 | 2026-07-21 | Priority-1
[12 empty] | T-00135-0465 | 2026-07-17 | Priority-1
[12 empty] | T-00135-0466 | 2026-07-17 | Priority-1
[12 empty] | T-00140-0065 | 2026-07-17 | Priority-1
[12 empty] | T-00140-0066 | 2026-07-17 | Priority-1
[12 empty] | T-00140-0067 | 2026-07-17 | Priority-1
[12 empty] | T-00140-0068 | 2026-07-17 | Priority-1
[12 empty] | T-00141-0132 | 2026-07-17 | Priority-1
[12 empty] | T-00141-0133 | 2026-07-30 | Priority-1
[12 empty] | T-00141-0142 | 2026-07-17 | Priority-1
[12 empty] | T-00141-0143 | 2026-07-17 | Priority-1
[12 empty] | T-00141-0151 | 2026-07-17 | Priority-1
[12 empty] | T-00141-0152 | 2026-07-17 | Priority-1
[12 empty] | T-00141-0158 | 2026-07-17 | Priority-1
[12 empty] | T-00141-0159 | 2026-07-17 | Priority-1
[12 empty] | T-00141-0165 | 2026-07-30 | Priority-1
[12 empty] | T-00141-0166 | 2026-07-30 | Priority-1
[12 empty] | T-00141-0172 | 2026-07-30 | Priority-1
[12 empty] | T-00141-0173 | 2026-07-31 | Priority-1
[12 empty] | T-00141-0179 | 2026-07-17 | Priority-1
[12 empty] | T-00141-0180 | 2026-07-17 | Priority-1
[12 empty] | T-00141-0190 | 2026-07-31 | Priority-2
[12 empty] | T-00141-0191 | 2026-07-31 | Priority-2
[12 empty] | T-00141-0201 | 2026-07-21 | Priority-1
[12 empty] | T-00146-0173 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0174 | 2026-07-30 | Priority-1
[12 empty] | T-00146-0182 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0183 | 2026-07-30 | Priority-1
[12 empty] | T-00146-0184 | 2026-07-30 | Priority-1
[12 empty] | T-00146-0190 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0191 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0196 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0197 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0204 | 2026-07-31 | Priority-2
[12 empty] | T-00146-0205 | 2026-07-31 | Priority-2
[12 empty] | T-00146-0209 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0210 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0211 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0212 | 2026-07-30 | Priority-1
[12 empty] | T-00146-0218 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0219 | 2026-07-30 | Priority-1
[12 empty] | T-00146-0225 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0226 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0237 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0238 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0244 | 2026-07-30 | Priority-1
[12 empty] | T-00146-0245 | 2026-07-31 | Priority-1
[12 empty] | T-00146-0251 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0252 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0258 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0259 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0265 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0266 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0267 | 2026-07-30 | Priority-1
[12 empty] | T-00146-0274 | 2026-07-30 | Priority-1
[12 empty] | T-00146-0275 | 2026-07-31 | Priority-1
[12 empty] | T-00146-0282 | 2026-07-31 | Priority-2
[12 empty] | T-00146-0283 | 2026-07-21 | Priority-1
[12 empty] | T-00146-0418 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0419 | 2026-07-17 | Priority-1
[12 empty] | T-00146-0449 | 2026-07-30 | Priority-1
[12 empty] | T-00146-0450 | 2026-07-31 | Priority-1
[12 empty] | T-00146-0461 | 2026-07-31 | Priority-2
[12 empty] | T-00171-4342 | 2026-07-30 | Priority-1
[12 empty] | T-00171-4343 | 2026-07-30 | Priority-1
[12 empty] | T-00171-4344 | 2026-07-30 | Priority-1
[12 empty] | T-00171-4345 | 2026-07-30 | Priority-1
[12 empty] | T-00171-4365 | 2026-07-30 | Priority-1
[12 empty] | T-00171-4366 | 2026-07-30 | Priority-1
[12 empty] | T-00171-4367 | 2026-07-30 | Priority-1
[12 empty] | T-00171-4368 | 2026-07-30 | Priority-1
[12 empty] | T-00171-4369 | 2026-07-30 | Priority-1
[12 empty] | T-00171-4370 | 2026-07-30 | Priority-1
[12 empty] | T-00171-4371 | 2026-07-17 | Priority-1
[12 empty] | T-00171-4372 | 2026-07-30 | Priority-1
[12 empty] | T-00171-4378 | 2026-07-30 | Priority-1
[12 empty] | T-00171-4379 | 2026-07-30 | Priority-1
[12 empty] | T-00171-4385 | 2026-07-17 | Priority-1
[12 empty] | T-00171-4386 | 2026-07-31 | Priority-1
[12 empty] | T-00171-4393 | 2026-07-30 | Priority-1
[12 empty] | T-00171-4394 | 2026-07-30 | Priority-1
[12 empty] | T-00171-4395 | 2026-07-30 | Priority-1
[12 empty] | T-00171-4398 | 2026-07-31 | Priority-1
[12 empty] | T-00171-4399 | 2026-07-31 | Priority-1
[12 empty] | T-00171-4400 | 2026-07-31 | Priority-1
[12 empty] | T-00171-4401 | 2026-07-31 | Priority-1
[12 empty] | T-00171-4402 | 2026-07-31 | Priority-1
[12 empty] | T-00171-4403 | 2026-07-31 | Priority-1
[12 empty] | T-00171-4404 | 2026-07-31 | Priority-1
[12 empty] | T-00171-4407 | 2026-07-31 | Priority-2
[12 empty] | T-00171-4408 | 2026-07-21 | Priority-1
[12 empty] | T-00214-0231 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0232 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0233 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0234 | 2026-07-30 | Priority-1
[12 empty] | T-00214-0235 | 2026-07-30 | Priority-1
[12 empty] | T-00214-0236 | 2026-07-30 | Priority-1
[12 empty] | T-00214-0267 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0268 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0269 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0270 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0278 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0279 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0280 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0281 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0292 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0293 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0294 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0295 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0306 | 2026-07-30 | Priority-1
[12 empty] | T-00214-0307 | 2026-07-30 | Priority-1
[12 empty] | T-00214-0308 | 2026-07-30 | Priority-1
[12 empty] | T-00214-0309 | 2026-07-30 | Priority-1
[12 empty] | T-00214-0320 | 2026-07-30 | Priority-1
[12 empty] | T-00214-0321 | 2026-07-30 | Priority-1
[12 empty] | T-00214-0322 | 2026-07-31 | Priority-1
[12 empty] | T-00214-0323 | 2026-07-31 | Priority-1
[12 empty] | T-00214-0334 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0335 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0336 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0337 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0338 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0339 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0340 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0341 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0342 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0343 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0344 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0345 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0391 | 2026-07-31 | Priority-2
[12 empty] | T-00214-0392 | 2026-07-31 | Priority-2
[12 empty] | T-00214-0393 | 2026-07-31 | Priority-2
[12 empty] | T-00214-0394 | 2026-07-31 | Priority-2
[12 empty] | T-00214-0395 | 2026-07-31 | Priority-2
[12 empty] | T-00214-0418 | 2026-07-21 | Priority-1
[12 empty] | T-00214-0419 | 2026-07-21 | Priority-1
[12 empty] | T-00214-0420 | 2026-07-21 | Priority-1
[12 empty] | T-00214-0421 | 2026-07-21 | Priority-1
[12 empty] | T-00214-0422 | 2026-07-21 | Priority-1
[12 empty] | T-00214-0512 | 2026-07-17 | Priority-1
[12 empty] | T-00214-0513 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0231 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0232 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0233 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0234 | 2026-07-30 | Priority-1
[12 empty] | T-00215-0235 | 2026-07-30 | Priority-1
[12 empty] | T-00215-0236 | 2026-07-30 | Priority-1
[12 empty] | T-00215-0267 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0268 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0269 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0270 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0278 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0279 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0280 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0281 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0292 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0293 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0294 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0295 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0306 | 2026-07-30 | Priority-1
[12 empty] | T-00215-0307 | 2026-07-30 | Priority-1
[12 empty] | T-00215-0308 | 2026-07-30 | Priority-1
[12 empty] | T-00215-0309 | 2026-07-30 | Priority-1
[12 empty] | T-00215-0320 | 2026-07-30 | Priority-1
[12 empty] | T-00215-0321 | 2026-07-30 | Priority-1
[12 empty] | T-00215-0322 | 2026-07-31 | Priority-1
[12 empty] | T-00215-0323 | 2026-07-31 | Priority-1
[12 empty] | T-00215-0334 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0335 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0336 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0337 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0338 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0339 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0340 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0341 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0342 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0343 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0344 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0345 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0391 | 2026-07-31 | Priority-2
[12 empty] | T-00215-0392 | 2026-07-31 | Priority-2
[12 empty] | T-00215-0393 | 2026-07-31 | Priority-2
[12 empty] | T-00215-0394 | 2026-07-31 | Priority-2
[12 empty] | T-00215-0395 | 2026-07-31 | Priority-2
[12 empty] | T-00215-0418 | 2026-07-21 | Priority-1
[12 empty] | T-00215-0419 | 2026-07-21 | Priority-1
[12 empty] | T-00215-0420 | 2026-07-21 | Priority-1
[12 empty] | T-00215-0421 | 2026-07-21 | Priority-1
[12 empty] | T-00215-0422 | 2026-07-21 | Priority-1
[12 empty] | T-00215-0512 | 2026-07-17 | Priority-1
[12 empty] | T-00215-0513 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0231 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0232 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0233 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0234 | 2026-07-30 | Priority-1
[12 empty] | T-00216-0235 | 2026-07-30 | Priority-1
[12 empty] | T-00216-0236 | 2026-07-30 | Priority-1
[12 empty] | T-00216-0267 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0268 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0269 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0270 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0278 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0279 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0280 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0281 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0292 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0293 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0294 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0295 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0306 | 2026-07-30 | Priority-1
[12 empty] | T-00216-0307 | 2026-07-30 | Priority-1
[12 empty] | T-00216-0308 | 2026-07-30 | Priority-1
[12 empty] | T-00216-0309 | 2026-07-30 | Priority-1
[12 empty] | T-00216-0320 | 2026-07-30 | Priority-1
[12 empty] | T-00216-0321 | 2026-07-30 | Priority-1
[12 empty] | T-00216-0322 | 2026-07-31 | Priority-1
[12 empty] | T-00216-0323 | 2026-07-31 | Priority-1
[12 empty] | T-00216-0334 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0335 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0336 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0337 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0338 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0339 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0340 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0341 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0342 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0343 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0344 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0345 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0391 | 2026-07-31 | Priority-2
[12 empty] | T-00216-0392 | 2026-07-31 | Priority-2
[12 empty] | T-00216-0393 | 2026-07-31 | Priority-2
[12 empty] | T-00216-0394 | 2026-07-31 | Priority-2
[12 empty] | T-00216-0395 | 2026-07-31 | Priority-2
[12 empty] | T-00216-0418 | 2026-07-21 | Priority-1
[12 empty] | T-00216-0419 | 2026-07-21 | Priority-1
[12 empty] | T-00216-0420 | 2026-07-21 | Priority-1
[12 empty] | T-00216-0421 | 2026-07-21 | Priority-1
[12 empty] | T-00216-0422 | 2026-07-21 | Priority-1
[12 empty] | T-00216-0512 | 2026-07-17 | Priority-1
[12 empty] | T-00216-0513 | 2026-07-17 | Priority-1
[12 empty] | T-00218-0097 | 2026-07-17 | Priority-1
[12 empty] | T-00218-0098 | 2026-07-30 | Priority-1
[12 empty] | T-00218-0107 | 2026-07-17 | Priority-1
[12 empty] | T-00218-0108 | 2026-07-17 | Priority-1
[12 empty] | T-00218-0116 | 2026-07-17 | Priority-1
[12 empty] | T-00218-0117 | 2026-07-17 | Priority-1
[12 empty] | T-00218-0123 | 2026-07-17 | Priority-1
[12 empty] | T-00218-0124 | 2026-07-17 | Priority-1
[12 empty] | T-00218-0130 | 2026-07-30 | Priority-1
[12 empty] | T-00218-0131 | 2026-07-30 | Priority-1
[12 empty] | T-00218-0137 | 2026-07-30 | Priority-1
[12 empty] | T-00218-0138 | 2026-07-31 | Priority-1
[12 empty] | T-00218-0144 | 2026-07-17 | Priority-1
[12 empty] | T-00218-0145 | 2026-07-17 | Priority-1
[12 empty] | T-00218-0155 | 2026-07-31 | Priority-2
[12 empty] | T-00218-0156 | 2026-07-31 | Priority-2
[12 empty] | T-00218-0166 | 2026-07-21 | Priority-1
[12 empty] | T-00220-0008 | 2026-07-17 | Priority-1
[12 empty] | T-00220-0009 | 2026-07-17 | Priority-1
[12 empty] | T-00220-0015 | 2026-07-30 | Priority-1
[12 empty] | T-00220-0016 | 2026-07-30 | Priority-1
[12 empty] | T-00220-0022 | 2026-07-17 | Priority-1
[12 empty] | T-00220-0023 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0231 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0232 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0233 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0234 | 2026-07-30 | Priority-1
[12 empty] | T-00221-0235 | 2026-07-30 | Priority-1
[12 empty] | T-00221-0236 | 2026-07-30 | Priority-1
[12 empty] | T-00221-0267 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0268 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0269 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0270 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0278 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0279 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0280 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0281 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0292 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0293 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0294 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0295 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0306 | 2026-07-30 | Priority-1
[12 empty] | T-00221-0307 | 2026-07-30 | Priority-1
[12 empty] | T-00221-0308 | 2026-07-30 | Priority-1
[12 empty] | T-00221-0309 | 2026-07-30 | Priority-1
[12 empty] | T-00221-0320 | 2026-07-30 | Priority-1
[12 empty] | T-00221-0321 | 2026-07-30 | Priority-1
[12 empty] | T-00221-0322 | 2026-07-31 | Priority-1
[12 empty] | T-00221-0323 | 2026-07-31 | Priority-1
[12 empty] | T-00221-0334 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0335 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0336 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0337 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0338 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0339 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0340 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0341 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0342 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0343 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0344 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0345 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0391 | 2026-07-31 | Priority-2
[12 empty] | T-00221-0392 | 2026-07-31 | Priority-2
[12 empty] | T-00221-0393 | 2026-07-31 | Priority-2
[12 empty] | T-00221-0394 | 2026-07-31 | Priority-2
[12 empty] | T-00221-0395 | 2026-07-31 | Priority-2
[12 empty] | T-00221-0418 | 2026-07-21 | Priority-1
[12 empty] | T-00221-0419 | 2026-07-21 | Priority-1
[12 empty] | T-00221-0420 | 2026-07-21 | Priority-1
[12 empty] | T-00221-0421 | 2026-07-21 | Priority-1
[12 empty] | T-00221-0422 | 2026-07-21 | Priority-1
[12 empty] | T-00221-0512 | 2026-07-17 | Priority-1
[12 empty] | T-00221-0513 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0231 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0232 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0233 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0234 | 2026-07-30 | Priority-1
[12 empty] | T-00223-0235 | 2026-07-30 | Priority-1
[12 empty] | T-00223-0236 | 2026-07-30 | Priority-1
[12 empty] | T-00223-0267 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0268 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0269 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0270 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0278 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0279 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0280 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0281 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0292 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0293 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0294 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0295 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0306 | 2026-07-30 | Priority-1
[12 empty] | T-00223-0307 | 2026-07-30 | Priority-1
[12 empty] | T-00223-0308 | 2026-07-30 | Priority-1
[12 empty] | T-00223-0309 | 2026-07-30 | Priority-1
[12 empty] | T-00223-0320 | 2026-07-30 | Priority-1
[12 empty] | T-00223-0321 | 2026-07-30 | Priority-1
[12 empty] | T-00223-0322 | 2026-07-31 | Priority-1
[12 empty] | T-00223-0323 | 2026-07-31 | Priority-1
[12 empty] | T-00223-0334 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0335 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0336 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0337 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0338 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0339 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0340 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0341 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0342 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0343 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0344 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0345 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0391 | 2026-07-31 | Priority-2
[12 empty] | T-00223-0392 | 2026-07-31 | Priority-2
[12 empty] | T-00223-0393 | 2026-07-31 | Priority-2
[12 empty] | T-00223-0394 | 2026-07-31 | Priority-2
[12 empty] | T-00223-0395 | 2026-07-31 | Priority-2
[12 empty] | T-00223-0418 | 2026-07-21 | Priority-1
[12 empty] | T-00223-0419 | 2026-07-21 | Priority-1
[12 empty] | T-00223-0420 | 2026-07-21 | Priority-1
[12 empty] | T-00223-0421 | 2026-07-21 | Priority-1
[12 empty] | T-00223-0422 | 2026-07-21 | Priority-1
[12 empty] | T-00223-0512 | 2026-07-17 | Priority-1
[12 empty] | T-00223-0513 | 2026-07-17 | Priority-1
[12 empty] | T-00224-0120 | 2026-07-17 | Priority-1
[12 empty] | T-00224-0121 | 2026-07-30 | Priority-1
[12 empty] | T-00224-0130 | 2026-07-17 | Priority-1
[12 empty] | T-00224-0131 | 2026-07-17 | Priority-1
[12 empty] | T-00224-0139 | 2026-07-17 | Priority-1
[12 empty] | T-00224-0140 | 2026-07-17 | Priority-1
[12 empty] | T-00224-0146 | 2026-07-17 | Priority-1
[12 empty] | T-00224-0147 | 2026-07-17 | Priority-1
[12 empty] | T-00224-0153 | 2026-07-30 | Priority-1
[12 empty] | T-00224-0154 | 2026-07-30 | Priority-1
[12 empty] | T-00224-0160 | 2026-07-30 | Priority-1
[12 empty] | T-00224-0161 | 2026-07-31 | Priority-1
[12 empty] | T-00224-0167 | 2026-07-17 | Priority-1
[12 empty] | T-00224-0168 | 2026-07-17 | Priority-1
[12 empty] | T-00224-0178 | 2026-07-31 | Priority-2
[12 empty] | T-00224-0179 | 2026-07-31 | Priority-2
[12 empty] | T-00224-0189 | 2026-07-21 | Priority-1
[12 empty] | T-00227-0133 | 2026-07-17 | Priority-1
[12 empty] | T-00227-0134 | 2026-07-30 | Priority-1
[12 empty] | T-00232-0970 | 2026-07-17 | Priority-1
[12 empty] | T-00232-0971 | 2026-07-30 | Priority-1
[12 empty] | T-00232-1013 | 2026-07-17 | Priority-1
[12 empty] | T-00232-1014 | 2026-07-17 | Priority-1
[12 empty] | T-00232-1015 | 2026-07-17 | Priority-1
[12 empty] | T-00232-1016 | 2026-07-30 | Priority-1
[12 empty] | T-00232-1017 | 2026-07-30 | Priority-1
[12 empty] | T-00232-1018 | 2026-07-30 | Priority-1
[12 empty] | T-00232-1046 | 2026-07-17 | Priority-1
[12 empty] | T-00232-1047 | 2026-07-17 | Priority-1
[12 empty] | T-00232-1048 | 2026-07-17 | Priority-1
[12 empty] | T-00232-1049 | 2026-07-30 | Priority-1
[12 empty] | T-00232-1050 | 2026-07-30 | Priority-1
[12 empty] | T-00232-1051 | 2026-07-30 | Priority-1
[12 empty] | T-00233-10536 | 2026-07-17 | Priority-1
[12 empty] | T-00233-10537 | 2026-07-31 | Priority-1
[12 empty] | T-00233-10593 | 2026-07-17 | Priority-1
[12 empty] | T-00233-10594 | 2026-07-30 | Priority-1
[12 empty] | T-00233-10600 | 2026-07-30 | Priority-1
[12 empty] | T-00233-10601 | 2026-07-30 | Priority-1
[12 empty] | T-00233-10890 | 2026-07-30 | Priority-1
[12 empty] | T-00233-10891 | 2026-07-30 | Priority-1
[12 empty] | T-00233-10892 | 2026-07-31 | Priority-1
[12 empty] | T-00233-10893 | 2026-07-31 | Priority-1
[12 empty] | T-00233-10904 | 2026-07-17 | Priority-1
[12 empty] | T-00233-4978 | 2026-07-17 | Priority-1
[12 empty] | T-00233-4979 | 2026-07-17 | Priority-1
[12 empty] | T-00233-4981 | 2026-07-17 | Priority-1
[12 empty] | T-00233-4982 | 2026-07-17 | Priority-1
[12 empty] | T-00233-4983 | 2026-07-17 | Priority-1
[12 empty] | T-00233-4984 | 2026-07-17 | Priority-1
[12 empty] | T-00233-4986 | 2026-07-17 | Priority-1
[12 empty] | T-00233-4987 | 2026-07-17 | Priority-1
[12 empty] | T-00233-4988 | 2026-07-30 | Priority-1
[12 empty] | T-00233-4994 | 2026-07-30 | Priority-1
[12 empty] | T-00233-4995 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5001 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5002 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5008 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5009 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5010 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5011 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5012 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5013 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5014 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5015 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5016 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5017 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5018 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5019 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5020 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5021 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5022 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5023 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5024 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5025 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5026 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5027 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5028 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5029 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5030 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5031 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5092 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5093 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5094 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5095 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5096 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5097 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5108 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5109 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5115 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5116 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5117 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5118 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5129 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5130 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5136 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5137 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5138 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5139 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5140 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5141 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5157 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5166 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5167 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5168 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5169 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5170 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5171 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5187 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5188 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5189 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5190 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5201 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5202 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5204 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5205 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5206 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5207 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5208 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5209 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5211 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5212 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5213 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5214 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5215 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5216 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5254 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5255 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5256 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5257 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5258 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5259 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5260 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5261 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5262 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5263 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5264 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5265 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5271 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5272 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5273 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5274 | 2026-07-31 | Priority-1
[12 empty] | T-00233-5275 | 2026-07-31 | Priority-1
[12 empty] | T-00233-5276 | 2026-07-31 | Priority-1
[12 empty] | T-00233-5292 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5293 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5294 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5295 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5296 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5297 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5298 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5299 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5302 | 2026-07-31 | Priority-1
[12 empty] | T-00233-5303 | 2026-07-31 | Priority-1
[12 empty] | T-00233-5304 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5305 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5310 | 2026-07-31 | Priority-1
[12 empty] | T-00233-5311 | 2026-07-31 | Priority-1
[12 empty] | T-00233-5312 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5313 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5319 | 2026-07-17 | Priority-1
[12 empty] | T-00233-5320 | 2026-07-30 | Priority-1
[12 empty] | T-00233-5581 | 2026-07-31 | Priority-2
[12 empty] | T-00233-5582 | 2026-07-31 | Priority-2
[12 empty] | T-00233-5583 | 2026-07-31 | Priority-2
[12 empty] | T-00233-5584 | 2026-07-21 | Priority-1
[12 empty] | T-00233-5585 | 2026-07-21 | Priority-1
[12 empty] | T-00233-5586 | 2026-07-21 | Priority-1
[12 empty] | T-00233-5594 | 2026-07-31 | Priority-2
[12 empty] | T-00233-5595 | 2026-07-21 | Priority-1
[12 empty] | T-00233-5596 | 2026-07-31 | Priority-2
[12 empty] | T-00233-5597 | 2026-07-21 | Priority-1
[12 empty] | T-00233-5599 | 2026-07-31 | Priority-2
[12 empty] | T-00233-5601 | 2026-07-31 | Priority-2
[12 empty] | T-00233-9131 | 2026-07-30 | Priority-1
[12 empty] | T-00233-9132 | 2026-07-31 | Priority-1
[12 empty] | T-00233-9138 | 2026-07-30 | Priority-1
[12 empty] | T-00233-9139 | 2026-07-31 | Priority-1
[12 empty] | T-00233-9145 | 2026-07-30 | Priority-1
[12 empty] | T-00233-9146 | 2026-07-31 | Priority-1
[12 empty] | T-00233-9152 | 2026-07-30 | Priority-1
[12 empty] | T-00233-9153 | 2026-07-30 | Priority-1
[12 empty] | T-00233-9154 | 2026-07-30 | Priority-1
[12 empty] | T-00233-9155 | 2026-07-30 | Priority-1
[12 empty] | T-00233-9156 | 2026-07-30 | Priority-1
[12 empty] | T-00233-9157 | 2026-07-30 | Priority-1
[12 empty] | T-00233-9158 | 2026-07-30 | Priority-1
[12 empty] | T-00233-9159 | 2026-07-30 | Priority-1
[12 empty] | T-00233-9160 | 2026-07-30 | Priority-1
[12 empty] | T-00233-9161 | 2026-07-30 | Priority-1
[12 empty] | T-00233-9162 | 2026-07-30 | Priority-1
[12 empty] | T-00233-9163 | 2026-07-31 | Priority-1
[12 empty] | T-00233-9164 | 2026-07-31 | Priority-1
[12 empty] | T-00233-9165 | 2026-07-31 | Priority-1
[12 empty] | T-00233-9166 | 2026-07-31 | Priority-1
[12 empty] | T-00233-9167 | 2026-07-31 | Priority-1
[12 empty] | T-00233-9168 | 2026-07-31 | Priority-1
[12 empty] | T-00233-9169 | 2026-07-31 | Priority-1
[12 empty] | T-00233-9170 | 2026-07-31 | Priority-1
[12 empty] | T-00233-9171 | 2026-07-31 | Priority-1
[12 empty] | T-00233-9172 | 2026-07-31 | Priority-1
[12 empty] | T-00233-9173 | 2026-07-31 | Priority-1
[12 empty] | T-00233-9229 | 2026-07-30 | Priority-1
[12 empty] | T-00233-9230 | 2026-07-31 | Priority-1
[12 empty] | T-00233-9236 | 2026-07-30 | Priority-1
[12 empty] | T-00233-9237 | 2026-07-31 | Priority-1
[12 empty] | T-00233-9244 | 2026-07-31 | Priority-2
[12 empty] | T-00233-9245 | 2026-07-31 | Priority-2
[12 empty] | T-00233-9246 | 2026-07-31 | Priority-2
[12 empty] | T-00233-9247 | 2026-07-31 | Priority-2
[12 empty] | T-00233-9248 | 2026-07-31 | Priority-2
[12 empty] | T-00233-9249 | 2026-07-31 | Priority-2
[12 empty] | T-00233-9250 | 2026-07-31 | Priority-2
[12 empty] | T-00233-9251 | 2026-07-31 | Priority-2
[12 empty] | T-00233-9252 | 2026-07-21 | Priority-1
[12 empty] | T-00233-9253 | 2026-07-21 | Priority-1
[12 empty] | T-00233-9254 | 2026-07-21 | Priority-1
[12 empty] | T-00233-9255 | 2026-07-21 | Priority-1
[12 empty] | T-00234-2101 | 2026-07-17 | Priority-1
[12 empty] | T-00234-2102 | 2026-07-17 | Priority-1
[12 empty] | T-00234-2103 | 2026-07-17 | Priority-1
[12 empty] | T-00234-2104 | 2026-07-30 | Priority-1
[12 empty] | T-00234-2105 | 2026-07-30 | Priority-1
[12 empty] | T-00234-2106 | 2026-07-30 | Priority-1
[12 empty] | T-00234-2123 | 2026-07-17 | Priority-1
[12 empty] | T-00234-2124 | 2026-07-17 | Priority-1
[12 empty] | T-00234-2125 | 2026-07-17 | Priority-1
[12 empty] | T-00234-2126 | 2026-07-17 | Priority-1
[12 empty] | T-00234-2135 | 2026-07-17 | Priority-1
[12 empty] | T-00234-2136 | 2026-07-17 | Priority-1
[12 empty] | T-00234-2138 | 2026-07-30 | Priority-1
[12 empty] | T-00234-2139 | 2026-07-30 | Priority-1
[12 empty] | T-00234-2140 | 2026-07-30 | Priority-1
[12 empty] | T-00234-2141 | 2026-07-30 | Priority-1
[12 empty] | T-00234-2150 | 2026-07-30 | Priority-1
[12 empty] | T-00234-2151 | 2026-07-30 | Priority-1
[12 empty] | T-00238-0457 | 2026-07-17 | Priority-1
[12 empty] | T-00238-0458 | 2026-07-30 | Priority-1
[12 empty] | T-00238-0464 | 2026-07-30 | Priority-1
[12 empty] | T-00238-0465 | 2026-07-17 | Priority-1
[12 empty] | T-00238-0466 | 2026-07-30 | Priority-1
[12 empty] | T-00238-0472 | 2026-07-30 | Priority-1
[12 empty] | T-00238-0473 | 2026-07-17 | Priority-1
[12 empty] | T-00238-0474 | 2026-07-30 | Priority-1
[12 empty] | T-00238-0552 | 2026-07-17 | Priority-1
[12 empty] | T-00238-0553 | 2026-07-31 | Priority-1
[12 empty] | T-00238-0565 | 2026-07-31 | Priority-2
[12 empty] | T-00238-0566 | 2026-07-21 | Priority-1
[12 empty] | T-00243-0059 | 2026-07-17 | Priority-1
[12 empty] | T-00243-0060 | 2026-07-30 | Priority-1
[12 empty] | T-00247-0146 | 2026-07-20 | Priority-1
[12 empty] | T-00247-0147 | 2026-07-20 | Priority-1
[12 empty] | T-00247-0148 | 2026-07-20 | Priority-1
[12 empty] | T-00247-0160 | 2026-06-21 | Priority-1
[12 empty] | T-00254-12960 | 2026-07-17 | Priority-1
[12 empty] | T-00254-12961 | 2026-07-30 | Priority-1
[12 empty] | T-00254-12967 | 2026-07-30 | Priority-1
[12 empty] | T-00254-12968 | 2026-07-17 | Priority-1
[12 empty] | T-00254-12969 | 2026-07-17 | Priority-1
[12 empty] | T-00254-12970 | 2026-07-17 | Priority-1
[12 empty] | T-00254-12971 | 2026-07-30 | Priority-1
[12 empty] | T-00254-12972 | 2026-07-30 | Priority-1
[12 empty] | T-00254-12973 | 2026-07-30 | Priority-1
[12 empty] | T-00254-12989 | 2026-07-17 | Priority-1
[12 empty] | T-00254-12990 | 2026-07-17 | Priority-1
[12 empty] | T-00254-12991 | 2026-07-30 | Priority-1
[12 empty] | T-00254-12992 | 2026-07-30 | Priority-1
[12 empty] | T-00254-13003 | 2026-07-30 | Priority-1
[12 empty] | T-00254-13004 | 2026-07-30 | Priority-1
[12 empty] | T-00254-13005 | 2026-07-30 | Priority-1
[12 empty] | T-00254-13006 | 2026-07-30 | Priority-1
[12 empty] | T-00254-13007 | 2026-07-30 | Priority-1
[12 empty] | T-00254-13008 | 2026-07-31 | Priority-1
[12 empty] | T-00254-13014 | 2026-07-30 | Priority-1
[12 empty] | T-00254-13015 | 2026-07-31 | Priority-1
[12 empty] | T-00254-4900 | 2026-07-17 | Priority-1
[12 empty] | T-00254-4901 | 2026-07-17 | Priority-1
[12 empty] | T-00254-4902 | 2026-07-30 | Priority-1
[12 empty] | T-00254-4903 | 2026-07-30 | Priority-1
[12 empty] | T-00254-4909 | 2026-07-17 | Priority-1
[12 empty] | T-00254-4910 | 2026-07-17 | Priority-1
[12 empty] | T-00254-4911 | 2026-07-30 | Priority-1
[12 empty] | T-00254-4912 | 2026-07-30 | Priority-1
[12 empty] | T-00254-4923 | 2026-07-30 | Priority-1
[12 empty] | T-00254-4924 | 2026-07-30 | Priority-1
[12 empty] | T-00254-4925 | 2026-07-30 | Priority-1
[12 empty] | T-00254-4926 | 2026-07-30 | Priority-1
[12 empty] | T-00254-4927 | 2026-07-30 | Priority-1
[12 empty] | T-00254-4928 | 2026-07-30 | Priority-1
[12 empty] | T-00254-4929 | 2026-07-17 | Priority-1
[12 empty] | T-00254-4930 | 2026-07-30 | Priority-1
[12 empty] | T-00254-4936 | 2026-07-17 | Priority-1
[12 empty] | T-00254-4937 | 2026-07-17 | Priority-1
[12 empty] | T-00254-4938 | 2026-07-30 | Priority-1
[12 empty] | T-00254-4939 | 2026-07-30 | Priority-1
[12 empty] | T-00254-4950 | 2026-07-17 | Priority-1
[12 empty] | T-00254-4951 | 2026-07-17 | Priority-1
[12 empty] | T-00254-4952 | 2026-07-17 | Priority-1
[12 empty] | T-00254-4953 | 2026-07-17 | Priority-1
[12 empty] | T-00254-4954 | 2026-07-17 | Priority-1
[12 empty] | T-00254-4955 | 2026-07-17 | Priority-1
[12 empty] | T-00254-4956 | 2026-07-30 | Priority-1
[12 empty] | T-00254-4957 | 2026-07-31 | Priority-1
[12 empty] | T-00254-4958 | 2026-07-31 | Priority-1
[12 empty] | T-00254-4959 | 2026-07-31 | Priority-1
[12 empty] | T-00254-4960 | 2026-07-31 | Priority-1
[12 empty] | T-00254-4961 | 2026-07-31 | Priority-1
[12 empty] | T-00254-4992 | 2026-07-17 | Priority-1
[12 empty] | T-00254-4993 | 2026-07-17 | Priority-1
[12 empty] | T-00254-4994 | 2026-07-17 | Priority-1
[12 empty] | T-00254-4995 | 2026-07-17 | Priority-1
[12 empty] | T-00254-4996 | 2026-07-30 | Priority-1
[12 empty] | T-00254-4997 | 2026-07-30 | Priority-1
[12 empty] | T-00254-4998 | 2026-07-30 | Priority-1
[12 empty] | T-00254-4999 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5020 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5021 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5022 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5023 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5024 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5025 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5026 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5027 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5048 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5049 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5055 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5056 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5057 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5058 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5069 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5075 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5076 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5077 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5078 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5079 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5080 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5081 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5082 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5083 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5084 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5085 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5086 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5087 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5088 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5093 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5094 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5095 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5096 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5097 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5098 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5099 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5100 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5101 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5102 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5103 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5104 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5105 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5106 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5107 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5108 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5113 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5114 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5215 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5216 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5217 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5218 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5219 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5220 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5221 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5225 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5226 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5227 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5228 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5229 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5230 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5231 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5232 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5253 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5254 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5255 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5256 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5257 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5258 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5259 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5260 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5261 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5262 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5263 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5264 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5296 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5297 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5298 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5299 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5300 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5301 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5302 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5303 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5304 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5311 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5312 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5313 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5314 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5315 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5316 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5317 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5328 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5329 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5330 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5331 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5332 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5333 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5334 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5335 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5336 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5337 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5338 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5339 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5340 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5341 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5342 | 2026-07-31 | Priority-1
[12 empty] | T-00254-5351 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5352 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5358 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5359 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5360 | 2026-07-17 | Priority-1
[12 empty] | T-00254-5361 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5362 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5363 | 2026-07-30 | Priority-1
[12 empty] | T-00254-5390 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5391 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5394 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5395 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5396 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5397 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5398 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5399 | 2026-07-21 | Priority-1
[12 empty] | T-00254-5400 | 2026-07-21 | Priority-1
[12 empty] | T-00254-5401 | 2026-07-21 | Priority-1
[12 empty] | T-00254-5402 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5403 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5404 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5405 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5411 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5412 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5413 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5414 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5415 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5416 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5417 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5418 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5419 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5420 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5479 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5480 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5481 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5482 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5486 | 2026-07-21 | Priority-1
[12 empty] | T-00254-5487 | 2026-07-21 | Priority-1
[12 empty] | T-00254-5488 | 2026-07-21 | Priority-1
[12 empty] | T-00254-5489 | 2026-07-21 | Priority-1
[12 empty] | T-00254-5528 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5529 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5530 | 2026-07-21 | Priority-1
[12 empty] | T-00254-5531 | 2026-07-21 | Priority-1
[12 empty] | T-00254-5532 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5533 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5534 | 2026-07-21 | Priority-1
[12 empty] | T-00254-5535 | 2026-07-21 | Priority-1
[12 empty] | T-00254-5536 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5537 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5538 | 2026-07-21 | Priority-1
[12 empty] | T-00254-5539 | 2026-07-21 | Priority-1
[12 empty] | T-00254-5540 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5541 | 2026-07-31 | Priority-2
[12 empty] | T-00254-5542 | 2026-07-21 | Priority-1
[12 empty] | T-00254-5543 | 2026-07-21 | Priority-1
[12 empty] | T-00256-0027 | 2026-07-30 | Priority-1
[12 empty] | T-00256-0028 | 2026-07-30 | Priority-1
[12 empty] | T-00256-0029 | 2026-07-30 | Priority-1
[12 empty] | T-00256-0090 | 2026-07-30 | Priority-1
[12 empty] | T-00257-0173 | 2026-07-17 | Priority-1
[12 empty] | T-00257-0175 | 2026-07-17 | Priority-1
[12 empty] | T-00257-0182 | 2026-07-17 | Priority-1
[12 empty] | T-00257-0184 | 2026-07-17 | Priority-1
[12 empty] | T-00257-0194 | 2026-07-17 | Priority-1
[12 empty] | T-00257-0198 | 2026-07-17 | Priority-1
[12 empty] | T-00257-0207 | 2026-07-17 | Priority-1
[12 empty] | T-00257-0208 | 2026-07-17 | Priority-1
[12 empty] | T-00275-1945 | 2026-07-30 | Priority-1
[12 empty] | T-00275-1946 | 2026-07-30 | Priority-1
[12 empty] | T-00275-1947 | 2026-07-30 | Priority-1
[12 empty] | T-00275-1948 | 2026-07-30 | Priority-1
[12 empty] | T-00275-1968 | 2026-07-30 | Priority-1
[12 empty] | T-00275-1969 | 2026-07-30 | Priority-1
[12 empty] | T-00275-1970 | 2026-07-30 | Priority-1
[12 empty] | T-00275-1971 | 2026-07-30 | Priority-1
[12 empty] | T-00275-1972 | 2026-07-30 | Priority-1
[12 empty] | T-00275-1973 | 2026-07-30 | Priority-1
[12 empty] | T-00275-1974 | 2026-07-17 | Priority-1
[12 empty] | T-00275-1975 | 2026-07-30 | Priority-1
[12 empty] | T-00275-1981 | 2026-07-30 | Priority-1
[12 empty] | T-00275-1982 | 2026-07-30 | Priority-1
[12 empty] | T-00275-1988 | 2026-07-17 | Priority-1
[12 empty] | T-00275-1989 | 2026-07-31 | Priority-1
[12 empty] | T-00275-1996 | 2026-07-30 | Priority-1
[12 empty] | T-00275-1997 | 2026-07-30 | Priority-1
[12 empty] | T-00275-1998 | 2026-07-30 | Priority-1
[12 empty] | T-00275-2001 | 2026-07-31 | Priority-1
[12 empty] | T-00275-2002 | 2026-07-31 | Priority-1
[12 empty] | T-00275-2003 | 2026-07-31 | Priority-1
[12 empty] | T-00275-2004 | 2026-07-31 | Priority-1
[12 empty] | T-00275-2005 | 2026-07-31 | Priority-1
[12 empty] | T-00275-2006 | 2026-07-31 | Priority-1
[12 empty] | T-00275-2007 | 2026-07-31 | Priority-1
[12 empty] | T-00275-2010 | 2026-07-31 | Priority-2
[12 empty] | T-00275-2011 | 2026-07-21 | Priority-1
[12 empty] | T-00525-0026 | 2026-07-17 | Priority-1
[12 empty] | T-00525-0027 | 2026-07-30 | Priority-1
[12 empty] | T-00525-0219 | 2026-07-17 | Priority-1
[12 empty] | T-00525-0220 | 2026-07-30 | Priority-1
[12 empty] | T-00525-0221 | 2026-07-30 | Priority-1
[12 empty] | T-00525-0227 | 2026-07-17 | Priority-1
[12 empty] | T-00525-0228 | 2026-07-17 | Priority-1
[12 empty] | T-00525-0233 | 2026-07-17 | Priority-1
[12 empty] | T-00525-0234 | 2026-07-17 | Priority-1
[12 empty] | T-00525-0241 | 2026-07-31 | Priority-2
[12 empty] | T-00525-0242 | 2026-07-31 | Priority-2
[12 empty] | T-00525-0278 | 2026-07-17 | Priority-1
[12 empty] | T-00525-0279 | 2026-07-30 | Priority-1
[12 empty] | T-00525-0466 | 2026-07-17 | Priority-1
[12 empty] | T-00525-0467 | 2026-07-17 | Priority-1
[12 empty] | T-00525-0468 | 2026-07-17 | Priority-1
[12 empty] | T-00525-0469 | 2026-07-17 | Priority-1
[12 empty] | T-00525-0546 | 2026-07-31 | Priority-1
[12 empty] | T-00525-0560 | 2026-07-31 | Priority-2
[12 empty] | T-00525-0561 | 2026-07-17 | Priority-1
[12 empty] | T-00525-0566 | 2026-07-30 | Priority-1
[12 empty] | T-00525-0570 | 2026-07-17 | Priority-1
[12 empty] | T-00525-0573 | 2026-07-31 | Priority-1
[12 empty] | T-00525-0583 | 2026-07-17 | Priority-1
[12 empty] | T-00525-0609 | 2026-07-30 | Priority-1
[12 empty] | T-00525-0899 | 2026-07-17 | Priority-1
[12 empty] | T-00525-0900 | 2026-07-30 | Priority-1
[12 empty] | T-00610-0220 | 2026-07-17 | Priority-1
[12 empty] | T-00610-0221 | 2026-07-17 | Priority-1
[12 empty] | T-00610-0222 | 2026-07-17 | Priority-1
[12 empty] | T-00610-0223 | 2026-07-30 | Priority-1
[12 empty] | T-00610-0224 | 2026-07-30 | Priority-1
[12 empty] | T-00610-0225 | 2026-07-30 | Priority-1
[12 empty] | T-00610-0241 | 2026-07-30 | Priority-1
[12 empty] | T-00610-0242 | 2026-07-30 | Priority-1
[12 empty] | T-00610-0574 | 2026-07-30 | Priority-1
[12 empty] | T-00610-0575 | 2026-07-30 | Priority-1
[12 empty] | T-00610-0576 | 2026-07-30 | Priority-1
[12 empty] | T-00614-0853 | 2026-06-25 | Priority-1
[12 empty] | T-00614-0854 | 2026-06-25 | Priority-1
[12 empty] | T-00614-0856 | 2026-06-25 | Priority-1
[12 empty] | T-00614-0859 | 2026-06-25 | Priority-1
[12 empty] | T-00614-0893 | 2026-06-25 | Priority-1
[12 empty] | T-00614-0896 | 2026-06-25 | Priority-1
[12 empty] | T-00614-0899 | 2026-06-25 | Priority-1
[12 empty] | T-00614-0903 | 2026-06-25 | Priority-1
[12 empty] | T-00614-0904 | 2026-06-25 | Priority-1
[12 empty] | T-00614-0953 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0954 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0955 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0956 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0957 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0961 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0965 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0966 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0967 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0982 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0983 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0984 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0985 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0986 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0987 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0988 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0989 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0991 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0992 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0993 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0994 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0995 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0996 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0997 | 2026-07-31 | Priority-1
[12 empty] | T-00614-0998 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1014 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1017 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1018 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1023 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1030 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1034 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1035 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1036 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1037 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1038 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1039 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1040 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1041 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1062 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1063 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1064 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1065 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1078 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1079 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1080 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1082 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1083 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1084 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1085 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1086 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1087 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1089 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1090 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1091 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1092 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1093 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1094 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1095 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1096 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1097 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1098 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1099 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1100 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1101 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1102 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1104 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1106 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1111 | 2026-07-31 | Priority-2
[12 empty] | T-00614-1112 | 2026-07-31 | Priority-2
[12 empty] | T-00614-1113 | 2026-07-31 | Priority-2
[12 empty] | T-00614-1114 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1115 | 2026-07-31 | Priority-1
[12 empty] | T-00614-1116 | 2026-07-31 | Priority-1