## Priority-1
CPP AGI - E/I/T Static & Conformity Closure Summary by Subsystem
Source: uploaded ovTasks_TestsPlanned_1369 (21).xlsx ¦ Updated all 44 workbook subsystems ¦ Company filter: CPP AGI ¦ Disciplines combined: Electrical + Instrumentation + Telecom ¦ Closed = Task State = Closed ¦ Overall = Static Test + Conformity Check.
| Subsystem IDs | Static Total | Static Closed | Static Balance | Static Closed % | Conformity Total | Conformity Closed | Conformity Balance | Conformity Closed % | Overall Total | Overall Closed | Overall Closed %
| 26 | 453 | 383 | 70 | 84.55% | 715 | 595 | 120 | 83.22% | 1168 | 978 | 83.73%
Combined Summary
| Group | Static Total | Static Closed | Static Balance | Static Closed % | Conformity Total | Conformity Closed | Conformity Balance | Conformity Closed % | Overall Total | Overall Closed | Overall Balance | Overall Closed %
| All E/I/T Disciplines | 453 | 383 | 70 | 84.55% | 715 | 595 | 120 | 83.22% | 1168 | 978 | 190 | 83.73%
Priority-01 | [15 empty] | We cannot Close the below ITR's Right now
Sl NO | Subsystem ID | Subsystem Description | Disciplines Included | Static Total | Static Closed | Static Balance | Static Closed % | Conformity Total | Conformity Closed | Conformity Balance | Conformity Closed % | Overall Total | Overall Closed | Overall Balance | Overall Closed % | Earthing | Cable LUG (Hole dia Issue) | Earthing Lightining Protection | CAT6/MODbus/Fiber | Transformer wall (Cables) | Drum Not available(EACOP) | Duplex filter JB & PIT Not find | Transformer | Total | Remarks as of 24-july-2026
1 | PS4-91-01 | Multicore cables & JB | I | 0 | 0 | 0 | 0% | 128 | 128 | 0 | 100% | 128 | 128 | 0 | 100% | [8 empty] | 0 |  | #VALUE! | #VALUE!
2 | PS4-63-03 | Electrical Earthing - Generator Building | E | 2 | 0 | 2 | 0% | 2 | 0 | 2 | 0% | 4 | 0 | 4 | 0% |  |  | 2 | [5 empty] | 2 | 2 ITR with Punch A | #VALUE! | #VALUE!
3 | PS4-63-01 | Electrical Earthing | E | 34 | 1 | 33 | 2.941% | 34 | 2 | 32 | 5.882% | 68 | 3 | 65 | 4.412% | 65 | [7 empty] | 65 | covered in above | #VALUE! | #VALUE!
4 | PS4-60-27 | Compressed Air Starting Skid | E/I | 4 | 4 | 0 | 100% | 6 | 6 | 0 | 100% | 10 | 10 | 0 | 100% | [8 empty] | 0 |  | #VALUE! | #VALUE!
5 | PS4-60-42 | Oil Mist Separator Skid PS4-60-VS-9100A | E/I | 2 | 2 | 0 | 100% | 4 | 4 | 0 | 100% | 6 | 6 | 0 | 100% | [8 empty] | 0 |  | #VALUE! | #VALUE!
6 | PS4-60-43 | Oil Mist Separator Skid PS4-60-VS-9100B | E/I | 2 | 2 | 0 | 100% | 4 | 4 | 0 | 100% | 6 | 6 | 0 | 100% | [8 empty] | 0 |  | #VALUE! | #VALUE!
7 | PS4-60-26 | Instrument Air Compressor Skid | E/I | 5 | 5 | 0 | 100% | 7 | 7 | 0 | 100% | 12 | 12 | 0 | 100% | [8 empty] | 0 |  | #VALUE! | #VALUE!
8 | PS4-60-49 | Lube Oil Separator Module PS4-60-UO-81100A | E/I/T | 8 | 7 | 1 | 87.5% | 10 | 9 | 1 | 90% | 18 | 16 | 2 | 88.89% |  |  |  | 2 |  |  |  |  | 2 | Scope to be clarify with EACOP and CPP headoffice | #VALUE! | #VALUE!
9 | PS4-60-50 | Lube Oil Separator Module PS4-60-UO-81100B | E/I/T | 8 | 7 | 1 | 87.5% | 10 | 9 | 1 | 90% | 18 | 16 | 2 | 88.89% |  |  |  | 2 |  |  |  |  | 2 | Scope to be clarify with EACOP and CPP headoffice | #VALUE! | #VALUE!
10 | PS4-60-56 | Fuel Conditioning Module PS4-60-UZ-8900A | E/I | 10 | 10 | 0 | 100% | 15 | 11 | 4 | 73.33% | 25 | 21 | 4 | 84% | [6 empty] | 4 |  | 4 |  | #VALUE! | #VALUE!
11 | PS4-60-58 | Fuel Conditioning Module PS4-60-UZ-8900B | E/I | 10 | 10 | 0 | 100% | 15 | 11 | 4 | 73.33% | 25 | 21 | 4 | 84% | [6 empty] | 4 |  | 4 |  | #VALUE! | #VALUE!
12 | PS4-60-57 | Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | E/I/T | 17 | 16 | 1 | 94.12% | 17 | 16 | 1 | 94.12% | 34 | 32 | 2 | 94.12% |  |  |  | 2 |  |  |  |  | 2 | Scope to be clarify with EACOP and CPP headoffice | #VALUE! | #VALUE!
13 | PS4-60-59 | Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | E/I/T | 17 | 16 | 1 | 94.12% | 17 | 16 | 1 | 94.12% | 34 | 32 | 2 | 94.12% |  |  |  | 2 |  |  |  |  | 2 | Scope to be clarify with EACOP and CPP headoffice | #VALUE! | #VALUE!
14 | PS4-60-02 | Power Gen Package A (UCP) | E/I | 31 | 31 | 0 | 100% | 36 | 36 | 0 | 100% | 67 | 67 | 0 | 100% | [8 empty] | 0 |  | #VALUE! | #VALUE!
15 | PS4-60-05 | Power Gen Package B (UCP) | E/I/T | 35 | 32 | 3 | 91.43% | 40 | 36 | 4 | 90% | 75 | 68 | 7 | 90.67% |  |  |  | 7 |  |  |  |  | 7 | Scope to be clarify with EACOP and CPP headoffice | #VALUE! | #VALUE!
16 | PS4-60-03 | Power Gen Package A Generator Auxiliary MCCs & DBs | E/I/T | 12 | 9 | 3 | 75% | 12 | 8 | 4 | 66.67% | 24 | 17 | 7 | 70.83% |  |  |  | 6 |  |  |  |  | 6 | Scope to be clarify with EACOP and CPP headoffice | #VALUE! | #VALUE!
17 | PS4-60-06 | Power Gen Package B Generator Auxiliary MCCs & DBs | E/I/T | 11 | 8 | 3 | 72.73% | 11 | 8 | 3 | 72.73% | 22 | 16 | 6 | 72.73% |  |  |  | 6 |  |  |  |  | 6 | Scope to be clarify with EACOP and CPP headoffice | #VALUE! | #VALUE!
18 | PS4-60-35 | Injector Tip Cooling Module A | E/I | 3 | 3 | 0 | 100% | 9 | 9 | 0 | 100% | 12 | 12 | 0 | 100% | [8 empty] | 0 |  | #VALUE! | #VALUE!
19 | PS4-60-36 | Injector Tip Cooling Module B | E/I | 3 | 3 | 0 | 100% | 9 | 9 | 0 | 100% | 12 | 12 | 0 | 100% | [8 empty] | 0 |  | #VALUE! | #VALUE!
20 | PS4-60-22 | Power Gen Master UCP | E/I/T | 53 | 37 | 16 | 69.81% | 64 | 34 | 30 | 53.12% | 117 | 71 | 46 | 60.68% |  |  |  | 42 |  |  |  |  | 42 | Scope to be clarify with EACOP and CPP headoffice | #VALUE! | #VALUE!
21 | PS4-71-23 | Diesel Fuel Pre Pressure Module (UCP) | E/I/T | 11 | 10 | 1 | 90.91% | 15 | 5 | 10 | 33.33% | 26 | 15 | 11 | 57.69% |  |  |  | 2 |  |  |  |  | 2 | Scope to be clarify with EACOP and CPP headoffice | #VALUE! | #VALUE!
22 | PS4-60-70 | Engine A Cooling system | E/I | 6 | 6 | 0 | 100% | 18 | 18 | 0 | 100% | 24 | 24 | 0 | 100% | [8 empty] | 0 |  | #VALUE! | #VALUE!
23 | PS4-60-71 | Engine B Cooling system | E/I | 6 | 6 | 0 | 100% | 18 | 18 | 0 | 100% | 24 | 24 | 0 | 100% | [8 empty] | 0 |  | #VALUE! | #VALUE!
24 | PS4-60-01 | Power Generation Package A | E/I | 86 | 84 | 2 | 97.67% | 112 | 94 | 18 | 83.93% | 198 | 178 | 20 | 89.9% |  |  |  |  | 3 |  |  | 2 | 5 | 1.Transformer top up oil to be completed , 2.CCP1 to be finalise cable tray support in Transformer wall | #VALUE! | #VALUE!
25 | PS4-60-04 | Power Generation Package B | E/I | 62 | 59 | 3 | 95.16% | 80 | 75 | 5 | 93.75% | 142 | 134 | 8 | 94.37% |  |  |  |  | 3 | 2 |  | 2 | 7 | 1.SRN-02017 ETA 29 0ctober(140 Mtr for Genset-B (6T X 0.75 IS/OS FL RTD) 2..Transformer top up oil to be completed , 3.CCP1 to be finalise cable tray support in Transformer wall | #VALUE! | #VALUE!
26 | PS4-71-22 | Diesel Fuel Pre Pressure Module | E/I | 15 | 15 | 0 | 100% | 22 | 22 | 0 | 100% | 37 | 37 | 0 | 100% | [8 empty] | 0 |  | #VALUE! | #VALUE!
27 | PS4-61-04 | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | E/I | 53 | 50 | 3 | 94.34% | 63 | 14 | 49 | 22.22% | 116 | 64 | 52 | 55.17% |  | 36 | [6 empty] | 36 | Cable lugs (500 SQ) mm hole not matching to SWG bus-bar bolt (Hole big size) | #VALUE! | #VALUE!
28 | PS4-06-02 | AC UPS - Power Generator Building | E/I | 26 | 19 | 7 | 73.08% | 32 | 20 | 12 | 62.5% | 58 | 39 | 19 | 67.24% | [8 empty] | 0 |  | #VALUE! | #VALUE!
|  |  |  | 532 | 452 | 80 | 23.263 | 810 | 629 | 181 |  | 1342 | 1042 | 242 | 77.65% | 65 | 36 | 2 | 71 | 6 | 2 | 8 | 4 | 194

## Priority-2 (hidden)
CPP AGI - E/I/T Static & Conformity Closure Summary by Subsystem
Source: uploaded ovTasks_TestsPlanned_1369 (21).xlsx ¦ Updated all 44 workbook subsystems ¦ Company filter: CPP AGI ¦ Disciplines combined: Electrical + Instrumentation + Telecom ¦ Closed = Task State = Closed ¦ Overall = Static Test + Conformity Check.
| Subsystem IDs | Static Total | Static Balance | Static Closed % | Conformity Total | Conformity Closed | Conformity Balance | Conformity Closed % | Overall Total | Overall Closed | Overall Closed %
| 23 | 461 | #REF! | #REF! | 610 | 87 | 523 | 14.26% | 1071 | #REF! | #REF!
Combined Summary
| Group | Static Total | Static Balance | Static Closed % | Conformity Total | Conformity Closed | Conformity Balance | Conformity Closed % | Overall Total | Overall Closed | Overall Balance | Overall Closed %
| All E/I/T Disciplines | 461 | #REF! | #REF! | 610 | 87 | 523 | 14.26% | 1071 | #REF! | #REF! | #REF!
Priority-01 C & D | [14 empty] | We cannot Close the below ITR's Right now
Sl NO | Subsystem ID | Subsystem Description | Static Total | Static Closed | Static Balance | Static Closed % | Conformity Total | Conformity Closed | Conformity Balance | Conformity Closed % | Overall Total | Overall Closed | Overall Balance | Overall Closed % | CAT6/MODbus/Fiber | Transformer wall (Cables) | Transformer | Duplex filter JB & PIT Not find
1 | PS4-60-07 | Power Generation Package C | 62 | 56 | 6 | 90.32% | 80 | 21 | 59 | 26.25% | 142 | 77 | 65 | 54.23%
2 | PS4-60-08 | Power Gen Package C (UCP) | 35 | 27 | 8 | 77.14% | 40 | 0 | 40 | 0% | 75 | 27 | 48 | 36%
3 | PS4-60-09 | Power Gen Package C Generator Auxiliary MCCs & DBs | 12 | 9 | 3 | 75% | 12 | 5 | 7 | 41.67% | 24 | 14 | 10 | 58.33%
4 | PS4-60-10 | Power Generation Package D | 76 | 66 | 10 | 86.84% | 95 | 10 | 85 | 10.53% | 171 | 76 | 95 | 44.44%
5 | PS4-60-11 | Power Gen Package D (UCP) | 35 | 23 | 12 | 65.71% | 40 | 0 | 40 | 0% | 75 | 23 | 52 | 30.67%
6 | PS4-60-12 | Power Gen Package D Generator Auxiliary MCCs & DBs | 11 | 8 | 3 | 72.73% | 11 | 4 | 7 | 36.36% | 22 | 12 | 10 | 54.55%
7 | PS4-60-37 | Injector Tip Cooling Module C | 3 | 3 | 0 | 100% | 9 | 2 | 7 | 22.22% | 12 | 5 | 7 | 41.67%
8 | PS4-60-38 | Injector Tip Cooling Module D | 3 | 3 | 0 | 100% | 9 | 0 | 9 | 0% | 12 | 3 | 9 | 25%
9 | PS4-60-44 | Oil Mist Separator Skid PS4-60-VS-9100C | 2 | 2 | 0 | 100% | 4 | 0 | 4 | 0% | 6 | 2 | 4 | 33.33%
10 | PS4-60-45 | Oil Mist Separator Skid PS4-60-VS-9100D | 2 | 2 | 0 | 100% | 4 | 0 | 4 | 0% | 6 | 2 | 4 | 33.33%
11 | PS4-60-51 | Lube Oil Separator Module PS4-60-UO-81100C | 8 | 7 | 1 | 87.5% | 10 | 1 | 9 | 10% | 18 | 8 | 10 | 44.44%
12 | PS4-60-52 | Lube Oil Separator Module PS4-60-UO-81100D | 8 | 6 | 2 | 75% | 10 | 1 | 9 | 10% | 18 | 7 | 11 | 38.89%
13 | PS4-60-60 | Fuel Conditioning Module PS4-60-UZ-8900C | 10 | 9 | 1 | 90% | 15 | 0 | 15 | 0% | 25 | 9 | 16 | 36%
14 | PS4-60-61 | Fuel Conditioning Module PS4-60-UZ-8900C (UCP) | 17 | 12 | 5 | 70.59% | 17 | 0 | 17 | 0% | 34 | 12 | 22 | 35.29%
15 | PS4-60-62 | Fuel Conditioning Module PS4-60-UZ-8900D | 10 | 7 | 3 | 70% | 15 | 0 | 15 | 0% | 25 | 7 | 18 | 28%
16 | PS4-60-63 | Fuel Conditioning Module PS4-60-UZ-8900D (UCP) | 17 | 12 | 5 | 70.59% | 17 | 0 | 17 | 0% | 34 | 12 | 22 | 35.29%
17 | PS4-60-72 | Engine C Cooling system | 6 | 6 | 0 | 100% | 18 | 8 | 10 | 44.44% | 24 | 14 | 10 | 58.33%
18 | PS4-60-73 | Engine D Cooling system | 6 | 6 | 0 | 100% | 18 | 8 | 10 | 44.44% | 24 | 14 | 10 | 58.33%
19 | PS4-03-14 | FZ-14 - Power Generation Building - Switchgear Room | 30 | 28 | 2 | 93.33% | 46 | 0 | 46 | 0% | 76 | 28 | 48 | 36.84%
20 | PS4-71-18 | Diesel Separator Module | 13 | 8 | 5 | 61.54% | 21 | 0 | 21 | 0% | 34 | 8 | 26 | 23.53%
21 | PS4-71-06 | Crude Fuel Separation Module | 16 | 6 | 10 | 37.5% | 26 | 0 | 26 | 0% | 42 | 6 | 36 | 14.29%
22 | PS4-71-08 | CFO Pre-Pressure Module | 25 | 25 | 0 | 100% | 33 | 25 | 8 | 75.76% | 58 | 50 | 8 | 86.21%
23 | PS4-71-07 | Crude Fuel Separation Module (UCP) | 54 | 48 | 6 | 88.89% | 60 | 2 | 58 | 3.333% | 114 | 50 | 64 | 43.86%
|  |  | 461 | 379 | 82 | 82.21% | 610 | 87 | 523 | 14.26% | 1071 | 466 | 605 | 43.51% | 0 | 0 | 0 | 0 | 0

## Priority-EDG
CPP AGI - E/I/T Static & Conformity Closure Summary by Subsystem
Source: uploaded ovTasks_TestsPlanned_1369 (21).xlsx ¦ Updated all 44 workbook subsystems ¦ Company filter: CPP AGI ¦ Disciplines combined: Electrical + Instrumentation + Telecom ¦ Closed = Task State = Closed ¦ Overall = Static Test + Conformity Check.
| Subsystem IDs | Static Total | Static Balance | Static Closed % | Conformity Total | Conformity Closed | Conformity Balance | Conformity Closed % | Overall Total | Overall Closed | Overall Closed %
| 2 | 75 | #REF! | #REF! | 84 | 42 | 42 | 50% | 159 | #REF! | #REF!
Combined Summary
| Group | Static Total | Static Balance | Static Closed % | Conformity Total | Conformity Closed | Conformity Balance | Conformity Closed % | Overall Total | Overall Closed | Overall Balance | Overall Closed %
| All E/I/T Disciplines | 75 | #REF! | #REF! | 84 | 42 | 42 | 50% | 159 | #REF! | #REF! | #REF!
EDG ITR Status | [14 empty] | ITR Closing ON-Going | We cannot Close the below ITR's Right now
Sl NO | Subsystem ID | Subsystem Description | Static Total | Static Closed | Static Balance | Static Closed % | Conformity Total | Conformity Closed | Conformity Balance | Conformity Closed % | Overall Total ITR | Overall Closed ITR | Overall Balance ITR | Overall Closed % |  | Cable Gland Not available M25/M32/M40 | Cable Lug 500 Sqmm (Hole Missmatch) | Total
1 | PS4-05-01 | Emergency Diesel Generator Package | 51 | 51 | 0 | 100% | 55 | 20 | 35 | 36.36% | 106 | 71 | 35 | 66.98% | 8 | 9 | 18 | 27
2 | PS4-05-02 | Emergency Diesel Generator Package (UCP) | 24 | 23 | 1 | 95.83% | 29 | 22 | 7 | 75.86% | 53 | 45 | 8 | 84.91% | 7 | 1 | 0 | 1
|  | Total | 75 | 74 | 1 | 98.67% | 84 | 42 | 42 | 50% | 159 | 116 | 43 | 72.96% | 15 | 10 | 18 | 28

## Exported from SC
Task ID | Asset - Tag | Asset Pack ID | Cable Pack ID | Pipe Pack ID | Loop Name | Description | Category (Summary) | Discipline | Task Type (Name) | Discipline (Summary) | Asset - Description | Systemization - Process Plant ID | Responsible Company (Summary) | Actual Duration | Scheduled Duration | Task Duration | Title - Actual MH/Person | Title - Planned MH/Person | Field005 (Custom) | Physical Location - Area (Summary) | Systemization - Subsystem (Summary) | Closing Date | Subsystem ID | Task Priority | Priority | Test Form - Description | Asset Discipline | Task State | Subsystem Priority | Task Model | Closed By
T-00018-0106 | PS4-61-ISR-0101 |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Shunt Reactor | EACOP | CPP AGI |  |  | 16 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00018
T-00018-0107 | PS4-61-IU-0010 |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LLHT Oil Transformer | EACOP | CPP AGI |  |  | 16 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) |  | PS4-61-02 |  |  | Power Transformer | E | To be completed | PS4 - Milestone G | TM-00018
T-00018-0108 | PS4-61-IV-0001A |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Distribution Transformer | EACOP | CPP AGI |  |  | 16 |  | 16 | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-07-02 11:23 | PS4-61-06 |  |  | Power Transformer | E | Closed | PS4 - Milestone A | TM-00018 | sridhar, muthu
T-00018-0109 | PS4-61-IV-0001B |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Distribution Transformer | EACOP | CPP AGI |  |  | 16 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-07-02 11:26 | PS4-61-06 |  |  | Power Transformer | E | Closed | PS4 - Milestone A | TM-00018 | sridhar, muthu
T-00018-0110 | PS4-63-IV-0010 |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing Transformer | EACOP | CPP AGI |  |  | 16 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00018
T-00018-0111 | PS4-63-IV-0011 |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing Transformer | EACOP | CPP AGI |  |  | 16 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00018
T-00018-0117 | PS4-61-IV-0002A |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Distribution Transformer | EACOP | CPP AGI |  |  | 16 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00018
T-00018-0118 | PS4-61-IV-0002B |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Distribution Transformer | EACOP | CPP AGI |  |  | 16 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00018
T-00018-0119 | PS4-61-IV-0007A |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Distribution Transformer | EACOP | CPP AGI |  |  | 16 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00018
T-00018-0120 | PS4-61-IV-0007B |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Distribution Transformer | EACOP | CPP AGI |  |  | 16 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00018
T-00018-0174 | PS4-61-IU-3100A |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | VFD Transformer | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Power Transformer | E | To be completed | PS4 - Milestone H | TM-00018
T-00018-0175 | PS4-61-IU-3100B |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | VFD Transformer | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Power Transformer | E | To be completed | PS4 - Milestone H | TM-00018
T-00018-0176 | PS4-61-IU-3100C |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | VFD Transformer | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Power Transformer | E | To be completed | PS4 - Milestone H | TM-00018
T-00018-0185 | PS4-61-IU-0001A |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A |  | PS4-60-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone B | TM-00018
T-00018-0186 | PS4-61-IU-0001B |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B |  | PS4-60-04 |  |  | Power Transformer | E | To be completed | PS4 - Milestone B | TM-00018
T-00018-0187 | PS4-61-IU-0001C |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00018
T-00018-0188 | PS4-61-IU-0001D |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00018
T-00018-0189 | PS4-61-IU-0001E |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00018
T-00018-0190 | PS4-61-IU-0001F |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00018
T-00018-0191 | PS4-61-IU-0001G |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Power Transformer | E | To be completed | PS4 - Milestone E | TM-00018
T-00018-0221 | PS4-79-IV-0001 |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Feeder to EHT Transformer / DB 1 | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone H | TM-00018
T-00018-0222 | PS4-79-IV-0002 |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Feeder to EHT Transformer / DB 2 | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Power Transformer | E | To be completed | PS4 - Milestone H | TM-00018
T-00018-0223 | PS4-79-IV-0003 |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Feeder to EHT Transformer / DB 3 | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Power Transformer | E | To be completed | PS4 - Milestone H | TM-00018
T-00018-0224 | PS4-79-IV-0004 |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Feeder to EHT Transformer / DB 4 | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Power Transformer | E | To be completed | PS4 - Milestone H | TM-00018
T-00018-0225 | PS4-79-IV-0005 |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Feeder to EHT Transformer / DB 5 | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Power Transformer | E | To be completed | PS4 - Milestone H | TM-00018
T-00018-0226 | PS4-79-IV-0006 |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Feeder to EHT Transformer / DB 6 | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Power Transformer | E | To be completed | PS4 - Milestone H | TM-00018
T-00018-0227 | PS4-79-IV-0007 |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Feeder to EHT Transformer / DB 7 | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Power Transformer | E | To be completed | PS4 - Milestone H | TM-00018
T-00018-0228 | PS4-79-IV-0008 |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Feeder to EHT Transformer / DB 8 | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Power Transformer | E | To be completed | PS4 - Milestone H | TM-00018
T-00018-0229 | PS4-79-IV-0009 |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Feeder to EHT Transformer / DB 9 | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Power Transformer | E | To be completed | PS4 - Milestone H | TM-00018
T-00018-0230 | PS4-79-IV-0010 |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Feeder to EHT Transformer / DB 10 | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Power Transformer | E | To be completed | PS4 - Milestone H | TM-00018
T-00018-0231 | PS4-79-IV-0011 |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Feeder to EHT Transformer / DB 11 | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Power Transformer | E | To be completed | PS4 - Milestone H | TM-00018
T-00018-0232 | PS4-79-IV-0012 |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Feeder to EHT Transformer / DB 12 | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Power Transformer | E | To be completed | PS4 - Milestone H | TM-00018
T-00018-0233 | PS4-87-IRF-0001 |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Transformer Rectifier Unit 1-for tank (PS4-53-TR-4100) | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-53-01 - Utility Water / Storage Tank |  | PS4-53-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone C | TM-00018
T-00018-0234 | PS4-87-IRF-0002 |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Transformer Rectifier Unit 2-for tank (PS4-71-TR-4100) | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Power Transformer | E | To be completed | PS4 - Milestone H | TM-00018
T-00018-0235 | PS4-87-IRF-0003 |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Transformer Rectifier Unit 3-for tank (PS4-71-TR-4200) | EACOP | CPP AGI |  |  | 16 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Power Transformer | E | To be completed | PS4 - Milestone H | TM-00018
T-00018-0236 | PS4-87-IRF-0004 |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Transformer Rectifier Unit 4-for tank ( PS4-71-TR-4400) | EACOP | CPP AGI |  |  | 16 |  | 16 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank |  | PS4-71-15 |  |  | Power Transformer | E | To be completed | PS4 - Milestone F | TM-00018
T-00018-0292 | PS4-61-IV-0005A |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Distribution Transformer | EACOP | CPP AGI |  |  | 16 |  | 16 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00018
T-00018-0293 | PS4-61-IV-0005B |  |  |  |  | CPX02 - Power transformer | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Distribution Transformer | EACOP | CPP AGI |  |  | 16 |  | 16 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00018
T-00019-0033 | PS4-61-IK-0003 |  |  |  |  | CPX05 - LV switchboard | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LV SWGR | EACOP | CPP AGI |  |  | 24 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV- Switchboard | E | To be completed | PS4 - Milestone B | TM-00019
T-00019-0034 | PS4-61-IK-0006 |  |  |  |  | CPX05 - LV switchboard | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LV SWGR | EACOP | CPP AGI |  |  | 24 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV- Switchboard | E | To be completed | PS4 - Milestone D | TM-00019
T-00022-3489 | PS4-25-DM-3100A-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-24 08:41 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3490 | PS4-25-DM-3100A-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-24 08:41 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3491 | PS4-25-DM-3100A-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-24 08:42 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3492 | PS4-25-DM-3100A-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-24 08:42 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3493 | PS4-25-DM-3100A-CH05 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-24 08:42 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3494 | PS4-25-DM-3100A-CH06 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-24 08:43 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3495 | PS4-25-DM-3100B-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-24 08:44 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3496 | PS4-25-DM-3100B-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-24 08:44 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3497 | PS4-25-DM-3100B-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-24 08:44 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3498 | PS4-25-DM-3100B-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-24 08:45 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3499 | PS4-25-DM-3100B-CH05 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-24 08:45 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3500 | PS4-25-DM-3100B-CH06 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-24 08:46 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3501 | PS4-25-DM-3100C-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-24 08:46 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3502 | PS4-25-DM-3100C-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-24 08:47 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3503 | PS4-25-DM-3100C-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-24 08:47 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3504 | PS4-25-DM-3100C-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-24 08:47 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3505 | PS4-25-DM-3100C-CH05 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-24 08:48 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3506 | PS4-25-DM-3100C-CH06 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-24 08:48 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3507 | PS4-60-IJ-0001A-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100A TO PS4-60-IJ-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-18 05:19 | PS4-60-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00022 | sridhar, muthu
T-00022-3508 | PS4-60-IJ-0001B-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100B TO PS4-60-IJ-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-18 05:21 | PS4-60-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00022 | sridhar, muthu
T-00022-3509 | PS4-60-IJ-0001C-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100C TO PS4-60-IJ-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-18 05:24 | PS4-60-07 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3510 | PS4-60-IJ-0001D-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100D TO PS4-60-IJ-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-18 05:25 | PS4-60-10 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3511 | PS4-60-IJ-0001E-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100E TO PS4-60-IJ-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-18 05:26 | PS4-60-13 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3512 | PS4-60-IJ-0001F-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100F TO PS4-60-IJ-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-18 05:27 | PS4-60-16 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3513 | PS4-60-IJ-0001G-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100G TO PS4-60-IJ-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-18 05:29 | PS4-60-19 |  |  | HV Power Cable | E | Closed | PS4 - Milestone E | TM-00022 | sridhar, muthu
T-00022-3514 | PS4-61-IDH-3100A-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-23 14:01 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3515 | PS4-61-IDH-3100A-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-23 14:03 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3516 | PS4-61-IDH-3100A-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-23 14:04 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3517 | PS4-61-IDH-3100A-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-23 14:05 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3518 | PS4-61-IDH-3100A-CH05 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-23 14:06 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3519 | PS4-61-IDH-3100A-CH06 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-23 14:07 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3520 | PS4-61-IDH-3100A-CH07 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-23 14:08 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3521 | PS4-61-IDH-3100A-CH08 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-23 14:09 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3522 | PS4-61-IDH-3100A-CH09 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-23 14:27 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3523 | PS4-61-IDH-3100A-CH10 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-23 14:28 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3524 | PS4-61-IDH-3100A-CH11 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-23 14:29 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3525 | PS4-61-IDH-3100A-CH12 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-23 14:30 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3526 | PS4-61-IDH-3100B-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-23 14:31 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3527 | PS4-61-IDH-3100B-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-23 14:32 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3528 | PS4-61-IDH-3100B-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-23 14:33 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3529 | PS4-61-IDH-3100B-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-23 14:33 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3530 | PS4-61-IDH-3100B-CH05 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-23 14:36 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3531 | PS4-61-IDH-3100B-CH06 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-23 14:36 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3532 | PS4-61-IDH-3100B-CH07 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-23 14:37 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3533 | PS4-61-IDH-3100B-CH08 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-23 14:38 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3534 | PS4-61-IDH-3100B-CH09 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-23 14:39 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3535 | PS4-61-IDH-3100B-CH10 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-23 14:39 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3536 | PS4-61-IDH-3100B-CH11 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-23 14:40 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3537 | PS4-61-IDH-3100B-CH12 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-23 14:41 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3538 | PS4-61-IDH-3100C-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-23 14:42 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3539 | PS4-61-IDH-3100C-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-23 14:44 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3540 | PS4-61-IDH-3100C-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-23 14:45 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3541 | PS4-61-IDH-3100C-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-23 14:45 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3542 | PS4-61-IDH-3100C-CH05 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-23 14:46 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3543 | PS4-61-IDH-3100C-CH06 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-23 14:47 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3544 | PS4-61-IDH-3100C-CH07 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-23 14:47 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3545 | PS4-61-IDH-3100C-CH08 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-23 14:48 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3546 | PS4-61-IDH-3100C-CH09 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-23 14:49 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3547 | PS4-61-IDH-3100C-CH10 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-23 14:49 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3548 | PS4-61-IDH-3100C-CH11 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-23 14:51 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3549 | PS4-61-IDH-3100C-CH12 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-23 14:52 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3550 | PS4-61-IJ-0001-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0001A TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-03-02 13:42 | PS4-60-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00022 | sridhar, muthu
T-00022-3551 | PS4-61-IJ-0001-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0001A TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-03-02 13:43 | PS4-60-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00022 | sridhar, muthu
T-00022-3552 | PS4-61-IJ-0001-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0001A TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-03-02 13:44 | PS4-60-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00022 | sridhar, muthu
T-00022-3553 | PS4-61-IJ-0001-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0001B TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-03-02 13:46 | PS4-60-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00022 | sridhar, muthu
T-00022-3554 | PS4-61-IJ-0001-CH05 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0001B TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-03-02 13:47 | PS4-60-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00022 | sridhar, muthu
T-00022-3555 | PS4-61-IJ-0001-CH06 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0001B TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-03-02 13:48 | PS4-60-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00022 | sridhar, muthu
T-00022-3556 | PS4-61-IJ-0001-CH07 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0001C TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-03-02 13:49 | PS4-60-07 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3557 | PS4-61-IJ-0001-CH08 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0001C TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-03-02 13:50 | PS4-60-07 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3558 | PS4-61-IJ-0001-CH09 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0001C TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-03-02 13:51 | PS4-60-07 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3559 | PS4-61-IJ-0001-CH10 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0001D TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-03-02 13:53 | PS4-60-10 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3560 | PS4-61-IJ-0001-CH11 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0001D TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-03-02 13:54 | PS4-60-10 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3561 | PS4-61-IJ-0001-CH12 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0001D TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-03-02 13:56 | PS4-60-10 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3562 | PS4-61-IJ-0001-CH13 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0001E TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-03-02 13:57 | PS4-60-13 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3563 | PS4-61-IJ-0001-CH14 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0001E TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-03-02 13:59 | PS4-60-13 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3564 | PS4-61-IJ-0001-CH15 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0001E TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-03-02 14:00 | PS4-60-13 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3565 | PS4-61-IJ-0001-CH16 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0001F TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-03-02 14:02 | PS4-60-16 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3566 | PS4-61-IJ-0001-CH17 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0001F TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-03-03 04:26 | PS4-60-16 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3567 | PS4-61-IJ-0001-CH18 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0001F TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-03-03 04:28 | PS4-60-16 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3568 | PS4-61-IJ-0001-CH19 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0001G TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-03-03 04:30 | PS4-60-19 |  |  | HV Power Cable | E | Closed | PS4 - Milestone E | TM-00022 | sridhar, muthu
T-00022-3569 | PS4-61-IJ-0001-CH20 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0001G TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-03-03 04:31 | PS4-60-19 |  |  | HV Power Cable | E | Closed | PS4 - Milestone E | TM-00022 | sridhar, muthu
T-00022-3570 | PS4-61-IJ-0001-CH21 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0001G TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-03-03 04:32 | PS4-60-19 |  |  | HV Power Cable | E | Closed | PS4 - Milestone E | TM-00022 | sridhar, muthu
T-00022-3571 | PS4-61-IJ-0010-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0010 TO PS4-61-IJ-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-03-03 04:45 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00022 | sridhar, muthu
T-00022-3572 | PS4-61-IJ-0010-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0010 TO PS4-61-IJ-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-03-03 04:46 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00022 | sridhar, muthu
T-00022-3573 | PS4-61-IJ-0010-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0010 TO PS4-61-IJ-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-03-03 04:47 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00022 | sridhar, muthu
T-00022-3574 | PS4-61-IJ-0010-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0010 TO PS4-61-IJ-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-03-03 04:49 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00022 | sridhar, muthu
T-00022-3575 | PS4-61-IJ-0010-CH05 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0010 TO PS4-61-IJ-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-03-03 04:51 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00022 | sridhar, muthu
T-00022-3576 | PS4-61-IJ-0010-CH06 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0010 TO PS4-61-IJ-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-03-03 04:52 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00022 | sridhar, muthu
T-00022-3577 | PS4-61-ISR-0101-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-ISR-0101 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-03-02 12:09 | PS4-61-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3578 | PS4-61-ISR-0101-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-ISR-0101 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-03-02 12:09 | PS4-61-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3579 | PS4-61-ISR-0101-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-ISR-0101 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-03-02 12:09 | PS4-61-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3580 | PS4-61-IU-0001A-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100A TO PS4-61-IU-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-01-31 04:47 | PS4-60-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00022 | sridhar, muthu
T-00022-3581 | PS4-61-IU-0001A-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100A TO PS4-61-IU-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-01-31 04:53 | PS4-60-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00022 | sridhar, muthu
T-00022-3582 | PS4-61-IU-0001A-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100A TO PS4-61-IU-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-01-31 04:59 | PS4-60-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00022 | sridhar, muthu
T-00022-3583 | PS4-61-IU-0001B-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100B TO PS4-61-IU-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-01-31 05:02 | PS4-60-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00022 | sridhar, muthu
T-00022-3584 | PS4-61-IU-0001B-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100B TO PS4-61-IU-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-01-31 05:07 | PS4-60-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00022 | sridhar, muthu
T-00022-3585 | PS4-61-IU-0001B-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100B TO PS4-61-IU-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-01-31 05:27 | PS4-60-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00022 | sridhar, muthu
T-00022-3586 | PS4-61-IU-0001C-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100C TO PS4-61-IU-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-01-31 05:29 | PS4-60-07 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3587 | PS4-61-IU-0001C-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100C TO PS4-61-IU-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-01-31 05:36 | PS4-60-07 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3588 | PS4-61-IU-0001C-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100C TO PS4-61-IU-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-01-31 05:39 | PS4-60-07 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3589 | PS4-61-IU-0001D-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100D TO PS4-61-IU-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-01-31 05:42 | PS4-60-10 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3590 | PS4-61-IU-0001D-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100D TO PS4-61-IU-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-01-31 05:44 | PS4-60-10 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3591 | PS4-61-IU-0001D-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100D TO PS4-61-IU-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-01-31 05:47 | PS4-60-10 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3592 | PS4-61-IU-0001E-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100E TO PS4-61-IU-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-01-31 05:48 | PS4-60-13 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3593 | PS4-61-IU-0001E-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100E TO PS4-61-IU-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-01-31 05:51 | PS4-60-13 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3594 | PS4-61-IU-0001E-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100E TO PS4-61-IU-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-01-31 05:53 | PS4-60-13 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3595 | PS4-61-IU-0001F-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100F TO PS4-61-IU-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-01-31 05:56 | PS4-60-16 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3596 | PS4-61-IU-0001F-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100F TO PS4-61-IU-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-01-31 05:59 | PS4-60-16 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3597 | PS4-61-IU-0001F-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100F TO PS4-61-IU-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-01-31 06:01 | PS4-60-16 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3598 | PS4-61-IU-0001G-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100G TO PS4-61-IU-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-01-31 06:03 | PS4-60-19 |  |  | HV Power Cable | E | Closed | PS4 - Milestone E | TM-00022 | sridhar, muthu
T-00022-3599 | PS4-61-IU-0001G-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100G TO PS4-61-IU-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-01-31 06:04 | PS4-60-19 |  |  | HV Power Cable | E | Closed | PS4 - Milestone E | TM-00022 | sridhar, muthu
T-00022-3600 | PS4-61-IU-0001G-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-GE-8100G TO PS4-61-IU-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-01-31 06:06 | PS4-60-19 |  |  | HV Power Cable | E | Closed | PS4 - Milestone E | TM-00022 | sridhar, muthu
T-00022-3601 | PS4-61-IU-0010-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-03-02 12:13 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00022 | sridhar, muthu
T-00022-3602 | PS4-61-IU-0010-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-03-02 12:15 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00022 | sridhar, muthu
T-00022-3603 | PS4-61-IU-0010-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-03-02 12:15 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00022 | sridhar, muthu
T-00022-3604 | PS4-61-IU-3100A-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-24 08:49 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3605 | PS4-61-IU-3100A-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-24 08:49 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3606 | PS4-61-IU-3100A-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-24 08:49 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3607 | PS4-61-IU-3100A-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0006A TO PS4-61-IU-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-23 14:54 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3608 | PS4-61-IU-3100B-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-24 08:51 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3609 | PS4-61-IU-3100B-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-24 08:51 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3610 | PS4-61-IU-3100B-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-24 08:51 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3611 | PS4-61-IU-3100B-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0006B TO PS4-61-IU-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-23 14:55 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3612 | PS4-61-IU-3100C-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-24 08:52 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3613 | PS4-61-IU-3100C-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-24 08:53 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3614 | PS4-61-IU-3100C-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-24 08:53 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3615 | PS4-61-IU-3100C-CH04 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0006C TO PS4-61-IU-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-23 14:56 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00022 | sridhar, muthu
T-00022-3616 | PS4-61-IV-0001A-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-03-03 04:34 | PS4-61-06 |  |  | HV Power Cable | E | Closed | PS4 - Milestone A | TM-00022 | sridhar, muthu
T-00022-3617 | PS4-61-IV-0001A-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-03-03 04:36 | PS4-61-06 |  |  | HV Power Cable | E | Closed | PS4 - Milestone A | TM-00022 | sridhar, muthu
T-00022-3618 | PS4-61-IV-0001A-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-03-03 04:37 | PS4-61-06 |  |  | HV Power Cable | E | Closed | PS4 - Milestone A | TM-00022 | sridhar, muthu
T-00022-3619 | PS4-61-IV-0001B-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-03-03 04:39 | PS4-61-06 |  |  | HV Power Cable | E | Closed | PS4 - Milestone A | TM-00022 | sridhar, muthu
T-00022-3620 | PS4-61-IV-0001B-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-03-03 04:40 | PS4-61-06 |  |  | HV Power Cable | E | Closed | PS4 - Milestone A | TM-00022 | sridhar, muthu
T-00022-3621 | PS4-61-IV-0001B-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-03-03 04:41 | PS4-61-06 |  |  | HV Power Cable | E | Closed | PS4 - Milestone A | TM-00022 | sridhar, muthu
T-00022-3622 | PS4-61-IV-0002A-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-03-02 12:42 | PS4-61-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00022 | sridhar, muthu
T-00022-3623 | PS4-61-IV-0002A-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-03-02 12:43 | PS4-61-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00022 | sridhar, muthu
T-00022-3624 | PS4-61-IV-0002A-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-03-02 12:44 | PS4-61-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00022 | sridhar, muthu
T-00022-3625 | PS4-61-IV-0002B-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-03-02 12:59 | PS4-61-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00022 | sridhar, muthu
T-00022-3626 | PS4-61-IV-0002B-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-03-02 13:00 | PS4-61-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00022 | sridhar, muthu
T-00022-3627 | PS4-61-IV-0002B-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-03-02 13:01 | PS4-61-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00022 | sridhar, muthu
T-00022-3628 | PS4-61-IV-0005A-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0005A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-03 - 0.4kV Switchboard Office & Facilities Building (PS4-61-IK-0005) |  | PS4-61-03 |  |  | HV Power Cable | E | To be completed | PS4 - Milestone I | TM-00022
T-00022-3629 | PS4-61-IV-0005A-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0005A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-03 - 0.4kV Switchboard Office & Facilities Building (PS4-61-IK-0005) |  | PS4-61-03 |  |  | HV Power Cable | E | To be completed | PS4 - Milestone I | TM-00022
T-00022-3630 | PS4-61-IV-0005A-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0005A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-03 - 0.4kV Switchboard Office & Facilities Building (PS4-61-IK-0005) |  | PS4-61-03 |  |  | HV Power Cable | E | To be completed | PS4 - Milestone I | TM-00022
T-00022-3631 | PS4-61-IV-0005B-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0005B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-03 - 0.4kV Switchboard Office & Facilities Building (PS4-61-IK-0005) |  | PS4-61-03 |  |  | HV Power Cable | E | To be completed | PS4 - Milestone I | TM-00022
T-00022-3632 | PS4-61-IV-0005B-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0005B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-03 - 0.4kV Switchboard Office & Facilities Building (PS4-61-IK-0005) |  | PS4-61-03 |  |  | HV Power Cable | E | To be completed | PS4 - Milestone I | TM-00022
T-00022-3633 | PS4-61-IV-0005B-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0005B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-03 - 0.4kV Switchboard Office & Facilities Building (PS4-61-IK-0005) |  | PS4-61-03 |  |  | HV Power Cable | E | To be completed | PS4 - Milestone I | TM-00022
T-00022-3634 | PS4-61-IV-0007A-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0007A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-03-02 13:26 | PS4-61-05 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3635 | PS4-61-IV-0007A-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0007A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-03-02 13:28 | PS4-61-05 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3636 | PS4-61-IV-0007A-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0007A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-03-02 13:30 | PS4-61-05 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3637 | PS4-61-IV-0007B-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0007B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-03-02 13:32 | PS4-61-05 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3638 | PS4-61-IV-0007B-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0007B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-03-02 13:35 | PS4-61-05 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3639 | PS4-61-IV-0007B-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0007B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-03-02 13:36 | PS4-61-05 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3640 | PS4-61-NER-0010-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0010 TO PS4-61-NER-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) |  | PS4-61-02 |  |  | HV Power Cable | E | To be completed | PS4 - Milestone G | TM-00022
T-00022-3641 | PS4-63-IV-0010-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-63-IV-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-03-02 12:19 | PS4-61-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3642 | PS4-63-IV-0010-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-63-IV-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-03-02 12:26 | PS4-61-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3643 | PS4-63-IV-0010-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-63-IV-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-03-02 12:25 | PS4-61-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3644 | PS4-63-IV-0011-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-63-IV-0011 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-03-02 12:31 | PS4-61-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3645 | PS4-63-IV-0011-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-63-IV-0011 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-03-02 12:34 | PS4-61-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3646 | PS4-63-IV-0011-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-63-IV-0011 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-03-02 12:36 | PS4-61-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00022 | sridhar, muthu
T-00022-3647 | PS4-63-NER-0010-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-63-IV-0010 TO PS4-63-NER-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | HV Power Cable | E | To be completed | PS4 - Milestone D | TM-00022
T-00022-3648 | PS4-63-NER-0011-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-63-IV-0011 TO PS4-63-NER-0011 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | HV Power Cable | E | To be completed | PS4 - Milestone D | TM-00022
T-00022-3649 | PS4-79-BH-0001-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0010 TO PS4-79-BH-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-04-24 08:54 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00022 | sridhar, muthu
T-00022-3650 | PS4-79-BH-0001-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0010 TO PS4-79-BH-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-04-24 08:54 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00022 | sridhar, muthu
T-00022-3651 | PS4-79-BH-0001-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0010 TO PS4-79-BH-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-04-24 08:55 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00022 | sridhar, muthu
T-00022-3652 | PS4-79-BH-0002-CH01 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0010 TO PS4-79-BH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-04-24 08:55 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00022 | sridhar, muthu
T-00022-3653 | PS4-79-BH-0002-CH02 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0010 TO PS4-79-BH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-04-24 08:56 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00022 | sridhar, muthu
T-00022-3654 | PS4-79-BH-0002-CH03 |  |  |  |  | CPX08 - HV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0010 TO PS4-79-BH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-04-24 08:56 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00022 | sridhar, muthu
T-00023-10030 | PS4-62-IE-0001-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10031 | PS4-62-IE-0001-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10032 | PS4-62-IE-0001-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10033 | PS4-62-IE-0001-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10034 | PS4-62-IE-0001-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10035 | PS4-62-IE-0001-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10036 | PS4-62-IE-0001-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10037 | PS4-62-IE-0001-CL52 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10038 | PS4-62-IE-0001-CL53 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10039 | PS4-62-IE-0001-CL54 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10040 | PS4-62-IE-0001-CL55 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10041 | PS4-62-IE-0001-CL56 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10042 | PS4-62-IE-0001-CL57 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10043 | PS4-62-IE-0001-CL58 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10044 | PS4-62-IE-0001-CL59 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10045 | PS4-62-IE-0001-CL60 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10046 | PS4-62-IE-0002-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10047 | PS4-62-IE-0002-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10048 | PS4-62-IE-0002-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10049 | PS4-62-IE-0002-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10050 | PS4-62-IE-0002-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10051 | PS4-62-IE-0002-CL51 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10052 | PS4-62-IE-0002-CL52 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10053 | PS4-62-IE-0002-CL53 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10054 | PS4-62-IE-0002-CL54 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10055 | PS4-62-IE-0002-CL55 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10056 | PS4-62-IE-0002-CL56 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10057 | PS4-62-IE-0002-CL57 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10058 | PS4-62-IE-0002-CL58 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10059 | PS4-62-IE-0002-CL59 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-10527 | PS4-06-GB-0003-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-GB-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-30 14:49 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-10528 | PS4-60-IN-0002A-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-07-17 19:38 | PS4-60-57 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-10529 | PS4-60-IN-0002B-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-07-17 19:40 | PS4-60-59 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-10530 | PS4-60-IN-0002C-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-10531 | PS4-60-IN-0002D-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-10532 | PS4-60-IN-0002E-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) |  | PS4-60-65 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-10533 | PS4-60-IN-0002F-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) |  | PS4-60-67 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-10534 | PS4-60-IN-0002G-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) |  | PS4-60-69 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-10621 | PS4-05-BE-0001-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-25 13:03 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00023 | sridhar, muthu
T-00023-10622 | PS4-06-IG-0004A-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-IG-0004A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-30 16:22 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-10623 | PS4-06-IG-0004B-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-GU-0003B TO PS4-06-IG-0004B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-30 16:29 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-10624 | PS4-25-DM-3100A-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-10625 | PS4-25-DM-3100A-CG02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-10626 | PS4-25-DM-3100B-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-10627 | PS4-25-DM-3100B-CG02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-10628 | PS4-25-DM-3100C-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-10629 | PS4-25-DM-3100C-CG02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-10630 | PS4-60-IH-0001A-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-07-23 07:40 | PS4-60-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-10631 | PS4-60-IH-0001B-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-07-17 18:46 | PS4-60-06 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-10632 | PS4-60-IH-0001C-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | 2026-07-23 08:24 | PS4-60-09 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-10633 | PS4-60-IH-0001D-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS4-60-12 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-10634 | PS4-60-IH-0001E-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001E | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | 2026-07-01 14:49 | PS4-60-15 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-10635 | PS4-60-IH-0001F-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001F | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS4-60-18 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-10636 | PS4-60-IH-0001G-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001G | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS4-60-21 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-10637 | PS4-60-IH-0002-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-02 04:50 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-10638 | PS4-60-IH-0002-CG02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-17 18:50 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-10639 | PS4-61-IH-0004-CG01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-10640 | PS4-61-IH-0004-CG02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-10641 | PS4-61-IH-0004-CG03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-10642 | PS4-61-IH-0004-CG04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-10653 | PS4-61-IK-0003-CG07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-10868 | PS4-60-BE-0007A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BE-0007A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A |  | PS4-60-56 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-10869 | PS4-60-BE-0007A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BE-0007A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A |  | PS4-60-56 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-10870 | PS4-60-BE-0007B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BE-0007B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B |  | PS4-60-58 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-10871 | PS4-60-BE-0007B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BE-0007B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B |  | PS4-60-58 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-10872 | PS4-60-BE-0007C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BE-0007C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C |  | PS4-60-60 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-10873 | PS4-60-BE-0007C-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BE-0007C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C |  | PS4-60-60 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-10874 | PS4-60-BE-0007D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BE-0007D | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D |  | PS4-60-62 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-10875 | PS4-60-BE-0007D-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BE-0007D | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D |  | PS4-60-62 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-10876 | PS4-60-BE-0007E-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BE-0007E | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E |  | PS4-60-64 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-10877 | PS4-60-BE-0007E-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BE-0007E | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E |  | PS4-60-64 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-10878 | PS4-60-BE-0007F-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BE-0007F | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F |  | PS4-60-66 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-10879 | PS4-60-BE-0007F-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BE-0007F | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F |  | PS4-60-66 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-10880 | PS4-60-BE-0007G-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BE-0007G | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G |  | PS4-60-68 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-10881 | PS4-60-BE-0007G-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BE-0007G | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G |  | PS4-60-68 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-10882 | PS4-60-ISO-62800A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-ISO-62800A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS4-60-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-10883 | PS4-60-ISO-62800C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-ISO-62800C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS4-60-09 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-10884 | PS4-60-ISO-62800E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-ISO-62800E | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS4-60-15 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-10885 | PS4-60-ISO-62800G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-ISO-62800G | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS4-60-21 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-10968 | PS4-05-BE-0001-CL12 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0020 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-10969 | PS4-08-52BT-0131-CS01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-08-15CB-1001 TO PS4-08-52BT-0131 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00023
T-00023-10970 | PS4-08-85CP-1201-CS01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-08-11CB-1201 TO PS4-08-85CP-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00023
T-00023-10971 | PS4-08-85CP-1202-CS01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-08-11CB-1201 TO PS4-08-85CP-1202 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00023
T-00023-10972 | PS4-08-85CP-1601-CS01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-08-11CB-1601 TO PS4-08-85CP-1601 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00023
T-00023-10973 | PS4-09-DM-84500A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-DM-84500A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-10974 | PS4-09-DM-84500B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-DM-84500B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-11222 | PS4-71-BE-0001A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11223 | PS4-71-BE-0001A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11224 | PS4-71-BE-0001A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11225 | PS4-71-BE-0001A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11226 | PS4-71-BE-0001A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11227 | PS4-71-BE-0001A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11228 | PS4-71-BE-0001A-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11229 | PS4-71-BE-0001A-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11230 | PS4-71-BE-0001A-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11231 | PS4-71-BE-0001A-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11232 | PS4-71-BE-0001A-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11233 | PS4-71-BE-0001A-CL12 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11234 | PS4-71-BE-0001B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11235 | PS4-71-BE-0001B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11236 | PS4-71-BE-0001B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11237 | PS4-71-BE-0001B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11238 | PS4-71-BE-0001B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11239 | PS4-71-BE-0001B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11240 | PS4-71-BE-0001B-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11241 | PS4-71-BE-0001B-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11242 | PS4-71-BE-0001B-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11243 | PS4-71-BE-0001B-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11244 | PS4-71-BE-0001B-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11245 | PS4-71-BE-0001B-CL12 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-11246 | PS4-71-BE-0005-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0001 TO PS4-71-BE-0005 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00023
T-00023-11247 | PS4-71-BE-0005-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0001 TO PS4-71-BE-0005 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00023
T-00023-11248 | PS4-71-BE-0005-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0001 TO PS4-71-BE-0005 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00023
T-00023-11249 | PS4-71-BE-0005-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0001 TO PS4-71-BE-0005 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00023
T-00023-5645 | PS4-01-BE-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-01-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-01-08 - PS4 Deluge Valve Skid (PS4-01-UK-6100) |  | PS4-01-08 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00023
T-00023-5646 | PS4-01-FCV-0003A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-01-FCV-0003A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-5647 | PS4-01-FCV-0003B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-01-FCV-0003B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-5648 | PS4-01-FCV-0004A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-01-FCV-0004A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-5649 | PS4-01-FCV-0004B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-01-FCV-0004B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-5660 | PS4-01-IG-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-01-IG-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-5661 | PS4-01-LB-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-01-LB-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling | 2026-07-17 07:05 | PS4-01-11 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00023 | sridhar, muthu
T-00023-5662 | PS4-01-LB-0004-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-01-LB-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling | 2026-07-17 07:04 | PS4-01-11 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00023 | sridhar, muthu
T-00023-5663 | PS4-01-LB-0004-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0010 TO PS4-01-LB-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-5664 | PS4-01-MOV-8701-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-01-MOV-8701 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-01-05 - Foam Skid |  | PS4-01-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00023
T-00023-5674 | PS4-03-SEA-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0005 TO PS4-03-SEA-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-03-22 - FZ-G1 Guard House |  | PS4-03-22 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone I | TM-00023
T-00023-5675 | PS4-03-SEA-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-03-SEA-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-5677 | PS4-05-BE-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-25 13:06 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00023 | sridhar, muthu
T-00023-5678 | PS4-05-BE-0001-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-25 13:08 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00023 | sridhar, muthu
T-00023-5679 | PS4-05-BE-0001-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-25 13:10 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00023 | sridhar, muthu
T-00023-5680 | PS4-05-BE-0001-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-25 13:12 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00023 | sridhar, muthu
T-00023-5681 | PS4-05-BE-0001-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-25 13:14 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00023 | sridhar, muthu
T-00023-5682 | PS4-05-BE-0001-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-25 13:16 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00023 | sridhar, muthu
T-00023-5683 | PS4-05-BE-0001-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-25 13:19 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00023 | sridhar, muthu
T-00023-5684 | PS4-05-BE-0001-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-25 13:21 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00023 | sridhar, muthu
T-00023-5685 | PS4-05-BE-0001-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-25 13:23 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00023 | sridhar, muthu
T-00023-5686 | PS4-05-BE-0001-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-25 13:25 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00023 | sridhar, muthu
T-00023-5687 | PS4-05-BE-0001-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-25 13:27 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00023 | sridhar, muthu
T-00023-5688 | PS4-05-IE-8100-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) |  | PS4-05-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-5689 | PS4-05-IE-8100-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) |  | PS4-05-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-5690 | PS4-05-IG-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IG-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone I | TM-00023
T-00023-5693 | PS4-05-IG-0009-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IG-0009 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-5694 | PS4-05-IG-0009-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-05-IG-0009 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-5695 | PS4-05-IG-0014-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IG-0014 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-62-06 - CRO Generator Building Emergency Lighting DB - PS4-05-IG-0014 |  | PS4-62-06 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-5696 | PS4-05-IG-0020-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IG-0020 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-62-07 - CRO Generator Electrical Building Emergency L&SP DB - PS4-05-IG-0020 |  | PS4-62-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-5697 | PS4-06-GB-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-GB-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-30 14:56 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5698 | PS4-06-GB-0003-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-GB-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-30 16:14 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5699 | PS4-06-GB-0003-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-GB-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-30 16:15 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5700 | PS4-06-GB-0003-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-GB-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-30 16:17 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5701 | PS4-06-GB-0003-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-GB-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-30 16:18 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5702 | PS4-06-GB-0003-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-GB-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-30 16:19 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5703 | PS4-06-GU-0003A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-06-GU-0003A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building |  | PS4-06-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-5704 | PS4-06-GU-0003B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-06-GU-0003B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building |  | PS4-06-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-5705 | PS4-06-GU-0003C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-06-GU-0003C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building |  | PS4-06-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-5707 | PS4-06-IG-0004A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-IG-0004A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-30 16:24 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5708 | PS4-06-IG-0004A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-IG-0004A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-30 16:26 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5709 | PS4-06-IG-0004A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-IG-0004A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-30 16:27 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5710 | PS4-06-IG-0004A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-IG-0004A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-30 16:28 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5712 | PS4-06-IG-0004B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-GU-0003B TO PS4-06-IG-0004B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-30 16:31 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5713 | PS4-06-IG-0004B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-GU-0003B TO PS4-06-IG-0004B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-30 16:33 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5714 | PS4-06-IG-0004B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-GU-0003B TO PS4-06-IG-0004B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-30 16:37 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5715 | PS4-06-IG-0004B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-GU-0003B TO PS4-06-IG-0004B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-30 16:38 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5760 | PS4-08-11CB-1501-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0005 TO PS4-08-11CB-1501 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SSF1-171120 | PS4 - TZA - PS4 - Tanzania | PS4-08-11 - Corporate LAN (SIE) |  | PS4-08-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-5761 | PS4-08-11CB-1901-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-08-11CB-1901 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SSF1-171120 | PS4 - TZA - PS4 - Tanzania | PS4-08-11 - Corporate LAN (SIE) |  | PS4-08-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-5829 | PS4-09-LB-0008-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-09-LB-0008 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-5830 | PS4-09-LB-0008-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-09-LB-0008 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-5833 | PS4-25-DM-3100A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5834 | PS4-25-DM-3100A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0014 TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5837 | PS4-25-DM-3100B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5838 | PS4-25-DM-3100B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0014 TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5841 | PS4-25-DM-3100C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5842 | PS4-25-DM-3100C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0014 TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5855 | PS4-25-ESDV-0021-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-ESDV-0021 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5856 | PS4-25-ESDV-0023-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-ESDV-0023 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5857 | PS4-25-FCV-0003A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-FCV-0003A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5858 | PS4-25-FCV-0003B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-FCV-0003B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5859 | PS4-25-FCV-0003C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-FCV-0003C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5860 | PS4-25-FCV-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-FCV-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5869 | PS4-25-MOV-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-MOV-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5870 | PS4-25-MOV-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-MOV-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5871 | PS4-25-MOV-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-MOV-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5872 | PS4-25-MOV-0008-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-MOV-0008 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5873 | PS4-25-MOV-0011-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-MOV-0011 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5874 | PS4-25-MOV-0012-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-MOV-0012 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5875 | PS4-25-MOV-0025-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-MOV-0025 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5876 | PS4-25-MOV-0026-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-MOV-0026 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5877 | PS4-25-MOV-0027-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-MOV-0027 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5878 | PS4-25-MOV-0028-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-MOV-0028 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5879 | PS4-25-SDV-0022-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-SDV-0022 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5880 | PS4-25-SDV-0035A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-SDV-0035A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5881 | PS4-25-SDV-0035B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-SDV-0035B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5882 | PS4-25-SDV-0035C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-SDV-0035C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5883 | PS4-25-SDV-0036A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-SDV-0036A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5884 | PS4-25-SDV-0036B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-SDV-0036B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5885 | PS4-25-SDV-0036C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-SDV-0036C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5886 | PS4-25-SDV-0046-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-SDV-0046 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5887 | PS4-25-SDV-0052-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-SDV-0052 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5888 | PS4-25-SDV-0054A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-SDV-0054A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5889 | PS4-25-SDV-0054B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-SDV-0054B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5890 | PS4-25-SDV-0054C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-SDV-0054C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5892 | PS4-25-XV-0053-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-XV-0053 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5893 | PS4-25-XV-0070-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-XV-0070 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5895 | PS4-28-BE-0002A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-28-BE-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump | 2026-07-23 05:39 | PS4-28-17 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-5897 | PS4-28-BE-0002B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-28-BE-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump | 2026-07-23 05:42 | PS4-28-17 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-5913 | PS4-28-HE-2100-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-28-HE-2100 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-5915 | PS4-28-HE-2200-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-28-HE-2200 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-5917 | PS4-28-LB-8200-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-28-LB-8200 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-28-11 - Open Drain Interceptor |  | PS4-28-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone I | TM-00023
T-00023-5918 | PS4-28-SDV-0045-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-28-SDV-0045 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5919 | PS4-28-SDV-0053A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-28-SDV-0053A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5920 | PS4-28-SDV-0053B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-28-SDV-0053B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5921 | PS4-28-SDV-0053C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-28-SDV-0053C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-5929 | PS4-60-BE-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-60-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-27 - Compressed Air Starting Skid | 2026-07-08 03:48 | PS4-60-27 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5930 | PS4-60-BE-0001-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-60-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-27 - Compressed Air Starting Skid | 2026-07-08 03:50 | PS4-60-27 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5932 | PS4-60-BE-0001-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-BE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-27 - Compressed Air Starting Skid | 2026-07-08 03:51 | PS4-60-27 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5933 | PS4-60-BE-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-60-BE-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-26 - Instrument Air Compressor Skid | 2026-07-08 03:53 | PS4-60-26 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5934 | PS4-60-BE-0002-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-60-BE-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-26 - Instrument Air Compressor Skid | 2026-07-08 03:54 | PS4-60-26 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5935 | PS4-60-BE-0002-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-60-BE-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-26 - Instrument Air Compressor Skid | 2026-07-08 03:57 | PS4-60-26 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5937 | PS4-60-BE-0002-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-BE-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-26 - Instrument Air Compressor Skid | 2026-07-08 03:59 | PS4-60-26 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5938 | PS4-60-BE-0003A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0003A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-01 14:44 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5939 | PS4-60-BE-0003B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-17 07:03 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5940 | PS4-60-BE-0003C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0003C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-5941 | PS4-60-BE-0003D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0003D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-5942 | PS4-60-BE-0003E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0003E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-5943 | PS4-60-BE-0003F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0003F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-5944 | PS4-60-BE-0003G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0003G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-5945 | PS4-60-BE-0004A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0004A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-49 - Lube Oil Separator Module PS4-60-UO-81100A | 2026-06-25 13:51 | PS4-60-49 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5946 | PS4-60-BE-0004B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0004B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-50 - Lube Oil Separator Module PS4-60-UO-81100B | 2026-06-25 13:55 | PS4-60-50 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5947 | PS4-60-BE-0004C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0004C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-51 - Lube Oil Separator Module PS4-60-UO-81100C | 2026-07-23 05:44 | PS4-60-51 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-5948 | PS4-60-BE-0004D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0004D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-52 - Lube Oil Separator Module PS4-60-UO-81100D |  | PS4-60-52 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-5949 | PS4-60-BE-0004E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0004E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-53 - Lube Oil Separator Module PS4-60-UO-81100E |  | PS4-60-53 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-5950 | PS4-60-BE-0004F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0004F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-54 - Lube Oil Separator Module PS4-60-UO-81100F |  | PS4-60-54 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-5951 | PS4-60-BE-0004G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0004G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-55 - Lube Oil Separator Module PS4-60-UO-81100G |  | PS4-60-55 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-5952 | PS4-60-BE-0005A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0005A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-01 14:45 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5953 | PS4-60-BE-0005B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0005B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-17 07:02 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5954 | PS4-60-BE-0005C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0005C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-5955 | PS4-60-BE-0005D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0005D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-5956 | PS4-60-BE-0005E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0005E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-5957 | PS4-60-BE-0005F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0005F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-5958 | PS4-60-BE-0005G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0005G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-5959 | PS4-60-BE-0011A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-17 07:01 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5960 | PS4-60-BE-0011A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-17 07:00 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5961 | PS4-60-BE-0011A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-17 06:59 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5962 | PS4-60-BE-0011A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-17 07:08 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5963 | PS4-60-BE-0011A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-17 07:11 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5964 | PS4-60-BE-0011A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-17 07:14 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5965 | PS4-60-BE-0011B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-17 07:16 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5966 | PS4-60-BE-0011B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-17 07:26 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5967 | PS4-60-BE-0011B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-17 07:30 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5968 | PS4-60-BE-0011B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-17 07:33 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5969 | PS4-60-BE-0011B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-17 07:35 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5970 | PS4-60-BE-0011B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-17 07:39 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5971 | PS4-60-BE-0012A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-17 07:45 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5972 | PS4-60-BE-0012A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-17 07:49 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5973 | PS4-60-BE-0012A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-17 07:53 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5974 | PS4-60-BE-0012A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-17 07:55 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5975 | PS4-60-BE-0012A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-17 07:58 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5976 | PS4-60-BE-0012A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-17 08:01 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5977 | PS4-60-BE-0012B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-17 08:05 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5978 | PS4-60-BE-0012B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-17 08:09 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5979 | PS4-60-BE-0012B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-17 08:12 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5980 | PS4-60-BE-0012B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-17 08:14 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5981 | PS4-60-BE-0012B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-17 08:20 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5982 | PS4-60-BE-0012B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-17 14:36 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-5983 | PS4-60-BE-0013A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-25 13:30 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-5984 | PS4-60-BE-0013A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-25 13:33 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-5985 | PS4-60-BE-0013A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-25 13:35 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-5986 | PS4-60-BE-0013A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-25 13:38 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-5987 | PS4-60-BE-0013A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-25 13:41 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-5988 | PS4-60-BE-0013A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-25 13:42 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-5989 | PS4-60-BE-0013B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-25 13:44 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-5990 | PS4-60-BE-0013B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-25 13:47 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-5991 | PS4-60-BE-0013B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-25 13:48 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-5992 | PS4-60-BE-0013B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-25 13:51 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-5993 | PS4-60-BE-0013B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-25 13:53 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-5994 | PS4-60-BE-0013B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-25 13:54 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-5995 | PS4-60-BE-0014A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-5996 | PS4-60-BE-0014A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-5997 | PS4-60-BE-0014A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-5998 | PS4-60-BE-0014A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-5999 | PS4-60-BE-0014A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6000 | PS4-60-BE-0014A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6001 | PS4-60-BE-0014B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6002 | PS4-60-BE-0014B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6003 | PS4-60-BE-0014B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6004 | PS4-60-BE-0014B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6005 | PS4-60-BE-0014B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6006 | PS4-60-BE-0014B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6007 | PS4-60-BE-0015A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-27 11:41 | PS4-60-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6008 | PS4-60-BE-0015A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6009 | PS4-60-BE-0015A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6010 | PS4-60-BE-0015A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6011 | PS4-60-BE-0015A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6012 | PS4-60-BE-0015A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6013 | PS4-60-BE-0015B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6014 | PS4-60-BE-0015B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6015 | PS4-60-BE-0015B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6016 | PS4-60-BE-0015B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6017 | PS4-60-BE-0015B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6018 | PS4-60-BE-0015B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6019 | PS4-60-BE-0016A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6020 | PS4-60-BE-0016A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6021 | PS4-60-BE-0016A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6022 | PS4-60-BE-0016A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6023 | PS4-60-BE-0016A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6024 | PS4-60-BE-0016A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6025 | PS4-60-BE-0016B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6026 | PS4-60-BE-0016B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6027 | PS4-60-BE-0016B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6028 | PS4-60-BE-0016B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6029 | PS4-60-BE-0016B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6030 | PS4-60-BE-0016B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6031 | PS4-60-BE-0017A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6032 | PS4-60-BE-0017A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6033 | PS4-60-BE-0017A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6034 | PS4-60-BE-0017A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6035 | PS4-60-BE-0017A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6036 | PS4-60-BE-0017A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6037 | PS4-60-BE-0017B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6038 | PS4-60-BE-0017B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6039 | PS4-60-BE-0017B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6040 | PS4-60-BE-0017B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6041 | PS4-60-BE-0017B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6042 | PS4-60-BE-0017B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6043 | PS4-60-BE-0021A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-60-BE-0021B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-23 05:47 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6044 | PS4-60-BE-0021B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-60-BE-0021B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6045 | PS4-60-BE-0024A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0024A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-35 - Injector Tip Cooling Module A | 2026-06-24 08:08 | PS4-60-35 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6046 | PS4-60-BE-0024A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0024A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-35 - Injector Tip Cooling Module A | 2026-06-24 08:10 | PS4-60-35 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6047 | PS4-60-BE-0024B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0024B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-36 - Injector Tip Cooling Module B | 2026-06-24 08:15 | PS4-60-36 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6048 | PS4-60-BE-0024B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0024B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-36 - Injector Tip Cooling Module B | 2026-06-24 08:17 | PS4-60-36 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6049 | PS4-60-BE-0024C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0024C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-37 - Injector Tip Cooling Module C | 2026-07-23 05:49 | PS4-60-37 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6050 | PS4-60-BE-0024C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0024C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-37 - Injector Tip Cooling Module C | 2026-07-23 05:52 | PS4-60-37 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6051 | PS4-60-BE-0024D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0024D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-38 - Injector Tip Cooling Module D |  | PS4-60-38 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6052 | PS4-60-BE-0024D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0024D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-38 - Injector Tip Cooling Module D |  | PS4-60-38 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6053 | PS4-60-BE-0024E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0024E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-39 - Injector Tip Cooling Module E |  | PS4-60-39 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6054 | PS4-60-BE-0024E-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0024E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-39 - Injector Tip Cooling Module E |  | PS4-60-39 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6055 | PS4-60-BE-0024F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0024F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-40 - Injector Tip Cooling Module F |  | PS4-60-40 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6056 | PS4-60-BE-0024F-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0024F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-40 - Injector Tip Cooling Module F |  | PS4-60-40 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6057 | PS4-60-BE-0024G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0024G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-41 - Injector Tip Cooling Module G |  | PS4-60-41 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6058 | PS4-60-BE-0024G-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0024G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-41 - Injector Tip Cooling Module G |  | PS4-60-41 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6059 | PS4-60-BE-0025A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0025A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-35 - Injector Tip Cooling Module A | 2026-06-24 08:12 | PS4-60-35 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6060 | PS4-60-BE-0025B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0025B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-36 - Injector Tip Cooling Module B | 2026-06-24 08:18 | PS4-60-36 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6061 | PS4-60-BE-0025C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0025C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-37 - Injector Tip Cooling Module C |  | PS4-60-37 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6062 | PS4-60-BE-0025D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0025D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-38 - Injector Tip Cooling Module D |  | PS4-60-38 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6063 | PS4-60-BE-0025E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0025E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-39 - Injector Tip Cooling Module E |  | PS4-60-39 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6064 | PS4-60-BE-0025F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0025F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-40 - Injector Tip Cooling Module F |  | PS4-60-40 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6065 | PS4-60-BE-0025G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0025G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-41 - Injector Tip Cooling Module G |  | PS4-60-41 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6066 | PS4-60-BE-0026A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0026A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-06-24 08:20 | PS4-60-70 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6067 | PS4-60-BE-0026A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0026A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-06-24 08:22 | PS4-60-70 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6068 | PS4-60-BE-0026B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0026B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-06-24 08:24 | PS4-60-71 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6069 | PS4-60-BE-0026B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0026B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-06-24 08:25 | PS4-60-71 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6070 | PS4-60-BE-0026C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0026C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system |  | PS4-60-72 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6071 | PS4-60-BE-0026C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0026C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system |  | PS4-60-72 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6072 | PS4-60-BE-0026D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0026D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system |  | PS4-60-73 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6073 | PS4-60-BE-0026D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0026D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system |  | PS4-60-73 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6074 | PS4-60-BE-0026E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0026E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6075 | PS4-60-BE-0026E-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0026E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6076 | PS4-60-BE-0026F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0026F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6077 | PS4-60-BE-0026F-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0026F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6078 | PS4-60-BE-0026G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0026G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6079 | PS4-60-BE-0026G-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0026G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6080 | PS4-60-BI-0005A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BI-0005A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-01 14:46 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6081 | PS4-60-BI-0005B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BI-0005B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-23 05:54 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6082 | PS4-60-BI-0005C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BI-0005C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6083 | PS4-60-BI-0005D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BI-0005D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6084 | PS4-60-BI-0005E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BI-0005E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6085 | PS4-60-BI-0005F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BI-0005F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6086 | PS4-60-BI-0005G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BI-0005G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6087 | PS4-60-BI-0015A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BI-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-01 14:47 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6088 | PS4-60-BI-0015A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BI-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-01 14:47 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6089 | PS4-60-BI-0015A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BI-0015A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-01 14:48 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6090 | PS4-60-BI-0015B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BI-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-23 05:56 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6091 | PS4-60-BI-0015B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BI-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-23 06:00 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6092 | PS4-60-BI-0015B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BI-0015B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-23 06:04 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6093 | PS4-60-BI-0015C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BI-0015C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6094 | PS4-60-BI-0015C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BI-0015C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6095 | PS4-60-BI-0015C-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BI-0015C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6096 | PS4-60-BI-0015D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BI-0015D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6097 | PS4-60-BI-0015D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BI-0015D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6098 | PS4-60-BI-0015D-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BI-0015D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6099 | PS4-60-BI-0015E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BI-0015E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6100 | PS4-60-BI-0015E-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BI-0015E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6101 | PS4-60-BI-0015E-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BI-0015E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6102 | PS4-60-BI-0015F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BI-0015F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6103 | PS4-60-BI-0015F-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BI-0015F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6104 | PS4-60-BI-0015F-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BI-0015F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6105 | PS4-60-BI-0015G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BI-0015G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6106 | PS4-60-BI-0015G-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BI-0015G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6107 | PS4-60-BI-0015G-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BI-0015G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6117 | PS4-60-IE-0002A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-17 18:26 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6118 | PS4-60-IE-0002A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-17 18:29 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6119 | PS4-60-IE-0002A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015A TO PS4-60-IE-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-23 06:16 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6120 | PS4-60-IE-0002B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-17 18:33 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6121 | PS4-60-IE-0002B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-17 18:36 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6122 | PS4-60-IE-0002B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015B TO PS4-60-IE-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-23 06:33 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6123 | PS4-60-IE-0002C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6124 | PS4-60-IE-0002C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6125 | PS4-60-IE-0002C-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015C TO PS4-60-IE-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6126 | PS4-60-IE-0002D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0002D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6127 | PS4-60-IE-0002D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0002D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6128 | PS4-60-IE-0002D-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015D TO PS4-60-IE-0002D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6129 | PS4-60-IE-0002E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0002E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6130 | PS4-60-IE-0002E-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0002E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6131 | PS4-60-IE-0002E-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015E TO PS4-60-IE-0002E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6132 | PS4-60-IE-0002F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0002F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6133 | PS4-60-IE-0002F-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0002F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6134 | PS4-60-IE-0002F-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015F TO PS4-60-IE-0002F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6135 | PS4-60-IE-0002G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0002G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6136 | PS4-60-IE-0002G-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0002G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6137 | PS4-60-IE-0002G-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015G TO PS4-60-IE-0002G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6138 | PS4-60-IE-0003A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-23 07:06 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6139 | PS4-60-IE-0003A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-23 07:09 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6140 | PS4-60-IE-0003B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-23 07:33 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6141 | PS4-60-IE-0003B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-23 07:37 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6142 | PS4-60-IE-0003C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6143 | PS4-60-IE-0003C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6144 | PS4-60-IE-0003D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6145 | PS4-60-IE-0003D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6146 | PS4-60-IE-0003E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6147 | PS4-60-IE-0003E-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6148 | PS4-60-IE-0003F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6149 | PS4-60-IE-0003F-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6150 | PS4-60-IE-0003G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6151 | PS4-60-IE-0003G-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6152 | PS4-60-IE-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-17 18:39 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6153 | PS4-60-IE-0004-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-17 18:41 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6155 | PS4-60-IH-0001A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-07-23 07:44 | PS4-60-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6156 | PS4-60-IH-0001A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-07-23 07:47 | PS4-60-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6157 | PS4-60-IH-0001A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-07-23 07:49 | PS4-60-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6158 | PS4-60-IH-0001A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-07-23 07:52 | PS4-60-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6159 | PS4-60-IH-0001A-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-07-23 07:56 | PS4-60-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6160 | PS4-60-IH-0001A-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-07-23 07:59 | PS4-60-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6162 | PS4-60-IH-0001B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-07-23 08:02 | PS4-60-06 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6163 | PS4-60-IH-0001B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-07-23 08:06 | PS4-60-06 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6164 | PS4-60-IH-0001B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-07-23 08:10 | PS4-60-06 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6165 | PS4-60-IH-0001B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-07-23 08:14 | PS4-60-06 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6166 | PS4-60-IH-0001B-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-07-23 08:19 | PS4-60-06 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6167 | PS4-60-IH-0001B-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-07-23 08:21 | PS4-60-06 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6169 | PS4-60-IH-0001C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | 2026-07-23 08:27 | PS4-60-09 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6170 | PS4-60-IH-0001C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | 2026-07-23 08:30 | PS4-60-09 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6171 | PS4-60-IH-0001C-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | 2026-07-23 08:36 | PS4-60-09 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6172 | PS4-60-IH-0001C-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | 2026-07-23 08:40 | PS4-60-09 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6173 | PS4-60-IH-0001C-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS4-60-09 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6174 | PS4-60-IH-0001C-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS4-60-09 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6176 | PS4-60-IH-0001D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | 2026-07-27 11:43 | PS4-60-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6177 | PS4-60-IH-0001D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | 2026-07-27 11:45 | PS4-60-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6178 | PS4-60-IH-0001D-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | 2026-07-27 11:47 | PS4-60-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6179 | PS4-60-IH-0001D-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | 2026-07-27 11:49 | PS4-60-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6180 | PS4-60-IH-0001D-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS4-60-12 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6181 | PS4-60-IH-0001D-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS4-60-12 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6183 | PS4-60-IH-0001E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | 2026-07-01 14:50 | PS4-60-15 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6184 | PS4-60-IH-0001E-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | 2026-07-01 14:51 | PS4-60-15 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6185 | PS4-60-IH-0001E-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | 2026-07-02 04:47 | PS4-60-15 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6186 | PS4-60-IH-0001E-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | 2026-07-02 04:48 | PS4-60-15 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6187 | PS4-60-IH-0001E-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IH-0001E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS4-60-15 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6188 | PS4-60-IH-0001E-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IH-0001E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS4-60-15 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6190 | PS4-60-IH-0001F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS4-60-18 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6191 | PS4-60-IH-0001F-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS4-60-18 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6192 | PS4-60-IH-0001F-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | 2026-07-27 11:55 | PS4-60-18 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6193 | PS4-60-IH-0001F-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS4-60-18 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6194 | PS4-60-IH-0001F-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IH-0001F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS4-60-18 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6195 | PS4-60-IH-0001F-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IH-0001F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS4-60-18 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6197 | PS4-60-IH-0001G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS4-60-21 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6198 | PS4-60-IH-0001G-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS4-60-21 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6199 | PS4-60-IH-0001G-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS4-60-21 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6200 | PS4-60-IH-0001G-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS4-60-21 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6201 | PS4-60-IH-0001G-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IH-0001G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS4-60-21 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6202 | PS4-60-IH-0001G-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IH-0001G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS4-60-21 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6205 | PS4-60-IH-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-17 18:53 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6206 | PS4-60-IH-0002-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-17 18:56 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6207 | PS4-60-IH-0002-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-02 04:51 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6208 | PS4-60-IH-0002-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-02 04:51 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6209 | PS4-60-IH-0002-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-02 04:52 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6210 | PS4-60-IH-0002-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-02 04:53 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6211 | PS4-60-IH-0002-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-23 08:42 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6212 | PS4-60-IH-0002-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-23 10:49 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6213 | PS4-60-IH-0002-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-23 10:52 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6214 | PS4-60-IH-0002-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-23 10:55 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6215 | PS4-60-IN-0001A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-IN-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-49 - Lube Oil Separator Module PS4-60-UO-81100A | 2026-06-25 13:53 | PS4-60-49 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6216 | PS4-60-IN-0001B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-IN-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-50 - Lube Oil Separator Module PS4-60-UO-81100B | 2026-06-25 13:58 | PS4-60-50 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6217 | PS4-60-IN-0001C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-IN-0001C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-51 - Lube Oil Separator Module PS4-60-UO-81100C |  | PS4-60-51 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6218 | PS4-60-IN-0001D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-IN-0001D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-52 - Lube Oil Separator Module PS4-60-UO-81100D | 2026-07-23 10:58 | PS4-60-52 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6219 | PS4-60-IN-0001E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-IN-0001E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-53 - Lube Oil Separator Module PS4-60-UO-81100E |  | PS4-60-53 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6220 | PS4-60-IN-0001F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-IN-0001F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-54 - Lube Oil Separator Module PS4-60-UO-81100F |  | PS4-60-54 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6221 | PS4-60-IN-0001G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-IN-0001G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-55 - Lube Oil Separator Module PS4-60-UO-81100G |  | PS4-60-55 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6222 | PS4-60-IN-0002A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-07-17 18:58 | PS4-60-57 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6223 | PS4-60-IN-0002A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-07-17 19:01 | PS4-60-57 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6224 | PS4-60-IN-0002A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-07-17 19:03 | PS4-60-57 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6225 | PS4-60-IN-0002B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-07-17 19:05 | PS4-60-59 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6226 | PS4-60-IN-0002B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-07-17 19:07 | PS4-60-59 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6227 | PS4-60-IN-0002B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-07-17 19:10 | PS4-60-59 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6228 | PS4-60-IN-0002C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6229 | PS4-60-IN-0002C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6230 | PS4-60-IN-0002C-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6231 | PS4-60-IN-0002D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6232 | PS4-60-IN-0002D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6233 | PS4-60-IN-0002D-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6234 | PS4-60-IN-0002E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) |  | PS4-60-65 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6235 | PS4-60-IN-0002E-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) |  | PS4-60-65 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6236 | PS4-60-IN-0002E-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) |  | PS4-60-65 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6237 | PS4-60-IN-0002F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) |  | PS4-60-67 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6238 | PS4-60-IN-0002F-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) |  | PS4-60-67 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6239 | PS4-60-IN-0002F-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) |  | PS4-60-67 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6240 | PS4-60-IN-0002G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) |  | PS4-60-69 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6241 | PS4-60-IN-0002G-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) |  | PS4-60-69 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6242 | PS4-60-IN-0002G-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) |  | PS4-60-69 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6243 | PS4-60-IWK-0001A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IWK-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6244 | PS4-60-IWK-0001A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IWK-0001A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6245 | PS4-60-IWK-0001B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IWK-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6246 | PS4-60-IWK-0001B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IWK-0001B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6247 | PS4-60-LA-0002A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-17 19:13 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6248 | PS4-60-LA-0002A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-17 19:17 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6249 | PS4-60-LA-0002B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6250 | PS4-60-LA-0002B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6251 | PS4-60-LA-0002C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6252 | PS4-60-LA-0002C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6253 | PS4-60-LA-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-17 19:21 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6254 | PS4-60-LA-0003-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-17 19:25 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6255 | PS4-60-MOV-0005-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-60-MOV-0005 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-23 11:03 | PS4-71-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-6256 | PS4-60-MOV-0006-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-60-MOV-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-23 11:06 | PS4-71-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-6257 | PS4-60-MOV-0011-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-60-MOV-0011 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-23 11:16 | PS4-71-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-6258 | PS4-60-MOV-0012-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-60-MOV-0012 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-23 11:19 | PS4-71-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-6259 | PS4-60-SEA-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6260 | PS4-60-SEA-0001-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6261 | PS4-60-VS-9100A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-VS-9100A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-42 - Oil Mist Separator Skid PS4-60-VS-9100A | 2026-07-10 05:53 | PS4-60-42 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6262 | PS4-60-VS-9100B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-VS-9100B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-43 - Oil Mist Separator Skid PS4-60-VS-9100B | 2026-06-25 14:15 | PS4-60-43 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6263 | PS4-60-VS-9100C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-VS-9100C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-44 - Oil Mist Separator Skid PS4-60-VS-9100C |  | PS4-60-44 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6264 | PS4-60-VS-9100D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-VS-9100D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-45 - Oil Mist Separator Skid PS4-60-VS-9100D |  | PS4-60-45 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6265 | PS4-60-VS-9100E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-VS-9100E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-46 - Oil Mist Separator Skid PS4-60-VS-9100E |  | PS4-60-46 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6266 | PS4-60-VS-9100F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-VS-9100F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-47 - Oil Mist Separator Skid PS4-60-VS-9100F |  | PS4-60-47 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6267 | PS4-60-VS-9100G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-VS-9100G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-48 - Oil Mist Separator Skid PS4-60-VS-9100G |  | PS4-60-48 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6268 | PS4-61-BI-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-61-BI-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-23 11:22 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6269 | PS4-61-BI-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-61-BI-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-23 11:26 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6270 | PS4-61-BI-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-61-BI-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-23 11:28 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6271 | PS4-61-BI-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-61-BI-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-23 11:31 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6272 | PS4-61-BI-0005-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-61-BI-0005 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6273 | PS4-61-BI-0006-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-61-BI-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-27 12:00 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6274 | PS4-61-BI-0007-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-61-BI-0007 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6280 | PS4-61-IG-0010-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IG-0010 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-62-10 - CRO Generator Electrical Building Normal L&SP DB - PS4-61-IG-0010 |  | PS4-62-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6285 | PS4-61-IG-0030-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IG-0030 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6292 | PS4-61-IH-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6293 | PS4-61-IH-0004-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6294 | PS4-61-IH-0004-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6295 | PS4-61-IH-0004-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6296 | PS4-61-IH-0004-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6297 | PS4-61-IH-0004-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6298 | PS4-61-IH-0004-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6299 | PS4-61-IH-0004-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6300 | PS4-61-IH-0004-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6301 | PS4-61-IH-0004-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6302 | PS4-61-IH-0004-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6303 | PS4-61-IH-0004-CL12 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6304 | PS4-61-IH-0004-CL13 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6305 | PS4-61-IH-0004-CL14 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6306 | PS4-61-IH-0004-CL15 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6307 | PS4-61-IH-0004-CL16 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6308 | PS4-61-IH-0004-CL17 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6309 | PS4-61-IH-0004-CL18 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6310 | PS4-61-IH-0004-CL19 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6311 | PS4-61-IH-0004-CL20 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6312 | PS4-61-IH-0004-CL21 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6313 | PS4-61-IH-0004-CL22 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6373 | PS4-61-IK-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-07-30 16:40 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6374 | PS4-61-IK-0003-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-07-27 12:04 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6375 | PS4-61-IK-0003-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6376 | PS4-61-IK-0003-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0010 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6377 | PS4-61-IK-0003-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0010 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6378 | PS4-61-IK-0003-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0010 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6379 | PS4-61-IK-0003-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6380 | PS4-61-IK-0003-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6381 | PS4-61-IK-0003-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6382 | PS4-61-IK-0003-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6383 | PS4-61-IK-0003-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6384 | PS4-61-IK-0003-CL12 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6385 | PS4-61-IK-0003-CL13 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6386 | PS4-61-IK-0003-CL14 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6387 | PS4-61-IK-0003-CL15 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6388 | PS4-61-IK-0003-CL16 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6389 | PS4-61-IK-0003-CL17 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6390 | PS4-61-IK-0003-CL18 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6391 | PS4-61-IK-0003-CL19 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6392 | PS4-61-IK-0003-CL20 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6393 | PS4-61-IK-0003-CL21 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6394 | PS4-61-IK-0003-CL22 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6395 | PS4-61-IK-0003-CL23 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6396 | PS4-61-IK-0003-CL24 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6397 | PS4-61-IK-0003-CL25 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6398 | PS4-61-IK-0003-CL26 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6399 | PS4-61-IK-0003-CL27 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6400 | PS4-61-IK-0003-CL28 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6401 | PS4-61-IK-0003-CL29 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6402 | PS4-61-IK-0003-CL30 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6403 | PS4-61-IK-0003-CL31 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6404 | PS4-61-IK-0003-CL32 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6405 | PS4-61-IK-0003-CL33 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6406 | PS4-61-IK-0003-CL34 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6407 | PS4-61-IK-0003-CL35 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6408 | PS4-61-IK-0003-CL36 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6409 | PS4-61-IK-0003-CL37 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6410 | PS4-61-IK-0003-CL38 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6411 | PS4-61-IK-0003-CL39 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6412 | PS4-61-IK-0003-CL40 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6413 | PS4-61-IK-0003-CL41 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6414 | PS4-61-IK-0003-CL42 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6415 | PS4-61-IK-0003-CL43 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-6416 | PS4-61-IK-0003-CL44 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-6417 | PS4-61-IK-0003-CL45 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-6418 | PS4-61-IK-0003-CL46 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-6419 | PS4-61-IK-0003-CL48 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-6420 | PS4-61-IK-0003-CL49 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-6421 | PS4-61-IK-0003-CL50 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-6422 | PS4-61-IK-0003-CL51 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-6423 | PS4-61-IK-0003-CL52 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-6424 | PS4-61-IK-0003-CL53 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-6425 | PS4-61-IK-0003-CL54 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-6426 | PS4-61-IK-0003-CL55 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-6427 | PS4-61-IK-0003-CL56 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-6428 | PS4-61-IK-0003-CL57 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-6429 | PS4-61-IK-0003-CL58 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-6430 | PS4-61-IK-0003-CL59 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-6431 | PS4-61-IK-0003-CL60 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-6432 | PS4-61-IK-0003-CL61 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-6433 | PS4-61-IK-0003-CL62 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-07-02 04:56 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6434 | PS4-61-IK-0003-CL63 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-07-02 04:57 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6439 | PS4-61-IK-0006-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6440 | PS4-61-IK-0006-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6441 | PS4-61-IK-0006-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6442 | PS4-61-IK-0006-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6443 | PS4-61-IK-0006-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6444 | PS4-61-IK-0006-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6445 | PS4-61-IK-0006-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6446 | PS4-61-IK-0006-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6447 | PS4-61-IK-0006-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6448 | PS4-61-IK-0006-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6449 | PS4-61-IK-0006-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6450 | PS4-61-IK-0006-CL12 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6451 | PS4-61-IK-0006-CL13 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6452 | PS4-61-IK-0006-CL14 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6453 | PS4-61-IK-0006-CL15 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6454 | PS4-61-IK-0006-CL16 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6455 | PS4-61-IK-0006-CL17 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6456 | PS4-61-IK-0006-CL18 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6457 | PS4-61-IK-0006-CL19 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6458 | PS4-61-IK-0006-CL20 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6459 | PS4-61-IK-0006-CL21 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6460 | PS4-61-IK-0006-CL22 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6461 | PS4-61-IK-0006-CL23 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6462 | PS4-61-IK-0006-CL24 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6463 | PS4-61-IK-0006-CL25 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6464 | PS4-61-IK-0006-CL26 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6465 | PS4-61-IK-0006-CL27 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6466 | PS4-61-IK-0006-CL28 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6467 | PS4-61-IK-0006-CL29 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6468 | PS4-61-IK-0006-CL30 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6469 | PS4-61-IK-0006-CL31 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0010 TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6470 | PS4-61-IK-0006-CL32 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0010 TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6471 | PS4-61-IK-0006-CL33 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-07-02 04:58 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6472 | PS4-61-IK-0006-CL34 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-07-02 04:59 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00023 | sridhar, muthu
T-00023-6476 | PS4-61-IU-3100A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-61-IU-3100A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-02 05:00 | PS4-25-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-6477 | PS4-61-IU-3100B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-61-IU-3100B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-02 05:00 | PS4-25-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-6478 | PS4-61-IU-3100C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-61-IU-3100C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-02 05:02 | PS4-25-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-6481 | PS4-61-IV-0002A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0010 TO PS4-61-IV-0002A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6482 | PS4-61-IV-0002B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0010 TO PS4-61-IV-0002B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6486 | PS4-61-IV-0007A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0010 TO PS4-61-IV-0007A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6487 | PS4-61-IV-0007B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0010 TO PS4-61-IV-0007B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-6489 | PS4-62-IE-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 | 2026-07-02 05:03 | PS4-62-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone G | TM-00023 | sridhar, muthu
T-00023-6490 | PS4-62-IE-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 | 2026-07-02 05:04 | PS4-62-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone G | TM-00023 | sridhar, muthu
T-00023-6504 | PS4-71-FCV-0018-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-71-FCV-0018 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-6505 | PS4-71-FCV-0019-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-71-FCV-0019 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6506 | PS4-71-FCV-0020-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-71-FCV-0020 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-6510 | PS4-71-HE-2200-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-71-HE-2200 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-6512 | PS4-71-HE-2300-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-71-HE-2300 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-6521 | PS4-71-IN-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00023
T-00023-6522 | PS4-71-IN-0001-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00023
T-00023-6523 | PS4-71-IN-0001-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00023
T-00023-6524 | PS4-71-IN-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-71-IN-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-09 - CFO Pre-Pressure Module (UCP) | 2026-07-17 19:28 | PS4-71-09 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-6525 | PS4-71-IN-0002-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-71-IN-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-09 - CFO Pre-Pressure Module (UCP) | 2026-07-17 19:30 | PS4-71-09 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-6526 | PS4-71-IN-0002-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-71-IN-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-09 - CFO Pre-Pressure Module (UCP) | 2026-07-17 19:32 | PS4-71-09 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-6527 | PS4-71-IN-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-71-IN-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-07-17 19:35 | PS4-71-23 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6528 | PS4-71-IN-0003-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-71-IN-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-07-17 19:37 | PS4-71-23 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6529 | PS4-71-IN-0003-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-71-IN-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-07-23 12:06 | PS4-71-23 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6530 | PS4-71-IN-0004A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-6531 | PS4-71-IN-0004A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-6532 | PS4-71-IN-0004A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-6533 | PS4-71-IN-0004B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-6534 | PS4-71-IN-0004B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-6535 | PS4-71-IN-0004B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-6536 | PS4-71-LCV-4101-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-71-LCV-4101 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-6537 | PS4-71-MOV-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-MOV-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-23 12:08 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-6538 | PS4-71-MOV-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-MOV-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-23 12:11 | PS4-71-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6539 | PS4-71-MOV-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-MOV-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-23 12:14 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-6540 | PS4-71-MOV-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-MOV-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-23 12:17 | PS4-71-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-6541 | PS4-71-MOV-0007-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-MOV-0007 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-07-23 12:19 | PS4-71-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-6542 | PS4-71-MOV-0008-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-MOV-0008 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-23 12:22 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-6543 | PS4-71-MOV-0009-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-MOV-0009 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-07-23 12:25 | PS4-71-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-6544 | PS4-71-MOV-0010-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-MOV-0010 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-23 12:27 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-6545 | PS4-71-SDV-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-71-SDV-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank |  | PS4-71-20 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6546 | PS4-71-SDV-0022-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-71-SDV-0022 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-6547 | PS4-71-SDV-0029-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-71-SDV-0029 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank |  | PS4-71-15 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00023
T-00023-6548 | PS4-71-SDV-0039-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-71-SDV-0039 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-6549 | PS4-71-UZ-6200-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0014 TO PS4-71-UZ-6200 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-14 - Diesel Fuel Transfer and Dispensing Station | 2026-07-23 12:31 | PS4-71-14 |  |  | LV Power Cable | E | Closed | PS4 - Milestone F | TM-00023 | sridhar, muthu
T-00023-6550 | PS4-71-XV-0089-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-71-XV-0089 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-6551 | PS4-71-XV-0090-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-XV-0090 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-6552 | PS4-71-XV-0091-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-XV-0091 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00023
T-00023-6553 | PS4-71-XV-0092-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-XV-0092 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank |  | PS4-71-20 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00023
T-00023-6555 | PS4-74-LB-5101-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-74-LB-5101 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-74-02 - N2 Generation Skid (UCP) |  | PS4-74-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00023
T-00023-6556 | PS4-74-LB-5101-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-74-LB-5101 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-74-02 - N2 Generation Skid (UCP) |  | PS4-74-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00023
T-00023-6563 | PS4-75-MOV-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-75-MOV-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-28-07 - Open Drains (OD2) |  | PS4-28-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-6564 | PS4-75-UI-6200-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0001A TO PS4-75-UI-6200 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-75-01 - DRA Injection Package |  | PS4-75-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-6565 | PS4-75-UI-6200-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0001B TO PS4-75-UI-6200 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-75-01 - DRA Injection Package |  | PS4-75-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00023
T-00023-6566 | PS4-78-JC-9100A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-78-JC-9100A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-78-01 - Lifting and handling equipment |  | PS4-78-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6567 | PS4-78-JC-9100B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-78-JC-9100B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-78-01 - Lifting and handling equipment |  | PS4-78-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6568 | PS4-78-JC-9100C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-78-JC-9100C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-78-01 - Lifting and handling equipment |  | PS4-78-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6569 | PS4-78-JC-9100D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-78-JC-9100D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-78-01 - Lifting and handling equipment |  | PS4-78-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-6583 | PS4-87-IRF-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-87-IRF-0001 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-53-01 - Utility Water / Storage Tank |  | PS4-53-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00023
T-00023-6584 | PS4-87-IRF-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-87-IRF-0002 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-6585 | PS4-87-IRF-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-87-IRF-0003 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-6586 | PS4-87-IRF-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-87-IRF-0004 | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank |  | PS4-71-15 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00023
T-00023-8764 | PS4-79-IG-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0001 TO PS4-79-IG-0001 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-8765 | PS4-79-IG-0002-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0002 TO PS4-79-IG-0002 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-8766 | PS4-79-IG-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0003 TO PS4-79-IG-0003 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-8767 | PS4-79-IG-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0004 TO PS4-79-IG-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-8768 | PS4-79-IG-0005-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0005 TO PS4-79-IG-0005 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-8769 | PS4-79-IG-0006-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0006 TO PS4-79-IG-0006 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-8770 | PS4-79-IG-0007-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0007 TO PS4-79-IG-0007 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-8771 | PS4-79-IG-0008-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0008 TO PS4-79-IG-0008 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-8772 | PS4-79-IG-0009-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0009 TO PS4-79-IG-0009 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-8773 | PS4-79-IG-0010-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0010 TO PS4-79-IG-0010 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-8774 | PS4-79-IG-0011-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0011 TO PS4-79-IG-0011 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-8775 | PS4-79-IG-0012-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0012 TO PS4-79-IG-0012 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-8985 | PS4-02-SWSI-0001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-02-SWSI-0001 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-02-01 - Miscellaneous Safety equipment |  | PS4-02-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-8986 | PS4-02-SWSI-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-02-SWSI-0003 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-02-01 - Miscellaneous Safety equipment |  | PS4-02-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00023
T-00023-8987 | PS4-06-GU-0005-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0007 TO PS4-06-GU-0005 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-06-04 - AC UPS - Guard House |  | PS4-06-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone I | TM-00023
T-00023-8992 | PS4-09-LB-7001-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-05-IG-0007 TO PS4-09-LB-7001 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-09-02 - HVAC for Guard House |  | PS4-09-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone I | TM-00023
T-00023-8995 | PS4-60-BE-0007A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BE-0007A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A | 2026-06-25 13:27 | PS4-60-56 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-8996 | PS4-60-BE-0007B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BE-0007B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B | 2026-06-25 13:41 | PS4-60-58 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-8997 | PS4-60-BE-0007C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BE-0007C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C |  | PS4-60-60 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-8998 | PS4-60-BE-0007D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BE-0007D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D |  | PS4-60-62 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-8999 | PS4-60-BE-0007E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BE-0007E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E |  | PS4-60-64 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9000 | PS4-60-BE-0007F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BE-0007F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F |  | PS4-60-66 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9001 | PS4-60-BE-0007G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BE-0007G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G |  | PS4-60-68 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-9002 | PS4-60-BE-0027A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BE-0027A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A | 2026-06-25 13:30 | PS4-60-56 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9003 | PS4-60-BE-0027B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BE-0027B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B | 2026-06-25 13:42 | PS4-60-58 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9004 | PS4-60-BE-0027C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BE-0027C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C |  | PS4-60-60 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9005 | PS4-60-BE-0027D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BE-0027D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D |  | PS4-60-62 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9006 | PS4-60-BE-0027E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BE-0027E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E |  | PS4-60-64 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9007 | PS4-60-BE-0027F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BE-0027F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F |  | PS4-60-66 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9008 | PS4-60-BE-0027G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BE-0027G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G |  | PS4-60-68 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-9009 | PS4-60-BE-0028A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BE-0028A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A | 2026-06-25 13:33 | PS4-60-56 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9010 | PS4-60-BE-0028B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BE-0028B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B | 2026-06-25 13:45 | PS4-60-58 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9011 | PS4-60-BE-0028C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BE-0028C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C |  | PS4-60-60 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9012 | PS4-60-BE-0028D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BE-0028D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D |  | PS4-60-62 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9013 | PS4-60-BE-0028E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BE-0028E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E |  | PS4-60-64 |  |  | LV Power Cable | E | Started (not Completed) | PS4 - Milestone D | TM-00023
T-00023-9014 | PS4-60-BE-0028F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BE-0028F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F |  | PS4-60-66 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9015 | PS4-60-BE-0028G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BE-0028G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G |  | PS4-60-68 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-9016 | PS4-60-BI-0006A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-17 14:38 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9017 | PS4-60-BI-0006A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-17 14:40 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9018 | PS4-60-BI-0006A-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-17 14:42 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9019 | PS4-60-BI-0006A-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-17 14:44 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9020 | PS4-60-BI-0006A-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-17 14:46 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9021 | PS4-60-BI-0006A-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-17 14:48 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9022 | PS4-60-BI-0006A-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-17 14:51 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9023 | PS4-60-BI-0006A-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-17 14:53 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9024 | PS4-60-BI-0006A-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-17 14:56 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9025 | PS4-60-BI-0006A-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-17 14:57 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9026 | PS4-60-BI-0006A-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-17 17:48 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9027 | PS4-60-BI-0006B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-17 17:51 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9028 | PS4-60-BI-0006B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-17 17:53 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9029 | PS4-60-BI-0006B-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-17 17:58 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9030 | PS4-60-BI-0006B-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-17 18:01 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9031 | PS4-60-BI-0006B-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-17 18:03 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9032 | PS4-60-BI-0006B-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-17 18:07 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9033 | PS4-60-BI-0006B-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-17 18:11 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9034 | PS4-60-BI-0006B-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-17 18:14 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9035 | PS4-60-BI-0006B-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-17 18:16 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9036 | PS4-60-BI-0006B-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-17 18:19 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9037 | PS4-60-BI-0006B-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-17 18:22 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9038 | PS4-60-BI-0006C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9039 | PS4-60-BI-0006C-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9040 | PS4-60-BI-0006C-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9041 | PS4-60-BI-0006C-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9042 | PS4-60-BI-0006C-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9043 | PS4-60-BI-0006C-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9044 | PS4-60-BI-0006C-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9045 | PS4-60-BI-0006C-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9046 | PS4-60-BI-0006C-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9047 | PS4-60-BI-0006C-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9048 | PS4-60-BI-0006C-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9049 | PS4-60-BI-0006D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9050 | PS4-60-BI-0006D-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9051 | PS4-60-BI-0006D-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9052 | PS4-60-BI-0006D-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9053 | PS4-60-BI-0006D-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9054 | PS4-60-BI-0006D-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9055 | PS4-60-BI-0006D-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9056 | PS4-60-BI-0006D-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9057 | PS4-60-BI-0006D-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9058 | PS4-60-BI-0006D-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9059 | PS4-60-BI-0006D-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9060 | PS4-60-BI-0006E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9061 | PS4-60-BI-0006E-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9062 | PS4-60-BI-0006E-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9063 | PS4-60-BI-0006E-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9064 | PS4-60-BI-0006E-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9065 | PS4-60-BI-0006E-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9066 | PS4-60-BI-0006E-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9067 | PS4-60-BI-0006E-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9068 | PS4-60-BI-0006E-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9069 | PS4-60-BI-0006E-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9070 | PS4-60-BI-0006E-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9071 | PS4-60-BI-0006F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9072 | PS4-60-BI-0006F-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9073 | PS4-60-BI-0006F-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9074 | PS4-60-BI-0006F-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9075 | PS4-60-BI-0006F-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9076 | PS4-60-BI-0006F-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9077 | PS4-60-BI-0006F-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9078 | PS4-60-BI-0006F-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9079 | PS4-60-BI-0006F-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9080 | PS4-60-BI-0006F-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9081 | PS4-60-BI-0006F-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9082 | PS4-60-BI-0006G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-9083 | PS4-60-BI-0006G-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-9084 | PS4-60-BI-0006G-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-9085 | PS4-60-BI-0006G-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-9086 | PS4-60-BI-0006G-CL05 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-9087 | PS4-60-BI-0006G-CL06 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-9088 | PS4-60-BI-0006G-CL07 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-9089 | PS4-60-BI-0006G-CL08 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-9090 | PS4-60-BI-0006G-CL09 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-9091 | PS4-60-BI-0006G-CL10 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-9092 | PS4-60-BI-0006G-CL11 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-9093 | PS4-60-BI-0017A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0017A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A | 2026-06-25 13:35 | PS4-60-56 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9094 | PS4-60-BI-0017B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0017B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B | 2026-06-25 13:47 | PS4-60-58 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9095 | PS4-60-BI-0017C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0017C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C |  | PS4-60-60 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9096 | PS4-60-BI-0017D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0017D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D |  | PS4-60-62 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9097 | PS4-60-BI-0017E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0017E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E |  | PS4-60-64 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9098 | PS4-60-BI-0017F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0017F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F |  | PS4-60-66 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9099 | PS4-60-BI-0017G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0017G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G |  | PS4-60-68 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-9100 | PS4-60-EA-2900A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-EA-2900A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A | 2026-06-25 13:37 | PS4-60-56 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9101 | PS4-60-EA-2900B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-EA-2900B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B | 2026-06-25 13:49 | PS4-60-58 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9102 | PS4-60-EA-2900C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-EA-2900C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C |  | PS4-60-60 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9103 | PS4-60-EA-2900D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-EA-2900D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D |  | PS4-60-62 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9104 | PS4-60-EA-2900E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-EA-2900E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E |  | PS4-60-64 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9105 | PS4-60-EA-2900F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-EA-2900F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F |  | PS4-60-66 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9106 | PS4-60-EA-2900G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-EA-2900G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G |  | PS4-60-68 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00023
T-00023-9107 | PS4-61-IK-0005-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IK-0005 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-61-03 - 0.4kV Switchboard Office & Facilities Building (PS4-61-IK-0005) |  | PS4-61-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone I | TM-00023
T-00023-9108 | PS4-71-BE-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0002 TO PS4-71-BE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-27 12:06 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-9109 | PS4-71-BE-0004-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0002 TO PS4-71-BE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-27 12:10 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-9110 | PS4-71-BE-0004-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0002 TO PS4-71-BE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-27 12:14 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-9111 | PS4-71-BI-0003-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0002 TO PS4-71-BI-0003 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-23 11:35 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-9112 | PS4-71-BI-0003-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0002 TO PS4-71-BI-0003 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-23 11:38 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-9113 | PS4-71-BI-0003-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0002 TO PS4-71-BI-0003 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-23 11:42 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-9114 | PS4-71-BI-0003-CL04 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0002 TO PS4-71-BI-0003 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-23 11:44 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-9115 | PS4-71-BI-0004-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0002 TO PS4-71-BI-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-23 11:46 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00023 | sridhar, muthu
T-00023-9116 | PS4-71-BI-0005-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0003 TO PS4-71-BI-0005 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-23 11:49 | PS4-71-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9117 | PS4-71-BI-0005-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0003 TO PS4-71-BI-0005 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-23 11:51 | PS4-71-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9118 | PS4-71-BI-0005-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0003 TO PS4-71-BI-0005 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-23 11:53 | PS4-71-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9119 | PS4-71-BI-0006-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IN-0003 TO PS4-71-BI-0006 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-23 12:03 | PS4-71-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00023 | sridhar, muthu
T-00023-9580 | PS4-09-AHU-8111A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8111A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9581 | PS4-09-AHU-8111B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8111B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9582 | PS4-09-AHU-8211A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8211A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9583 | PS4-09-AHU-8211B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8211B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9584 | PS4-09-AHU-8311A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8311A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9585 | PS4-09-AHU-8311A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8311A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9586 | PS4-09-AHU-8311B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8311B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9587 | PS4-09-AHU-8311B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8311B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9588 | PS4-09-AHU-8321A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8321A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9589 | PS4-09-AHU-8321A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8321A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9590 | PS4-09-AHU-8321B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8321B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9591 | PS4-09-AHU-8321B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8321B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9592 | PS4-09-AHU-8331A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8331A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9593 | PS4-09-AHU-8331A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8331A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9594 | PS4-09-AHU-8331B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8331B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9595 | PS4-09-AHU-8331B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8331B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9596 | PS4-09-AHU-8341-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8341 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9597 | PS4-09-AHU-8341-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8341 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9598 | PS4-09-AHU-8411A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8411A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9599 | PS4-09-AHU-8411A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8411A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9600 | PS4-09-AHU-8411B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8411B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9601 | PS4-09-AHU-8411B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8411B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9602 | PS4-09-FCU-8442A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-FCU-8442A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9603 | PS4-09-FCU-8442B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-FCU-8442B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9604 | PS4-09-FCU-8442C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-FCU-8442C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9605 | PS4-09-FCU-8442D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-FCU-8442D | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9606 | PS4-09-FCU-8442E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-FCU-8442E | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9607 | PS4-09-FCU-8442F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-FCU-8442F | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9608 | PS4-09-FCU-8442G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-FCU-8442G | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9609 | PS4-09-FCU-8442H-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-FCU-8442H | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9610 | PS4-09-LB-0008-CL03 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-LB-0008 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9611 | PS4-09-PA-84500A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-PA-84500A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9612 | PS4-09-PA-84500B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-PA-84500B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9613 | PS4-09-QX-8451A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-QX-8451A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9614 | PS4-09-QX-8451A-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-QX-8451A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9615 | PS4-09-QX-8451B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-QX-8451B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9616 | PS4-09-QX-8451B-CL02 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-QX-8451B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9617 | PS4-09-RF-81200A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-RF-81200A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9618 | PS4-09-RF-81200B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-RF-81200B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9619 | PS4-09-RF-81200C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-RF-81200C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9620 | PS4-09-RF-82200A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-RF-82200A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9621 | PS4-09-RF-82200B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-RF-82200B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9622 | PS4-09-RF-82200C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-RF-82200C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9623 | PS4-09-RF-82200D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-RF-82200D | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9624 | PS4-09-RF-83500A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9625 | PS4-09-RF-83500B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9626 | PS4-09-RF-83500C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9627 | PS4-09-RF-83500D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500D | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9628 | PS4-09-RF-83500E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500E | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9629 | PS4-09-RF-83500F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500F | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9630 | PS4-09-RF-83500G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500G | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9631 | PS4-09-RF-83500H-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500H | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9632 | PS4-09-RF-83500J-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500J | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9633 | PS4-09-RF-83500K-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500K | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9634 | PS4-09-RF-83500L-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500L | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9635 | PS4-09-RF-83500M-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500M | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9636 | PS4-09-RF-83500N-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500N | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9637 | PS4-09-RF-83500P-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500P | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9638 | PS4-09-RF-83600A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9639 | PS4-09-RF-83600B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9640 | PS4-09-RF-83600C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9641 | PS4-09-RF-83600D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600D | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9642 | PS4-09-RF-83600E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600E | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9643 | PS4-09-RF-83600F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600F | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9644 | PS4-09-RF-83600G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600G | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9645 | PS4-09-RF-83600H-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600H | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9646 | PS4-09-RF-83600J-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600J | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9647 | PS4-09-RF-83600K-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600K | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9648 | PS4-09-RF-83600L-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600L | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9649 | PS4-09-RF-83600M-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600M | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9650 | PS4-09-RF-83600N-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600N | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9651 | PS4-09-RF-83600P-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600P | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9652 | PS4-09-RF-83700A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9653 | PS4-09-RF-83700B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9654 | PS4-09-RF-83700C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9655 | PS4-09-RF-83700D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700D | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9656 | PS4-09-RF-83700E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700E | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9657 | PS4-09-RF-83700F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700F | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9658 | PS4-09-RF-83700G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700G | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9659 | PS4-09-RF-83700H-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700H | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9660 | PS4-09-RF-83700J-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700J | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9661 | PS4-09-RF-83700K-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700K | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9662 | PS4-09-RF-83700L-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700L | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9663 | PS4-09-RF-83700M-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700M | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9664 | PS4-09-RF-83700N-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700N | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9665 | PS4-09-RF-83700P-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700P | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9666 | PS4-09-RF-83800A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004D TO PS4-09-RF-83800A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9667 | PS4-09-RF-83800B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004D TO PS4-09-RF-83800B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9668 | PS4-09-RF-83800C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004D TO PS4-09-RF-83800C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9669 | PS4-09-RF-83800D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004D TO PS4-09-RF-83800D | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9670 | PS4-09-RF-83800E-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004D TO PS4-09-RF-83800E | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9671 | PS4-09-RF-83800F-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004D TO PS4-09-RF-83800F | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9672 | PS4-09-RF-83800G-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004D TO PS4-09-RF-83800G | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9673 | PS4-09-RF-84200A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-RF-84200A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9674 | PS4-09-RF-84200B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-RF-84200B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9675 | PS4-09-UZ-84600-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-09-IH-0004 TO PS4-09-UZ-84600 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9676 | PS4-61-IH-0004A-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-61-IH-0004A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9677 | PS4-61-IH-0004B-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-61-IH-0004B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9678 | PS4-61-IH-0004C-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-61-IH-0004C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00023-9679 | PS4-61-IH-0004D-CL01 |  |  |  |  | CPX09 - LV Power Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-61-IH-0004D | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00023
T-00024-2305 | PS4-05-IE-8100-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-01 14:21 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00024 | sridhar, muthu
T-00024-2306 | PS4-05-IE-8100-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-01 14:23 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00024 | sridhar, muthu
T-00024-2307 | PS4-05-IE-8100-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-01 06:17 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00024 | sridhar, muthu
T-00024-2308 | PS4-05-IE-8100-CD04 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-01 06:20 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00024 | sridhar, muthu
T-00024-2309 | PS4-05-IE-8100-CD05 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-01 14:25 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00024 | sridhar, muthu
T-00024-2310 | PS4-05-IE-8100-CD06 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-01 14:26 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00024 | sridhar, muthu
T-00024-2311 | PS4-05-IE-8100-CD07 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-01 14:27 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00024 | sridhar, muthu
T-00024-2312 | PS4-05-IE-8100-CD08 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-01 14:28 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00024 | sridhar, muthu
T-00024-2314 | PS4-05-IE-8100-CD10 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-01 14:30 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00024 | sridhar, muthu
T-00024-2315 | PS4-05-IE-8100-CD11 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-01 14:31 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00024 | sridhar, muthu
T-00024-2316 | PS4-05-IE-8100-CD12 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-01 14:33 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00024 | sridhar, muthu
T-00024-2317 | PS4-05-IE-8100-CD13 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-01 14:34 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00024 | sridhar, muthu
T-00024-2318 | PS4-05-IE-8100-CD14 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-01 14:35 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00024 | sridhar, muthu
T-00024-2319 | PS4-05-IE-8100-CD15 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-01 14:36 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00024 | sridhar, muthu
T-00024-2320 | PS4-05-IE-8100-CD16 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-01 14:37 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00024 | sridhar, muthu
T-00024-2321 | PS4-05-IE-8100-CD17 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-01 14:38 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00024 | sridhar, muthu
T-00024-2322 | PS4-05-IE-8100-CD18 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-01 14:39 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00024 | sridhar, muthu
T-00024-2323 | PS4-05-IE-8100-CD19 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-01 14:40 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00024 | sridhar, muthu
T-00024-2324 | PS4-05-IE-8100-CD20 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-01 14:41 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00024 | sridhar, muthu
T-00024-2325 | PS4-05-IE-8100-CD21 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-01 14:42 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00024 | sridhar, muthu
T-00024-2329 | PS4-05-IE-8100-CD25 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0004 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-23 05:36 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00024 | sridhar, muthu
T-00024-2338 | PS4-25-DM-3100A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00024
T-00024-2339 | PS4-25-DM-3100B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00024
T-00024-2340 | PS4-25-DM-3100C-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00024
T-00024-2344 | PS4-25-IES-3100A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-IES-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-01 14:43 | PS4-25-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00024 | sridhar, muthu
T-00024-2345 | PS4-25-IES-3100B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-IES-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00024
T-00024-2346 | PS4-25-IES-3100C-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-IES-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00024
T-00024-2374 | PS4-50-IE-0001-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-50-IE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-50-01 - Water Well Submersible Pumps (3100) |  | PS4-50-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone I | TM-00024
T-00024-2375 | PS4-50-IE-0002-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-50-IE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-50-02 - Water Well Submersible Pumps (3200) |  | PS4-50-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone I | TM-00024
T-00024-2378 | PS4-60-IE-0002A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015A TO PS4-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-23 06:06 | PS4-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00024 | sridhar, muthu
T-00024-2379 | PS4-60-IE-0002A-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015A TO PS4-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-23 06:08 | PS4-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00024 | sridhar, muthu
T-00024-2380 | PS4-60-IE-0002A-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015A TO PS4-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-23 06:11 | PS4-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00024 | sridhar, muthu
T-00024-2381 | PS4-60-IE-0002B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015B TO PS4-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-23 06:26 | PS4-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00024 | sridhar, muthu
T-00024-2382 | PS4-60-IE-0002B-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015B TO PS4-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-23 06:29 | PS4-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00024 | sridhar, muthu
T-00024-2383 | PS4-60-IE-0002B-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015B TO PS4-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-23 06:31 | PS4-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00024 | sridhar, muthu
T-00024-2384 | PS4-60-IE-0002C-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015C TO PS4-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2385 | PS4-60-IE-0002C-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015C TO PS4-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2386 | PS4-60-IE-0002C-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015C TO PS4-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2387 | PS4-60-IE-0002D-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015D TO PS4-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2388 | PS4-60-IE-0002D-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015D TO PS4-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2389 | PS4-60-IE-0002D-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015D TO PS4-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2390 | PS4-60-IE-0002E-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015E TO PS4-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2391 | PS4-60-IE-0002E-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015E TO PS4-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2392 | PS4-60-IE-0002E-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015E TO PS4-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2393 | PS4-60-IE-0002F-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015F TO PS4-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2394 | PS4-60-IE-0002F-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015F TO PS4-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2395 | PS4-60-IE-0002F-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015F TO PS4-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2396 | PS4-60-IE-0002G-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015G TO PS4-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone E | TM-00024
T-00024-2397 | PS4-60-IE-0002G-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015G TO PS4-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone E | TM-00024
T-00024-2398 | PS4-60-IE-0002G-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015G TO PS4-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone E | TM-00024
T-00024-2400 | PS4-60-IE-0003A-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-23 06:35 | PS4-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00024 | sridhar, muthu
T-00024-2401 | PS4-60-IE-0003A-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-23 06:37 | PS4-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00024 | sridhar, muthu
T-00024-2402 | PS4-60-IE-0003A-CD04 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0005A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-23 06:40 | PS4-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00024 | sridhar, muthu
T-00024-2403 | PS4-60-IE-0003A-CD05 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-23 06:57 | PS4-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00024 | sridhar, muthu
T-00024-2412 | PS4-60-IE-0003A-CD14 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0002A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-23 07:01 | PS4-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00024 | sridhar, muthu
T-00024-2413 | PS4-60-IE-0003A-CD15 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-23 12:35 | PS4-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00024 | sridhar, muthu
T-00024-2415 | PS4-60-IE-0003B-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-23 07:12 | PS4-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00024 | sridhar, muthu
T-00024-2416 | PS4-60-IE-0003B-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-23 07:15 | PS4-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00024 | sridhar, muthu
T-00024-2417 | PS4-60-IE-0003B-CD04 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0005B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-23 07:19 | PS4-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00024 | sridhar, muthu
T-00024-2418 | PS4-60-IE-0003B-CD05 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-23 07:27 | PS4-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00024 | sridhar, muthu
T-00024-2427 | PS4-60-IE-0003B-CD14 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0002B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-23 07:30 | PS4-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00024 | sridhar, muthu
T-00024-2428 | PS4-60-IE-0003B-CD15 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-23 12:38 | PS4-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00024 | sridhar, muthu
T-00024-2430 | PS4-60-IE-0003C-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2431 | PS4-60-IE-0003C-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2432 | PS4-60-IE-0003C-CD04 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0005C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2433 | PS4-60-IE-0003C-CD05 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2442 | PS4-60-IE-0003C-CD14 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0002C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2443 | PS4-60-IE-0003C-CD15 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-23 12:41 | PS4-60-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00024 | sridhar, muthu
T-00024-2445 | PS4-60-IE-0003D-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2446 | PS4-60-IE-0003D-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2447 | PS4-60-IE-0003D-CD04 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0005D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2448 | PS4-60-IE-0003D-CD05 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2457 | PS4-60-IE-0003D-CD14 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0002D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2458 | PS4-60-IE-0003D-CD15 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-25 13:57 | PS4-60-10 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00024 | sridhar, muthu
T-00024-2460 | PS4-60-IE-0003E-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2461 | PS4-60-IE-0003E-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2462 | PS4-60-IE-0003E-CD04 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0005E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2463 | PS4-60-IE-0003E-CD05 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2472 | PS4-60-IE-0003E-CD14 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0002E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2473 | PS4-60-IE-0003E-CD15 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2475 | PS4-60-IE-0003F-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2476 | PS4-60-IE-0003F-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2477 | PS4-60-IE-0003F-CD04 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0005F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2478 | PS4-60-IE-0003F-CD05 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2487 | PS4-60-IE-0003F-CD14 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0002F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-2488 | PS4-60-IE-0003F-CD15 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-27 12:18 | PS4-60-16 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00024 | sridhar, muthu
T-00024-2490 | PS4-60-IE-0003G-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone E | TM-00024
T-00024-2491 | PS4-60-IE-0003G-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone E | TM-00024
T-00024-2492 | PS4-60-IE-0003G-CD04 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0005G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone E | TM-00024
T-00024-2493 | PS4-60-IE-0003G-CD05 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-BI-0015G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone E | TM-00024
T-00024-2502 | PS4-60-IE-0003G-CD14 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0002G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone E | TM-00024
T-00024-2503 | PS4-60-IE-0003G-CD15 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-27 12:20 | PS4-60-19 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone E | TM-00024 | sridhar, muthu
T-00024-2510 | PS4-61-IDH-3100A-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-02 04:54 | PS4-25-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00024 | sridhar, muthu
T-00024-2513 | PS4-61-IDH-3100B-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-02 04:55 | PS4-25-03 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00024 | sridhar, muthu
T-00024-2516 | PS4-61-IDH-3100C-CD03 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-02 04:55 | PS4-25-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00024 | sridhar, muthu
T-00024-2558 | PS4-62-IE-0001-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-62-IE-0002 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 | 2026-07-02 05:02 | PS4-62-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone G | TM-00024 | sridhar, muthu
T-00024-3180 | PS4-79-IG-0001-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0001 TO PS4-79-IG-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00024
T-00024-3181 | PS4-79-IG-0002-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0002 TO PS4-79-IG-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00024
T-00024-3182 | PS4-79-IG-0003-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0003 TO PS4-79-IG-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00024
T-00024-3183 | PS4-79-IG-0004-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0004 TO PS4-79-IG-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00024
T-00024-3184 | PS4-79-IG-0005-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0005 TO PS4-79-IG-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00024
T-00024-3185 | PS4-79-IG-0006-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0006 TO PS4-79-IG-0006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00024
T-00024-3186 | PS4-79-IG-0007-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0007 TO PS4-79-IG-0007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00024
T-00024-3187 | PS4-79-IG-0008-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0008 TO PS4-79-IG-0008 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00024
T-00024-3188 | PS4-79-IG-0009-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0009 TO PS4-79-IG-0009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00024
T-00024-3189 | PS4-79-IG-0010-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0010 TO PS4-79-IG-0010 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00024
T-00024-3190 | PS4-79-IG-0011-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0011 TO PS4-79-IG-0011 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00024
T-00024-3191 | PS4-79-IG-0012-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-79-IV-0012 TO PS4-79-IG-0012 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00024
T-00024-3398 | PS4-06-GU-0003A-CD02 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-GB-0003 TO PS4-06-GU-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-30 16:21 | PS4-06-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00024 | sridhar, muthu
T-00024-3580 | PS4-09-IES-8101A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8101A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3581 | PS4-09-IES-8101B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8101B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3582 | PS4-09-IES-8102A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8102A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3583 | PS4-09-IES-8102B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8102B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3584 | PS4-09-IES-8102C-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8102C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3585 | PS4-09-IES-8201A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8201A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3586 | PS4-09-IES-8201B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8201B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3587 | PS4-09-IES-8202A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8202A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3588 | PS4-09-IES-8202B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8202B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3589 | PS4-09-IES-8202C-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8202C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3590 | PS4-09-IES-8202D-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8202D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3591 | PS4-09-IES-8301A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8301A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3592 | PS4-09-IES-8301B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8301B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3593 | PS4-09-IES-8302A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8302A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3594 | PS4-09-IES-8302B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8302B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3595 | PS4-09-IES-8304A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8304A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3596 | PS4-09-IES-8304B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8304B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3597 | PS4-09-IES-8305A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8305A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3598 | PS4-09-IES-8305B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8305B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3599 | PS4-09-IES-8307A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8307A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3600 | PS4-09-IES-8307B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8307B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3601 | PS4-09-IES-8308A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8308A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3602 | PS4-09-IES-8308B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8308B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3603 | PS4-09-IES-8311A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8311A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3604 | PS4-09-IES-8311B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8311B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3605 | PS4-09-IES-8313-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-IES-8313 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3606 | PS4-09-IES-8314-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-IES-8314 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3607 | PS4-09-IES-8315-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8315 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3608 | PS4-09-IES-8316-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-IES-8316 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3609 | PS4-09-IES-8317-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-IES-8317 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3610 | PS4-09-IES-8318-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8318 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3611 | PS4-09-IES-8319-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-IES-8319 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3612 | PS4-09-IES-8321-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-IES-8321 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3613 | PS4-09-IES-8322-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8322 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3614 | PS4-09-IES-8323-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004D TO PS4-09-IES-8323 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3615 | PS4-09-IES-8324-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004D TO PS4-09-IES-8324 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3616 | PS4-09-IES-8325-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8325 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3617 | PS4-09-IES-8401A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8401A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3618 | PS4-09-IES-8401B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8401B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3619 | PS4-09-IES-8403A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8403A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3620 | PS4-09-IES-8403B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8403B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3621 | PS4-09-IES-8404A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8404A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3622 | PS4-09-IES-8404B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8404B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3623 | PS4-09-IES-8405A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8405A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3624 | PS4-09-IES-8405B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8405B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3625 | PS4-09-IES-8406A-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8406A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3626 | PS4-09-IES-8406B-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8406B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3627 | PS4-09-IES-8406C-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8406C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3628 | PS4-09-IES-8406D-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8406D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3629 | PS4-09-IES-8406E-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8406E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3630 | PS4-09-IES-8406F-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8406F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3631 | PS4-09-IES-8406G-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8406G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3632 | PS4-09-IES-8406H-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8406H | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-3633 | PS4-09-IES-8407-CD01 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8407 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00024
T-00024-4388 | PS4-61-IE-0002-CD45 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00024
T-00024-4389 | PS4-61-IE-0002-CD46 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00024
T-00024-4390 | PS4-61-IE-0002-CD47 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00024
T-00024-4391 | PS4-61-IE-0002-CD48 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00024
T-00024-4392 | PS4-61-IE-0002-CD49 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00024
T-00024-4393 | PS4-61-IE-0002-CD50 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00024
T-00024-4394 | PS4-61-IE-0002-CD51 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0005 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00024
T-00024-4395 | PS4-61-IE-0002-CD52 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0005 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00024
T-00024-4396 | PS4-61-IE-0002-CD53 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0005 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00024
T-00024-4397 | PS4-61-IE-0002-CD54 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0005 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00024
T-00024-4398 | PS4-61-IE-0002-CD55 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0005 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00024
T-00024-4399 | PS4-61-IE-0003-CD11 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IE-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00024
T-00024-4400 | PS4-61-IE-0003-CD12 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IE-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00024
T-00024-4401 | PS4-61-IE-0003-CD13 |  |  |  |  | CPX10 - Multicore Electrical Control Cable | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IE-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00024
T-00025-0010 | PS4-25-DM-3100A |  |  |  |  | CPX12 - HV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE OIL EXPORT PUMP A MOTOR | EACOP | CPP AGI |  |  | 8 |  | 8 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | HV Motor | E | To be completed | PS4 - Milestone H | TM-00025
T-00025-0011 | PS4-25-DM-3100B |  |  |  |  | CPX12 - HV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE OIL EXPORT PUMP B MOTOR | EACOP | CPP AGI |  |  | 8 |  | 8 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | HV Motor | E | To be completed | PS4 - Milestone H | TM-00025
T-00025-0012 | PS4-25-DM-3100C |  |  |  |  | CPX12 - HV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE OIL EXPORT PUMP C MOTOR | EACOP | CPP AGI |  |  | 8 |  | 8 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | HV Motor | E | To be completed | PS4 - Milestone H | TM-00025
T-00026-0114 | PS4-28-DM-3300 |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Relief Drum Pump Motor | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump |  | PS4-28-06 |  |  | LV Motor | E | To be completed | PS4 - Milestone G | TM-00026
T-00026-0115 | PS4-28-DM-3400 |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Closed Drain Drum 01 Pump Motor | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | LV Motor | E | To be completed | PS4 - Milestone G | TM-00026
T-00026-0116 | PS4-28-DM-3500 |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Oily Water Sump Pump Motor | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | LV Motor | E | To be completed | PS4 - Milestone G | TM-00026
T-00026-0117 | PS4-28-DM-3600A |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Open Drain Sump Pump Motor A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | LV Motor | E | To be completed | PS4 - Milestone G | TM-00026
T-00026-0118 | PS4-28-DM-3600B |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Open Drain Sump Pump Motor B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | LV Motor | E | To be completed | PS4 - Milestone G | TM-00026
T-00026-0119 | PS4-28-DM-3700A |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Closed Drain Drum 02 Pump Motor A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | LV Motor | E | To be completed | PS4 - Milestone E | TM-00026
T-00026-0120 | PS4-28-DM-3700B |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Closed Drain Drum 02 Pump Motor B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | LV Motor | E | To be completed | PS4 - Milestone E | TM-00026
T-00026-0121 | PS4-28-DM-3800A |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Seal Oil Drain Drum Pump Motor A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | LV Motor | E | To be completed | PS4 - Milestone H | TM-00026
T-00026-0122 | PS4-28-DM-3800B |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Seal Oil Drain Drum Pump Motor B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | LV Motor | E | To be completed | PS4 - Milestone H | TM-00026
T-00026-0123 | PS4-28-DM-3800C |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Seal Oil Drain Drum Pump Motor C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | LV Motor | E | To be completed | PS4 - Milestone H | TM-00026
T-00026-0124 | PS4-28-DM-3900A |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Reinjection Pump Motor A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | LV Motor | E | To be completed | PS4 - Milestone H | TM-00026
T-00026-0125 | PS4-28-DM-3900B |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Reinjection Pump Motor B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | LV Motor | E | To be completed | PS4 - Milestone H | TM-00026
T-00026-0126 | PS4-53-DM-3100A |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Water Distribution Pump Motor A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-53-02 - Water Distribution Pump A/B |  | PS4-53-02 |  |  | LV Motor | E | To be completed | PS4 - Milestone E | TM-00026
T-00026-0127 | PS4-53-DM-3100B |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Water Distribution Pump Motor B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-53-02 - Water Distribution Pump A/B |  | PS4-53-02 |  |  | LV Motor | E | To be completed | PS4 - Milestone E | TM-00026
T-00026-0128 | PS4-60-DM-3300 |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cooling Water Pump Motor | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-24 - Cooling Water Tank & Pump |  | PS4-60-24 |  |  | LV Motor | E | To be completed | PS4 - Milestone E | TM-00026
T-00026-0129 | PS4-60-DM-3400 |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cooling Water Return Pump Motor | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-25 - Cooling Water Maintenance Tank & Return Pump |  | PS4-60-25 |  |  | LV Motor | E | To be completed | PS4 - Milestone E | TM-00026
T-00026-0130 | PS4-71-DM-3100A |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Diesel Fuel Supply Pump Motor A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-16 - Diesel Fuel Supply Pump A/B |  | PS4-71-16 |  |  | LV Motor | E | To be completed | PS4 - Milestone F | TM-00026
T-00026-0131 | PS4-71-DM-3100B |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Diesel Fuel Supply Pump Motor B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-16 - Diesel Fuel Supply Pump A/B |  | PS4-71-16 |  |  | LV Motor | E | To be completed | PS4 - Milestone F | TM-00026
T-00026-0132 | PS4-71-DM-3200 |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Diesel Fuel Make-Up Pump Motor | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-14 - Diesel Fuel Transfer and Dispensing Station |  | PS4-71-14 |  |  | LV Motor | E | To be completed | PS4 - Milestone F | TM-00026
T-00026-0133 | PS4-71-DM-3300A |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Crude Fuel Oil Transfer Pump Motor A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | LV Motor | E | To be completed | PS4 - Milestone H | TM-00026
T-00026-0134 | PS4-71-DM-3300B |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Crude Fuel Oil Transfer Pump Motor B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | LV Motor | E | To be completed | PS4 - Milestone H | TM-00026
T-00026-0135 | PS4-71-DM-3400A |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Crude Fuel Oil Service Pump Motor A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | LV Motor | E | To be completed | PS4 - Milestone H | TM-00026
T-00026-0136 | PS4-71-DM-3400B |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Crude Fuel Oil Service Pump Motor B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | LV Motor | E | To be completed | PS4 - Milestone H | TM-00026
T-00026-0137 | PS4-71-DM-3500A |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Diesel Transfer Pump Motor A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | LV Motor | E | To be completed | PS4 - Milestone B | TM-00026
T-00026-0138 | PS4-71-DM-3500B |  |  |  |  | CPX13 - LV Motor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Diesel Transfer Pump Motor B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | LV Motor | E | To be completed | PS4 - Milestone B | TM-00026
T-00028-0433 | PS4-01-IG-0001 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Water Mist System Main Distribution Board | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Distribution Board | E | To be completed | PS4 - Milestone E | TM-00028
T-00028-0434 | PS4-05-IG-0002 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Indoor Emergency L&SP DB Office and Facilities Building | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Distribution Board | E | To be completed | PS4 - Milestone I | TM-00028
T-00028-0435 | PS4-05-IG-0004 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Outdoor Emergency Lighting Distribution Board PS-4 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-03 - Outdoor Emergency Lighting DB - PS4-05-IG-0004 | 2026-06-01 12:22 | PS4-62-03 |  |  | Distribution Board | E | Closed | PS4 - Milestone G | TM-00028 | sridhar, muthu
T-00028-0436 | PS4-05-IG-0006 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Outdoor Emergency Lighting Distribution Board PS-4 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-04 - Outdoor Emergency Lighting DB - PS4-05-IG-0006 | 2026-06-01 12:22 | PS4-62-04 |  |  | Distribution Board | E | Closed | PS4 - Milestone G | TM-00028 | sridhar, muthu
T-00028-0437 | PS4-05-IG-0007 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Indoor Emergency L&SP DB - Guard House | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-05 - Guard House Emergency L&SP DB - PS4-05-IG-0007 |  | PS4-62-05 |  |  | Distribution Board | E | To be completed | PS4 - Milestone I | TM-00028
T-00028-0438 | PS4-05-IG-0014 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRO Generator Building Emergency Lighting Distribution Board PS-4 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-06 - CRO Generator Building Emergency Lighting DB - PS4-05-IG-0014 |  | PS4-62-06 |  |  | Distribution Board | E | To be completed | PS4 - Milestone B | TM-00028
T-00028-0439 | PS4-05-IG-0020 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Generator Electrical Building Emergency L&SP Distribution Board PS-4 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-07 - CRO Generator Electrical Building Emergency L&SP DB - PS4-05-IG-0020 |  | PS4-62-07 |  |  | Distribution Board | E | To be completed | PS4 - Milestone B | TM-00028
T-00028-0440 | PS4-06-IG-0004A |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | AC UPS DB - Generator Electrical Bldng | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building |  | PS4-06-02 |  |  | Distribution Board | E | To be completed | PS4 - Milestone B | TM-00028
T-00028-0441 | PS4-06-IG-0004B |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | AC UPS DB - Generator Electrical Bldng | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building |  | PS4-06-02 |  |  | Distribution Board | E | To be completed | PS4 - Milestone B | TM-00028
T-00028-0442 | PS4-61-IG-0005 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Outdoor Normal Lighting Distribution Board PS-4 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 | 2026-06-01 12:24 | PS4-62-08 |  |  | Distribution Board | E | Closed | PS4 - Milestone G | TM-00028 | sridhar, muthu
T-00028-0443 | PS4-61-IG-0007 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Outdoor Normal Lighting Distribution Board PS-4 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 | 2026-06-01 12:24 | PS4-62-09 |  |  | Distribution Board | E | Closed | PS4 - Milestone G | TM-00028 | sridhar, muthu
T-00028-0444 | PS4-61-IG-0010 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Generator Electrical Building Normal L&SP Distribution Board PS-4 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-10 - CRO Generator Electrical Building Normal L&SP DB - PS4-61-IG-0010 |  | PS4-62-10 |  |  | Distribution Board | E | To be completed | PS4 - Milestone B | TM-00028
T-00028-0445 | PS4-61-IG-0014 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Outdoor Power Distribution Board PS-4 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-61-08 - Outdoor Power Distribution Board - PS4-61-IG-0014 |  | PS4-61-08 |  |  | Distribution Board | E | To be completed | PS4 - Milestone G | TM-00028
T-00028-0446 | PS4-61-IG-0030 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRO Generator Building Normal L&SP Distribution Board PS-4 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Distribution Board | E | To be completed | PS4 - Milestone B | TM-00028
T-00028-0447 | PS4-61-IG-0041 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Outdoor valves Distribution Board PS-4 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-61-09 - Outdoor Valves Distribution Board - PS4-61-IG-0041 | 2026-06-01 12:20 | PS4-61-09 |  |  | Distribution Board | E | Closed | PS4 - Milestone F | TM-00028 | sridhar, muthu
T-00028-0448 | PS4-61-IG-0042 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Outdoor valves Distribution Board PS-4 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-61-10 - Outdoor Valves Distribution Board - PS4-61-IG-0042 | 2026-06-01 12:21 | PS4-61-10 |  |  | Distribution Board | E | Closed | PS4 - Milestone F | TM-00028 | sridhar, muthu
T-00028-0449 | PS4-74-IG-5101 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Nitrogen Generation Skid Power Distribution Panel | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-74-02 - N2 Generation Skid (UCP) |  | PS4-74-02 |  |  | Distribution Board | E | To be completed | PS4 - Milestone F | TM-00028
T-00028-0450 | PS4-79-IG-0001 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | EHT Distribution Board 1 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Distribution Board | E | To be completed | PS4 - Milestone H | TM-00028
T-00028-0451 | PS4-79-IG-0002 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | EHT Distribution Board 2 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Distribution Board | E | To be completed | PS4 - Milestone H | TM-00028
T-00028-0452 | PS4-79-IG-0003 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | EHT Distribution Board 3 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Distribution Board | E | To be completed | PS4 - Milestone H | TM-00028
T-00028-0453 | PS4-79-IG-0004 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | EHT Distribution Board 4 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Distribution Board | E | To be completed | PS4 - Milestone H | TM-00028
T-00028-0454 | PS4-79-IG-0005 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | EHT Distribution Board 5 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Distribution Board | E | To be completed | PS4 - Milestone H | TM-00028
T-00028-0455 | PS4-79-IG-0006 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | EHT Distribution Board 6 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Distribution Board | E | To be completed | PS4 - Milestone H | TM-00028
T-00028-0456 | PS4-79-IG-0007 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | EHT Distribution Board 7 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Distribution Board | E | To be completed | PS4 - Milestone H | TM-00028
T-00028-0457 | PS4-79-IG-0008 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | EHT Distribution Board 8 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Distribution Board | E | To be completed | PS4 - Milestone H | TM-00028
T-00028-0458 | PS4-79-IG-0009 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | EHT Distribution Board 9 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Distribution Board | E | To be completed | PS4 - Milestone H | TM-00028
T-00028-0459 | PS4-79-IG-0010 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | EHT Distribution Board 10 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Distribution Board | E | To be completed | PS4 - Milestone H | TM-00028
T-00028-0460 | PS4-79-IG-0011 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | EHT Distribution Board 11 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Distribution Board | E | To be completed | PS4 - Milestone H | TM-00028
T-00028-0461 | PS4-79-IG-0012 |  |  |  |  | CPX15 - Distribution Board | PCOM - Precommissioning | E | Conformity Check | E - Electrical | EHT Distribution Board 12 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Distribution Board | E | To be completed | PS4 - Milestone H | TM-00028
T-00029-0231 | PS4-06-GU-0003A |  |  |  |  | CPX16 - Charger/Inverter | PCOM - Precommissioning | E | Conformity Check | E - Electrical | AC UPS A - Generator Electrical Building | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building |  | PS4-06-02 |  |  | Charger/Inverter | E | Started (not Completed) | PS4 - Milestone B | TM-00029
T-00029-0232 | PS4-06-GU-0003B |  |  |  |  | CPX16 - Charger/Inverter | PCOM - Precommissioning | E | Conformity Check | E - Electrical | AC UPS B - Generator Electrical Building | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building |  | PS4-06-02 |  |  | Charger/Inverter | E | To be completed | PS4 - Milestone B | TM-00029
T-00029-0233 | PS4-06-GU-0003C |  |  |  |  | CPX16 - Charger/Inverter | PCOM - Precommissioning | E | Conformity Check | E - Electrical | AC UPS Bypass - Generator Electrical Building | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building |  | PS4-06-02 |  |  | Charger/Inverter | E | To be completed | PS4 - Milestone B | TM-00029
T-00031-1130 |  | PS4-05-IG-0002_CKT01 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1131 |  | PS4-05-IG-0002_CKT02 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1132 |  | PS4-05-IG-0002_CKT03 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1133 |  | PS4-05-IG-0002_CKT04 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1134 |  | PS4-05-IG-0002_CKT05 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1135 |  | PS4-05-IG-0002_CKT06 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1136 |  | PS4-05-IG-0002_CKT07 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1137 |  | PS4-05-IG-0002_CKT08 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1138 |  | PS4-05-IG-0002_CKT09 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1139 |  | PS4-05-IG-0002_CKT10 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1140 |  | PS4-05-IG-0002_CKT11 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1141 |  | PS4-05-IG-0002_CKT12 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1142 |  | PS4-05-IG-0002_CKT13 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1143 |  | PS4-05-IG-0007_CKT01 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-05 - Guard House Emergency L&SP DB - PS4-05-IG-0007 |  | PS4-62-05 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1144 |  | PS4-05-IG-0007_CKT02 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-05 - Guard House Emergency L&SP DB - PS4-05-IG-0007 |  | PS4-62-05 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1145 |  | PS4-05-IG-0007_CKT03 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-05 - Guard House Emergency L&SP DB - PS4-05-IG-0007 |  | PS4-62-05 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1146 |  | PS4-05-IG-0007_CKT04 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-05 - Guard House Emergency L&SP DB - PS4-05-IG-0007 |  | PS4-62-05 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1147 |  | PS4-05-IG-0014_CKT01 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-06 - CRO Generator Building Emergency Lighting DB - PS4-05-IG-0014 |  | PS4-62-06 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1148 |  | PS4-05-IG-0014_CKT02 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-06 - CRO Generator Building Emergency Lighting DB - PS4-05-IG-0014 |  | PS4-62-06 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1149 |  | PS4-05-IG-0014_CKT03 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-06 - CRO Generator Building Emergency Lighting DB - PS4-05-IG-0014 |  | PS4-62-06 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1150 |  | PS4-05-IG-0014_CKT04 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-06 - CRO Generator Building Emergency Lighting DB - PS4-05-IG-0014 |  | PS4-62-06 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1151 |  | PS4-05-IG-0014_CKT07 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-06 - CRO Generator Building Emergency Lighting DB - PS4-05-IG-0014 |  | PS4-62-06 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1152 |  | PS4-05-IG-0014_CKT08 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-06 - CRO Generator Building Emergency Lighting DB - PS4-05-IG-0014 |  | PS4-62-06 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1153 |  | PS4-05-IG-0014_CKT09 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-06 - CRO Generator Building Emergency Lighting DB - PS4-05-IG-0014 |  | PS4-62-06 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1154 |  | PS4-05-IG-0020_CKT01 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-07 - CRO Generator Electrical Building Emergency L&SP DB - PS4-05-IG-0020 |  | PS4-62-07 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1155 |  | PS4-05-IG-0020_CKT02 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-07 - CRO Generator Electrical Building Emergency L&SP DB - PS4-05-IG-0020 |  | PS4-62-07 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1156 |  | PS4-05-IG-0020_CKT03 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-07 - CRO Generator Electrical Building Emergency L&SP DB - PS4-05-IG-0020 |  | PS4-62-07 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1157 |  | PS4-05-IG-0020_CKT05 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-07 - CRO Generator Electrical Building Emergency L&SP DB - PS4-05-IG-0020 |  | PS4-62-07 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1158 |  | PS4-05-IG-0020_CKT06 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-07 - CRO Generator Electrical Building Emergency L&SP DB - PS4-05-IG-0020 |  | PS4-62-07 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1159 |  | PS4-05-IG-0020_CKT09 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-07 - CRO Generator Electrical Building Emergency L&SP DB - PS4-05-IG-0020 |  | PS4-62-07 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1160 |  | PS4-05-IG-0101_CKT01 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-19 - Workshop & Warehouse Emergency L&SP DB - PS4-05-IG-0101 |  | PS4-62-19 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1161 |  | PS4-05-IG-0101_CKT02 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-19 - Workshop & Warehouse Emergency L&SP DB - PS4-05-IG-0101 |  | PS4-62-19 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1162 |  | PS4-05-IG-0101_CKT03 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-19 - Workshop & Warehouse Emergency L&SP DB - PS4-05-IG-0101 |  | PS4-62-19 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1163 |  | PS4-05-IG-0101_CKT04 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-19 - Workshop & Warehouse Emergency L&SP DB - PS4-05-IG-0101 |  | PS4-62-19 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1164 |  | PS4-05-IG-0101_CKT05 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-19 - Workshop & Warehouse Emergency L&SP DB - PS4-05-IG-0101 |  | PS4-62-19 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1165 |  | PS4-05-IG-0101_CKT06 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-19 - Workshop & Warehouse Emergency L&SP DB - PS4-05-IG-0101 |  | PS4-62-19 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1166 |  | PS4-05-IG-0101_CKT07 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-19 - Workshop & Warehouse Emergency L&SP DB - PS4-05-IG-0101 |  | PS4-62-19 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1167 |  | PS4-05-IG-0101_CKT08 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-19 - Workshop & Warehouse Emergency L&SP DB - PS4-05-IG-0101 |  | PS4-62-19 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1168 |  | PS4-05-IG-0101_CKT09 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-19 - Workshop & Warehouse Emergency L&SP DB - PS4-05-IG-0101 |  | PS4-62-19 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1169 |  | PS4-05-IG-0101_CKT10 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-19 - Workshop & Warehouse Emergency L&SP DB - PS4-05-IG-0101 |  | PS4-62-19 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1170 |  | PS4-61-IG-0002_CKT01 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1171 |  | PS4-61-IG-0002_CKT02 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1172 |  | PS4-61-IG-0002_CKT03 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1173 |  | PS4-61-IG-0002_CKT04 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1174 |  | PS4-61-IG-0002_CKT05 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1175 |  | PS4-61-IG-0002_CKT06 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1176 |  | PS4-61-IG-0002_CKT07 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1177 |  | PS4-61-IG-0002_CKT08 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1178 |  | PS4-61-IG-0002_CKT09 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1179 |  | PS4-61-IG-0002_CKT10 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1180 |  | PS4-61-IG-0002_CKT11 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1181 |  | PS4-61-IG-0002_CKT12 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1182 |  | PS4-61-IG-0004_CKT01 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1183 |  | PS4-61-IG-0004_CKT02 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1184 |  | PS4-61-IG-0004_CKT03 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1185 |  | PS4-61-IG-0004_CKT04 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1186 |  | PS4-61-IG-0004_CKT05 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1187 |  | PS4-61-IG-0004_CKT06 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1188 |  | PS4-61-IG-0004_CKT08 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1189 |  | PS4-61-IG-0004_CKT09 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1190 |  | PS4-61-IG-0005_CKT09 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 |  | PS4-62-08 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1191 |  | PS4-61-IG-0005_CKT10 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 |  | PS4-62-08 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1192 |  | PS4-61-IG-0005_CKT11 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 |  | PS4-62-08 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1193 |  | PS4-61-IG-0005_CKT13 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 |  | PS4-62-08 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1194 |  | PS4-61-IG-0005_CKT15 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 |  | PS4-62-08 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1195 |  | PS4-61-IG-0005_CKT16 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 |  | PS4-62-08 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1196 |  | PS4-61-IG-0005_CKT17 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 |  | PS4-62-08 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1197 |  | PS4-61-IG-0005_CKT18 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 |  | PS4-62-08 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1198 |  | PS4-61-IG-0005_CKT19 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 |  | PS4-62-08 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1199 |  | PS4-61-IG-0007_CKT06 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 |  | PS4-62-09 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1200 |  | PS4-61-IG-0007_CKT09 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 |  | PS4-62-09 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1201 |  | PS4-61-IG-0007_CKT11 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 |  | PS4-62-09 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1202 |  | PS4-61-IG-0007_CKT12 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 |  | PS4-62-09 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1203 |  | PS4-61-IG-0007_CKT13 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 |  | PS4-62-09 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1204 |  | PS4-61-IG-0007_CKT15 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 |  | PS4-62-09 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1205 |  | PS4-61-IG-0007_CKT16 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 |  | PS4-62-09 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1206 |  | PS4-61-IG-0007_CKT18 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 |  | PS4-62-09 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1207 |  | PS4-61-IG-0007_CKT19 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 |  | PS4-62-09 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1208 |  | PS4-61-IG-0007_CKT20 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 |  | PS4-62-09 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1209 |  | PS4-61-IG-0009_CKT01 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-20 - Office Building Normal L&SP DB - PS4-61-IG-0009 |  | PS4-62-20 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1210 |  | PS4-61-IG-0009_CKT02 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-20 - Office Building Normal L&SP DB - PS4-61-IG-0009 |  | PS4-62-20 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1211 |  | PS4-61-IG-0009_CKT03 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-20 - Office Building Normal L&SP DB - PS4-61-IG-0009 |  | PS4-62-20 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1212 |  | PS4-61-IG-0010_CKT01 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-10 - CRO Generator Electrical Building Normal L&SP DB - PS4-61-IG-0010 |  | PS4-62-10 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1213 |  | PS4-61-IG-0010_CKT03 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-10 - CRO Generator Electrical Building Normal L&SP DB - PS4-61-IG-0010 |  | PS4-62-10 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1214 |  | PS4-61-IG-0010_CKT04 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-10 - CRO Generator Electrical Building Normal L&SP DB - PS4-61-IG-0010 |  | PS4-62-10 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1215 |  | PS4-61-IG-0010_CKT05 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-10 - CRO Generator Electrical Building Normal L&SP DB - PS4-61-IG-0010 |  | PS4-62-10 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1216 |  | PS4-61-IG-0010_CKT06 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-10 - CRO Generator Electrical Building Normal L&SP DB - PS4-61-IG-0010 |  | PS4-62-10 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1217 |  | PS4-61-IG-0030_CKT01 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1218 |  | PS4-61-IG-0030_CKT02 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1219 |  | PS4-61-IG-0030_CKT03 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1220 |  | PS4-61-IG-0030_CKT04 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1221 |  | PS4-61-IG-0030_CKT05 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1222 |  | PS4-61-IG-0030_CKT06 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1223 |  | PS4-61-IG-0030_CKT07 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1224 |  | PS4-61-IG-0030_CKT08 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1225 |  | PS4-61-IG-0030_CKT09 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1226 |  | PS4-61-IG-0030_CKT10 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1227 |  | PS4-61-IG-0030_CKT11 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1228 |  | PS4-61-IG-0030_CKT12 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1229 |  | PS4-61-IG-0030_CKT14 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1230 |  | PS4-61-IG-0030_CKT15 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00031
T-00031-1231 |  | PS4-61-IG-0111_CKT01 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-16 - Guard Hut A Normal L&SP DB - PS4-61-IG-0111 |  | PS4-62-16 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1232 |  | PS4-61-IG-0112_CKT01 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-17 - Guard Hut B Normal L&SP DB - PS4-61-IG-0112 |  | PS4-62-17 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00031
T-00031-1233 |  | PS4-62-IE-0001_CKT-KA01 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1234 |  | PS4-62-IE-0001_CKT-KA02 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1235 |  | PS4-62-IE-0001_CKT-KA03 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1236 |  | PS4-62-IE-0001_CKT-KA04 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1237 |  | PS4-62-IE-0001_CKT-KA05 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1238 |  | PS4-62-IE-0001_CKT-KA06 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1239 |  | PS4-62-IE-0001_CKT-KA07 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1240 |  | PS4-62-IE-0001_CKT-KA08 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1241 |  | PS4-62-IE-0001_CKT-KA09 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1242 |  | PS4-62-IE-0001_CKT-KA10 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1243 |  | PS4-62-IE-0001_CKT-KA11 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1244 |  | PS4-62-IE-0001_CKT-KA12 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1245 |  | PS4-62-IE-0001_CKT-KA13 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1246 |  | PS4-62-IE-0001_CKT-KB01 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1247 |  | PS4-62-IE-0001_CKT-KB04 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1248 |  | PS4-62-IE-0001_CKT-KB06 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1249 |  | PS4-62-IE-0002_CKT-KA01 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1250 |  | PS4-62-IE-0002_CKT-KA02 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1251 |  | PS4-62-IE-0002_CKT-KA03 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1252 |  | PS4-62-IE-0002_CKT-KA05 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1253 |  | PS4-62-IE-0002_CKT-KA06 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1254 |  | PS4-62-IE-0002_CKT-KA08 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1255 |  | PS4-62-IE-0002_CKT-KA11 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1256 |  | PS4-62-IE-0002_CKT-KA12 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1257 |  | PS4-62-IE-0002_CKT-KA13 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1258 |  | PS4-62-IE-0002_CKT-KA14 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1259 |  | PS4-62-IE-0002_CKT-KA15 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1260 |  | PS4-62-IE-0002_CKT-KA16 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1261 |  | PS4-62-IE-0002_CKT-KA17 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1262 |  | PS4-62-IE-0002_CKT-KB01 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00031-1263 |  | PS4-62-IE-0002_CKT-KB04 |  |  |  | CPX18 - Lighting Circuits | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00031
T-00032-0163 | PS4-25-UD-3100A |  |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical | 5 pin 32A plug and socket for Oil Purifier Control Panel(Portable Load) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Power Sock Outlet | E | To be completed | PS4 - Milestone H | TM-00032
T-00032-0164 | PS4-28-ISO-2008 |  |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Socket Outlet 63A for mobile oil skimmer (PS4-28-UZ-8100) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-10 - Oil Skimmer Package |  | PS4-28-10 |  |  | Power Sock Outlet | E | To be completed | PS4 - Milestone I | TM-00032
T-00032-0386 |  | PS4-05-IG-0007_CKT07 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-05 - Guard House Emergency L&SP DB - PS4-05-IG-0007 |  | PS4-62-05 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0387 |  | PS4-05-IG-0007_CKT09 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-05 - Guard House Emergency L&SP DB - PS4-05-IG-0007 |  | PS4-62-05 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0388 |  | PS4-05-IG-0007_CKT13 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-05 - Guard House Emergency L&SP DB - PS4-05-IG-0007 |  | PS4-62-05 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0389 |  | PS4-05-IG-0007_CKT14 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-05 - Guard House Emergency L&SP DB - PS4-05-IG-0007 |  | PS4-62-05 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0390 |  | PS4-05-IG-0007_CKT15 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-05 - Guard House Emergency L&SP DB - PS4-05-IG-0007 |  | PS4-62-05 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0391 |  | PS4-06-GU-0101_CKT01 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-06-03 - AC UPS - Office & Facilities Building |  | PS4-06-03 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0392 |  | PS4-06-GU-0101_CKT02 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-06-03 - AC UPS - Office & Facilities Building |  | PS4-06-03 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0393 |  | PS4-06-GU-0101_CKT03 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-06-03 - AC UPS - Office & Facilities Building |  | PS4-06-03 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0394 |  | PS4-06-IG-0020_CKT12 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-06-05 - AC UPS - Workshop & Warehouse |  | PS4-06-05 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0395 |  | PS4-61-IG-0002_CKT13 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0396 |  | PS4-61-IG-0002_CKT14 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0397 |  | PS4-61-IG-0002_CKT15 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0398 |  | PS4-61-IG-0002_CKT16 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0399 |  | PS4-61-IG-0002_CKT17 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0400 |  | PS4-61-IG-0002_CKT18 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0401 |  | PS4-61-IG-0002_CKT19 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0402 |  | PS4-61-IG-0002_CKT20 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0403 |  | PS4-61-IG-0002_CKT21 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0404 |  | PS4-61-IG-0002_CKT22 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0405 |  | PS4-61-IG-0002_CKT23 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0406 |  | PS4-61-IG-0004_CKT10 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0407 |  | PS4-61-IG-0004_CKT11 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0408 |  | PS4-61-IG-0004_CKT12 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0409 |  | PS4-61-IG-0004_CKT13 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0410 |  | PS4-61-IG-0009_CKT04 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-20 - Office Building Normal L&SP DB - PS4-61-IG-0009 |  | PS4-62-20 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0411 |  | PS4-61-IG-0009_CKT05 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-20 - Office Building Normal L&SP DB - PS4-61-IG-0009 |  | PS4-62-20 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0412 |  | PS4-61-IG-0010_CKT07 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-10 - CRO Generator Electrical Building Normal L&SP DB - PS4-61-IG-0010 |  | PS4-62-10 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone B | TM-00032
T-00032-0413 |  | PS4-61-IG-0010_CKT08 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-10 - CRO Generator Electrical Building Normal L&SP DB - PS4-61-IG-0010 |  | PS4-62-10 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone B | TM-00032
T-00032-0414 |  | PS4-61-IG-0014_CKT01 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-08 - Outdoor Power Distribution Board - PS4-61-IG-0014 |  | PS4-61-08 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone G | TM-00032
T-00032-0415 |  | PS4-61-IG-0014_CKT02 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-08 - Outdoor Power Distribution Board - PS4-61-IG-0014 |  | PS4-61-08 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone G | TM-00032
T-00032-0416 |  | PS4-61-IG-0014_CKT03 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-08 - Outdoor Power Distribution Board - PS4-61-IG-0014 |  | PS4-61-08 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone G | TM-00032
T-00032-0417 |  | PS4-61-IG-0014_CKT04 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-08 - Outdoor Power Distribution Board - PS4-61-IG-0014 |  | PS4-61-08 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone G | TM-00032
T-00032-0418 |  | PS4-61-IG-0014_CKT05 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-08 - Outdoor Power Distribution Board - PS4-61-IG-0014 |  | PS4-61-08 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone G | TM-00032
T-00032-0419 |  | PS4-61-IG-0014_CKT06 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-08 - Outdoor Power Distribution Board - PS4-61-IG-0014 |  | PS4-61-08 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone G | TM-00032
T-00032-0420 |  | PS4-61-IG-0014_CKT08 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-08 - Outdoor Power Distribution Board - PS4-61-IG-0014 |  | PS4-61-08 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone G | TM-00032
T-00032-0421 |  | PS4-61-IG-0014_CKT11 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-08 - Outdoor Power Distribution Board - PS4-61-IG-0014 |  | PS4-61-08 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone G | TM-00032
T-00032-0422 |  | PS4-61-IG-0019_CKT15 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-13 - Power Distribution Board Workshop & Warehouse - PS4-61-IG-0019 |  | PS4-61-13 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0423 |  | PS4-61-IG-0019_CKT16 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-13 - Power Distribution Board Workshop & Warehouse - PS4-61-IG-0019 |  | PS4-61-13 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0424 |  | PS4-61-IG-0019_CKT17 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-13 - Power Distribution Board Workshop & Warehouse - PS4-61-IG-0019 |  | PS4-61-13 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0425 |  | PS4-61-IG-0019_CKT18 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-13 - Power Distribution Board Workshop & Warehouse - PS4-61-IG-0019 |  | PS4-61-13 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0426 |  | PS4-61-IG-0019_CKT19 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-13 - Power Distribution Board Workshop & Warehouse - PS4-61-IG-0019 |  | PS4-61-13 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0427 |  | PS4-61-IG-0019_CKT31 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-13 - Power Distribution Board Workshop & Warehouse - PS4-61-IG-0019 |  | PS4-61-13 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0428 |  | PS4-61-IG-0019_CKT32 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-13 - Power Distribution Board Workshop & Warehouse - PS4-61-IG-0019 |  | PS4-61-13 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0429 |  | PS4-61-IG-0019_CKT33 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-13 - Power Distribution Board Workshop & Warehouse - PS4-61-IG-0019 |  | PS4-61-13 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0430 |  | PS4-61-IG-0019_CKT34 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-13 - Power Distribution Board Workshop & Warehouse - PS4-61-IG-0019 |  | PS4-61-13 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0431 |  | PS4-61-IG-0030_CKT19 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone B | TM-00032
T-00032-0432 |  | PS4-61-IG-0030_CKT20 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone B | TM-00032
T-00032-0433 |  | PS4-61-IG-0030_CKT21 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone B | TM-00032
T-00032-0434 |  | PS4-61-IG-0111_CKT02 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-16 - Guard Hut A Normal L&SP DB - PS4-61-IG-0111 |  | PS4-62-16 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0435 |  | PS4-61-IG-0111_CKT03 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-16 - Guard Hut A Normal L&SP DB - PS4-61-IG-0111 |  | PS4-62-16 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0436 |  | PS4-61-IG-0112_CKT02 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-17 - Guard Hut B Normal L&SP DB - PS4-61-IG-0112 |  | PS4-62-17 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00032-0437 |  | PS4-61-IG-0112_CKT03 |  |  |  | CPX19 - Power Socket Outlet | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-17 - Guard Hut B Normal L&SP DB - PS4-61-IG-0112 |  | PS4-62-17 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00032
T-00033-0050 | PS4-28-HE-2100 |  |  |  |  | CPX20 - Heater | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CLOSED DRAIN DRUM HEATER 01 | EACOP | CPP AGI |  |  | 5 |  |  | TZ-MID-67-WPR2-135401 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Heater | E | To be completed | PS4 - Milestone G | TM-00033
T-00033-0051 | PS4-28-HE-2200 |  |  |  |  | CPX20 - Heater | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CLOSED DRAIN DRUM HEATER 02 | EACOP | CPP AGI |  |  | 5 |  |  | TZ-MID-67-WPR2-135404 | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Heater | E | To be completed | PS4 - Milestone E | TM-00033
T-00033-0052 | PS4-71-HE-2200 |  |  |  |  | CPX20 - Heater | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE FUEL OIL SERVICE TANK HEATER | EACOP | CPP AGI |  |  | 5 |  |  | TZ-MID-67-WPR2-135003 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Heater | E | To be completed | PS4 - Milestone H | TM-00033
T-00033-0053 | PS4-71-HE-2300 |  |  |  |  | CPX20 - Heater | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE FUEL OIL STORAGE TANK HEATER | EACOP | CPP AGI |  |  | 5 |  |  | TZ-MID-67-WPR2-135000 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Heater | E | To be completed | PS4 - Milestone H | TM-00033
T-00033-0054 | PS4-71-HE-2400A |  |  |  |  | CPX20 - Heater | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE FUEL OIL STORAGE TANK FEED HEATER | EACOP | CPP AGI |  |  | 5 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Heater | E | To be completed | PS4 - Milestone H | TM-00033
T-00033-0055 | PS4-71-HE-2400B |  |  |  |  | CPX20 - Heater | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE FUEL OIL STORAGE TANK FEED HEATER | EACOP | CPP AGI |  |  | 5 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Heater | E | To be completed | PS4 - Milestone H | TM-00033
T-00033-0065 | PS4-25-HE-2100 |  |  |  |  | CPX20 - Heater | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Crude Oil Export Pump Motor A - Lube Oil System Oil Reservoir Heater | EACOP | CPP AGI |  |  | 5 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Heater | E | To be completed | PS4 - Milestone H | TM-00033
T-00033-0066 | PS4-25-HE-2200 |  |  |  |  | CPX20 - Heater | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Crude Oil Export Pump Motor B - Lube Oil System Oil Reservoir Heater | EACOP | CPP AGI |  |  | 5 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Heater | E | To be completed | PS4 - Milestone H | TM-00033
T-00033-0067 | PS4-25-HE-2300 |  |  |  |  | CPX20 - Heater | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Crude Oil Export Pump Motor C - Lube Oil System Oil Reservoir Heater | EACOP | CPP AGI |  |  | 5 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Heater | E | To be completed | PS4 - Milestone H | TM-00033
T-00034-0045 | PS4-61-NER-0010 |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LLHT Transformer NER | EACOP | CPP AGI |  |  | 8 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) |  | PS4-61-02 |  |  | Neutral Earthing Resistor | E | To be completed | PS4 - Milestone G | TM-00034
T-00034-0046 | PS4-63-NER-0010 |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing Transformer NER | EACOP | CPP AGI |  |  | 8 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Neutral Earthing Resistor | E | To be completed | PS4 - Milestone D | TM-00034
T-00034-0047 | PS4-63-NER-0011 |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing Transformer NER | EACOP | CPP AGI |  |  | 8 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Neutral Earthing Resistor | E | To be completed | PS4 - Milestone D | TM-00034
T-00034-0052 | PS4-60-IJ-0001A |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Neutral Grounding resistor for Generator set 1 (A) | EACOP | CPP AGI |  |  | 8 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 13:33 | PS4-60-01 |  |  | Neutral Earthing Resistor | E | Closed | PS4 - Milestone B | TM-00034 | sridhar, muthu
T-00034-0053 | PS4-60-IJ-0001B |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Neutral Grounding resistor for Generator set 2 (B) | EACOP | CPP AGI |  |  | 8 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 13:34 | PS4-60-04 |  |  | Neutral Earthing Resistor | E | Closed | PS4 - Milestone B | TM-00034 | sridhar, muthu
T-00034-0054 | PS4-60-IJ-0001C |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Neutral Grounding resistor for Generator set 3 (C) | EACOP | CPP AGI |  |  | 8 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Neutral Earthing Resistor | E | To be completed | PS4 - Milestone D | TM-00034
T-00034-0055 | PS4-60-IJ-0001D |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Neutral Grounding resistor for Generator set 4 (D) | EACOP | CPP AGI |  |  | 8 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Neutral Earthing Resistor | E | To be completed | PS4 - Milestone D | TM-00034
T-00034-0056 | PS4-60-IJ-0001E |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Neutral Grounding resistor for Generator set 5 (E) | EACOP | CPP AGI |  |  | 8 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Neutral Earthing Resistor | E | To be completed | PS4 - Milestone D | TM-00034
T-00034-0057 | PS4-60-IJ-0001F |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Neutral Grounding resistor for Generator set 6 (F) | EACOP | CPP AGI |  |  | 8 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Neutral Earthing Resistor | E | To be completed | PS4 - Milestone D | TM-00034
T-00034-0058 | PS4-60-IJ-0001G |  |  |  |  | CPX21 - Neutral Earthing Resistor | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Neutral Grounding resistor for Generator set 7 (G) | EACOP | CPP AGI |  |  | 8 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Neutral Earthing Resistor | E | To be completed | PS4 - Milestone E | TM-00034
T-00035-0991 |  | PS4-79-IG-0001_CKT01 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-0992 |  | PS4-79-IG-0001_CKT02 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-0993 |  | PS4-79-IG-0001_CKT03 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-0994 |  | PS4-79-IG-0001_CKT04 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-0995 |  | PS4-79-IG-0001_CKT05 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-0996 |  | PS4-79-IG-0001_CKT06 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-0997 |  | PS4-79-IG-0001_CKT07 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-0998 |  | PS4-79-IG-0001_CKT08 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-0999 |  | PS4-79-IG-0001_CKT09 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1000 |  | PS4-79-IG-0001_CKT10 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1001 |  | PS4-79-IG-0001_CKT11 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1002 |  | PS4-79-IG-0001_CKT12 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1003 |  | PS4-79-IG-0001_CKT13 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1004 |  | PS4-79-IG-0001_CKT14 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1005 |  | PS4-79-IG-0001_CKT15 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1006 |  | PS4-79-IG-0001_CKT16 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1007 |  | PS4-79-IG-0001_CKT17 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1008 |  | PS4-79-IG-0001_CKT18 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1009 |  | PS4-79-IG-0001_CKT19 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1010 |  | PS4-79-IG-0001_CKT20 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1011 |  | PS4-79-IG-0001_CKT21 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1012 |  | PS4-79-IG-0001_CKT22 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1013 |  | PS4-79-IG-0001_CKT23 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1014 |  | PS4-79-IG-0001_CKT24 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1015 |  | PS4-79-IG-0001_CKT25 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1016 |  | PS4-79-IG-0001_CKT26 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1017 |  | PS4-79-IG-0001_CKT27 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1018 |  | PS4-79-IG-0001_CKT28 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1019 |  | PS4-79-IG-0001_CKT31 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1020 |  | PS4-79-IG-0002_CKT01 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1021 |  | PS4-79-IG-0002_CKT02 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1022 |  | PS4-79-IG-0002_CKT03 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1023 |  | PS4-79-IG-0002_CKT04 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1024 |  | PS4-79-IG-0002_CKT05 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1025 |  | PS4-79-IG-0002_CKT06 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1026 |  | PS4-79-IG-0002_CKT07 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1027 |  | PS4-79-IG-0002_CKT08 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1028 |  | PS4-79-IG-0002_CKT09 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1029 |  | PS4-79-IG-0002_CKT10 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1030 |  | PS4-79-IG-0002_CKT11 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1031 |  | PS4-79-IG-0002_CKT12 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1032 |  | PS4-79-IG-0002_CKT13 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1033 |  | PS4-79-IG-0002_CKT14 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1034 |  | PS4-79-IG-0002_CKT15 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1035 |  | PS4-79-IG-0002_CKT16 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1036 |  | PS4-79-IG-0002_CKT17 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1037 |  | PS4-79-IG-0002_CKT18 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1038 |  | PS4-79-IG-0002_CKT19 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1039 |  | PS4-79-IG-0002_CKT20 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1040 |  | PS4-79-IG-0002_CKT21 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1041 |  | PS4-79-IG-0002_CKT22 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1042 |  | PS4-79-IG-0002_CKT23 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1043 |  | PS4-79-IG-0002_CKT24 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1044 |  | PS4-79-IG-0002_CKT25 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1045 |  | PS4-79-IG-0002_CKT26 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1046 |  | PS4-79-IG-0002_CKT27 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1047 |  | PS4-79-IG-0002_CKT28 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1048 |  | PS4-79-IG-0002_CKT29 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1049 |  | PS4-79-IG-0002_CKT31 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1050 |  | PS4-79-IG-0003_CKT01 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1051 |  | PS4-79-IG-0003_CKT02 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1052 |  | PS4-79-IG-0003_CKT03 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1053 |  | PS4-79-IG-0003_CKT04 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1054 |  | PS4-79-IG-0003_CKT05 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1055 |  | PS4-79-IG-0003_CKT06 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1056 |  | PS4-79-IG-0003_CKT07 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1057 |  | PS4-79-IG-0003_CKT08 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1058 |  | PS4-79-IG-0003_CKT09 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1059 |  | PS4-79-IG-0003_CKT10 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1060 |  | PS4-79-IG-0003_CKT11 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1061 |  | PS4-79-IG-0003_CKT12 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1062 |  | PS4-79-IG-0003_CKT13 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1063 |  | PS4-79-IG-0003_CKT14 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1064 |  | PS4-79-IG-0003_CKT15 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1065 |  | PS4-79-IG-0003_CKT16 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1066 |  | PS4-79-IG-0003_CKT17 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1067 |  | PS4-79-IG-0003_CKT18 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1068 |  | PS4-79-IG-0003_CKT19 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1069 |  | PS4-79-IG-0003_CKT20 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1070 |  | PS4-79-IG-0003_CKT21 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1071 |  | PS4-79-IG-0003_CKT22 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1072 |  | PS4-79-IG-0003_CKT23 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1073 |  | PS4-79-IG-0003_CKT24 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1074 |  | PS4-79-IG-0003_CKT25 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1075 |  | PS4-79-IG-0003_CKT26 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1076 |  | PS4-79-IG-0003_CKT27 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1077 |  | PS4-79-IG-0003_CKT28 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1078 |  | PS4-79-IG-0003_CKT31 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1079 |  | PS4-79-IG-0004_CKT01 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1080 |  | PS4-79-IG-0004_CKT02 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1081 |  | PS4-79-IG-0004_CKT03 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1082 |  | PS4-79-IG-0004_CKT04 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1083 |  | PS4-79-IG-0004_CKT05 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1084 |  | PS4-79-IG-0004_CKT06 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1085 |  | PS4-79-IG-0004_CKT07 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1086 |  | PS4-79-IG-0004_CKT08 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1087 |  | PS4-79-IG-0004_CKT09 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1088 |  | PS4-79-IG-0004_CKT10 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1089 |  | PS4-79-IG-0004_CKT11 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1090 |  | PS4-79-IG-0004_CKT12 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1091 |  | PS4-79-IG-0004_CKT13 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1092 |  | PS4-79-IG-0004_CKT14 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1093 |  | PS4-79-IG-0004_CKT15 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1094 |  | PS4-79-IG-0004_CKT16 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1095 |  | PS4-79-IG-0004_CKT17 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1096 |  | PS4-79-IG-0004_CKT18 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1097 |  | PS4-79-IG-0004_CKT19 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1098 |  | PS4-79-IG-0004_CKT20 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1099 |  | PS4-79-IG-0004_CKT21 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1100 |  | PS4-79-IG-0004_CKT22 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1101 |  | PS4-79-IG-0004_CKT23 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1102 |  | PS4-79-IG-0004_CKT24 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1103 |  | PS4-79-IG-0004_CKT25 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1104 |  | PS4-79-IG-0004_CKT26 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1105 |  | PS4-79-IG-0004_CKT28 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1106 |  | PS4-79-IG-0005_CKT01 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1107 |  | PS4-79-IG-0005_CKT02 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1108 |  | PS4-79-IG-0005_CKT03 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1109 |  | PS4-79-IG-0005_CKT04 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1110 |  | PS4-79-IG-0005_CKT05 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1111 |  | PS4-79-IG-0005_CKT06 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1112 |  | PS4-79-IG-0005_CKT07 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1113 |  | PS4-79-IG-0005_CKT08 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1114 |  | PS4-79-IG-0005_CKT09 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1115 |  | PS4-79-IG-0005_CKT10 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1116 |  | PS4-79-IG-0005_CKT11 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1117 |  | PS4-79-IG-0005_CKT12 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1118 |  | PS4-79-IG-0005_CKT13 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1119 |  | PS4-79-IG-0005_CKT14 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1120 |  | PS4-79-IG-0005_CKT15 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1121 |  | PS4-79-IG-0005_CKT16 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1122 |  | PS4-79-IG-0005_CKT17 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1123 |  | PS4-79-IG-0005_CKT18 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1124 |  | PS4-79-IG-0005_CKT19 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1125 |  | PS4-79-IG-0005_CKT20 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1126 |  | PS4-79-IG-0005_CKT21 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1127 |  | PS4-79-IG-0005_CKT22 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1128 |  | PS4-79-IG-0005_CKT23 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1129 |  | PS4-79-IG-0005_CKT24 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1130 |  | PS4-79-IG-0005_CKT25 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1131 |  | PS4-79-IG-0005_CKT26 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1132 |  | PS4-79-IG-0005_CKT27 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1133 |  | PS4-79-IG-0005_CKT28 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1134 |  | PS4-79-IG-0006_CKT01 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1135 |  | PS4-79-IG-0006_CKT02 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1136 |  | PS4-79-IG-0006_CKT03 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1137 |  | PS4-79-IG-0006_CKT04 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1138 |  | PS4-79-IG-0006_CKT05 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1139 |  | PS4-79-IG-0006_CKT06 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1140 |  | PS4-79-IG-0006_CKT07 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1141 |  | PS4-79-IG-0006_CKT08 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1142 |  | PS4-79-IG-0006_CKT09 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1143 |  | PS4-79-IG-0006_CKT10 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1144 |  | PS4-79-IG-0006_CKT11 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1145 |  | PS4-79-IG-0006_CKT12 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1146 |  | PS4-79-IG-0006_CKT13 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1147 |  | PS4-79-IG-0006_CKT14 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1148 |  | PS4-79-IG-0006_CKT15 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1149 |  | PS4-79-IG-0006_CKT16 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1150 |  | PS4-79-IG-0006_CKT17 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1151 |  | PS4-79-IG-0006_CKT18 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1152 |  | PS4-79-IG-0006_CKT19 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1153 |  | PS4-79-IG-0006_CKT20 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1154 |  | PS4-79-IG-0006_CKT21 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1155 |  | PS4-79-IG-0006_CKT22 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1156 |  | PS4-79-IG-0006_CKT23 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1157 |  | PS4-79-IG-0006_CKT24 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1158 |  | PS4-79-IG-0006_CKT25 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1159 |  | PS4-79-IG-0006_CKT26 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1160 |  | PS4-79-IG-0006_CKT27 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1161 |  | PS4-79-IG-0006_CKT28 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1162 |  | PS4-79-IG-0006_CKT29 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1163 |  | PS4-79-IG-0006_CKT30 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1164 |  | PS4-79-IG-0006_CKT31 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1165 |  | PS4-79-IG-0006_CKT34 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1166 |  | PS4-79-IG-0007_CKT01 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1167 |  | PS4-79-IG-0007_CKT02 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1168 |  | PS4-79-IG-0007_CKT03 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1169 |  | PS4-79-IG-0007_CKT04 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1170 |  | PS4-79-IG-0007_CKT05 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1171 |  | PS4-79-IG-0007_CKT06 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1172 |  | PS4-79-IG-0007_CKT07 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1173 |  | PS4-79-IG-0007_CKT08 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1174 |  | PS4-79-IG-0007_CKT09 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1175 |  | PS4-79-IG-0007_CKT10 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1176 |  | PS4-79-IG-0007_CKT11 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1177 |  | PS4-79-IG-0007_CKT12 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1178 |  | PS4-79-IG-0007_CKT13 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1179 |  | PS4-79-IG-0007_CKT14 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1180 |  | PS4-79-IG-0007_CKT15 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1181 |  | PS4-79-IG-0007_CKT16 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1182 |  | PS4-79-IG-0007_CKT17 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1183 |  | PS4-79-IG-0007_CKT18 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1184 |  | PS4-79-IG-0007_CKT19 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1185 |  | PS4-79-IG-0007_CKT20 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1186 |  | PS4-79-IG-0007_CKT21 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1187 |  | PS4-79-IG-0007_CKT22 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1188 |  | PS4-79-IG-0007_CKT23 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1189 |  | PS4-79-IG-0007_CKT24 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1190 |  | PS4-79-IG-0007_CKT25 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1191 |  | PS4-79-IG-0007_CKT26 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1192 |  | PS4-79-IG-0007_CKT27 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1193 |  | PS4-79-IG-0007_CKT28 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1194 |  | PS4-79-IG-0007_CKT29 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1195 |  | PS4-79-IG-0007_CKT30 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1196 |  | PS4-79-IG-0007_CKT31 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1197 |  | PS4-79-IG-0007_CKT40 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1198 |  | PS4-79-IG-0008_CKT01 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1199 |  | PS4-79-IG-0008_CKT02 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1200 |  | PS4-79-IG-0008_CKT03 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1201 |  | PS4-79-IG-0008_CKT04 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1202 |  | PS4-79-IG-0008_CKT05 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1203 |  | PS4-79-IG-0008_CKT06 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1204 |  | PS4-79-IG-0008_CKT07 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1205 |  | PS4-79-IG-0008_CKT08 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1206 |  | PS4-79-IG-0008_CKT09 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1207 |  | PS4-79-IG-0008_CKT10 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1208 |  | PS4-79-IG-0008_CKT11 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1209 |  | PS4-79-IG-0008_CKT12 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1210 |  | PS4-79-IG-0008_CKT13 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1211 |  | PS4-79-IG-0008_CKT14 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1212 |  | PS4-79-IG-0008_CKT15 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1213 |  | PS4-79-IG-0008_CKT16 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1214 |  | PS4-79-IG-0008_CKT17 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1215 |  | PS4-79-IG-0008_CKT18 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1216 |  | PS4-79-IG-0008_CKT19 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1217 |  | PS4-79-IG-0008_CKT20 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1218 |  | PS4-79-IG-0008_CKT21 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1219 |  | PS4-79-IG-0008_CKT22 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1220 |  | PS4-79-IG-0008_CKT23 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1221 |  | PS4-79-IG-0008_CKT24 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1222 |  | PS4-79-IG-0008_CKT25 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1223 |  | PS4-79-IG-0008_CKT26 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1224 |  | PS4-79-IG-0008_CKT27 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1225 |  | PS4-79-IG-0008_CKT28 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1226 |  | PS4-79-IG-0008_CKT29 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1227 |  | PS4-79-IG-0008_CKT30 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1228 |  | PS4-79-IG-0008_CKT31 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1229 |  | PS4-79-IG-0008_CKT40 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1230 |  | PS4-79-IG-0009_CKT01 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1231 |  | PS4-79-IG-0009_CKT02 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1232 |  | PS4-79-IG-0009_CKT03 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1233 |  | PS4-79-IG-0009_CKT04 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1234 |  | PS4-79-IG-0009_CKT05 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1235 |  | PS4-79-IG-0009_CKT06 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1236 |  | PS4-79-IG-0009_CKT07 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1237 |  | PS4-79-IG-0009_CKT08 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1238 |  | PS4-79-IG-0009_CKT09 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1239 |  | PS4-79-IG-0009_CKT10 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1240 |  | PS4-79-IG-0009_CKT11 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1241 |  | PS4-79-IG-0009_CKT12 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1242 |  | PS4-79-IG-0009_CKT13 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1243 |  | PS4-79-IG-0009_CKT14 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1244 |  | PS4-79-IG-0009_CKT15 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1245 |  | PS4-79-IG-0009_CKT16 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1246 |  | PS4-79-IG-0009_CKT17 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1247 |  | PS4-79-IG-0009_CKT18 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1248 |  | PS4-79-IG-0009_CKT19 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1249 |  | PS4-79-IG-0009_CKT20 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1250 |  | PS4-79-IG-0009_CKT21 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1251 |  | PS4-79-IG-0009_CKT22 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1252 |  | PS4-79-IG-0009_CKT23 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1253 |  | PS4-79-IG-0009_CKT24 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1254 |  | PS4-79-IG-0009_CKT25 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1255 |  | PS4-79-IG-0009_CKT26 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1256 |  | PS4-79-IG-0009_CKT27 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1257 |  | PS4-79-IG-0009_CKT28 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1258 |  | PS4-79-IG-0009_CKT29 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1259 |  | PS4-79-IG-0009_CKT30 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1260 |  | PS4-79-IG-0009_CKT31 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1261 |  | PS4-79-IG-0009_CKT40 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1262 |  | PS4-79-IG-0010_CKT01 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1263 |  | PS4-79-IG-0010_CKT02 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1264 |  | PS4-79-IG-0010_CKT03 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1265 |  | PS4-79-IG-0010_CKT04 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1266 |  | PS4-79-IG-0010_CKT05 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1267 |  | PS4-79-IG-0010_CKT06 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1268 |  | PS4-79-IG-0010_CKT07 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1269 |  | PS4-79-IG-0010_CKT08 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1270 |  | PS4-79-IG-0010_CKT09 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1271 |  | PS4-79-IG-0010_CKT10 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1272 |  | PS4-79-IG-0010_CKT11 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1273 |  | PS4-79-IG-0010_CKT12 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1274 |  | PS4-79-IG-0010_CKT13 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1275 |  | PS4-79-IG-0010_CKT14 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1276 |  | PS4-79-IG-0010_CKT15 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1277 |  | PS4-79-IG-0010_CKT16 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1278 |  | PS4-79-IG-0010_CKT17 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1279 |  | PS4-79-IG-0010_CKT18 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1280 |  | PS4-79-IG-0010_CKT19 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1281 |  | PS4-79-IG-0010_CKT20 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1282 |  | PS4-79-IG-0010_CKT21 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1283 |  | PS4-79-IG-0010_CKT22 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1284 |  | PS4-79-IG-0010_CKT23 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1285 |  | PS4-79-IG-0010_CKT24 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1286 |  | PS4-79-IG-0010_CKT25 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1287 |  | PS4-79-IG-0010_CKT26 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1288 |  | PS4-79-IG-0010_CKT27 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1289 |  | PS4-79-IG-0010_CKT28 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1290 |  | PS4-79-IG-0010_CKT29 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1291 |  | PS4-79-IG-0010_CKT31 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1292 |  | PS4-79-IG-0011_CKT01 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1293 |  | PS4-79-IG-0011_CKT02 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1294 |  | PS4-79-IG-0011_CKT03 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1295 |  | PS4-79-IG-0011_CKT04 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1296 |  | PS4-79-IG-0011_CKT05 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1297 |  | PS4-79-IG-0011_CKT06 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1298 |  | PS4-79-IG-0011_CKT07 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1299 |  | PS4-79-IG-0011_CKT08 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1300 |  | PS4-79-IG-0011_CKT09 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1301 |  | PS4-79-IG-0011_CKT10 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1302 |  | PS4-79-IG-0011_CKT11 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1303 |  | PS4-79-IG-0011_CKT12 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1304 |  | PS4-79-IG-0011_CKT13 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1305 |  | PS4-79-IG-0011_CKT14 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1306 |  | PS4-79-IG-0011_CKT15 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1307 |  | PS4-79-IG-0011_CKT16 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1308 |  | PS4-79-IG-0011_CKT17 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1309 |  | PS4-79-IG-0011_CKT18 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1310 |  | PS4-79-IG-0011_CKT19 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1311 |  | PS4-79-IG-0011_CKT20 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1312 |  | PS4-79-IG-0011_CKT21 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1313 |  | PS4-79-IG-0011_CKT22 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1314 |  | PS4-79-IG-0011_CKT23 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1315 |  | PS4-79-IG-0011_CKT24 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1316 |  | PS4-79-IG-0011_CKT25 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1317 |  | PS4-79-IG-0011_CKT26 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1318 |  | PS4-79-IG-0011_CKT27 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1319 |  | PS4-79-IG-0011_CKT28 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1320 |  | PS4-79-IG-0011_CKT29 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1321 |  | PS4-79-IG-0011_CKT30 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1322 |  | PS4-79-IG-0012_CKT01 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1323 |  | PS4-79-IG-0012_CKT02 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1324 |  | PS4-79-IG-0012_CKT03 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1325 |  | PS4-79-IG-0012_CKT04 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1326 |  | PS4-79-IG-0012_CKT05 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1327 |  | PS4-79-IG-0012_CKT06 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1328 |  | PS4-79-IG-0012_CKT07 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1329 |  | PS4-79-IG-0012_CKT08 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1330 |  | PS4-79-IG-0012_CKT09 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1331 |  | PS4-79-IG-0012_CKT10 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1332 |  | PS4-79-IG-0012_CKT11 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1333 |  | PS4-79-IG-0012_CKT12 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1334 |  | PS4-79-IG-0012_CKT13 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1335 |  | PS4-79-IG-0012_CKT14 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1336 |  | PS4-79-IG-0012_CKT15 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1337 |  | PS4-79-IG-0012_CKT16 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1338 |  | PS4-79-IG-0012_CKT17 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1339 |  | PS4-79-IG-0012_CKT18 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1340 |  | PS4-79-IG-0012_CKT19 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1341 |  | PS4-79-IG-0012_CKT20 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1342 |  | PS4-79-IG-0012_CKT21 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1343 |  | PS4-79-IG-0012_CKT22 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1344 |  | PS4-79-IG-0012_CKT23 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1345 |  | PS4-79-IG-0012_CKT24 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1346 |  | PS4-79-IG-0012_CKT25 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1347 |  | PS4-79-IG-0012_CKT26 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1348 |  | PS4-79-IG-0012_CKT27 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1349 |  | PS4-79-IG-0012_CKT28 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1350 |  | PS4-79-IG-0012_CKT29 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1351 |  | PS4-79-IG-0012_CKT30 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1352 |  | PS4-79-IG-0012_CKT31 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1353 |  | PS4-79-IG-0012_CKT32 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1354 |  | PS4-79-IG-0012_CKT33 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1355 |  | PS4-79-IG-0012_CKT34 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00035-1356 |  | PS4-79-IG-0012_CKT37 |  |  |  | CPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Conformity Check | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00035
T-00039-0251 | PS4 - CFO AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151156 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0252 | PS4 - CHEMICAL AND WASTE STORAGE AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151146 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0253 | PS4 - CLOSED DRAIN DRUM AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  | 10 | TZ-MID-67-WPR2-151158 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | Submitted | PS4 - Milestone A | TM-00039
T-00039-0254 | PS4 - DIESEL FUEL STORAGE AND PUMP AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151148 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0255 | PS4 - FENCE EAST AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151161 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0256 | PS4 - FENCE SOUTH EAST AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151163 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0257 | PS4 - FENCE SOUTH WEST AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151162 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0258 | PS4 - FENCE WEST AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151160 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0259 | PS4 - LAUNCHER/RECEIVER AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151154 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0260 | PS4 - LOADING PUMP AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151155 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0261 | PS4 - OBSERVATION BASIN AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151151 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0262 | PS4 - POWER DISTRIBUTION AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  | 10 | TZ-MID-67-WPR2-151153 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing | 2026-01-10 10:51 | PS4-63-01 |  |  | Earthing System | E | Closed | PS4 - Milestone A | TM-00039 | sridhar, muthu
T-00039-0263 | PS4 - POWER GENERATION BUILDING AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151157 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0264 | PS4 - POWER GENERATION COOLING TOWER AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  | 10 | TZ-MID-67-WPR2-151159 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0265 | PS4 - PUMP VSD AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  | 10 | TZ-MID-67-WPR2-151152 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing | 2026-02-07 08:26 | PS4-63-01 |  |  | Earthing System | E | Closed | PS4 - Milestone A | TM-00039 | sridhar, muthu
T-00039-0266 | PS4 - TURNSTILE GATE AND OFFICE BUILDING AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151147 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0267 | PS4 - UTILITY AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151149 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0268 | PS4 - UTILITY/FIRE WATER STORAGE TANK AREA_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151150 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0269 | PS4-82-OB-0001_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing for Office and Facilities building | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-CPP1-150005 | PS4 - TZA - PS4 - Tanzania | PS4-63-02 - Electrical Earthing - Office and Facilities building |  | PS4-63-02 |  |  | Earthing System | E | To be completed | PS4 - Milestone I | TM-00039
T-00039-0270 | PS4-82-OB-0005_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing for Guard House | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151183 | PS4 - TZA - PS4 - Tanzania | PS4-63-06 - Electrical Earthing - Guard House |  | PS4-63-06 |  |  | Earthing System | E | To be completed | PS4 - Milestone I | TM-00039
T-00039-0271 | PS4-82-OB-0009A_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing for Guard Hut A | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-CPP1-150012 | PS4 - TZA - PS4 - Tanzania | PS4-63-05 - Electrical Earthing - Guard Hut A & B |  | PS4-63-05 |  |  | Earthing System | E | To be completed | PS4 - Milestone I | TM-00039
T-00039-0272 | PS4-82-OB-0009B_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing for Guard Hut B | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-CPP1-150019 | PS4 - TZA - PS4 - Tanzania | PS4-63-05 - Electrical Earthing - Guard Hut A & B |  | PS4-63-05 |  |  | Earthing System | E | To be completed | PS4 - Milestone I | TM-00039
T-00039-0273 | PS4-84-OB-0001_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing for Workshop & Warehouse | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-CPP1-150026 | PS4 - TZA - PS4 - Tanzania | PS4-63-07 - Electrical Earthing - Workshop & Warehouse |  | PS4-63-07 |  |  | Earthing System | E | To be completed | PS4 - Milestone I | TM-00039
T-00039-0274 | PS4-84-OB-0003_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing for Hazardous Waste Shelter | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151187 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0275 | PS4-84-OB-0004_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing for Non-Hazardous Waste Shelter | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151187 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0276 | PS4-84-OB-0005_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing for Generator Electrical Building | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151185 | PS4 - TZA - PS4 - Tanzania | PS4-63-03 - Electrical Earthing - Generator Building |  | PS4-63-03 |  |  | Earthing System | E | To be completed | PS4 - Milestone B | TM-00039
T-00039-0277 | PS4-84-OB-0006_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing for Chemical Storage Shelter | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151187 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0278 | PS4-84-OB-0007_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing for Chemical Waste Storage Shelter | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151187 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0279 | PS4-86-OB-0001_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing for Closed Drain Drum Shelter | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151189 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0280 | PS4-86-OB-0002_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing for Relief Drain Drum Shelter | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151191 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0281 | PS4-86-OB-0003_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing for Fire Water Pump Shelter | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151193 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00039-0282 | PS4-86-OB-0004_Earthing |  |  |  |  | CPX26 - Earthing system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Earthing for Closed Drain Drum Shelter | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151195 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00039
T-00040-0038 | PS4 - RECEIVER AND LAUNCHER AREA_Lightning |  |  |  |  | CPX28 - Lightning protection system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Lightning | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-151613 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone A | TM-00040
T-00040-0039 | PS4-82-OB-0001_Lightning |  |  |  |  | CPX28 - Lightning protection system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Lightning for Office and Facilities building | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-150006 | PS4 - TZA - PS4 - Tanzania | PS4-63-02 - Electrical Earthing - Office and Facilities building |  | PS4-63-02 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone I | TM-00040
T-00040-0040 | PS4-82-OB-0005_Lightning |  |  |  |  | CPX28 - Lightning protection system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Lightning for Guard House | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-151197 | PS4 - TZA - PS4 - Tanzania | PS4-63-06 - Electrical Earthing - Guard House |  | PS4-63-06 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone I | TM-00040
T-00040-0041 | PS4-82-OB-0009A_Lightning |  |  |  |  | CPX28 - Lightning protection system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Lightning for Guard Hut A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-150013 | PS4 - TZA - PS4 - Tanzania | PS4-63-05 - Electrical Earthing - Guard Hut A & B |  | PS4-63-05 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone I | TM-00040
T-00040-0042 | PS4-82-OB-0009B_Ligthning |  |  |  |  | CPX28 - Lightning protection system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Lightning for Guard Hut B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-150020 | PS4 - TZA - PS4 - Tanzania | PS4-63-05 - Electrical Earthing - Guard Hut A & B |  | PS4-63-05 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone I | TM-00040
T-00040-0043 | PS4-84-OB-0001_Lightning |  |  |  |  | CPX28 - Lightning protection system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Lightning for Workshop & Warehouse | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-150027 | PS4 - TZA - PS4 - Tanzania | PS4-63-07 - Electrical Earthing - Workshop & Warehouse |  | PS4-63-07 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone I | TM-00040
T-00040-0044 | PS4-84-OB-0003_Lightning |  |  |  |  | CPX28 - Lightning protection system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Lightning for Hazardous Waste Shelter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-151199 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone A | TM-00040
T-00040-0045 | PS4-84-OB-0005_Lightning |  |  |  |  | CPX28 - Lightning protection system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Lightning for Generator Electrical Building | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-151198 | PS4 - TZA - PS4 - Tanzania | PS4-63-03 - Electrical Earthing - Generator Building |  | PS4-63-03 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone B | TM-00040
T-00040-0046 | PS4-84-OB-0006_Lightning |  |  |  |  | CPX28 - Lightning protection system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Lightning for Chemical Storage Shelter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-151601 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone A | TM-00040
T-00040-0047 | PS4-84-OB-0007_Lightning |  |  |  |  | CPX28 - Lightning protection system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Lightning for Chemical Waste Storage Shelter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-151601 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone A | TM-00040
T-00040-0048 | PS4-86-OB-0001_Lightning |  |  |  |  | CPX28 - Lightning protection system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Lightning for Closed Drain Drum Shelter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-151603 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone A | TM-00040
T-00040-0049 | PS4-86-OB-0002_Lightning |  |  |  |  | CPX28 - Lightning protection system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Lightning for Relief Drain Drum Shelter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-151604 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone A | TM-00040
T-00040-0050 | PS4-86-OB-0003_Lightning |  |  |  |  | CPX28 - Lightning protection system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Lightning for Fire Water Pump Shelter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-151605 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone A | TM-00040
T-00040-0051 | PS4-86-OB-0004_Lightning |  |  |  |  | CPX28 - Lightning protection system | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Lightning for Closed Drain Drum Shelter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-151606 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone A | TM-00040
T-00041-0023 | PS4-82-OB-0001 |  |  |  |  | CPX29 - MCT cabling | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Office and Facilities building | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-82-05 - Office and Facilities building |  | PS4-82-05 |  |  | MCT Cabling | B | To be completed | PS4 - Milestone I | TM-00041
T-00041-0024 | PS4-82-OB-0005 |  |  |  |  | CPX29 - MCT cabling | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Guard House | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-82-06 - Guard House Building |  | PS4-82-06 |  |  | MCT Cabling | B | To be completed | PS4 - Milestone I | TM-00041
T-00041-0025 | PS4-84-OB-0005 |  |  |  |  | CPX29 - MCT cabling | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Generator Electrical Building | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-84-01 - Generator Building |  | PS4-84-01 |  |  | MCT Cabling | B | To be completed | PS4 - Milestone E | TM-00041
T-00042-0132 | PS4_AREA_COMPLETION_FOR_BUILDING_AREA_NORTH |  |  |  |  | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Area completion | EACOP | CPP AGI |  |  | 2 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-99-01 - Area Completion for Building area |  | PS4-99-01 |  |  | Cable Tray/Ladder | B | To be completed | PS4 - Milestone I | TM-00042
T-00042-0133 | PS4_AREA_COMPLETION_FOR_BUILDING_AREA_NORTH_EAST |  |  |  |  | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Area completion | EACOP | CPP AGI |  |  | 2 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-99-01 - Area Completion for Building area |  | PS4-99-01 |  |  | Cable Tray/Ladder | B | To be completed | PS4 - Milestone I | TM-00042
T-00042-0134 | PS4_AREA_COMPLETION_FOR_BUILDING_AREA_NORTH_WEST |  |  |  |  | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Area completion | EACOP | CPP AGI |  |  | 2 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-99-01 - Area Completion for Building area |  | PS4-99-01 |  |  | Cable Tray/Ladder | B | To be completed | PS4 - Milestone I | TM-00042
T-00042-0135 | PS4_AREA_COMPLETION_FOR_CFO_AREA |  |  |  |  | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Area completion | EACOP | CPP AGI |  |  | 2 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-99-05 - Area Completion for CFO area |  | PS4-99-05 |  |  | Cable Tray/Ladder | B | To be completed | PS4 - Milestone I | TM-00042
T-00042-0136 | PS4_AREA_COMPLETION_FOR_POWER_DISTRIBUTION_AREA |  |  |  |  | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Area completion | EACOP | CPP AGI |  |  | 2 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-99-03 - Area Completion for Power Distribution area |  | PS4-99-03 |  |  | Cable Tray/Ladder | B | To be completed | PS4 - Milestone I | TM-00042
T-00042-0137 | PS4_AREA_COMPLETION_FOR_POWER_GENERATION_AREA |  |  |  |  | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Area completion | EACOP | CPP AGI |  |  | 2 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-99-06 - Area Completion for Power Generation area |  | PS4-99-06 |  |  | Cable Tray/Ladder | B | To be completed | PS4 - Milestone I | TM-00042
T-00042-0138 | PS4_AREA_COMPLETION_FOR_PROCESS_AREA |  |  |  |  | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Area completion | EACOP | CPP AGI |  |  | 2 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-99-04 - Area Completion for Process area |  | PS4-99-04 |  |  | Cable Tray/Ladder | B | To be completed | PS4 - Milestone I | TM-00042
T-00042-0139 | PS4_AREA_COMPLETION_FOR_PROCESS_AREA_NORTH |  |  |  |  | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Area completion | EACOP | CPP AGI |  |  | 2 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-99-04 - Area Completion for Process area |  | PS4-99-04 |  |  | Cable Tray/Ladder | B | To be completed | PS4 - Milestone I | TM-00042
T-00042-0140 | PS4_AREA_COMPLETION_FOR_PROCESS_AREA_SOUTH |  |  |  |  | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Area completion | EACOP | CPP AGI |  |  | 2 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-99-04 - Area Completion for Process area |  | PS4-99-04 |  |  | Cable Tray/Ladder | B | To be completed | PS4 - Milestone I | TM-00042
T-00042-0141 | PS4_AREA_COMPLETION_FOR_UTILITY_AREA |  |  |  |  | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Area completion | EACOP | CPP AGI |  |  | 2 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-99-02 - Area Completion for Utility area |  | PS4-99-02 |  |  | Cable Tray/Ladder | B | To be completed | PS4 - Milestone I | TM-00042
T-00042-0164 | PS4-82-OB-0001 |  |  |  |  | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Office and Facilities building | EACOP | CPP AGI |  |  | 2 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-82-05 - Office and Facilities building |  | PS4-82-05 |  |  | Cable Tray/Ladder | B | To be completed | PS4 - Milestone I | TM-00042
T-00042-0165 | PS4-82-OB-0005 |  |  |  |  | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Guard House | EACOP | CPP AGI |  |  | 2 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-82-06 - Guard House Building |  | PS4-82-06 |  |  | Cable Tray/Ladder | B | To be completed | PS4 - Milestone I | TM-00042
T-00042-0166 | PS4-84-OB-0005 |  |  |  |  | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Generator Electrical Building | EACOP | CPP AGI |  |  | 2 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-84-01 - Generator Building |  | PS4-84-01 |  |  | Cable Tray/Ladder | B | To be completed | PS4 - Milestone E | TM-00042
T-00042-0198 | PS4-83-OB-0001_Installation |  |  |  |  | CPX30 - Cable tray / ladder | PCOM - Precommissioning | E | Conformity Check | E - Electrical | EITS Building | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-83-01 - EITS Building | 2026-07-13 06:11 | PS4-83-01 |  |  | Cable Tray/Ladder | M | Closed | PS4 - Milestone A | TM-00042 | sridhar, muthu
T-00043-0043 | PS4-79-BH-0001 |  |  |  |  | CPX31 - Junction and marshalling box | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LLHT High Voltage Power Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) |  | PS4-61-02 |  |  | Junction and Marshalling Box | E | To be completed | PS4 - Milestone G | TM-00043
T-00043-0044 | PS4-79-BH-0002 |  |  |  |  | CPX31 - Junction and marshalling box | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LLHT High Voltage Power Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) |  | PS4-61-02 |  |  | Junction and Marshalling Box | E | To be completed | PS4 - Milestone G | TM-00043
T-00043-0072 | PS4-05-BE-0001 |  |  |  |  | CPX31 - Junction and marshalling box | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Power Junction Box | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | Junction and Marshalling Box | E | To be completed | PS4 - Milestone C | TM-00043
T-00044-0125 | PS4-01-IE-0001A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Foam Package(PS4-01-UV-8700) Pump Control Panel A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-05 - Foam Skid |  | PS4-01-05 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone F | TM-00044
T-00044-0126 | PS4-01-IE-0001B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Foam Package(PS4-01-UV-8700) Pump Control Panel B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-05 - Foam Skid |  | PS4-01-05 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone F | TM-00044
T-00044-0127 | PS4-01-IE-0002A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fire Water Jockey Pump Control Panel A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone C | TM-00044
T-00044-0128 | PS4-01-IE-0002B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fire Water Jockey Pump Control panel B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone C | TM-00044
T-00044-0129 | PS4-01-IE-0009A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fire Water starter pump Local Control Panel A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone C | TM-00044
T-00044-0130 | PS4-01-IE-0009B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fire Water starter pump Local Control Panel B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone C | TM-00044
T-00044-0132 | PS4-05-IE-8100 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Unit Control Panel for Emergency Diesel Generator | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) |  | PS4-05-02 |  |  | Console / Control Panel | E | Submitted | PS4 - Milestone C | TM-00044
T-00044-0133 | PS4-50-IE-0001 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Water Well Submersible Pump Control Panel A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-50-01 - Water Well Submersible Pumps (3100) |  | PS4-50-01 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone I | TM-00044
T-00044-0134 | PS4-50-IE-0002 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Water Well Submersible Pump Control Panel B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-50-02 - Water Well Submersible Pumps (3200) |  | PS4-50-02 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone I | TM-00044
T-00044-0135 | PS4-60-IE-0002A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Local Display Panel (LDP) for Generator Set A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-03 05:49 | PS4-60-01 |  |  | Console / Control Panel | E | Closed | PS4 - Milestone B | TM-00044 | sridhar, muthu
T-00044-0136 | PS4-60-IE-0002B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Local Display Panel (LDP) for Generator Set B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-03 06:02 | PS4-60-04 |  |  | Console / Control Panel | E | Closed | PS4 - Milestone B | TM-00044 | sridhar, muthu
T-00044-0137 | PS4-60-IE-0002C |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Local Display Panel (LDP) for Generator Set C | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone D | TM-00044
T-00044-0138 | PS4-60-IE-0002D |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Local Display Panel (LDP) for Generator Set D | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone D | TM-00044
T-00044-0139 | PS4-60-IE-0002E |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Local Display Panel (LDP) for Generator Set E | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone D | TM-00044
T-00044-0140 | PS4-60-IE-0002F |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Local Display Panel (LDP) for Generator Set F | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone D | TM-00044
T-00044-0141 | PS4-60-IE-0002G |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Local Display Panel (LDP) for Generator Set G | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone E | TM-00044
T-00044-0142 | PS4-60-IE-0003A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Generator control panel for generator set- 1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-21 13:35 | PS4-60-02 |  |  | Console / Control Panel | E | Closed | PS4 - Milestone B | TM-00044 | sridhar, muthu
T-00044-0143 | PS4-60-IE-0003B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Generator control panel for generator set- 2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-21 13:36 | PS4-60-05 |  |  | Console / Control Panel | E | Closed | PS4 - Milestone B | TM-00044 | sridhar, muthu
T-00044-0144 | PS4-60-IE-0003C |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Generator control panel for generator set- 3 (C) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone D | TM-00044
T-00044-0145 | PS4-60-IE-0003D |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Generator control panel for generator set- 4 (D) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone D | TM-00044
T-00044-0146 | PS4-60-IE-0003E |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Generator control panel for generator set- 5 (E) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone D | TM-00044
T-00044-0147 | PS4-60-IE-0003F |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Generator control panel for generator set- 6 (F) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone D | TM-00044
T-00044-0148 | PS4-60-IE-0003G |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Generator control panel for generator set- 7 (G) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone E | TM-00044
T-00044-0149 | PS4-60-IE-0004 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Master Control Panel | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-15 18:24 | PS4-60-22 |  |  | Console / Control Panel | E | Closed | PS4 - Milestone B | TM-00044 | sridhar, muthu
T-00044-0150 | PS4-60-IH-0001A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Generator A Auxiliary MCC | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-07-21 13:37 | PS4-60-03 |  |  | Console / Control Panel | E | Closed | PS4 - Milestone B | TM-00044 | sridhar, muthu
T-00044-0151 | PS4-60-IH-0001B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Generator B Auxiliary MCC | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-07-21 13:38 | PS4-60-06 |  |  | Console / Control Panel | E | Closed | PS4 - Milestone B | TM-00044 | sridhar, muthu
T-00044-0152 | PS4-60-IH-0001C |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Generator C Auxiliary MCC | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS4-60-09 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone D | TM-00044
T-00044-0153 | PS4-60-IH-0001D |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Generator D Auxiliary MCC | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS4-60-12 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone D | TM-00044
T-00044-0154 | PS4-60-IH-0001E |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Generator E Auxiliary MCC | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS4-60-15 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone D | TM-00044
T-00044-0155 | PS4-60-IH-0001F |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Generator F Auxiliary MCC | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS4-60-18 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone D | TM-00044
T-00044-0156 | PS4-60-IH-0001G |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Generator G Auxiliary MCC | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS4-60-21 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone E | TM-00044
T-00044-0157 | PS4-60-IH-0002 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Generator Common MCC - Feeder A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-15 18:25 | PS4-60-22 |  |  | Console / Control Panel | E | Closed | PS4 - Milestone B | TM-00044 | sridhar, muthu
T-00044-0158 | PS4-60-IN-0002A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-07-03 06:05 | PS4-60-57 |  |  | Console / Control Panel | E | Closed | PS4 - Milestone B | TM-00044 | sridhar, muthu
T-00044-0159 | PS4-60-IN-0002B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-07-03 06:09 | PS4-60-59 |  |  | Console / Control Panel | E | Closed | PS4 - Milestone B | TM-00044 | sridhar, muthu
T-00044-0160 | PS4-60-IN-0002C |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone D | TM-00044
T-00044-0161 | PS4-60-IN-0002D |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone D | TM-00044
T-00044-0162 | PS4-60-IN-0002E |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) |  | PS4-60-65 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone D | TM-00044
T-00044-0163 | PS4-60-IN-0002F |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) |  | PS4-60-67 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone D | TM-00044
T-00044-0164 | PS4-60-IN-0002G |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) |  | PS4-60-69 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone E | TM-00044
T-00044-0165 | PS4-61-IH-0004 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | HVAC MCC - Generator Building | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-07-15 18:54 | PS4-09-03 |  |  | Console / Control Panel | E | Closed | PS4 - Milestone D | TM-00044 | sridhar, muthu
T-00044-0166 | PS4-61-IH-0004A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | HVAC MCC - Power Generator Building Feeder A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone D | TM-00044
T-00044-0167 | PS4-61-IH-0004B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | HVAC MCC - Power Generator Building Feeder B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone D | TM-00044
T-00044-0168 | PS4-62-IE-0001 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Lighting Control panel 1 - Pump Station 4 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone G | TM-00044
T-00044-0169 | PS4-62-IE-0002 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Lighting Control panel 2 - Pump Station 4 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone G | TM-00044
T-00044-0170 | PS4-71-IN-0001 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | DFO- SEPARATOR CONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) | 2026-07-15 18:51 | PS4-71-19 |  |  | Console / Control Panel | E | Closed | PS4 - Milestone F | TM-00044 | sridhar, muthu
T-00044-0171 | PS4-71-IN-0002 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CFO-PRE PRESSURE CONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-09 - CFO Pre-Pressure Module (UCP) | 2026-07-15 18:41 | PS4-71-09 |  |  | Console / Control Panel | E | Closed | PS4 - Milestone H | TM-00044 | sridhar, muthu
T-00044-0172 | PS4-71-IN-0003 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | DFO- PRE PRESSURE CONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-07-15 18:43 | PS4-71-23 |  |  | Console / Control Panel | E | Closed | PS4 - Milestone B | TM-00044 | sridhar, muthu
T-00044-0173 | PS4-71-IN-0004A |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRO- SEPARATOR CONTROL PANEL-1 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-15 18:46 | PS4-71-07 |  |  | Console / Control Panel | E | Closed | PS4 - Milestone H | TM-00044 | sridhar, muthu
T-00044-0174 | PS4-71-IN-0004B |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRO- SEPARATOR CONTROL PANEL-2 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-15 18:48 | PS4-71-07 |  |  | Console / Control Panel | E | Closed | PS4 - Milestone H | TM-00044 | sridhar, muthu
T-00044-0264 | PS4-09-LB-0008 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | HVAC UNIT CONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone D | TM-00044
T-00044-0265 | PS4-61-IH-0004C |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LOCAL STARTER PANEL | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone D | TM-00044
T-00044-0266 | PS4-61-IH-0004D |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LOCAL STARTER PANEL | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone D | TM-00044
T-00044-0278 | PS4-09-LB-7001 |  |  |  |  | CPX32 - Console / control panel | PCOM - Precommissioning | E | Conformity Check | E - Electrical | HVAC UCP - Guard House | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-02 - HVAC for Guard House |  | PS4-09-02 |  |  | Console / Control Panel | E | To be completed | PS4 - Milestone I | TM-00044
T-00045-0004 | PS4-53-TR-4100 |  |  |  |  | CPX33 - Cathodic protection | PCOM - Precommissioning | E | Conformity Check | E - Electrical | UTILITY WATER / FIRE WATER STORAGE TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-67-FZC2-180013 | PS4 - TZA - PS4 - Tanzania | PS4-53-01 - Utility Water / Storage Tank |  | PS4-53-01 |  |  | Cathodic Protection | P | To be completed | PS4 - Milestone C | TM-00045
T-00045-0005 | PS4-71-TR-4100 |  |  |  |  | CPX33 - Cathodic protection | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE FUEL OIL STORAGE TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-67-FZC2-180096 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Cathodic Protection | P | To be completed | PS4 - Milestone H | TM-00045
T-00045-0006 | PS4-71-TR-4200 |  |  |  |  | CPX33 - Cathodic protection | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE FUEL OIL SERVICE TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-67-FZC2-180095 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Cathodic Protection | P | To be completed | PS4 - Milestone H | TM-00045
T-00045-0007 | PS4-71-TR-4400 |  |  |  |  | CPX33 - Cathodic protection | PCOM - Precommissioning | E | Conformity Check | E - Electrical | DIESEL FUEL STORAGE TANK | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-67-FZC2-180029 | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank |  | PS4-71-15 |  |  | Cathodic Protection | P | To be completed | PS4 - Milestone F | TM-00045
T-00046-0408 | PS4-60-UR-8100A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION PACKAGE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135100 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 12:06 | PS4-60-01 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0409 | PS4-60-UR-8100B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION PACKAGE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135103 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 12:09 | PS4-60-04 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0410 | PS4-60-UR-8100C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION PACKAGE C | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135106 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0411 | PS4-60-UR-8100D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION PACKAGE D | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135109 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0412 | PS4-60-UR-8100E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION PACKAGE E | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135112 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0413 | PS4-60-UR-8100F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION PACKAGE F | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135115 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0414 | PS4-60-UR-8100G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION PACKAGE G | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135118 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00046
T-00046-0415 | PS4-05-UR-8100 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | EMERGENCY DIESEL ENGINE GENERATOR PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135204 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | Package | M | To be completed | PS4 - Milestone C | TM-00046
T-00046-0416 | PS4-71-UZ-6200 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | DIESEL FUEL DISPENSER STATION | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135200 | PS4 - TZA - PS4 - Tanzania | PS4-71-14 - Diesel Fuel Transfer and Dispensing Station |  | PS4-71-14 |  |  | Package | M | To be completed | PS4 - Milestone F | TM-00046
T-00046-0417 | PS4-60-UA-5100 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | COMPRESSOR AIR STARTING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135128 | PS4 - TZA - PS4 - Tanzania | PS4-60-27 - Compressed Air Starting Skid | 2026-07-08 17:34 | PS4-60-27 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0418 | PS4-60-UO-81100A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135124 | PS4 - TZA - PS4 - Tanzania | PS4-60-49 - Lube Oil Separator Module PS4-60-UO-81100A | 2026-07-05 12:36 | PS4-60-49 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0419 | PS4-60-UO-81100B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135124 | PS4 - TZA - PS4 - Tanzania | PS4-60-50 - Lube Oil Separator Module PS4-60-UO-81100B | 2026-07-05 12:33 | PS4-60-50 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0420 | PS4-60-UO-81100C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135124 | PS4 - TZA - PS4 - Tanzania | PS4-60-51 - Lube Oil Separator Module PS4-60-UO-81100C |  | PS4-60-51 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0421 | PS4-60-UO-81100D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135124 | PS4 - TZA - PS4 - Tanzania | PS4-60-52 - Lube Oil Separator Module PS4-60-UO-81100D |  | PS4-60-52 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0422 | PS4-60-UO-81100E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135124 | PS4 - TZA - PS4 - Tanzania | PS4-60-53 - Lube Oil Separator Module PS4-60-UO-81100E |  | PS4-60-53 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0423 | PS4-60-UO-81100F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135124 | PS4 - TZA - PS4 - Tanzania | PS4-60-54 - Lube Oil Separator Module PS4-60-UO-81100F |  | PS4-60-54 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0424 | PS4-60-UO-81100G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135124 | PS4 - TZA - PS4 - Tanzania | PS4-60-55 - Lube Oil Separator Module PS4-60-UO-81100G |  | PS4-60-55 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00046
T-00046-0425 | PS4-60-UZ-8200A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-35 - Injector Tip Cooling Module A | 2026-06-24 08:27 | PS4-60-35 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0426 | PS4-60-UZ-8200B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-36 - Injector Tip Cooling Module B | 2026-06-24 08:28 | PS4-60-36 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0427 | PS4-60-UZ-8200C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-37 - Injector Tip Cooling Module C |  | PS4-60-37 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0428 | PS4-60-UZ-8200D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-38 - Injector Tip Cooling Module D |  | PS4-60-38 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0429 | PS4-60-UZ-8200E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-39 - Injector Tip Cooling Module E |  | PS4-60-39 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0430 | PS4-60-UZ-8200F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-40 - Injector Tip Cooling Module F |  | PS4-60-40 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0431 | PS4-60-VS-9100A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135130 | PS4 - TZA - PS4 - Tanzania | PS4-60-42 - Oil Mist Separator Skid PS4-60-VS-9100A | 2026-07-10 05:57 | PS4-60-42 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0432 | PS4-60-VS-9100B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135130 | PS4 - TZA - PS4 - Tanzania | PS4-60-43 - Oil Mist Separator Skid PS4-60-VS-9100B | 2026-07-10 05:59 | PS4-60-43 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0433 | PS4-60-VS-9100C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135130 | PS4 - TZA - PS4 - Tanzania | PS4-60-44 - Oil Mist Separator Skid PS4-60-VS-9100C |  | PS4-60-44 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0434 | PS4-60-VS-9100D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135130 | PS4 - TZA - PS4 - Tanzania | PS4-60-45 - Oil Mist Separator Skid PS4-60-VS-9100D |  | PS4-60-45 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0435 | PS4-60-VS-9100E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135130 | PS4 - TZA - PS4 - Tanzania | PS4-60-46 - Oil Mist Separator Skid PS4-60-VS-9100E |  | PS4-60-46 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0436 | PS4-60-VS-9100F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135130 | PS4 - TZA - PS4 - Tanzania | PS4-60-47 - Oil Mist Separator Skid PS4-60-VS-9100F |  | PS4-60-47 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0437 | PS4-60-VS-9100G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135130 | PS4 - TZA - PS4 - Tanzania | PS4-60-48 - Oil Mist Separator Skid PS4-60-VS-9100G |  | PS4-60-48 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00046
T-00046-0438 | PS4-71-UZ-6500 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | DIESEL FUEL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135009 | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Package | M | To be completed | PS4 - Milestone F | TM-00046
T-00046-0439 | PS4-71-UZ-6800A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE FUEL SEPARATOR MODULE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135002 | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Package | M | To be completed | PS4 - Milestone H | TM-00046
T-00046-0440 | PS4-71-UZ-6800B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE FUEL SEPARATOR MODULE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135002 | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Package | M | To be completed | PS4 - Milestone H | TM-00046
T-00046-0441 | PS4-01-UK-6100 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | DELUGE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-125904 | PS4 - TZA - PS4 - Tanzania | PS4-01-08 - PS4 Deluge Valve Skid (PS4-01-UK-6100) |  | PS4-01-08 |  |  | Package | M | To be completed | PS4 - Milestone F | TM-00046
T-00046-0442 | PS4-01-UV-8700 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | FOAM SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-125900 | PS4 - TZA - PS4 - Tanzania | PS4-01-05 - Foam Skid |  | PS4-01-05 |  |  | Package | M | To be completed | PS4 - Milestone F | TM-00046
T-00046-0443 | PS4-01-UZ-6900 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | WATER MIST FIRE PROTECTION PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-125922 | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00046
T-00046-0444 | PS4-53-UT-8100 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | WATER PRE-TREATMENT PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135500 | PS4 - TZA - PS4 - Tanzania | PS4-50-03 - Water Pre-Treatment Package |  | PS4-50-03 |  |  | Package | M | To be completed | PS4 - Milestone F | TM-00046
T-00046-0445 | PS4-53-UT-8200 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | WATER TREATMENT/ PURIFICATION PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135502 | PS4 - TZA - PS4 - Tanzania | PS4-53-04 - Water Treatment Purification Package |  | PS4-53-04 |  |  | Package | M | To be completed | PS4 - Milestone F | TM-00046
T-00046-0446 | PS4-60-EA-2100A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-06-24 08:29 | PS4-60-70 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0447 | PS4-60-EA-2100B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-06-24 08:32 | PS4-60-70 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0448 | PS4-60-EA-21100A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CW AIR FIN COOLER - DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135100 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 12:14 | PS4-60-01 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0449 | PS4-60-EA-21100B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CW AIR FIN COOLER - DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135103 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 12:17 | PS4-60-04 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0450 | PS4-60-EA-21100C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CW AIR FIN COOLER - DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135106 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0451 | PS4-60-EA-21100D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CW AIR FIN COOLER - DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135109 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0452 | PS4-60-EA-21100E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CW AIR FIN COOLER - DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135112 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0453 | PS4-60-EA-21100F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CW AIR FIN COOLER - DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135115 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0454 | PS4-60-EA-21100G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CW AIR FIN COOLER - DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135118 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00046
T-00046-0455 | PS4-60-EA-21200A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CW AIR FIN COOLER - NON-DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135100 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 12:19 | PS4-60-01 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0456 | PS4-60-EA-21200B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CW AIR FIN COOLER - NON-DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135103 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 12:21 | PS4-60-04 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0457 | PS4-60-EA-21200C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CW AIR FIN COOLER - NON-DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135106 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0458 | PS4-60-EA-21200D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CW AIR FIN COOLER - NON-DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135109 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0459 | PS4-60-EA-21200E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CW AIR FIN COOLER - NON-DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135112 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0460 | PS4-60-EA-21200F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CW AIR FIN COOLER - NON-DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135115 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0461 | PS4-60-EA-21200G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CW AIR FIN COOLER - NON-DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135118 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00046
T-00046-0462 | PS4-60-EA-2200A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-06-24 08:34 | PS4-60-71 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0463 | PS4-60-EA-2200B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-06-24 08:36 | PS4-60-71 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0464 | PS4-60-EA-2300A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system |  | PS4-60-72 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0465 | PS4-60-EA-2300B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system |  | PS4-60-72 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0466 | PS4-60-EA-2400A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system |  | PS4-60-73 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0467 | PS4-60-EA-2400B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system |  | PS4-60-73 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0468 | PS4-60-EA-2500A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0469 | PS4-60-EA-2500B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0470 | PS4-60-EA-2600A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0471 | PS4-60-EA-2600B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0472 | PS4-60-EA-2700A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00046
T-00046-0473 | PS4-60-EA-2700B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00046
T-00046-0474 | PS4-60-EA-2800A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-35 - Injector Tip Cooling Module A | 2026-06-24 08:42 | PS4-60-35 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0475 | PS4-60-EA-2800B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-36 - Injector Tip Cooling Module B | 2026-06-24 08:46 | PS4-60-36 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0476 | PS4-60-EA-2800C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-37 - Injector Tip Cooling Module C |  | PS4-60-37 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0477 | PS4-60-EA-2800D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-38 - Injector Tip Cooling Module D |  | PS4-60-38 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0478 | PS4-60-EA-2800E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-39 - Injector Tip Cooling Module E |  | PS4-60-39 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0479 | PS4-60-EA-2800F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-40 - Injector Tip Cooling Module F |  | PS4-60-40 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0480 | PS4-60-EA-2800G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-41 - Injector Tip Cooling Module G |  | PS4-60-41 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00046
T-00046-0481 | PS4-60-EA-2900A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | AIR BLAST COOLER 33KW CAPACITY - COF MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A | 2026-07-21 12:23 | PS4-60-56 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0482 | PS4-60-EA-2900B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | AIR BLAST COOLER 33KW CAPACITY - COF MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B | 2026-07-21 12:26 | PS4-60-58 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0483 | PS4-60-EA-2900C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | AIR BLAST COOLER 33KW CAPACITY - COF MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C |  | PS4-60-60 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0484 | PS4-60-EA-2900D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | AIR BLAST COOLER 33KW CAPACITY - COF MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D |  | PS4-60-62 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0485 | PS4-60-EA-2900E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | AIR BLAST COOLER 33KW CAPACITY - COF MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135138 | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E |  | PS4-60-64 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0486 | PS4-60-EA-2900F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | AIR BLAST COOLER 33KW CAPACITY - COF MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135138 | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F |  | PS4-60-66 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0487 | PS4-60-EA-2900G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | AIR BLAST COOLER 33KW CAPACITY - COF MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135138 | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G |  | PS4-60-68 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00046
T-00046-0488 | PS4-60-TCV-0001A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135136 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-06-24 08:48 | PS4-60-70 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0489 | PS4-60-TCV-0001B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135136 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-06-24 08:51 | PS4-60-71 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0490 | PS4-60-TCV-0001C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135136 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system |  | PS4-60-72 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0491 | PS4-60-TCV-0001D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135136 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system |  | PS4-60-73 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0492 | PS4-60-TCV-0001E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135136 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0493 | PS4-60-TCV-0001F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135136 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0494 | PS4-60-TCV-0001G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135136 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00046
T-00046-0495 | PS4-60-TCV-0002A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135137 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-06-24 08:55 | PS4-60-70 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0496 | PS4-60-TCV-0002B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135137 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-06-24 08:57 | PS4-60-71 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0497 | PS4-60-TCV-0002C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135137 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system |  | PS4-60-72 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0498 | PS4-60-TCV-0002D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135137 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system |  | PS4-60-73 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0499 | PS4-60-TCV-0002E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135137 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0500 | PS4-60-TCV-0002F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135137 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0501 | PS4-60-TCV-0002G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135137 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00046
T-00046-0502 | PS4-60-UA-5200 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INSTRUMENT AIR COMPRESSOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135127 | PS4 - TZA - PS4 - Tanzania | PS4-60-26 - Instrument Air Compressor Skid | 2026-07-21 12:28 | PS4-60-26 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0503 | PS4-60-UR-8200A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135100 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 12:32 | PS4-60-01 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0504 | PS4-60-UR-8200B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135103 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 12:34 | PS4-60-04 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0505 | PS4-60-UR-8200C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135106 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0506 | PS4-60-UR-8200D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135109 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0507 | PS4-60-UR-8200E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135112 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0508 | PS4-60-UR-8200F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135115 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0509 | PS4-60-UR-8200G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135118 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00046
T-00046-0510 | PS4-60-UZ-8200G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-41 - Injector Tip Cooling Module G |  | PS4-60-41 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00046
T-00046-0511 | PS4-60-UZ-8900A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A | 2026-07-21 12:36 | PS4-60-56 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0512 | PS4-60-UZ-8900B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B | 2026-07-21 12:39 | PS4-60-58 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0513 | PS4-60-UZ-8900C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C |  | PS4-60-60 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0514 | PS4-60-UZ-8900D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D |  | PS4-60-62 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0515 | PS4-60-UZ-8900E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135138 | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E |  | PS4-60-64 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0516 | PS4-60-UZ-8900F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135138 | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F |  | PS4-60-66 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0517 | PS4-60-UZ-8900G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135138 | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G |  | PS4-60-68 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00046
T-00046-0518 | PS4-71-UN-7200 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE FUEL OIL ALLOCATION METERING PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135010 | PS4 - TZA - PS4 - Tanzania | PS4-71-02 - CFO Allocation Metering Package |  | PS4-71-02 |  |  | Package | M | To be completed | PS4 - Milestone H | TM-00046
T-00046-0519 | PS4-71-UZ-6400 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CRUDE FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135004 | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module |  | PS4-71-08 |  |  | Package | M | To be completed | PS4 - Milestone H | TM-00046
T-00046-0520 | PS4-71-UZ-6700 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | DIESEL FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135126 | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-21 12:41 | PS4-71-22 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0521 | PS4-74-UB-5100 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | NITROGEN GENERATION PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135800 | PS4 - TZA - PS4 - Tanzania | PS4-74-01 - N2 Generation Skid |  | PS4-74-01 |  |  | Package | M | To be completed | PS4 - Milestone F | TM-00046
T-00046-0522 | PS4-75-UI-6100 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | BIOCIDE INJECTION PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135300 | PS4 - TZA - PS4 - Tanzania | PS4-75-02 - Biocide Injection Package |  | PS4-75-02 |  |  | Package | M | To be completed | PS4 - Milestone G | TM-00046
T-00046-0523 | PS4-75-UI-6200 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | DRA PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135300 | PS4 - TZA - PS4 - Tanzania | PS4-75-01 - DRA Injection Package |  | PS4-75-01 |  |  | Package | M | To be completed | PS4 - Milestone G | TM-00046
T-00046-0524 | PS4-75-UI-6300 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | CORROSION INHIBITOR PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135300 | PS4 - TZA - PS4 - Tanzania | PS4-75-03 - Corrosion Inhibitor Injection Package |  | PS4-75-03 |  |  | Package | M | To be completed | PS4 - Milestone G | TM-00046
T-00046-0525 | PS4-77-UZ-8200 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | WATER DEIONIZATION PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135502 | PS4 - TZA - PS4 - Tanzania | PS4-53-03 - Water Softener Package |  | PS4-53-03 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00046
T-00046-0526 | PS4-82-UZ-8100 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | SEWAGE TREATMENT PLANT PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135601 | PS4 - TZA - PS4 - Tanzania | PS4-82-02 - Sewage Treatment Plant Package |  | PS4-82-02 |  |  | Package | M | To be completed | PS4 - Milestone I | TM-00046
T-00046-0539 | PS4-83-EHO-0001A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | VSD E-HOUSE | EACOP | CPP AGI |  |  | 20 |  | 20 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Package | E | To be completed | PS4 - Milestone H | TM-00046
T-00046-0540 | PS4-83-EHO-0001B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | VSD E-HOUSE | EACOP | CPP AGI |  |  | 20 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Package | E | To be completed | PS4 - Milestone H | TM-00046
T-00046-0541 | PS4-83-EHO-0001C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | VSD E-HOUSE | EACOP | CPP AGI |  |  | 20 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Package | E | To be completed | PS4 - Milestone H | TM-00046
T-00046-0548 | PS4-01-UZ-610 |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Fire suppression skid | EACOP | CPP AGI |  |  | 20 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00046
T-00046-0564 | PS4-60-UR-8300A |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  | 20 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-35 - Injector Tip Cooling Module A | 2026-06-24 08:59 | PS4-60-35 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0565 | PS4-60-UR-8300B |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  | 20 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-36 - Injector Tip Cooling Module B | 2026-06-24 09:02 | PS4-60-36 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00046 | sridhar, muthu
T-00046-0566 | PS4-60-UR-8300C |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  | 20 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-37 - Injector Tip Cooling Module C |  | PS4-60-37 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0567 | PS4-60-UR-8300D |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  | 20 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-38 - Injector Tip Cooling Module D |  | PS4-60-38 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0568 | PS4-60-UR-8300E |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  | 20 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-39 - Injector Tip Cooling Module E |  | PS4-60-39 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0569 | PS4-60-UR-8300F |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  | 20 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-40 - Injector Tip Cooling Module F |  | PS4-60-40 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00046
T-00046-0570 | PS4-60-UR-8300G |  |  |  |  | CZX01E - Package | PCOM - Precommissioning | E | Conformity Check | E - Electrical | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  | 20 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-41 - Injector Tip Cooling Module G |  | PS4-60-41 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00046
T-00064-0404 | PS4-01-RAB-61001A |  |  |  |  | CJX00 - Miscellaneous | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DISCHARGE SOUNDER & BEACON | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SAN1-120001 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Miscellaneous | I | To be completed | PS4 - Milestone E | TM-00064
T-00064-0405 | PS4-01-RAB-61001B |  |  |  |  | CJX00 - Miscellaneous | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRE-DISCHARGE SOUNDER & BEACON | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SAN1-120001 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Miscellaneous | I | To be completed | PS4 - Milestone E | TM-00064
T-00064-0406 | PS4-01-RAB-61002A |  |  |  |  | CJX00 - Miscellaneous | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DISCHARGE SOUNDER & BEACON | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SAN1-120001 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Miscellaneous | I | To be completed | PS4 - Milestone E | TM-00064
T-00064-0407 | PS4-01-RAB-61002B |  |  |  |  | CJX00 - Miscellaneous | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRE-DISCHARGE SOUNDER & BEACON | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SAN1-120001 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Miscellaneous | I | To be completed | PS4 - Milestone E | TM-00064
T-00064-0408 | PS4-01-RAB-61003A |  |  |  |  | CJX00 - Miscellaneous | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DISCHARGE SOUNDER & BEACON | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SAN1-120001 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Miscellaneous | I | To be completed | PS4 - Milestone E | TM-00064
T-00064-0409 | PS4-01-RAB-61003B |  |  |  |  | CJX00 - Miscellaneous | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRE-DISCHARGE SOUNDER & BEACON | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SAN1-120001 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Miscellaneous | I | To be completed | PS4 - Milestone E | TM-00064
T-00064-0410 | PS4-01-RAB-61004A |  |  |  |  | CJX00 - Miscellaneous | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DISCHARGE SOUNDER & BEACON | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SAN1-120001 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Miscellaneous | I | To be completed | PS4 - Milestone E | TM-00064
T-00064-0411 | PS4-01-RAB-61004B |  |  |  |  | CJX00 - Miscellaneous | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRE-DISCHARGE SOUNDER & BEACON | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SAN1-120001 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Miscellaneous | I | To be completed | PS4 - Milestone E | TM-00064
T-00064-0422 | PS4-03-RAB-B402 |  |  |  |  | CJX00 - Miscellaneous | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Audible and Visual alarm | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Miscellaneous | I | To be completed | PS4 - Milestone I | TM-00064
T-00064-0423 | PS4-03-RAB-B902 |  |  |  |  | CJX00 - Miscellaneous | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Audible and Visual alarm | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Miscellaneous | I | To be completed | PS4 - Milestone I | TM-00064
T-00064-0424 | PS4-03-RAB-W503 |  |  |  |  | CJX00 - Miscellaneous | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Audible and Visual alarm | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Miscellaneous | I | To be completed | PS4 - Milestone I | TM-00064
T-00065-0145 | PS4-25-PSV-1103 |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00065
T-00065-0146 | PS4-25-PSV-1203 |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00065
T-00065-0147 | PS4-28-PRV-0008 |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135401 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Relief Valve | I | To be completed | PS4 - Milestone G | TM-00065
T-00065-0148 | PS4-28-PRV-0040 |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135401 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Relief Valve | I | To be completed | PS4 - Milestone G | TM-00065
T-00065-0149 | PS4-28-PRV-0046A |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135405 | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00065
T-00065-0150 | PS4-28-PRV-0046B |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135406 | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00065
T-00065-0151 | PS4-28-PRV-0046C |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135407 | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00065
T-00065-0152 | PS4-28-PRV-0047A |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135405 | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00065
T-00065-0153 | PS4-28-PRV-0047B |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135406 | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00065
T-00065-0154 | PS4-28-PRV-0047C |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135407 | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00065
T-00065-0155 | PS4-28-PRV-0054 |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135404 | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Relief Valve | I | To be completed | PS4 - Milestone E | TM-00065
T-00065-0156 | PS4-28-PRV-0055 |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135404 | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Relief Valve | I | To be completed | PS4 - Milestone E | TM-00065
T-00065-0157 | PS4-28-PSV-0044 |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135401 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Relief Valve | I | To be completed | PS4 - Milestone G | TM-00065
T-00065-0158 | PS4-28-PSV-0061 |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135404 | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Relief Valve | I | To be completed | PS4 - Milestone E | TM-00065
T-00065-0159 | PS4-28-PSV-0064A |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135405 | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00065
T-00065-0160 | PS4-28-PSV-0064B |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135406 | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00065
T-00065-0161 | PS4-28-PSV-0064C |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135407 | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00065
T-00065-0162 | PS4-28-PSV-3901A |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-134009 | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00065
T-00065-0163 | PS4-28-PSV-3901B |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-134009 | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00065
T-00065-0164 | PS4-50-PSV-0004A |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135500 | PS4 - TZA - PS4 - Tanzania | PS4-50-01 - Water Well Submersible Pumps (3100) |  | PS4-50-01 |  |  | Relief Valve | I | To be completed | PS4 - Milestone I | TM-00065
T-00065-0165 | PS4-50-PSV-0004B |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135500 | PS4 - TZA - PS4 - Tanzania | PS4-50-02 - Water Well Submersible Pumps (3200) |  | PS4-50-02 |  |  | Relief Valve | I | To be completed | PS4 - Milestone I | TM-00065
T-00065-0166 | PS4-71-PRV-0015 |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135000 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00065
T-00065-0167 | PS4-71-PRV-0016 |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135000 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00065
T-00065-0168 | PS4-71-PRV-0018 |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135003 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00065
T-00065-0169 | PS4-71-PRV-0041 |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135003 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00065
T-00065-0170 | PS4-71-PSV-2403A |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00065
T-00065-0171 | PS4-71-PSV-2403B |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00065
T-00065-0172 | PS4-71-PVSV-4102 |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure / Vacuum Safety Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135000 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00065
T-00065-0173 | PS4-71-PVSV-4202 |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure / Vacuum Safety Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135003 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00065
T-00065-0174 | PS4-74-PSV-0003 |  |  |  |  | CJX03 - Relief valve | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 2 |  |  | TZ-MID-67-WPR2-135800 | PS4 - TZA - PS4 - Tanzania | PS4-74-03 - Nitrogen Receiver |  | PS4-74-03 |  |  | Relief Valve | I | To be completed | PS4 - Milestone F | TM-00065
T-00066-0071 | PS4-01-FCV-0003A |  |  |  |  | CJX06 - Tubing Hydraulic | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | Tubing Hydraulic | I | To be completed | PS4 - Milestone C | TM-00066
T-00066-0072 | PS4-01-FCV-0003B |  |  |  |  | CJX06 - Tubing Hydraulic | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | Tubing Hydraulic | I | To be completed | PS4 - Milestone C | TM-00066
T-00066-0073 | PS4-01-FCV-0004A |  |  |  |  | CJX06 - Tubing Hydraulic | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Tubing Hydraulic | I | To be completed | PS4 - Milestone C | TM-00066
T-00066-0074 | PS4-01-FCV-0004B |  |  |  |  | CJX06 - Tubing Hydraulic | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Tubing Hydraulic | I | To be completed | PS4 - Milestone C | TM-00066
T-00066-0075 | PS4-25-FCV-0003A |  |  |  |  | CJX06 - Tubing Hydraulic | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Tubing Hydraulic | I | To be completed | PS4 - Milestone H | TM-00066
T-00066-0076 | PS4-25-FCV-0003B |  |  |  |  | CJX06 - Tubing Hydraulic | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Tubing Hydraulic | I | To be completed | PS4 - Milestone H | TM-00066
T-00066-0077 | PS4-25-FCV-0003C |  |  |  |  | CJX06 - Tubing Hydraulic | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Tubing Hydraulic | I | To be completed | PS4 - Milestone H | TM-00066
T-00066-0078 | PS4-25-FCV-0004 |  |  |  |  | CJX06 - Tubing Hydraulic | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Tubing Hydraulic | I | To be completed | PS4 - Milestone H | TM-00066
T-00066-0079 | PS4-71-FCV-0018 |  |  |  |  | CJX06 - Tubing Hydraulic | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Tubing Hydraulic | I | To be completed | PS4 - Milestone H | TM-00066
T-00066-0080 | PS4-71-FCV-0019 |  |  |  |  | CJX06 - Tubing Hydraulic | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Tubing Hydraulic | I | To be completed | PS4 - Milestone B | TM-00066
T-00066-0081 | PS4-71-FCV-0020 |  |  |  |  | CJX06 - Tubing Hydraulic | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Tubing Hydraulic | I | To be completed | PS4 - Milestone H | TM-00066
T-00066-0082 | PS4-71-LCV-4101 |  |  |  |  | CJX06 - Tubing Hydraulic | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Level Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Tubing Hydraulic | I | To be completed | PS4 - Milestone H | TM-00066
T-00067-0062 | PS4-03-RMAC-0101 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-0063 | PS4-03-RMAC-0102 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-0064 | PS4-03-RMAC-0103 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-0065 | PS4-03-RMAC-0120 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-0066 | PS4-03-RMAC-0301 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-03 - FZ-03 - Buildings Area |  | PS4-03-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-0067 | PS4-03-RMAC-0401 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone F | TM-00067
T-00067-0068 | PS4-03-RMAC-0402 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone F | TM-00067
T-00067-0069 | PS4-03-RMAC-0613 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-0071 | PS4-03-RMAC-0827 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-0434 | PS4-03-RMAC-0304 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-03 - FZ-03 - Buildings Area |  | PS4-03-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-0435 | PS4-03-RMAC-0706 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area |  | PS4-03-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-0436 | PS4-03-RMAC-0707 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area |  | PS4-03-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-0438 | PS4-03-RMAC-0824 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-0439 | PS4-03-RMAC-0825 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-0440 | PS4-03-RMAC-0834 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-0441 | PS4-03-RMAC-1301 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-13 - FZ-13 - Power Generation Building - Instrument Air Room |  | PS4-03-13 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-0442 | PS4-03-RMAC-1409 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-0662 | PS4-03-NMR-0801 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | WATER MIST RELEASE PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-0663 | PS4-03-NMR-0802 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | WATER MIST RELEASE PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-0664 | PS4-03-NMR-0803 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | WATER MIST RELEASE PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-0665 | PS4-03-NMR-0804 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | WATER MIST RELEASE PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-0674 | PS4-03-RMAC-1410 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-0675 | PS4-03-RMAC-1411 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MANUAL CALL POINT | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-2170 | PS4-03-HS-7002 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Hand Switch | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-03 - FZ-03 - Buildings Area |  | PS4-03-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2171 | PS4-25-ZIT-0001 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Position transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2172 | PS4-25-ZIT-0002 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Position transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2173 | PS4-25-ZS-1101 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Position Switch | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2174 | PS4-25-ZS-1201 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Position Switch | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2175 | PS4-71-HZH-0058 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Position Switch Opened | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135205 | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone B | TM-00067
T-00067-2176 | PS4-71-HZH-0059 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Position Switch Opened | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135009 | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone F | TM-00067
T-00067-2177 | PS4-71-HZL-0058 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Position Switch Closed | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135205 | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone B | TM-00067
T-00067-2178 | PS4-71-HZL-0059 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Position Switch Closed | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135009 | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone F | TM-00067
T-00067-2179 | PS4-01-FIT-0003A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Electromagnetic Flow Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125903 | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone C | TM-00067
T-00067-2180 | PS4-01-FIT-0003B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Electromagnetic Flow Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125903 | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone C | TM-00067
T-00067-2181 | PS4-01-FIT-0004A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Electromagnetic Flow Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125902 | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone C | TM-00067
T-00067-2182 | PS4-01-FIT-0004B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Electromagnetic Flow Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125902 | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone C | TM-00067
T-00067-2183 | PS4-01-LIT-4101A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125903 | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone C | TM-00067
T-00067-2184 | PS4-01-LIT-4101B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125903 | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone C | TM-00067
T-00067-2185 | PS4-01-PDIT-0011A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125902 | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone C | TM-00067
T-00067-2186 | PS4-01-PDIT-0011B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125902 | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone C | TM-00067
T-00067-2187 | PS4-01-PDIT-0012A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125903 | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone C | TM-00067
T-00067-2188 | PS4-01-PDIT-0012B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125903 | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone C | TM-00067
T-00067-2189 | PS4-01-PIT-0010 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125901 | PS4 - TZA - PS4 - Tanzania | PS4-01-07 - Fire Water Ring Main & Distribution |  | PS4-01-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone C | TM-00067
T-00067-2190 | PS4-01-PIT-0013 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125901 | PS4 - TZA - PS4 - Tanzania | PS4-01-07 - Fire Water Ring Main & Distribution |  | PS4-01-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone C | TM-00067
T-00067-2191 | PS4-01-PIT-0014 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125901 | PS4 - TZA - PS4 - Tanzania | PS4-01-07 - Fire Water Ring Main & Distribution |  | PS4-01-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone C | TM-00067
T-00067-2192 | PS4-01-PIT-0015 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125901 | PS4 - TZA - PS4 - Tanzania | PS4-01-07 - Fire Water Ring Main & Distribution |  | PS4-01-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone C | TM-00067
T-00067-2193 | PS4-01-PIT-0016 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125901 | PS4 - TZA - PS4 - Tanzania | PS4-01-07 - Fire Water Ring Main & Distribution |  | PS4-01-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone C | TM-00067
T-00067-2194 | PS4-01-PIT-0017 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125901 | PS4 - TZA - PS4 - Tanzania | PS4-01-07 - Fire Water Ring Main & Distribution |  | PS4-01-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone C | TM-00067
T-00067-2195 | PS4-25-FIT-0001 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Ultrasonic Flow Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2196 | PS4-25-FIT-0003A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Ultrasonic Flow Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134003 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2197 | PS4-25-FIT-0003B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Ultrasonic Flow Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134004 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2198 | PS4-25-FIT-0003C |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Ultrasonic Flow Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134005 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2199 | PS4-25-FIT-0004 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Ultrasonic Flow Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134006 | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2200 | PS4-25-PDIT-0034A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134003 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2201 | PS4-25-PDIT-0034B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134004 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2202 | PS4-25-PDIT-0034C |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134005 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2203 | PS4-25-PDIT-0050 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134006 | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2204 | PS4-25-PIT-0001 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2205 | PS4-25-PIT-0004A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134003 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2206 | PS4-25-PIT-0004B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134004 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2207 | PS4-25-PIT-0004C |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134005 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2208 | PS4-25-PIT-0005A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134003 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2209 | PS4-25-PIT-0005B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134004 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2210 | PS4-25-PIT-0005C |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134005 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2211 | PS4-25-PIT-0007A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134003 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2212 | PS4-25-PIT-0007B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134004 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2213 | PS4-25-PIT-0007C |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134005 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2214 | PS4-25-PIT-0008A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2215 | PS4-25-PIT-0008B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2216 | PS4-25-PIT-0008C |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2217 | PS4-25-PIT-0013 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134006 | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2218 | PS4-25-PIT-0018 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134003 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2219 | PS4-25-PIT-0071A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2220 | PS4-25-PIT-0071B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2221 | PS4-25-PIT-0071C |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2222 | PS4-25-PIT-1102 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2223 | PS4-25-PIT-1202 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2224 | PS4-25-TIT-0001 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2225 | PS4-25-TIT-0002A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134003 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2226 | PS4-25-TIT-0002B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134004 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2227 | PS4-25-TIT-0002C |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134005 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2228 | PS4-25-TIT-0003A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134003 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2229 | PS4-25-TIT-0003B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134004 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2230 | PS4-25-TIT-0003C |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134005 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2231 | PS4-25-TIT-0004 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2232 | PS4-25-TIT-1101 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2233 | PS4-25-TIT-1201 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2234 | PS4-28-LIT-0002 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GWR Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135701 | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone G | TM-00067
T-00067-2235 | PS4-28-LIT-0008 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GWR Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135701 | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone G | TM-00067
T-00067-2236 | PS4-28-LIT-1101 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GWR Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135401 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone G | TM-00067
T-00067-2237 | PS4-28-LIT-1102 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GWR Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135401 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone G | TM-00067
T-00067-2238 | PS4-28-LIT-1201 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GWR Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135402 | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump |  | PS4-28-06 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone G | TM-00067
T-00067-2239 | PS4-28-LIT-1202 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GWR Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135402 | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump |  | PS4-28-06 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone G | TM-00067
T-00067-2240 | PS4-28-LIT-1301A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GWR Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135405 | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2241 | PS4-28-LIT-1301B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GWR Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135406 | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2242 | PS4-28-LIT-1301C |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GWR Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135407 | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2243 | PS4-28-LIT-1401 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GWR Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135404 | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-2244 | PS4-28-LIT-1402 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GWR Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135404 | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-2245 | PS4-28-PIT-0015 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134009 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone G | TM-00067
T-00067-2246 | PS4-28-PIT-0033 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135402 | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump |  | PS4-28-06 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone G | TM-00067
T-00067-2247 | PS4-28-PIT-0041 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2248 | PS4-28-TIT-1104 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135401 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone G | TM-00067
T-00067-2249 | PS4-28-TIT-1105 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135401 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone G | TM-00067
T-00067-2250 | PS4-28-TIT-1201 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135402 | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump |  | PS4-28-06 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone G | TM-00067
T-00067-2251 | PS4-28-TIT-1401 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135404 | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-2252 | PS4-28-TIT-1402 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135404 | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-2253 | PS4-50-FIT-0001 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DP Flow Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135500 | PS4 - TZA - PS4 - Tanzania | PS4-50-03 - Water Pre-Treatment Package |  | PS4-50-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone F | TM-00067
T-00067-2254 | PS4-50-LIT-0001 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135500 | PS4 - TZA - PS4 - Tanzania | PS4-50-01 - Water Well Submersible Pumps (3100) |  | PS4-50-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone I | TM-00067
T-00067-2255 | PS4-50-LIT-0002 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135500 | PS4 - TZA - PS4 - Tanzania | PS4-50-02 - Water Well Submersible Pumps (3200) |  | PS4-50-02 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone I | TM-00067
T-00067-2256 | PS4-53-LIT-4101 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DP Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135501 | PS4 - TZA - PS4 - Tanzania | PS4-53-01 - Utility Water / Storage Tank |  | PS4-53-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone C | TM-00067
T-00067-2257 | PS4-53-LIT-4102 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DP Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135501 | PS4 - TZA - PS4 - Tanzania | PS4-53-01 - Utility Water / Storage Tank |  | PS4-53-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone C | TM-00067
T-00067-2258 | PS4-53-PIT-0005 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135501 | PS4 - TZA - PS4 - Tanzania | PS4-53-02 - Water Distribution Pump A/B |  | PS4-53-02 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-2259 | PS4-60-LIT-4301 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DP Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135120 | PS4 - TZA - PS4 - Tanzania | PS4-60-24 - Cooling Water Tank & Pump |  | PS4-60-24 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-2260 | PS4-60-LIT-4401 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DP Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135121 | PS4 - TZA - PS4 - Tanzania | PS4-60-25 - Cooling Water Maintenance Tank & Return Pump |  | PS4-60-25 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-2261 | PS4-71-FIT-0005 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DP Flow Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135203 | PS4 - TZA - PS4 - Tanzania | PS4-71-17 - Diesel Fuel Distribution Header |  | PS4-71-17 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone F | TM-00067
T-00067-2262 | PS4-71-FIT-0011A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Coriolis Flow Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2263 | PS4-71-FIT-0011B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Coriolis Flow Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2264 | PS4-71-FIT-0012 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DP Flow Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135204 | PS4 - TZA - PS4 - Tanzania | PS4-71-17 - Diesel Fuel Distribution Header |  | PS4-71-17 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone F | TM-00067
T-00067-2265 | PS4-71-FIT-0018 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DP Flow Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135007 | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2266 | PS4-71-FIT-0019 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DP Flow Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135008 | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone B | TM-00067
T-00067-2267 | PS4-71-FIT-0020 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DP Flow Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135006 | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2268 | PS4-71-LIT-1201 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DP Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135205 | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank |  | PS4-71-20 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone B | TM-00067
T-00067-2269 | PS4-71-LIT-1202 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DP Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135205 | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank |  | PS4-71-20 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone B | TM-00067
T-00067-2270 | PS4-71-LIT-4101 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GWR Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135000 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2271 | PS4-71-LIT-4102 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GWR Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135000 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2272 | PS4-71-LIT-4201 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GWR Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135003 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2273 | PS4-71-LIT-4202 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GWR Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135003 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2274 | PS4-71-LIT-4401 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DP Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135201 | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank |  | PS4-71-15 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone F | TM-00067
T-00067-2275 | PS4-71-LIT-4402 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DP Level Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135201 | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank |  | PS4-71-15 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone F | TM-00067
T-00067-2276 | PS4-71-PDIT-0030 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2277 | PS4-71-PDIT-0056A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135006 | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2278 | PS4-71-PDIT-0056B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135006 | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2279 | PS4-71-PIT-0014 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135203 | PS4 - TZA - PS4 - Tanzania | PS4-71-17 - Diesel Fuel Distribution Header |  | PS4-71-17 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone F | TM-00067
T-00067-2280 | PS4-71-PIT-2402A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2281 | PS4-71-PIT-2402B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2282 | PS4-71-TIT-0003 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2283 | PS4-71-TIT-0004 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2284 | PS4-71-TIT-0006 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2285 | PS4-71-TIT-0007 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2286 | PS4-71-TIT-2403A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2287 | PS4-71-TIT-2403B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2288 | PS4-71-TIT-4102 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135000 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2289 | PS4-71-TIT-4103 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135000 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2290 | PS4-71-TIT-4202 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135003 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2291 | PS4-71-TIT-4203 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135003 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2292 | PS4-74-PIT-0002 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135800 | PS4 - TZA - PS4 - Tanzania | PS4-74-04 - Nitrogen Distribution Header |  | PS4-74-04 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone F | TM-00067
T-00067-2390 | PS4-25-IES-3200A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Crude Oil Export Pump Motor A - Lube OilPump 1 Motor | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone H | TM-00067
T-00067-2391 | PS4-25-IES-3200B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Crude Oil Export Pump Motor A - Lube OilPump 2 Motor | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone H | TM-00067
T-00067-2392 | PS4-25-IES-3300A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Crude Oil Export Pump Motor B - Lube OilPump 1 Motor | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone H | TM-00067
T-00067-2393 | PS4-25-IES-3300B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Crude Oil Export Pump Motor B - Lube OilPump 2 Motor | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone H | TM-00067
T-00067-2394 | PS4-25-IES-3400A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Crude Oil Export Pump C - Lube OilPump 1 Motor | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone H | TM-00067
T-00067-2395 | PS4-25-IES-3400B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Crude Oil Export Pump C - Lube OilPump 2 Motor | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone H | TM-00067
T-00067-2396 | PS4-25-IES-6400A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Crude Oil Export Pump Motor A - Lube Oil Heat Exchanger Fan Motor 1 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone H | TM-00067
T-00067-2397 | PS4-25-IES-6400B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Crude Oil Export Pump Motor A- Lube Oil Heat Exchanger Fan Motor 2 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone H | TM-00067
T-00067-2398 | PS4-25-IES-6500A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Crude Oil Export Pump Motor B - Lube Oil Heat Exchanger Fan Motor 1 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone H | TM-00067
T-00067-2399 | PS4-25-IES-6500B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Crude Oil Export Pump Motor B- Lube Oil Heat Exchanger Fan Motor 2 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone H | TM-00067
T-00067-2400 | PS4-25-IES-6600A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Crude Oil Export Pump C - Lube Oil Heat Exchanger Fan Motor 1 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone H | TM-00067
T-00067-2401 | PS4-25-IES-6600B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Crude Oil Export Pump C - Lube Oil Heat Exchanger Fan Motor 2 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone H | TM-00067
T-00067-2402 | PS4-28-IES-2008 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Socket Outlet 63A for mobile oil skimmer (PS4-28-UZ-8100) | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-10 - Oil Skimmer Package |  | PS4-28-10 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone I | TM-00067
T-00067-2403 | PS4-28-IES-3300 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Relief Drum Pump Motor | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump |  | PS4-28-06 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone G | TM-00067
T-00067-2404 | PS4-28-IES-3400 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Closed Drain Drum 01 Pump Motor | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone G | TM-00067
T-00067-2405 | PS4-28-IES-3500 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Oily Water Sump Pump Motor | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone G | TM-00067
T-00067-2406 | PS4-28-IES-3600A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Open Drain Sump Pump Motor A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone G | TM-00067
T-00067-2407 | PS4-28-IES-3600B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Open Drain Sump Pump Motor B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone G | TM-00067
T-00067-2408 | PS4-28-IES-3700A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Closed Drain Drum 02 Pump Motor A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone E | TM-00067
T-00067-2409 | PS4-28-IES-3700B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Closed Drain Drum 02 Pump Motor B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone E | TM-00067
T-00067-2410 | PS4-28-IES-3800A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Seal Oil Drain Drum Pump Motor A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone H | TM-00067
T-00067-2411 | PS4-28-IES-3800B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Seal Oil Drain Drum Pump Motor B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone H | TM-00067
T-00067-2412 | PS4-28-IES-3800C |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Seal Oil Drain Drum Pump Motor C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone H | TM-00067
T-00067-2413 | PS4-28-IES-3900A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Reinjection Pump Motor A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone H | TM-00067
T-00067-2414 | PS4-28-IES-3900B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Reinjection Pump Motor B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone H | TM-00067
T-00067-2415 | PS4-53-IES-3100A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Water Distribution Pump Motor A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-53-02 - Water Distribution Pump A/B |  | PS4-53-02 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone E | TM-00067
T-00067-2416 | PS4-53-IES-3100B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Water Distribution Pump Motor B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-53-02 - Water Distribution Pump A/B |  | PS4-53-02 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone E | TM-00067
T-00067-2417 | PS4-60-IES-3300 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Cooling Water Pump Motor | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-24 - Cooling Water Tank & Pump |  | PS4-60-24 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone E | TM-00067
T-00067-2418 | PS4-60-IES-3400 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Cooling Water Return Pump Motor | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-25 - Cooling Water Maintenance Tank & Return Pump |  | PS4-60-25 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone E | TM-00067
T-00067-2419 | PS4-71-IES-3100A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Diesel Fuel Supply Pump Motor A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-16 - Diesel Fuel Supply Pump A/B |  | PS4-71-16 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone F | TM-00067
T-00067-2420 | PS4-71-IES-3100B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Diesel Fuel Supply Pump Motor B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-16 - Diesel Fuel Supply Pump A/B |  | PS4-71-16 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone F | TM-00067
T-00067-2421 | PS4-71-IES-3200 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Diesel Fuel Make-Up Pump Motor | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-14 - Diesel Fuel Transfer and Dispensing Station |  | PS4-71-14 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone F | TM-00067
T-00067-2422 | PS4-71-IES-3300A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Crude Fuel Oil Transfer Pump Motor A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone H | TM-00067
T-00067-2423 | PS4-71-IES-3300B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Crude Fuel Oil Transfer Pump Motor B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone H | TM-00067
T-00067-2424 | PS4-71-IES-3400A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Crude Fuel Oil Service Pump Motor A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone H | TM-00067
T-00067-2425 | PS4-71-IES-3400B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Crude Fuel Oil Service Pump Motor B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone H | TM-00067
T-00067-2426 | PS4-71-IES-3500A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Diesel Transfer Pump Motor A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone B | TM-00067
T-00067-2427 | PS4-71-IES-3500B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LCS for Diesel Transfer Pump Motor B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone B | TM-00067
T-00067-2556 | PS4-01-LB-6101A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | STATUS PANEL JUNCTION BOX | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SAN1-120001 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-2557 | PS4-01-LB-6102A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | STATUS PANEL JUNCTION BOX | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SAN1-120001 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-2558 | PS4-01-LB-6103A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | STATUS PANEL JUNCTION BOX | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SAN1-120001 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-2559 | PS4-01-LB-6104A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | STATUS PANEL JUNCTION BOX | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SAN1-120001 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone E | TM-00067
T-00067-2590 | PS4-03-RMAC-B401 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Manual call point | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone I | TM-00067
T-00067-2591 | PS4-03-RMAC-B402 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Manual call point | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone I | TM-00067
T-00067-2592 | PS4-03-RMAC-B902 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Manual call point | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone I | TM-00067
T-00067-2593 | PS4-03-RMAC-W502 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Manual call point | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone I | TM-00067
T-00067-2648 | PS4-09-IES-8101A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2649 | PS4-09-IES-8101B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2650 | PS4-09-IES-8102A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2651 | PS4-09-IES-8102B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2652 | PS4-09-IES-8102C |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2653 | PS4-09-IES-8201A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2654 | PS4-09-IES-8201B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2655 | PS4-09-IES-8202A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2656 | PS4-09-IES-8202B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2657 | PS4-09-IES-8202C |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2658 | PS4-09-IES-8202D |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2659 | PS4-09-IES-8301A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2660 | PS4-09-IES-8301B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2661 | PS4-09-IES-8302A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2662 | PS4-09-IES-8302B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2663 | PS4-09-IES-8304A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2664 | PS4-09-IES-8304B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2665 | PS4-09-IES-8305A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2666 | PS4-09-IES-8305B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2667 | PS4-09-IES-8307A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2668 | PS4-09-IES-8307B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2669 | PS4-09-IES-8308A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2670 | PS4-09-IES-8308B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2671 | PS4-09-IES-8311A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2672 | PS4-09-IES-8311B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2673 | PS4-09-IES-8313 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2674 | PS4-09-IES-8314 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2675 | PS4-09-IES-8315 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2676 | PS4-09-IES-8316 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2677 | PS4-09-IES-8317 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2678 | PS4-09-IES-8318 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2679 | PS4-09-IES-8319 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2680 | PS4-09-IES-8321 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2681 | PS4-09-IES-8322 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2682 | PS4-09-IES-8323 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2683 | PS4-09-IES-8324 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2684 | PS4-09-IES-8325 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2685 | PS4-09-IES-8401A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2686 | PS4-09-IES-8401B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2687 | PS4-09-IES-8403A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2688 | PS4-09-IES-8403B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2689 | PS4-09-IES-8404A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2690 | PS4-09-IES-8404B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2691 | PS4-09-IES-8405A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2692 | PS4-09-IES-8405B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2693 | PS4-09-IES-8406A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2694 | PS4-09-IES-8406B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2695 | PS4-09-IES-8406C |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2696 | PS4-09-IES-8406D |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2697 | PS4-09-IES-8406E |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2698 | PS4-09-IES-8406F |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2699 | PS4-09-IES-8406G |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2700 | PS4-09-IES-8406H |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2701 | PS4-09-IES-8407 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY STOP PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | E | To be completed | PS4 - Milestone D | TM-00067
T-00067-2702 | PS4-09-PDIT-8207 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DIFFERENTIAL PRESSURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2703 | PS4-09-PDIT-8407 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DIFFERENTIAL PRESSURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2704 | PS4-09-PDIT-8408 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DIFFERENTIAL PRESSURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2705 | PS4-09-PDIT-8409 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DIFFERENTIAL PRESSURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2706 | PS4-09-PDIT-8411 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DIFFERENTIAL PRESSURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2707 | PS4-09-PIT-8401 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRESSURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2708 | PS4-09-PIT-8402 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRESSURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2709 | PS4-09-PIT-8403 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRESSURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2710 | PS4-09-PIT-8404 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRESSURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2711 | PS4-09-TIT-8101 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2712 | PS4-09-TIT-8201 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2713 | PS4-09-TIT-8301 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2714 | PS4-09-TIT-8302 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2715 | PS4-09-TIT-8303 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2716 | PS4-09-TIT-8304 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2717 | PS4-09-TIT-8401 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2718 | PS4-09-TIT-8402 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2719 | PS4-09-TIT-8403 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2720 | PS4-09-TIT-8404 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2721 | PS4-09-TIT-8405 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2722 | PS4-09-TIT-8406 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2723 | PS4-09-TIT-8407 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2724 | PS4-09-TIT-8408 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2725 | PS4-09-AH-8401 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | HUMIDITY TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2726 | PS4-09-AH-8402 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | HUMIDITY TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2727 | PS4-09-AH-8403 |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | HUMIDITY TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone D | TM-00067
T-00067-2921 | PS4-23-SPZM-0011A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CORROSION PROBE INTRUSIVE FLUSH TYPE - weight loss coupon [CP] | EACOP | CPP AGI |  |  | 1 |  | 1 | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2922 | PS4-23-SPZM-0011B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CORROSION PROBE INTRUSIVE FLUSH TYPE - Bio-coupon [BP] | EACOP | CPP AGI |  |  | 1 |  | 1 | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2923 | PS4-23-SPZM-0011C |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CORROSION PROBE INTRUSIVE FLUSH TYPE -Electrical Resistance Probe [ ER] | EACOP | CPP AGI |  |  | 1 |  | 1 | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2924 | PS4-23-SPZM-0011D |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | ULTRASONIC THICKNESS SENSORS NON INTRUSIVE - ultrasonic wall thickness [UT] sensors | EACOP | CPP AGI |  |  | 1 |  | 1 | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2925 | PS4-23-SPZM-0012A |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CORROSION PROBE INTRUSIVE FLUSH TYPE - weight loss coupon [CP] | EACOP | CPP AGI |  |  | 1 |  | 1 | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2926 | PS4-23-SPZM-0012B |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CORROSION PROBE INTRUSIVE FLUSH TYPE - Bio-coupon [BP] | EACOP | CPP AGI |  |  | 1 |  | 1 | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2927 | PS4-23-SPZM-0012C |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CORROSION PROBE INTRUSIVE FLUSH TYPE - Electrical Resistance Probe [ ER] | EACOP | CPP AGI |  |  | 1 |  | 1 | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00067-2928 | PS4-23-SPZM-0012D |  |  |  |  | CJX08 - Electrical instrument | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | ULTRASONIC THICKNESS SENSORS NON INTRUSIVE.- ultrasonic wall thickness [UT] sensors | EACOP | CPP AGI |  |  | 1 |  | 1 | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Electrical Instrument | I | To be completed | PS4 - Milestone H | TM-00067
T-00069-10000 | PS4-03-RDOS-B901A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B901B TO PS4-03-RDOS-B901A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-10001 | PS4-03-RDOS-B901B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B801A TO PS4-03-RDOS-B901C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-10002 | PS4-03-RDOS-B901C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B901C TO PS4-03-RDOS-B901D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-10003 | PS4-03-RDOS-B901D-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B901D TO PS4-03-RDOS-B901E | EACOP | CPP AGI |  |  | 4 |  | 4 | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-10004 | PS4-03-RDOS-B901E-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B901E TO PS4-03-RMAC-B902 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-10005 | PS4-03-RDOS-W201A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-W201B TO PS4-03-RDOS-W201A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-10006 | PS4-03-RDOS-W201B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-W301A TO PS4-03-RDOS-W201B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-10007 | PS4-03-RDOS-W201C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-W201D TO PS4-03-RDOS-W201C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-10008 | PS4-03-RDOS-W201D-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-W501A TO PS4-03-RDOS-W201D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-10009 | PS4-03-RDOS-W301A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-W401A TO PS4-03-RDOS-W301A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-10010 | PS4-03-RDOS-W401A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-W201C TO PS4-03-RDOS-W401A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-10011 | PS4-03-RDOS-W501A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-W501B TO PS4-03-RDOS-W501A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-10012 | PS4-03-RDOS-W501B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-W501C TO PS4-03-RDOS-W501B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-10013 | PS4-03-RDOS-W501C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-W501D TO PS4-03-RDOS-W501C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-10014 | PS4-03-RDOS-W501D-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-W501E TO PS4-03-RDOS-W501D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-10015 | PS4-03-RDOS-W501E-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-W501F TO PS4-03-RDOS-W501E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-10016 | PS4-03-RDOS-W501F-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RMAC-W502 TO PS4-03-RDOS-W501F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-10017 | PS4-03-RMAC-B402-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B401C TO PS4-03-RMAC-B402 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-10018 | PS4-03-RMAC-B902-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SEA-0005 TO PS4-03-RMAC-B902 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-10019 | PS4-03-RMAC-W502-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SEA-0006 TO PS4-03-RMAC-W502 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-11326 | PS4-09-AH-8401-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AH-8401 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11327 | PS4-09-AH-8401-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AH-8401 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11328 | PS4-09-AH-8402-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AH-8402 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11329 | PS4-09-AH-8402-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AH-8402 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11330 | PS4-09-AH-8403-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AH-8403 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11331 | PS4-09-AH-8403-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AH-8403 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11332 | PS4-09-AS-8111A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8111A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11333 | PS4-09-AS-8111A-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8111A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11334 | PS4-09-AS-8111B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8111B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11335 | PS4-09-AS-8111B-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8111B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11336 | PS4-09-AS-8211A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8211A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11337 | PS4-09-AS-8211A-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8211A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11338 | PS4-09-AS-8211B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8211B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11339 | PS4-09-AS-8211B-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8211B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11340 | PS4-09-AS-8311A-A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8311A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11341 | PS4-09-AS-8311A-A-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8311A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11342 | PS4-09-AS-8311B-B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8311B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11343 | PS4-09-AS-8311B-B-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8311B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11344 | PS4-09-AS-8311C-A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8311C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11345 | PS4-09-AS-8311C-A-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8311C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11346 | PS4-09-AS-8311D-B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8311D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11347 | PS4-09-AS-8311D-B-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8311D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11348 | PS4-09-AS-8321A-A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8321A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11349 | PS4-09-AS-8321A-A-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8321A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11350 | PS4-09-AS-8321B-B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8321B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11351 | PS4-09-AS-8321B-B-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8321B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11352 | PS4-09-AS-8321C-A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8321C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11353 | PS4-09-AS-8321C-A-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8321C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11354 | PS4-09-AS-8321D-B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8321D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11355 | PS4-09-AS-8321D-B-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8321D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11356 | PS4-09-AS-8331A-A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8331A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11357 | PS4-09-AS-8331A-A-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8331A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11358 | PS4-09-AS-8331B-B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8331B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11359 | PS4-09-AS-8331B-B-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8331B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11360 | PS4-09-AS-8331C-A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8331C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11361 | PS4-09-AS-8331C-A-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8331C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11362 | PS4-09-AS-8331D-B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8331D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11363 | PS4-09-AS-8331D-B-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8331D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11364 | PS4-09-AS-8341A-A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8341A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11365 | PS4-09-AS-8341A-A-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8341A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11366 | PS4-09-AS-8341B-B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8341B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11367 | PS4-09-AS-8341B-B-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8341B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11368 | PS4-09-AS-8411A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8411A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11369 | PS4-09-AS-8411A-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8411A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11370 | PS4-09-AS-8411B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8411B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11371 | PS4-09-AS-8411B-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8411B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11372 | PS4-09-AS-8412A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8412A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11373 | PS4-09-AS-8412A-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8412A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11374 | PS4-09-AS-8412B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8412B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11375 | PS4-09-AS-8412B-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8412B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11376 | PS4-09-AS-8421A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8421A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11377 | PS4-09-AS-8421A-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8421A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11378 | PS4-09-AS-8421B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8421B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11379 | PS4-09-AS-8421B-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8421B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11380 | PS4-09-AS-8432A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8432A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11381 | PS4-09-AS-8432A-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8432A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11382 | PS4-09-AS-8432B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8432B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11383 | PS4-09-AS-8432B-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8432B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11384 | PS4-09-BI-8111A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8111A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11385 | PS4-09-BI-8111B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8111B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11386 | PS4-09-BI-8211A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8211A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11387 | PS4-09-BI-8211B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8211B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11388 | PS4-09-BI-8311A-A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8312A (PS4-09-BI-8311A-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11389 | PS4-09-BI-8311A-B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8312B (PS4-09-BI-8311A-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11390 | PS4-09-BI-8311B-A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8312C (PS4-09-BI-8311B-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11391 | PS4-09-BI-8311B-B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8312D (PS4-09-BI-8311B-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11392 | PS4-09-BI-8321A-A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8322A (PS4-09-BI-8321A-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11393 | PS4-09-BI-8321A-B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8322B (PS4-09-BI-8321A-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11394 | PS4-09-BI-8321B-A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8322C (PS4-09-BI-8321B-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11395 | PS4-09-BI-8321B-B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8322D (PS4-09-BI-8321B-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11396 | PS4-09-BI-8331A-A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8332A (PS4-09-BI-8331A-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11397 | PS4-09-BI-8331A-B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8332B (PS4-09-BI-8331A-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11398 | PS4-09-BI-8331B-A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8332C (PS4-09-BI-8331B-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11399 | PS4-09-BI-8331B-B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8332D (PS4-09-BI-8331B-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11400 | PS4-09-BI-8341A-A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8342A (PS4-09-BI-8341A-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11401 | PS4-09-BI-8341A-B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8342B (PS4-09-BI-8341A-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11402 | PS4-09-BI-8411A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8411A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11403 | PS4-09-BI-8411B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8411B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11404 | PS4-09-FCU-8442A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11405 | PS4-09-FCU-8442A-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11406 | PS4-09-FCU-8442B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11407 | PS4-09-FCU-8442B-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11408 | PS4-09-FCU-8442C-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11409 | PS4-09-FCU-8442C-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11410 | PS4-09-FCU-8442D-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11411 | PS4-09-FCU-8442D-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11412 | PS4-09-FCU-8442E-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11413 | PS4-09-FCU-8442E-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11414 | PS4-09-FCU-8442F-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11415 | PS4-09-FCU-8442F-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11416 | PS4-09-FCU-8442G-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11417 | PS4-09-FCU-8442G-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11418 | PS4-09-FCU-8442H-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442H | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11419 | PS4-09-FCU-8442H-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442H | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11420 | PS4-09-FD-0019-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0019 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11421 | PS4-09-FD-0019-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0019 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11422 | PS4-09-FD-0019-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0019 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11423 | PS4-09-FD-0021-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0021 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11424 | PS4-09-FD-0021-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0021 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11425 | PS4-09-FD-0021-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0021 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11426 | PS4-09-FD-0024-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0024 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11427 | PS4-09-FD-0024-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0024 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11428 | PS4-09-FD-0024-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0024 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11429 | PS4-09-FD-0025-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0025 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11430 | PS4-09-FD-0025-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0025 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11431 | PS4-09-FD-0025-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0025 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11432 | PS4-09-FD-0026-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0026 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11433 | PS4-09-FD-0026-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0026 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11434 | PS4-09-FD-0026-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0026 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11435 | PS4-09-FD-0027-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0027 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11436 | PS4-09-FD-0027-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0027 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11437 | PS4-09-FD-0027-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0027 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11438 | PS4-09-FD-0028-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0028 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11439 | PS4-09-FD-0028-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0028 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11440 | PS4-09-FD-0028-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0028 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11441 | PS4-09-FD-0029-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0029 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11442 | PS4-09-FD-0029-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0029 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11443 | PS4-09-FD-0029-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0029 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11444 | PS4-09-FD-0030-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0030 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11445 | PS4-09-FD-0030-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0030 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11446 | PS4-09-FD-0030-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0030 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11447 | PS4-09-FD-0031-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0031 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11448 | PS4-09-FD-0031-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0031 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11449 | PS4-09-FD-0031-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0031 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11450 | PS4-09-FD-0032-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0032 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11451 | PS4-09-FD-0032-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0032 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11452 | PS4-09-FD-0032-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0032 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11453 | PS4-09-FD-0033-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0033 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11454 | PS4-09-FD-0033-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0033 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11455 | PS4-09-FD-0033-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0033 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11456 | PS4-09-HE-8401A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-61-IH-0004 TO PS4-09-HE-8401A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11457 | PS4-09-HE-8401B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-61-IH-0004 TO PS4-09-HE-8401B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11458 | PS4-09-LB-8111A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8111A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11459 | PS4-09-LB-8111B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8111B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11460 | PS4-09-LB-8211A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8211A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11461 | PS4-09-LB-8211B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8211B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11462 | PS4-09-LB-8311A-A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8311B (PS4-09-LB-8311A-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11463 | PS4-09-LB-8311A-B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8311C (PS4-09-LB-8311B-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11464 | PS4-09-LB-8311B-A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8311D (PS4-09-LB-8311B-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11465 | PS4-09-LB-8311B-B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8321A (PS4-09-LB-8321A-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11466 | PS4-09-LB-8321A-A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8321B (PS4-09-LB-8321A-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11467 | PS4-09-LB-8321A-B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8321C (PS4-09-LB-8321B-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11468 | PS4-09-LB-8321B-A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8321D (PS4-09-LB-8321B-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11469 | PS4-09-LB-8321B-B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8331A (PS4-09-LB-8331A-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11470 | PS4-09-LB-8331A-A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8331B (PS4-09-LB-8331A-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11471 | PS4-09-LB-8331A-B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8331C (PS4-09-LB-8331B-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11472 | PS4-09-LB-8331B-A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8331D (PS4-09-LB-8331B-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11473 | PS4-09-LB-8331B-B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8341A (PS4-09-LB-8341A-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11474 | PS4-09-LB-8341A-A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8341B (PS4-09-LB-8341A-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11475 | PS4-09-LB-8341A-B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8341A-B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11476 | PS4-09-LB-8411A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8411A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11477 | PS4-09-LB-8411B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8411B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11478 | PS4-09-LB-8442A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442A (PS4-09-LB-8442A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11479 | PS4-09-LB-8442B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442B (PS4-09-LB-8442B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11480 | PS4-09-LB-8442C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442C (PS4-09-LB-8442C) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11481 | PS4-09-LB-8442D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442D (PS4-09-LB-8442D) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11482 | PS4-09-LB-8442E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442E (PS4-09-LB-8442E) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11483 | PS4-09-LB-8442F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442F (PS4-09-LB-8442F) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11484 | PS4-09-LB-8442G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442G (PS4-09-LB-8442G) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11485 | PS4-09-LB-8442H-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442H (PS4-09-LB-8442H) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11486 | PS4-09-LB-8451A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8451A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11487 | PS4-09-LB-8451A-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8451A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11488 | PS4-09-LB-8451B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8451B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11489 | PS4-09-LB-8451B-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8451B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11490 | PS4-09-PDIT-8207-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-PDIT-8207 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11491 | PS4-09-PDIT-8407-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-PDIT-8407 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11492 | PS4-09-PDIT-8408-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-PDIT-8408 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11493 | PS4-09-PDIT-8409-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-PDIT-8409 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11494 | PS4-09-PDIT-8411-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-PDIT-8411 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11495 | PS4-09-PIT-8401-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-PIT-8401 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11496 | PS4-09-PIT-8402-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-PIT-8402 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11497 | PS4-09-PIT-8403-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-PIT-8403 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11498 | PS4-09-PIT-8404-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-PIT-8404 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11499 | PS4-09-TCV-8401-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TCV-8401 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11500 | PS4-09-TCV-8401-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TCV-8401 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11501 | PS4-09-TCV-8402-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TCV-8402 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11502 | PS4-09-TCV-8402-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TCV-8402 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11503 | PS4-09-TIT-8101-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8101 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11504 | PS4-09-TIT-8201-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8201 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11505 | PS4-09-TIT-8301-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8301 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11506 | PS4-09-TIT-8302-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8302 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11507 | PS4-09-TIT-8303-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8303 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11508 | PS4-09-TIT-8304-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8304 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11509 | PS4-09-TIT-8401-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8401 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11510 | PS4-09-TIT-8402-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8402 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11511 | PS4-09-TIT-8403-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8403 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11512 | PS4-09-TIT-8404-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8404 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11513 | PS4-09-TIT-8405-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8405 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11514 | PS4-09-TIT-8406-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8406 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11515 | PS4-09-TIT-8407-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8407 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11516 | PS4-09-TIT-8408-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8408 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11517 | PS4-09-UZ-84600-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-UZ-84600 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11518 | PS4-09-UZ-84600-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-UZ-84600 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11519 | PS4-09-XV-8401-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8401 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11520 | PS4-09-XV-8401-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8401 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11521 | PS4-09-XV-8402-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8402 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11522 | PS4-09-XV-8402-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8402 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11523 | PS4-09-XV-8403-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8403 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11524 | PS4-09-XV-8403-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8403 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11525 | PS4-09-XV-8404-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8404 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11526 | PS4-09-XV-8404-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8404 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11527 | PS4-09-XV-8413-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8413 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11528 | PS4-09-XV-8413-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8413 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11529 | PS4-09-XV-8414-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8414 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11530 | PS4-09-XV-8414-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8414 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11531 | PS4-61-IH-0004A-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11532 | PS4-61-IH-0004A-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11533 | PS4-61-IH-0004A-CU03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11534 | PS4-61-IH-0004A-CU04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11535 | PS4-61-IH-0004B-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11536 | PS4-61-IH-0004B-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11537 | PS4-61-IH-0004B-CU03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11538 | PS4-61-IH-0004B-CU04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11539 | PS4-61-IH-0004C-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11540 | PS4-61-IH-0004C-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11541 | PS4-61-IH-0004C-CU03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11542 | PS4-61-IH-0004C-CU04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11543 | PS4-61-IH-0004-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11544 | PS4-61-IH-0004-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11545 | PS4-61-IH-0004-CU03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11546 | PS4-61-IH-0004-CU04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11547 | PS4-61-IH-0004-CU05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11548 | PS4-61-IH-0004-CU06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11549 | PS4-61-IH-0004-CU07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11550 | PS4-61-IH-0004-CU08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11551 | PS4-61-IH-0004-CU09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11552 | PS4-61-IH-0004-CU10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11553 | PS4-61-IH-0004-CU11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11554 | PS4-61-IH-0004-CU12 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11555 | PS4-61-IH-0004-CU13 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11556 | PS4-61-IH-0004-CU14 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11557 | PS4-61-IH-0004-CU15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11558 | PS4-61-IH-0004-CU16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11559 | PS4-61-IH-0004-CU17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11560 | PS4-61-IH-0004-CU18 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11561 | PS4-61-IH-0004-CU19 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11562 | PS4-61-IH-0004-CU20 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11563 | PS4-61-IH-0004-CU21 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11564 | PS4-61-IH-0004-CU22 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11565 | PS4-61-IH-0004-CU23 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11566 | PS4-61-IH-0004-CU24 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11567 | PS4-61-IH-0004-CU25 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11568 | PS4-61-IH-0004-CU26 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11569 | PS4-61-IH-0004-CU27 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11570 | PS4-61-IH-0004-CU28 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11571 | PS4-61-IH-0004-CU29 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11572 | PS4-61-IH-0004D-CU01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-11573 | PS4-61-IH-0004D-CU02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13010 | PS4-60-BI-0001A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 17:33 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-13011 | PS4-60-BI-0001B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 18:01 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-13012 | PS4-60-BI-0001C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-BI-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13013 | PS4-60-BI-0001D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-BI-0001D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13014 | PS4-60-BI-0001E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-BI-0001E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13015 | PS4-60-BI-0001F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001F TO PS4-60-BI-0001F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13016 | PS4-60-BI-0001G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001G TO PS4-60-BI-0001G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-13017 | PS4-60-BI-0003-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-22 04:54 | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-13018 | PS4-60-IE-0002A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 17:35 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-13019 | PS4-60-IE-0002A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 17:40 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-13020 | PS4-60-IE-0002A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 17:42 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-13021 | PS4-60-IE-0002B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 18:03 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-13022 | PS4-60-IE-0002B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 18:06 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-13023 | PS4-60-IE-0002B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 18:09 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-13024 | PS4-60-IE-0002C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13025 | PS4-60-IE-0002C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13026 | PS4-60-IE-0002C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13027 | PS4-60-IE-0002D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13028 | PS4-60-IE-0002D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13029 | PS4-60-IE-0002D-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13030 | PS4-60-IE-0002E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13031 | PS4-60-IE-0002E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13032 | PS4-60-IE-0002E-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13033 | PS4-60-IE-0002F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001F TO PS4-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13034 | PS4-60-IE-0002F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001F TO PS4-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13035 | PS4-60-IE-0002F-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001F TO PS4-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13036 | PS4-60-IE-0002G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001G TO PS4-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-13037 | PS4-60-IE-0002G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001G TO PS4-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-13038 | PS4-60-IE-0002G-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001G TO PS4-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-13039 | PS4-60-IH-0001A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS4-60-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-13040 | PS4-60-IH-0001A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS4-60-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-13041 | PS4-60-IH-0001B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS4-60-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-13042 | PS4-60-IH-0001B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS4-60-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-13043 | PS4-60-IH-0001C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS4-60-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13044 | PS4-60-IH-0001C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS4-60-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13045 | PS4-60-IH-0001D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS4-60-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13046 | PS4-60-IH-0001D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS4-60-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13047 | PS4-60-IH-0001E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS4-60-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13048 | PS4-60-IH-0001E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS4-60-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13049 | PS4-60-IH-0001F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS4-60-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13050 | PS4-60-IH-0001F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS4-60-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13051 | PS4-60-IH-0001G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS4-60-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-13052 | PS4-60-IH-0001G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS4-60-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-13053 | PS4-60-IH-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-13054 | PS4-60-IH-0002-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-13055 | PS4-60-IN-0004A-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IN-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-13056 | PS4-60-IN-0004B-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IN-0004B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-13057 | PS4-60-PIT-8113A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-PIT-8113A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A |  | PS4-60-56 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-13058 | PS4-60-PIT-8113B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-PIT-8113B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B |  | PS4-60-58 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-13059 | PS4-60-PIT-8113C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-PIT-8113C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C |  | PS4-60-60 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13060 | PS4-60-PIT-8113D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-PIT-8113D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D |  | PS4-60-62 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13061 | PS4-60-PIT-8113E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-PIT-8113E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E |  | PS4-60-64 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13062 | PS4-60-PIT-8113F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001F TO PS4-60-PIT-8113F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F |  | PS4-60-66 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13063 | PS4-60-PIT-8113G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001G TO PS4-60-PIT-8113G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G |  | PS4-60-68 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-13064 | PS4-60-PIT-8114A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-PIT-8114A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A |  | PS4-60-56 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-13065 | PS4-60-PIT-8114B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-PIT-8114B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B |  | PS4-60-58 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-13066 | PS4-60-PIT-8114C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-PIT-8114C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C |  | PS4-60-60 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13067 | PS4-60-PIT-8114D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-PIT-8114D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D |  | PS4-60-62 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13068 | PS4-60-PIT-8114E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-PIT-8114E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E |  | PS4-60-64 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13069 | PS4-60-PIT-8114F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001F TO PS4-60-PIT-8114F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F |  | PS4-60-66 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-13070 | PS4-60-PIT-8114G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001G TO PS4-60-PIT-8114G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G |  | PS4-60-68 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-7981 | PS4-01-BI-0007-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-BI-0007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-7982 | PS4-01-BI-0008-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-BI-0008 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-7983 | PS4-01-BI-0009-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-BI-0009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-7994 | PS4-01-FCV-0003A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-FCV-0003A-HPU TO PS4-01-FCV-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-7995 | PS4-01-FCV-0003B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-FCV-0003B-HPU TO PS4-01-FCV-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-7996 | PS4-01-FCV-0004A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-FCV-0004A-HPU TO PS4-01-FCV-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-7997 | PS4-01-FCV-0004B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-FCV-0004B-HPU TO PS4-01-FCV-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-7998 | PS4-01-FIT-0003A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1117 TO PS4-01-FIT-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-7999 | PS4-01-FIT-0003B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1117 TO PS4-01-FIT-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8000 | PS4-01-FIT-0004A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1117 TO PS4-01-FIT-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8001 | PS4-01-FIT-0004B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1117 TO PS4-01-FIT-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8002 | PS4-01-FXS-0003A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-2110 TO PS4-01-FCV-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8003 | PS4-01-FXS-0003B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-2110 TO PS4-01-FCV-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8004 | PS4-01-FXS-0004A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-2110 TO PS4-01-FCV-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8005 | PS4-01-FXS-0004B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-2110 TO PS4-01-FCV-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8006 | PS4-01-FY-0003A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1118 TO PS4-01-FCV-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8007 | PS4-01-FY-0003B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1118 TO PS4-01-FCV-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8008 | PS4-01-FY-0004A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1118 TO PS4-01-FCV-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8009 | PS4-01-FY-0004B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1118 TO PS4-01-FCV-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8010 | PS4-01-HS-3108AB-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-IE-0009A TO PS4-03-MTX-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8011 | PS4-01-HS-3108BB-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-IE-0009B TO PS4-03-MTX-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8023 | PS4-01-LB-6101A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-LB-6101A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8024 | PS4-01-LB-6102A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-LB-6102A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8025 | PS4-01-LB-6103A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-LB-6103A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8026 | PS4-01-LB-6104A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-LB-6104A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8027 | PS4-01-LIT-4101A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-IE-0009A TO PS4-01-LIT-4101A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8028 | PS4-01-LIT-4101B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-IE-0009B TO PS4-01-LIT-4101B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8030 | PS4-01-NMR-61001-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-NMR-61001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8031 | PS4-01-NMR-61002-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-NMR-61002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8032 | PS4-01-NMR-61003-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-NMR-61003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8033 | PS4-01-NMR-61004-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-NMR-61004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8034 | PS4-01-NMRA-61001-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-NMRA-61001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8035 | PS4-01-NMRA-61002-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-NMRA-61002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8036 | PS4-01-NMRA-61003-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-NMRA-61003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8037 | PS4-01-NMRA-61004-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-NMRA-61004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8038 | PS4-01-PDIT-0011A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1515 TO PS4-01-PDIT-0011A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8039 | PS4-01-PDIT-0011B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1515 TO PS4-01-PDIT-0011B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8040 | PS4-01-PDIT-0012A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1515 TO PS4-01-PDIT-0012A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8041 | PS4-01-PDIT-0012B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1515 TO PS4-01-PDIT-0012B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8042 | PS4-01-PIT-0003AA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1118 TO PS4-01-FCV-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8043 | PS4-01-PIT-0003BA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1118 TO PS4-01-FCV-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8044 | PS4-01-PIT-0004AA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1118 TO PS4-01-FCV-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8045 | PS4-01-PIT-0004BA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1118 TO PS4-01-FCV-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8046 | PS4-01-PIT-0010-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1501 TO PS4-01-PIT-0010 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-07 - Fire Water Ring Main & Distribution |  | PS4-01-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8047 | PS4-01-PIT-0013-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1515 TO PS4-01-PIT-0013 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-07 - Fire Water Ring Main & Distribution |  | PS4-01-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8052 | PS4-01-PIT-8101A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1520 TO PS4-01-PIT-8101A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8053 | PS4-01-PIT-8101B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1520 TO PS4-01-PIT-8101B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8054 | PS4-01-PIT-8101C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1520 TO PS4-01-PIT-8101C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8055 | PS4-01-PIT-8101D-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1520 TO PS4-01-PIT-8101D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8056 | PS4-01-PIT-8101E-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1520 TO PS4-01-PIT-8101E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8057 | PS4-01-PIT-8101F-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1520 TO PS4-01-PIT-8101F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8058 | PS4-01-PIT-8101G-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1520 TO PS4-01-PIT-8101G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8059 | PS4-01-PIT-8101H-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-1520 TO PS4-01-PIT-8101H | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8060 | PS4-01-RAB-61001A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-RAB-61001A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8061 | PS4-01-RAB-61001B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-RAB-61001B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8062 | PS4-01-RAB-61002A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-RAB-61002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8063 | PS4-01-RAB-61002B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-RAB-61002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8064 | PS4-01-RAB-61003A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-RAB-61003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8065 | PS4-01-RAB-61003B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-RAB-61003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8066 | PS4-01-RAB-61004A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-RAB-61004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8067 | PS4-01-RAB-61004B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-RAB-61004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8068 | PS4-01-SY-8101A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-2520 TO PS4-01-SY-8101A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8069 | PS4-01-SY-8101B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-2520 TO PS4-01-SY-8101B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8070 | PS4-01-SY-8101C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-2520 TO PS4-01-SY-8101C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8071 | PS4-01-SY-8101D-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-2520 TO PS4-01-SY-8101D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8072 | PS4-01-SY-8101E-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-2520 TO PS4-01-SY-8101E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8073 | PS4-01-SY-8101F-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-2520 TO PS4-01-SY-8101F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8074 | PS4-01-SY-8101G-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-2520 TO PS4-01-SY-8101G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8075 | PS4-01-SY-8101H-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-BI-2520 TO PS4-01-SY-8101H | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8102 | PS4-03-GDIR-0901-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-0901 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8103 | PS4-03-GDIR-0902-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-0902 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8104 | PS4-03-GDIR-0903-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-0903 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8105 | PS4-03-GDIR-0904-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-0904 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8106 | PS4-03-GDIR-0906-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-0906 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8107 | PS4-03-GDIR-0907-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-0907 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8108 | PS4-03-GDIR-0908-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-0908 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8109 | PS4-03-GDIR-0909-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-0909 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8110 | PS4-03-GDIR-1001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8111 | PS4-03-GDIR-1002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8112 | PS4-03-GDIR-1003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8113 | PS4-03-GDIR-1004-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8114 | PS4-03-GDIR-1006-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8115 | PS4-03-GDIR-1007-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8116 | PS4-03-GDIR-1008-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1008 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8117 | PS4-03-GDIR-1009-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8118 | PS4-03-GDIR-1101-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8119 | PS4-03-GDIR-1102-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1102 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8120 | PS4-03-GDIR-1103-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1103 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8121 | PS4-03-GDIR-1104-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1104 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8122 | PS4-03-GDIR-1106-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1106 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8123 | PS4-03-GDIR-1107-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1107 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8124 | PS4-03-GDIR-1108-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1108 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8125 | PS4-03-GDIR-1109-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1109 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8126 | PS4-03-GDIR-1201-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1201 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8127 | PS4-03-GDIR-1202-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1202 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8128 | PS4-03-GDIR-1203-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1203 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8129 | PS4-03-GDIR-1204-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1204 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8130 | PS4-03-GDLHP-0137-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2511 TO PS4-03-GDLHP-0137 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8131 | PS4-03-GDLHP-0142-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2511 TO PS4-03-GDLHP-0142 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8132 | PS4-03-GDLHP-0143-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2511 TO PS4-03-GDLHP-0143 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8133 | PS4-03-GDLHP-0144-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2511 TO PS4-03-GDLHP-0144 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8134 | PS4-03-GDLHP-0146-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2511 TO PS4-03-GDLHP-0146 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8135 | PS4-03-GDLHP-0147-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2511 TO PS4-03-GDLHP-0147 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8136 | PS4-03-GDLHP-0149-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2511 TO PS4-03-GDLHP-0149 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8137 | PS4-03-GDLHP-0150-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2511 TO PS4-03-GDLHP-0150 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8138 | PS4-03-GDLHP-0401-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2512 TO PS4-03-GDLHP-0401 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-8152 | PS4-03-RDH-0302-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2510 TO PS4-03-RDH-0302 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-03 - FZ-03 - Buildings Area |  | PS4-03-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8153 | PS4-03-RDH-0303-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2510 TO PS4-03-RDH-0303 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-03 - FZ-03 - Buildings Area |  | PS4-03-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8154 | PS4-03-RDH-0601-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2502 TO PS4-03-RDH-0601 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8155 | PS4-03-RDH-0602-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2502 TO PS4-03-RDH-0602 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8156 | PS4-03-RDH-0603-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2502 TO PS4-03-RDH-0603 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8157 | PS4-03-RDH-0604-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2502 TO PS4-03-RDH-0604 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8158 | PS4-03-RDH-0605-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2502 TO PS4-03-RDH-0605 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8159 | PS4-03-RDH-0606-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2502 TO PS4-03-RDH-0606 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8160 | PS4-03-RDH-0607-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2503 TO PS4-03-RDH-0607 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8161 | PS4-03-RDH-0608-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2503 TO PS4-03-RDH-0608 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8162 | PS4-03-RDH-0609-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2503 TO PS4-03-RDH-0609 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8163 | PS4-03-RDH-0610-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2503 TO PS4-03-RDH-0610 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8164 | PS4-03-RDH-0611-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2503 TO PS4-03-RDH-0611 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8165 | PS4-03-RDH-0612-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2503 TO PS4-03-RDH-0612 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8166 | PS4-03-RDH-0614-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2501 TO PS4-03-RDH-0614 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8167 | PS4-03-RDH-0615-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2501 TO PS4-03-RDH-0615 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8168 | PS4-03-RDH-0616-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2501 TO PS4-03-RDH-0616 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8169 | PS4-03-RDH-0617-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2502 TO PS4-03-RDH-0617 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8170 | PS4-03-RDH-0618-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2502 TO PS4-03-RDH-0618 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8171 | PS4-03-RDH-0620-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2502 TO PS4-03-RDH-0620 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8172 | PS4-03-RDH-0828-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2505 TO PS4-03-RDH-0828 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8173 | PS4-03-RDH-0829-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2505 TO PS4-03-RDH-0829 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8174 | PS4-03-RDH-0830-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2503 TO PS4-03-RDH-0830 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8175 | PS4-03-RDH-0831-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2503 TO PS4-03-RDH-0831 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8176 | PS4-03-RDH-0901-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RDH-0901 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8177 | PS4-03-RDH-0902-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RDH-0902 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8178 | PS4-03-RDH-0903-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RDH-0903 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8179 | PS4-03-RDH-0904-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RDH-0904 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8180 | PS4-03-RDH-0905-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RDH-0905 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8181 | PS4-03-RDH-0906-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RDH-0906 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8182 | PS4-03-RDH-0909-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RDH-0909 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8183 | PS4-03-RDH-0910-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RDH-0910 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8184 | PS4-03-RDH-0911-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RDH-0911 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8185 | PS4-03-RDH-0912-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RDH-0912 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8186 | PS4-03-RDH-1001-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2507 TO PS4-03-RDH-1001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8187 | PS4-03-RDH-1002-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2507 TO PS4-03-RDH-1002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8188 | PS4-03-RDH-1003-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2507 TO PS4-03-RDH-1003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8189 | PS4-03-RDH-1004-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2507 TO PS4-03-RDH-1004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8190 | PS4-03-RDH-1005-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2507 TO PS4-03-RDH-1005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8191 | PS4-03-RDH-1006-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2507 TO PS4-03-RDH-1006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8192 | PS4-03-RDH-1009-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2507 TO PS4-03-RDH-1009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8193 | PS4-03-RDH-1010-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2507 TO PS4-03-RDH-1010 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8194 | PS4-03-RDH-1011-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2507 TO PS4-03-RDH-1011 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8195 | PS4-03-RDH-1012-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2507 TO PS4-03-RDH-1012 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8196 | PS4-03-RDH-1101-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2508 TO PS4-03-RDH-1101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8197 | PS4-03-RDH-1102-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2508 TO PS4-03-RDH-1102 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8198 | PS4-03-RDH-1103-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2508 TO PS4-03-RDH-1103 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8199 | PS4-03-RDH-1104-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2508 TO PS4-03-RDH-1104 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8200 | PS4-03-RDH-1105-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2508 TO PS4-03-RDH-1105 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8201 | PS4-03-RDH-1106-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2508 TO PS4-03-RDH-1106 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8202 | PS4-03-RDH-1109-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2508 TO PS4-03-RDH-1109 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8203 | PS4-03-RDH-1110-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2508 TO PS4-03-RDH-1110 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8204 | PS4-03-RDH-1111-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2508 TO PS4-03-RDH-1111 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8205 | PS4-03-RDH-1112-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2508 TO PS4-03-RDH-1112 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8206 | PS4-03-RDH-1201-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2514 TO PS4-03-RDH-1201 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8207 | PS4-03-RDH-1202-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2514 TO PS4-03-RDH-1202 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8208 | PS4-03-RDH-1203-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2514 TO PS4-03-RDH-1203 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8209 | PS4-03-RDH-1204-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2514 TO PS4-03-RDH-1204 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8210 | PS4-03-RDH-1205-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2514 TO PS4-03-RDH-1205 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8211 | PS4-03-RDH-1302-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2515 TO PS4-03-RDH-1302 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-13 - FZ-13 - Power Generation Building - Instrument Air Room |  | PS4-03-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8212 | PS4-03-RDH-1303-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2515 TO PS4-03-RDH-1303 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-13 - FZ-13 - Power Generation Building - Instrument Air Room |  | PS4-03-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8213 | PS4-03-RDH-1304-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2515 TO PS4-03-RDH-1304 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-13 - FZ-13 - Power Generation Building - Instrument Air Room |  | PS4-03-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8214 | PS4-03-RDH-1901-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDH-1903 TO PS4-03-RDH-1901 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-19 - FZ-19 - Power Generation Building - Battery Room |  | PS4-03-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8215 | PS4-03-RDH-1902-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDH-1901 TO PS4-03-RDH-1902 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-19 - FZ-19 - Power Generation Building - Battery Room |  | PS4-03-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8216 | PS4-03-RDH-1903-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RMAC-1410 TO PS4-03-RDH-1903 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-19 - FZ-19 - Power Generation Building - Battery Room |  | PS4-03-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8217 | PS4-03-RDIR-0104-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1507 TO PS4-03-RDIR-0104 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8218 | PS4-03-RDIR-0105-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1507 TO PS4-03-RDIR-0105 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8219 | PS4-03-RDIR-0106-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1507 TO PS4-03-RDIR-0106 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8220 | PS4-03-RDIR-0107-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1507 TO PS4-03-RDIR-0107 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8221 | PS4-03-RDIR-0108-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1508 TO PS4-03-RDIR-0108 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8222 | PS4-03-RDIR-0109-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1508 TO PS4-03-RDIR-0109 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8223 | PS4-03-RDIR-0110-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1508 TO PS4-03-RDIR-0110 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8224 | PS4-03-RDIR-0111-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1508 TO PS4-03-RDIR-0111 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8225 | PS4-03-RDIR-0112-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1508 TO PS4-03-RDIR-0112 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8226 | PS4-03-RDIR-0113-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1508 TO PS4-03-RDIR-0113 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8227 | PS4-03-RDIR-0114-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1509 TO PS4-03-RDIR-0114 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8228 | PS4-03-RDIR-0115-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1509 TO PS4-03-RDIR-0115 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8229 | PS4-03-RDIR-0116-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1509 TO PS4-03-RDIR-0116 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8230 | PS4-03-RDIR-0117-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1509 TO PS4-03-RDIR-0117 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8231 | PS4-03-RDIR-0118-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1509 TO PS4-03-RDIR-0118 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8232 | PS4-03-RDIR-0121-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0121 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8233 | PS4-03-RDIR-0122-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0122 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8234 | PS4-03-RDIR-0123-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0123 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8235 | PS4-03-RDIR-0124-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0124 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8236 | PS4-03-RDIR-0125-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0125 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8237 | PS4-03-RDIR-0126-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0126 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8238 | PS4-03-RDIR-0127-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0127 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8239 | PS4-03-RDIR-0128-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0128 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8240 | PS4-03-RDIR-0129-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0129 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8241 | PS4-03-RDIR-0130-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0130 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8242 | PS4-03-RDIR-0131-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0131 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8243 | PS4-03-RDIR-0132-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0132 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8244 | PS4-03-RDIR-0133-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0133 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8245 | PS4-03-RDIR-0137-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1507 TO PS4-03-RDIR-0137 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8246 | PS4-03-RDIR-0138-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1508 TO PS4-03-RDIR-0138 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8247 | PS4-03-RDIR-0141-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1507 TO PS4-03-RDIR-0141 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8248 | PS4-03-RDIR-0142-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1507 TO PS4-03-RDIR-0142 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8249 | PS4-03-RDIR-0403-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1503 TO PS4-03-RDIR-0403 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-8250 | PS4-03-RDIR-0404-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1503 TO PS4-03-RDIR-0404 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-8251 | PS4-03-RDIR-0405-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1502 TO PS4-03-RDIR-0405 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-8252 | PS4-03-RDIR-0406-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1502 TO PS4-03-RDIR-0406 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-8253 | PS4-03-RDIR-0409-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1503 TO PS4-03-RDIR-0409 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-8254 | PS4-03-RDIR-0411-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1503 TO PS4-03-RDIR-0411 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-8255 | PS4-03-RDIR-0819-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1510 TO PS4-03-RDIR-0819 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8256 | PS4-03-RDIR-0820-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1510 TO PS4-03-RDIR-0820 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8257 | PS4-03-RDIR-0832-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1510 TO PS4-03-RDIR-0832 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8258 | PS4-03-RDIR-0833-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1510 TO PS4-03-RDIR-0833 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8259 | PS4-03-RDOS-1401-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RMAC-1411 TO PS4-03-RDOS-1401 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8260 | PS4-03-RDOS-1402-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-1401 TO PS4-03-RDOS-1402 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8261 | PS4-03-RDOS-1403-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-1402 TO PS4-03-RDOS-1403 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8262 | PS4-03-RDOS-1404-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-1403 TO PS4-03-RDOS-1404 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8263 | PS4-03-RDOS-1405-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-1404 TO PS4-03-RDOS-1405 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8264 | PS4-03-RDOS-1406-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-1503 TO PS4-03-RDOS-1406 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8265 | PS4-03-RDOS-1407-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-1405 TO PS4-03-RDOS-1407 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8266 | PS4-03-RDOS-1408-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-1407 TO PS4-03-RDOS-1408 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8267 | PS4-03-RDOS-1501-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-1603 TO PS4-03-RDOS-1501 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-15 - FZ-15 - Power Generation Building - Generator Room 1 |  | PS4-03-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8268 | PS4-03-RDOS-1502-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-1501 TO PS4-03-RDOS-1502 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-15 - FZ-15 - Power Generation Building - Generator Room 1 |  | PS4-03-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8269 | PS4-03-RDOS-1503-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-1502 TO PS4-03-RDOS-1503 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-15 - FZ-15 - Power Generation Building - Generator Room 1 |  | PS4-03-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8270 | PS4-03-RDOS-1601-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-1703 TO PS4-03-RDOS-1601 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-16 - FZ-16 - Power Generation Building - Generator Room 2 |  | PS4-03-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8271 | PS4-03-RDOS-1602-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-1601 TO PS4-03-RDOS-1602 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-16 - FZ-16 - Power Generation Building - Generator Room 2 |  | PS4-03-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8272 | PS4-03-RDOS-1603-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-1602 TO PS4-03-RDOS-1603 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-16 - FZ-16 - Power Generation Building - Generator Room 2 |  | PS4-03-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8273 | PS4-03-RDOS-1701-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-1803 TO PS4-03-RDOS-1701 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-17 - FZ-17 - Power Generation Building - Generator Room 3 |  | PS4-03-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8274 | PS4-03-RDOS-1702-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-1701 TO PS4-03-RDOS-1702 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-17 - FZ-17 - Power Generation Building - Generator Room 3 |  | PS4-03-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8275 | PS4-03-RDOS-1703-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-1702 TO PS4-03-RDOS-1703 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-17 - FZ-17 - Power Generation Building - Generator Room 3 |  | PS4-03-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8276 | PS4-03-RDOS-1801-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDH-1902 TO PS4-03-RDOS-1801 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-18 - FZ-18 - Power Generation Building - Generator Room 4 |  | PS4-03-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8277 | PS4-03-RDOS-1802-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-1801 TO PS4-03-RDOS-1802 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-18 - FZ-18 - Power Generation Building - Generator Room 4 |  | PS4-03-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8278 | PS4-03-RDOS-1803-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-1802 TO PS4-03-RDOS-1803 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-18 - FZ-18 - Power Generation Building - Generator Room 4 |  | PS4-03-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8279 | PS4-03-RDOS-2101-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RMAC-1409 TO PS4-03-RDOS-2101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-21 - FZ-21 - Power Generation Building - Air Handling Unit |  | PS4-03-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8280 | PS4-03-RDOS-2102-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-2101 TO PS4-03-RDOS-2102 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-21 - FZ-21 - Power Generation Building - Air Handling Unit |  | PS4-03-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8281 | PS4-03-RDOS-2103-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-2102 TO PS4-03-RDOS-2103 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-21 - FZ-21 - Power Generation Building - Air Handling Unit |  | PS4-03-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8282 | PS4-03-RDOS-G101A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-G101B TO PS4-03-RDOS-G101A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-22 - FZ-G1 Guard House |  | PS4-03-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-8283 | PS4-03-RDOS-G101B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SEA-0002 TO PS4-03-RDOS-G101B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-22 - FZ-G1 Guard House |  | PS4-03-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-8284 | PS4-03-RDUIR-0701-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1511 TO PS4-03-RDUIR-0701 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area |  | PS4-03-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8285 | PS4-03-RDUIR-0702-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1511 TO PS4-03-RDUIR-0702 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area |  | PS4-03-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8286 | PS4-03-RDUIR-0703-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1511 TO PS4-03-RDUIR-0703 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area |  | PS4-03-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8287 | PS4-03-RDUIR-0704-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1511 TO PS4-03-RDUIR-0704 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area |  | PS4-03-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8288 | PS4-03-RDUIR-0705-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1511 TO PS4-03-RDUIR-0705 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area |  | PS4-03-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8289 | PS4-03-RDUIR-0907-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1512 TO PS4-03-RDUIR-0907 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8290 | PS4-03-RDUIR-0908-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1512 TO PS4-03-RDUIR-0908 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8291 | PS4-03-RDUIR-1007-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1513 TO PS4-03-RDUIR-1007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8292 | PS4-03-RDUIR-1008-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1513 TO PS4-03-RDUIR-1008 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8293 | PS4-03-RDUIR-1107-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1514 TO PS4-03-RDUIR-1107 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8294 | PS4-03-RDUIR-1108-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1514 TO PS4-03-RDUIR-1108 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8295 | PS4-03-RDUIR-1207-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1516 TO PS4-03-RDUIR-1207 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8296 | PS4-03-RDUIR-1208-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-1516 TO PS4-03-RDUIR-1208 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8297 | PS4-03-RMAC-0101-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2504 TO PS4-03-RMAC-0101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8298 | PS4-03-RMAC-0102-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2504 TO PS4-03-RMAC-0102 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8299 | PS4-03-RMAC-0103-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2504 TO PS4-03-RMAC-0103 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8301 | PS4-03-RMAC-0301-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2509 TO PS4-03-RMAC-0301 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-03 - FZ-03 - Buildings Area |  | PS4-03-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8302 | PS4-03-RMAC-0304-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2509 TO PS4-03-RMAC-0304 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-03 - FZ-03 - Buildings Area |  | PS4-03-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8303 | PS4-03-RMAC-0401-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2509 TO PS4-03-RMAC-0401 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-8304 | PS4-03-RMAC-0402-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2509 TO PS4-03-RMAC-0402 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-8305 | PS4-03-RMAC-0613-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2503 TO PS4-03-RMAC-0613 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8306 | PS4-03-RMAC-0706-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2515 TO PS4-03-RMAC-0706 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area |  | PS4-03-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8307 | PS4-03-RMAC-0707-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2515 TO PS4-03-RMAC-0707 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area |  | PS4-03-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8309 | PS4-03-RMAC-0825-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RMAC-0825 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8310 | PS4-03-RMAC-0827-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2505 TO PS4-03-RMAC-0827 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8311 | PS4-03-RMAC-0834-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2514 TO PS4-03-RMAC-0834 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8312 | PS4-03-RMAC-1301-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-BI-2515 TO PS4-03-RMAC-1301 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-13 - FZ-13 - Power Generation Building - Instrument Air Room |  | PS4-03-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8313 | PS4-03-RMAC-1409-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SEA-0003 TO PS4-03-RMAC-1409 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8314 | PS4-03-RMAC-1410-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-2103 TO PS4-03-RMAC-1410 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8315 | PS4-03-RMAC-1411-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-1406 TO PS4-03-RMAC-1411 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8316 | PS4-03-SEA-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-20 - FZ-20 - Emergency Diesel Generator Enclosure |  | PS4-03-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8325 | PS4-05-BI-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8326 | PS4-05-BI-0002-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-30 14:33 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00069 | sridhar, muthu
T-00069-8327 | PS4-05-BI-0002-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-30 14:40 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00069 | sridhar, muthu
T-00069-8328 | PS4-05-BI-0002-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8329 | PS4-05-BI-0002-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8330 | PS4-05-BI-0002-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8333 | PS4-05-BI-0002-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-30 14:34 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00069 | sridhar, muthu
T-00069-8334 | PS4-05-BI-0002-CJ02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-30 14:36 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00069 | sridhar, muthu
T-00069-8335 | PS4-05-BI-0002-CJ03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-30 14:41 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00069 | sridhar, muthu
T-00069-8336 | PS4-05-GC-8100-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8339 | PS4-05-IE-8101-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8340 | PS4-05-IG-0009-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8341 | PS4-05-IG-0009-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8342 | PS4-05-IG-0009-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-30 14:43 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00069 | sridhar, muthu
T-00069-8343 | PS4-05-LIT-4101-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-30 14:37 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00069 | sridhar, muthu
T-00069-8344 | PS4-05-UH-8100-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-30 14:38 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00069 | sridhar, muthu
T-00069-8345 | PS4-05-UH-8100-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8385 | PS4-25-BI-1802A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-61-IDH-3100A TO PS4-25-BI-1802A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8387 | PS4-25-BI-1802B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-61-IDH-3100B TO PS4-25-BI-1802B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8389 | PS4-25-BI-1802C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-61-IDH-3100C TO PS4-25-BI-1802C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8416 | PS4-25-ESDV-0021-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1201 TO PS4-25-ESDV-0021 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8417 | PS4-25-ESDV-0021-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2201 TO PS4-25-ESDV-0021 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8418 | PS4-25-ESDV-0021-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2203 TO PS4-25-ESDV-0021 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8419 | PS4-25-ESDV-0023-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1201 TO PS4-25-ESDV-0023 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8420 | PS4-25-ESDV-0023-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2201 TO PS4-25-ESDV-0023 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8421 | PS4-25-ESDV-0023-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2203 TO PS4-25-ESDV-0023 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8422 | PS4-25-ESY-0021A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2205 TO PS4-25-ESDV-0021 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8423 | PS4-25-ESY-0021B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2309 TO PS4-25-ESDV-0021 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8424 | PS4-25-ESY-0023B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2309 TO PS4-25-ESDV-0023 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8425 | PS4-25-FCV-0003A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-FCV-0003A-HPU TO PS4-25-FCV-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8426 | PS4-25-FCV-0003B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-FCV-0003B-HPU TO PS4-25-FCV-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8427 | PS4-25-FCV-0003C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-FCV-0003C-HPU TO PS4-25-FCV-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8428 | PS4-25-FCV-0004-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-FCV-0004-HPU TO PS4-25-FCV-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8429 | PS4-25-FIT-0001-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-25-FIT-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8430 | PS4-25-FIT-0003A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-FIT-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8431 | PS4-25-FIT-0003B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-FIT-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8432 | PS4-25-FIT-0003C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1104 TO PS4-25-FIT-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8433 | PS4-25-FIT-0004-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1115 TO PS4-25-FIT-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8434 | PS4-25-FXS-0003A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2106 TO PS4-25-FCV-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8435 | PS4-25-FXS-0003B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2106 TO PS4-25-FCV-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8436 | PS4-25-FXS-0003C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2106 TO PS4-25-FCV-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8437 | PS4-25-FXS-0004-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2105 TO PS4-25-FCV-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8438 | PS4-25-FY-0003A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-FCV-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8439 | PS4-25-FY-0003B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-FCV-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8440 | PS4-25-FY-0003C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1104 TO PS4-25-FCV-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8441 | PS4-25-FY-0004-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1115 TO PS4-25-FCV-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8442 | PS4-25-HS-8101A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-HS-8101A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8443 | PS4-25-HS-8101B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-HS-8101B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8444 | PS4-25-HS-8101C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-HS-8101C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8445 | PS4-25-HS-8102A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-HS-8102A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8446 | PS4-25-HS-8102B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-HS-8102B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8447 | PS4-25-HS-8102C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-HS-8102C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8448 | PS4-25-MOV-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2101 TO PS4-25-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8449 | PS4-25-MOV-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2101 TO PS4-25-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8450 | PS4-25-MOV-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2101 TO PS4-25-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8451 | PS4-25-MOV-0008-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2102 TO PS4-25-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8452 | PS4-25-MOV-0011-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2102 TO PS4-25-MOV-0011 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8453 | PS4-25-MOV-0012-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2102 TO PS4-25-MOV-0012 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8454 | PS4-25-MOV-0025-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2101 TO PS4-25-MOV-0025 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8455 | PS4-25-MOV-0026-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2103 TO PS4-25-MOV-0026 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8456 | PS4-25-MOV-0026-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-25-MOV-0026 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8457 | PS4-25-MOV-0027-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2103 TO PS4-25-MOV-0027 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8458 | PS4-25-MOV-0027-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-25-MOV-0027 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8459 | PS4-25-MOV-0028-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2102 TO PS4-25-MOV-0028 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8460 | PS4-25-MXS-0001-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2101 TO PS4-25-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8461 | PS4-25-MXS-0008-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2102 TO PS4-25-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8462 | PS4-25-MXS-0025-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2101 TO PS4-25-MOV-0025 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8463 | PS4-25-MXS-0028-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2102 TO PS4-25-MOV-0028 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8470 | PS4-25-PDIT-0034A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-PDIT-0034A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8471 | PS4-25-PDIT-0034B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-PDIT-0034B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8472 | PS4-25-PDIT-0034C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1104 TO PS4-25-PDIT-0034C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8473 | PS4-25-PDIT-0050-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-25-PDIT-0050 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8474 | PS4-25-PI-1102B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-PIT-1102 TO PS4-25-PI-1102B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8475 | PS4-25-PI-1202B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-PIT-1202 TO PS4-25-PI-1202B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8476 | PS4-25-PIT-0001-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-25-PIT-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8477 | PS4-25-PIT-0003AA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-FCV-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8478 | PS4-25-PIT-0003BA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-FCV-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8479 | PS4-25-PIT-0003CA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1104 TO PS4-25-FCV-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8480 | PS4-25-PIT-0004AA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1115 TO PS4-25-FCV-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8481 | PS4-25-PIT-0004A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-25-PIT-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8482 | PS4-25-PIT-0004B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-25-PIT-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8483 | PS4-25-PIT-0004C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-25-PIT-0004C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8484 | PS4-25-PIT-0005A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-PIT-0005A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8485 | PS4-25-PIT-0005B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-PIT-0005B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8486 | PS4-25-PIT-0005C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1104 TO PS4-25-PIT-0005C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8487 | PS4-25-PIT-0007A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-PIT-0007A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8488 | PS4-25-PIT-0007B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-PIT-0007B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8489 | PS4-25-PIT-0007C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1104 TO PS4-25-PIT-0007C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8490 | PS4-25-PIT-0008A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1301 TO PS4-25-PIT-0008A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8491 | PS4-25-PIT-0008B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-25-PIT-0008B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8492 | PS4-25-PIT-0008C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-25-PIT-0008C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8493 | PS4-25-PIT-0013-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1115 TO PS4-25-PIT-0013 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8494 | PS4-25-PIT-0018-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-PIT-0018 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8495 | PS4-25-PIT-0022-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1301 TO PS4-25-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8496 | PS4-25-PIT-0035A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-25-SDV-0035A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8497 | PS4-25-PIT-0035B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-25-SDV-0035B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8498 | PS4-25-PIT-0035C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-25-SDV-0035C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8499 | PS4-25-PIT-0036A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-25-SDV-0036A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8500 | PS4-25-PIT-0036B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-25-SDV-0036B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8501 | PS4-25-PIT-0036C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-25-SDV-0036C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8502 | PS4-25-PIT-0046-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-25-SDV-0046 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8504 | PS4-25-PIT-0053-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1115 TO PS4-25-XV-0053 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8505 | PS4-25-PIT-0054A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-25-SDV-0054A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8506 | PS4-25-PIT-0054B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-25-SDV-0054B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8507 | PS4-25-PIT-0054C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-25-SDV-0054C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8508 | PS4-25-PIT-0070-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-XV-0070 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8512 | PS4-25-PIT-1102-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-25-PIT-1102 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8513 | PS4-25-PIT-1202-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-25-PIT-1202 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8514 | PS4-25-SDV-0022-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8515 | PS4-25-SDV-0022-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-SDV-0022-HPU TO PS4-25-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8516 | PS4-25-SDV-0035A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-SDV-0035A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8517 | PS4-25-SDV-0035B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-SDV-0035B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8518 | PS4-25-SDV-0035C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2315 TO PS4-25-SDV-0035C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8519 | PS4-25-SDV-0036A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-SDV-0036A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8520 | PS4-25-SDV-0036B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2315 TO PS4-25-SDV-0036B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8521 | PS4-25-SDV-0036C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2315 TO PS4-25-SDV-0036C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8522 | PS4-25-SDV-0046-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-SDV-0046 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8525 | PS4-25-SDV-0054A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-SDV-0054A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8526 | PS4-25-SDV-0054B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-SDV-0054B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8527 | PS4-25-SDV-0054C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2315 TO PS4-25-SDV-0054C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8529 | PS4-25-SXS-0022-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2302 TO PS4-25-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8530 | PS4-25-SXS-0035A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2301 TO PS4-25-SDV-0035A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8531 | PS4-25-SXS-0035B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2301 TO PS4-25-SDV-0035B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8532 | PS4-25-SXS-0035C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2312 TO PS4-25-SDV-0035C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8533 | PS4-25-SXS-0036A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2301 TO PS4-25-SDV-0036A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8534 | PS4-25-SXS-0036B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2312 TO PS4-25-SDV-0036B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8535 | PS4-25-SXS-0036C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2312 TO PS4-25-SDV-0036C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8536 | PS4-25-SXS-0046-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2312 TO PS4-25-SDV-0046 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8538 | PS4-25-SXS-0054A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2301 TO PS4-25-SDV-0054A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8539 | PS4-25-SXS-0054B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2312 TO PS4-25-SDV-0054B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8540 | PS4-25-SXS-0054C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2312 TO PS4-25-SDV-0054C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8541 | PS4-25-SY-0022-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2308 TO PS4-25-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8542 | PS4-25-SY-0035AA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2308 TO PS4-25-SDV-0035A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8543 | PS4-25-SY-0035AB-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2109 TO PS4-25-SDV-0035A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8544 | PS4-25-SY-0035BA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2308 TO PS4-25-SDV-0035B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8545 | PS4-25-SY-0035BB-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2109 TO PS4-25-SDV-0035B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8546 | PS4-25-SY-0035CA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2316 TO PS4-25-SDV-0035C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8547 | PS4-25-SY-0035CB-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2108 TO PS4-25-SDV-0035C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8548 | PS4-25-SY-0036AA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2308 TO PS4-25-SDV-0036A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8549 | PS4-25-SY-0036AB-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2109 TO PS4-25-SDV-0036A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8550 | PS4-25-SY-0036BA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2316 TO PS4-25-SDV-0036B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8551 | PS4-25-SY-0036BB-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2108 TO PS4-25-SDV-0036B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8552 | PS4-25-SY-0036CA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2316 TO PS4-25-SDV-0036C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8553 | PS4-25-SY-0036CB-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2108 TO PS4-25-SDV-0036C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8554 | PS4-25-SY-0046A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2308 TO PS4-25-SDV-0046 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8555 | PS4-25-SY-0046B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2109 TO PS4-25-SDV-0046 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8557 | PS4-25-SY-0052B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2316 TO PS4-25-SDV-0052 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8558 | PS4-25-SY-0054AA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2308 TO PS4-25-SDV-0054A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8559 | PS4-25-SY-0054AB-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2109 TO PS4-25-SDV-0054A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8560 | PS4-25-SY-0054BA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2316 TO PS4-25-SDV-0054B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8561 | PS4-25-SY-0054BB-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2108 TO PS4-25-SDV-0054B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8562 | PS4-25-SY-0054CA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2316 TO PS4-25-SDV-0054C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8563 | PS4-25-SY-0054CB-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2108 TO PS4-25-SDV-0054C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8564 | PS4-25-TIT-0001-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-25-TIT-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8565 | PS4-25-TIT-0002A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-25-TIT-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8566 | PS4-25-TIT-0002B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-25-TIT-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8567 | PS4-25-TIT-0002C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-25-TIT-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8568 | PS4-25-TIT-0003A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-TIT-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8569 | PS4-25-TIT-0003B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-TIT-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8570 | PS4-25-TIT-0003C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1104 TO PS4-25-TIT-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8571 | PS4-25-TIT-0004-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-25-TIT-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8572 | PS4-25-TIT-1101-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-25-TIT-1101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8573 | PS4-25-TIT-1201-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-25-TIT-1201 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8574 | PS4-25-XV-0053-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2104 TO PS4-25-XV-0053 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8575 | PS4-25-XV-0053-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-XV-0053-HPU TO PS4-25-XV-0053 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8576 | PS4-25-XV-0070-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2104 TO PS4-25-XV-0070 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8577 | PS4-25-XXS-0053-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2105 TO PS4-25-XV-0053 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8578 | PS4-25-XXS-0070-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2105 TO PS4-25-XV-0070 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8579 | PS4-25-XY-0053-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2109 TO PS4-25-XV-0053 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8580 | PS4-25-XY-0070-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2109 TO PS4-25-XV-0070 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8581 | PS4-25-ZIT-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1102 TO PS4-25-ZIT-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8582 | PS4-25-ZIT-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1102 TO PS4-25-ZIT-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8583 | PS4-25-ZS-1101-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2104 TO PS4-25-ZS-1101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8584 | PS4-25-ZS-1201-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2104 TO PS4-25-ZS-1201 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8592 | PS4-28-HXA-1402-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2115 TO PS4-28-HXA-1402 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8593 | PS4-28-HY-3901A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1105 TO PS4-28-HY-3901A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8594 | PS4-28-HY-3901B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1105 TO PS4-28-HY-3901B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8597 | PS4-28-LI-1101B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-LIT-1101 TO PS4-28-LI-1101B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone G | TM-00069
T-00069-8598 | PS4-28-LI-1101C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-28-LI-1101C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone G | TM-00069
T-00069-8599 | PS4-28-LI-1402B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-LIT-1402 TO PS4-28-LI-1402B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8600 | PS4-28-LIT-0002-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-50-BI-1107 TO PS4-28-LIT-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone G | TM-00069
T-00069-8601 | PS4-28-LIT-0008-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-50-BI-1107 TO PS4-28-LIT-0008 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone G | TM-00069
T-00069-8602 | PS4-28-LIT-1101-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1105 TO PS4-28-LIT-1101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone G | TM-00069
T-00069-8603 | PS4-28-LIT-1102-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1303 TO PS4-28-LIT-1102 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone G | TM-00069
T-00069-8604 | PS4-28-LIT-1201-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1106 TO PS4-28-LIT-1201 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump |  | PS4-28-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone G | TM-00069
T-00069-8605 | PS4-28-LIT-1202-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1303 TO PS4-28-LIT-1202 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump |  | PS4-28-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone G | TM-00069
T-00069-8606 | PS4-28-LIT-1301A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-28-LIT-1301A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8607 | PS4-28-LIT-1301B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-28-LIT-1301B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8608 | PS4-28-LIT-1301C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1104 TO PS4-28-LIT-1301C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8609 | PS4-28-LIT-1401-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1307 TO PS4-28-LIT-1401 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8610 | PS4-28-LIT-1402-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1114 TO PS4-28-LIT-1402 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8611 | PS4-28-PIT-0015-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1105 TO PS4-28-PIT-0015 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone G | TM-00069
T-00069-8612 | PS4-28-PIT-0033-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1106 TO PS4-28-PIT-0033 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump |  | PS4-28-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone G | TM-00069
T-00069-8613 | PS4-28-PIT-0041-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1303 TO PS4-28-PIT-0041 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8614 | PS4-28-PIT-0045-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1303 TO PS4-28-SDV-0045 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8615 | PS4-28-PIT-0053A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-28-SDV-0053A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8616 | PS4-28-PIT-0053B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-28-SDV-0053B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8617 | PS4-28-PIT-0053C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-28-SDV-0053C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8618 | PS4-28-PIT-3901A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1303 TO PS4-28-PIT-3901A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8619 | PS4-28-PIT-3901B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1303 TO PS4-28-PIT-3901B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8620 | PS4-28-SDV-0045-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-2304 TO PS4-28-SDV-0045 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8621 | PS4-28-SDV-0045-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-SDV-0045-HPU TO PS4-28-SDV-0045 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8622 | PS4-28-SDV-0053A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-28-SDV-0053A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8623 | PS4-28-SDV-0053A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-SDV-0053A-HPU TO PS4-28-SDV-0053A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8624 | PS4-28-SDV-0053B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2315 TO PS4-28-SDV-0053B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8625 | PS4-28-SDV-0053B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-SDV-0053B-HPU TO PS4-28-SDV-0053B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8626 | PS4-28-SDV-0053C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2315 TO PS4-28-SDV-0053C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8627 | PS4-28-SDV-0053C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-SDV-0053C-HPU TO PS4-28-SDV-0053C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8628 | PS4-28-SXS-0045-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2302 TO PS4-28-SDV-0045 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8629 | PS4-28-SXS-0053A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2301 TO PS4-28-SDV-0053A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8630 | PS4-28-SXS-0053B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2301 TO PS4-28-SDV-0053B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8631 | PS4-28-SXS-0053C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2312 TO PS4-28-SDV-0053C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8632 | PS4-28-SY-0045A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2309 TO PS4-28-SDV-0045 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8633 | PS4-28-SY-0045B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2109 TO PS4-28-SDV-0045 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8634 | PS4-28-SY-0053AA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2308 TO PS4-28-SDV-0053A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8635 | PS4-28-SY-0053AB-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2109 TO PS4-28-SDV-0053A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8636 | PS4-28-SY-0053BA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2308 TO PS4-28-SDV-0053B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8637 | PS4-28-SY-0053BB-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2109 TO PS4-28-SDV-0053B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8638 | PS4-28-SY-0053CA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2316 TO PS4-28-SDV-0053C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8639 | PS4-28-SY-0053CB-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2108 TO PS4-28-SDV-0053C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-8640 | PS4-28-TIT-1104-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1105 TO PS4-28-TIT-1104 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone G | TM-00069
T-00069-8641 | PS4-28-TIT-1105-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1303 TO PS4-28-TIT-1105 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone G | TM-00069
T-00069-8642 | PS4-28-TIT-1201-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1106 TO PS4-28-TIT-1201 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump |  | PS4-28-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone G | TM-00069
T-00069-8643 | PS4-28-TIT-1401-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1114 TO PS4-28-TIT-1401 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8644 | PS4-28-TIT-1402-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1307 TO PS4-28-TIT-1402 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8645 | PS4-28-TIT-2101-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1303 TO PS4-28-TIT-2101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone G | TM-00069
T-00069-8646 | PS4-28-TIT-2201-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1307 TO PS4-28-TIT-2201 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8648 | PS4-50-FIT-0001-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-50-BI-1107 TO PS4-50-FIT-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-50-03 - Water Pre-Treatment Package |  | PS4-50-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-8656 | PS4-53-LIT-4101-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-53-BI-1108 TO PS4-53-LIT-4101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-53-01 - Utility Water / Storage Tank |  | PS4-53-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8657 | PS4-53-LIT-4102-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-53-BI-1304 TO PS4-53-LIT-4102 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-53-01 - Utility Water / Storage Tank |  | PS4-53-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00069
T-00069-8658 | PS4-53-PIT-0005-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-53-BI-1108 TO PS4-53-PIT-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-53-02 - Water Distribution Pump A/B |  | PS4-53-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8659 | PS4-60-BE-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-27 - Compressed Air Starting Skid | 2026-07-08 17:35 | PS4-60-27 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8660 | PS4-60-BE-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-26 - Instrument Air Compressor Skid | 2026-07-22 11:20 | PS4-60-26 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8661 | PS4-60-BE-0004A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0001A TO PS4-60-BE-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-49 - Lube Oil Separator Module PS4-60-UO-81100A | 2026-07-05 12:38 | PS4-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8662 | PS4-60-BE-0004B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0001B TO PS4-60-BE-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-50 - Lube Oil Separator Module PS4-60-UO-81100B | 2026-07-05 12:39 | PS4-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8663 | PS4-60-BE-0004C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0001C TO PS4-60-BE-0004C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-51 - Lube Oil Separator Module PS4-60-UO-81100C |  | PS4-60-51 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8664 | PS4-60-BE-0004D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0001D TO PS4-60-BE-0004D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-52 - Lube Oil Separator Module PS4-60-UO-81100D |  | PS4-60-52 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8665 | PS4-60-BE-0004E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0001E TO PS4-60-BE-0004E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-53 - Lube Oil Separator Module PS4-60-UO-81100E |  | PS4-60-53 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8666 | PS4-60-BE-0004F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0001F TO PS4-60-BE-0004F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-54 - Lube Oil Separator Module PS4-60-UO-81100F |  | PS4-60-54 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8667 | PS4-60-BE-0004G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0001G TO PS4-60-BE-0004G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-55 - Lube Oil Separator Module PS4-60-UO-81100G |  | PS4-60-55 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8668 | PS4-60-BI-0001A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 18:54 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8669 | PS4-60-BI-0001A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 18:52 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8670 | PS4-60-BI-0001B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 19:56 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8671 | PS4-60-BI-0001B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 19:52 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8672 | PS4-60-BI-0001C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0001C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8673 | PS4-60-BI-0001C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0001C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8674 | PS4-60-BI-0001D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0001D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8675 | PS4-60-BI-0001D-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0001D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8676 | PS4-60-BI-0001E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0001E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8677 | PS4-60-BI-0001E-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0001E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8678 | PS4-60-BI-0001F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0001F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8679 | PS4-60-BI-0001F-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0001F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8680 | PS4-60-BI-0001G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0001G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8681 | PS4-60-BI-0001G-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0001G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8682 | PS4-60-BI-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-22 04:52 | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8683 | PS4-60-BI-0002-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-21 21:03 | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8684 | PS4-60-BI-0002-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-21 20:53 | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8685 | PS4-60-BI-0002-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-21 20:50 | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8686 | PS4-60-BI-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-21 20:55 | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8687 | PS4-60-BI-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-21 21:00 | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8688 | PS4-60-BI-0004A-CCO1 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-BI-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-30 14:47 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8689 | PS4-60-BI-0004B-CCO1 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-BI-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-30 14:48 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8690 | PS4-60-BI-0004C-CCO1 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-BI-0004C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8691 | PS4-60-BI-0004D-CCO1 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-BI-0004D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8692 | PS4-60-BI-0004E-CCO1 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-BI-0004E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8693 | PS4-60-BI-0004F-CCO1 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001F TO PS4-60-BI-0004F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8694 | PS4-60-BI-0004G-CCO1 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001G TO PS4-60-BI-0004G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8695 | PS4-60-BI-0005A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0005A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 19:18 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8696 | PS4-60-BI-0005A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0005A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 19:21 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8697 | PS4-60-BI-0005B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0005B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 20:18 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8698 | PS4-60-BI-0005B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0005B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 20:22 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8699 | PS4-60-BI-0005C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0005C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8700 | PS4-60-BI-0005C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0005C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8701 | PS4-60-BI-0005D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0005D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8702 | PS4-60-BI-0005D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0005D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8703 | PS4-60-BI-0005E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0005E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8704 | PS4-60-BI-0005E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0005E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8705 | PS4-60-BI-0005F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0005F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8706 | PS4-60-BI-0005F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0005F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8707 | PS4-60-BI-0005G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0005G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8708 | PS4-60-BI-0005G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0005G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8709 | PS4-60-BI-0006A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-17 04:56 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8710 | PS4-60-BI-0006A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-07-22 18:13 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8711 | PS4-60-BI-0006A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-07-22 18:05 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8712 | PS4-60-BI-0006A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-07-22 18:17 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8713 | PS4-60-BI-0006A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-07-22 18:00 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8714 | PS4-60-BI-0006A-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-07-22 18:07 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8715 | PS4-60-BI-0006B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-22 18:03 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8716 | PS4-60-BI-0006B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-07-22 18:15 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8717 | PS4-60-BI-0006B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-07-22 18:09 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8718 | PS4-60-BI-0006B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-07-22 18:18 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8719 | PS4-60-BI-0006B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-07-22 18:01 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8720 | PS4-60-BI-0006B-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-07-22 18:10 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8721 | PS4-60-BI-0006C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8722 | PS4-60-BI-0006C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8723 | PS4-60-BI-0006C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8724 | PS4-60-BI-0006C-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8725 | PS4-60-BI-0006C-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8726 | PS4-60-BI-0006C-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8727 | PS4-60-BI-0006D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8728 | PS4-60-BI-0006D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8729 | PS4-60-BI-0006D-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8730 | PS4-60-BI-0006D-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8731 | PS4-60-BI-0006D-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8732 | PS4-60-BI-0006D-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8733 | PS4-60-BI-0006E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8734 | PS4-60-BI-0006E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) |  | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8735 | PS4-60-BI-0006E-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) |  | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8736 | PS4-60-BI-0006E-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) |  | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8737 | PS4-60-BI-0006E-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) |  | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8738 | PS4-60-BI-0006E-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) |  | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8739 | PS4-60-BI-0006F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8740 | PS4-60-BI-0006F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) |  | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8741 | PS4-60-BI-0006F-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) |  | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8742 | PS4-60-BI-0006F-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) |  | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8743 | PS4-60-BI-0006F-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) |  | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8744 | PS4-60-BI-0006F-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) |  | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8745 | PS4-60-BI-0006G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8746 | PS4-60-BI-0006G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) |  | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8747 | PS4-60-BI-0006G-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) |  | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8748 | PS4-60-BI-0006G-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) |  | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8749 | PS4-60-BI-0006G-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) |  | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8750 | PS4-60-BI-0006G-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) |  | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8751 | PS4-60-BI-0008A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 19:32 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8752 | PS4-60-BI-0008A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IH-0001A TO PS4-60-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-22 04:57 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8753 | PS4-60-BI-0008B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 19:35 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8754 | PS4-60-BI-0008B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IH-0001A TO PS4-60-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-22 05:02 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8755 | PS4-60-BI-0009A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0009A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-30 14:44 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8756 | PS4-60-BI-0009A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IH-0001B TO PS4-60-BI-0009A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-22 05:04 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8757 | PS4-60-BI-0009B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0009B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-30 14:45 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8758 | PS4-60-BI-0009B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IH-0001B TO PS4-60-BI-0009B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-22 05:06 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8759 | PS4-60-BI-0010A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0010A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A |  | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-8760 | PS4-60-BI-0010A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IH-0001C TO PS4-60-BI-0010A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A |  | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-8761 | PS4-60-BI-0010B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0010B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8762 | PS4-60-BI-0010B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IH-0001C TO PS4-60-BI-0010B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8763 | PS4-60-BI-0011A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A |  | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-8764 | PS4-60-BI-0011A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IH-0001D TO PS4-60-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A |  | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-8765 | PS4-60-BI-0011B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8766 | PS4-60-BI-0011B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IH-0001D TO PS4-60-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8767 | PS4-60-BI-0012A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0012A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A |  | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-8768 | PS4-60-BI-0012A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IH-0001E TO PS4-60-BI-0012A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A |  | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-8769 | PS4-60-BI-0012B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0012B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8770 | PS4-60-BI-0012B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IH-0001E TO PS4-60-BI-0012B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8771 | PS4-60-BI-0013A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0013A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A |  | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-8772 | PS4-60-BI-0013A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IH-0001F TO PS4-60-BI-0013A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A |  | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-8773 | PS4-60-BI-0013B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0013B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8774 | PS4-60-BI-0013B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IH-0001F TO PS4-60-BI-0013B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8775 | PS4-60-BI-0014A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0014A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A |  | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-8776 | PS4-60-BI-0014A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IH-0001G TO PS4-60-BI-0014A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A |  | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-8777 | PS4-60-BI-0014B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0014B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8778 | PS4-60-BI-0014B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IH-0001G TO PS4-60-BI-0014B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8779 | PS4-60-BI-0016A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 19:14 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8780 | PS4-60-BI-0016A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 19:39 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8781 | PS4-60-BI-0016A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 19:02 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8782 | PS4-60-BI-0016A-CCO4 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A |  | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-8783 | PS4-60-BI-0016B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 20:13 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8784 | PS4-60-BI-0016B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 20:46 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8785 | PS4-60-BI-0016B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 20:00 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8786 | PS4-60-BI-0016B-CCO4 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B |  | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-8787 | PS4-60-BI-0016C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8788 | PS4-60-BI-0016C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8789 | PS4-60-BI-0016C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8790 | PS4-60-BI-0016C-CCO4 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8791 | PS4-60-BI-0016D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8792 | PS4-60-BI-0016D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8793 | PS4-60-BI-0016D-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8794 | PS4-60-BI-0016D-CCO4 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8795 | PS4-60-BI-0016E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0016E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8796 | PS4-60-BI-0016E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0016E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8797 | PS4-60-BI-0016E-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0016E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8798 | PS4-60-BI-0016E-CCO4 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-BI-0016E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8799 | PS4-60-BI-0016F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0016F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8800 | PS4-60-BI-0016F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0016F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8801 | PS4-60-BI-0016F-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0016F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8802 | PS4-60-BI-0016F-CCO4 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001F TO PS4-60-BI-0016F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8803 | PS4-60-BI-0016G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0016G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8804 | PS4-60-BI-0016G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0016G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8805 | PS4-60-BI-0016G-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0016G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8806 | PS4-60-BI-0016G-CCO4 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001G TO PS4-60-BI-0016G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8807 | PS4-60-BI-0017A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0017A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A | 2026-07-31 05:15 | PS4-60-56 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8808 | PS4-60-BI-0017B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0017B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B | 2026-07-31 05:19 | PS4-60-58 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8809 | PS4-60-BI-0017C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0017C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C |  | PS4-60-60 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8810 | PS4-60-BI-0017D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0017D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D |  | PS4-60-62 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8811 | PS4-60-BI-0017E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0017E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E |  | PS4-60-64 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8812 | PS4-60-BI-0017F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0017F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F |  | PS4-60-66 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8813 | PS4-60-BI-0017G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0017G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G |  | PS4-60-68 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8814 | PS4-60-BI-0019A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0019A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-31 05:24 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8815 | PS4-60-BI-0019A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0019A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-31 05:26 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8816 | PS4-60-BI-0019B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0019B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-31 05:28 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8817 | PS4-60-BI-0019B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0019B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-31 05:31 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8818 | PS4-60-BI-0019C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0019C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8819 | PS4-60-BI-0019C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0019C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8820 | PS4-60-BI-0019D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0019D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8821 | PS4-60-BI-0019D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0019D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8822 | PS4-60-BI-0019E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0019E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8823 | PS4-60-BI-0019E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0019E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8824 | PS4-60-BI-0019F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0019F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8825 | PS4-60-BI-0019F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0019F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8826 | PS4-60-BI-0019G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0019G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8827 | PS4-60-BI-0019G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0019G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8828 | PS4-60-IE-0002B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002A TO PS4-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 18:11 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8829 | PS4-60-IE-0002C-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002B TO PS4-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8830 | PS4-60-IE-0002D-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002C TO PS4-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8831 | PS4-60-IE-0002E-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002D TO PS4-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8832 | PS4-60-IE-0002F-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002E TO PS4-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8833 | PS4-60-IE-0002G-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002F TO PS4-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8834 | PS4-60-IE-0003A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-17 04:50 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8835 | PS4-60-IE-0003A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-17 04:52 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8836 | PS4-60-IE-0003A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-16 15:00 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8837 | PS4-60-IE-0003A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-17 04:54 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8838 | PS4-60-IE-0003A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-17 04:55 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8839 | PS4-60-IE-0003A-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-16 15:02 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8840 | PS4-60-IE-0003A-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-16 14:58 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8841 | PS4-60-IE-0003A-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-16 15:09 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8842 | PS4-60-IE-0003A-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-16 15:10 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8843 | PS4-60-IE-0003A-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-17 04:47 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8844 | PS4-60-IE-0003A-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-17 04:49 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8845 | PS4-60-IE-0003A-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-16 14:57 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8846 | PS4-60-IE-0003A-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-16 15:04 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8847 | PS4-60-IE-0003A-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-16 15:07 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8852 | PS4-60-IE-0003A-CC25 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-TX-41100A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-16 14:53 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8853 | PS4-60-IE-0003A-CC26 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-TX-41100B TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-16 14:55 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8854 | PS4-60-IE-0003B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-21 17:49 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8855 | PS4-60-IE-0003B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-21 17:52 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8856 | PS4-60-IE-0003B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-21 17:45 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8857 | PS4-60-IE-0003B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-21 17:55 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8858 | PS4-60-IE-0003B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-21 17:58 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8859 | PS4-60-IE-0003B-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-21 18:27 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8860 | PS4-60-IE-0003B-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-21 18:30 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8861 | PS4-60-IE-0003B-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-21 18:46 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8862 | PS4-60-IE-0003B-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-21 18:48 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8863 | PS4-60-IE-0003B-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-21 20:35 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8864 | PS4-60-IE-0003B-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-21 20:38 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8865 | PS4-60-IE-0003B-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-21 18:22 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8866 | PS4-60-IE-0003B-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-21 18:37 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8867 | PS4-60-IE-0003B-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-21 18:42 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8872 | PS4-60-IE-0003B-CC25 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-TX-41200A TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-21 20:04 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8873 | PS4-60-IE-0003B-CC26 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-TX-41200B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-21 20:08 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8874 | PS4-60-IE-0003C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8875 | PS4-60-IE-0003C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8876 | PS4-60-IE-0003C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8877 | PS4-60-IE-0003C-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8878 | PS4-60-IE-0003C-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8879 | PS4-60-IE-0003C-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8880 | PS4-60-IE-0003C-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8881 | PS4-60-IE-0003C-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8882 | PS4-60-IE-0003C-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8883 | PS4-60-IE-0003C-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8884 | PS4-60-IE-0003C-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8885 | PS4-60-IE-0003C-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8886 | PS4-60-IE-0003C-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8887 | PS4-60-IE-0003C-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8892 | PS4-60-IE-0003C-CC25 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-TX-41300A TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8893 | PS4-60-IE-0003C-CC26 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-TX-41300B TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8894 | PS4-60-IE-0003D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8895 | PS4-60-IE-0003D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8896 | PS4-60-IE-0003D-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8897 | PS4-60-IE-0003D-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8898 | PS4-60-IE-0003D-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8899 | PS4-60-IE-0003D-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8900 | PS4-60-IE-0003D-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8901 | PS4-60-IE-0003D-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8902 | PS4-60-IE-0003D-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8903 | PS4-60-IE-0003D-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8904 | PS4-60-IE-0003D-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8905 | PS4-60-IE-0003D-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8906 | PS4-60-IE-0003D-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8907 | PS4-60-IE-0003D-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8912 | PS4-60-IE-0003D-CC25 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-TX-41400A TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8913 | PS4-60-IE-0003D-CC26 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-TX-41400B TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8914 | PS4-60-IE-0003E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8915 | PS4-60-IE-0003E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8916 | PS4-60-IE-0003E-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8917 | PS4-60-IE-0003E-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8918 | PS4-60-IE-0003E-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IE-0001E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8919 | PS4-60-IE-0003E-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8920 | PS4-60-IE-0003E-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8921 | PS4-60-IE-0003E-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8922 | PS4-60-IE-0003E-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8923 | PS4-60-IE-0003E-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8924 | PS4-60-IE-0003E-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8925 | PS4-60-IE-0003E-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8926 | PS4-60-IE-0003E-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8927 | PS4-60-IE-0003E-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8932 | PS4-60-IE-0003E-CC25 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-TX-41500A TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8933 | PS4-60-IE-0003E-CC26 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-TX-41500B TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8934 | PS4-60-IE-0003F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IF-0003F TO PS4-60-IF-0001F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8935 | PS4-60-IE-0003F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IF-0003F TO PS4-60-IF-0001F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8936 | PS4-60-IE-0003F-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8937 | PS4-60-IE-0003F-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IF-0003F TO PS4-60-IF-0001F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8938 | PS4-60-IE-0003F-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IE-0001F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8939 | PS4-60-IE-0003F-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8940 | PS4-60-IE-0003F-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8941 | PS4-60-IE-0003F-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8942 | PS4-60-IE-0003F-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8943 | PS4-60-IE-0003F-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8944 | PS4-60-IE-0003F-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8945 | PS4-60-IE-0003F-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8946 | PS4-60-IE-0003F-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8947 | PS4-60-IE-0003F-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8952 | PS4-60-IE-0003F-CC25 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-TX-41600A TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8953 | PS4-60-IE-0003F-CC26 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-TX-41600B TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8954 | PS4-60-IE-0003G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IG-0003G TO PS4-60-IG-0001G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8955 | PS4-60-IE-0003G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IG-0003G TO PS4-60-IG-0001G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8956 | PS4-60-IE-0003G-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8957 | PS4-60-IE-0003G-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IG-0003G TO PS4-60-IG-0001G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8958 | PS4-60-IE-0003G-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0001G TO PS4-60-IE-0003H | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8959 | PS4-60-IE-0003G-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8960 | PS4-60-IE-0003G-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8961 | PS4-60-IE-0003G-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8962 | PS4-60-IE-0003G-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8963 | PS4-60-IE-0003G-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8964 | PS4-60-IE-0003G-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8965 | PS4-60-IE-0003G-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8966 | PS4-60-IE-0003G-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8967 | PS4-60-IE-0003G-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0002G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8972 | PS4-60-IE-0003G-CC25 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-TX-41700A TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8973 | PS4-60-IE-0003G-CC26 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-TX-41700B TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-8974 | PS4-60-IE-0004-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-8975 | PS4-60-IE-0004-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-8976 | PS4-60-IE-0004-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-8977 | PS4-60-IE-0004-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-8978 | PS4-60-IE-0004-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-8979 | PS4-60-IE-0004-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-8980 | PS4-60-IE-0004-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-8984 | PS4-60-IN-0001A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-49 - Lube Oil Separator Module PS4-60-UO-81100A | 2026-07-05 12:40 | PS4-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8985 | PS4-60-IN-0001A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-49 - Lube Oil Separator Module PS4-60-UO-81100A | 2026-07-05 12:41 | PS4-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8986 | PS4-60-IN-0001A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-49 - Lube Oil Separator Module PS4-60-UO-81100A | 2026-07-05 12:42 | PS4-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8987 | PS4-60-IN-0001A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-49 - Lube Oil Separator Module PS4-60-UO-81100A | 2026-07-05 12:42 | PS4-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8988 | PS4-60-IN-0001B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-50 - Lube Oil Separator Module PS4-60-UO-81100B | 2026-07-05 12:43 | PS4-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8989 | PS4-60-IN-0001B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-50 - Lube Oil Separator Module PS4-60-UO-81100B | 2026-07-05 12:44 | PS4-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8990 | PS4-60-IN-0001B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-50 - Lube Oil Separator Module PS4-60-UO-81100B | 2026-07-05 12:45 | PS4-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8991 | PS4-60-IN-0001B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-50 - Lube Oil Separator Module PS4-60-UO-81100B | 2026-07-05 12:46 | PS4-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-8992 | PS4-60-IN-0001C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-51 - Lube Oil Separator Module PS4-60-UO-81100C |  | PS4-60-51 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8993 | PS4-60-IN-0001C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-51 - Lube Oil Separator Module PS4-60-UO-81100C |  | PS4-60-51 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8994 | PS4-60-IN-0001C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-51 - Lube Oil Separator Module PS4-60-UO-81100C |  | PS4-60-51 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8995 | PS4-60-IN-0001C-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-51 - Lube Oil Separator Module PS4-60-UO-81100C |  | PS4-60-51 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8996 | PS4-60-IN-0001D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-52 - Lube Oil Separator Module PS4-60-UO-81100D |  | PS4-60-52 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8997 | PS4-60-IN-0001D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-52 - Lube Oil Separator Module PS4-60-UO-81100D |  | PS4-60-52 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8998 | PS4-60-IN-0001D-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-52 - Lube Oil Separator Module PS4-60-UO-81100D |  | PS4-60-52 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-8999 | PS4-60-IN-0001D-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-52 - Lube Oil Separator Module PS4-60-UO-81100D |  | PS4-60-52 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9000 | PS4-60-IN-0001E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0001E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-53 - Lube Oil Separator Module PS4-60-UO-81100E |  | PS4-60-53 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9001 | PS4-60-IN-0001E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0001E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-53 - Lube Oil Separator Module PS4-60-UO-81100E |  | PS4-60-53 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9002 | PS4-60-IN-0001E-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0001E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-53 - Lube Oil Separator Module PS4-60-UO-81100E |  | PS4-60-53 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9003 | PS4-60-IN-0001E-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0001E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-53 - Lube Oil Separator Module PS4-60-UO-81100E |  | PS4-60-53 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9004 | PS4-60-IN-0001F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0001F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-54 - Lube Oil Separator Module PS4-60-UO-81100F |  | PS4-60-54 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9005 | PS4-60-IN-0001F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0001F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-54 - Lube Oil Separator Module PS4-60-UO-81100F |  | PS4-60-54 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9006 | PS4-60-IN-0001F-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0001F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-54 - Lube Oil Separator Module PS4-60-UO-81100F |  | PS4-60-54 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9007 | PS4-60-IN-0001F-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0001F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-54 - Lube Oil Separator Module PS4-60-UO-81100F |  | PS4-60-54 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9008 | PS4-60-IN-0001G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0001G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-55 - Lube Oil Separator Module PS4-60-UO-81100G |  | PS4-60-55 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9009 | PS4-60-IN-0001G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0001G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-55 - Lube Oil Separator Module PS4-60-UO-81100G |  | PS4-60-55 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9010 | PS4-60-IN-0001G-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0001G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-55 - Lube Oil Separator Module PS4-60-UO-81100G |  | PS4-60-55 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9011 | PS4-60-IN-0001G-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0001G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-55 - Lube Oil Separator Module PS4-60-UO-81100G |  | PS4-60-55 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9012 | PS4-60-IN-0002A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-07-22 14:26 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9013 | PS4-60-IN-0002A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-07-22 17:54 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9014 | PS4-60-IN-0002A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-07-22 17:45 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9015 | PS4-60-IN-0002A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-07-22 14:31 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9016 | PS4-60-IN-0002A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-07-22 17:47 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9017 | PS4-60-IN-0002A-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-07-22 14:13 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9018 | PS4-60-IN-0002B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-07-22 17:40 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9019 | PS4-60-IN-0002B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-07-22 17:56 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9020 | PS4-60-IN-0002B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-07-22 17:49 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9021 | PS4-60-IN-0002B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-07-22 17:43 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9022 | PS4-60-IN-0002B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-07-22 17:51 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9023 | PS4-60-IN-0002B-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-07-22 14:20 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9024 | PS4-60-IN-0002C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9025 | PS4-60-IN-0002C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9026 | PS4-60-IN-0002C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9027 | PS4-60-IN-0002C-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9028 | PS4-60-IN-0002C-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9029 | PS4-60-IN-0002C-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9030 | PS4-60-IN-0002D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9031 | PS4-60-IN-0002D-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9032 | PS4-60-IN-0002D-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9033 | PS4-60-IN-0002D-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9034 | PS4-60-IN-0002D-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9035 | PS4-60-IN-0002D-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9036 | PS4-60-IN-0002E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) |  | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9037 | PS4-60-IN-0002E-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) |  | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9038 | PS4-60-IN-0002E-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) |  | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9039 | PS4-60-IN-0002E-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) |  | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9040 | PS4-60-IN-0002E-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) |  | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9041 | PS4-60-IN-0002E-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) |  | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9042 | PS4-60-IN-0002F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) |  | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9043 | PS4-60-IN-0002F-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) |  | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9044 | PS4-60-IN-0002F-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) |  | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9045 | PS4-60-IN-0002F-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) |  | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9046 | PS4-60-IN-0002F-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) |  | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9047 | PS4-60-IN-0002F-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) |  | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9048 | PS4-60-IN-0002G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) |  | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9049 | PS4-60-IN-0002G-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) |  | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9050 | PS4-60-IN-0002G-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) |  | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9051 | PS4-60-IN-0002G-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) |  | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9052 | PS4-60-IN-0002G-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) |  | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9053 | PS4-60-IN-0002G-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) |  | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9054 | PS4-60-LA-0002A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 19:24 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9055 | PS4-60-LA-0002A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 19:26 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9056 | PS4-60-LA-0002A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 19:29 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9057 | PS4-60-LA-0002A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 20:25 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9058 | PS4-60-LA-0002A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 20:28 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9059 | PS4-60-LA-0002A-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 20:31 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9060 | PS4-60-LA-0002A-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A |  | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9061 | PS4-60-LA-0002A-CC08 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A |  | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9062 | PS4-60-LA-0002A-CC09 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A |  | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9063 | PS4-60-LA-0002B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9064 | PS4-60-LA-0002B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9065 | PS4-60-LA-0002B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9066 | PS4-60-LA-0002B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9067 | PS4-60-LA-0002B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9068 | PS4-60-LA-0002B-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9069 | PS4-60-LA-0002C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9070 | PS4-60-LA-0002C-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9071 | PS4-60-LA-0002C-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9072 | PS4-60-LA-0002C-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9073 | PS4-60-LA-0002C-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9074 | PS4-60-LA-0002C-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9075 | PS4-60-LA-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9076 | PS4-60-LA-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9077 | PS4-60-LA-0003-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9078 | PS4-60-LIT-4301-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1113 TO PS4-60-LIT-4301 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-24 - Cooling Water Tank & Pump |  | PS4-60-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9079 | PS4-60-LIT-4401-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1113 TO PS4-60-LIT-4401 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-25 - Cooling Water Maintenance Tank & Return Pump |  | PS4-60-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9080 | PS4-60-MOV-0005-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2120 TO PS4-60-MOV-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9081 | PS4-60-MOV-0005-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2124 TO PS4-60-MOV-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9082 | PS4-60-MOV-0006-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2121 TO PS4-60-MOV-0006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9083 | PS4-60-MOV-0006-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2125 TO PS4-60-MOV-0006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9084 | PS4-60-MOV-0011-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2118 TO PS4-60-MOV-0011 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9085 | PS4-60-MOV-0011-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2122 TO PS4-60-MOV-0011 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9086 | PS4-60-MOV-0012-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2119 TO PS4-60-MOV-0012 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9087 | PS4-60-MOV-0012-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2123 TO PS4-60-MOV-0012 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9088 | PS4-60-SEA-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9089 | PS4-60-SEA-0001-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9090 | PS4-60-SEA-0001-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9091 | PS4-60-SEA-0001-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9092 | PS4-60-SEA-0001-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9093 | PS4-60-SEA-0001-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9094 | PS4-60-SEA-0001-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9095 | PS4-60-SEA-0001-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9096 | PS4-60-SEA-0001-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9097 | PS4-60-SEA-0001-CC12 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9098 | PS4-60-SEA-0001-CC13 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9099 | PS4-60-SEA-0001-CC14 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9100 | PS4-60-SEA-0001-CC15 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9101 | PS4-60-SEA-0001-CC16 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9102 | PS4-60-SEA-0001-CC17 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9104 | PS4-60-SY-0007-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-SY-0007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-28 - Air Receiver A & Air Regulator A |  | PS4-60-28 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9105 | PS4-60-SY-0008-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-SY-0008 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-29 - Air Receiver B & Air Regulator B |  | PS4-60-29 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9106 | PS4-60-SY-0009-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-SY-0009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-30 - Air Receiver C & Air Regulator C |  | PS4-60-30 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9107 | PS4-60-SY-0010-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-SY-0010 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-31 - Air Receiver D & Air Regulator D |  | PS4-60-31 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9108 | PS4-60-SY-0011-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-SY-0011 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-32 - Air Receiver E & Air Regulator E |  | PS4-60-32 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9109 | PS4-60-SY-0012-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-SY-0012 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-33 - Air Receiver F & Air Regulator F |  | PS4-60-33 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9110 | PS4-60-SY-0013-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-SY-0013 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-34 - Air Receiver G & Air Regulator G |  | PS4-60-34 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9111 | PS4-60-VS-9101A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-VS-9101A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-42 - Oil Mist Separator Skid PS4-60-VS-9100A | 2026-07-22 05:31 | PS4-60-42 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9112 | PS4-60-VS-9101B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-VS-9101B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-43 - Oil Mist Separator Skid PS4-60-VS-9100B | 2026-07-22 05:37 | PS4-60-43 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9113 | PS4-60-VS-9101C-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-VS-9101C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-44 - Oil Mist Separator Skid PS4-60-VS-9100C |  | PS4-60-44 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9114 | PS4-60-VS-9101D-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-VS-9101D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-45 - Oil Mist Separator Skid PS4-60-VS-9100D |  | PS4-60-45 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9115 | PS4-60-VS-9101E-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-VS-9101E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-46 - Oil Mist Separator Skid PS4-60-VS-9100E |  | PS4-60-46 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9116 | PS4-60-VS-9101F-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-VS-9101F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-47 - Oil Mist Separator Skid PS4-60-VS-9100F |  | PS4-60-47 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9117 | PS4-60-VS-9101G-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-VS-9101G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-48 - Oil Mist Separator Skid PS4-60-VS-9100G |  | PS4-60-48 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9118 | PS4-61-BI-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A |  | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9119 | PS4-61-BI-0001-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A |  | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9120 | PS4-61-BI-0001-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-61-TE-0003A TO PS4-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A |  | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9121 | PS4-61-BI-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B |  | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9122 | PS4-61-BI-0002-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B |  | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9123 | PS4-61-BI-0002-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-61-TE-0003B TO PS4-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B |  | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9124 | PS4-61-BI-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-61-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9125 | PS4-61-BI-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-61-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9126 | PS4-61-BI-0003-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-61-TE-0003C TO PS4-61-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9127 | PS4-61-BI-0004-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-61-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9128 | PS4-61-BI-0004-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-61-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9129 | PS4-61-BI-0004-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-61-TE-0003D TO PS4-61-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9130 | PS4-61-BI-0005-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-61-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9131 | PS4-61-BI-0005-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-61-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9132 | PS4-61-BI-0005-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-61-TE-0003E TO PS4-61-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9133 | PS4-61-BI-0006-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-61-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9134 | PS4-61-BI-0006-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-61-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9135 | PS4-61-BI-0006-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-61-TE-0003F TO PS4-61-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00069
T-00069-9136 | PS4-61-BI-0007-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-61-BI-0007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9137 | PS4-61-BI-0007-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-61-BI-0007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9138 | PS4-61-BI-0007-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-61-TE-0003G TO PS4-61-BI-0007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00069
T-00069-9148 | PS4-71-BAV-0058-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2113 TO PS4-71-BAV-0058 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9149 | PS4-71-BAV-0059-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2113 TO PS4-71-BAV-0059 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9150 | PS4-71-BI-0001A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9151 | PS4-71-BI-0001B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9153 | PS4-71-BI-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0001 TO PS4-71-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9154 | PS4-71-BI-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-21 20:58 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00069 | sridhar, muthu
T-00069-9155 | PS4-71-BI-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0002 TO PS4-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-22 05:20 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00069 | sridhar, muthu
T-00069-9156 | PS4-71-BI-0003-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0002 TO PS4-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-22 05:24 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00069 | sridhar, muthu
T-00069-9157 | PS4-71-BI-0003-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0002 TO PS4-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-22 05:08 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00069 | sridhar, muthu
T-00069-9158 | PS4-71-BI-0004-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0002 TO PS4-71-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-22 05:11 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00069 | sridhar, muthu
T-00069-9159 | PS4-71-BI-0005-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0003 TO PS4-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS4-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9160 | PS4-71-BI-0005-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS4-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9161 | PS4-71-BI-0006-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0003 TO PS4-71-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-22 05:28 | PS4-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9162 | PS4-71-BI-0008A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9163 | PS4-71-BI-0008A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9164 | PS4-71-BI-0008B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9165 | PS4-71-BI-0008B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9166 | PS4-71-BI-0009-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0001 TO PS4-71-BI-0009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9167 | PS4-71-BI-0009-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0001 TO PS4-71-BI-0009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9168 | PS4-71-BI-0009-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0001 TO PS4-71-BI-0009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9169 | PS4-71-BI-0009-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0001 TO PS4-71-BI-0009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9170 | PS4-71-BI-0010-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0001 TO PS4-71-BI-0010 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9171 | PS4-71-BI-0011A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9172 | PS4-71-BI-0011A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9173 | PS4-71-BI-0011A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9174 | PS4-71-BI-0011A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9175 | PS4-71-BI-0011A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9176 | PS4-71-BI-0011B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9177 | PS4-71-BI-0011B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9178 | PS4-71-BI-0011B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9179 | PS4-71-BI-0011B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9180 | PS4-71-BI-0011B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9213 | PS4-71-FCV-0018-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-FCV-0018-HPU TO PS4-71-FCV-0018 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9214 | PS4-71-FCV-0019-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-FCV-0019-HPU TO PS4-71-FCV-0019 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9215 | PS4-71-FCV-0020-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-FCV-0020-HPU TO PS4-71-FCV-0020 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9216 | PS4-71-FIT-0005-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1111 TO PS4-71-FIT-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-17 - Diesel Fuel Distribution Header |  | PS4-71-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9217 | PS4-71-FIT-0011A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-FIT-0011A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9218 | PS4-71-FIT-0011B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-FIT-0011B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9219 | PS4-71-FIT-0012-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1112 TO PS4-71-FIT-0012 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-17 - Diesel Fuel Distribution Header |  | PS4-71-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9220 | PS4-71-FIT-0018-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1110 TO PS4-71-FIT-0018 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9221 | PS4-71-FIT-0019-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1110 TO PS4-71-FIT-0019 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9222 | PS4-71-FIT-0020-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1110 TO PS4-71-FIT-0020 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9223 | PS4-71-FXS-0018-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2107 TO PS4-71-FCV-0018 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9224 | PS4-71-FXS-0019-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2114 TO PS4-71-FCV-0019 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9225 | PS4-71-FXS-0020-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2107 TO PS4-71-FCV-0020 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9226 | PS4-71-FY-0018-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1116 TO PS4-71-FCV-0018 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9227 | PS4-71-FY-0019-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1113 TO PS4-71-FCV-0019 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9228 | PS4-71-FY-0020-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1116 TO PS4-71-FCV-0020 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9229 | PS4-71-IN-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9230 | PS4-71-IN-0001-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9231 | PS4-71-IN-0001-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9232 | PS4-71-IN-0001-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-0011A TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9233 | PS4-71-IN-0001-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-0011B TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9234 | PS4-71-IN-0001-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9235 | PS4-71-IN-0001-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9239 | PS4-71-IN-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-09 - CFO Pre-Pressure Module (UCP) |  | PS4-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9240 | PS4-71-IN-0002-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-09 - CFO Pre-Pressure Module (UCP) |  | PS4-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9241 | PS4-71-IN-0002-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-09 - CFO Pre-Pressure Module (UCP) |  | PS4-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9242 | PS4-71-IN-0002-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-09 - CFO Pre-Pressure Module (UCP) |  | PS4-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9246 | PS4-71-IN-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS4-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9247 | PS4-71-IN-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS4-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9248 | PS4-71-IN-0003-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS4-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9249 | PS4-71-IN-0003-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS4-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9253 | PS4-71-IN-0004A-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9254 | PS4-71-IN-0004A-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9255 | PS4-71-IN-0004A-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9256 | PS4-71-IN-0004A-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-0011A TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9257 | PS4-71-IN-0004A-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-0011A TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9258 | PS4-71-IN-0004A-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9259 | PS4-71-IN-0004A-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9262 | PS4-71-IN-0004A-CC10 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9263 | PS4-71-IN-0004A-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9265 | PS4-71-IN-0004A-CC13 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0004B TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9266 | PS4-71-IN-0004B-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9267 | PS4-71-IN-0004B-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9268 | PS4-71-IN-0004B-CC03 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9269 | PS4-71-IN-0004B-CC04 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-0011B TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9270 | PS4-71-IN-0004B-CC05 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-0011B TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9271 | PS4-71-IN-0004B-CC06 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9272 | PS4-71-IN-0004B-CC07 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9275 | PS4-71-IN-0004B-CC11 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IN-0001 TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9277 | PS4-71-LCV-4101-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-LCV-4101-HPU TO PS4-71-LCV-4101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9278 | PS4-71-LI-4201B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-LIT-4201 TO PS4-71-LI-4201B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9279 | PS4-71-LIT-1201-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1113 TO PS4-71-LIT-1201 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank |  | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9280 | PS4-71-LIT-1202-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1307 TO PS4-71-LIT-1202 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank |  | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9281 | PS4-71-LIT-4101-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-LIT-4101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9282 | PS4-71-LIT-4102-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1305 TO PS4-71-LIT-4102 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9283 | PS4-71-LIT-4201-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-LIT-4201 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9284 | PS4-71-LIT-4202-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1306 TO PS4-71-LIT-4202 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9285 | PS4-71-LIT-4401-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1111 TO PS4-71-LIT-4401 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank |  | PS4-71-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9286 | PS4-71-LIT-4402-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1308 TO PS4-71-LIT-4402 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank |  | PS4-71-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9287 | PS4-71-LXS-4101-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2107 TO PS4-71-LCV-4101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9288 | PS4-71-LY-4101-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-LCV-4101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9289 | PS4-71-MOV-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2120 TO PS4-71-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-22 06:05 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00069 | sridhar, muthu
T-00069-9290 | PS4-71-MOV-0001-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2124 TO PS4-71-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-22 06:59 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00069 | sridhar, muthu
T-00069-9291 | PS4-71-MOV-0002-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2120 TO PS4-71-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-22 06:10 | PS4-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9292 | PS4-71-MOV-0002-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2124 TO PS4-71-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-22 07:03 | PS4-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9293 | PS4-71-MOV-0003-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2121 TO PS4-71-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-22 06:15 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00069 | sridhar, muthu
T-00069-9294 | PS4-71-MOV-0003-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2125 TO PS4-71-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-22 07:05 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00069 | sridhar, muthu
T-00069-9295 | PS4-71-MOV-0004-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2121 TO PS4-71-MOV-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-22 06:39 | PS4-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9296 | PS4-71-MOV-0004-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2125 TO PS4-71-MOV-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-22 07:08 | PS4-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9297 | PS4-71-MOV-0007-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2118 TO PS4-71-MOV-0007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-22 05:57 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00069 | sridhar, muthu
T-00069-9298 | PS4-71-MOV-0007-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2122 TO PS4-71-MOV-0007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-22 06:46 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00069 | sridhar, muthu
T-00069-9299 | PS4-71-MOV-0008-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2118 TO PS4-71-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-22 05:59 | PS4-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9300 | PS4-71-MOV-0008-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2122 TO PS4-71-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-22 06:49 | PS4-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9301 | PS4-71-MOV-0009-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2119 TO PS4-71-MOV-0009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-22 06:00 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00069 | sridhar, muthu
T-00069-9302 | PS4-71-MOV-0009-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2123 TO PS4-71-MOV-0009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-22 06:52 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00069 | sridhar, muthu
T-00069-9303 | PS4-71-MOV-0010-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2119 TO PS4-71-MOV-0010 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-22 06:03 | PS4-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9304 | PS4-71-MOV-0010-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2123 TO PS4-71-MOV-0010 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-22 06:57 | PS4-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00069 | sridhar, muthu
T-00069-9305 | PS4-71-PDIT-0030-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-PDIT-0030 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9306 | PS4-71-PDIT-0056A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1110 TO PS4-71-PDIT-0056A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9307 | PS4-71-PDIT-0056B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1110 TO PS4-71-PDIT-0056B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9308 | PS4-71-PIT-0001-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-28-BI-1307 TO PS4-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank |  | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9309 | PS4-71-PIT-0014-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1111 TO PS4-71-PIT-0014 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-17 - Diesel Fuel Distribution Header |  | PS4-71-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9310 | PS4-71-PIT-0018A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1116 TO PS4-71-FCV-0018 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9311 | PS4-71-PIT-0019A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1113 TO PS4-71-FCV-0019 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9312 | PS4-71-PIT-0020A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1116 TO PS4-71-FCV-0020 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9313 | PS4-71-PIT-0022-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1305 TO PS4-71-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9314 | PS4-71-PIT-0029-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1308 TO PS4-71-SDV-0029 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank |  | PS4-71-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9315 | PS4-71-PIT-0039-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1306 TO PS4-71-SDV-0039 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9316 | PS4-71-PIT-0089-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1117 TO PS4-71-XV-0089 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9317 | PS4-71-PIT-0090-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1117 TO PS4-71-XV-0090 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9318 | PS4-71-PIT-0091-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1113 TO PS4-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9319 | PS4-71-PIT-0092-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1113 TO PS4-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank |  | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9320 | PS4-71-PIT-2402A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-PIT-2402A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9321 | PS4-71-PIT-2402B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-PIT-2402B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9322 | PS4-71-PIT-3301A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1306 TO PS4-71-PIT-3301A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9323 | PS4-71-PIT-3301B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1306 TO PS4-71-PIT-3301B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9324 | PS4-71-PIT-3302A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1110 TO PS4-71-PIT-3302A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9325 | PS4-71-PIT-3302B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1110 TO PS4-71-PIT-3302B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9326 | PS4-71-PIT-3401A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1306 TO PS4-71-PIT-3401A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9327 | PS4-71-PIT-3401B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1306 TO PS4-71-PIT-3401B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9328 | PS4-71-PIT-3402A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1110 TO PS4-71-PIT-3402A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9329 | PS4-71-PIT-3402B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1110 TO PS4-71-PIT-3402B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9330 | PS4-71-PIT-4101A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-LCV-4101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9331 | PS4-71-SDV-0001-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2315 TO PS4-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank |  | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9332 | PS4-71-SDV-0001-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-SDV-0001-HPU TO PS4-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank |  | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9333 | PS4-71-SDV-0022-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2306 TO PS4-71-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9334 | PS4-71-SDV-0022-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-SDV-0022-HPU TO PS4-71-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9335 | PS4-71-SDV-0029-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2307 TO PS4-71-SDV-0029 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank |  | PS4-71-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9336 | PS4-71-SDV-0029-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-SDV-0029-HPU TO PS4-71-SDV-0029 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank |  | PS4-71-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9337 | PS4-71-SDV-0039-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2306 TO PS4-71-SDV-0039 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9338 | PS4-71-SDV-0039-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-SDV-0039-HPU TO PS4-71-SDV-0039 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9339 | PS4-71-SXS-0001-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2312 TO PS4-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank |  | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9340 | PS4-71-SXS-0022-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2314 TO PS4-71-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9341 | PS4-71-SXS-0029-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2313 TO PS4-71-SDV-0029 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank |  | PS4-71-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9342 | PS4-71-SXS-0039-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2314 TO PS4-71-SDV-0039 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9343 | PS4-71-SY-0001-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-BI-2316 TO PS4-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank |  | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9344 | PS4-71-SY-0022-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2310 TO PS4-71-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9345 | PS4-71-SY-0029-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2317 TO PS4-71-SDV-0029 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank |  | PS4-71-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9346 | PS4-71-SY-0039-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2310 TO PS4-71-SDV-0039 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9347 | PS4-71-TIT-0003-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-TIT-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9348 | PS4-71-TIT-0004-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-TIT-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9349 | PS4-71-TIT-0006-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1305 TO PS4-71-TIT-0006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9350 | PS4-71-TIT-0007-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1306 TO PS4-71-TIT-0007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9351 | PS4-71-TIT-2204-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1306 TO PS4-71-TIT-2204 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9352 | PS4-71-TIT-2301-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1305 TO PS4-71-TIT-2301 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9353 | PS4-71-TIT-2402AA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1305 TO PS4-71-TIT-2402AA | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9354 | PS4-71-TIT-2402BA-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1306 TO PS4-71-TIT-2402BA | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9357 | PS4-71-TIT-4102-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-TIT-4102 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9358 | PS4-71-TIT-4103-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1305 TO PS4-71-TIT-4103 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9359 | PS4-71-TIT-4202-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-TIT-4202 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9360 | PS4-71-TIT-4203-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-1306 TO PS4-71-TIT-4203 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9361 | PS4-71-XV-0089-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2116 TO PS4-71-XV-0089 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9362 | PS4-71-XV-0089-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-XV-0089-HPU TO PS4-71-XV-0089 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9363 | PS4-71-XV-0090-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2116 TO PS4-71-XV-0090 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9364 | PS4-71-XV-0090-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-XV-0090-HPU TO PS4-71-XV-0090 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9365 | PS4-71-XV-0091-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2113 TO PS4-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9366 | PS4-71-XV-0091-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-XV-0091-HPU TO PS4-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9367 | PS4-71-XV-0092-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2113 TO PS4-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank |  | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9368 | PS4-71-XV-0092-CC02 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-XV-0092-HPU TO PS4-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank |  | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9369 | PS4-71-XXS-0089-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2107 TO PS4-71-XV-0089 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9370 | PS4-71-XXS-0090-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2107 TO PS4-71-XV-0090 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9371 | PS4-71-XXS-0091-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2114 TO PS4-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9372 | PS4-71-XXS-0092-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2114 TO PS4-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank |  | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9373 | PS4-71-XY-0089-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2101 TO PS4-71-XV-0089 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9374 | PS4-71-XY-0090-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2101 TO PS4-71-XV-0090 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00069
T-00069-9375 | PS4-71-XY-0091-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2115 TO PS4-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9376 | PS4-71-XY-0092-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-BI-2115 TO PS4-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank |  | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00069
T-00069-9379 | PS4-74-PIT-0002-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-50-BI-1107 TO PS4-74-PIT-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-74-04 - Nitrogen Distribution Header |  | PS4-74-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00069
T-00069-9942 | PS4-03-RAB-B403-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SEA-0005 TO PS4-03-RAB-B402 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9943 | PS4-03-RAB-B903-CC01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SEA-0005 TO PS4-03-RAB-B902 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9944 | PS4-03-RAB-W503-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SEA-0006 TO PS4-03-RAB-W503 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9945 | PS4-03-RDHR-W101A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-W201A TO PS4-03-RDHR-W101A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9946 | PS4-03-RDHR-W101B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W101A TO PS4-03-RDHR-W101B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9947 | PS4-03-RDHR-W101C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W101B TO PS4-03-RDHR-W101C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9948 | PS4-03-RDHR-W101D-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W101C TO PS4-03-RDHR-W101D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9949 | PS4-03-RDHR-W101E-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W101D TO PS4-03-RDHR-W101E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9950 | PS4-03-RDHR-W101F-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W101E TO PS4-03-RDHR-W101F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9951 | PS4-03-RDHR-W101G-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W101F TO PS4-03-RDHR-W101G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9952 | PS4-03-RDHR-W101H-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W101G TO PS4-03-RDHR-W101H | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9953 | PS4-03-RDHR-W101I-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W101H TO PS4-03-RDHR-W101I | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9954 | PS4-03-RDHR-W601A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W601A TO PS4-03-RDHR-W601B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9955 | PS4-03-RDHR-W601B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W601B TO PS4-03-RDHR-W601C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9956 | PS4-03-RDHR-W601C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W601C TO PS4-03-RDHR-W601D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9957 | PS4-03-RDHR-W601D-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W601D TO PS4-03-RDHR-W601E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9958 | PS4-03-RDHR-W601E-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W601E TO PS4-03-RDHR-W601F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9959 | PS4-03-RDHR-W601F-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W601F TO PS4-03-RDHR-W601G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9960 | PS4-03-RDHR-W601G-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W601G TO PS4-03-RDHR-W601H | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9961 | PS4-03-RDHR-W601H-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W601H TO PS4-03-RDHR-W601I | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9962 | PS4-03-RDHR-W601I-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W601I TO PS4-03-RDHR-W601J | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9963 | PS4-03-RDHR-W601J-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W601J TO PS4-03-RDHR-W601K | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9964 | PS4-03-RDHR-W601K-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W601K TO PS4-03-RDHR-W601L | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9965 | PS4-03-RDHR-W601L-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W601L TO PS4-03-RDHR-W601M | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9966 | PS4-03-RDHR-W601M-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W601M TO PS4-03-RDHR-W601N | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9967 | PS4-03-RDHR-W601N-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W601N TO PS4-03-RDHR-W601O | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9968 | PS4-03-RDHR-W601O-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W601O TO PS4-03-RDHR-W601P | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9969 | PS4-03-RDHR-W601P-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDHR-W601P TO PS4-03-RMAC-W502 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9970 | PS4-03-RDOS-B101A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B101B TO PS4-03-RDOS-B101A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9971 | PS4-03-RDOS-B101B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B101C TO PS4-03-RDOS-B101B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9972 | PS4-03-RDOS-B101C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B101D TO PS4-03-RDOS-B101C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9973 | PS4-03-RDOS-B101D-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B401A TO PS4-03-RDOS-B101D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9974 | PS4-03-RDOS-B201A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B201B TO PS4-03-RDOS-B201A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9975 | PS4-03-RDOS-B201B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B201C TO PS4-03-RDOS-B201B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9976 | PS4-03-RDOS-B201C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B201D TO PS4-03-RDOS-B201C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9977 | PS4-03-RDOS-B201D-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B201E TO PS4-03-RDOS-B201D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9978 | PS4-03-RDOS-B201E-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SEA-0005 TO PS4-03-RDOS-B201E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9979 | PS4-03-RDOS-B301A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B101A TO PS4-03-RDOS-B301A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9980 | PS4-03-RDOS-B301B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B301A TO PS4-03-RDOS-B301B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9981 | PS4-03-RDOS-B301C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B301B TO PS4-03-RDOS-B301C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9982 | PS4-03-RDOS-B301D-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B301D TO PS4-03-RDOS-B901B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9983 | PS4-03-RDOS-B401A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B401B TO PS4-03-RDOS-B401A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9984 | PS4-03-RDOS-B401B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RMAC-B401 TO PS4-03-RDOS-B401B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9985 | PS4-03-RDOS-B401C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B401D TO PS4-03-RDOS-B401C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9986 | PS4-03-RDOS-B401D-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B501A TO PS4-03-RDOS-B401D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9987 | PS4-03-RDOS-B501A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B601A TO PS4-03-RDOS-B501A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9988 | PS4-03-RDOS-B601A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RMAC-B902 TO PS4-03-RDOS-B601A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9989 | PS4-03-RDOS-B701A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B901A TO PS4-03-RDOS-B701A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9990 | PS4-03-RDOS-B701B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B701B TO PS4-03-RDOS-B701C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9991 | PS4-03-RDOS-B701C-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B701C TO PS4-03-RDOS-B701D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9992 | PS4-03-RDOS-B701D-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B701D TO PS4-03-RDOS-B701E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9993 | PS4-03-RDOS-B701E-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B701E TO PS4-03-RDOS-B701F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9994 | PS4-03-RDOS-B701F-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B701F TO PS4-03-RDOS-B701G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9995 | PS4-03-RDOS-B701G-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B701G TO PS4-03-RDOS-B701I | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9996 | PS4-03-RDOS-B701H-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B701H TO PS4-03-RDOS-B301D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9997 | PS4-03-RDOS-B701I-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B701I TO PS4-03-RDOS-B701H | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9998 | PS4-03-RDOS-B801A-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B801B TO PS4-03-RDOS-B801A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00069-9999 | PS4-03-RDOS-B801B-CJ01 |  |  |  |  | CJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-RDOS-B701A TO PS4-03-RDOS-B801B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00069
T-00070-0067 | PS4-25-FO-0008 |  |  |  |  | CJX11 - Orifice plate | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134006 | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone H | TM-00070
T-00070-0068 | PS4-28-FO-0002A |  |  |  |  | CJX11 - Orifice plate | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135701 | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone G | TM-00070
T-00070-0069 | PS4-28-FO-0002B |  |  |  |  | CJX11 - Orifice plate | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135701 | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone G | TM-00070
T-00070-0070 | PS4-28-FO-0003 |  |  |  |  | CJX11 - Orifice plate | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135402 | PS4 - TZA - PS4 - Tanzania | PS4-28-05 - HP Relief Header |  | PS4-28-05 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone G | TM-00070
T-00070-0071 | PS4-28-FO-0004 |  |  |  |  | CJX11 - Orifice plate | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135402 | PS4 - TZA - PS4 - Tanzania | PS4-28-16 - LP Relief Header |  | PS4-28-16 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone G | TM-00070
T-00070-0072 | PS4-28-FO-0005 |  |  |  |  | CJX11 - Orifice plate | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135402 | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump |  | PS4-28-06 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone G | TM-00070
T-00070-0073 | PS4-28-FO-0006 |  |  |  |  | CJX11 - Orifice plate | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135701 | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone G | TM-00070
T-00070-0074 | PS4-28-FO-0007 |  |  |  |  | CJX11 - Orifice plate | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135401 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone G | TM-00070
T-00070-0075 | PS4-28-FO-0009A |  |  |  |  | CJX11 - Orifice plate | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135404 | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone E | TM-00070
T-00070-0076 | PS4-28-FO-0009B |  |  |  |  | CJX11 - Orifice plate | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135404 | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone E | TM-00070
T-00070-0077 | PS4-50-FE-0001 |  |  |  |  | CJX11 - Orifice plate | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Orifice Flow Element | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135500 | PS4 - TZA - PS4 - Tanzania | PS4-50-03 - Water Pre-Treatment Package |  | PS4-50-03 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone F | TM-00070
T-00070-0078 | PS4-60-FO-0001 |  |  |  |  | CJX11 - Orifice plate | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135121 | PS4 - TZA - PS4 - Tanzania | PS4-60-25 - Cooling Water Maintenance Tank & Return Pump |  | PS4-60-25 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone E | TM-00070
T-00070-0079 | PS4-60-FO-0002 |  |  |  |  | CJX11 - Orifice plate | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135120 | PS4 - TZA - PS4 - Tanzania | PS4-60-24 - Cooling Water Tank & Pump |  | PS4-60-24 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone E | TM-00070
T-00070-0080 | PS4-71-FE-0018 |  |  |  |  | CJX11 - Orifice plate | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Orifice Flow Element | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135007 | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone H | TM-00070
T-00070-0081 | PS4-71-FE-0019 |  |  |  |  | CJX11 - Orifice plate | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Orifice Flow Element | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135008 | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone B | TM-00070
T-00070-0082 | PS4-71-FO-0013A |  |  |  |  | CJX11 - Orifice plate | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135203 | PS4 - TZA - PS4 - Tanzania | PS4-71-16 - Diesel Fuel Supply Pump A/B |  | PS4-71-16 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone F | TM-00070
T-00070-0083 | PS4-71-FO-0013B |  |  |  |  | CJX11 - Orifice plate | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135203 | PS4 - TZA - PS4 - Tanzania | PS4-71-16 - Diesel Fuel Supply Pump A/B |  | PS4-71-16 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone F | TM-00070
T-00070-0084 | PS4-74-FO-0001 |  |  |  |  | CJX11 - Orifice plate | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135002 | PS4 - TZA - PS4 - Tanzania | PS4-74-04 - Nitrogen Distribution Header |  | PS4-74-04 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone F | TM-00070
T-00071-0067 | PS4-09-LB-0006-CX01 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-09-LB-0006 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-09-01 - HVAC for Office and Facilities building |  | PS4-09-01 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone I | TM-00071
T-00071-0068 | PS4-09-LB-0007-CX01 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-09-LB-0007 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-09-04 - HVAC for Workshop & Warehouse |  | PS4-09-04 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone I | TM-00071
T-00071-0069 | PS4-09-LB-0008-CX01 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-09-LB-0008 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone D | TM-00071
T-00071-0070 | PS4-53-LA-0001-CX01 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-53-LA-0001 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-53-04 - Water Treatment Purification Package |  | PS4-53-04 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone F | TM-00071
T-00071-0071 | PS4-60-IE-0004-CX03 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone B | TM-00071
T-00071-0072 | PS4-60-IE-0004-CX04 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone B | TM-00071
T-00071-0073 | PS4-60-LA-0003-CX01 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone B | TM-00071
T-00071-0074 | PS4-74-LB-5101-CX01 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-74-LB-5101 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-74-02 - N2 Generation Skid (UCP) |  | PS4-74-02 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone F | TM-00071
T-00071-0075 | PS4-82-LA-0001-CX01 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-82-LA-0001 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-82-03 - Sewage Treatment Plant Package (UCP) |  | PS4-82-03 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone I | TM-00071
T-00071-0084 | PS4-75-LA-6200-CX01 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-75-LA-6200 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-75-01 - DRA Injection Package |  | PS4-75-01 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone G | TM-00071
T-00071-0091 | PS4-60-LA-0003-CX02 |  |  |  |  | CJX12 - Optical fiber cable | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone B | TM-00071
T-00072-0215 | PS4-25-TW-0001 |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00072
T-00072-0216 | PS4-25-TW-0002A |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134003 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00072
T-00072-0217 | PS4-25-TW-0002B |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134004 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00072
T-00072-0218 | PS4-25-TW-0002C |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134005 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00072
T-00072-0219 | PS4-25-TW-0003A |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134003 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00072
T-00072-0220 | PS4-25-TW-0003B |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134004 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00072
T-00072-0221 | PS4-25-TW-0003C |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134005 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00072
T-00072-0222 | PS4-25-TW-0004 |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00072
T-00072-0223 | PS4-28-TW-1104 |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135401 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Thermowell | I | To be completed | PS4 - Milestone G | TM-00072
T-00072-0224 | PS4-28-TW-1105 |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135401 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Thermowell | I | To be completed | PS4 - Milestone G | TM-00072
T-00072-0225 | PS4-28-TW-1201 |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135402 | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump |  | PS4-28-06 |  |  | Thermowell | I | To be completed | PS4 - Milestone G | TM-00072
T-00072-0226 | PS4-28-TW-1401 |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135404 | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Thermowell | I | To be completed | PS4 - Milestone E | TM-00072
T-00072-0227 | PS4-28-TW-1402 |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135404 | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Thermowell | I | To be completed | PS4 - Milestone E | TM-00072
T-00072-0228 | PS4-60-TW-0005A |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135100 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-06-30 14:55 | PS4-60-70 |  |  | Thermowell | I | Closed | PS4 - Milestone B | TM-00072 | sridhar, muthu
T-00072-0229 | PS4-60-TW-0005B |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135103 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-06-30 14:56 | PS4-60-71 |  |  | Thermowell | I | Closed | PS4 - Milestone B | TM-00072 | sridhar, muthu
T-00072-0230 | PS4-60-TW-0005C |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135106 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system | 2026-07-29 11:10 | PS4-60-72 |  |  | Thermowell | I | Closed | PS4 - Milestone D | TM-00072 | sridhar, muthu
T-00072-0231 | PS4-60-TW-0005D |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135109 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system | 2026-07-29 11:15 | PS4-60-73 |  |  | Thermowell | I | Closed | PS4 - Milestone D | TM-00072 | sridhar, muthu
T-00072-0232 | PS4-60-TW-0005E |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135112 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | Thermowell | I | To be completed | PS4 - Milestone D | TM-00072
T-00072-0233 | PS4-60-TW-0005F |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135115 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | Thermowell | I | To be completed | PS4 - Milestone D | TM-00072
T-00072-0234 | PS4-60-TW-0005G |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135118 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | Thermowell | I | To be completed | PS4 - Milestone E | TM-00072
T-00072-0235 | PS4-60-TW-0006A |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135100 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-06-30 14:58 | PS4-60-70 |  |  | Thermowell | I | Closed | PS4 - Milestone B | TM-00072 | sridhar, muthu
T-00072-0236 | PS4-60-TW-0006B |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135103 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-06-30 14:59 | PS4-60-71 |  |  | Thermowell | I | Closed | PS4 - Milestone B | TM-00072 | sridhar, muthu
T-00072-0237 | PS4-60-TW-0006C |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135106 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system | 2026-07-29 11:20 | PS4-60-72 |  |  | Thermowell | I | Closed | PS4 - Milestone D | TM-00072 | sridhar, muthu
T-00072-0238 | PS4-60-TW-0006D |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135109 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system | 2026-07-29 11:23 | PS4-60-73 |  |  | Thermowell | I | Closed | PS4 - Milestone D | TM-00072 | sridhar, muthu
T-00072-0239 | PS4-60-TW-0006E |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135112 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | Thermowell | I | To be completed | PS4 - Milestone D | TM-00072
T-00072-0240 | PS4-60-TW-0006F |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135115 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | Thermowell | I | To be completed | PS4 - Milestone D | TM-00072
T-00072-0241 | PS4-60-TW-0006G |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135118 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | Thermowell | I | To be completed | PS4 - Milestone E | TM-00072
T-00072-0242 | PS4-60-TW-0007A |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135100 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-06-30 15:00 | PS4-60-70 |  |  | Thermowell | I | Closed | PS4 - Milestone B | TM-00072 | sridhar, muthu
T-00072-0243 | PS4-60-TW-0007B |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135103 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-06-30 15:01 | PS4-60-71 |  |  | Thermowell | I | Closed | PS4 - Milestone B | TM-00072 | sridhar, muthu
T-00072-0244 | PS4-60-TW-0007C |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135106 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system | 2026-07-29 11:27 | PS4-60-72 |  |  | Thermowell | I | Closed | PS4 - Milestone D | TM-00072 | sridhar, muthu
T-00072-0245 | PS4-60-TW-0007D |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135109 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system | 2026-07-29 11:30 | PS4-60-73 |  |  | Thermowell | I | Closed | PS4 - Milestone D | TM-00072 | sridhar, muthu
T-00072-0246 | PS4-60-TW-0007E |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135112 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | Thermowell | I | To be completed | PS4 - Milestone D | TM-00072
T-00072-0247 | PS4-60-TW-0007F |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135115 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | Thermowell | I | To be completed | PS4 - Milestone D | TM-00072
T-00072-0248 | PS4-60-TW-0007G |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135118 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | Thermowell | I | To be completed | PS4 - Milestone E | TM-00072
T-00072-0249 | PS4-60-TW-0008A |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135100 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-06-30 15:02 | PS4-60-70 |  |  | Thermowell | I | Closed | PS4 - Milestone B | TM-00072 | sridhar, muthu
T-00072-0250 | PS4-60-TW-0008B |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135103 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-06-30 15:02 | PS4-60-71 |  |  | Thermowell | I | Closed | PS4 - Milestone B | TM-00072 | sridhar, muthu
T-00072-0251 | PS4-60-TW-0008C |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135106 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system | 2026-07-29 11:36 | PS4-60-72 |  |  | Thermowell | I | Closed | PS4 - Milestone D | TM-00072 | sridhar, muthu
T-00072-0252 | PS4-60-TW-0008D |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135109 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system | 2026-07-29 11:39 | PS4-60-73 |  |  | Thermowell | I | Closed | PS4 - Milestone D | TM-00072 | sridhar, muthu
T-00072-0253 | PS4-60-TW-0008E |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135112 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | Thermowell | I | To be completed | PS4 - Milestone D | TM-00072
T-00072-0254 | PS4-60-TW-0008F |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135115 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | Thermowell | I | To be completed | PS4 - Milestone D | TM-00072
T-00072-0255 | PS4-60-TW-0008G |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135118 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | Thermowell | I | To be completed | PS4 - Milestone E | TM-00072
T-00072-0256 | PS4-71-TW-0003 |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00072
T-00072-0257 | PS4-71-TW-0004 |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00072
T-00072-0258 | PS4-71-TW-0006 |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00072
T-00072-0259 | PS4-71-TW-0007 |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00072
T-00072-0260 | PS4-71-TW-4102 |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135000 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00072
T-00072-0261 | PS4-71-TW-4103 |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135000 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00072
T-00072-0262 | PS4-71-TW-4202 |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135003 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00072
T-00072-0263 | PS4-71-TW-4203 |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135003 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00072
T-00072-0264 | PS4-74-TW-0001 |  |  |  |  | CJX13 - Thermowell | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135002 | PS4 - TZA - PS4 - Tanzania | PS4-74-04 - Nitrogen Distribution Header |  | PS4-74-04 |  |  | Thermowell | I | To be completed | PS4 - Milestone F | TM-00072
T-00075-0274 | PS4-25-PG-0010 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone H | TM-00075
T-00075-0275 | PS4-25-PG-0019 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone H | TM-00075
T-00075-0276 | PS4-25-PG-1101A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone H | TM-00075
T-00075-0277 | PS4-25-PG-1101B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone H | TM-00075
T-00075-0278 | PS4-25-PG-1201A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone H | TM-00075
T-00075-0279 | PS4-25-PG-1201B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone H | TM-00075
T-00075-0280 | PS4-28-PG-0001 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135701 | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone G | TM-00075
T-00075-0281 | PS4-28-PG-0007A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135701 | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone G | TM-00075
T-00075-0282 | PS4-28-PG-0007B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135701 | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone G | TM-00075
T-00075-0283 | PS4-28-PG-0014A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134009 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone G | TM-00075
T-00075-0284 | PS4-28-PG-0014B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134009 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone G | TM-00075
T-00075-0285 | PS4-28-PG-0067A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134009 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone G | TM-00075
T-00075-0286 | PS4-28-PG-0067B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134009 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone G | TM-00075
T-00075-0287 | PS4-28-PG-0070A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135405 | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone H | TM-00075
T-00075-0288 | PS4-28-PG-0070B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135406 | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone H | TM-00075
T-00075-0289 | PS4-28-PG-0070C |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135407 | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone H | TM-00075
T-00075-0290 | PS4-28-PG-0071 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135404 | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone E | TM-00075
T-00075-0291 | PS4-28-PG-1101 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135401 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone G | TM-00075
T-00075-0292 | PS4-28-PG-1201 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135402 | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump |  | PS4-28-06 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone G | TM-00075
T-00075-0293 | PS4-28-PG-1401 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135404 | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone E | TM-00075
T-00075-0294 | PS4-53-PG-0022A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135501 | PS4 - TZA - PS4 - Tanzania | PS4-53-02 - Water Distribution Pump A/B |  | PS4-53-02 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone E | TM-00075
T-00075-0295 | PS4-53-PG-0022B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135501 | PS4 - TZA - PS4 - Tanzania | PS4-53-02 - Water Distribution Pump A/B |  | PS4-53-02 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone E | TM-00075
T-00075-0296 | PS4-60-LG-0001 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Magnetic Level Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135121 | PS4 - TZA - PS4 - Tanzania | PS4-60-25 - Cooling Water Maintenance Tank & Return Pump |  | PS4-60-25 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone E | TM-00075
T-00075-0297 | PS4-60-PG-0002A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135128 | PS4 - TZA - PS4 - Tanzania | PS4-60-28 - Air Receiver A & Air Regulator A |  | PS4-60-28 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone B | TM-00075
T-00075-0298 | PS4-60-PG-0002B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135128 | PS4 - TZA - PS4 - Tanzania | PS4-60-29 - Air Receiver B & Air Regulator B |  | PS4-60-29 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone B | TM-00075
T-00075-0299 | PS4-60-PG-0002C |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135128 | PS4 - TZA - PS4 - Tanzania | PS4-60-30 - Air Receiver C & Air Regulator C |  | PS4-60-30 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0300 | PS4-60-PG-0002D |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135128 | PS4 - TZA - PS4 - Tanzania | PS4-60-31 - Air Receiver D & Air Regulator D |  | PS4-60-31 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0301 | PS4-60-PG-0002E |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135128 | PS4 - TZA - PS4 - Tanzania | PS4-60-32 - Air Receiver E & Air Regulator E |  | PS4-60-32 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0302 | PS4-60-PG-0002F |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135128 | PS4 - TZA - PS4 - Tanzania | PS4-60-33 - Air Receiver F & Air Regulator F |  | PS4-60-33 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0303 | PS4-60-PG-0002G |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135128 | PS4 - TZA - PS4 - Tanzania | PS4-60-34 - Air Receiver G & Air Regulator G |  | PS4-60-34 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone E | TM-00075
T-00075-0304 | PS4-60-PG-0027 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135120 | PS4 - TZA - PS4 - Tanzania | PS4-60-24 - Cooling Water Tank & Pump |  | PS4-60-24 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone E | TM-00075
T-00075-0305 | PS4-60-TG-0005A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135100 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-06-30 15:04 | PS4-60-70 |  |  | Local Gauge/Indicator | I | Closed | PS4 - Milestone B | TM-00075 | sridhar, muthu
T-00075-0306 | PS4-60-TG-0005B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135103 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-06-30 15:05 | PS4-60-71 |  |  | Local Gauge/Indicator | I | Closed | PS4 - Milestone B | TM-00075 | sridhar, muthu
T-00075-0307 | PS4-60-TG-0005C |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135106 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system | 2026-07-29 11:52 | PS4-60-72 |  |  | Local Gauge/Indicator | I | Closed | PS4 - Milestone D | TM-00075 | sridhar, muthu
T-00075-0308 | PS4-60-TG-0005D |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135109 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system | 2026-07-29 11:55 | PS4-60-73 |  |  | Local Gauge/Indicator | I | Closed | PS4 - Milestone D | TM-00075 | sridhar, muthu
T-00075-0309 | PS4-60-TG-0005E |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135112 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0310 | PS4-60-TG-0005F |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135115 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0311 | PS4-60-TG-0005G |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135118 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone E | TM-00075
T-00075-0312 | PS4-60-TG-0006A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135100 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-06-30 15:12 | PS4-60-70 |  |  | Local Gauge/Indicator | I | Closed | PS4 - Milestone B | TM-00075 | sridhar, muthu
T-00075-0313 | PS4-60-TG-0006B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135103 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-06-30 15:13 | PS4-60-71 |  |  | Local Gauge/Indicator | I | Closed | PS4 - Milestone B | TM-00075 | sridhar, muthu
T-00075-0314 | PS4-60-TG-0006C |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135106 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system | 2026-07-29 11:58 | PS4-60-72 |  |  | Local Gauge/Indicator | I | Closed | PS4 - Milestone D | TM-00075 | sridhar, muthu
T-00075-0315 | PS4-60-TG-0006D |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135109 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system | 2026-07-29 12:03 | PS4-60-73 |  |  | Local Gauge/Indicator | I | Closed | PS4 - Milestone D | TM-00075 | sridhar, muthu
T-00075-0316 | PS4-60-TG-0006E |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135112 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0317 | PS4-60-TG-0006F |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135115 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0318 | PS4-60-TG-0006G |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135118 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone E | TM-00075
T-00075-0319 | PS4-60-TG-0007A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135100 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-07-01 04:48 | PS4-60-70 |  |  | Local Gauge/Indicator | I | Closed | PS4 - Milestone B | TM-00075 | sridhar, muthu
T-00075-0320 | PS4-60-TG-0007B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135103 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-07-01 04:49 | PS4-60-71 |  |  | Local Gauge/Indicator | I | Closed | PS4 - Milestone B | TM-00075 | sridhar, muthu
T-00075-0321 | PS4-60-TG-0007C |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135106 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system | 2026-07-29 12:10 | PS4-60-72 |  |  | Local Gauge/Indicator | I | Closed | PS4 - Milestone D | TM-00075 | sridhar, muthu
T-00075-0322 | PS4-60-TG-0007D |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135109 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system | 2026-07-29 12:13 | PS4-60-73 |  |  | Local Gauge/Indicator | I | Closed | PS4 - Milestone D | TM-00075 | sridhar, muthu
T-00075-0323 | PS4-60-TG-0007E |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135112 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0324 | PS4-60-TG-0007F |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135115 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0325 | PS4-60-TG-0007G |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135118 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone E | TM-00075
T-00075-0326 | PS4-60-TG-0008A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135100 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-07-01 04:50 | PS4-60-70 |  |  | Local Gauge/Indicator | I | Closed | PS4 - Milestone B | TM-00075 | sridhar, muthu
T-00075-0327 | PS4-60-TG-0008B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135103 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-07-01 04:51 | PS4-60-71 |  |  | Local Gauge/Indicator | I | Closed | PS4 - Milestone B | TM-00075 | sridhar, muthu
T-00075-0328 | PS4-60-TG-0008C |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135106 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system | 2026-07-29 12:27 | PS4-60-72 |  |  | Local Gauge/Indicator | I | Closed | PS4 - Milestone D | TM-00075 | sridhar, muthu
T-00075-0329 | PS4-60-TG-0008D |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135109 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system | 2026-07-29 12:32 | PS4-60-73 |  |  | Local Gauge/Indicator | I | Closed | PS4 - Milestone D | TM-00075 | sridhar, muthu
T-00075-0330 | PS4-60-TG-0008E |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135112 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0331 | PS4-60-TG-0008F |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135115 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0332 | PS4-60-TG-0008G |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135118 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone E | TM-00075
T-00075-0333 | PS4-71-PDG-0043A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Diff Press Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135203 | PS4 - TZA - PS4 - Tanzania | PS4-71-16 - Diesel Fuel Supply Pump A/B |  | PS4-71-16 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone F | TM-00075
T-00075-0334 | PS4-71-PDG-0043B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Diff Press Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135203 | PS4 - TZA - PS4 - Tanzania | PS4-71-16 - Diesel Fuel Supply Pump A/B |  | PS4-71-16 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone F | TM-00075
T-00075-0335 | PS4-71-PDG-0049A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Diff Press Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135008 | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone B | TM-00075
T-00075-0336 | PS4-71-PDG-0049B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Diff Press Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135008 | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone B | TM-00075
T-00075-0337 | PS4-71-PG-0005 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135200 | PS4 - TZA - PS4 - Tanzania | PS4-71-14 - Diesel Fuel Transfer and Dispensing Station |  | PS4-71-14 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone F | TM-00075
T-00075-0338 | PS4-71-PG-0006A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135203 | PS4 - TZA - PS4 - Tanzania | PS4-71-16 - Diesel Fuel Supply Pump A/B |  | PS4-71-16 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone F | TM-00075
T-00075-0339 | PS4-71-PG-0006B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135203 | PS4 - TZA - PS4 - Tanzania | PS4-71-16 - Diesel Fuel Supply Pump A/B |  | PS4-71-16 |  |  | Local Gauge/Indicator | I | Started (not Completed) | PS4 - Milestone F | TM-00075
T-00075-0340 | PS4-71-PG-0007 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135200 | PS4 - TZA - PS4 - Tanzania | PS4-71-14 - Diesel Fuel Transfer and Dispensing Station |  | PS4-71-14 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone F | TM-00075
T-00075-0341 | PS4-71-PG-0044 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135000 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone H | TM-00075
T-00075-0342 | PS4-71-PG-0045 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135003 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone H | TM-00075
T-00075-0343 | PS4-71-PG-0050A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135008 | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone B | TM-00075
T-00075-0344 | PS4-71-PG-0050B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135008 | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone B | TM-00075
T-00075-0345 | PS4-71-PG-0053A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135006 | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone H | TM-00075
T-00075-0346 | PS4-71-PG-0053B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135006 | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone H | TM-00075
T-00075-0347 | PS4-71-PG-0059A |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135007 | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone H | TM-00075
T-00075-0348 | PS4-71-PG-0059B |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135007 | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone H | TM-00075
T-00075-0349 | PS4-74-PG-0001 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Pressure Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135800 | PS4 - TZA - PS4 - Tanzania | PS4-74-03 - Nitrogen Receiver |  | PS4-74-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone F | TM-00075
T-00075-0350 | PS4-74-TG-0001 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Temperature Gauge | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135002 | PS4 - TZA - PS4 - Tanzania | PS4-74-04 - Nitrogen Distribution Header |  | PS4-74-04 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone F | TM-00075
T-00075-0351 | PS4-09-PI-8401 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRESSURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0352 | PS4-09-PI-8402 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRESSURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0353 | PS4-09-PI-8403 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRESSURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0354 | PS4-09-PI-8404 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRESSURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0355 | PS4-09-PI-8405 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRESSURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0356 | PS4-09-PI-8406 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRESSURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0357 | PS4-09-PI-8407 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRESSURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0358 | PS4-09-PI-8408 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRESSURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0359 | PS4-09-PI-8409 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRESSURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0360 | PS4-09-PI-8411 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRESSURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0361 | PS4-09-PI-8412 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRESSURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0362 | PS4-09-PI-8413 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRESSURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0363 | PS4-09-PI-8414 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRESSURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0364 | PS4-09-PI-8415 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRESSURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0365 | PS4-09-PI-8416 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | PRESSURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0366 | PS4-09-TI-8401 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0367 | PS4-09-TI-8402 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0368 | PS4-09-TI-8403 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0369 | PS4-09-TI-8404 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0370 | PS4-09-TI-8405 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0371 | PS4-09-TI-8406 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0372 | PS4-09-TI-8407 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0373 | PS4-09-TI-8408 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0374 | PS4-09-TI-8409 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00075-0375 | PS4-09-TI-8411 |  |  |  |  | CJX16 - Local gauge / indicator | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TEMPERATURE INDICATOR | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Local Gauge/Indicator | I | To be completed | PS4 - Milestone D | TM-00075
T-00076-0015 | PS4-71-PSE-2401A |  |  |  |  | CJX20 - Bursting disc | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Bursting Disc | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Bursting Disc | I | To be completed | PS4 - Milestone H | TM-00076
T-00076-0016 | PS4-71-PSE-2401B |  |  |  |  | CJX20 - Bursting disc | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Bursting Disc | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Bursting Disc | I | To be completed | PS4 - Milestone H | TM-00076
T-00077-0264 | PS4-25-ESDV-0021 |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Emergency Shut Down Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0265 | PS4-25-ESDV-0023 |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Emergency Shut Down Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0266 | PS4-25-SDV-0022 |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Shutdown Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0267 | PS4-25-SDV-0035A |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Shutdown Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134003 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0268 | PS4-25-SDV-0035B |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Shutdown Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134004 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0269 | PS4-25-SDV-0035C |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Shutdown Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134005 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0270 | PS4-25-SDV-0036A |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Shutdown Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134003 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0271 | PS4-25-SDV-0036B |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Shutdown Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134004 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0272 | PS4-25-SDV-0036C |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Shutdown Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134005 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0273 | PS4-25-SDV-0046 |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Shutdown Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134006 | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0274 | PS4-25-SDV-0052 |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Shutdown Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0275 | PS4-25-SDV-0054A |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Shutdown Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134003 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0276 | PS4-25-SDV-0054B |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Shutdown Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134003 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0277 | PS4-25-SDV-0054C |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Shutdown Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134003 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0278 | PS4-25-XV-0053 |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | On / Off Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134006 | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0279 | PS4-25-XV-0070 |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | On / Off Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134003 | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0280 | PS4-28-SDV-0045 |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Shutdown Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0281 | PS4-28-SDV-0053A |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Shutdown Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135405 | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0282 | PS4-28-SDV-0053B |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Shutdown Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135406 | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0283 | PS4-28-SDV-0053C |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Shutdown Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135407 | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0284 | PS4-71-SDV-0001 |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Shutdown Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135205 | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank |  | PS4-71-20 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone B | TM-00077
T-00077-0285 | PS4-71-SDV-0022 |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Shutdown Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135000 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0286 | PS4-71-SDV-0029 |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Shutdown Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135201 | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank |  | PS4-71-15 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone F | TM-00077
T-00077-0287 | PS4-71-SDV-0039 |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Shutdown Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135003 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0288 | PS4-71-XV-0089 |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | On / Off Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135010 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0289 | PS4-71-XV-0090 |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | On / Off Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135003 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00077
T-00077-0290 | PS4-71-XV-0091 |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | On / Off Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135205 | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone F | TM-00077
T-00077-0291 | PS4-71-XV-0092 |  |  |  |  | CJX23 - Actuated on/off valve - Pneumatic/Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | On / Off Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135205 | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank |  | PS4-71-20 |  |  | Actuated on/off Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone B | TM-00077
T-00078-0127 | PS4-25-MOV-0001 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Actuated on/off Valve | I | To be completed | PS4 - Milestone H | TM-00078
T-00078-0128 | PS4-25-MOV-0008 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Actuated on/off Valve | I | To be completed | PS4 - Milestone H | TM-00078
T-00078-0129 | PS4-25-MOV-0025 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Actuated on/off Valve | I | To be completed | PS4 - Milestone H | TM-00078
T-00078-0130 | PS4-25-MOV-0028 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Actuated on/off Valve | I | To be completed | PS4 - Milestone H | TM-00078
T-00078-0135 | PS4-25-MOV-0026 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Actuated on/off Valve | I | To be completed | PS4 - Milestone H | TM-00078
T-00078-0136 | PS4-25-MOV-0027 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Actuated on/off Valve | I | To be completed | PS4 - Milestone H | TM-00078
T-00078-0156 | PS4-25-MOV-0002 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Actuated on/off Valve | I | To be completed | PS4 - Milestone H | TM-00078
T-00078-0157 | PS4-25-MOV-0003 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Actuated on/off Valve | I | To be completed | PS4 - Milestone H | TM-00078
T-00078-0158 | PS4-25-MOV-0011 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Actuated on/off Valve | I | To be completed | PS4 - Milestone H | TM-00078
T-00078-0159 | PS4-25-MOV-0012 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Actuated on/off Valve | I | To be completed | PS4 - Milestone H | TM-00078
T-00078-0160 | PS4-60-MOV-0005 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Actuated on/off Valve | I | To be completed | PS4 - Milestone H | TM-00078
T-00078-0161 | PS4-60-MOV-0006 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Actuated on/off Valve | I | To be completed | PS4 - Milestone H | TM-00078
T-00078-0162 | PS4-60-MOV-0011 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135138 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Actuated on/off Valve | I | To be completed | PS4 - Milestone H | TM-00078
T-00078-0163 | PS4-60-MOV-0012 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135138 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Actuated on/off Valve | I | To be completed | PS4 - Milestone H | TM-00078
T-00078-0164 | PS4-71-MOV-0001 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module |  | PS4-71-08 |  |  | Actuated on/off Valve | I | To be completed | PS4 - Milestone H | TM-00078
T-00078-0165 | PS4-71-MOV-0002 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-21 12:52 | PS4-71-22 |  |  | Actuated on/off Valve | I | Closed | PS4 - Milestone B | TM-00078 | sridhar, muthu
T-00078-0166 | PS4-71-MOV-0003 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module |  | PS4-71-08 |  |  | Actuated on/off Valve | I | To be completed | PS4 - Milestone H | TM-00078
T-00078-0167 | PS4-71-MOV-0004 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-21 12:54 | PS4-71-22 |  |  | Actuated on/off Valve | I | Closed | PS4 - Milestone B | TM-00078 | sridhar, muthu
T-00078-0168 | PS4-71-MOV-0007 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135138 | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module |  | PS4-71-08 |  |  | Actuated on/off Valve | I | To be completed | PS4 - Milestone H | TM-00078
T-00078-0169 | PS4-71-MOV-0008 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135138 | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-21 12:56 | PS4-71-22 |  |  | Actuated on/off Valve | I | Closed | PS4 - Milestone B | TM-00078 | sridhar, muthu
T-00078-0170 | PS4-71-MOV-0009 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135138 | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module |  | PS4-71-08 |  |  | Actuated on/off Valve | I | To be completed | PS4 - Milestone H | TM-00078
T-00078-0171 | PS4-71-MOV-0010 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135138 | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-21 12:58 | PS4-71-22 |  |  | Actuated on/off Valve | I | Closed | PS4 - Milestone B | TM-00078 | sridhar, muthu
T-00078-0172 | PS4-75-MOV-0001 |  |  |  |  | CJX24 - Actuated on/off valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Motor Operated Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135300 | PS4 - TZA - PS4 - Tanzania | PS4-28-07 - Open Drains (OD2) |  | PS4-28-07 |  |  | Actuated on/off Valve | I | To be completed | PS4 - Milestone G | TM-00078
T-00079-0074 | PS4-01-FCV-0003A |  |  |  |  | CJX27 - Control valve - Pneumatic / Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125903 | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | Control Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone C | TM-00079
T-00079-0075 | PS4-01-FCV-0003B |  |  |  |  | CJX27 - Control valve - Pneumatic / Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125903 | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | Control Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone C | TM-00079
T-00079-0076 | PS4-01-FCV-0004A |  |  |  |  | CJX27 - Control valve - Pneumatic / Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125902 | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Control Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone C | TM-00079
T-00079-0077 | PS4-01-FCV-0004B |  |  |  |  | CJX27 - Control valve - Pneumatic / Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125902 | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Control Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone C | TM-00079
T-00079-0078 | PS4-25-FCV-0003A |  |  |  |  | CJX27 - Control valve - Pneumatic / Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134003 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Control Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00079
T-00079-0079 | PS4-25-FCV-0003B |  |  |  |  | CJX27 - Control valve - Pneumatic / Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134004 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Control Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00079
T-00079-0080 | PS4-25-FCV-0003C |  |  |  |  | CJX27 - Control valve - Pneumatic / Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134005 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Control Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00079
T-00079-0081 | PS4-25-FCV-0004 |  |  |  |  | CJX27 - Control valve - Pneumatic / Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134006 | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Control Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00079
T-00079-0082 | PS4-71-FCV-0018 |  |  |  |  | CJX27 - Control valve - Pneumatic / Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135007 | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Control Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00079
T-00079-0083 | PS4-71-FCV-0019 |  |  |  |  | CJX27 - Control valve - Pneumatic / Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135008 | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Control Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone B | TM-00079
T-00079-0084 | PS4-71-FCV-0020 |  |  |  |  | CJX27 - Control valve - Pneumatic / Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135006 | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Control Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00079
T-00079-0085 | PS4-71-LCV-4101 |  |  |  |  | CJX27 - Control valve - Pneumatic / Hydraulic type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Level Control Valve | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135000 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Control Valve-Pneumatic/Hydraulic Type | I | To be completed | PS4 - Milestone H | TM-00079
T-00080-0001 | PS4-09-TCV-8401 |  |  |  |  | CJX28 - Control valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CONTROL VALVE | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Control Valve-Electrical Type | I | To be completed | PS4 - Milestone D | TM-00080
T-00080-0002 | PS4-09-TCV-8402 |  |  |  |  | CJX28 - Control valve - Electrical type | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CONTROL VALVE | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Control Valve-Electrical Type | I | To be completed | PS4 - Milestone D | TM-00080
T-00082-1000 | PS4-01-BI-0001 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-05 - Foam Skid |  | PS4-01-05 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone F | TM-00082
T-00082-1001 | PS4-01-BI-0002 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1002 | PS4-01-BI-0003 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1003 | PS4-01-BI-0004 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1004 | PS4-01-BI-0005 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-05 - Foam Skid |  | PS4-01-05 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone F | TM-00082
T-00082-1005 | PS4-01-BI-0006 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-05 - Foam Skid |  | PS4-01-05 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone F | TM-00082
T-00082-1006 | PS4-01-BI-0007 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1007 | PS4-01-BI-0008 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1008 | PS4-01-BI-0009 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1009 | PS4-01-BI-1117 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-04-29 07:22 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1010 | PS4-01-BI-1118 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-04-29 07:14 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1011 | PS4-01-BI-1501 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-07 - Fire Water Ring Main & Distribution | 2026-05-14 15:07 | PS4-01-07 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone C | TM-00082 | sridhar, muthu
T-00082-1012 | PS4-01-BI-1515 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-04-29 07:12 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1013 | PS4-01-BI-1520 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package | 2026-05-14 16:17 | PS4-01-10 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone E | TM-00082 | sridhar, muthu
T-00082-1014 | PS4-01-BI-1571 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-08 - PS4 Deluge Valve Skid (PS4-01-UK-6100) |  | PS4-01-08 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone F | TM-00082
T-00082-1015 | PS4-01-BI-2110 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-04-29 07:13 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1016 | PS4-01-BI-2520 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package | 2026-06-05 07:08 | PS4-01-10 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone E | TM-00082 | sridhar, muthu
T-00082-1017 | PS4-01-BI-2571A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-08 - PS4 Deluge Valve Skid (PS4-01-UK-6100) |  | PS4-01-08 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone F | TM-00082
T-00082-1018 | PS4-01-BI-2571B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-08 - PS4 Deluge Valve Skid (PS4-01-UK-6100) |  | PS4-01-08 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone F | TM-00082
T-00082-1019 | PS4-03-BI-1502 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | 2026-06-05 09:04 | PS4-03-04 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone F | TM-00082 | sridhar, muthu
T-00082-1020 | PS4-03-BI-1503 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | 2026-04-29 07:36 | PS4-03-04 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone F | TM-00082 | sridhar, muthu
T-00082-1021 | PS4-03-BI-1506 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-06-05 07:12 | PS4-03-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone H | TM-00082 | sridhar, muthu
T-00082-1022 | PS4-03-BI-1507 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-05-14 16:44 | PS4-03-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone H | TM-00082 | sridhar, muthu
T-00082-1023 | PS4-03-BI-1508 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-06-05 07:22 | PS4-03-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone H | TM-00082 | sridhar, muthu
T-00082-1024 | PS4-03-BI-1509 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-05-14 16:27 | PS4-03-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone H | TM-00082 | sridhar, muthu
T-00082-1025 | PS4-03-BI-1510 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External | 2026-05-14 16:46 | PS4-03-08 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone E | TM-00082 | sridhar, muthu
T-00082-1026 | PS4-03-BI-1511 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area | 2026-06-05 07:26 | PS4-03-07 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone E | TM-00082 | sridhar, muthu
T-00082-1027 | PS4-03-BI-1512 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | 2026-05-14 16:47 | PS4-03-09 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone E | TM-00082 | sridhar, muthu
T-00082-1028 | PS4-03-BI-1513 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | 2026-04-29 07:40 | PS4-03-10 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone E | TM-00082 | sridhar, muthu
T-00082-1029 | PS4-03-BI-1514 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | 2026-05-14 13:49 | PS4-03-11 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone E | TM-00082 | sridhar, muthu
T-00082-1030 | PS4-03-BI-1516 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | 2026-06-05 09:29 | PS4-03-12 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone E | TM-00082 | sridhar, muthu
T-00082-1031 | PS4-03-BI-2501 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area | 2026-05-14 16:02 | PS4-03-06 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone E | TM-00082 | sridhar, muthu
T-00082-1032 | PS4-03-BI-2502 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1033 | PS4-03-BI-2503 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-06-05 09:11 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1034 | PS4-03-BI-2504 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-06-05 07:24 | PS4-03-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone H | TM-00082 | sridhar, muthu
T-00082-1035 | PS4-03-BI-2505 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External | 2026-06-05 09:21 | PS4-03-08 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone E | TM-00082 | sridhar, muthu
T-00082-1036 | PS4-03-BI-2506 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 13:45 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1037 | PS4-03-BI-2507 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | 2026-04-29 07:41 | PS4-03-10 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone E | TM-00082 | sridhar, muthu
T-00082-1038 | PS4-03-BI-2508 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | 2026-05-14 14:18 | PS4-03-11 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone E | TM-00082 | sridhar, muthu
T-00082-1039 | PS4-03-BI-2509 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-04-29 07:24 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1040 | PS4-03-BI-2510 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-03 - FZ-03 - Buildings Area |  | PS4-03-03 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1041 | PS4-03-BI-2511 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-05-14 16:29 | PS4-03-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone H | TM-00082 | sridhar, muthu
T-00082-1042 | PS4-03-BI-2512 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | 2026-04-29 07:39 | PS4-03-04 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone F | TM-00082 | sridhar, muthu
T-00082-1043 | PS4-03-BI-2514 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 14:20 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1044 | PS4-03-BI-2515 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-06-05 07:31 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1045 | PS4-05-BI-0002 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone C | TM-00082
T-00082-1046 | PS4-09-BI-2501 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-09-04 - HVAC for Workshop & Warehouse |  | PS4-09-04 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone I | TM-00082
T-00082-1047 | PS4-09-BI-2502 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-09-01 - HVAC for Office and Facilities building |  | PS4-09-01 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone I | TM-00082
T-00082-1048 | PS4-09-BI-2503 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1049 | PS4-25-BI-1101 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 14:27 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1050 | PS4-25-BI-1102 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:05 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1051 | PS4-25-BI-1103 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-06-05 08:57 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1052 | PS4-25-BI-1104 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:30 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1053 | PS4-25-BI-1115 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 14:31 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1054 | PS4-25-BI-1174A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1055 | PS4-25-BI-1174B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1056 | PS4-25-BI-1174C |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1057 | PS4-25-BI-1201 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:53 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1058 | PS4-25-BI-1274A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1059 | PS4-25-BI-1274B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1060 | PS4-25-BI-1274C |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1061 | PS4-25-BI-1301 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 14:44 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1062 | PS4-25-BI-1302 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:18 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1063 | PS4-25-BI-1310 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:19 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1064 | PS4-25-BI-1801A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1065 | PS4-25-BI-1801B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1066 | PS4-25-BI-1801C |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1067 | PS4-25-BI-1802A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1068 | PS4-25-BI-1802B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1069 | PS4-25-BI-1802C |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1070 | PS4-25-BI-1803A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1071 | PS4-25-BI-1803B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1072 | PS4-25-BI-1803C |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1073 | PS4-25-BI-2101 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-05-14 14:22 | PS4-25-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone H | TM-00082 | sridhar, muthu
T-00082-1074 | PS4-25-BI-2102 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-05-14 16:07 | PS4-25-07 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone H | TM-00082 | sridhar, muthu
T-00082-1075 | PS4-25-BI-2103 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:09 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1076 | PS4-25-BI-2104 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:16 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1077 | PS4-25-BI-2105 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 14:34 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1078 | PS4-25-BI-2106 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:28 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1079 | PS4-25-BI-2108 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:36 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1080 | PS4-25-BI-2109 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:20 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1081 | PS4-25-BI-2201 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:38 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1082 | PS4-25-BI-2203 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:39 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1083 | PS4-25-BI-2205 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-05-14 16:40 | PS4-25-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone H | TM-00082 | sridhar, muthu
T-00082-1084 | PS4-25-BI-2301 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 14:29 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1085 | PS4-25-BI-2302 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 14:48 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1086 | PS4-25-BI-2305 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:21 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1087 | PS4-25-BI-2308 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:28 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1088 | PS4-25-BI-2309 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:54 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1089 | PS4-25-BI-2312 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:31 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1090 | PS4-25-BI-2315 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:37 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1091 | PS4-25-BI-2316 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:37 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1092 | PS4-28-BI-1105 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:10 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1093 | PS4-28-BI-1106 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump | 2026-05-14 16:12 | PS4-28-06 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone G | TM-00082 | sridhar, muthu
T-00082-1094 | PS4-28-BI-1114 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 | 2026-06-05 09:13 | PS4-28-04 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone E | TM-00082 | sridhar, muthu
T-00082-1095 | PS4-28-BI-1303 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:45 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1096 | PS4-28-BI-1307 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:47 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1097 | PS4-28-BI-2304 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump | 2026-06-05 09:15 | PS4-28-17 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone H | TM-00082 | sridhar, muthu
T-00082-1098 | PS4-50-BI-1107 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-04-29 07:45 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1099 | PS4-53-BI-1108 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:14 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1100 | PS4-53-BI-1304 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-53-01 - Utility Water / Storage Tank | 2026-06-05 09:18 | PS4-53-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone C | TM-00082 | sridhar, muthu
T-00082-1101 | PS4-60-BI-0001A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 12:59 | PS4-60-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1102 | PS4-60-BI-0001B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 13:00 | PS4-60-04 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1103 | PS4-60-BI-0001C |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1104 | PS4-60-BI-0001D |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1105 | PS4-60-BI-0001E |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1106 | PS4-60-BI-0001F |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1107 | PS4-60-BI-0001G |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1108 | PS4-60-BI-0002 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-15 19:07 | PS4-60-22 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1109 | PS4-60-BI-0003 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-15 19:09 | PS4-60-22 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1110 | PS4-60-BI-0004A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 13:01 | PS4-60-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1111 | PS4-60-BI-0004B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 13:01 | PS4-60-04 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1112 | PS4-60-BI-0004C |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1113 | PS4-60-BI-0004D |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1114 | PS4-60-BI-0004E |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1115 | PS4-60-BI-0004F |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1116 | PS4-60-BI-0004G |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1117 | PS4-60-BI-0005A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 13:02 | PS4-60-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1118 | PS4-60-BI-0005B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 13:03 | PS4-60-04 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1119 | PS4-60-BI-0005C |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1120 | PS4-60-BI-0005D |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1121 | PS4-60-BI-0005E |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1122 | PS4-60-BI-0005F |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1123 | PS4-60-BI-0005G |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1124 | PS4-60-BI-0006A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-21 13:04 | PS4-60-02 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1125 | PS4-60-BI-0006B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-21 13:05 | PS4-60-05 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1126 | PS4-60-BI-0006C |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1127 | PS4-60-BI-0006D |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1128 | PS4-60-BI-0006E |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1129 | PS4-60-BI-0006F |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1130 | PS4-60-BI-0006G |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1131 | PS4-60-BI-0008A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 13:05 | PS4-60-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1132 | PS4-60-BI-0008B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 13:06 | PS4-60-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1133 | PS4-60-BI-0009A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 13:07 | PS4-60-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1134 | PS4-60-BI-0009B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 13:08 | PS4-60-04 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1135 | PS4-60-BI-0010A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 13:22 | PS4-60-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1136 | PS4-60-BI-0010B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1137 | PS4-60-BI-0011A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 13:23 | PS4-60-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1138 | PS4-60-BI-0011B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1139 | PS4-60-BI-0012A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 13:23 | PS4-60-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1140 | PS4-60-BI-0012B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1141 | PS4-60-BI-0013A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 13:24 | PS4-60-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1142 | PS4-60-BI-0013B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1143 | PS4-60-BI-0014A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 13:25 | PS4-60-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1144 | PS4-60-BI-0014B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1145 | PS4-60-BI-0016A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 13:25 | PS4-60-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1146 | PS4-60-BI-0016B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 13:26 | PS4-60-04 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1147 | PS4-60-BI-0016C |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1148 | PS4-60-BI-0016D |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1149 | PS4-60-BI-0016E |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1150 | PS4-60-BI-0016F |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1151 | PS4-60-BI-0016G |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1152 | PS4-60-BI-0017A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A | 2026-07-21 13:27 | PS4-60-56 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1153 | PS4-60-BI-0017B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B | 2026-07-21 13:28 | PS4-60-58 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1154 | PS4-60-BI-0017C |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C |  | PS4-60-60 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1155 | PS4-60-BI-0017D |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D |  | PS4-60-62 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1156 | PS4-60-BI-0017E |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E |  | PS4-60-64 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1157 | PS4-60-BI-0017F |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F |  | PS4-60-66 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1158 | PS4-60-BI-0017G |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G |  | PS4-60-68 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1159 | PS4-60-BI-0019A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 13:28 | PS4-60-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1160 | PS4-60-BI-0019B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 13:29 | PS4-60-04 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1161 | PS4-60-BI-0019C |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1162 | PS4-60-BI-0019D |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1163 | PS4-60-BI-0019E |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1164 | PS4-60-BI-0019F |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1165 | PS4-60-BI-0019G |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1166 | PS4-61-BI-0001 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 13:30 | PS4-60-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1167 | PS4-61-BI-0002 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 13:30 | PS4-60-04 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1168 | PS4-61-BI-0003 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1169 | PS4-61-BI-0004 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1170 | PS4-61-BI-0005 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1171 | PS4-61-BI-0006 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone D | TM-00082
T-00082-1172 | PS4-61-BI-0007 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1173 | PS4-71-BI-0001 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-02 - CFO Allocation Metering Package |  | PS4-71-02 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1174 | PS4-71-BI-0001A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1175 | PS4-71-BI-0001B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1176 | PS4-71-BI-0002 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone F | TM-00082
T-00082-1177 | PS4-71-BI-0003 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module |  | PS4-71-08 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1178 | PS4-71-BI-0004 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module |  | PS4-71-08 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1179 | PS4-71-BI-0005 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-07-21 13:31 | PS4-71-23 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1180 | PS4-71-BI-0006 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-21 13:32 | PS4-71-22 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone B | TM-00082 | sridhar, muthu
T-00082-1181 | PS4-71-BI-0008A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1182 | PS4-71-BI-0008B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1183 | PS4-71-BI-0009 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone F | TM-00082
T-00082-1184 | PS4-71-BI-0010 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone F | TM-00082
T-00082-1185 | PS4-71-BI-0011A |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1186 | PS4-71-BI-0011B |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1187 | PS4-71-BI-0021 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-02 - CFO Allocation Metering Package |  | PS4-71-02 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone H | TM-00082
T-00082-1188 | PS4-71-BI-1109 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-06-05 07:15 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1189 | PS4-71-BI-1110 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-06-05 07:20 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1190 | PS4-71-BI-1111 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-04-29 07:38 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1191 | PS4-71-BI-1112 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-17 - Diesel Fuel Distribution Header | 2026-05-14 16:13 | PS4-71-17 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone F | TM-00082 | sridhar, muthu
T-00082-1192 | PS4-71-BI-1113 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:24 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1193 | PS4-71-BI-1116 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:42 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1194 | PS4-71-BI-1117 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 14:50 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1195 | PS4-71-BI-1305 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-06-05 07:18 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1196 | PS4-71-BI-1306 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:43 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1197 | PS4-71-BI-1308 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank | 2026-05-14 16:23 | PS4-71-15 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone F | TM-00082 | sridhar, muthu
T-00082-1198 | PS4-71-BI-2101 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:55 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1199 | PS4-71-BI-2107 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:40 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1200 | PS4-71-BI-2113 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:25 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1201 | PS4-71-BI-2114 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:26 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1202 | PS4-71-BI-2115 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:26 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1203 | PS4-71-BI-2116 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-06-05 09:00 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1204 | PS4-71-BI-2118 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:17 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1205 | PS4-71-BI-2119 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:56 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1206 | PS4-71-BI-2120 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 14:58 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1207 | PS4-71-BI-2121 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 15:03 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1208 | PS4-71-BI-2122 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:18 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1209 | PS4-71-BI-2123 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:56 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1210 | PS4-71-BI-2124 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 15:00 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1211 | PS4-71-BI-2125 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 15:05 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1212 | PS4-71-BI-2306 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:44 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1213 | PS4-71-BI-2307 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank | 2026-05-14 16:22 | PS4-71-15 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone F | TM-00082 | sridhar, muthu
T-00082-1214 | PS4-71-BI-2310 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-06-05 09:03 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1215 | PS4-71-BI-2313 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank | 2026-06-05 09:26 | PS4-71-15 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone F | TM-00082 | sridhar, muthu
T-00082-1216 | PS4-71-BI-2314 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-14 16:41 | PS4-91-01 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone A | TM-00082 | sridhar, muthu
T-00082-1217 | PS4-71-BI-2317 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Junction Box | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank | 2026-05-14 16:23 | PS4-71-15 |  |  | Junction and Marshalling Box | I | Closed | PS4 - Milestone F | TM-00082 | sridhar, muthu
T-00082-1222 | PS4-01-NMR-61001 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DISCHARGE PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SAN1-120001 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1223 | PS4-01-NMR-61002 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DISCHARGE PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SAN1-120001 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1224 | PS4-01-NMR-61003 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DISCHARGE PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SAN1-120001 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1225 | PS4-01-NMR-61004 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DISCHARGE PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SAN1-120001 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1226 | PS4-01-NMRA-61001 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | ABORT DISCHARGE PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SAN1-120001 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1227 | PS4-01-NMRA-61002 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | ABORT DISCHARGE PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SAN1-120001 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1228 | PS4-01-NMRA-61003 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | ABORT DISCHARGE PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SAN1-120001 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00082-1229 | PS4-01-NMRA-61004 |  |  |  |  | CJX31 - Junction & marshalling box | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | ABORT DISCHARGE PUSH BUTTON | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-SAN1-120001 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Junction and Marshalling Box | I | To be completed | PS4 - Milestone E | TM-00082
T-00083-0124 | PS4-03-GDLHP-0137 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT TYPE LIQUID HYDROCARBON DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone H | TM-00083
T-00083-0125 | PS4-03-GDLHP-0142 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT TYPE LIQUID HYDROCARBON DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone H | TM-00083
T-00083-0126 | PS4-03-GDLHP-0143 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TRACE TAPE TYPE LIQUID HYDROCARBON LEAK DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone H | TM-00083
T-00083-0127 | PS4-03-GDLHP-0144 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | TRACE TAPE TYPE LIQUID HYDROCARBON LEAK DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone H | TM-00083
T-00083-0129 | PS4-03-GDLHP-0401 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT TYPE LIQUID HYDROCARBON DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone F | TM-00083
T-00083-0131 | PS4-03-RDH-0302 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-03 - FZ-03 - Buildings Area |  | PS4-03-03 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone H | TM-00083
T-00083-0132 | PS4-03-RDH-0303 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-03 - FZ-03 - Buildings Area |  | PS4-03-03 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone H | TM-00083
T-00083-0133 | PS4-03-RDH-0601 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0134 | PS4-03-RDH-0602 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0135 | PS4-03-RDH-0603 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0136 | PS4-03-RDH-0604 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0137 | PS4-03-RDH-0605 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0138 | PS4-03-RDH-0606 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0139 | PS4-03-RDH-0607 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0140 | PS4-03-RDH-0608 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0141 | PS4-03-RDH-0609 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0142 | PS4-03-RDH-0610 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0143 | PS4-03-RDH-0611 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0144 | PS4-03-RDH-0612 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0145 | PS4-03-RDH-0614 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0146 | PS4-03-RDH-0615 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0147 | PS4-03-RDH-0616 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0148 | PS4-03-RDH-0617 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0149 | PS4-03-RDH-0618 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0150 | PS4-03-RDH-0828 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0151 | PS4-03-RDH-0829 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0152 | PS4-03-RDH-0830 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0153 | PS4-03-RDH-0831 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0154 | PS4-03-RDH-0901 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0155 | PS4-03-RDH-0902 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0156 | PS4-03-RDH-0903 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0157 | PS4-03-RDH-0904 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0158 | PS4-03-RDH-0905 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0159 | PS4-03-RDH-0906 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0160 | PS4-03-RDH-0909 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0161 | PS4-03-RDH-0910 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0162 | PS4-03-RDH-0911 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0163 | PS4-03-RDH-0912 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0164 | PS4-03-RDH-1001 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0165 | PS4-03-RDH-1002 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0166 | PS4-03-RDH-1003 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0167 | PS4-03-RDH-1004 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0168 | PS4-03-RDH-1005 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0169 | PS4-03-RDH-1006 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0170 | PS4-03-RDH-1009 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0171 | PS4-03-RDH-1010 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0172 | PS4-03-RDH-1011 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0173 | PS4-03-RDH-1012 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0174 | PS4-03-RDH-1101 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0175 | PS4-03-RDH-1102 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0176 | PS4-03-RDH-1103 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0177 | PS4-03-RDH-1104 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0178 | PS4-03-RDH-1105 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0179 | PS4-03-RDH-1106 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0180 | PS4-03-RDH-1109 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0181 | PS4-03-RDH-1110 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0182 | PS4-03-RDH-1111 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0183 | PS4-03-RDH-1112 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0252 | PS4-03-GDLHP-0146 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT TYPE LIQUID HYDROCARBON DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone H | TM-00083
T-00083-0253 | PS4-03-GDLHP-0147 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT TYPE LIQUID HYDROCARBON DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone H | TM-00083
T-00083-0254 | PS4-03-GDLHP-0149 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT TYPE LIQUID HYDROCARBON DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone H | TM-00083
T-00083-0255 | PS4-03-GDLHP-0150 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT TYPE LIQUID HYDROCARBON DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone H | TM-00083
T-00083-0256 | PS4-03-RDH-0619 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0257 | PS4-03-RDH-0620 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0258 | PS4-03-RDH-1201 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0259 | PS4-03-RDH-1202 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0260 | PS4-03-RDH-1203 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0261 | PS4-03-RDH-1204 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0262 | PS4-03-RDH-1205 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0263 | PS4-03-RDH-1302 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-13 - FZ-13 - Power Generation Building - Instrument Air Room |  | PS4-03-13 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0264 | PS4-03-RDH-1303 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-13 - FZ-13 - Power Generation Building - Instrument Air Room |  | PS4-03-13 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0265 | PS4-03-RDH-1304 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-13 - FZ-13 - Power Generation Building - Instrument Air Room |  | PS4-03-13 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0266 | PS4-03-RDH-1901 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-19 - FZ-19 - Power Generation Building - Battery Room |  | PS4-03-19 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0267 | PS4-03-RDH-1902 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-19 - FZ-19 - Power Generation Building - Battery Room |  | PS4-03-19 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0268 | PS4-03-RDH-1903 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POINT HEAT DETECTOR (THERMOSTATIC, RATE COMPENSATED TYPE) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-19 - FZ-19 - Power Generation Building - Battery Room |  | PS4-03-19 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0269 | PS4-03-RDOS-1401 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0270 | PS4-03-RDOS-1402 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0271 | PS4-03-RDOS-1403 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0272 | PS4-03-RDOS-1404 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0273 | PS4-03-RDOS-1405 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0274 | PS4-03-RDOS-1406 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0275 | PS4-03-RDOS-1407 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0276 | PS4-03-RDOS-1408 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0277 | PS4-03-RDOS-1501 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-15 - FZ-15 - Power Generation Building - Generator Room 1 |  | PS4-03-15 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0278 | PS4-03-RDOS-1502 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-15 - FZ-15 - Power Generation Building - Generator Room 1 |  | PS4-03-15 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0279 | PS4-03-RDOS-1601 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-16 - FZ-16 - Power Generation Building - Generator Room 2 |  | PS4-03-16 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0280 | PS4-03-RDOS-1602 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-16 - FZ-16 - Power Generation Building - Generator Room 2 |  | PS4-03-16 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0281 | PS4-03-RDOS-1701 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-17 - FZ-17 - Power Generation Building - Generator Room 3 |  | PS4-03-17 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0282 | PS4-03-RDOS-1702 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-17 - FZ-17 - Power Generation Building - Generator Room 3 |  | PS4-03-17 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0283 | PS4-03-RDOS-1801 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-18 - FZ-18 - Power Generation Building - Generator Room 4 |  | PS4-03-18 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0284 | PS4-03-RDOS-1802 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-18 - FZ-18 - Power Generation Building - Generator Room 4 |  | PS4-03-18 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0285 | PS4-03-RDOS-1803 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-18 - FZ-18 - Power Generation Building - Generator Room 4 |  | PS4-03-18 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0286 | PS4-03-RDOS-G101A |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121133 | PS4 - TZA - PS4 - Tanzania | PS4-03-22 - FZ-G1 Guard House |  | PS4-03-22 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-0287 | PS4-03-RDOS-G101B |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121133 | PS4 - TZA - PS4 - Tanzania | PS4-03-22 - FZ-G1 Guard House |  | PS4-03-22 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-0890 | PS4-03-GDIR-0901 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0891 | PS4-03-GDIR-0902 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0892 | PS4-03-GDIR-0903 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0893 | PS4-03-GDIR-0904 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0894 | PS4-03-GDIR-0906 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0895 | PS4-03-GDIR-0907 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0896 | PS4-03-GDIR-0908 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0897 | PS4-03-GDIR-0909 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0898 | PS4-03-GDIR-1001 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0899 | PS4-03-GDIR-1002 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0900 | PS4-03-GDIR-1003 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0901 | PS4-03-GDIR-1004 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET C | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0902 | PS4-03-GDIR-1006 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0903 | PS4-03-GDIR-1007 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0904 | PS4-03-GDIR-1008 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0905 | PS4-03-GDIR-1009 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET D | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0906 | PS4-03-GDIR-1101 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0907 | PS4-03-GDIR-1102 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0908 | PS4-03-GDIR-1103 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0909 | PS4-03-GDIR-1104 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET E | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0910 | PS4-03-GDIR-1106 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0911 | PS4-03-GDIR-1107 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0912 | PS4-03-GDIR-1108 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0913 | PS4-03-GDIR-1109 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET F | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0914 | PS4-03-GDIR-1201 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0915 | PS4-03-GDIR-1202 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0916 | PS4-03-GDIR-1203 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0917 | PS4-03-GDIR-1204 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTOR - GENRATOR SET G | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0918 | PS4-03-RDOS-1503 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-15 - FZ-15 - Power Generation Building - Generator Room 1 |  | PS4-03-15 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0919 | PS4-03-RDOS-1603 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-16 - FZ-16 - Power Generation Building - Generator Room 2 |  | PS4-03-16 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0920 | PS4-03-RDOS-1703 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-17 - FZ-17 - Power Generation Building - Generator Room 3 |  | PS4-03-17 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0921 | PS4-03-RDOS-2101 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-21 - FZ-21 - Power Generation Building - Air Handling Unit |  | PS4-03-21 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0922 | PS4-03-RDOS-2102 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-21 - FZ-21 - Power Generation Building - Air Handling Unit |  | PS4-03-21 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-0923 | PS4-03-RDOS-2103 |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SMOKE DETECTOR | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-21 - FZ-21 - Power Generation Building - Air Handling Unit |  | PS4-03-21 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone E | TM-00083
T-00083-1345 | PS4-03-RDHR-W101A |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1346 | PS4-03-RDHR-W101B |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1347 | PS4-03-RDHR-W101C |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1348 | PS4-03-RDHR-W101D |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1349 | PS4-03-RDHR-W101E |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1350 | PS4-03-RDHR-W101F |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1351 | PS4-03-RDHR-W101G |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1352 | PS4-03-RDHR-W101H |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1353 | PS4-03-RDHR-W101I |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1354 | PS4-03-RDHR-W601A |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1355 | PS4-03-RDHR-W601B |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1356 | PS4-03-RDHR-W601C |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1357 | PS4-03-RDHR-W601D |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1358 | PS4-03-RDHR-W601E |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1359 | PS4-03-RDHR-W601F |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1360 | PS4-03-RDHR-W601G |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1361 | PS4-03-RDHR-W601H |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1362 | PS4-03-RDHR-W601I |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1363 | PS4-03-RDHR-W601J |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1364 | PS4-03-RDHR-W601K |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1365 | PS4-03-RDHR-W601L |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1366 | PS4-03-RDHR-W601M |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1367 | PS4-03-RDHR-W601N |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1368 | PS4-03-RDHR-W601O |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1369 | PS4-03-RDHR-W601P |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Heat Detector | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1370 | PS4-03-RDOS-B101A |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1371 | PS4-03-RDOS-B101B |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1372 | PS4-03-RDOS-B101C |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1373 | PS4-03-RDOS-B101D |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1374 | PS4-03-RDOS-B201A |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1375 | PS4-03-RDOS-B201B |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1376 | PS4-03-RDOS-B201C |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1377 | PS4-03-RDOS-B201D |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1378 | PS4-03-RDOS-B201E |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1379 | PS4-03-RDOS-B301A |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1380 | PS4-03-RDOS-B301B |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1381 | PS4-03-RDOS-B301C |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1382 | PS4-03-RDOS-B301D |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1383 | PS4-03-RDOS-B401A |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1384 | PS4-03-RDOS-B401B |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1385 | PS4-03-RDOS-B401C |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1386 | PS4-03-RDOS-B401D |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1387 | PS4-03-RDOS-B501A |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1388 | PS4-03-RDOS-B601A |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1389 | PS4-03-RDOS-B701A |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1390 | PS4-03-RDOS-B701B |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1391 | PS4-03-RDOS-B701C |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1392 | PS4-03-RDOS-B701D |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1393 | PS4-03-RDOS-B701E |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1394 | PS4-03-RDOS-B701F |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1395 | PS4-03-RDOS-B701G |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1396 | PS4-03-RDOS-B701H |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1397 | PS4-03-RDOS-B701I |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1398 | PS4-03-RDOS-B801A |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1399 | PS4-03-RDOS-B801B |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1400 | PS4-03-RDOS-B901A |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1401 | PS4-03-RDOS-B901B |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1402 | PS4-03-RDOS-B901C |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1403 | PS4-03-RDOS-B901D |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1404 | PS4-03-RDOS-B901E |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1405 | PS4-03-RDOS-W201A |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1406 | PS4-03-RDOS-W201B |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1407 | PS4-03-RDOS-W201C |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1408 | PS4-03-RDOS-W201D |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1409 | PS4-03-RDOS-W301A |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1410 | PS4-03-RDOS-W401A |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1411 | PS4-03-RDOS-W501A |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1412 | PS4-03-RDOS-W501B |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1413 | PS4-03-RDOS-W501C |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1414 | PS4-03-RDOS-W501D |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1415 | PS4-03-RDOS-W501E |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00083-1416 | PS4-03-RDOS-W501F |  |  |  |  | CJX42 - Gas / smoke detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Smoke detector - optical | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Gas/Smoke Detector | I | To be completed | PS4 - Milestone I | TM-00083
T-00084-0219 | PS4-03-RDIR-0104 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0220 | PS4-03-RDIR-0105 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0221 | PS4-03-RDIR-0106 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0222 | PS4-03-RDIR-0107 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0223 | PS4-03-RDIR-0108 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0224 | PS4-03-RDIR-0109 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0225 | PS4-03-RDIR-0110 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0226 | PS4-03-RDIR-0111 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0227 | PS4-03-RDIR-0112 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0228 | PS4-03-RDIR-0113 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0229 | PS4-03-RDIR-0114 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0230 | PS4-03-RDIR-0115 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0231 | PS4-03-RDIR-0116 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0232 | PS4-03-RDIR-0117 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0233 | PS4-03-RDIR-0118 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0234 | PS4-03-RDIR-0121 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0235 | PS4-03-RDIR-0122 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0236 | PS4-03-RDIR-0123 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0237 | PS4-03-RDIR-0124 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0238 | PS4-03-RDIR-0125 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0239 | PS4-03-RDIR-0126 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0240 | PS4-03-RDIR-0127 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0241 | PS4-03-RDIR-0128 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0242 | PS4-03-RDIR-0129 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0243 | PS4-03-RDIR-0130 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0244 | PS4-03-RDIR-0131 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0245 | PS4-03-RDIR-0132 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0246 | PS4-03-RDIR-0133 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0247 | PS4-03-RDIR-0137 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0248 | PS4-03-RDIR-0138 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0251 | PS4-03-RDIR-0403 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  | Fire Detector | I | To be completed | PS4 - Milestone F | TM-00084
T-00084-0252 | PS4-03-RDIR-0404 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  | Fire Detector | I | To be completed | PS4 - Milestone F | TM-00084
T-00084-0253 | PS4-03-RDIR-0405 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  | Fire Detector | I | To be completed | PS4 - Milestone F | TM-00084
T-00084-0254 | PS4-03-RDIR-0406 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  | Fire Detector | I | To be completed | PS4 - Milestone F | TM-00084
T-00084-0255 | PS4-03-RDIR-0409 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  | Fire Detector | I | To be completed | PS4 - Milestone F | TM-00084
T-00084-0257 | PS4-03-RDIR-0411 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  | Fire Detector | I | To be completed | PS4 - Milestone F | TM-00084
T-00084-0262 | PS4-03-RDIR-0819 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Fire Detector | I | To be completed | PS4 - Milestone E | TM-00084
T-00084-0263 | PS4-03-RDIR-0820 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Fire Detector | I | To be completed | PS4 - Milestone E | TM-00084
T-00084-0264 | PS4-03-RDIR-0832 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Fire Detector | I | To be completed | PS4 - Milestone E | TM-00084
T-00084-0265 | PS4-03-RDIR-0833 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Fire Detector | I | To be completed | PS4 - Milestone E | TM-00084
T-00084-0266 | PS4-03-RDUIR-0701 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area |  | PS4-03-07 |  |  | Fire Detector | I | To be completed | PS4 - Milestone E | TM-00084
T-00084-0267 | PS4-03-RDUIR-0702 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area |  | PS4-03-07 |  |  | Fire Detector | I | To be completed | PS4 - Milestone E | TM-00084
T-00084-0268 | PS4-03-RDUIR-0703 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area |  | PS4-03-07 |  |  | Fire Detector | I | To be completed | PS4 - Milestone E | TM-00084
T-00084-0269 | PS4-03-RDUIR-0704 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area |  | PS4-03-07 |  |  | Fire Detector | I | To be completed | PS4 - Milestone E | TM-00084
T-00084-0270 | PS4-03-RDUIR-0705 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area |  | PS4-03-07 |  |  | Fire Detector | I | To be completed | PS4 - Milestone E | TM-00084
T-00084-0271 | PS4-03-RDUIR-0907 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Fire Detector | I | To be completed | PS4 - Milestone E | TM-00084
T-00084-0272 | PS4-03-RDUIR-0908 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Fire Detector | I | To be completed | PS4 - Milestone E | TM-00084
T-00084-0273 | PS4-03-RDUIR-1007 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Fire Detector | I | To be completed | PS4 - Milestone E | TM-00084
T-00084-0274 | PS4-03-RDUIR-1008 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Fire Detector | I | To be completed | PS4 - Milestone E | TM-00084
T-00084-0275 | PS4-03-RDUIR-1107 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Fire Detector | I | To be completed | PS4 - Milestone E | TM-00084
T-00084-0276 | PS4-03-RDUIR-1108 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Fire Detector | I | To be completed | PS4 - Milestone E | TM-00084
T-00084-0343 | PS4-03-RDIR-0141 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0344 | PS4-03-RDIR-0142 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | MULTI-FREQUENCY INFRARED FLAME DETECTOR (MIR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121110 | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Fire Detector | I | To be completed | PS4 - Milestone H | TM-00084
T-00084-0345 | PS4-03-RDUIR-1207 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Fire Detector | I | To be completed | PS4 - Milestone E | TM-00084
T-00084-0346 | PS4-03-RDUIR-1208 |  |  |  |  | CJX43 - Fire detector | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | ULTRAVIOLET / INFRARED FLAME DETECTOR (UV/IR) | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Fire Detector | I | To be completed | PS4 - Milestone E | TM-00084
T-00087-0013 | PS4-03-SEA-0002 |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FIRE ALARM CONTROL PANEL | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121133 | PS4 - TZA - PS4 - Tanzania | PS4-03-22 - FZ-G1 Guard House |  | PS4-03-22 |  |  | Indoor Cabinet/Panel | I | To be completed | PS4 - Milestone I | TM-00087
T-00087-0014 | PS4-03-SEA-0003 |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FIRE ALARM CONTROL PANEL | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Indoor Cabinet/Panel | I | To be completed | PS4 - Milestone E | TM-00087
T-00087-0104 | PS4-60-SEA-0001 |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GAS DETECTION PANEL | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-121112 | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Indoor Cabinet/Panel | I | To be completed | PS4 - Milestone E | TM-00087
T-00087-0286 | PS4-03-MTX-0001 |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SIS/FGS Matrix Panel | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-04-02 - Office Building SIS/FGS System |  | PS4-04-02 |  |  | Indoor Cabinet/Panel | I | To be completed | PS4 - Milestone E | TM-00087
T-00087-0491 | PS4-01-LB-0004 |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FIRE SUPPRESSION SKID CONTROL PANEL | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Indoor Cabinet/Panel | I | Submitted | PS4 - Milestone E | TM-00087
T-00087-0503 | PS4-03-SEA-0005 |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FIRE ALARM CONTROL PANEL | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Indoor Cabinet/Panel | I | To be completed | PS4 - Milestone I | TM-00087
T-00087-0504 | PS4-03-SEA-0006 |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FIRE ALARM CONTROL PANEL | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Indoor Cabinet/Panel | I | To be completed | PS4 - Milestone I | TM-00087
T-00087-0522 | PS4-60-LA-0002A |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | VTMS VIBRATION AND TEMPERATURE MONITORING SYSTEM | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-15 18:32 | PS4-60-01 |  |  | Indoor Cabinet/Panel | I | Closed | PS4 - Milestone B | TM-00087 | sridhar, muthu
T-00087-0523 | PS4-60-LA-0002B |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | VTMS VIBRATION AND TEMPERATURE MONITORING SYSTEM | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-15 18:35 | PS4-60-10 |  |  | Indoor Cabinet/Panel | I | Closed | PS4 - Milestone D | TM-00087 | sridhar, muthu
T-00087-0524 | PS4-60-LA-0002C |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | VTMS VIBRATION AND TEMPERATURE MONITORING SYSTEM | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Indoor Cabinet/Panel | I | To be completed | PS4 - Milestone D | TM-00087
T-00087-0527 | PS4-60-LA-0003 |  |  |  |  | CJX48 - Indoor cabinet / panel | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Remote Access Panel | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-21 13:32 | PS4-60-22 |  |  | Indoor Cabinet/Panel | I | Closed | PS4 - Milestone B | TM-00087 | sridhar, muthu
T-00090-0303 | PS4-60-UR-8100A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION PACKAGE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135100 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 12:07 | PS4-60-01 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0304 | PS4-60-UR-8100B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION PACKAGE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135103 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 12:12 | PS4-60-04 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0305 | PS4-60-UR-8100C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION PACKAGE C | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135106 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0306 | PS4-60-UR-8100D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION PACKAGE D | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135109 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0307 | PS4-60-UR-8100E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION PACKAGE E | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135112 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0308 | PS4-60-UR-8100F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION PACKAGE F | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135115 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0309 | PS4-60-UR-8100G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION PACKAGE G | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135118 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00090
T-00090-0310 | PS4-05-UR-8100 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | EMERGENCY DIESEL ENGINE GENERATOR PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135204 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package |  | PS4-05-01 |  |  | Package | M | To be completed | PS4 - Milestone C | TM-00090
T-00090-0311 | PS4-71-UZ-6200 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DIESEL FUEL DISPENSER STATION | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135200 | PS4 - TZA - PS4 - Tanzania | PS4-71-14 - Diesel Fuel Transfer and Dispensing Station |  | PS4-71-14 |  |  | Package | M | To be completed | PS4 - Milestone F | TM-00090
T-00090-0312 | PS4-60-UA-5100 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | COMPRESSOR AIR STARTING SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135128 | PS4 - TZA - PS4 - Tanzania | PS4-60-27 - Compressed Air Starting Skid | 2026-07-08 17:34 | PS4-60-27 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0313 | PS4-60-UO-81100A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135124 | PS4 - TZA - PS4 - Tanzania | PS4-60-49 - Lube Oil Separator Module PS4-60-UO-81100A | 2026-07-05 12:37 | PS4-60-49 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0314 | PS4-60-UO-81100B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135124 | PS4 - TZA - PS4 - Tanzania | PS4-60-50 - Lube Oil Separator Module PS4-60-UO-81100B | 2026-07-05 12:34 | PS4-60-50 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0315 | PS4-60-UO-81100C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135124 | PS4 - TZA - PS4 - Tanzania | PS4-60-51 - Lube Oil Separator Module PS4-60-UO-81100C |  | PS4-60-51 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0316 | PS4-60-UO-81100D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135124 | PS4 - TZA - PS4 - Tanzania | PS4-60-52 - Lube Oil Separator Module PS4-60-UO-81100D |  | PS4-60-52 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0317 | PS4-60-UO-81100E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135124 | PS4 - TZA - PS4 - Tanzania | PS4-60-53 - Lube Oil Separator Module PS4-60-UO-81100E |  | PS4-60-53 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0318 | PS4-60-UO-81100F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135124 | PS4 - TZA - PS4 - Tanzania | PS4-60-54 - Lube Oil Separator Module PS4-60-UO-81100F |  | PS4-60-54 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0319 | PS4-60-UO-81100G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | LUBE OIL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135124 | PS4 - TZA - PS4 - Tanzania | PS4-60-55 - Lube Oil Separator Module PS4-60-UO-81100G |  | PS4-60-55 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00090
T-00090-0320 | PS4-60-UZ-8200A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-35 - Injector Tip Cooling Module A | 2026-06-24 08:27 | PS4-60-35 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0321 | PS4-60-UZ-8200B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-36 - Injector Tip Cooling Module B | 2026-06-24 08:29 | PS4-60-36 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0322 | PS4-60-UZ-8200C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-37 - Injector Tip Cooling Module C |  | PS4-60-37 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0323 | PS4-60-UZ-8200D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-38 - Injector Tip Cooling Module D |  | PS4-60-38 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0324 | PS4-60-UZ-8200E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-39 - Injector Tip Cooling Module E |  | PS4-60-39 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0325 | PS4-60-UZ-8200F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-40 - Injector Tip Cooling Module F |  | PS4-60-40 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0326 | PS4-60-VS-9100A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135130 | PS4 - TZA - PS4 - Tanzania | PS4-60-42 - Oil Mist Separator Skid PS4-60-VS-9100A | 2026-07-10 05:58 | PS4-60-42 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0327 | PS4-60-VS-9100B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135130 | PS4 - TZA - PS4 - Tanzania | PS4-60-43 - Oil Mist Separator Skid PS4-60-VS-9100B | 2026-07-10 05:59 | PS4-60-43 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0328 | PS4-60-VS-9100C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135130 | PS4 - TZA - PS4 - Tanzania | PS4-60-44 - Oil Mist Separator Skid PS4-60-VS-9100C |  | PS4-60-44 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0329 | PS4-60-VS-9100D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135130 | PS4 - TZA - PS4 - Tanzania | PS4-60-45 - Oil Mist Separator Skid PS4-60-VS-9100D |  | PS4-60-45 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0330 | PS4-60-VS-9100E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135130 | PS4 - TZA - PS4 - Tanzania | PS4-60-46 - Oil Mist Separator Skid PS4-60-VS-9100E |  | PS4-60-46 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0331 | PS4-60-VS-9100F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135130 | PS4 - TZA - PS4 - Tanzania | PS4-60-47 - Oil Mist Separator Skid PS4-60-VS-9100F |  | PS4-60-47 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0332 | PS4-60-VS-9100G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | OIL MIST SEPARATOR SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135130 | PS4 - TZA - PS4 - Tanzania | PS4-60-48 - Oil Mist Separator Skid PS4-60-VS-9100G |  | PS4-60-48 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00090
T-00090-0333 | PS4-71-UZ-6500 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DIESEL FUEL SEPARATOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135009 | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Package | M | To be completed | PS4 - Milestone F | TM-00090
T-00090-0334 | PS4-71-UZ-6800A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CRUDE FUEL SEPARATOR MODULE A | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135002 | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Package | M | To be completed | PS4 - Milestone H | TM-00090
T-00090-0335 | PS4-71-UZ-6800B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CRUDE FUEL SEPARATOR MODULE B | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135002 | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Package | M | To be completed | PS4 - Milestone H | TM-00090
T-00090-0336 | PS4-01-UK-6100 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DELUGE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-125904 | PS4 - TZA - PS4 - Tanzania | PS4-01-08 - PS4 Deluge Valve Skid (PS4-01-UK-6100) |  | PS4-01-08 |  |  | Package | M | To be completed | PS4 - Milestone F | TM-00090
T-00090-0337 | PS4-01-UV-8700 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FOAM SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-125900 | PS4 - TZA - PS4 - Tanzania | PS4-01-05 - Foam Skid |  | PS4-01-05 |  |  | Package | M | To be completed | PS4 - Milestone F | TM-00090
T-00090-0338 | PS4-01-UZ-6900 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | WATER MIST FIRE PROTECTION PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-125922 | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00090
T-00090-0339 | PS4-53-UT-8100 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | WATER PRE-TREATMENT PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135500 | PS4 - TZA - PS4 - Tanzania | PS4-50-03 - Water Pre-Treatment Package |  | PS4-50-03 |  |  | Package | M | To be completed | PS4 - Milestone F | TM-00090
T-00090-0340 | PS4-53-UT-8200 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | WATER TREATMENT/ PURIFICATION PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135502 | PS4 - TZA - PS4 - Tanzania | PS4-53-04 - Water Treatment Purification Package |  | PS4-53-04 |  |  | Package | M | To be completed | PS4 - Milestone F | TM-00090
T-00090-0341 | PS4-60-EA-2100A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-06-24 08:30 | PS4-60-70 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0342 | PS4-60-EA-2100B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-06-24 08:33 | PS4-60-70 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0343 | PS4-60-EA-21100A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CW AIR FIN COOLER - DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135100 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 12:15 | PS4-60-01 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0344 | PS4-60-EA-21100B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CW AIR FIN COOLER - DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135103 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 12:18 | PS4-60-04 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0345 | PS4-60-EA-21100C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CW AIR FIN COOLER - DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135106 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0346 | PS4-60-EA-21100D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CW AIR FIN COOLER - DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135109 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0347 | PS4-60-EA-21100E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CW AIR FIN COOLER - DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135112 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0348 | PS4-60-EA-21100F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CW AIR FIN COOLER - DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135115 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0349 | PS4-60-EA-21100G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CW AIR FIN COOLER - DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135118 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00090
T-00090-0350 | PS4-60-EA-21200A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CW AIR FIN COOLER - NON-DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135100 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 12:20 | PS4-60-01 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0351 | PS4-60-EA-21200B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CW AIR FIN COOLER - NON-DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135103 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 12:22 | PS4-60-04 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0352 | PS4-60-EA-21200C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CW AIR FIN COOLER - NON-DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135106 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0353 | PS4-60-EA-21200D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CW AIR FIN COOLER - NON-DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135109 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0354 | PS4-60-EA-21200E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CW AIR FIN COOLER - NON-DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135112 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0355 | PS4-60-EA-21200F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CW AIR FIN COOLER - NON-DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135115 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0356 | PS4-60-EA-21200G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CW AIR FIN COOLER - NON-DRIVE END BEARING (ALT BRG) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135118 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00090
T-00090-0357 | PS4-60-EA-2200A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-06-24 08:35 | PS4-60-71 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0358 | PS4-60-EA-2200B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-06-24 08:41 | PS4-60-71 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0359 | PS4-60-EA-2300A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system |  | PS4-60-72 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0360 | PS4-60-EA-2300B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system |  | PS4-60-72 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0361 | PS4-60-EA-2400A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system |  | PS4-60-73 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0362 | PS4-60-EA-2400B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system |  | PS4-60-73 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0363 | PS4-60-EA-2500A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0364 | PS4-60-EA-2500B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0365 | PS4-60-EA-2600A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0366 | PS4-60-EA-2600B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0367 | PS4-60-EA-2700A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00090
T-00090-0368 | PS4-60-EA-2700B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION ENGINE RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135122 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00090
T-00090-0369 | PS4-60-EA-2800A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-35 - Injector Tip Cooling Module A | 2026-06-24 08:43 | PS4-60-35 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0370 | PS4-60-EA-2800B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-36 - Injector Tip Cooling Module B | 2026-06-24 08:47 | PS4-60-36 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0371 | PS4-60-EA-2800C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-37 - Injector Tip Cooling Module C |  | PS4-60-37 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0372 | PS4-60-EA-2800D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-38 - Injector Tip Cooling Module D |  | PS4-60-38 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0373 | PS4-60-EA-2800E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-39 - Injector Tip Cooling Module E |  | PS4-60-39 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0374 | PS4-60-EA-2800F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-40 - Injector Tip Cooling Module F |  | PS4-60-40 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0375 | PS4-60-EA-2800G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | RADIATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-41 - Injector Tip Cooling Module G |  | PS4-60-41 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00090
T-00090-0376 | PS4-60-EA-2900A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | AIR BLAST COOLER 33KW CAPACITY - COF MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A | 2026-07-21 12:24 | PS4-60-56 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0377 | PS4-60-EA-2900B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | AIR BLAST COOLER 33KW CAPACITY - COF MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B | 2026-07-21 12:27 | PS4-60-58 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0378 | PS4-60-EA-2900C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | AIR BLAST COOLER 33KW CAPACITY - COF MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C |  | PS4-60-60 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0379 | PS4-60-EA-2900D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | AIR BLAST COOLER 33KW CAPACITY - COF MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D |  | PS4-60-62 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0380 | PS4-60-EA-2900E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | AIR BLAST COOLER 33KW CAPACITY - COF MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135138 | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E |  | PS4-60-64 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0381 | PS4-60-EA-2900F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | AIR BLAST COOLER 33KW CAPACITY - COF MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135138 | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F |  | PS4-60-66 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0382 | PS4-60-EA-2900G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | AIR BLAST COOLER 33KW CAPACITY - COF MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135138 | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G |  | PS4-60-68 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00090
T-00090-0383 | PS4-60-TCV-0001A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135136 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-06-24 08:49 | PS4-60-70 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0384 | PS4-60-TCV-0001B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135136 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-06-24 08:52 | PS4-60-71 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0385 | PS4-60-TCV-0001C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135136 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system |  | PS4-60-72 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0386 | PS4-60-TCV-0001D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135136 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system |  | PS4-60-73 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0387 | PS4-60-TCV-0001E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135136 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0388 | PS4-60-TCV-0001F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135136 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0389 | PS4-60-TCV-0001G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135136 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00090
T-00090-0390 | PS4-60-TCV-0002A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135137 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-06-24 08:56 | PS4-60-70 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0391 | PS4-60-TCV-0002B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135137 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-06-24 08:58 | PS4-60-71 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0392 | PS4-60-TCV-0002C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135137 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system |  | PS4-60-72 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0393 | PS4-60-TCV-0002D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135137 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system |  | PS4-60-73 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0394 | PS4-60-TCV-0002E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135137 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0395 | PS4-60-TCV-0002F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135137 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0396 | PS4-60-TCV-0002G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | THERMAL REGULATING VALVE SKID | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135137 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00090
T-00090-0397 | PS4-60-UA-5200 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INSTRUMENT AIR COMPRESSOR MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135127 | PS4 - TZA - PS4 - Tanzania | PS4-60-26 - Instrument Air Compressor Skid | 2026-07-21 12:29 | PS4-60-26 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0398 | PS4-60-UR-8200A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135100 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-21 12:32 | PS4-60-01 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0399 | PS4-60-UR-8200B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135103 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-21 12:35 | PS4-60-04 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0400 | PS4-60-UR-8200C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135106 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0401 | PS4-60-UR-8200D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135109 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0402 | PS4-60-UR-8200E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135112 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0403 | PS4-60-UR-8200F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135115 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0404 | PS4-60-UR-8200G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | GENERATOR CW PUMP MODULE (ALTERN/ATOR BEARING SYSTEM) | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135118 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00090
T-00090-0405 | PS4-60-UZ-8200G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | INJECTOR TIP COOLING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135129 | PS4 - TZA - PS4 - Tanzania | PS4-60-41 - Injector Tip Cooling Module G |  | PS4-60-41 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00090
T-00090-0406 | PS4-60-UZ-8900A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A | 2026-07-21 12:37 | PS4-60-56 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0407 | PS4-60-UZ-8900B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B | 2026-07-21 12:38 | PS4-60-58 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0408 | PS4-60-UZ-8900C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C |  | PS4-60-60 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0409 | PS4-60-UZ-8900D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135123 | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D |  | PS4-60-62 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0410 | PS4-60-UZ-8900E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135138 | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E |  | PS4-60-64 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0411 | PS4-60-UZ-8900F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135138 | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F |  | PS4-60-66 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0412 | PS4-60-UZ-8900G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FUEL CONDITIONING MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135138 | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G |  | PS4-60-68 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00090
T-00090-0413 | PS4-71-UN-7200 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CRUDE FUEL OIL ALLOCATION METERING PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135010 | PS4 - TZA - PS4 - Tanzania | PS4-71-02 - CFO Allocation Metering Package |  | PS4-71-02 |  |  | Package | M | To be completed | PS4 - Milestone H | TM-00090
T-00090-0414 | PS4-71-UZ-6400 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CRUDE FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135004 | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module |  | PS4-71-08 |  |  | Package | M | To be completed | PS4 - Milestone H | TM-00090
T-00090-0415 | PS4-71-UZ-6700 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DIESEL FUEL OIL PRE-PRESSURE MODULE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135126 | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-23 14:47 | PS4-71-22 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0416 | PS4-74-UB-5100 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | NITROGEN GENERATION PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135800 | PS4 - TZA - PS4 - Tanzania | PS4-74-01 - N2 Generation Skid |  | PS4-74-01 |  |  | Package | M | To be completed | PS4 - Milestone F | TM-00090
T-00090-0417 | PS4-75-UI-6100 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | BIOCIDE INJECTION PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135300 | PS4 - TZA - PS4 - Tanzania | PS4-75-02 - Biocide Injection Package |  | PS4-75-02 |  |  | Package | M | To be completed | PS4 - Milestone G | TM-00090
T-00090-0418 | PS4-75-UI-6200 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | DRA PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135300 | PS4 - TZA - PS4 - Tanzania | PS4-75-01 - DRA Injection Package |  | PS4-75-01 |  |  | Package | M | To be completed | PS4 - Milestone G | TM-00090
T-00090-0419 | PS4-75-UI-6300 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | CORROSION INHIBITOR PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135300 | PS4 - TZA - PS4 - Tanzania | PS4-75-03 - Corrosion Inhibitor Injection Package |  | PS4-75-03 |  |  | Package | M | To be completed | PS4 - Milestone G | TM-00090
T-00090-0420 | PS4-77-UZ-8200 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | WATER DEIONIZATION PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135502 | PS4 - TZA - PS4 - Tanzania | PS4-53-03 - Water Softener Package |  | PS4-53-03 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00090
T-00090-0421 | PS4-82-UZ-8100 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | SEWAGE TREATMENT PLANT PACKAGE | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135601 | PS4 - TZA - PS4 - Tanzania | PS4-82-02 - Sewage Treatment Plant Package |  | PS4-82-02 |  |  | Package | M | To be completed | PS4 - Milestone I | TM-00090
T-00090-0422 | PS4-60-PRV-0008A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | AIR REGULATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135128 | PS4 - TZA - PS4 - Tanzania | PS4-60-28 - Air Receiver A & Air Regulator A |  | PS4-60-28 |  |  | Package | I | To be completed | PS4 - Milestone B | TM-00090
T-00090-0423 | PS4-60-PRV-0008B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | AIR REGULATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135128 | PS4 - TZA - PS4 - Tanzania | PS4-60-29 - Air Receiver B & Air Regulator B |  | PS4-60-29 |  |  | Package | I | To be completed | PS4 - Milestone B | TM-00090
T-00090-0424 | PS4-60-PRV-0008C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | AIR REGULATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135128 | PS4 - TZA - PS4 - Tanzania | PS4-60-30 - Air Receiver C & Air Regulator C |  | PS4-60-30 |  |  | Package | I | To be completed | PS4 - Milestone D | TM-00090
T-00090-0425 | PS4-60-PRV-0008D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | AIR REGULATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135128 | PS4 - TZA - PS4 - Tanzania | PS4-60-31 - Air Receiver D & Air Regulator D |  | PS4-60-31 |  |  | Package | I | To be completed | PS4 - Milestone D | TM-00090
T-00090-0426 | PS4-60-PRV-0008E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | AIR REGULATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135128 | PS4 - TZA - PS4 - Tanzania | PS4-60-32 - Air Receiver E & Air Regulator E |  | PS4-60-32 |  |  | Package | I | To be completed | PS4 - Milestone D | TM-00090
T-00090-0427 | PS4-60-PRV-0008F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | AIR REGULATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135128 | PS4 - TZA - PS4 - Tanzania | PS4-60-33 - Air Receiver F & Air Regulator F |  | PS4-60-33 |  |  | Package | I | To be completed | PS4 - Milestone D | TM-00090
T-00090-0428 | PS4-60-PRV-0008G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | AIR REGULATOR | EACOP | CPP AGI |  |  | 20 |  |  | TZ-MID-67-WPR2-135128 | PS4 - TZA - PS4 - Tanzania | PS4-60-34 - Air Receiver G & Air Regulator G |  | PS4-60-34 |  |  | Package | I | To be completed | PS4 - Milestone E | TM-00090
T-00090-0432 | PS4-01-UZ-610 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Fire suppression skid | EACOP | CPP AGI |  |  | 20 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00090
T-00090-0454 | PS4-03-SEA-0001 |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | FACP | EACOP | CPP AGI |  |  | 20 |  | 20 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-20 - FZ-20 - Emergency Diesel Generator Enclosure |  | PS4-03-20 |  |  | Package | I | To be completed | PS4 - Milestone C | TM-00090
T-00090-0457 | PS4-60-UR-8300A |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  | 20 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-35 - Injector Tip Cooling Module A | 2026-06-24 09:00 | PS4-60-35 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0458 | PS4-60-UR-8300B |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  | 20 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-36 - Injector Tip Cooling Module B | 2026-06-24 09:03 | PS4-60-36 |  |  | Package | M | Closed | PS4 - Milestone B | TM-00090 | sridhar, muthu
T-00090-0459 | PS4-60-UR-8300C |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  | 20 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-37 - Injector Tip Cooling Module C |  | PS4-60-37 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0460 | PS4-60-UR-8300D |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  | 20 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-38 - Injector Tip Cooling Module D |  | PS4-60-38 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0461 | PS4-60-UR-8300E |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  | 20 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-39 - Injector Tip Cooling Module E |  | PS4-60-39 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0462 | PS4-60-UR-8300F |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  | 20 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-40 - Injector Tip Cooling Module F |  | PS4-60-40 |  |  | Package | M | To be completed | PS4 - Milestone D | TM-00090
T-00090-0463 | PS4-60-UR-8300G |  |  |  |  | CZX01I - Package | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | POWER GENERATION - Cooler Module | EACOP | CPP AGI |  |  | 20 |  | 20 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-41 - Injector Tip Cooling Module G |  | PS4-60-41 |  |  | Package | M | To be completed | PS4 - Milestone E | TM-00090
T-00171-8784 | PS4-60-IE-0003B-CA02 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003A TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) |  | PS4-60-05 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone B | TM-00171
T-00171-8785 | PS4-60-IE-0003B-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003A TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) |  | PS4-60-05 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone B | TM-00171
T-00171-8786 | PS4-60-IE-0003B-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003A TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) |  | PS4-60-05 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone B | TM-00171
T-00171-8787 | PS4-60-IE-0003B-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003A TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) |  | PS4-60-05 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone B | TM-00171
T-00171-8788 | PS4-60-IE-0003C-CA02 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003B TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8789 | PS4-60-IE-0003C-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003B TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8790 | PS4-60-IE-0003C-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003B TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8791 | PS4-60-IE-0003C-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003B TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8792 | PS4-60-IE-0003D-CA02 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003C TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8793 | PS4-60-IE-0003D-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003C TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8794 | PS4-60-IE-0003D-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003C TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8795 | PS4-60-IE-0003D-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003C TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8796 | PS4-60-IE-0003E-CA02 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003D TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8797 | PS4-60-IE-0003E-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003D TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8798 | PS4-60-IE-0003E-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003D TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8799 | PS4-60-IE-0003E-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003D TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8800 | PS4-60-IE-0003F-CA02 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003E TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8801 | PS4-60-IE-0003F-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003E TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8802 | PS4-60-IE-0003F-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003E TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8803 | PS4-60-IE-0003F-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003E TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8804 | PS4-60-IE-0003G-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003F TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone E | TM-00171
T-00171-8805 | PS4-60-IE-0003G-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003F TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone E | TM-00171
T-00171-8806 | PS4-60-IE-0003G-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003F TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone E | TM-00171
T-00171-8807 | PS4-60-IE-0004-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003A TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone B | TM-00171
T-00171-8808 | PS4-60-IE-0004-CA07 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003G TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone B | TM-00171
T-00171-8809 | PS4-60-IE-0004-CA08 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003A TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone B | TM-00171
T-00171-8810 | PS4-60-IE-0004-CA14 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003G TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone B | TM-00171
T-00171-8811 | PS4-60-IE-0004-CA15 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003A TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone B | TM-00171
T-00171-8812 | PS4-60-IE-0004-CA21 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003G TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone B | TM-00171
T-00171-8813 | PS4-60-IH-0001A-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003G TO PS4-60-IH-0001A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS4-60-03 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone B | TM-00171
T-00171-8814 | PS4-60-IH-0001B-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0001B TO PS4-60-IH-0001B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS4-60-06 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone B | TM-00171
T-00171-8815 | PS4-60-IH-0001C-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0001C TO PS4-60-IH-0001C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS4-60-09 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8816 | PS4-60-IH-0001D-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0001D TO PS4-60-IH-0001D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS4-60-12 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8817 | PS4-60-IH-0001E-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0001E TO PS4-60-IH-0001E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS4-60-15 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8818 | PS4-60-IH-0001F-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0001F TO PS4-60-IH-0001F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS4-60-18 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8819 | PS4-60-IH-0001G-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0001G TO PS4-60-IH-0001G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS4-60-21 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone E | TM-00171
T-00171-8820 | PS4-60-IN-0001A-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-49 - Lube Oil Separator Module PS4-60-UO-81100A |  | PS4-60-49 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone B | TM-00171
T-00171-8821 | PS4-60-IN-0001B-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-50 - Lube Oil Separator Module PS4-60-UO-81100B |  | PS4-60-50 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone B | TM-00171
T-00171-8822 | PS4-60-IN-0001C-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0001C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-51 - Lube Oil Separator Module PS4-60-UO-81100C |  | PS4-60-51 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8823 | PS4-60-IN-0001D-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0001D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-52 - Lube Oil Separator Module PS4-60-UO-81100D |  | PS4-60-52 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8824 | PS4-60-IN-0001E-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0001E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-53 - Lube Oil Separator Module PS4-60-UO-81100E |  | PS4-60-53 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8825 | PS4-60-IN-0001F-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0001F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-54 - Lube Oil Separator Module PS4-60-UO-81100F |  | PS4-60-54 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8826 | PS4-60-IN-0001G-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0001G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-55 - Lube Oil Separator Module PS4-60-UO-81100G |  | PS4-60-55 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone E | TM-00171
T-00171-8827 | PS4-60-IN-0002A-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) |  | PS4-60-57 |  |  | Telecom Cable Power/Control/Multicore | T | Started (not Completed) | PS4 - Milestone B | TM-00171
T-00171-8828 | PS4-60-IN-0002B-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) |  | PS4-60-59 |  |  | Telecom Cable Power/Control/Multicore | T | Started (not Completed) | PS4 - Milestone B | TM-00171
T-00171-8829 | PS4-60-IN-0002C-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8830 | PS4-60-IN-0002D-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8831 | PS4-60-IN-0002E-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) |  | PS4-60-65 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8832 | PS4-60-IN-0002F-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) |  | PS4-60-67 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8833 | PS4-60-IN-0002G-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) |  | PS4-60-69 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone E | TM-00171
T-00171-8834 | PS4-60-LA-0002B-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0004 TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8835 | PS4-60-LA-0002B-CA02 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-LA-0002A TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8836 | PS4-60-LA-0002B-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-LA-0002A TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8837 | PS4-60-LA-0002B-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-LA-0002A TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8838 | PS4-60-LA-0002B-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-LA-0002C TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8839 | PS4-60-LA-0002B-CA06 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-LA-0002C TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8840 | PS4-60-LA-0002C-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0004 TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8841 | PS4-60-LA-0002C-CA02 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-LA-0002A TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8842 | PS4-60-LA-0002C-CA03 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-LA-0002A TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8843 | PS4-60-LA-0002C-CA04 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-LA-0002A TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8844 | PS4-60-LA-0002C-CA05 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-LA-0002B TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8845 | PS4-60-LA-0002C-CA06 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-LA-0002B TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-8846 | PS4-60-SEA-0001-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0004 TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone E | TM-00171
T-00171-8847 | PS4-71-IN-0001-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone F | TM-00171
T-00171-8848 | PS4-71-IN-0001-CA11 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0003A TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone F | TM-00171
T-00171-8849 | PS4-71-IN-0002-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0002 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-09 - CFO Pre-Pressure Module (UCP) |  | PS4-71-09 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone H | TM-00171
T-00171-8850 | PS4-71-IN-0003-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0003 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS4-71-23 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone B | TM-00171
T-00171-8851 | PS4-71-IN-0004A-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone H | TM-00171
T-00171-8852 | PS4-71-IN-0004B-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone H | TM-00171
T-00171-9466 | PS4-09-LB-8451A-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8451A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00171-9467 | PS4-09-LB-8451B-CA01 |  |  |  |  | CIX09 - Telecom cable power / Control / Multicore | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8451B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Telecom Cable Power/Control/Multicore | T | To be completed | PS4 - Milestone D | TM-00171
T-00227-0074 | PS4-61-ISR-0101 |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Shunt Reactor | EACOP | CPP AGI |  |  | 24 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00227
T-00227-0075 | PS4-61-IU-0010 |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | LLHT Oil Transformer | EACOP | CPP AGI |  |  | 24 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) |  | PS4-61-02 |  |  | Power Transformer | E | To be completed | PS4 - Milestone G | TM-00227
T-00227-0076 | PS4-63-IV-0010 |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing Transformer | EACOP | CPP AGI |  |  | 24 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00227
T-00227-0077 | PS4-63-IV-0011 |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing Transformer | EACOP | CPP AGI |  |  | 24 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00227
T-00227-0115 | PS4-61-IU-3100A |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | VFD Transformer | EACOP | CPP AGI |  |  | 24 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Power Transformer | E | To be completed | PS4 - Milestone H | TM-00227
T-00227-0116 | PS4-61-IU-3100B |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | VFD Transformer | EACOP | CPP AGI |  |  | 24 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Power Transformer | E | To be completed | PS4 - Milestone H | TM-00227
T-00227-0117 | PS4-61-IU-3100C |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | VFD Transformer | EACOP | CPP AGI |  |  | 24 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Power Transformer | E | To be completed | PS4 - Milestone H | TM-00227
T-00227-0126 | PS4-61-IU-0001A |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 24 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A |  | PS4-60-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone B | TM-00227
T-00227-0127 | PS4-61-IU-0001B |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 24 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B |  | PS4-60-04 |  |  | Power Transformer | E | To be completed | PS4 - Milestone B | TM-00227
T-00227-0128 | PS4-61-IU-0001C |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 24 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00227
T-00227-0129 | PS4-61-IU-0001D |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 24 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00227
T-00227-0130 | PS4-61-IU-0001E |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 24 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00227
T-00227-0131 | PS4-61-IU-0001F |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 24 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00227
T-00227-0132 | PS4-61-IU-0001G |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | 11/33kV Transformer - 6.8 MVA | EACOP | CPP AGI |  |  | 24 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Power Transformer | E | To be completed | PS4 - Milestone E | TM-00227
T-00227-0154 | PS4-61-IV-0001A |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Distribution Transformer | EACOP | CPP AGI |  |  | 24 |  | 24 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-07-02 11:23 | PS4-61-06 |  |  | Power Transformer | E | Closed | PS4 - Milestone A | TM-00227 | sridhar, muthu
T-00227-0155 | PS4-61-IV-0001B |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Distribution Transformer | EACOP | CPP AGI |  |  | 24 |  | 24 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-07-02 11:33 | PS4-61-06 |  |  | Power Transformer | E | Closed | PS4 - Milestone A | TM-00227 | sridhar, muthu
T-00227-0158 | PS4-61-IV-0002A |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Distribution Transformer | EACOP | CPP AGI |  |  | 24 |  | 24 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00227
T-00227-0159 | PS4-61-IV-0002B |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Distribution Transformer | EACOP | CPP AGI |  |  | 24 |  | 24 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00227
T-00227-0160 | PS4-61-IV-0007A |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Distribution Transformer | EACOP | CPP AGI |  |  | 24 |  | 24 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00227
T-00227-0161 | PS4-61-IV-0007B |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Distribution Transformer | EACOP | CPP AGI |  |  | 24 |  | 24 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00227
T-00227-0173 | PS4-61-IV-0005A |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Distribution Transformer | EACOP | CPP AGI |  |  | 24 |  | 24 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00227
T-00227-0174 | PS4-61-IV-0005B |  |  |  |  | TPX02 - Power transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Distribution Transformer | EACOP | CPP AGI |  |  | 24 |  | 24 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Power Transformer | E | To be completed | PS4 - Milestone D | TM-00227
T-00228-0080 | PS4-79-IV-0001 |  |  |  |  | TPX03 - LV transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Feeder to EHT Transformer / DB 1 | EACOP | CPP AGI |  |  | 20 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | LV Transformer | E | To be completed | PS4 - Milestone H | TM-00228
T-00228-0081 | PS4-79-IV-0002 |  |  |  |  | TPX03 - LV transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Feeder to EHT Transformer / DB 2 | EACOP | CPP AGI |  |  | 20 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | LV Transformer | E | To be completed | PS4 - Milestone H | TM-00228
T-00228-0082 | PS4-79-IV-0003 |  |  |  |  | TPX03 - LV transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Feeder to EHT Transformer / DB 3 | EACOP | CPP AGI |  |  | 20 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | LV Transformer | E | To be completed | PS4 - Milestone H | TM-00228
T-00228-0083 | PS4-79-IV-0004 |  |  |  |  | TPX03 - LV transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Feeder to EHT Transformer / DB 4 | EACOP | CPP AGI |  |  | 20 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | LV Transformer | E | To be completed | PS4 - Milestone H | TM-00228
T-00228-0084 | PS4-79-IV-0005 |  |  |  |  | TPX03 - LV transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Feeder to EHT Transformer / DB 5 | EACOP | CPP AGI |  |  | 20 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | LV Transformer | E | To be completed | PS4 - Milestone H | TM-00228
T-00228-0085 | PS4-79-IV-0006 |  |  |  |  | TPX03 - LV transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Feeder to EHT Transformer / DB 6 | EACOP | CPP AGI |  |  | 20 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | LV Transformer | E | To be completed | PS4 - Milestone H | TM-00228
T-00228-0086 | PS4-79-IV-0007 |  |  |  |  | TPX03 - LV transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Feeder to EHT Transformer / DB 7 | EACOP | CPP AGI |  |  | 20 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | LV Transformer | E | To be completed | PS4 - Milestone H | TM-00228
T-00228-0087 | PS4-79-IV-0008 |  |  |  |  | TPX03 - LV transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Feeder to EHT Transformer / DB 8 | EACOP | CPP AGI |  |  | 20 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | LV Transformer | E | To be completed | PS4 - Milestone H | TM-00228
T-00228-0088 | PS4-79-IV-0009 |  |  |  |  | TPX03 - LV transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Feeder to EHT Transformer / DB 9 | EACOP | CPP AGI |  |  | 20 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | LV Transformer | E | To be completed | PS4 - Milestone H | TM-00228
T-00228-0089 | PS4-79-IV-0010 |  |  |  |  | TPX03 - LV transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Feeder to EHT Transformer / DB 10 | EACOP | CPP AGI |  |  | 20 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | LV Transformer | E | To be completed | PS4 - Milestone H | TM-00228
T-00228-0090 | PS4-79-IV-0011 |  |  |  |  | TPX03 - LV transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Feeder to EHT Transformer / DB 11 | EACOP | CPP AGI |  |  | 20 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | LV Transformer | E | To be completed | PS4 - Milestone H | TM-00228
T-00228-0091 | PS4-79-IV-0012 |  |  |  |  | TPX03 - LV transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Feeder to EHT Transformer / DB 12 | EACOP | CPP AGI |  |  | 20 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | LV Transformer | E | To be completed | PS4 - Milestone H | TM-00228
T-00228-0092 | PS4-87-IRF-0001 |  |  |  |  | TPX03 - LV transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Transformer Rectifier Unit 1-for tank (PS4-53-TR-4100) | EACOP | CPP AGI |  |  | 20 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-53-01 - Utility Water / Storage Tank |  | PS4-53-01 |  |  | LV Transformer | E | To be completed | PS4 - Milestone C | TM-00228
T-00228-0093 | PS4-87-IRF-0002 |  |  |  |  | TPX03 - LV transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Transformer Rectifier Unit 2-for tank (PS4-71-TR-4100) | EACOP | CPP AGI |  |  | 20 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | LV Transformer | E | To be completed | PS4 - Milestone H | TM-00228
T-00228-0094 | PS4-87-IRF-0003 |  |  |  |  | TPX03 - LV transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Transformer Rectifier Unit 3-for tank (PS4-71-TR-4200) | EACOP | CPP AGI |  |  | 20 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | LV Transformer | E | To be completed | PS4 - Milestone H | TM-00228
T-00228-0095 | PS4-87-IRF-0004 |  |  |  |  | TPX03 - LV transformer | PCOM - Precommissioning | E | Static Test | E - Electrical | Transformer Rectifier Unit 4-for tank ( PS4-71-TR-4400) | EACOP | CPP AGI |  |  | 20 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank |  | PS4-71-15 |  |  | LV Transformer | E | To be completed | PS4 - Milestone F | TM-00228
T-00230-0033 | PS4-61-IK-0003 |  |  |  |  | TPX05 - LV switchboard | PCOM - Precommissioning | E | Static Test | E - Electrical | LV SWGR | EACOP | CPP AGI |  |  | 28 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Switchboard | E | Submitted | PS4 - Milestone B | TM-00230
T-00230-0034 | PS4-61-IK-0006 |  |  |  |  | TPX05 - LV switchboard | PCOM - Precommissioning | E | Static Test | E - Electrical | LV SWGR | EACOP | CPP AGI |  |  | 28 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Switchboard | E | To be completed | PS4 - Milestone D | TM-00230
T-00232-1125 | PS4-25-DM-3100A-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-27 13:41 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1126 | PS4-25-DM-3100A-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-27 13:42 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1127 | PS4-25-DM-3100A-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-27 13:43 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1128 | PS4-25-DM-3100A-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-27 13:44 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1129 | PS4-25-DM-3100A-CH05 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-27 13:45 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1130 | PS4-25-DM-3100A-CH06 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-27 13:46 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1131 | PS4-25-DM-3100B-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-27 13:49 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1132 | PS4-25-DM-3100B-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-27 13:55 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1133 | PS4-25-DM-3100B-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-27 13:57 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1134 | PS4-25-DM-3100B-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-27 13:57 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1135 | PS4-25-DM-3100B-CH05 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-27 13:59 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1136 | PS4-25-DM-3100B-CH06 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-27 13:59 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1137 | PS4-25-DM-3100C-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-27 14:00 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1138 | PS4-25-DM-3100C-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-27 14:06 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1139 | PS4-25-DM-3100C-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-27 14:07 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1140 | PS4-25-DM-3100C-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-27 14:09 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1141 | PS4-25-DM-3100C-CH05 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-27 14:09 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1142 | PS4-25-DM-3100C-CH06 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-27 14:10 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1143 | PS4-60-IJ-0001A-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100A TO PS4-60-IJ-0001A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-18 11:08 | PS4-60-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00232 | tereshchenko, nikolai
T-00232-1144 | PS4-60-IJ-0001B-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100B TO PS4-60-IJ-0001B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-18 11:08 | PS4-60-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00232 | tereshchenko, nikolai
T-00232-1145 | PS4-60-IJ-0001C-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100C TO PS4-60-IJ-0001C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-18 11:10 | PS4-60-07 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | tereshchenko, nikolai
T-00232-1146 | PS4-60-IJ-0001D-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100D TO PS4-60-IJ-0001D | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-18 11:11 | PS4-60-10 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | tereshchenko, nikolai
T-00232-1147 | PS4-60-IJ-0001E-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100E TO PS4-60-IJ-0001E | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-18 11:12 | PS4-60-13 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | tereshchenko, nikolai
T-00232-1148 | PS4-60-IJ-0001F-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100F TO PS4-60-IJ-0001F | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-18 11:13 | PS4-60-16 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | tereshchenko, nikolai
T-00232-1149 | PS4-60-IJ-0001G-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100G TO PS4-60-IJ-0001G | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-18 11:13 | PS4-60-19 |  |  | HV Power Cable | E | Closed | PS4 - Milestone E | TM-00232 | tereshchenko, nikolai
T-00232-1150 | PS4-61-IDH-3100A-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-22 11:29 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1151 | PS4-61-IDH-3100A-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-22 11:31 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1152 | PS4-61-IDH-3100A-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-22 11:35 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1153 | PS4-61-IDH-3100A-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-22 11:37 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1154 | PS4-61-IDH-3100A-CH05 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-22 11:40 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1155 | PS4-61-IDH-3100A-CH06 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-22 11:42 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1156 | PS4-61-IDH-3100A-CH07 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-22 11:43 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1157 | PS4-61-IDH-3100A-CH08 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-22 11:44 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1158 | PS4-61-IDH-3100A-CH09 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-22 11:45 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1159 | PS4-61-IDH-3100A-CH10 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-22 11:48 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1160 | PS4-61-IDH-3100A-CH11 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-22 11:49 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1161 | PS4-61-IDH-3100A-CH12 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-22 11:49 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1162 | PS4-61-IDH-3100B-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-22 11:50 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1163 | PS4-61-IDH-3100B-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-22 11:52 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1164 | PS4-61-IDH-3100B-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-22 11:52 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1165 | PS4-61-IDH-3100B-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-22 11:53 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1166 | PS4-61-IDH-3100B-CH05 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-22 11:54 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1167 | PS4-61-IDH-3100B-CH06 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-22 11:55 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1168 | PS4-61-IDH-3100B-CH07 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-22 11:56 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1169 | PS4-61-IDH-3100B-CH08 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-22 11:57 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1170 | PS4-61-IDH-3100B-CH09 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-22 11:58 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1171 | PS4-61-IDH-3100B-CH10 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-22 11:58 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1172 | PS4-61-IDH-3100B-CH11 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-22 11:59 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1173 | PS4-61-IDH-3100B-CH12 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-22 12:00 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1174 | PS4-61-IDH-3100C-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-22 12:01 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1175 | PS4-61-IDH-3100C-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-22 13:20 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1176 | PS4-61-IDH-3100C-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-22 13:21 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1177 | PS4-61-IDH-3100C-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-22 13:24 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1178 | PS4-61-IDH-3100C-CH05 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-22 13:25 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1179 | PS4-61-IDH-3100C-CH06 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-22 13:25 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1180 | PS4-61-IDH-3100C-CH07 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-22 13:26 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1181 | PS4-61-IDH-3100C-CH08 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-22 13:27 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1182 | PS4-61-IDH-3100C-CH09 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-22 13:28 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1183 | PS4-61-IDH-3100C-CH10 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-22 13:28 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1184 | PS4-61-IDH-3100C-CH11 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-22 13:29 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1185 | PS4-61-IDH-3100C-CH12 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-22 13:30 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1186 | PS4-61-IJ-0001-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0001A TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-03-06 12:20 | PS4-60-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00232 | battalov, rustam
T-00232-1187 | PS4-61-IJ-0001-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0001A TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-03-06 12:22 | PS4-60-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00232 | battalov, rustam
T-00232-1188 | PS4-61-IJ-0001-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0001A TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-03-06 12:22 | PS4-60-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00232 | battalov, rustam
T-00232-1189 | PS4-61-IJ-0001-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0001B TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-03-06 12:23 | PS4-60-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00232 | battalov, rustam
T-00232-1190 | PS4-61-IJ-0001-CH05 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0001B TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-03-06 12:27 | PS4-60-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00232 | battalov, rustam
T-00232-1191 | PS4-61-IJ-0001-CH06 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0001B TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-03-06 12:28 | PS4-60-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00232 | battalov, rustam
T-00232-1192 | PS4-61-IJ-0001-CH07 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0001C TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-03-06 12:29 | PS4-60-07 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1193 | PS4-61-IJ-0001-CH08 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0001C TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-03-06 12:30 | PS4-60-07 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1194 | PS4-61-IJ-0001-CH09 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0001C TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-03-06 12:31 | PS4-60-07 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1195 | PS4-61-IJ-0001-CH10 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0001D TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-03-06 12:32 | PS4-60-10 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1196 | PS4-61-IJ-0001-CH11 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0001D TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-03-06 12:33 | PS4-60-10 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1197 | PS4-61-IJ-0001-CH12 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0001D TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-03-06 12:34 | PS4-60-10 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1198 | PS4-61-IJ-0001-CH13 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0001E TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-03-06 12:35 | PS4-60-13 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1199 | PS4-61-IJ-0001-CH14 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0001E TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-03-06 12:36 | PS4-60-13 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1200 | PS4-61-IJ-0001-CH15 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0001E TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-03-06 12:36 | PS4-60-13 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1201 | PS4-61-IJ-0001-CH16 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0001F TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-03-06 12:37 | PS4-60-16 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1202 | PS4-61-IJ-0001-CH17 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0001F TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-03-06 12:37 | PS4-60-16 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1203 | PS4-61-IJ-0001-CH18 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0001F TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-03-06 12:38 | PS4-60-16 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1204 | PS4-61-IJ-0001-CH19 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0001G TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-03-06 12:38 | PS4-60-19 |  |  | HV Power Cable | E | Closed | PS4 - Milestone E | TM-00232 | battalov, rustam
T-00232-1205 | PS4-61-IJ-0001-CH20 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0001G TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-03-06 12:39 | PS4-60-19 |  |  | HV Power Cable | E | Closed | PS4 - Milestone E | TM-00232 | battalov, rustam
T-00232-1206 | PS4-61-IJ-0001-CH21 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0001G TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-03-06 12:39 | PS4-60-19 |  |  | HV Power Cable | E | Closed | PS4 - Milestone E | TM-00232 | battalov, rustam
T-00232-1207 | PS4-61-IJ-0010-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0010 TO PS4-61-IJ-0010 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-03-06 12:41 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00232 | battalov, rustam
T-00232-1208 | PS4-61-IJ-0010-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0010 TO PS4-61-IJ-0010 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-03-06 12:41 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00232 | battalov, rustam
T-00232-1209 | PS4-61-IJ-0010-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0010 TO PS4-61-IJ-0010 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-03-06 12:42 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00232 | battalov, rustam
T-00232-1210 | PS4-61-IJ-0010-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0010 TO PS4-61-IJ-0010 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-03-06 12:42 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00232 | battalov, rustam
T-00232-1211 | PS4-61-IJ-0010-CH05 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0010 TO PS4-61-IJ-0010 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-03-06 12:43 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00232 | battalov, rustam
T-00232-1212 | PS4-61-IJ-0010-CH06 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0010 TO PS4-61-IJ-0010 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-03-06 12:44 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00232 | battalov, rustam
T-00232-1213 | PS4-61-ISR-0101-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-ISR-0101 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-03-06 08:35 | PS4-61-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1214 | PS4-61-ISR-0101-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-ISR-0101 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-03-06 08:37 | PS4-61-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1215 | PS4-61-ISR-0101-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-ISR-0101 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-03-06 08:37 | PS4-61-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1216 | PS4-61-IU-0001A-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100A TO PS4-61-IU-0001A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-02-27 13:12 | PS4-60-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00232 | battalov, rustam
T-00232-1217 | PS4-61-IU-0001A-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100A TO PS4-61-IU-0001A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-02-27 13:13 | PS4-60-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00232 | battalov, rustam
T-00232-1218 | PS4-61-IU-0001A-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100A TO PS4-61-IU-0001A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-02-27 13:13 | PS4-60-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00232 | battalov, rustam
T-00232-1219 | PS4-61-IU-0001B-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100B TO PS4-61-IU-0001B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-02-27 13:16 | PS4-60-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00232 | battalov, rustam
T-00232-1220 | PS4-61-IU-0001B-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100B TO PS4-61-IU-0001B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-02-27 13:16 | PS4-60-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00232 | battalov, rustam
T-00232-1221 | PS4-61-IU-0001B-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100B TO PS4-61-IU-0001B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-02-27 13:17 | PS4-60-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00232 | battalov, rustam
T-00232-1222 | PS4-61-IU-0001C-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100C TO PS4-61-IU-0001C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-02-27 13:17 | PS4-60-07 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1223 | PS4-61-IU-0001C-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100C TO PS4-61-IU-0001C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-02-27 13:18 | PS4-60-07 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1224 | PS4-61-IU-0001C-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100C TO PS4-61-IU-0001C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-02-27 13:18 | PS4-60-07 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1225 | PS4-61-IU-0001D-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100D TO PS4-61-IU-0001D | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-02-27 13:19 | PS4-60-10 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1226 | PS4-61-IU-0001D-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100D TO PS4-61-IU-0001D | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-02-27 13:19 | PS4-60-10 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1227 | PS4-61-IU-0001D-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100D TO PS4-61-IU-0001D | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-02-27 13:20 | PS4-60-10 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1228 | PS4-61-IU-0001E-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100E TO PS4-61-IU-0001E | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-02-27 13:20 | PS4-60-13 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1229 | PS4-61-IU-0001E-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100E TO PS4-61-IU-0001E | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-02-27 13:21 | PS4-60-13 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1230 | PS4-61-IU-0001E-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100E TO PS4-61-IU-0001E | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-02-27 13:21 | PS4-60-13 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1231 | PS4-61-IU-0001F-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100F TO PS4-61-IU-0001F | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-02-27 13:22 | PS4-60-16 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1232 | PS4-61-IU-0001F-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100F TO PS4-61-IU-0001F | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-02-27 13:22 | PS4-60-16 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1233 | PS4-61-IU-0001F-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100F TO PS4-61-IU-0001F | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-02-27 13:23 | PS4-60-16 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1234 | PS4-61-IU-0001G-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100G TO PS4-61-IU-0001G | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-02-27 13:23 | PS4-60-19 |  |  | HV Power Cable | E | Closed | PS4 - Milestone E | TM-00232 | battalov, rustam
T-00232-1235 | PS4-61-IU-0001G-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100G TO PS4-61-IU-0001G | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-02-27 13:24 | PS4-60-19 |  |  | HV Power Cable | E | Closed | PS4 - Milestone E | TM-00232 | battalov, rustam
T-00232-1236 | PS4-61-IU-0001G-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-GE-8100G TO PS4-61-IU-0001G | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-02-27 13:24 | PS4-60-19 |  |  | HV Power Cable | E | Closed | PS4 - Milestone E | TM-00232 | battalov, rustam
T-00232-1237 | PS4-61-IU-0010-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-0010 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-03-06 08:40 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00232 | battalov, rustam
T-00232-1238 | PS4-61-IU-0010-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-0010 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-03-06 08:41 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00232 | battalov, rustam
T-00232-1239 | PS4-61-IU-0010-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-0010 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-03-06 08:41 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00232 | battalov, rustam
T-00232-1240 | PS4-61-IU-3100A-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-20 11:19 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1241 | PS4-61-IU-3100A-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-20 11:20 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1242 | PS4-61-IU-3100A-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-20 11:20 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1243 | PS4-61-IU-3100A-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0006A TO PS4-61-IU-3100A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-04-22 13:30 | PS4-25-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1244 | PS4-61-IU-3100B-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-20 11:21 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1245 | PS4-61-IU-3100B-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-20 11:22 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1246 | PS4-61-IU-3100B-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-20 11:25 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1247 | PS4-61-IU-3100B-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0006B TO PS4-61-IU-3100B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-04-22 13:31 | PS4-25-03 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1248 | PS4-61-IU-3100C-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-20 11:26 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1249 | PS4-61-IU-3100C-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-20 11:27 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1250 | PS4-61-IU-3100C-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IU-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-20 11:28 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1251 | PS4-61-IU-3100C-CH04 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0006C TO PS4-61-IU-3100C | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-04-22 13:31 | PS4-25-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone H | TM-00232 | tereshchenko, nikolai
T-00232-1252 | PS4-61-IV-0001A-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0001A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-03-06 11:58 | PS4-61-06 |  |  | HV Power Cable | E | Closed | PS4 - Milestone A | TM-00232 | battalov, rustam
T-00232-1253 | PS4-61-IV-0001A-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0001A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-03-06 11:58 | PS4-61-06 |  |  | HV Power Cable | E | Closed | PS4 - Milestone A | TM-00232 | battalov, rustam
T-00232-1254 | PS4-61-IV-0001A-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0001A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-03-06 11:59 | PS4-61-06 |  |  | HV Power Cable | E | Closed | PS4 - Milestone A | TM-00232 | battalov, rustam
T-00232-1255 | PS4-61-IV-0001B-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0001B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-03-06 12:00 | PS4-61-06 |  |  | HV Power Cable | E | Closed | PS4 - Milestone A | TM-00232 | battalov, rustam
T-00232-1256 | PS4-61-IV-0001B-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0001B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-03-06 12:17 | PS4-61-06 |  |  | HV Power Cable | E | Closed | PS4 - Milestone A | TM-00232 | battalov, rustam
T-00232-1257 | PS4-61-IV-0001B-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0001B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-03-06 12:16 | PS4-61-06 |  |  | HV Power Cable | E | Closed | PS4 - Milestone A | TM-00232 | battalov, rustam
T-00232-1258 | PS4-61-IV-0002A-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0002A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-03-06 10:26 | PS4-61-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00232 | battalov, rustam
T-00232-1259 | PS4-61-IV-0002A-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0002A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-03-06 10:27 | PS4-61-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00232 | battalov, rustam
T-00232-1260 | PS4-61-IV-0002A-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0002A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-03-06 10:27 | PS4-61-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00232 | battalov, rustam
T-00232-1261 | PS4-61-IV-0002B-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0002B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-03-06 11:47 | PS4-61-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00232 | battalov, rustam
T-00232-1262 | PS4-61-IV-0002B-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0002B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-03-06 11:48 | PS4-61-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00232 | battalov, rustam
T-00232-1263 | PS4-61-IV-0002B-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0002B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-03-06 11:49 | PS4-61-04 |  |  | HV Power Cable | E | Closed | PS4 - Milestone B | TM-00232 | battalov, rustam
T-00232-1264 | PS4-61-IV-0005A-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0005A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-03 - 0.4kV Switchboard Office & Facilities Building (PS4-61-IK-0005) |  | PS4-61-03 |  |  | HV Power Cable | E | To be completed | PS4 - Milestone I | TM-00232
T-00232-1265 | PS4-61-IV-0005A-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0005A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-03 - 0.4kV Switchboard Office & Facilities Building (PS4-61-IK-0005) |  | PS4-61-03 |  |  | HV Power Cable | E | To be completed | PS4 - Milestone I | TM-00232
T-00232-1266 | PS4-61-IV-0005A-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0005A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-03 - 0.4kV Switchboard Office & Facilities Building (PS4-61-IK-0005) |  | PS4-61-03 |  |  | HV Power Cable | E | To be completed | PS4 - Milestone I | TM-00232
T-00232-1267 | PS4-61-IV-0005B-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0005B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-03 - 0.4kV Switchboard Office & Facilities Building (PS4-61-IK-0005) |  | PS4-61-03 |  |  | HV Power Cable | E | To be completed | PS4 - Milestone I | TM-00232
T-00232-1268 | PS4-61-IV-0005B-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0005B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-03 - 0.4kV Switchboard Office & Facilities Building (PS4-61-IK-0005) |  | PS4-61-03 |  |  | HV Power Cable | E | To be completed | PS4 - Milestone I | TM-00232
T-00232-1269 | PS4-61-IV-0005B-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0005B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-03 - 0.4kV Switchboard Office & Facilities Building (PS4-61-IK-0005) |  | PS4-61-03 |  |  | HV Power Cable | E | To be completed | PS4 - Milestone I | TM-00232
T-00232-1270 | PS4-61-IV-0007A-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0007A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-03-06 11:51 | PS4-61-05 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1271 | PS4-61-IV-0007A-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0007A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-03-06 11:52 | PS4-61-05 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1272 | PS4-61-IV-0007A-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0007A | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-03-06 11:53 | PS4-61-05 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1273 | PS4-61-IV-0007B-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0007B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-03-06 11:54 | PS4-61-05 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1274 | PS4-61-IV-0007B-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0007B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-03-06 11:55 | PS4-61-05 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1275 | PS4-61-IV-0007B-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IV-0007B | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-03-06 11:56 | PS4-61-05 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1276 | PS4-61-NER-0010-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-0010 TO PS4-61-NER-0010 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) |  | PS4-61-02 |  |  | HV Power Cable | E | To be completed | PS4 - Milestone G | TM-00232
T-00232-1277 | PS4-63-IV-0010-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-63-IV-0010 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-03-06 10:02 | PS4-61-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1278 | PS4-63-IV-0010-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-63-IV-0010 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-03-06 10:02 | PS4-61-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1279 | PS4-63-IV-0010-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-63-IV-0010 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-03-06 10:02 | PS4-61-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1280 | PS4-63-IV-0011-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-63-IV-0011 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-03-06 10:03 | PS4-61-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1281 | PS4-63-IV-0011-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-63-IV-0011 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-03-06 10:03 | PS4-61-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1282 | PS4-63-IV-0011-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-63-IV-0011 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-03-06 10:03 | PS4-61-01 |  |  | HV Power Cable | E | Closed | PS4 - Milestone D | TM-00232 | battalov, rustam
T-00232-1283 | PS4-63-NER-0010-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-63-IV-0010 TO PS4-63-NER-0010 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | HV Power Cable | E | To be completed | PS4 - Milestone D | TM-00232
T-00232-1284 | PS4-63-NER-0011-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-63-IV-0011 TO PS4-63-NER-0011 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | HV Power Cable | E | To be completed | PS4 - Milestone D | TM-00232
T-00232-1285 | PS4-79-BH-0001-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0010 TO PS4-79-BH-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-07-18 11:15 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00232 | tereshchenko, nikolai
T-00232-1286 | PS4-79-BH-0001-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0010 TO PS4-79-BH-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-07-18 11:16 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00232 | tereshchenko, nikolai
T-00232-1287 | PS4-79-BH-0001-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0010 TO PS4-79-BH-0001 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-07-18 11:16 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00232 | tereshchenko, nikolai
T-00232-1288 | PS4-79-BH-0002-CH01 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0010 TO PS4-79-BH-0002 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-07-18 11:17 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00232 | tereshchenko, nikolai
T-00232-1289 | PS4-79-BH-0002-CH02 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0010 TO PS4-79-BH-0002 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-07-18 11:18 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00232 | tereshchenko, nikolai
T-00232-1290 | PS4-79-BH-0002-CH03 |  |  |  |  | TPX08 - HV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IJ-0010 TO PS4-79-BH-0002 | EACOP | CPP AGI |  |  | 2 |  | 2 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-07-18 11:23 | PS4-61-02 |  |  | HV Power Cable | E | Closed | PS4 - Milestone G | TM-00232 | tereshchenko, nikolai
T-00233-10030 | PS4-62-IE-0001-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10031 | PS4-62-IE-0001-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10032 | PS4-62-IE-0001-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10033 | PS4-62-IE-0001-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10034 | PS4-62-IE-0001-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10035 | PS4-62-IE-0001-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10036 | PS4-62-IE-0001-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10037 | PS4-62-IE-0001-CL52 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10038 | PS4-62-IE-0001-CL53 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10039 | PS4-62-IE-0001-CL54 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10040 | PS4-62-IE-0001-CL55 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10041 | PS4-62-IE-0001-CL56 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10042 | PS4-62-IE-0001-CL57 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10043 | PS4-62-IE-0001-CL58 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10044 | PS4-62-IE-0001-CL59 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10045 | PS4-62-IE-0001-CL60 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10046 | PS4-62-IE-0002-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10047 | PS4-62-IE-0002-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10048 | PS4-62-IE-0002-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10049 | PS4-62-IE-0002-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10050 | PS4-62-IE-0002-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10051 | PS4-62-IE-0002-CL51 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10052 | PS4-62-IE-0002-CL52 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10053 | PS4-62-IE-0002-CL53 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10054 | PS4-62-IE-0002-CL54 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10055 | PS4-62-IE-0002-CL55 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10056 | PS4-62-IE-0002-CL56 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10057 | PS4-62-IE-0002-CL57 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10058 | PS4-62-IE-0002-CL58 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10059 | PS4-62-IE-0002-CL59 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-10527 | PS4-06-GB-0003-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-GB-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building |  | PS4-06-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00233
T-00233-10528 | PS4-60-IN-0002A-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-07-04 12:23 | PS4-60-57 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-10529 | PS4-60-IN-0002B-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-07-04 12:30 | PS4-60-59 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-10530 | PS4-60-IN-0002C-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) | 2026-07-04 12:38 | PS4-60-61 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-10531 | PS4-60-IN-0002D-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) | 2026-07-04 12:41 | PS4-60-63 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-10532 | PS4-60-IN-0002E-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) | 2026-07-04 12:44 | PS4-60-65 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-10533 | PS4-60-IN-0002F-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) | 2026-07-04 12:47 | PS4-60-67 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-10534 | PS4-60-IN-0002G-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) | 2026-07-04 12:50 | PS4-60-69 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-10621 | PS4-05-BE-0001-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 10:49 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-10622 | PS4-06-IG-0004A-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-IG-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building |  | PS4-06-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00233
T-00233-10623 | PS4-06-IG-0004B-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-GU-0003B TO PS4-06-IG-0004B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building |  | PS4-06-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00233
T-00233-10624 | PS4-25-DM-3100A-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-06-12 05:50 | PS4-25-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-10625 | PS4-25-DM-3100A-CG02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-06-12 05:51 | PS4-25-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-10626 | PS4-25-DM-3100B-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-06-12 05:59 | PS4-25-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-10627 | PS4-25-DM-3100B-CG02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-06-12 06:01 | PS4-25-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-10628 | PS4-25-DM-3100C-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-06-12 06:04 | PS4-25-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-10629 | PS4-25-DM-3100C-CG02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-06-12 06:05 | PS4-25-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-10630 | PS4-60-IH-0001A-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-09 14:07 | PS4-60-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-10631 | PS4-60-IH-0001B-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-07 13:04 | PS4-60-06 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-10632 | PS4-60-IH-0001C-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | 2026-06-08 05:48 | PS4-60-09 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-10633 | PS4-60-IH-0001D-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | 2026-06-08 07:32 | PS4-60-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-10634 | PS4-60-IH-0001E-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | 2026-06-09 14:10 | PS4-60-15 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-10635 | PS4-60-IH-0001F-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | 2026-06-09 14:13 | PS4-60-18 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-10636 | PS4-60-IH-0001G-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | 2026-06-09 14:17 | PS4-60-21 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-10637 | PS4-60-IH-0002-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-11 14:19 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-10638 | PS4-60-IH-0002-CG02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-11 14:21 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-10639 | PS4-61-IH-0004-CG01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-07-05 05:58 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-10640 | PS4-61-IH-0004-CG02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-10641 | PS4-61-IH-0004-CG03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-10642 | PS4-61-IH-0004-CG04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-10653 | PS4-61-IK-0003-CG07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-06-07 12:51 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-10871 | PS4-60-BE-0007A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BE-0007A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A | 2026-07-04 10:45 | PS4-60-56 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-10872 | PS4-60-BE-0007A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BE-0007A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A | 2026-07-04 10:51 | PS4-60-56 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-10873 | PS4-60-BE-0007B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BE-0007B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B | 2026-07-04 10:57 | PS4-60-58 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-10874 | PS4-60-BE-0007B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BE-0007B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B | 2026-07-04 11:11 | PS4-60-58 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-10875 | PS4-60-BE-0007C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BE-0007C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C | 2026-07-04 11:15 | PS4-60-60 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-10876 | PS4-60-BE-0007C-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BE-0007C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C | 2026-07-04 11:21 | PS4-60-60 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-10877 | PS4-60-BE-0007D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BE-0007D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D | 2026-07-04 11:24 | PS4-60-62 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-10878 | PS4-60-BE-0007D-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BE-0007D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D | 2026-07-04 11:26 | PS4-60-62 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-10879 | PS4-60-BE-0007E-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BE-0007E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E | 2026-07-04 11:29 | PS4-60-64 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-10880 | PS4-60-BE-0007E-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BE-0007E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E | 2026-07-04 11:40 | PS4-60-64 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-10881 | PS4-60-BE-0007F-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BE-0007F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F | 2026-07-04 11:51 | PS4-60-66 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-10882 | PS4-60-BE-0007F-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BE-0007F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F | 2026-07-04 11:55 | PS4-60-66 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-10883 | PS4-60-BE-0007G-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BE-0007G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G | 2026-07-04 11:59 | PS4-60-68 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-10884 | PS4-60-BE-0007G-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BE-0007G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G | 2026-07-04 12:15 | PS4-60-68 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-10885 | PS4-60-ISO-62800A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-ISO-62800A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-07-04 12:53 | PS4-60-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-10886 | PS4-60-ISO-62800C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-ISO-62800C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | 2026-07-04 12:56 | PS4-60-09 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-10887 | PS4-60-ISO-62800E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-ISO-62800E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | 2026-07-04 13:00 | PS4-60-15 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-10888 | PS4-60-ISO-62800G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-ISO-62800G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | 2026-07-04 13:08 | PS4-60-21 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-10971 | PS4-05-BE-0001-CL12 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0020 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-04 10:42 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-10972 | PS4-08-52BT-0131-CS01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-08-15CB-1001 TO PS4-08-52BT-0131 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00233
T-00233-10973 | PS4-08-85CP-1201-CS01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-08-11CB-1201 TO PS4-08-85CP-1201 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00233
T-00233-10974 | PS4-08-85CP-1202-CS01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-08-11CB-1201 TO PS4-08-85CP-1202 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00233
T-00233-10975 | PS4-08-85CP-1601-CS01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-08-11CB-1601 TO PS4-08-85CP-1601 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00233
T-00233-10976 | PS4-09-DM-84500A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-DM-84500A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-10977 | PS4-09-DM-84500B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-DM-84500B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-11225 | PS4-71-BE-0001A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 06:10 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11226 | PS4-71-BE-0001A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 06:13 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11227 | PS4-71-BE-0001A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 06:19 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11228 | PS4-71-BE-0001A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 06:24 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11229 | PS4-71-BE-0001A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 06:30 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11230 | PS4-71-BE-0001A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 06:34 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11231 | PS4-71-BE-0001A-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 06:38 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11232 | PS4-71-BE-0001A-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 06:55 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11233 | PS4-71-BE-0001A-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 07:02 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11234 | PS4-71-BE-0001A-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 07:06 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11235 | PS4-71-BE-0001A-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 07:10 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11236 | PS4-71-BE-0001A-CL12 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004A TO PS4-71-BE-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 07:14 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11237 | PS4-71-BE-0001B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 07:17 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11238 | PS4-71-BE-0001B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 07:19 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11239 | PS4-71-BE-0001B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 07:22 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11240 | PS4-71-BE-0001B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 07:25 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11241 | PS4-71-BE-0001B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 07:27 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11242 | PS4-71-BE-0001B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 07:30 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11243 | PS4-71-BE-0001B-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 07:33 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11244 | PS4-71-BE-0001B-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 07:36 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11245 | PS4-71-BE-0001B-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 07:40 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11246 | PS4-71-BE-0001B-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 07:42 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11247 | PS4-71-BE-0001B-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 07:51 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11248 | PS4-71-BE-0001B-CL12 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0004B TO PS4-71-BE-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-05 07:59 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-11249 | PS4-71-BE-0005-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0001 TO PS4-71-BE-0005 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) | 2026-07-05 08:02 | PS4-71-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone F | TM-00233 | sridhar, muthu
T-00233-11250 | PS4-71-BE-0005-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0001 TO PS4-71-BE-0005 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) | 2026-07-05 08:05 | PS4-71-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone F | TM-00233 | sridhar, muthu
T-00233-11251 | PS4-71-BE-0005-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0001 TO PS4-71-BE-0005 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) | 2026-07-05 08:08 | PS4-71-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone F | TM-00233 | sridhar, muthu
T-00233-11252 | PS4-71-BE-0005-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0001 TO PS4-71-BE-0005 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) | 2026-07-05 08:11 | PS4-71-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone F | TM-00233 | sridhar, muthu
T-00233-5645 | PS4-01-BE-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-01-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-01-08 - PS4 Deluge Valve Skid (PS4-01-UK-6100) | 2026-06-08 13:53 | PS4-01-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone F | TM-00233 | sridhar, muthu
T-00233-5646 | PS4-01-FCV-0003A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-01-FCV-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A | 2026-06-05 11:28 | PS4-01-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-5647 | PS4-01-FCV-0003B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-01-FCV-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B | 2026-06-05 11:28 | PS4-01-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-5648 | PS4-01-FCV-0004A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-01-FCV-0004A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A | 2026-06-05 11:25 | PS4-01-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-5649 | PS4-01-FCV-0004B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-01-FCV-0004B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B | 2026-06-05 11:27 | PS4-01-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-5660 | PS4-01-IG-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-01-IG-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00233
T-00233-5661 | PS4-01-LB-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-01-LB-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling | 2026-06-08 11:09 | PS4-01-11 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-5662 | PS4-01-LB-0004-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-01-LB-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling | 2026-06-08 11:19 | PS4-01-11 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-5663 | PS4-01-LB-0004-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0010 TO PS4-01-LB-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling | 2026-06-08 11:25 | PS4-01-11 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-5664 | PS4-01-MOV-8701-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-01-MOV-8701 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-01-05 - Foam Skid | 2026-07-24 10:51 | PS4-01-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone F | TM-00233 | sridhar, muthu
T-00233-5674 | PS4-03-SEA-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0005 TO PS4-03-SEA-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-03-22 - FZ-G1 Guard House |  | PS4-03-22 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone I | TM-00233
T-00233-5675 | PS4-03-SEA-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-03-SEA-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-06-07 06:14 | PS4-03-14 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-5677 | PS4-05-BE-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 11:02 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-5678 | PS4-05-BE-0001-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 11:09 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-5679 | PS4-05-BE-0001-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 11:13 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-5680 | PS4-05-BE-0001-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 11:16 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-5681 | PS4-05-BE-0001-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 11:22 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-5682 | PS4-05-BE-0001-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 11:25 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-5683 | PS4-05-BE-0001-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 11:29 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-5684 | PS4-05-BE-0001-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 11:35 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-5685 | PS4-05-BE-0001-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 11:38 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-5686 | PS4-05-BE-0001-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 11:45 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-5687 | PS4-05-BE-0001-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-DG-8100 TO PS4-05-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 11:48 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-5688 | PS4-05-IE-8100-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-08 11:56 | PS4-05-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-5689 | PS4-05-IE-8100-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-08 12:02 | PS4-05-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-5690 | PS4-05-IG-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IG-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone I | TM-00233
T-00233-5693 | PS4-05-IG-0009-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IG-0009 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-06-09 08:09 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-5694 | PS4-05-IG-0009-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-05-IG-0009 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-06-09 08:13 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-5695 | PS4-05-IG-0014-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IG-0014 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-62-06 - CRO Generator Building Emergency Lighting DB - PS4-05-IG-0014 | 2026-07-24 10:53 | PS4-62-06 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5696 | PS4-05-IG-0020-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IG-0020 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-62-07 - CRO Generator Electrical Building Emergency L&SP DB - PS4-05-IG-0020 | 2026-06-09 08:17 | PS4-62-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5697 | PS4-06-GB-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-GB-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-06-06 10:09 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5698 | PS4-06-GB-0003-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-GB-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-06-06 10:12 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5699 | PS4-06-GB-0003-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-GB-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-06-06 10:15 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5700 | PS4-06-GB-0003-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-GB-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-06-06 10:18 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5701 | PS4-06-GB-0003-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-GB-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-06-06 10:21 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5702 | PS4-06-GB-0003-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-GB-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-06-06 10:24 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5703 | PS4-06-GU-0003A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-06-GU-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-06-08 12:09 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5704 | PS4-06-GU-0003B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-06-GU-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-06-08 12:17 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5705 | PS4-06-GU-0003C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-06-GU-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building |  | PS4-06-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00233
T-00233-5707 | PS4-06-IG-0004A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-IG-0004A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-06-06 08:40 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5708 | PS4-06-IG-0004A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-IG-0004A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-06-06 08:40 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5709 | PS4-06-IG-0004A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-IG-0004A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-06-06 08:39 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5710 | PS4-06-IG-0004A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-GU-0003A TO PS4-06-IG-0004A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-06-06 08:45 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5712 | PS4-06-IG-0004B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-GU-0003B TO PS4-06-IG-0004B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-06-07 06:19 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5713 | PS4-06-IG-0004B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-GU-0003B TO PS4-06-IG-0004B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-06-07 06:23 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5714 | PS4-06-IG-0004B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-GU-0003B TO PS4-06-IG-0004B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-06-07 06:48 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5715 | PS4-06-IG-0004B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-GU-0003B TO PS4-06-IG-0004B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-06-07 06:52 | PS4-06-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5760 | PS4-08-11CB-1501-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0005 TO PS4-08-11CB-1501 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-SSF1-171120 | PS4 - TZA - PS4 - Tanzania | PS4-08-11 - Corporate LAN (SIE) |  | PS4-08-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone C | TM-00233
T-00233-5761 | PS4-08-11CB-1901-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-08-11CB-1901 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-SSF1-171120 | PS4 - TZA - PS4 - Tanzania | PS4-08-11 - Corporate LAN (SIE) | 2026-06-09 11:37 | PS4-08-11 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-5829 | PS4-09-LB-0008-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-09-LB-0008 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-07-24 10:55 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5830 | PS4-09-LB-0008-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-09-LB-0008 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-07-24 10:58 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5833 | PS4-25-DM-3100A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-06-12 05:52 | PS4-25-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5834 | PS4-25-DM-3100A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0014 TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-06-12 05:54 | PS4-25-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5837 | PS4-25-DM-3100B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-06-12 06:02 | PS4-25-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5838 | PS4-25-DM-3100B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0014 TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-06-12 06:03 | PS4-25-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5841 | PS4-25-DM-3100C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-06-12 06:36 | PS4-25-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5842 | PS4-25-DM-3100C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0014 TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-06-09 11:47 | PS4-25-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5855 | PS4-25-ESDV-0021-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-ESDV-0021 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-06-12 06:38 | PS4-25-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5856 | PS4-25-ESDV-0023-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-ESDV-0023 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-06-12 06:39 | PS4-25-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5857 | PS4-25-FCV-0003A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-FCV-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-06-12 06:41 | PS4-25-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5858 | PS4-25-FCV-0003B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-FCV-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-06-13 07:59 | PS4-25-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5859 | PS4-25-FCV-0003C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-FCV-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-06-13 08:01 | PS4-25-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5860 | PS4-25-FCV-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-FCV-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge | 2026-06-13 08:04 | PS4-25-06 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5869 | PS4-25-MOV-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-08 15:39 | PS4-25-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5870 | PS4-25-MOV-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-06-09 12:11 | PS4-25-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5871 | PS4-25-MOV-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-08 15:48 | PS4-25-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5872 | PS4-25-MOV-0008-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-06-13 08:05 | PS4-25-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5873 | PS4-25-MOV-0011-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-MOV-0011 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-06-13 08:07 | PS4-25-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5874 | PS4-25-MOV-0012-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-MOV-0012 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-06-13 08:10 | PS4-25-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5875 | PS4-25-MOV-0025-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-MOV-0025 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-06-13 08:11 | PS4-25-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5876 | PS4-25-MOV-0026-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-MOV-0026 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-06-13 08:15 | PS4-25-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5877 | PS4-25-MOV-0027-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-MOV-0027 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge | 2026-06-13 08:17 | PS4-25-06 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5878 | PS4-25-MOV-0028-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-MOV-0028 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-06-13 08:19 | PS4-25-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5879 | PS4-25-SDV-0022-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-06-09 12:33 | PS4-25-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5880 | PS4-25-SDV-0035A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-SDV-0035A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-06-08 12:32 | PS4-25-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5881 | PS4-25-SDV-0035B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-SDV-0035B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-06-09 12:37 | PS4-25-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5882 | PS4-25-SDV-0035C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-SDV-0035C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-06-08 12:39 | PS4-25-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5883 | PS4-25-SDV-0036A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-SDV-0036A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-06-09 12:42 | PS4-25-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5884 | PS4-25-SDV-0036B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-SDV-0036B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-06-08 12:44 | PS4-25-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5885 | PS4-25-SDV-0036C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-SDV-0036C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-06-09 12:46 | PS4-25-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5886 | PS4-25-SDV-0046-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-SDV-0046 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass | 2026-06-09 12:53 | PS4-25-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5887 | PS4-25-SDV-0052-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-SDV-0052 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-06-12 06:42 | PS4-25-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5888 | PS4-25-SDV-0054A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-25-SDV-0054A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-06-08 12:48 | PS4-25-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5889 | PS4-25-SDV-0054B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-SDV-0054B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-06-08 12:51 | PS4-25-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5890 | PS4-25-SDV-0054C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-SDV-0054C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-06-09 13:48 | PS4-25-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5892 | PS4-25-XV-0053-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-XV-0053 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass | 2026-06-12 06:43 | PS4-25-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5893 | PS4-25-XV-0070-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-25-XV-0070 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass | 2026-06-12 06:43 | PS4-25-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5895 | PS4-28-BE-0002A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-28-BE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump | 2026-06-08 05:29 | PS4-28-17 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5897 | PS4-28-BE-0002B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-28-BE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump | 2026-06-08 05:32 | PS4-28-17 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5913 | PS4-28-HE-2100-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-28-HE-2100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 | 2026-06-08 05:34 | PS4-28-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone G | TM-00233 | sridhar, muthu
T-00233-5915 | PS4-28-HE-2200-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-28-HE-2200 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 | 2026-06-08 05:37 | PS4-28-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-5917 | PS4-28-LB-8200-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-28-LB-8200 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-28-11 - Open Drain Interceptor | 2026-06-08 05:39 | PS4-28-11 |  |  | LV Power Cable | E | Closed | PS4 - Milestone I | TM-00233 | sridhar, muthu
T-00233-5918 | PS4-28-SDV-0045-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-28-SDV-0045 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump | 2026-06-09 13:51 | PS4-28-17 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5919 | PS4-28-SDV-0053A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-28-SDV-0053A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A | 2026-06-09 13:56 | PS4-28-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5920 | PS4-28-SDV-0053B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-28-SDV-0053B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B | 2026-06-09 13:59 | PS4-28-14 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5921 | PS4-28-SDV-0053C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-28-SDV-0053C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C | 2026-06-09 14:03 | PS4-28-15 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-5929 | PS4-60-BE-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-60-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-27 - Compressed Air Starting Skid | 2026-06-19 11:45 | PS4-60-27 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5930 | PS4-60-BE-0001-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-60-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-27 - Compressed Air Starting Skid | 2026-06-19 11:49 | PS4-60-27 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5932 | PS4-60-BE-0001-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-27 - Compressed Air Starting Skid | 2026-06-19 11:52 | PS4-60-27 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5933 | PS4-60-BE-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-26 - Instrument Air Compressor Skid | 2026-06-19 11:56 | PS4-60-26 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5934 | PS4-60-BE-0002-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-26 - Instrument Air Compressor Skid | 2026-06-19 12:00 | PS4-60-26 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5935 | PS4-60-BE-0002-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-26 - Instrument Air Compressor Skid | 2026-06-19 12:06 | PS4-60-26 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5937 | PS4-60-BE-0002-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-26 - Instrument Air Compressor Skid | 2026-06-19 12:11 | PS4-60-26 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5938 | PS4-60-BE-0003A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-19 12:15 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5939 | PS4-60-BE-0003B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B |  | PS4-60-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00233
T-00233-5940 | PS4-60-BE-0003C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-03 13:50 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5941 | PS4-60-BE-0003D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-03 13:51 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5942 | PS4-60-BE-0003E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-5943 | PS4-60-BE-0003F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-5944 | PS4-60-BE-0003G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00233
T-00233-5945 | PS4-60-BE-0004A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0004A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-49 - Lube Oil Separator Module PS4-60-UO-81100A | 2026-06-19 12:18 | PS4-60-49 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5946 | PS4-60-BE-0004B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0004B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-50 - Lube Oil Separator Module PS4-60-UO-81100B | 2026-06-19 12:21 | PS4-60-50 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5947 | PS4-60-BE-0004C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0004C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-51 - Lube Oil Separator Module PS4-60-UO-81100C | 2026-07-03 13:53 | PS4-60-51 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5948 | PS4-60-BE-0004D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0004D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-52 - Lube Oil Separator Module PS4-60-UO-81100D |  | PS4-60-52 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-5949 | PS4-60-BE-0004E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0004E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-53 - Lube Oil Separator Module PS4-60-UO-81100E |  | PS4-60-53 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-5950 | PS4-60-BE-0004F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0004F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-54 - Lube Oil Separator Module PS4-60-UO-81100F |  | PS4-60-54 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-5951 | PS4-60-BE-0004G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0004G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-55 - Lube Oil Separator Module PS4-60-UO-81100G |  | PS4-60-55 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00233
T-00233-5952 | PS4-60-BE-0005A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0005A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-19 12:24 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5953 | PS4-60-BE-0005B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0005B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-19 12:43 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5954 | PS4-60-BE-0005C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0005C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-03 13:54 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5955 | PS4-60-BE-0005D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0005D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-19 12:47 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5956 | PS4-60-BE-0005E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0005E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-03 13:54 | PS4-60-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5957 | PS4-60-BE-0005F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0005F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-5958 | PS4-60-BE-0005G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0005G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-03 13:55 | PS4-60-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-5959 | PS4-60-BE-0011A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-08 15:56 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5960 | PS4-60-BE-0011A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-08 16:00 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5961 | PS4-60-BE-0011A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-08 16:10 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5962 | PS4-60-BE-0011A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-08 16:13 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5963 | PS4-60-BE-0011A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-08 16:16 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5964 | PS4-60-BE-0011A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-08 16:19 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5965 | PS4-60-BE-0011B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-08 16:22 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5966 | PS4-60-BE-0011B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-08 16:27 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5967 | PS4-60-BE-0011B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-08 17:04 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5968 | PS4-60-BE-0011B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-08 17:08 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5969 | PS4-60-BE-0011B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-08 17:12 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5970 | PS4-60-BE-0011B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0011B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-08 17:20 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5971 | PS4-60-BE-0012A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-08 17:24 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5972 | PS4-60-BE-0012A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-08 17:27 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5973 | PS4-60-BE-0012A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-08 17:30 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5974 | PS4-60-BE-0012A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-08 17:33 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5975 | PS4-60-BE-0012A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-08 17:36 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5976 | PS4-60-BE-0012A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-08 17:38 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5977 | PS4-60-BE-0012B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-08 17:41 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5978 | PS4-60-BE-0012B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-08 17:44 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5979 | PS4-60-BE-0012B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-08 17:47 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5980 | PS4-60-BE-0012B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-08 17:50 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5981 | PS4-60-BE-0012B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-08 18:01 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5982 | PS4-60-BE-0012B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0012B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-08 18:05 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-5983 | PS4-60-BE-0013A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-08 18:08 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5984 | PS4-60-BE-0013A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-08 18:14 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5985 | PS4-60-BE-0013A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-08 18:17 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5986 | PS4-60-BE-0013A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-08 18:19 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5987 | PS4-60-BE-0013A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-08 18:22 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5988 | PS4-60-BE-0013A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-08 18:25 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5989 | PS4-60-BE-0013B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-08 18:30 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5990 | PS4-60-BE-0013B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-08 18:33 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5991 | PS4-60-BE-0013B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-08 18:36 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5992 | PS4-60-BE-0013B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-08 18:43 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5993 | PS4-60-BE-0013B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-08 18:47 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5994 | PS4-60-BE-0013B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0013B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-08 18:49 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5995 | PS4-60-BE-0014A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-08 18:54 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5996 | PS4-60-BE-0014A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-08 10:25 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5997 | PS4-60-BE-0014A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-08 10:32 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5998 | PS4-60-BE-0014A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-08 10:35 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-5999 | PS4-60-BE-0014A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-08 10:37 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6000 | PS4-60-BE-0014A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-08 10:40 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6001 | PS4-60-BE-0014B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-08 10:43 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6002 | PS4-60-BE-0014B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-08 10:47 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6003 | PS4-60-BE-0014B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-08 10:50 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6004 | PS4-60-BE-0014B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-08 10:52 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6005 | PS4-60-BE-0014B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-18 12:55 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6006 | PS4-60-BE-0014B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0014B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-08 11:03 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6007 | PS4-60-BE-0015A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-08 11:06 | PS4-60-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6008 | PS4-60-BE-0015A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-08 11:09 | PS4-60-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6009 | PS4-60-BE-0015A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-08 11:11 | PS4-60-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6010 | PS4-60-BE-0015A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-08 11:14 | PS4-60-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6011 | PS4-60-BE-0015A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-08 11:16 | PS4-60-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6012 | PS4-60-BE-0015A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-08 11:19 | PS4-60-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6013 | PS4-60-BE-0015B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-08 11:27 | PS4-60-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6014 | PS4-60-BE-0015B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-08 11:29 | PS4-60-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6015 | PS4-60-BE-0015B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-08 11:31 | PS4-60-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6016 | PS4-60-BE-0015B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-08 11:34 | PS4-60-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6017 | PS4-60-BE-0015B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-08 11:37 | PS4-60-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6018 | PS4-60-BE-0015B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-08 11:40 | PS4-60-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6019 | PS4-60-BE-0016A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-08 11:42 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6020 | PS4-60-BE-0016A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-08 11:45 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6021 | PS4-60-BE-0016A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-08 11:47 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6022 | PS4-60-BE-0016A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-08 11:50 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6023 | PS4-60-BE-0016A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-08 11:52 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6024 | PS4-60-BE-0016A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-08 11:55 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6025 | PS4-60-BE-0016B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-08 11:57 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6026 | PS4-60-BE-0016B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-08 12:01 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6027 | PS4-60-BE-0016B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-08 12:03 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6028 | PS4-60-BE-0016B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-08 12:05 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6029 | PS4-60-BE-0016B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-08 12:11 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6030 | PS4-60-BE-0016B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0016B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-08 12:14 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6031 | PS4-60-BE-0017A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-08 12:16 | PS4-60-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6032 | PS4-60-BE-0017A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-08 12:19 | PS4-60-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6033 | PS4-60-BE-0017A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-24 11:11 | PS4-60-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6034 | PS4-60-BE-0017A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-24 11:15 | PS4-60-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6035 | PS4-60-BE-0017A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-24 11:16 | PS4-60-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6036 | PS4-60-BE-0017A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-24 11:19 | PS4-60-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6037 | PS4-60-BE-0017B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-24 11:24 | PS4-60-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6038 | PS4-60-BE-0017B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-24 11:28 | PS4-60-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6039 | PS4-60-BE-0017B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-24 11:31 | PS4-60-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6040 | PS4-60-BE-0017B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-24 11:33 | PS4-60-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6041 | PS4-60-BE-0017B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-24 11:38 | PS4-60-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6042 | PS4-60-BE-0017B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0017B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-24 11:40 | PS4-60-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6043 | PS4-60-BE-0021A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-60-BE-0021B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-19 12:57 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6044 | PS4-60-BE-0021B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-60-BE-0021B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-19 13:00 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6045 | PS4-60-BE-0024A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0024A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-35 - Injector Tip Cooling Module A | 2026-06-19 13:03 | PS4-60-35 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6046 | PS4-60-BE-0024A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0024A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-35 - Injector Tip Cooling Module A | 2026-06-19 13:06 | PS4-60-35 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6047 | PS4-60-BE-0024B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0024B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-36 - Injector Tip Cooling Module B | 2026-06-19 13:09 | PS4-60-36 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6048 | PS4-60-BE-0024B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0024B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-36 - Injector Tip Cooling Module B | 2026-06-19 13:12 | PS4-60-36 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6049 | PS4-60-BE-0024C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0024C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-37 - Injector Tip Cooling Module C | 2026-07-03 13:56 | PS4-60-37 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6050 | PS4-60-BE-0024C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0024C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-37 - Injector Tip Cooling Module C | 2026-07-03 13:57 | PS4-60-37 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6051 | PS4-60-BE-0024D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0024D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-38 - Injector Tip Cooling Module D | 2026-07-03 13:58 | PS4-60-38 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6052 | PS4-60-BE-0024D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0024D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-38 - Injector Tip Cooling Module D | 2026-07-03 13:58 | PS4-60-38 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6053 | PS4-60-BE-0024E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0024E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-39 - Injector Tip Cooling Module E | 2026-07-03 13:59 | PS4-60-39 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6054 | PS4-60-BE-0024E-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0024E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-39 - Injector Tip Cooling Module E | 2026-07-03 14:05 | PS4-60-39 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6055 | PS4-60-BE-0024F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0024F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-40 - Injector Tip Cooling Module F | 2026-07-03 14:06 | PS4-60-40 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6056 | PS4-60-BE-0024F-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0024F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-40 - Injector Tip Cooling Module F | 2026-07-03 14:07 | PS4-60-40 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6057 | PS4-60-BE-0024G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0024G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-41 - Injector Tip Cooling Module G | 2026-07-03 14:08 | PS4-60-41 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6058 | PS4-60-BE-0024G-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0024G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-41 - Injector Tip Cooling Module G | 2026-07-03 14:09 | PS4-60-41 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6059 | PS4-60-BE-0025A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0025A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-35 - Injector Tip Cooling Module A | 2026-06-19 13:15 | PS4-60-35 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6060 | PS4-60-BE-0025B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0025B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-36 - Injector Tip Cooling Module B | 2026-06-19 13:17 | PS4-60-36 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6061 | PS4-60-BE-0025C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0025C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-37 - Injector Tip Cooling Module C | 2026-07-03 14:10 | PS4-60-37 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6062 | PS4-60-BE-0025D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0025D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-38 - Injector Tip Cooling Module D | 2026-07-03 14:10 | PS4-60-38 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6063 | PS4-60-BE-0025E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0025E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-39 - Injector Tip Cooling Module E | 2026-07-03 14:11 | PS4-60-39 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6064 | PS4-60-BE-0025F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0025F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-40 - Injector Tip Cooling Module F | 2026-07-03 14:12 | PS4-60-40 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6065 | PS4-60-BE-0025G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0025G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-41 - Injector Tip Cooling Module G | 2026-07-03 14:14 | PS4-60-41 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6066 | PS4-60-BE-0026A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0026A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-06-19 13:20 | PS4-60-70 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6067 | PS4-60-BE-0026A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BE-0026A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-06-19 13:23 | PS4-60-70 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6068 | PS4-60-BE-0026B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0026B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-06-19 13:26 | PS4-60-71 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6069 | PS4-60-BE-0026B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BE-0026B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-06-19 13:28 | PS4-60-71 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6070 | PS4-60-BE-0026C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0026C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system | 2026-07-03 14:14 | PS4-60-72 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6071 | PS4-60-BE-0026C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BE-0026C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system | 2026-07-03 14:15 | PS4-60-72 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6072 | PS4-60-BE-0026D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0026D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system | 2026-07-03 14:16 | PS4-60-73 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6073 | PS4-60-BE-0026D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BE-0026D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system | 2026-07-03 14:17 | PS4-60-73 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6074 | PS4-60-BE-0026E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0026E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system | 2026-07-03 14:23 | PS4-60-74 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6075 | PS4-60-BE-0026E-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BE-0026E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-6076 | PS4-60-BE-0026F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0026F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system | 2026-07-03 10:32 | PS4-60-75 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6077 | PS4-60-BE-0026F-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BE-0026F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system | 2026-07-03 10:35 | PS4-60-75 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6078 | PS4-60-BE-0026G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0026G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system | 2026-07-03 10:38 | PS4-60-76 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6079 | PS4-60-BE-0026G-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BE-0026G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system | 2026-07-03 10:41 | PS4-60-76 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6080 | PS4-60-BI-0005A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BI-0005A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-20 04:59 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6081 | PS4-60-BI-0005B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BI-0005B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-20 05:03 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6082 | PS4-60-BI-0005C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BI-0005C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-03 10:47 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6083 | PS4-60-BI-0005D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BI-0005D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-20 05:09 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6084 | PS4-60-BI-0005E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BI-0005E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-03 10:53 | PS4-60-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6085 | PS4-60-BI-0005F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BI-0005F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-20 05:14 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6086 | PS4-60-BI-0005G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BI-0005G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-03 10:57 | PS4-60-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6087 | PS4-60-BI-0015A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BI-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-20 07:22 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6088 | PS4-60-BI-0015A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BI-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-20 07:28 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6089 | PS4-60-BI-0015A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-BI-0015A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-20 07:32 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6090 | PS4-60-BI-0015B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BI-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-20 07:37 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6091 | PS4-60-BI-0015B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BI-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-20 07:40 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6092 | PS4-60-BI-0015B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-BI-0015B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-08 12:21 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6093 | PS4-60-BI-0015C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BI-0015C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-03 11:32 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6094 | PS4-60-BI-0015C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BI-0015C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-03 11:36 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6095 | PS4-60-BI-0015C-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-BI-0015C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-03 11:44 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6096 | PS4-60-BI-0015D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BI-0015D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-20 07:43 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6097 | PS4-60-BI-0015D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BI-0015D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-6098 | PS4-60-BI-0015D-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-BI-0015D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-20 07:48 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6099 | PS4-60-BI-0015E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BI-0015E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-03 11:48 | PS4-60-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6100 | PS4-60-BI-0015E-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BI-0015E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-03 11:54 | PS4-60-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6101 | PS4-60-BI-0015E-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-BI-0015E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-03 11:58 | PS4-60-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6102 | PS4-60-BI-0015F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BI-0015F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-20 07:52 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6103 | PS4-60-BI-0015F-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BI-0015F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-20 07:59 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6104 | PS4-60-BI-0015F-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-BI-0015F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-20 08:03 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6105 | PS4-60-BI-0015G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BI-0015G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-03 12:02 | PS4-60-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6106 | PS4-60-BI-0015G-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BI-0015G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-03 12:05 | PS4-60-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6107 | PS4-60-BI-0015G-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-BI-0015G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-03 12:08 | PS4-60-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6117 | PS4-60-IE-0002A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-20 10:34 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6118 | PS4-60-IE-0002A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-20 10:52 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6119 | PS4-60-IE-0002A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015A TO PS4-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-28 11:53 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6120 | PS4-60-IE-0002B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-20 11:14 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6121 | PS4-60-IE-0002B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-08 12:27 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6122 | PS4-60-IE-0002B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015B TO PS4-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-20 11:17 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6123 | PS4-60-IE-0002C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-03 14:35 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6124 | PS4-60-IE-0002C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-03 14:41 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6125 | PS4-60-IE-0002C-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015C TO PS4-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-6126 | PS4-60-IE-0002D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-20 11:27 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6127 | PS4-60-IE-0002D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-20 11:29 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6128 | PS4-60-IE-0002D-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015D TO PS4-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-20 11:32 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6129 | PS4-60-IE-0002E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-04 04:59 | PS4-60-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6130 | PS4-60-IE-0002E-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-04 05:04 | PS4-60-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6131 | PS4-60-IE-0002E-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015E TO PS4-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-6132 | PS4-60-IE-0002F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-20 11:45 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6133 | PS4-60-IE-0002F-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-20 11:48 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6134 | PS4-60-IE-0002F-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015F TO PS4-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-20 11:51 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6135 | PS4-60-IE-0002G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-04 05:22 | PS4-60-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6136 | PS4-60-IE-0002G-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-04 05:30 | PS4-60-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6137 | PS4-60-IE-0002G-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015G TO PS4-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00233
T-00233-6138 | PS4-60-IE-0003A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-20 12:07 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6139 | PS4-60-IE-0003A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-20 12:11 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6140 | PS4-60-IE-0003B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-20 12:21 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6141 | PS4-60-IE-0003B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-20 12:24 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6142 | PS4-60-IE-0003C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-6143 | PS4-60-IE-0003C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-6144 | PS4-60-IE-0003D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-6145 | PS4-60-IE-0003D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-6146 | PS4-60-IE-0003E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-6147 | PS4-60-IE-0003E-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-6148 | PS4-60-IE-0003F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-07-24 07:30 | PS4-60-17 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6149 | PS4-60-IE-0003F-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-6150 | PS4-60-IE-0003G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-07-24 07:33 | PS4-60-20 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6151 | PS4-60-IE-0003G-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-07-24 07:36 | PS4-60-20 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6152 | PS4-60-IE-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-07 06:56 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6153 | PS4-60-IE-0004-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-06 10:33 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6155 | PS4-60-IH-0001A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-07 13:01 | PS4-60-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6156 | PS4-60-IH-0001A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-07 13:02 | PS4-60-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6157 | PS4-60-IH-0001A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-07 13:03 | PS4-60-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6158 | PS4-60-IH-0001A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-07 13:03 | PS4-60-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6159 | PS4-60-IH-0001A-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-07 07:30 | PS4-60-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6160 | PS4-60-IH-0001A-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-06-07 07:37 | PS4-60-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6162 | PS4-60-IH-0001B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-07 13:05 | PS4-60-06 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6163 | PS4-60-IH-0001B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-07 13:06 | PS4-60-06 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6164 | PS4-60-IH-0001B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-07 13:07 | PS4-60-06 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6165 | PS4-60-IH-0001B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-07 13:08 | PS4-60-06 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6166 | PS4-60-IH-0001B-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-07 07:43 | PS4-60-06 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6167 | PS4-60-IH-0001B-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-06-07 07:49 | PS4-60-06 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6169 | PS4-60-IH-0001C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | 2026-06-08 05:51 | PS4-60-09 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6170 | PS4-60-IH-0001C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | 2026-06-08 05:54 | PS4-60-09 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6171 | PS4-60-IH-0001C-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | 2026-06-08 06:08 | PS4-60-09 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6172 | PS4-60-IH-0001C-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | 2026-06-08 07:27 | PS4-60-09 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6173 | PS4-60-IH-0001C-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | 2026-06-13 08:20 | PS4-60-09 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6174 | PS4-60-IH-0001C-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | 2026-06-13 08:22 | PS4-60-09 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6176 | PS4-60-IH-0001D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | 2026-06-08 07:36 | PS4-60-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6177 | PS4-60-IH-0001D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | 2026-06-08 08:08 | PS4-60-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6178 | PS4-60-IH-0001D-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | 2026-06-08 08:14 | PS4-60-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6179 | PS4-60-IH-0001D-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | 2026-06-08 08:21 | PS4-60-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6180 | PS4-60-IH-0001D-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | 2026-06-11 13:18 | PS4-60-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6181 | PS4-60-IH-0001D-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | 2026-06-11 13:21 | PS4-60-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6183 | PS4-60-IH-0001E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | 2026-06-07 13:09 | PS4-60-15 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6184 | PS4-60-IH-0001E-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | 2026-06-07 13:10 | PS4-60-15 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6185 | PS4-60-IH-0001E-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | 2026-06-07 13:10 | PS4-60-15 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6186 | PS4-60-IH-0001E-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | 2026-06-07 13:11 | PS4-60-15 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6187 | PS4-60-IH-0001E-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | 2026-06-11 13:22 | PS4-60-15 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6188 | PS4-60-IH-0001E-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | 2026-06-11 13:27 | PS4-60-15 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6190 | PS4-60-IH-0001F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | 2026-06-13 08:23 | PS4-60-18 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6191 | PS4-60-IH-0001F-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | 2026-06-13 08:24 | PS4-60-18 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6192 | PS4-60-IH-0001F-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | 2026-06-07 13:12 | PS4-60-18 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6193 | PS4-60-IH-0001F-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | 2026-06-07 13:13 | PS4-60-18 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6194 | PS4-60-IH-0001F-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | 2026-06-11 13:28 | PS4-60-18 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6195 | PS4-60-IH-0001F-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | 2026-06-11 13:49 | PS4-60-18 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6197 | PS4-60-IH-0001G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | 2026-06-07 13:14 | PS4-60-21 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6198 | PS4-60-IH-0001G-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | 2026-06-07 11:42 | PS4-60-21 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6199 | PS4-60-IH-0001G-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | 2026-06-07 11:45 | PS4-60-21 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6200 | PS4-60-IH-0001G-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | 2026-06-07 11:49 | PS4-60-21 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6201 | PS4-60-IH-0001G-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | 2026-06-11 13:51 | PS4-60-21 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6202 | PS4-60-IH-0001G-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | 2026-06-11 14:18 | PS4-60-21 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6205 | PS4-60-IH-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-07 07:54 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6206 | PS4-60-IH-0002-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-06 10:40 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6207 | PS4-60-IH-0002-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-11 14:22 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6208 | PS4-60-IH-0002-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-13 08:25 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6209 | PS4-60-IH-0002-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-11 14:23 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6210 | PS4-60-IH-0002-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-11 14:26 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6211 | PS4-60-IH-0002-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-11 14:27 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6212 | PS4-60-IH-0002-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-11 14:29 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6213 | PS4-60-IH-0002-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-11 14:30 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6214 | PS4-60-IH-0002-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-11 14:32 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6215 | PS4-60-IN-0001A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-49 - Lube Oil Separator Module PS4-60-UO-81100A | 2026-06-20 14:41 | PS4-60-49 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6216 | PS4-60-IN-0001B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-50 - Lube Oil Separator Module PS4-60-UO-81100B | 2026-06-20 14:44 | PS4-60-50 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6217 | PS4-60-IN-0001C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-51 - Lube Oil Separator Module PS4-60-UO-81100C | 2026-07-04 07:06 | PS4-60-51 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6218 | PS4-60-IN-0001D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-52 - Lube Oil Separator Module PS4-60-UO-81100D | 2026-07-04 07:09 | PS4-60-52 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6219 | PS4-60-IN-0001E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-IN-0001E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-53 - Lube Oil Separator Module PS4-60-UO-81100E | 2026-07-04 07:13 | PS4-60-53 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6220 | PS4-60-IN-0001F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-IN-0001F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-54 - Lube Oil Separator Module PS4-60-UO-81100F | 2026-07-04 07:22 | PS4-60-54 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6221 | PS4-60-IN-0001G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-IN-0001G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-55 - Lube Oil Separator Module PS4-60-UO-81100G | 2026-07-04 07:28 | PS4-60-55 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6222 | PS4-60-IN-0002A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-07-24 07:42 | PS4-60-57 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6223 | PS4-60-IN-0002A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-06-20 14:47 | PS4-60-57 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6224 | PS4-60-IN-0002A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-06-20 14:49 | PS4-60-57 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6225 | PS4-60-IN-0002B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-07-24 07:47 | PS4-60-59 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6226 | PS4-60-IN-0002B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-06-20 14:52 | PS4-60-59 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6227 | PS4-60-IN-0002B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-06-21 04:51 | PS4-60-59 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6228 | PS4-60-IN-0002C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-6229 | PS4-60-IN-0002C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-6230 | PS4-60-IN-0002C-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-6231 | PS4-60-IN-0002D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-6232 | PS4-60-IN-0002D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-6233 | PS4-60-IN-0002D-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-6234 | PS4-60-IN-0002E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) |  | PS4-60-65 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-6235 | PS4-60-IN-0002E-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) | 2026-07-04 07:32 | PS4-60-65 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6236 | PS4-60-IN-0002E-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) | 2026-07-04 07:35 | PS4-60-65 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6237 | PS4-60-IN-0002F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) |  | PS4-60-67 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-6238 | PS4-60-IN-0002F-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) | 2026-07-04 07:40 | PS4-60-67 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6239 | PS4-60-IN-0002F-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) | 2026-07-04 07:43 | PS4-60-67 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6240 | PS4-60-IN-0002G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) |  | PS4-60-69 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00233
T-00233-6241 | PS4-60-IN-0002G-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) | 2026-07-04 07:47 | PS4-60-69 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6242 | PS4-60-IN-0002G-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) | 2026-07-04 08:08 | PS4-60-69 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6243 | PS4-60-IWK-0001A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IWK-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-06 11:20 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6244 | PS4-60-IWK-0001A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IWK-0001A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-06 11:27 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6245 | PS4-60-IWK-0001B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-IWK-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-06 11:33 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6246 | PS4-60-IWK-0001B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-IWK-0001B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-06 11:35 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6247 | PS4-60-LA-0002A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-12 06:45 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6248 | PS4-60-LA-0002A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-12 06:45 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6249 | PS4-60-LA-0002B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-12 06:46 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6250 | PS4-60-LA-0002B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-12 06:47 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6251 | PS4-60-LA-0002C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-12 06:48 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6252 | PS4-60-LA-0002C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-12 06:49 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6253 | PS4-60-LA-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-12 06:50 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6254 | PS4-60-LA-0003-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-12 06:51 | PS4-60-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6255 | PS4-60-MOV-0005-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-60-MOV-0005 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-06-12 06:52 | PS4-71-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6256 | PS4-60-MOV-0006-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-60-MOV-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-08 12:43 | PS4-71-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6257 | PS4-60-MOV-0011-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-60-MOV-0011 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-24 07:54 | PS4-71-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6258 | PS4-60-MOV-0012-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-60-MOV-0012 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-06-13 08:26 | PS4-71-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6259 | PS4-60-SEA-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-06-21 04:54 | PS4-03-14 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6260 | PS4-60-SEA-0001-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-06-21 04:59 | PS4-03-14 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6261 | PS4-60-VS-9100A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-60-VS-9100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-42 - Oil Mist Separator Skid PS4-60-VS-9100A | 2026-07-08 12:46 | PS4-60-42 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6262 | PS4-60-VS-9100B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-60-VS-9100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-43 - Oil Mist Separator Skid PS4-60-VS-9100B | 2026-07-08 12:48 | PS4-60-43 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6263 | PS4-60-VS-9100C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-60-VS-9100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-44 - Oil Mist Separator Skid PS4-60-VS-9100C | 2026-07-04 08:12 | PS4-60-44 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6264 | PS4-60-VS-9100D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-60-VS-9100D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-45 - Oil Mist Separator Skid PS4-60-VS-9100D | 2026-07-04 08:16 | PS4-60-45 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6265 | PS4-60-VS-9100E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-60-VS-9100E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-46 - Oil Mist Separator Skid PS4-60-VS-9100E | 2026-07-04 08:24 | PS4-60-46 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6266 | PS4-60-VS-9100F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-60-VS-9100F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-47 - Oil Mist Separator Skid PS4-60-VS-9100F | 2026-07-04 08:27 | PS4-60-47 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6267 | PS4-60-VS-9100G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-60-VS-9100G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-48 - Oil Mist Separator Skid PS4-60-VS-9100G | 2026-07-04 08:33 | PS4-60-48 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6268 | PS4-61-BI-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001A TO PS4-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-06 11:39 | PS4-60-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6269 | PS4-61-BI-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001B TO PS4-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-06 12:41 | PS4-60-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6270 | PS4-61-BI-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001C TO PS4-61-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-06-12 06:53 | PS4-60-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6271 | PS4-61-BI-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001D TO PS4-61-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-12 06:55 | PS4-60-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6272 | PS4-61-BI-0005-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001E TO PS4-61-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-06-12 06:57 | PS4-60-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6273 | PS4-61-BI-0006-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001F TO PS4-61-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-12 07:06 | PS4-60-16 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6274 | PS4-61-BI-0007-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0001G TO PS4-61-BI-0007 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-06-12 05:48 | PS4-60-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6280 | PS4-61-IG-0010-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IG-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-62-10 - CRO Generator Electrical Building Normal L&SP DB - PS4-61-IG-0010 | 2026-06-06 11:52 | PS4-62-10 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6285 | PS4-61-IG-0030-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IG-0030 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 | 2026-06-12 07:18 | PS4-62-11 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6292 | PS4-61-IH-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-07 11:59 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6293 | PS4-61-IH-0004-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-07 12:32 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6294 | PS4-61-IH-0004-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-07 12:36 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6295 | PS4-61-IH-0004-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-06 12:52 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6296 | PS4-61-IH-0004-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-06 12:57 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6297 | PS4-61-IH-0004-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-06 13:00 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6298 | PS4-61-IH-0004-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-07 12:41 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6299 | PS4-61-IH-0004-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-06 13:45 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6300 | PS4-61-IH-0004-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-06 13:47 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6301 | PS4-61-IH-0004-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-06 13:51 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6302 | PS4-61-IH-0004-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-07 12:46 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6303 | PS4-61-IH-0004-CL12 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-06 13:55 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6304 | PS4-61-IH-0004-CL13 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-06 13:58 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6305 | PS4-61-IH-0004-CL14 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-06 14:01 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6306 | PS4-61-IH-0004-CL15 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-06 14:08 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6307 | PS4-61-IH-0004-CL16 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-06 14:12 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6308 | PS4-61-IH-0004-CL17 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-06 14:15 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6309 | PS4-61-IH-0004-CL18 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-06 14:18 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6310 | PS4-61-IH-0004-CL19 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-06 14:22 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6311 | PS4-61-IH-0004-CL20 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-06 14:24 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6312 | PS4-61-IH-0004-CL21 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-06 14:29 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6313 | PS4-61-IH-0004-CL22 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building | 2026-06-06 14:32 | PS4-09-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6373 | PS4-61-IK-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-07-24 08:09 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6374 | PS4-61-IK-0003-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-07-24 08:17 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6375 | PS4-61-IK-0003-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00233
T-00233-6376 | PS4-61-IK-0003-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0010 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-12 07:19 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6377 | PS4-61-IK-0003-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0010 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-12 07:20 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6378 | PS4-61-IK-0003-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0010 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-12 07:21 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6379 | PS4-61-IK-0003-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-04 11:52 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6380 | PS4-61-IK-0003-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-04 11:52 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6381 | PS4-61-IK-0003-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-04 11:51 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6382 | PS4-61-IK-0003-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-04 11:50 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6383 | PS4-61-IK-0003-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-04 12:07 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6384 | PS4-61-IK-0003-CL12 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-04 12:10 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6385 | PS4-61-IK-0003-CL13 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-04 12:13 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6386 | PS4-61-IK-0003-CL14 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-04 12:16 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6387 | PS4-61-IK-0003-CL15 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-04 12:19 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6388 | PS4-61-IK-0003-CL16 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-04 12:24 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6389 | PS4-61-IK-0003-CL17 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-04 12:28 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6390 | PS4-61-IK-0003-CL18 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-04 12:30 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6391 | PS4-61-IK-0003-CL19 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-04 12:33 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6392 | PS4-61-IK-0003-CL20 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-04 12:36 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6393 | PS4-61-IK-0003-CL21 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-04 12:38 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6394 | PS4-61-IK-0003-CL22 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-04 12:41 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6395 | PS4-61-IK-0003-CL23 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-04 12:44 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6396 | PS4-61-IK-0003-CL24 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-04 12:46 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6397 | PS4-61-IK-0003-CL25 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-05 08:12 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | tereshchenko, nikolai
T-00233-6398 | PS4-61-IK-0003-CL26 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-05 11:29 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6399 | PS4-61-IK-0003-CL27 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-05 11:30 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6400 | PS4-61-IK-0003-CL28 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-05 11:30 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6401 | PS4-61-IK-0003-CL29 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-05 11:31 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6402 | PS4-61-IK-0003-CL30 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-05 11:31 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6403 | PS4-61-IK-0003-CL31 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-05 11:32 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6404 | PS4-61-IK-0003-CL32 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-05 11:32 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6405 | PS4-61-IK-0003-CL33 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-05 11:32 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6406 | PS4-61-IK-0003-CL34 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-05 11:33 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6407 | PS4-61-IK-0003-CL35 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-05 11:33 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6408 | PS4-61-IK-0003-CL36 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-05 11:33 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6409 | PS4-61-IK-0003-CL37 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-05 11:34 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6410 | PS4-61-IK-0003-CL38 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-05 11:34 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6411 | PS4-61-IK-0003-CL39 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-05 11:35 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6412 | PS4-61-IK-0003-CL40 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-05 11:36 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6413 | PS4-61-IK-0003-CL41 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-05 11:36 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6414 | PS4-61-IK-0003-CL42 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-05 11:37 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6415 | PS4-61-IK-0003-CL43 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-06-07 12:55 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-6416 | PS4-61-IK-0003-CL44 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-06-08 08:25 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-6417 | PS4-61-IK-0003-CL45 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-06-08 08:29 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-6418 | PS4-61-IK-0003-CL46 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-06-08 08:32 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-6419 | PS4-61-IK-0003-CL48 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-06-08 10:17 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-6420 | PS4-61-IK-0003-CL49 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-06-08 10:14 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-6421 | PS4-61-IK-0003-CL50 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-06-08 09:42 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-6422 | PS4-61-IK-0003-CL51 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-06-08 09:45 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-6423 | PS4-61-IK-0003-CL52 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-06-08 09:47 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-6424 | PS4-61-IK-0003-CL53 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-06-08 09:50 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-6425 | PS4-61-IK-0003-CL54 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-06-08 09:53 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-6426 | PS4-61-IK-0003-CL55 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-06-08 09:56 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-6427 | PS4-61-IK-0003-CL56 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-06-08 09:58 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-6428 | PS4-61-IK-0003-CL57 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-06-08 10:01 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-6429 | PS4-61-IK-0003-CL58 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-06-08 10:03 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-6430 | PS4-61-IK-0003-CL59 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-06-08 10:06 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-6431 | PS4-61-IK-0003-CL60 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-06-08 10:08 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-6432 | PS4-61-IK-0003-CL61 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-BE-0001 TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-06-08 10:11 | PS4-05-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-6433 | PS4-61-IK-0003-CL62 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-07 08:03 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6434 | PS4-61-IK-0003-CL63 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone B | TM-00233
T-00233-6439 | PS4-61-IK-0006-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 11:55 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6440 | PS4-61-IK-0006-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 11:55 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6441 | PS4-61-IK-0006-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 11:56 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6442 | PS4-61-IK-0006-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 11:56 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6443 | PS4-61-IK-0006-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 11:58 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6444 | PS4-61-IK-0006-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 12:00 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6445 | PS4-61-IK-0006-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 12:00 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6446 | PS4-61-IK-0006-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 12:01 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6447 | PS4-61-IK-0006-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 12:01 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6448 | PS4-61-IK-0006-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 12:02 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6449 | PS4-61-IK-0006-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 12:03 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6450 | PS4-61-IK-0006-CL12 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 12:03 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6451 | PS4-61-IK-0006-CL13 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 12:04 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6452 | PS4-61-IK-0006-CL14 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 12:04 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6453 | PS4-61-IK-0006-CL15 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 12:52 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6454 | PS4-61-IK-0006-CL16 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 12:57 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6455 | PS4-61-IK-0006-CL17 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 13:01 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6456 | PS4-61-IK-0006-CL18 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 13:04 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6457 | PS4-61-IK-0006-CL19 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 13:09 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6458 | PS4-61-IK-0006-CL20 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 13:11 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6459 | PS4-61-IK-0006-CL21 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 13:14 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6460 | PS4-61-IK-0006-CL22 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 13:17 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6461 | PS4-61-IK-0006-CL23 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 13:20 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6462 | PS4-61-IK-0006-CL24 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 13:22 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6463 | PS4-61-IK-0006-CL25 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 13:25 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6464 | PS4-61-IK-0006-CL26 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 13:28 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6465 | PS4-61-IK-0006-CL27 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 13:33 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6466 | PS4-61-IK-0006-CL28 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-04 13:36 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6467 | PS4-61-IK-0006-CL29 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-07-24 08:20 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6468 | PS4-61-IK-0006-CL30 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-07-24 08:22 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6469 | PS4-61-IK-0006-CL31 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0010 TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-06 09:38 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6470 | PS4-61-IK-0006-CL32 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0010 TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-06 09:42 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6471 | PS4-61-IK-0006-CL33 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-6472 | PS4-61-IK-0006-CL34 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-6476 | PS4-61-IU-3100A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-61-IU-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-06-12 07:21 | PS4-25-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6477 | PS4-61-IU-3100B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-61-IU-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-06-12 07:24 | PS4-25-03 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6478 | PS4-61-IU-3100C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-61-IU-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-06-12 07:25 | PS4-25-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6481 | PS4-61-IV-0002A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0010 TO PS4-61-IV-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-11 13:07 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6482 | PS4-61-IV-0002B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0010 TO PS4-61-IV-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-06-11 13:09 | PS4-61-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6486 | PS4-61-IV-0007A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0010 TO PS4-61-IV-0007A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-07-18 13:00 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6487 | PS4-61-IV-0007B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0010 TO PS4-61-IV-0007B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-06-11 13:16 | PS4-61-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-6489 | PS4-62-IE-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0004 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-6490 | PS4-62-IE-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-6504 | PS4-71-FCV-0018-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-71-FCV-0018 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B | 2026-06-12 07:27 | PS4-71-13 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6505 | PS4-71-FCV-0019-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-71-FCV-0019 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B | 2026-06-12 07:27 | PS4-71-21 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6506 | PS4-71-FCV-0020-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-71-FCV-0020 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B | 2026-06-12 07:28 | PS4-71-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6510 | PS4-71-HE-2200-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-71-HE-2200 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-06-13 08:27 | PS4-71-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6512 | PS4-71-HE-2300-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-71-HE-2300 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-07-08 13:24 | PS4-71-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6521 | PS4-71-IN-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone F | TM-00233
T-00233-6522 | PS4-71-IN-0001-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) | 2026-06-13 08:28 | PS4-71-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone F | TM-00233 | sridhar, muthu
T-00233-6523 | PS4-71-IN-0001-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) | 2026-06-13 08:29 | PS4-71-19 |  |  | LV Power Cable | E | Closed | PS4 - Milestone F | TM-00233 | sridhar, muthu
T-00233-6524 | PS4-71-IN-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-09 - CFO Pre-Pressure Module (UCP) | 2026-06-13 08:30 | PS4-71-09 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6525 | PS4-71-IN-0002-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-09 - CFO Pre-Pressure Module (UCP) | 2026-06-13 08:31 | PS4-71-09 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6526 | PS4-71-IN-0002-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-09 - CFO Pre-Pressure Module (UCP) | 2026-06-13 08:32 | PS4-71-09 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6527 | PS4-71-IN-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-07-08 13:27 | PS4-71-23 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6528 | PS4-71-IN-0003-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-06-07 08:10 | PS4-71-23 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6529 | PS4-71-IN-0003-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-06-13 08:33 | PS4-71-23 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6530 | PS4-71-IN-0004A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-06-13 08:40 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6531 | PS4-71-IN-0004A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-06-13 08:40 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6532 | PS4-71-IN-0004A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-06-13 08:41 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6533 | PS4-71-IN-0004B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-06-13 08:42 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6534 | PS4-71-IN-0004B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-06-13 08:43 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6535 | PS4-71-IN-0004B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IH-0002 TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-06-13 08:44 | PS4-71-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6536 | PS4-71-LCV-4101-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-71-LCV-4101 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-06-13 08:45 | PS4-71-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6537 | PS4-71-MOV-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-06-13 08:46 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6538 | PS4-71-MOV-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-06-13 08:47 | PS4-71-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6539 | PS4-71-MOV-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-06-13 08:48 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6540 | PS4-71-MOV-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-MOV-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-06-13 08:49 | PS4-71-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6541 | PS4-71-MOV-0007-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-MOV-0007 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-06-13 08:50 | PS4-71-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6542 | PS4-71-MOV-0008-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-06-13 08:52 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6543 | PS4-71-MOV-0009-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-MOV-0009 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-06-13 08:56 | PS4-71-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6544 | PS4-71-MOV-0010-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-MOV-0010 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-06-13 08:58 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6545 | PS4-71-SDV-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank | 2026-06-06 09:52 | PS4-71-20 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6546 | PS4-71-SDV-0022-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-71-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-06-13 08:59 | PS4-71-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6547 | PS4-71-SDV-0029-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-71-SDV-0029 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank | 2026-06-13 09:00 | PS4-71-15 |  |  | LV Power Cable | E | Closed | PS4 - Milestone F | TM-00233 | sridhar, muthu
T-00233-6548 | PS4-71-SDV-0039-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-71-SDV-0039 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-06-13 09:01 | PS4-71-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6549 | PS4-71-UZ-6200-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0014 TO PS4-71-UZ-6200 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-14 - Diesel Fuel Transfer and Dispensing Station | 2026-06-13 09:02 | PS4-71-14 |  |  | LV Power Cable | E | Closed | PS4 - Milestone F | TM-00233 | sridhar, muthu
T-00233-6550 | PS4-71-XV-0089-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0041 TO PS4-71-XV-0089 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-06-13 09:04 | PS4-71-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6551 | PS4-71-XV-0090-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-XV-0090 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-06-13 10:21 | PS4-71-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6552 | PS4-71-XV-0091-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module | 2026-06-13 10:22 | PS4-71-18 |  |  | LV Power Cable | E | Closed | PS4 - Milestone F | TM-00233 | sridhar, muthu
T-00233-6553 | PS4-71-XV-0092-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank | 2026-06-06 09:56 | PS4-71-20 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-6555 | PS4-74-LB-5101-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004A TO PS4-74-LB-5101 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-74-02 - N2 Generation Skid (UCP) | 2026-06-13 10:24 | PS4-74-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone F | TM-00233 | sridhar, muthu
T-00233-6556 | PS4-74-LB-5101-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0004B TO PS4-74-LB-5101 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-74-02 - N2 Generation Skid (UCP) | 2026-06-13 10:25 | PS4-74-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone F | TM-00233 | sridhar, muthu
T-00233-6563 | PS4-75-MOV-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0042 TO PS4-75-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-28-07 - Open Drains (OD2) | 2026-06-13 06:44 | PS4-28-07 |  |  | LV Power Cable | E | Closed | PS4 - Milestone G | TM-00233 | sridhar, muthu
T-00233-6564 | PS4-75-UI-6200-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0001A TO PS4-75-UI-6200 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-75-01 - DRA Injection Package |  | PS4-75-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-6565 | PS4-75-UI-6200-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-IG-0001B TO PS4-75-UI-6200 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-75-01 - DRA Injection Package |  | PS4-75-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone G | TM-00233
T-00233-6566 | PS4-78-JC-9100A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-78-JC-9100A | EACOP | CPP AGI |  |  | 4 |  | 4 | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-78-01 - Lifting and handling equipment |  | PS4-78-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00233
T-00233-6567 | PS4-78-JC-9100B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-78-JC-9100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-78-01 - Lifting and handling equipment | 2026-07-04 10:33 | PS4-78-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6568 | PS4-78-JC-9100C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-78-JC-9100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-78-01 - Lifting and handling equipment | 2026-07-04 10:39 | PS4-78-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6569 | PS4-78-JC-9100D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-78-JC-9100D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-78-01 - Lifting and handling equipment | 2026-07-24 08:29 | PS4-78-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-6583 | PS4-87-IRF-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-87-IRF-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-53-01 - Utility Water / Storage Tank | 2026-06-13 07:39 | PS4-53-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone C | TM-00233 | sridhar, muthu
T-00233-6584 | PS4-87-IRF-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-87-IRF-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-06-13 07:37 | PS4-71-04 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6585 | PS4-87-IRF-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0005 TO PS4-87-IRF-0003 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-06-13 07:31 | PS4-71-12 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-6586 | PS4-87-IRF-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IG-0007 TO PS4-87-IRF-0004 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank | 2026-06-13 07:36 | PS4-71-15 |  |  | LV Power Cable | E | Closed | PS4 - Milestone F | TM-00233 | sridhar, muthu
T-00233-8764 | PS4-79-IG-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0001 TO PS4-79-IG-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00233
T-00233-8765 | PS4-79-IG-0002-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0002 TO PS4-79-IG-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00233
T-00233-8766 | PS4-79-IG-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0003 TO PS4-79-IG-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00233
T-00233-8767 | PS4-79-IG-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0004 TO PS4-79-IG-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00233
T-00233-8768 | PS4-79-IG-0005-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0005 TO PS4-79-IG-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00233
T-00233-8769 | PS4-79-IG-0006-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0006 TO PS4-79-IG-0006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00233
T-00233-8770 | PS4-79-IG-0007-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0007 TO PS4-79-IG-0007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00233
T-00233-8771 | PS4-79-IG-0008-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0008 TO PS4-79-IG-0008 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00233
T-00233-8772 | PS4-79-IG-0009-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0009 TO PS4-79-IG-0009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00233
T-00233-8773 | PS4-79-IG-0010-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0010 TO PS4-79-IG-0010 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00233
T-00233-8774 | PS4-79-IG-0011-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0011 TO PS4-79-IG-0011 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00233
T-00233-8775 | PS4-79-IG-0012-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0012 TO PS4-79-IG-0012 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone H | TM-00233
T-00233-8985 | PS4-02-SWSI-0001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-02-SWSI-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-02-01 - Miscellaneous Safety equipment | 2026-06-08 14:14 | PS4-02-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-8986 | PS4-02-SWSI-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0006 TO PS4-02-SWSI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-02-01 - Miscellaneous Safety equipment | 2026-06-08 14:18 | PS4-02-01 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-8987 | PS4-06-GU-0005-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0007 TO PS4-06-GU-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-06-04 - AC UPS - Guard House |  | PS4-06-04 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone I | TM-00233
T-00233-8992 | PS4-09-LB-7001-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-05-IG-0007 TO PS4-09-LB-7001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-09-02 - HVAC for Guard House |  | PS4-09-02 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone I | TM-00233
T-00233-8995 | PS4-60-BE-0007A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BE-0007A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A | 2026-06-19 12:51 | PS4-60-56 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-8996 | PS4-60-BE-0007B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BE-0007B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B | 2026-06-19 12:54 | PS4-60-58 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-8997 | PS4-60-BE-0007C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BE-0007C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C | 2026-07-24 11:00 | PS4-60-60 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-8998 | PS4-60-BE-0007D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BE-0007D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D |  | PS4-60-62 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-8999 | PS4-60-BE-0007E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BE-0007E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E | 2026-07-24 11:03 | PS4-60-64 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9000 | PS4-60-BE-0007F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BE-0007F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F | 2026-07-24 11:05 | PS4-60-66 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9001 | PS4-60-BE-0007G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BE-0007G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G | 2026-07-24 11:07 | PS4-60-68 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-9002 | PS4-60-BE-0027A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BE-0027A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A | 2026-06-19 13:32 | PS4-60-56 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9003 | PS4-60-BE-0027B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BE-0027B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B | 2026-06-19 13:34 | PS4-60-58 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9004 | PS4-60-BE-0027C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BE-0027C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C | 2026-07-24 08:32 | PS4-60-60 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9005 | PS4-60-BE-0027D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BE-0027D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D | 2026-07-24 08:35 | PS4-60-62 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9006 | PS4-60-BE-0027E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BE-0027E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E | 2026-07-24 08:37 | PS4-60-64 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9007 | PS4-60-BE-0027F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BE-0027F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F | 2026-07-24 08:40 | PS4-60-66 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9008 | PS4-60-BE-0027G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BE-0027G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G | 2026-07-24 08:42 | PS4-60-68 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-9009 | PS4-60-BE-0028A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BE-0028A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A | 2026-06-19 13:37 | PS4-60-56 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9010 | PS4-60-BE-0028B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BE-0028B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B | 2026-06-20 04:52 | PS4-60-58 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9011 | PS4-60-BE-0028C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BE-0028C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C | 2026-07-24 08:45 | PS4-60-60 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9012 | PS4-60-BE-0028D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BE-0028D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D | 2026-07-24 08:50 | PS4-60-62 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9013 | PS4-60-BE-0028E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BE-0028E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E | 2026-07-24 08:52 | PS4-60-64 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9014 | PS4-60-BE-0028F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BE-0028F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F | 2026-07-24 08:55 | PS4-60-66 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9015 | PS4-60-BE-0028G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BE-0028G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G | 2026-07-24 08:57 | PS4-60-68 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-9016 | PS4-60-BI-0006A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-20 05:19 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9017 | PS4-60-BI-0006A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-20 05:30 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9018 | PS4-60-BI-0006A-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-20 05:34 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9019 | PS4-60-BI-0006A-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-20 05:38 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9020 | PS4-60-BI-0006A-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-20 05:42 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9021 | PS4-60-BI-0006A-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-20 05:45 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9022 | PS4-60-BI-0006A-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-20 05:48 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9023 | PS4-60-BI-0006A-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-20 05:51 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9024 | PS4-60-BI-0006A-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-20 05:54 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9025 | PS4-60-BI-0006A-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-20 06:32 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9026 | PS4-60-BI-0006A-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-20 06:35 | PS4-60-02 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9027 | PS4-60-BI-0006B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-20 06:38 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9028 | PS4-60-BI-0006B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-20 06:41 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9029 | PS4-60-BI-0006B-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-20 06:45 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9030 | PS4-60-BI-0006B-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-20 06:49 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9031 | PS4-60-BI-0006B-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-20 06:52 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9032 | PS4-60-BI-0006B-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-20 06:55 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9033 | PS4-60-BI-0006B-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-20 06:58 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9034 | PS4-60-BI-0006B-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-20 07:03 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9035 | PS4-60-BI-0006B-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-20 07:07 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9036 | PS4-60-BI-0006B-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-20 07:10 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9037 | PS4-60-BI-0006B-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-20 07:19 | PS4-60-05 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9038 | PS4-60-BI-0006C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9039 | PS4-60-BI-0006C-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9040 | PS4-60-BI-0006C-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-07-24 11:42 | PS4-60-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9041 | PS4-60-BI-0006C-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-07-24 11:43 | PS4-60-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9042 | PS4-60-BI-0006C-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-07-24 11:45 | PS4-60-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9043 | PS4-60-BI-0006C-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-07-24 11:46 | PS4-60-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9044 | PS4-60-BI-0006C-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-07-24 11:50 | PS4-60-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9045 | PS4-60-BI-0006C-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-07-24 11:51 | PS4-60-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9046 | PS4-60-BI-0006C-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-07-24 11:53 | PS4-60-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9047 | PS4-60-BI-0006C-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-07-24 12:14 | PS4-60-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9048 | PS4-60-BI-0006C-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-07-24 12:19 | PS4-60-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9049 | PS4-60-BI-0006D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9050 | PS4-60-BI-0006D-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9051 | PS4-60-BI-0006D-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9052 | PS4-60-BI-0006D-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9053 | PS4-60-BI-0006D-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9054 | PS4-60-BI-0006D-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-07-24 12:23 | PS4-60-11 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9055 | PS4-60-BI-0006D-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-07-24 12:21 | PS4-60-11 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9056 | PS4-60-BI-0006D-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-07-24 12:25 | PS4-60-11 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9057 | PS4-60-BI-0006D-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-07-24 12:27 | PS4-60-11 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9058 | PS4-60-BI-0006D-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-07-24 12:28 | PS4-60-11 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9059 | PS4-60-BI-0006D-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9060 | PS4-60-BI-0006E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9061 | PS4-60-BI-0006E-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9062 | PS4-60-BI-0006E-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9063 | PS4-60-BI-0006E-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9064 | PS4-60-BI-0006E-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-07-24 12:30 | PS4-60-14 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9065 | PS4-60-BI-0006E-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-07-24 12:33 | PS4-60-14 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9066 | PS4-60-BI-0006E-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-07-24 12:34 | PS4-60-14 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9067 | PS4-60-BI-0006E-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-07-24 12:39 | PS4-60-14 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9068 | PS4-60-BI-0006E-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-07-24 12:40 | PS4-60-14 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9069 | PS4-60-BI-0006E-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-07-24 12:42 | PS4-60-14 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9070 | PS4-60-BI-0006E-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-07-24 12:44 | PS4-60-14 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9071 | PS4-60-BI-0006F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9072 | PS4-60-BI-0006F-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9073 | PS4-60-BI-0006F-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-07-03 11:01 | PS4-60-17 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9074 | PS4-60-BI-0006F-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-07-03 11:08 | PS4-60-17 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9075 | PS4-60-BI-0006F-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-07-03 11:13 | PS4-60-17 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9076 | PS4-60-BI-0006F-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-07-03 11:17 | PS4-60-17 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9077 | PS4-60-BI-0006F-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-07-03 11:20 | PS4-60-17 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9078 | PS4-60-BI-0006F-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-07-03 11:23 | PS4-60-17 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9079 | PS4-60-BI-0006F-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-07-03 11:26 | PS4-60-17 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9080 | PS4-60-BI-0006F-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-07-03 11:29 | PS4-60-17 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9081 | PS4-60-BI-0006F-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9082 | PS4-60-BI-0006G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00233
T-00233-9083 | PS4-60-BI-0006G-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone E | TM-00233
T-00233-9084 | PS4-60-BI-0006G-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-07-24 12:47 | PS4-60-20 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-9085 | PS4-60-BI-0006G-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-07-24 06:21 | PS4-60-20 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-9086 | PS4-60-BI-0006G-CL05 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-07-24 06:46 | PS4-60-20 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-9087 | PS4-60-BI-0006G-CL06 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-07-24 06:57 | PS4-60-20 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-9088 | PS4-60-BI-0006G-CL07 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-07-24 07:00 | PS4-60-20 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-9089 | PS4-60-BI-0006G-CL08 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-07-24 07:02 | PS4-60-20 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-9090 | PS4-60-BI-0006G-CL09 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-07-24 07:06 | PS4-60-20 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-9091 | PS4-60-BI-0006G-CL10 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-07-24 07:13 | PS4-60-20 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-9092 | PS4-60-BI-0006G-CL11 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-07-24 07:15 | PS4-60-20 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-9093 | PS4-60-BI-0017A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0017A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A | 2026-06-20 08:08 | PS4-60-56 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9094 | PS4-60-BI-0017B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0017B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B | 2026-06-20 08:12 | PS4-60-58 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9095 | PS4-60-BI-0017C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0017C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C | 2026-07-24 07:18 | PS4-60-60 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9096 | PS4-60-BI-0017D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0017D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D |  | PS4-60-62 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9097 | PS4-60-BI-0017E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0017E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E | 2026-07-24 07:23 | PS4-60-64 |  |  | LV Power Cable | E | Closed | PS4 - Milestone D | TM-00233 | sridhar, muthu
T-00233-9098 | PS4-60-BI-0017F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0017F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F |  | PS4-60-66 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9099 | PS4-60-BI-0017G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0017G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G | 2026-07-24 07:26 | PS4-60-68 |  |  | LV Power Cable | E | Closed | PS4 - Milestone E | TM-00233 | sridhar, muthu
T-00233-9100 | PS4-60-EA-2900A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002A TO PS4-60-EA-2900A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A | 2026-06-20 08:34 | PS4-60-56 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9101 | PS4-60-EA-2900B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002B TO PS4-60-EA-2900B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B | 2026-06-20 08:54 | PS4-60-58 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9102 | PS4-60-EA-2900C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002C TO PS4-60-EA-2900C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C |  | PS4-60-60 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9103 | PS4-60-EA-2900D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002D TO PS4-60-EA-2900D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D |  | PS4-60-62 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9104 | PS4-60-EA-2900E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002E TO PS4-60-EA-2900E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E |  | PS4-60-64 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9105 | PS4-60-EA-2900F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002F TO PS4-60-EA-2900F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F |  | PS4-60-66 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9106 | PS4-60-EA-2900G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IN-0002G TO PS4-60-EA-2900G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G |  | PS4-60-68 |  |  | LV Power Cable | E | Started (not Completed) | PS4 - Milestone E | TM-00233
T-00233-9107 | PS4-61-IK-0005-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IK-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-61-03 - 0.4kV Switchboard Office & Facilities Building (PS4-61-IK-0005) |  | PS4-61-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone I | TM-00233
T-00233-9108 | PS4-71-BE-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0002 TO PS4-71-BE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-06-21 05:02 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-9109 | PS4-71-BE-0004-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0002 TO PS4-71-BE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-06-21 05:05 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-9110 | PS4-71-BE-0004-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0002 TO PS4-71-BE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-06-21 05:08 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-9111 | PS4-71-BI-0003-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0002 TO PS4-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-08 12:53 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-9112 | PS4-71-BI-0003-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0002 TO PS4-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-08 12:55 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-9113 | PS4-71-BI-0003-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0002 TO PS4-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-08 12:58 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-9114 | PS4-71-BI-0003-CL04 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0002 TO PS4-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-08 13:02 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-9115 | PS4-71-BI-0004-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0002 TO PS4-71-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-08 13:04 | PS4-71-08 |  |  | LV Power Cable | E | Closed | PS4 - Milestone H | TM-00233 | sridhar, muthu
T-00233-9116 | PS4-71-BI-0005-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0003 TO PS4-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-08 13:07 | PS4-71-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9117 | PS4-71-BI-0005-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0003 TO PS4-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-08 13:12 | PS4-71-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9118 | PS4-71-BI-0005-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0003 TO PS4-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-08 13:15 | PS4-71-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9119 | PS4-71-BI-0006-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-71-IN-0003 TO PS4-71-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-08 13:22 | PS4-71-22 |  |  | LV Power Cable | E | Closed | PS4 - Milestone B | TM-00233 | sridhar, muthu
T-00233-9580 | PS4-09-AHU-8111A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8111A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9581 | PS4-09-AHU-8111B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8111B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9582 | PS4-09-AHU-8211A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8211A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9583 | PS4-09-AHU-8211B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8211B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9584 | PS4-09-AHU-8311A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8311A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9585 | PS4-09-AHU-8311A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8311A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9586 | PS4-09-AHU-8311B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8311B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9587 | PS4-09-AHU-8311B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8311B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9588 | PS4-09-AHU-8321A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8321A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9589 | PS4-09-AHU-8321A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8321A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9590 | PS4-09-AHU-8321B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8321B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9591 | PS4-09-AHU-8321B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8321B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9592 | PS4-09-AHU-8331A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8331A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9593 | PS4-09-AHU-8331A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8331A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9594 | PS4-09-AHU-8331B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8331B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9595 | PS4-09-AHU-8331B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8331B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9596 | PS4-09-AHU-8341-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8341 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9597 | PS4-09-AHU-8341-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8341 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9598 | PS4-09-AHU-8411A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8411A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9599 | PS4-09-AHU-8411A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8411A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9600 | PS4-09-AHU-8411B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8411B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9601 | PS4-09-AHU-8411B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-AHU-8411B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9602 | PS4-09-FCU-8442A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-FCU-8442A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9603 | PS4-09-FCU-8442B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-FCU-8442B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9604 | PS4-09-FCU-8442C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-FCU-8442C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9605 | PS4-09-FCU-8442D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-FCU-8442D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9606 | PS4-09-FCU-8442E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-FCU-8442E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9607 | PS4-09-FCU-8442F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-FCU-8442F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9608 | PS4-09-FCU-8442G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-FCU-8442G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9609 | PS4-09-FCU-8442H-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-FCU-8442H | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9610 | PS4-09-LB-0008-CL03 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-LB-0008 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9611 | PS4-09-PA-84500A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-PA-84500A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9612 | PS4-09-PA-84500B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-PA-84500B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9613 | PS4-09-QX-8451A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-QX-8451A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9614 | PS4-09-QX-8451A-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-QX-8451A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9615 | PS4-09-QX-8451B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-QX-8451B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9616 | PS4-09-QX-8451B-CL02 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-QX-8451B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9617 | PS4-09-RF-81200A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-RF-81200A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9618 | PS4-09-RF-81200B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-RF-81200B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9619 | PS4-09-RF-81200C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-RF-81200C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9620 | PS4-09-RF-82200A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-RF-82200A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9621 | PS4-09-RF-82200B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-RF-82200B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9622 | PS4-09-RF-82200C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-RF-82200C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9623 | PS4-09-RF-82200D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-RF-82200D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9624 | PS4-09-RF-83500A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9625 | PS4-09-RF-83500B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9626 | PS4-09-RF-83500C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9627 | PS4-09-RF-83500D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9628 | PS4-09-RF-83500E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9629 | PS4-09-RF-83500F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9630 | PS4-09-RF-83500G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9631 | PS4-09-RF-83500H-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500H | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9632 | PS4-09-RF-83500J-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500J | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9633 | PS4-09-RF-83500K-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500K | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9634 | PS4-09-RF-83500L-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500L | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9635 | PS4-09-RF-83500M-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500M | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9636 | PS4-09-RF-83500N-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500N | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9637 | PS4-09-RF-83500P-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-RF-83500P | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9638 | PS4-09-RF-83600A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9639 | PS4-09-RF-83600B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9640 | PS4-09-RF-83600C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9641 | PS4-09-RF-83600D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9642 | PS4-09-RF-83600E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9643 | PS4-09-RF-83600F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9644 | PS4-09-RF-83600G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9645 | PS4-09-RF-83600H-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600H | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9646 | PS4-09-RF-83600J-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600J | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9647 | PS4-09-RF-83600K-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600K | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9648 | PS4-09-RF-83600L-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600L | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9649 | PS4-09-RF-83600M-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600M | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9650 | PS4-09-RF-83600N-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600N | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9651 | PS4-09-RF-83600P-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-RF-83600P | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9652 | PS4-09-RF-83700A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9653 | PS4-09-RF-83700B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9654 | PS4-09-RF-83700C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9655 | PS4-09-RF-83700D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9656 | PS4-09-RF-83700E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9657 | PS4-09-RF-83700F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9658 | PS4-09-RF-83700G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9659 | PS4-09-RF-83700H-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700H | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9660 | PS4-09-RF-83700J-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700J | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9661 | PS4-09-RF-83700K-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700K | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9662 | PS4-09-RF-83700L-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700L | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9663 | PS4-09-RF-83700M-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700M | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9664 | PS4-09-RF-83700N-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700N | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9665 | PS4-09-RF-83700P-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-RF-83700P | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9666 | PS4-09-RF-83800A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004D TO PS4-09-RF-83800A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9667 | PS4-09-RF-83800B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004D TO PS4-09-RF-83800B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9668 | PS4-09-RF-83800C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004D TO PS4-09-RF-83800C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9669 | PS4-09-RF-83800D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004D TO PS4-09-RF-83800D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9670 | PS4-09-RF-83800E-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004D TO PS4-09-RF-83800E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9671 | PS4-09-RF-83800F-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004D TO PS4-09-RF-83800F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9672 | PS4-09-RF-83800G-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004D TO PS4-09-RF-83800G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9673 | PS4-09-RF-84200A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-RF-84200A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9674 | PS4-09-RF-84200B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-RF-84200B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9675 | PS4-09-UZ-84600-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-09-IH-0004 TO PS4-09-UZ-84600 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9676 | PS4-61-IH-0004A-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-61-IH-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9677 | PS4-61-IH-0004B-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-61-IH-0004B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9678 | PS4-61-IH-0004C-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-61-IH-0004C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00233-9679 | PS4-61-IH-0004D-CL01 |  |  |  |  | TPX09 - LV power cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-61-IH-0004D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | LV Power Cable | E | To be completed | PS4 - Milestone D | TM-00233
T-00234-2305 | PS4-05-IE-8100-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-08 14:22 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-2306 | PS4-05-IE-8100-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-08 14:25 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-2307 | PS4-05-IE-8100-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-08 14:29 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-2308 | PS4-05-IE-8100-CD04 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-09 05:04 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-2309 | PS4-05-IE-8100-CD05 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-09 05:06 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-2310 | PS4-05-IE-8100-CD06 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-09 05:09 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-2311 | PS4-05-IE-8100-CD07 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-09 05:14 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-2312 | PS4-05-IE-8100-CD08 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-08 11:32 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-2314 | PS4-05-IE-8100-CD10 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-09 05:17 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-2315 | PS4-05-IE-8100-CD11 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-09 05:20 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-2316 | PS4-05-IE-8100-CD12 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-09 05:24 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-2317 | PS4-05-IE-8100-CD13 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-09 05:27 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-2318 | PS4-05-IE-8100-CD14 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-09 05:30 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-2319 | PS4-05-IE-8100-CD15 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-09 05:33 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-2320 | PS4-05-IE-8100-CD16 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-09 07:47 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-2321 | PS4-05-IE-8100-CD17 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-09 07:49 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-2322 | PS4-05-IE-8100-CD18 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-09 07:53 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-2323 | PS4-05-IE-8100-CD19 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-09 07:56 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-2324 | PS4-05-IE-8100-CD20 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-09 07:59 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-2325 | PS4-05-IE-8100-CD21 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-09 08:01 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-2329 | PS4-05-IE-8100-CD25 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IE-0004 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-06-08 11:46 | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-2338 | PS4-25-DM-3100A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-DM-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-06-12 05:49 | PS4-25-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00234 | sridhar, muthu
T-00234-2339 | PS4-25-DM-3100B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-DM-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-06-12 05:58 | PS4-25-03 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00234 | sridhar, muthu
T-00234-2340 | PS4-25-DM-3100C-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-DM-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-06-12 06:04 | PS4-25-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00234 | sridhar, muthu
T-00234-2344 | PS4-25-IES-3100A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-25-IES-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-06-09 11:56 | PS4-25-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00234 | sridhar, muthu
T-00234-2345 | PS4-25-IES-3100B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-25-IES-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-06-09 12:04 | PS4-25-03 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00234 | sridhar, muthu
T-00234-2346 | PS4-25-IES-3100C-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-25-IES-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-06-09 12:06 | PS4-25-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00234 | sridhar, muthu
T-00234-2374 | PS4-50-IE-0001-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-50-IE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-50-01 - Water Well Submersible Pumps (3100) |  | PS4-50-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone I | TM-00234
T-00234-2375 | PS4-50-IE-0002-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-50-IE-0002 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-50-02 - Water Well Submersible Pumps (3200) |  | PS4-50-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone I | TM-00234
T-00234-2378 | PS4-60-IE-0002A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015A TO PS4-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-20 10:25 | PS4-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00234 | sridhar, muthu
T-00234-2379 | PS4-60-IE-0002A-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015A TO PS4-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-20 10:29 | PS4-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00234 | sridhar, muthu
T-00234-2380 | PS4-60-IE-0002A-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015A TO PS4-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-20 10:31 | PS4-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00234 | sridhar, muthu
T-00234-2381 | PS4-60-IE-0002B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015B TO PS4-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-20 10:56 | PS4-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00234 | sridhar, muthu
T-00234-2382 | PS4-60-IE-0002B-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015B TO PS4-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-20 11:00 | PS4-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00234 | sridhar, muthu
T-00234-2383 | PS4-60-IE-0002B-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015B TO PS4-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-20 11:04 | PS4-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00234 | sridhar, muthu
T-00234-2384 | PS4-60-IE-0002C-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015C TO PS4-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-03 12:32 | PS4-60-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2385 | PS4-60-IE-0002C-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015C TO PS4-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-03 14:28 | PS4-60-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2386 | PS4-60-IE-0002C-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015C TO PS4-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-03 14:32 | PS4-60-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2387 | PS4-60-IE-0002D-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015D TO PS4-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-20 11:19 | PS4-60-10 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2388 | PS4-60-IE-0002D-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015D TO PS4-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-20 11:21 | PS4-60-10 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2389 | PS4-60-IE-0002D-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015D TO PS4-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-20 11:24 | PS4-60-10 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2390 | PS4-60-IE-0002E-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015E TO PS4-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-04 04:44 | PS4-60-13 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2391 | PS4-60-IE-0002E-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015E TO PS4-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-04 04:48 | PS4-60-13 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2392 | PS4-60-IE-0002E-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015E TO PS4-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-04 04:52 | PS4-60-13 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2393 | PS4-60-IE-0002F-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015F TO PS4-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-20 11:34 | PS4-60-16 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2394 | PS4-60-IE-0002F-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015F TO PS4-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-20 11:36 | PS4-60-16 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2395 | PS4-60-IE-0002F-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015F TO PS4-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-20 11:38 | PS4-60-16 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2396 | PS4-60-IE-0002G-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015G TO PS4-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone E | TM-00234
T-00234-2397 | PS4-60-IE-0002G-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015G TO PS4-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone E | TM-00234
T-00234-2398 | PS4-60-IE-0002G-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015G TO PS4-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-04 05:12 | PS4-60-19 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone E | TM-00234 | sridhar, muthu
T-00234-2400 | PS4-60-IE-0003A-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-20 11:53 | PS4-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00234 | sridhar, muthu
T-00234-2401 | PS4-60-IE-0003A-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-20 11:56 | PS4-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00234 | sridhar, muthu
T-00234-2402 | PS4-60-IE-0003A-CD04 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0005A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-20 12:00 | PS4-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00234 | sridhar, muthu
T-00234-2403 | PS4-60-IE-0003A-CD05 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-20 12:03 | PS4-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00234 | sridhar, muthu
T-00234-2412 | PS4-60-IE-0003A-CD14 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IE-0002A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-20 12:05 | PS4-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00234 | sridhar, muthu
T-00234-2413 | PS4-60-IE-0003A-CD15 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-08 12:29 | PS4-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00234 | sridhar, muthu
T-00234-2415 | PS4-60-IE-0003B-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-08 12:31 | PS4-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00234 | sridhar, muthu
T-00234-2416 | PS4-60-IE-0003B-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-08 12:33 | PS4-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00234 | sridhar, muthu
T-00234-2417 | PS4-60-IE-0003B-CD04 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0005B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-08 12:35 | PS4-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00234 | sridhar, muthu
T-00234-2418 | PS4-60-IE-0003B-CD05 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-08 12:37 | PS4-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00234 | sridhar, muthu
T-00234-2427 | PS4-60-IE-0003B-CD14 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IE-0002B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-20 12:13 | PS4-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00234 | sridhar, muthu
T-00234-2428 | PS4-60-IE-0003B-CD15 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-20 12:15 | PS4-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00234 | sridhar, muthu
T-00234-2430 | PS4-60-IE-0003C-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-04 05:33 | PS4-60-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2431 | PS4-60-IE-0003C-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-04 05:38 | PS4-60-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2432 | PS4-60-IE-0003C-CD04 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0005C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-04 05:44 | PS4-60-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2433 | PS4-60-IE-0003C-CD05 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-04 05:51 | PS4-60-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2442 | PS4-60-IE-0003C-CD14 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IE-0002C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-04 05:53 | PS4-60-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2443 | PS4-60-IE-0003C-CD15 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-08 12:39 | PS4-60-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2445 | PS4-60-IE-0003D-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-20 13:27 | PS4-60-10 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2446 | PS4-60-IE-0003D-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-20 14:18 | PS4-60-10 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2447 | PS4-60-IE-0003D-CD04 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0005D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-08 12:41 | PS4-60-10 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2448 | PS4-60-IE-0003D-CD05 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-20 14:21 | PS4-60-10 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2457 | PS4-60-IE-0003D-CD14 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IE-0002D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-20 14:24 | PS4-60-10 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2458 | PS4-60-IE-0003D-CD15 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-20 14:26 | PS4-60-10 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2460 | PS4-60-IE-0003E-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-04 06:06 | PS4-60-13 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2461 | PS4-60-IE-0003E-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-04 06:23 | PS4-60-13 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2462 | PS4-60-IE-0003E-CD04 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0005E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-04 06:38 | PS4-60-13 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2463 | PS4-60-IE-0003E-CD05 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-04 06:45 | PS4-60-13 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2472 | PS4-60-IE-0003E-CD14 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IE-0002E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-04 06:49 | PS4-60-13 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2473 | PS4-60-IE-0003E-CD15 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-24 09:00 | PS4-60-13 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2475 | PS4-60-IE-0003F-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-20 14:28 | PS4-60-16 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2476 | PS4-60-IE-0003F-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-20 14:30 | PS4-60-16 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2477 | PS4-60-IE-0003F-CD04 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0005F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-20 14:32 | PS4-60-16 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2478 | PS4-60-IE-0003F-CD05 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-20 14:34 | PS4-60-16 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2487 | PS4-60-IE-0003F-CD14 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IE-0002F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-20 14:36 | PS4-60-16 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2488 | PS4-60-IE-0003F-CD15 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-20 14:39 | PS4-60-16 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00234 | sridhar, muthu
T-00234-2490 | PS4-60-IE-0003G-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-04 06:52 | PS4-60-19 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone E | TM-00234 | sridhar, muthu
T-00234-2491 | PS4-60-IE-0003G-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-04 06:55 | PS4-60-19 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone E | TM-00234 | sridhar, muthu
T-00234-2492 | PS4-60-IE-0003G-CD04 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0005G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-04 06:57 | PS4-60-19 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone E | TM-00234 | sridhar, muthu
T-00234-2493 | PS4-60-IE-0003G-CD05 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-BI-0015G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-04 07:01 | PS4-60-19 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone E | TM-00234 | sridhar, muthu
T-00234-2502 | PS4-60-IE-0003G-CD14 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IE-0002G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-04 07:03 | PS4-60-19 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone E | TM-00234 | sridhar, muthu
T-00234-2503 | PS4-60-IE-0003G-CD15 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-24 10:47 | PS4-60-19 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone E | TM-00234 | sridhar, muthu
T-00234-2510 | PS4-61-IDH-3100A-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-06-12 07:11 | PS4-25-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00234 | sridhar, muthu
T-00234-2513 | PS4-61-IDH-3100B-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-06-12 07:16 | PS4-25-03 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00234 | sridhar, muthu
T-00234-2516 | PS4-61-IDH-3100C-CD03 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IU-3100C TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-06-12 07:18 | PS4-25-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00234 | sridhar, muthu
T-00234-2558 | PS4-62-IE-0001-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-62-IE-0002 TO PS4-62-IE-0001 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-WPR2-150101 | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 | 2026-06-12 07:26 | PS4-62-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone G | TM-00234 | sridhar, muthu
T-00234-3180 | PS4-79-IG-0001-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0001 TO PS4-79-IG-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00234
T-00234-3181 | PS4-79-IG-0002-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0002 TO PS4-79-IG-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00234
T-00234-3182 | PS4-79-IG-0003-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0003 TO PS4-79-IG-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00234
T-00234-3183 | PS4-79-IG-0004-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0004 TO PS4-79-IG-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00234
T-00234-3184 | PS4-79-IG-0005-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0005 TO PS4-79-IG-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00234
T-00234-3185 | PS4-79-IG-0006-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0006 TO PS4-79-IG-0006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00234
T-00234-3186 | PS4-79-IG-0007-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0007 TO PS4-79-IG-0007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00234
T-00234-3187 | PS4-79-IG-0008-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0008 TO PS4-79-IG-0008 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00234
T-00234-3188 | PS4-79-IG-0009-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0009 TO PS4-79-IG-0009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00234
T-00234-3189 | PS4-79-IG-0010-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0010 TO PS4-79-IG-0010 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00234
T-00234-3190 | PS4-79-IG-0011-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0011 TO PS4-79-IG-0011 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00234
T-00234-3191 | PS4-79-IG-0012-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-79-IV-0012 TO PS4-79-IG-0012 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00234
T-00234-3398 | PS4-06-GU-0003A-CD02 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-06-GB-0003 TO PS4-06-GU-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-06-06 10:27 | PS4-06-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00234 | sridhar, muthu
T-00234-3580 | PS4-09-IES-8101A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8101A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3581 | PS4-09-IES-8101B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8101B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3582 | PS4-09-IES-8102A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8102A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3583 | PS4-09-IES-8102B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8102B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3584 | PS4-09-IES-8102C-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8102C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3585 | PS4-09-IES-8201A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8201A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3586 | PS4-09-IES-8201B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8201B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3587 | PS4-09-IES-8202A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8202A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3588 | PS4-09-IES-8202B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8202B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3589 | PS4-09-IES-8202C-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8202C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3590 | PS4-09-IES-8202D-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8202D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3591 | PS4-09-IES-8301A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8301A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3592 | PS4-09-IES-8301B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8301B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3593 | PS4-09-IES-8302A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8302A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3594 | PS4-09-IES-8302B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8302B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3595 | PS4-09-IES-8304A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8304A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3596 | PS4-09-IES-8304B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8304B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3597 | PS4-09-IES-8305A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8305A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3598 | PS4-09-IES-8305B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8305B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3599 | PS4-09-IES-8307A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8307A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3600 | PS4-09-IES-8307B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8307B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3601 | PS4-09-IES-8308A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8308A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3602 | PS4-09-IES-8308B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8308B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3603 | PS4-09-IES-8311A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8311A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3604 | PS4-09-IES-8311B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8311B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3605 | PS4-09-IES-8313-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-IES-8313 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3606 | PS4-09-IES-8314-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004A TO PS4-09-IES-8314 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3607 | PS4-09-IES-8315-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8315 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3608 | PS4-09-IES-8316-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-IES-8316 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3609 | PS4-09-IES-8317-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004B TO PS4-09-IES-8317 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3610 | PS4-09-IES-8318-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8318 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3611 | PS4-09-IES-8319-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-IES-8319 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3612 | PS4-09-IES-8321-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004C TO PS4-09-IES-8321 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3613 | PS4-09-IES-8322-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8322 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3614 | PS4-09-IES-8323-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004D TO PS4-09-IES-8323 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3615 | PS4-09-IES-8324-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004D TO PS4-09-IES-8324 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3616 | PS4-09-IES-8325-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8325 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3617 | PS4-09-IES-8401A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8401A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3618 | PS4-09-IES-8401B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8401B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3619 | PS4-09-IES-8403A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8403A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3620 | PS4-09-IES-8403B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8403B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3621 | PS4-09-IES-8404A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8404A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3622 | PS4-09-IES-8404B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8404B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3623 | PS4-09-IES-8405A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8405A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3624 | PS4-09-IES-8405B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8405B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3625 | PS4-09-IES-8406A-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8406A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3626 | PS4-09-IES-8406B-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8406B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3627 | PS4-09-IES-8406C-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8406C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3628 | PS4-09-IES-8406D-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8406D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3629 | PS4-09-IES-8406E-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8406E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3630 | PS4-09-IES-8406F-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8406F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3631 | PS4-09-IES-8406G-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8406G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3632 | PS4-09-IES-8406H-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8406H | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-3633 | PS4-09-IES-8407-CD01 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IH-0004 TO PS4-09-IES-8407 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00234
T-00234-4388 | PS4-61-IE-0002-CD45 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System | 2026-07-04 13:14 | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-4389 | PS4-61-IE-0002-CD46 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System | 2026-07-04 13:18 | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-4390 | PS4-61-IE-0002-CD47 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System | 2026-07-04 13:21 | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-4391 | PS4-61-IE-0002-CD48 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System | 2026-07-04 13:27 | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-4392 | PS4-61-IE-0002-CD49 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System | 2026-07-05 04:57 | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-4393 | PS4-61-IE-0002-CD50 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System | 2026-07-05 05:01 | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-4394 | PS4-61-IE-0002-CD51 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0005 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System | 2026-07-05 05:04 | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-4395 | PS4-61-IE-0002-CD52 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0005 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System | 2026-07-05 05:06 | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-4396 | PS4-61-IE-0002-CD53 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0005 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System | 2026-07-05 05:09 | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-4397 | PS4-61-IE-0002-CD54 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0005 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System | 2026-07-05 05:12 | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-4398 | PS4-61-IE-0002-CD55 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0005 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System | 2026-07-05 05:15 | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-4399 | PS4-61-IE-0003-CD11 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IE-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System | 2026-07-05 05:22 | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-4400 | PS4-61-IE-0003-CD12 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IE-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System | 2026-07-05 05:46 | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00234-4401 | PS4-61-IE-0003-CD13 |  |  |  |  | TPX10 - Multicore electrical control cable | PCOM - Precommissioning | E | Static Test | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IE-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System | 2026-07-05 05:50 | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00234 | sridhar, muthu
T-00235-0010 | PS4-25-DM-3100A |  |  |  |  | TPX12 - Motor HV | PCOM - Precommissioning | E | Static Test | E - Electrical | CRUDE OIL EXPORT PUMP A MOTOR | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | HV Motor | E | To be completed | PS4 - Milestone H | TM-00235
T-00235-0011 | PS4-25-DM-3100B |  |  |  |  | TPX12 - Motor HV | PCOM - Precommissioning | E | Static Test | E - Electrical | CRUDE OIL EXPORT PUMP B MOTOR | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | HV Motor | E | To be completed | PS4 - Milestone H | TM-00235
T-00235-0012 | PS4-25-DM-3100C |  |  |  |  | TPX12 - Motor HV | PCOM - Precommissioning | E | Static Test | E - Electrical | CRUDE OIL EXPORT PUMP C MOTOR | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | HV Motor | E | To be completed | PS4 - Milestone H | TM-00235
T-00236-0114 | PS4-28-DM-3300 |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Relief Drum Pump Motor | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump |  | PS4-28-06 |  |  | LV Motor | E | To be completed | PS4 - Milestone G | TM-00236
T-00236-0115 | PS4-28-DM-3400 |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Closed Drain Drum 01 Pump Motor | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | LV Motor | E | To be completed | PS4 - Milestone G | TM-00236
T-00236-0116 | PS4-28-DM-3500 |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Oily Water Sump Pump Motor | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | LV Motor | E | To be completed | PS4 - Milestone G | TM-00236
T-00236-0117 | PS4-28-DM-3600A |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Open Drain Sump Pump Motor A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | LV Motor | E | To be completed | PS4 - Milestone G | TM-00236
T-00236-0118 | PS4-28-DM-3600B |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Open Drain Sump Pump Motor B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | LV Motor | E | To be completed | PS4 - Milestone G | TM-00236
T-00236-0119 | PS4-28-DM-3700A |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Closed Drain Drum 02 Pump Motor A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | LV Motor | E | To be completed | PS4 - Milestone E | TM-00236
T-00236-0120 | PS4-28-DM-3700B |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Closed Drain Drum 02 Pump Motor B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | LV Motor | E | To be completed | PS4 - Milestone E | TM-00236
T-00236-0121 | PS4-28-DM-3800A |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Seal Oil Drain Drum Pump Motor A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | LV Motor | E | To be completed | PS4 - Milestone H | TM-00236
T-00236-0122 | PS4-28-DM-3800B |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Seal Oil Drain Drum Pump Motor B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | LV Motor | E | To be completed | PS4 - Milestone H | TM-00236
T-00236-0123 | PS4-28-DM-3800C |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Seal Oil Drain Drum Pump Motor C | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | LV Motor | E | To be completed | PS4 - Milestone H | TM-00236
T-00236-0124 | PS4-28-DM-3900A |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Reinjection Pump Motor A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | LV Motor | E | To be completed | PS4 - Milestone H | TM-00236
T-00236-0125 | PS4-28-DM-3900B |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Reinjection Pump Motor B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | LV Motor | E | To be completed | PS4 - Milestone H | TM-00236
T-00236-0126 | PS4-53-DM-3100A |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Water Distribution Pump Motor A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-53-02 - Water Distribution Pump A/B |  | PS4-53-02 |  |  | LV Motor | E | To be completed | PS4 - Milestone E | TM-00236
T-00236-0127 | PS4-53-DM-3100B |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Water Distribution Pump Motor B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-53-02 - Water Distribution Pump A/B |  | PS4-53-02 |  |  | LV Motor | E | To be completed | PS4 - Milestone E | TM-00236
T-00236-0128 | PS4-60-DM-3300 |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Cooling Water Pump Motor | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-24 - Cooling Water Tank & Pump |  | PS4-60-24 |  |  | LV Motor | E | To be completed | PS4 - Milestone E | TM-00236
T-00236-0129 | PS4-60-DM-3400 |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Cooling Water Return Pump Motor | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-25 - Cooling Water Maintenance Tank & Return Pump |  | PS4-60-25 |  |  | LV Motor | E | To be completed | PS4 - Milestone E | TM-00236
T-00236-0130 | PS4-71-DM-3100A |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Diesel Fuel Supply Pump Motor A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-16 - Diesel Fuel Supply Pump A/B |  | PS4-71-16 |  |  | LV Motor | E | To be completed | PS4 - Milestone F | TM-00236
T-00236-0131 | PS4-71-DM-3100B |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Diesel Fuel Supply Pump Motor B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-16 - Diesel Fuel Supply Pump A/B |  | PS4-71-16 |  |  | LV Motor | E | To be completed | PS4 - Milestone F | TM-00236
T-00236-0132 | PS4-71-DM-3200 |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Diesel Fuel Make-Up Pump Motor | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-14 - Diesel Fuel Transfer and Dispensing Station |  | PS4-71-14 |  |  | LV Motor | E | To be completed | PS4 - Milestone F | TM-00236
T-00236-0133 | PS4-71-DM-3300A |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Crude Fuel Oil Transfer Pump Motor A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | LV Motor | E | To be completed | PS4 - Milestone H | TM-00236
T-00236-0134 | PS4-71-DM-3300B |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Crude Fuel Oil Transfer Pump Motor B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | LV Motor | E | To be completed | PS4 - Milestone H | TM-00236
T-00236-0135 | PS4-71-DM-3400A |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Crude Fuel Oil Service Pump Motor A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | LV Motor | E | To be completed | PS4 - Milestone H | TM-00236
T-00236-0136 | PS4-71-DM-3400B |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Crude Fuel Oil Service Pump Motor B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | LV Motor | E | To be completed | PS4 - Milestone H | TM-00236
T-00236-0137 | PS4-71-DM-3500A |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Diesel Transfer Pump Motor A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | LV Motor | E | To be completed | PS4 - Milestone B | TM-00236
T-00236-0138 | PS4-71-DM-3500B |  |  |  |  | TPX13 - Motor LV | PCOM - Precommissioning | E | Static Test | E - Electrical | Diesel Transfer Pump Motor B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | LV Motor | E | To be completed | PS4 - Milestone B | TM-00236
T-00238-0492 | PS4-01-IE-0001A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Foam Package(PS4-01-UV-8700) Pump Control Panel A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-05 - Foam Skid |  | PS4-01-05 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone F | TM-00238
T-00238-0493 | PS4-01-IE-0001B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Foam Package(PS4-01-UV-8700) Pump Control Panel B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-05 - Foam Skid |  | PS4-01-05 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone F | TM-00238
T-00238-0494 | PS4-01-IE-0002A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fire Water Jockey Pump Control Panel A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone C | TM-00238
T-00238-0495 | PS4-01-IE-0002B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fire Water Jockey Pump Control panel B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone C | TM-00238
T-00238-0496 | PS4-01-IE-0009A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fire Water starter pump Local Control Panel A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone C | TM-00238
T-00238-0497 | PS4-01-IE-0009B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fire Water starter pump Local Control Panel B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone C | TM-00238
T-00238-0499 | PS4-05-IE-8100 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Unit Control Panel for Emergency Diesel Generator | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) |  | PS4-05-02 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone C | TM-00238
T-00238-0500 | PS4-50-IE-0001 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Water Well Submersible Pump Control Panel A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-50-01 - Water Well Submersible Pumps (3100) |  | PS4-50-01 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone I | TM-00238
T-00238-0501 | PS4-50-IE-0002 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Water Well Submersible Pump Control Panel B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-50-02 - Water Well Submersible Pumps (3200) |  | PS4-50-02 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone I | TM-00238
T-00238-0502 | PS4-60-IE-0002A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Local Display Panel (LDP) for Generator Set A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-29 13:40 | PS4-60-01 |  |  | Distribution Board/Console/Control Panel | E | Closed | PS4 - Milestone B | TM-00238 | sridhar, muthu
T-00238-0503 | PS4-60-IE-0002B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Local Display Panel (LDP) for Generator Set B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-29 13:48 | PS4-60-04 |  |  | Distribution Board/Console/Control Panel | E | Closed | PS4 - Milestone B | TM-00238 | sridhar, muthu
T-00238-0504 | PS4-60-IE-0002C |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Local Display Panel (LDP) for Generator Set C | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0505 | PS4-60-IE-0002D |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Local Display Panel (LDP) for Generator Set D | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0506 | PS4-60-IE-0002E |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Local Display Panel (LDP) for Generator Set E | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0507 | PS4-60-IE-0002F |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Local Display Panel (LDP) for Generator Set F | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0508 | PS4-60-IE-0002G |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Local Display Panel (LDP) for Generator Set G | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone E | TM-00238
T-00238-0509 | PS4-60-IE-0003A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Generator control panel for generator set- 1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-29 13:50 | PS4-60-02 |  |  | Distribution Board/Console/Control Panel | E | Closed | PS4 - Milestone B | TM-00238 | sridhar, muthu
T-00238-0510 | PS4-60-IE-0003B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Generator control panel for generator set- 2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-29 13:51 | PS4-60-05 |  |  | Distribution Board/Console/Control Panel | E | Closed | PS4 - Milestone B | TM-00238 | sridhar, muthu
T-00238-0511 | PS4-60-IE-0003C |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Generator control panel for generator set- 3 (C) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0512 | PS4-60-IE-0003D |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Generator control panel for generator set- 4 (D) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0513 | PS4-60-IE-0003E |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Generator control panel for generator set- 5 (E) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0514 | PS4-60-IE-0003F |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Generator control panel for generator set- 6 (F) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0515 | PS4-60-IE-0003G |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Generator control panel for generator set- 7 (G) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone E | TM-00238
T-00238-0516 | PS4-60-IE-0004 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Master Control Panel | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-29 13:39 | PS4-60-22 |  |  | Distribution Board/Console/Control Panel | E | Closed | PS4 - Milestone B | TM-00238 | sridhar, muthu
T-00238-0517 | PS4-60-IH-0001A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Generator A Auxiliary MCC | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS4-60-03 |  |  | Distribution Board/Console/Control Panel | E | Started (not Completed) | PS4 - Milestone B | TM-00238
T-00238-0518 | PS4-60-IH-0001B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Generator B Auxiliary MCC | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS4-60-06 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone B | TM-00238
T-00238-0519 | PS4-60-IH-0001C |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Generator C Auxiliary MCC | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS4-60-09 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0520 | PS4-60-IH-0001D |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Generator D Auxiliary MCC | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS4-60-12 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0521 | PS4-60-IH-0001E |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Generator E Auxiliary MCC | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS4-60-15 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0522 | PS4-60-IH-0001F |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Generator F Auxiliary MCC | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS4-60-18 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0523 | PS4-60-IH-0001G |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Generator G Auxiliary MCC | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS4-60-21 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone E | TM-00238
T-00238-0524 | PS4-60-IH-0002 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Generator Common MCC - Feeder A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone B | TM-00238
T-00238-0525 | PS4-60-IN-0002A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-07-29 13:53 | PS4-60-57 |  |  | Distribution Board/Console/Control Panel | E | Closed | PS4 - Milestone B | TM-00238 | sridhar, muthu
T-00238-0526 | PS4-60-IN-0002B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-07-29 13:54 | PS4-60-59 |  |  | Distribution Board/Console/Control Panel | E | Closed | PS4 - Milestone B | TM-00238 | sridhar, muthu
T-00238-0527 | PS4-60-IN-0002C |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0528 | PS4-60-IN-0002D |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0529 | PS4-60-IN-0002E |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) |  | PS4-60-65 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0530 | PS4-60-IN-0002F |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) |  | PS4-60-67 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0531 | PS4-60-IN-0002G |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) |  | PS4-60-69 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone E | TM-00238
T-00238-0532 | PS4-61-IH-0004 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | HVAC MCC - Generator Building | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0533 | PS4-61-IH-0004A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | HVAC MCC - Power Generator Building Feeder A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0534 | PS4-61-IH-0004B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | HVAC MCC - Power Generator Building Feeder B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0535 | PS4-62-IE-0001 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Lighting Control panel 1 - Pump Station 4 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone G | TM-00238
T-00238-0536 | PS4-62-IE-0002 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Lighting Control panel 2 - Pump Station 4 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone G | TM-00238
T-00238-0537 | PS4-71-IN-0001 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | DFO- SEPARATOR CONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone F | TM-00238
T-00238-0538 | PS4-71-IN-0002 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | CFO-PRE PRESSURE CONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-09 - CFO Pre-Pressure Module (UCP) |  | PS4-71-09 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone H | TM-00238
T-00238-0539 | PS4-71-IN-0003 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | DFO- PRE PRESSURE CONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-07-29 13:55 | PS4-71-23 |  |  | Distribution Board/Console/Control Panel | E | Closed | PS4 - Milestone B | TM-00238 | sridhar, muthu
T-00238-0540 | PS4-71-IN-0004A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | CRO- SEPARATOR CONTROL PANEL-1 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone H | TM-00238
T-00238-0541 | PS4-71-IN-0004B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | CRO- SEPARATOR CONTROL PANEL-2 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone H | TM-00238
T-00238-0685 | PS4-01-IG-0001 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Water Mist System Main Distribution Board | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone E | TM-00238
T-00238-0686 | PS4-05-IG-0002 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Indoor Emergency L&SP DB Office and Facilities Building | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone I | TM-00238
T-00238-0687 | PS4-05-IG-0004 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Outdoor Emergency Lighting Distribution Board PS-4 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-03 - Outdoor Emergency Lighting DB - PS4-05-IG-0004 | 2026-06-02 04:56 | PS4-62-03 |  |  | Distribution Board/Console/Control Panel | E | Closed | PS4 - Milestone G | TM-00238 | tereshchenko, nikolai
T-00238-0688 | PS4-05-IG-0006 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Outdoor Emergency Lighting Distribution Board PS-4 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-04 - Outdoor Emergency Lighting DB - PS4-05-IG-0006 | 2026-06-02 04:57 | PS4-62-04 |  |  | Distribution Board/Console/Control Panel | E | Closed | PS4 - Milestone G | TM-00238 | tereshchenko, nikolai
T-00238-0689 | PS4-05-IG-0007 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Indoor Emergency L&SP DB - Guard House | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-05 - Guard House Emergency L&SP DB - PS4-05-IG-0007 |  | PS4-62-05 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone I | TM-00238
T-00238-0690 | PS4-05-IG-0014 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | CRO Generator Building Emergency Lighting Distribution Board PS-4 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-06 - CRO Generator Building Emergency Lighting DB - PS4-05-IG-0014 |  | PS4-62-06 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone B | TM-00238
T-00238-0691 | PS4-05-IG-0020 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Generator Electrical Building Emergency L&SP Distribution Board PS-4 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-07 - CRO Generator Electrical Building Emergency L&SP DB - PS4-05-IG-0020 |  | PS4-62-07 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone B | TM-00238
T-00238-0692 | PS4-06-IG-0004A |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | AC UPS DB - Generator Electrical Bldng | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-29 13:57 | PS4-06-02 |  |  | Distribution Board/Console/Control Panel | E | Closed | PS4 - Milestone B | TM-00238 | sridhar, muthu
T-00238-0693 | PS4-06-IG-0004B |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | AC UPS DB - Generator Electrical Bldng | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-29 14:05 | PS4-06-02 |  |  | Distribution Board/Console/Control Panel | E | Closed | PS4 - Milestone B | TM-00238 | sridhar, muthu
T-00238-0694 | PS4-61-IG-0005 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Outdoor Normal Lighting Distribution Board PS-4 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 | 2026-06-02 04:59 | PS4-62-08 |  |  | Distribution Board/Console/Control Panel | E | Closed | PS4 - Milestone G | TM-00238 | tereshchenko, nikolai
T-00238-0695 | PS4-61-IG-0007 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Outdoor Normal Lighting Distribution Board PS-4 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 | 2026-06-02 04:58 | PS4-62-09 |  |  | Distribution Board/Console/Control Panel | E | Closed | PS4 - Milestone G | TM-00238 | tereshchenko, nikolai
T-00238-0696 | PS4-61-IG-0010 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Generator Electrical Building Normal L&SP Distribution Board PS-4 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-10 - CRO Generator Electrical Building Normal L&SP DB - PS4-61-IG-0010 |  | PS4-62-10 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone B | TM-00238
T-00238-0697 | PS4-61-IG-0014 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Outdoor Power Distribution Board PS-4 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-61-08 - Outdoor Power Distribution Board - PS4-61-IG-0014 |  | PS4-61-08 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone G | TM-00238
T-00238-0698 | PS4-61-IG-0030 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | CRO Generator Building Normal L&SP Distribution Board PS-4 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone B | TM-00238
T-00238-0699 | PS4-61-IG-0041 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Outdoor valves Distribution Board PS-4 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-61-09 - Outdoor Valves Distribution Board - PS4-61-IG-0041 | 2026-06-02 04:54 | PS4-61-09 |  |  | Distribution Board/Console/Control Panel | E | Closed | PS4 - Milestone F | TM-00238 | tereshchenko, nikolai
T-00238-0700 | PS4-61-IG-0042 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Outdoor valves Distribution Board PS-4 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-61-10 - Outdoor Valves Distribution Board - PS4-61-IG-0042 | 2026-06-02 04:55 | PS4-61-10 |  |  | Distribution Board/Console/Control Panel | E | Closed | PS4 - Milestone F | TM-00238 | tereshchenko, nikolai
T-00238-0701 | PS4-74-IG-5101 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | Nitrogen Generation Skid Power Distribution Panel | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-74-02 - N2 Generation Skid (UCP) |  | PS4-74-02 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone F | TM-00238
T-00238-0702 | PS4-79-IG-0001 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | EHT Distribution Board 1 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone H | TM-00238
T-00238-0703 | PS4-79-IG-0002 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | EHT Distribution Board 2 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone H | TM-00238
T-00238-0704 | PS4-79-IG-0003 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | EHT Distribution Board 3 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone H | TM-00238
T-00238-0705 | PS4-79-IG-0004 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | EHT Distribution Board 4 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone H | TM-00238
T-00238-0706 | PS4-79-IG-0005 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | EHT Distribution Board 5 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone H | TM-00238
T-00238-0707 | PS4-79-IG-0006 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | EHT Distribution Board 6 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone H | TM-00238
T-00238-0708 | PS4-79-IG-0007 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | EHT Distribution Board 7 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone H | TM-00238
T-00238-0709 | PS4-79-IG-0008 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | EHT Distribution Board 8 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone H | TM-00238
T-00238-0710 | PS4-79-IG-0009 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | EHT Distribution Board 9 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone H | TM-00238
T-00238-0711 | PS4-79-IG-0010 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | EHT Distribution Board 10 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone H | TM-00238
T-00238-0712 | PS4-79-IG-0011 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | EHT Distribution Board 11 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone H | TM-00238
T-00238-0713 | PS4-79-IG-0012 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | EHT Distribution Board 12 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone H | TM-00238
T-00238-0816 | PS4-09-LB-0008 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | HVAC UNIT CONTROL PANEL | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0817 | PS4-61-IH-0004C |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | LOCAL STARTER PANEL | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0818 | PS4-61-IH-0004D |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | LOCAL STARTER PANEL | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone D | TM-00238
T-00238-0857 | PS4-09-LB-7001 |  |  |  |  | TPX15 - Distribution board/console/control panel | PCOM - Precommissioning | E | Static Test | E - Electrical | HVAC UCP - Guard House | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-02 - HVAC for Guard House |  | PS4-09-02 |  |  | Distribution Board/Console/Control Panel | E | To be completed | PS4 - Milestone I | TM-00238
T-00239-0231 | PS4-06-GU-0003A |  |  |  |  | TPX16 - Charger / inverter | PCOM - Precommissioning | E | Static Test | E - Electrical | AC UPS A - Generator Electrical Building | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building |  | PS4-06-02 |  |  | Charger/Inverter | E | Submitted | PS4 - Milestone B | TM-00239
T-00239-0232 | PS4-06-GU-0003B |  |  |  |  | TPX16 - Charger / inverter | PCOM - Precommissioning | E | Static Test | E - Electrical | AC UPS B - Generator Electrical Building | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building |  | PS4-06-02 |  |  | Charger/Inverter | E | To be completed | PS4 - Milestone B | TM-00239
T-00239-0233 | PS4-06-GU-0003C |  |  |  |  | TPX16 - Charger / inverter | PCOM - Precommissioning | E | Static Test | E - Electrical | AC UPS Bypass - Generator Electrical Building | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building |  | PS4-06-02 |  |  | Charger/Inverter | E | To be completed | PS4 - Milestone B | TM-00239
T-00240-1130 |  | PS4-05-IG-0002_CKT01 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1131 |  | PS4-05-IG-0002_CKT02 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1132 |  | PS4-05-IG-0002_CKT03 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1133 |  | PS4-05-IG-0002_CKT04 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1134 |  | PS4-05-IG-0002_CKT05 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1135 |  | PS4-05-IG-0002_CKT06 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1136 |  | PS4-05-IG-0002_CKT07 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1137 |  | PS4-05-IG-0002_CKT08 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1138 |  | PS4-05-IG-0002_CKT09 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1139 |  | PS4-05-IG-0002_CKT10 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1140 |  | PS4-05-IG-0002_CKT11 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1141 |  | PS4-05-IG-0002_CKT12 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1142 |  | PS4-05-IG-0002_CKT13 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-14 - Office Building Emergency L&SP DB - PS4-05-IG-0002 |  | PS4-62-14 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1143 |  | PS4-05-IG-0007_CKT01 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-05 - Guard House Emergency L&SP DB - PS4-05-IG-0007 |  | PS4-62-05 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1144 |  | PS4-05-IG-0007_CKT02 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-05 - Guard House Emergency L&SP DB - PS4-05-IG-0007 |  | PS4-62-05 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1145 |  | PS4-05-IG-0007_CKT03 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-05 - Guard House Emergency L&SP DB - PS4-05-IG-0007 |  | PS4-62-05 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1146 |  | PS4-05-IG-0007_CKT04 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-05 - Guard House Emergency L&SP DB - PS4-05-IG-0007 |  | PS4-62-05 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1147 |  | PS4-05-IG-0014_CKT01 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-06 - CRO Generator Building Emergency Lighting DB - PS4-05-IG-0014 |  | PS4-62-06 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1148 |  | PS4-05-IG-0014_CKT02 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-06 - CRO Generator Building Emergency Lighting DB - PS4-05-IG-0014 |  | PS4-62-06 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1149 |  | PS4-05-IG-0014_CKT03 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-06 - CRO Generator Building Emergency Lighting DB - PS4-05-IG-0014 |  | PS4-62-06 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1150 |  | PS4-05-IG-0014_CKT04 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-06 - CRO Generator Building Emergency Lighting DB - PS4-05-IG-0014 |  | PS4-62-06 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1151 |  | PS4-05-IG-0014_CKT07 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-06 - CRO Generator Building Emergency Lighting DB - PS4-05-IG-0014 |  | PS4-62-06 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1152 |  | PS4-05-IG-0014_CKT08 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-06 - CRO Generator Building Emergency Lighting DB - PS4-05-IG-0014 |  | PS4-62-06 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1153 |  | PS4-05-IG-0014_CKT09 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-06 - CRO Generator Building Emergency Lighting DB - PS4-05-IG-0014 |  | PS4-62-06 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1154 |  | PS4-05-IG-0020_CKT01 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-07 - CRO Generator Electrical Building Emergency L&SP DB - PS4-05-IG-0020 |  | PS4-62-07 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1155 |  | PS4-05-IG-0020_CKT02 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-07 - CRO Generator Electrical Building Emergency L&SP DB - PS4-05-IG-0020 |  | PS4-62-07 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1156 |  | PS4-05-IG-0020_CKT03 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-07 - CRO Generator Electrical Building Emergency L&SP DB - PS4-05-IG-0020 |  | PS4-62-07 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1157 |  | PS4-05-IG-0020_CKT05 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-07 - CRO Generator Electrical Building Emergency L&SP DB - PS4-05-IG-0020 |  | PS4-62-07 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1158 |  | PS4-05-IG-0020_CKT06 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-07 - CRO Generator Electrical Building Emergency L&SP DB - PS4-05-IG-0020 |  | PS4-62-07 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1159 |  | PS4-05-IG-0020_CKT09 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-07 - CRO Generator Electrical Building Emergency L&SP DB - PS4-05-IG-0020 |  | PS4-62-07 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1160 |  | PS4-05-IG-0101_CKT01 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-19 - Workshop & Warehouse Emergency L&SP DB - PS4-05-IG-0101 |  | PS4-62-19 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1161 |  | PS4-05-IG-0101_CKT02 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-19 - Workshop & Warehouse Emergency L&SP DB - PS4-05-IG-0101 |  | PS4-62-19 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1162 |  | PS4-05-IG-0101_CKT03 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-19 - Workshop & Warehouse Emergency L&SP DB - PS4-05-IG-0101 |  | PS4-62-19 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1163 |  | PS4-05-IG-0101_CKT04 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-19 - Workshop & Warehouse Emergency L&SP DB - PS4-05-IG-0101 |  | PS4-62-19 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1164 |  | PS4-05-IG-0101_CKT05 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-19 - Workshop & Warehouse Emergency L&SP DB - PS4-05-IG-0101 |  | PS4-62-19 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1165 |  | PS4-05-IG-0101_CKT06 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-19 - Workshop & Warehouse Emergency L&SP DB - PS4-05-IG-0101 |  | PS4-62-19 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1166 |  | PS4-05-IG-0101_CKT07 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-19 - Workshop & Warehouse Emergency L&SP DB - PS4-05-IG-0101 |  | PS4-62-19 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1167 |  | PS4-05-IG-0101_CKT08 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-19 - Workshop & Warehouse Emergency L&SP DB - PS4-05-IG-0101 |  | PS4-62-19 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1168 |  | PS4-05-IG-0101_CKT09 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-19 - Workshop & Warehouse Emergency L&SP DB - PS4-05-IG-0101 |  | PS4-62-19 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1169 |  | PS4-05-IG-0101_CKT10 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-19 - Workshop & Warehouse Emergency L&SP DB - PS4-05-IG-0101 |  | PS4-62-19 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1170 |  | PS4-61-IG-0002_CKT01 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1171 |  | PS4-61-IG-0002_CKT02 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1172 |  | PS4-61-IG-0002_CKT03 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1173 |  | PS4-61-IG-0002_CKT04 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1174 |  | PS4-61-IG-0002_CKT05 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1175 |  | PS4-61-IG-0002_CKT06 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1176 |  | PS4-61-IG-0002_CKT07 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1177 |  | PS4-61-IG-0002_CKT08 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1178 |  | PS4-61-IG-0002_CKT09 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1179 |  | PS4-61-IG-0002_CKT10 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1180 |  | PS4-61-IG-0002_CKT11 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1181 |  | PS4-61-IG-0002_CKT12 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1182 |  | PS4-61-IG-0004_CKT01 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1183 |  | PS4-61-IG-0004_CKT02 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1184 |  | PS4-61-IG-0004_CKT03 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1185 |  | PS4-61-IG-0004_CKT04 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1186 |  | PS4-61-IG-0004_CKT05 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1187 |  | PS4-61-IG-0004_CKT06 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1188 |  | PS4-61-IG-0004_CKT08 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1189 |  | PS4-61-IG-0004_CKT09 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1190 |  | PS4-61-IG-0005_CKT09 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 |  | PS4-62-08 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1191 |  | PS4-61-IG-0005_CKT10 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 |  | PS4-62-08 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1192 |  | PS4-61-IG-0005_CKT11 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 |  | PS4-62-08 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1193 |  | PS4-61-IG-0005_CKT13 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 |  | PS4-62-08 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1194 |  | PS4-61-IG-0005_CKT15 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 |  | PS4-62-08 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1195 |  | PS4-61-IG-0005_CKT16 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 |  | PS4-62-08 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1196 |  | PS4-61-IG-0005_CKT17 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 |  | PS4-62-08 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1197 |  | PS4-61-IG-0005_CKT18 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 |  | PS4-62-08 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1198 |  | PS4-61-IG-0005_CKT19 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 |  | PS4-62-08 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1199 |  | PS4-61-IG-0007_CKT06 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 |  | PS4-62-09 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1200 |  | PS4-61-IG-0007_CKT09 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 |  | PS4-62-09 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1201 |  | PS4-61-IG-0007_CKT11 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 |  | PS4-62-09 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1202 |  | PS4-61-IG-0007_CKT12 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 |  | PS4-62-09 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1203 |  | PS4-61-IG-0007_CKT13 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 |  | PS4-62-09 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1204 |  | PS4-61-IG-0007_CKT15 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 |  | PS4-62-09 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1205 |  | PS4-61-IG-0007_CKT16 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 |  | PS4-62-09 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1206 |  | PS4-61-IG-0007_CKT18 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 |  | PS4-62-09 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1207 |  | PS4-61-IG-0007_CKT19 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 |  | PS4-62-09 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1208 |  | PS4-61-IG-0007_CKT20 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 |  | PS4-62-09 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1209 |  | PS4-61-IG-0009_CKT01 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-20 - Office Building Normal L&SP DB - PS4-61-IG-0009 |  | PS4-62-20 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1210 |  | PS4-61-IG-0009_CKT02 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-20 - Office Building Normal L&SP DB - PS4-61-IG-0009 |  | PS4-62-20 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1211 |  | PS4-61-IG-0009_CKT03 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-20 - Office Building Normal L&SP DB - PS4-61-IG-0009 |  | PS4-62-20 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1212 |  | PS4-61-IG-0010_CKT01 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-10 - CRO Generator Electrical Building Normal L&SP DB - PS4-61-IG-0010 |  | PS4-62-10 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1213 |  | PS4-61-IG-0010_CKT03 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-10 - CRO Generator Electrical Building Normal L&SP DB - PS4-61-IG-0010 |  | PS4-62-10 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1214 |  | PS4-61-IG-0010_CKT04 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-10 - CRO Generator Electrical Building Normal L&SP DB - PS4-61-IG-0010 |  | PS4-62-10 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1215 |  | PS4-61-IG-0010_CKT05 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-10 - CRO Generator Electrical Building Normal L&SP DB - PS4-61-IG-0010 |  | PS4-62-10 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1216 |  | PS4-61-IG-0010_CKT06 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-10 - CRO Generator Electrical Building Normal L&SP DB - PS4-61-IG-0010 |  | PS4-62-10 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1217 |  | PS4-61-IG-0030_CKT01 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1218 |  | PS4-61-IG-0030_CKT02 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1219 |  | PS4-61-IG-0030_CKT03 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1220 |  | PS4-61-IG-0030_CKT04 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1221 |  | PS4-61-IG-0030_CKT05 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1222 |  | PS4-61-IG-0030_CKT06 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1223 |  | PS4-61-IG-0030_CKT07 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1224 |  | PS4-61-IG-0030_CKT08 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1225 |  | PS4-61-IG-0030_CKT09 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1226 |  | PS4-61-IG-0030_CKT10 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1227 |  | PS4-61-IG-0030_CKT11 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1228 |  | PS4-61-IG-0030_CKT12 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1229 |  | PS4-61-IG-0030_CKT14 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1230 |  | PS4-61-IG-0030_CKT15 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone B | TM-00240
T-00240-1231 |  | PS4-61-IG-0111_CKT01 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-16 - Guard Hut A Normal L&SP DB - PS4-61-IG-0111 |  | PS4-62-16 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1232 |  | PS4-61-IG-0112_CKT01 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-17 - Guard Hut B Normal L&SP DB - PS4-61-IG-0112 |  | PS4-62-17 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone I | TM-00240
T-00240-1233 |  | PS4-62-IE-0001_CKT-KA01 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1234 |  | PS4-62-IE-0001_CKT-KA02 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1235 |  | PS4-62-IE-0001_CKT-KA03 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1236 |  | PS4-62-IE-0001_CKT-KA04 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1237 |  | PS4-62-IE-0001_CKT-KA05 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1238 |  | PS4-62-IE-0001_CKT-KA06 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1239 |  | PS4-62-IE-0001_CKT-KA07 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1240 |  | PS4-62-IE-0001_CKT-KA08 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1241 |  | PS4-62-IE-0001_CKT-KA09 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1242 |  | PS4-62-IE-0001_CKT-KA10 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1243 |  | PS4-62-IE-0001_CKT-KA11 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1244 |  | PS4-62-IE-0001_CKT-KA12 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1245 |  | PS4-62-IE-0001_CKT-KA13 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1246 |  | PS4-62-IE-0001_CKT-KB01 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1247 |  | PS4-62-IE-0001_CKT-KB04 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1248 |  | PS4-62-IE-0001_CKT-KB06 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-01 - Lighting Control Panel - PS4-62-IE-0001 |  | PS4-62-01 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1249 |  | PS4-62-IE-0002_CKT-KA01 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1250 |  | PS4-62-IE-0002_CKT-KA02 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1251 |  | PS4-62-IE-0002_CKT-KA03 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1252 |  | PS4-62-IE-0002_CKT-KA05 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1253 |  | PS4-62-IE-0002_CKT-KA06 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1254 |  | PS4-62-IE-0002_CKT-KA08 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1255 |  | PS4-62-IE-0002_CKT-KA11 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1256 |  | PS4-62-IE-0002_CKT-KA12 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1257 |  | PS4-62-IE-0002_CKT-KA13 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1258 |  | PS4-62-IE-0002_CKT-KA14 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1259 |  | PS4-62-IE-0002_CKT-KA15 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1260 |  | PS4-62-IE-0002_CKT-KA16 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1261 |  | PS4-62-IE-0002_CKT-KA17 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1262 |  | PS4-62-IE-0002_CKT-KB01 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00240-1263 |  | PS4-62-IE-0002_CKT-KB04 |  |  |  | TPX18 - Lighting circuits | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Lighting Circuits |  | To be completed | PS4 - Milestone G | TM-00240
T-00241-0163 | PS4-25-UD-3100A |  |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical | 5 pin 32A plug and socket for Oil Purifier Control Panel(Portable Load) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Power Sock Outlet | E | To be completed | PS4 - Milestone H | TM-00241
T-00241-0164 | PS4-28-ISO-2008 |  |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical | Socket Outlet 63A for mobile oil skimmer (PS4-28-UZ-8100) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-10 - Oil Skimmer Package |  | PS4-28-10 |  |  | Power Sock Outlet | E | To be completed | PS4 - Milestone I | TM-00241
T-00241-0386 |  | PS4-05-IG-0007_CKT07 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-05 - Guard House Emergency L&SP DB - PS4-05-IG-0007 |  | PS4-62-05 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0387 |  | PS4-05-IG-0007_CKT09 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-05 - Guard House Emergency L&SP DB - PS4-05-IG-0007 |  | PS4-62-05 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0388 |  | PS4-05-IG-0007_CKT13 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-05 - Guard House Emergency L&SP DB - PS4-05-IG-0007 |  | PS4-62-05 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0389 |  | PS4-05-IG-0007_CKT14 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-05 - Guard House Emergency L&SP DB - PS4-05-IG-0007 |  | PS4-62-05 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0390 |  | PS4-05-IG-0007_CKT15 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-05 - Guard House Emergency L&SP DB - PS4-05-IG-0007 |  | PS4-62-05 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0391 |  | PS4-06-GU-0101_CKT01 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-06-03 - AC UPS - Office & Facilities Building |  | PS4-06-03 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0392 |  | PS4-06-GU-0101_CKT02 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-06-03 - AC UPS - Office & Facilities Building |  | PS4-06-03 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0393 |  | PS4-06-GU-0101_CKT03 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-06-03 - AC UPS - Office & Facilities Building |  | PS4-06-03 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0394 |  | PS4-06-IG-0020_CKT12 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-06-05 - AC UPS - Workshop & Warehouse |  | PS4-06-05 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0395 |  | PS4-61-IG-0002_CKT13 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0396 |  | PS4-61-IG-0002_CKT14 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0397 |  | PS4-61-IG-0002_CKT15 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0398 |  | PS4-61-IG-0002_CKT16 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0399 |  | PS4-61-IG-0002_CKT17 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0400 |  | PS4-61-IG-0002_CKT18 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0401 |  | PS4-61-IG-0002_CKT19 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0402 |  | PS4-61-IG-0002_CKT20 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0403 |  | PS4-61-IG-0002_CKT21 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0404 |  | PS4-61-IG-0002_CKT22 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0405 |  | PS4-61-IG-0002_CKT23 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-15 - Office Building Normal L&SP DB - PS4-61-IG-0002 |  | PS4-62-15 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0406 |  | PS4-61-IG-0004_CKT10 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0407 |  | PS4-61-IG-0004_CKT11 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0408 |  | PS4-61-IG-0004_CKT12 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0409 |  | PS4-61-IG-0004_CKT13 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-18 - Workshop & Warehouse Normal L&SP DB - PS4-61-IG-0004 |  | PS4-62-18 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0410 |  | PS4-61-IG-0009_CKT04 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-20 - Office Building Normal L&SP DB - PS4-61-IG-0009 |  | PS4-62-20 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0411 |  | PS4-61-IG-0009_CKT05 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-20 - Office Building Normal L&SP DB - PS4-61-IG-0009 |  | PS4-62-20 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0412 |  | PS4-61-IG-0010_CKT07 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-10 - CRO Generator Electrical Building Normal L&SP DB - PS4-61-IG-0010 |  | PS4-62-10 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone B | TM-00241
T-00241-0413 |  | PS4-61-IG-0010_CKT08 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-10 - CRO Generator Electrical Building Normal L&SP DB - PS4-61-IG-0010 |  | PS4-62-10 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone B | TM-00241
T-00241-0414 |  | PS4-61-IG-0014_CKT01 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-08 - Outdoor Power Distribution Board - PS4-61-IG-0014 |  | PS4-61-08 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone G | TM-00241
T-00241-0415 |  | PS4-61-IG-0014_CKT02 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-08 - Outdoor Power Distribution Board - PS4-61-IG-0014 |  | PS4-61-08 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone G | TM-00241
T-00241-0416 |  | PS4-61-IG-0014_CKT03 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-08 - Outdoor Power Distribution Board - PS4-61-IG-0014 |  | PS4-61-08 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone G | TM-00241
T-00241-0417 |  | PS4-61-IG-0014_CKT04 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-08 - Outdoor Power Distribution Board - PS4-61-IG-0014 |  | PS4-61-08 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone G | TM-00241
T-00241-0418 |  | PS4-61-IG-0014_CKT05 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-08 - Outdoor Power Distribution Board - PS4-61-IG-0014 |  | PS4-61-08 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone G | TM-00241
T-00241-0419 |  | PS4-61-IG-0014_CKT06 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-08 - Outdoor Power Distribution Board - PS4-61-IG-0014 |  | PS4-61-08 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone G | TM-00241
T-00241-0420 |  | PS4-61-IG-0014_CKT08 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-08 - Outdoor Power Distribution Board - PS4-61-IG-0014 |  | PS4-61-08 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone G | TM-00241
T-00241-0421 |  | PS4-61-IG-0014_CKT11 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-08 - Outdoor Power Distribution Board - PS4-61-IG-0014 |  | PS4-61-08 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone G | TM-00241
T-00241-0422 |  | PS4-61-IG-0019_CKT15 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-13 - Power Distribution Board Workshop & Warehouse - PS4-61-IG-0019 |  | PS4-61-13 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0423 |  | PS4-61-IG-0019_CKT16 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-13 - Power Distribution Board Workshop & Warehouse - PS4-61-IG-0019 |  | PS4-61-13 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0424 |  | PS4-61-IG-0019_CKT17 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-13 - Power Distribution Board Workshop & Warehouse - PS4-61-IG-0019 |  | PS4-61-13 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0425 |  | PS4-61-IG-0019_CKT18 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-13 - Power Distribution Board Workshop & Warehouse - PS4-61-IG-0019 |  | PS4-61-13 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0426 |  | PS4-61-IG-0019_CKT19 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-13 - Power Distribution Board Workshop & Warehouse - PS4-61-IG-0019 |  | PS4-61-13 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0427 |  | PS4-61-IG-0019_CKT31 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-13 - Power Distribution Board Workshop & Warehouse - PS4-61-IG-0019 |  | PS4-61-13 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0428 |  | PS4-61-IG-0019_CKT32 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-13 - Power Distribution Board Workshop & Warehouse - PS4-61-IG-0019 |  | PS4-61-13 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0429 |  | PS4-61-IG-0019_CKT33 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-13 - Power Distribution Board Workshop & Warehouse - PS4-61-IG-0019 |  | PS4-61-13 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0430 |  | PS4-61-IG-0019_CKT34 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-13 - Power Distribution Board Workshop & Warehouse - PS4-61-IG-0019 |  | PS4-61-13 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0431 |  | PS4-61-IG-0030_CKT19 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone B | TM-00241
T-00241-0432 |  | PS4-61-IG-0030_CKT20 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone B | TM-00241
T-00241-0433 |  | PS4-61-IG-0030_CKT21 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone B | TM-00241
T-00241-0434 |  | PS4-61-IG-0111_CKT02 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-16 - Guard Hut A Normal L&SP DB - PS4-61-IG-0111 |  | PS4-62-16 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0435 |  | PS4-61-IG-0111_CKT03 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-16 - Guard Hut A Normal L&SP DB - PS4-61-IG-0111 |  | PS4-62-16 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0436 |  | PS4-61-IG-0112_CKT02 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-17 - Guard Hut B Normal L&SP DB - PS4-61-IG-0112 |  | PS4-62-17 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00241-0437 |  | PS4-61-IG-0112_CKT03 |  |  |  | TPX19 - Power socket outlet | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-17 - Guard Hut B Normal L&SP DB - PS4-61-IG-0112 |  | PS4-62-17 |  |  | Power Sock Outlet |  | To be completed | PS4 - Milestone I | TM-00241
T-00242-0050 | PS4-28-HE-2100 |  |  |  |  | TPX20 - Heater | PCOM - Precommissioning | E | Static Test | E - Electrical | CLOSED DRAIN DRUM HEATER 01 | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-67-WPR2-135401 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Heater | E | To be completed | PS4 - Milestone G | TM-00242
T-00242-0051 | PS4-28-HE-2200 |  |  |  |  | TPX20 - Heater | PCOM - Precommissioning | E | Static Test | E - Electrical | CLOSED DRAIN DRUM HEATER 02 | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-67-WPR2-135404 | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Heater | E | To be completed | PS4 - Milestone E | TM-00242
T-00242-0052 | PS4-71-HE-2200 |  |  |  |  | TPX20 - Heater | PCOM - Precommissioning | E | Static Test | E - Electrical | CRUDE FUEL OIL SERVICE TANK HEATER | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-67-WPR2-135003 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Heater | E | To be completed | PS4 - Milestone H | TM-00242
T-00242-0053 | PS4-71-HE-2300 |  |  |  |  | TPX20 - Heater | PCOM - Precommissioning | E | Static Test | E - Electrical | CRUDE FUEL OIL STORAGE TANK HEATER | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-67-WPR2-135000 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Heater | E | To be completed | PS4 - Milestone H | TM-00242
T-00242-0054 | PS4-71-HE-2400A |  |  |  |  | TPX20 - Heater | PCOM - Precommissioning | E | Static Test | E - Electrical | CRUDE FUEL OIL STORAGE TANK FEED HEATER | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Heater | E | To be completed | PS4 - Milestone H | TM-00242
T-00242-0055 | PS4-71-HE-2400B |  |  |  |  | TPX20 - Heater | PCOM - Precommissioning | E | Static Test | E - Electrical | CRUDE FUEL OIL STORAGE TANK FEED HEATER | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Heater | E | To be completed | PS4 - Milestone H | TM-00242
T-00242-0065 | PS4-25-HE-2100 |  |  |  |  | TPX20 - Heater | PCOM - Precommissioning | E | Static Test | E - Electrical | Crude Oil Export Pump Motor A - Lube Oil System Oil Reservoir Heater | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Heater | E | To be completed | PS4 - Milestone H | TM-00242
T-00242-0066 | PS4-25-HE-2200 |  |  |  |  | TPX20 - Heater | PCOM - Precommissioning | E | Static Test | E - Electrical | Crude Oil Export Pump Motor B - Lube Oil System Oil Reservoir Heater | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Heater | E | To be completed | PS4 - Milestone H | TM-00242
T-00242-0067 | PS4-25-HE-2300 |  |  |  |  | TPX20 - Heater | PCOM - Precommissioning | E | Static Test | E - Electrical | Crude Oil Export Pump Motor C - Lube Oil System Oil Reservoir Heater | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Heater | E | To be completed | PS4 - Milestone H | TM-00242
T-00243-0045 | PS4-61-NER-0010 |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | LLHT Transformer NER | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) |  | PS4-61-02 |  |  | Neutral Earthing Resistor | E | To be completed | PS4 - Milestone G | TM-00243
T-00243-0046 | PS4-63-NER-0010 |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing Transformer NER | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Neutral Earthing Resistor | E | To be completed | PS4 - Milestone D | TM-00243
T-00243-0047 | PS4-63-NER-0011 |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing Transformer NER | EACOP | CPP AGI |  |  | 6 |  |  | TZ-MID-67-SSF1-150259 | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Neutral Earthing Resistor | E | To be completed | PS4 - Milestone D | TM-00243
T-00243-0052 | PS4-60-IJ-0001A |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Neutral Grounding resistor for Generator set 1 (A) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A |  | PS4-60-01 |  |  | Neutral Earthing Resistor | E | Submitted | PS4 - Milestone B | TM-00243
T-00243-0053 | PS4-60-IJ-0001B |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Neutral Grounding resistor for Generator set 2 (B) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B |  | PS4-60-04 |  |  | Neutral Earthing Resistor | E | To be completed | PS4 - Milestone B | TM-00243
T-00243-0054 | PS4-60-IJ-0001C |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Neutral Grounding resistor for Generator set 3 (C) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Neutral Earthing Resistor | E | To be completed | PS4 - Milestone D | TM-00243
T-00243-0055 | PS4-60-IJ-0001D |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Neutral Grounding resistor for Generator set 4 (D) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Neutral Earthing Resistor | E | To be completed | PS4 - Milestone D | TM-00243
T-00243-0056 | PS4-60-IJ-0001E |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Neutral Grounding resistor for Generator set 5 (E) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Neutral Earthing Resistor | E | To be completed | PS4 - Milestone D | TM-00243
T-00243-0057 | PS4-60-IJ-0001F |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Neutral Grounding resistor for Generator set 6 (F) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Neutral Earthing Resistor | E | To be completed | PS4 - Milestone D | TM-00243
T-00243-0058 | PS4-60-IJ-0001G |  |  |  |  | TPX21 - Neutral earthing resistor | PCOM - Precommissioning | E | Static Test | E - Electrical | Neutral Grounding resistor for Generator set 7 (G) | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Neutral Earthing Resistor | E | To be completed | PS4 - Milestone E | TM-00243
T-00244-0991 |  | PS4-79-IG-0001_CKT01 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-0992 |  | PS4-79-IG-0001_CKT02 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-0993 |  | PS4-79-IG-0001_CKT03 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-0994 |  | PS4-79-IG-0001_CKT04 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-0995 |  | PS4-79-IG-0001_CKT05 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-0996 |  | PS4-79-IG-0001_CKT06 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-0997 |  | PS4-79-IG-0001_CKT07 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-0998 |  | PS4-79-IG-0001_CKT08 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-0999 |  | PS4-79-IG-0001_CKT09 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1000 |  | PS4-79-IG-0001_CKT10 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1001 |  | PS4-79-IG-0001_CKT11 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1002 |  | PS4-79-IG-0001_CKT12 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1003 |  | PS4-79-IG-0001_CKT13 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1004 |  | PS4-79-IG-0001_CKT14 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1005 |  | PS4-79-IG-0001_CKT15 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1006 |  | PS4-79-IG-0001_CKT16 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1007 |  | PS4-79-IG-0001_CKT17 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1008 |  | PS4-79-IG-0001_CKT18 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1009 |  | PS4-79-IG-0001_CKT19 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1010 |  | PS4-79-IG-0001_CKT20 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1011 |  | PS4-79-IG-0001_CKT21 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1012 |  | PS4-79-IG-0001_CKT22 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1013 |  | PS4-79-IG-0001_CKT23 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1014 |  | PS4-79-IG-0001_CKT24 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1015 |  | PS4-79-IG-0001_CKT25 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1016 |  | PS4-79-IG-0001_CKT26 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1017 |  | PS4-79-IG-0001_CKT27 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1018 |  | PS4-79-IG-0001_CKT28 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1019 |  | PS4-79-IG-0001_CKT31 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1020 |  | PS4-79-IG-0002_CKT01 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1021 |  | PS4-79-IG-0002_CKT02 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1022 |  | PS4-79-IG-0002_CKT03 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1023 |  | PS4-79-IG-0002_CKT04 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1024 |  | PS4-79-IG-0002_CKT05 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1025 |  | PS4-79-IG-0002_CKT06 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1026 |  | PS4-79-IG-0002_CKT07 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1027 |  | PS4-79-IG-0002_CKT08 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1028 |  | PS4-79-IG-0002_CKT09 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1029 |  | PS4-79-IG-0002_CKT10 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1030 |  | PS4-79-IG-0002_CKT11 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1031 |  | PS4-79-IG-0002_CKT12 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1032 |  | PS4-79-IG-0002_CKT13 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1033 |  | PS4-79-IG-0002_CKT14 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1034 |  | PS4-79-IG-0002_CKT15 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1035 |  | PS4-79-IG-0002_CKT16 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1036 |  | PS4-79-IG-0002_CKT17 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1037 |  | PS4-79-IG-0002_CKT18 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1038 |  | PS4-79-IG-0002_CKT19 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1039 |  | PS4-79-IG-0002_CKT20 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1040 |  | PS4-79-IG-0002_CKT21 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1041 |  | PS4-79-IG-0002_CKT22 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1042 |  | PS4-79-IG-0002_CKT23 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1043 |  | PS4-79-IG-0002_CKT24 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1044 |  | PS4-79-IG-0002_CKT25 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1045 |  | PS4-79-IG-0002_CKT26 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1046 |  | PS4-79-IG-0002_CKT27 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1047 |  | PS4-79-IG-0002_CKT28 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1048 |  | PS4-79-IG-0002_CKT29 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1049 |  | PS4-79-IG-0002_CKT31 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1050 |  | PS4-79-IG-0003_CKT01 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1051 |  | PS4-79-IG-0003_CKT02 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1052 |  | PS4-79-IG-0003_CKT03 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1053 |  | PS4-79-IG-0003_CKT04 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1054 |  | PS4-79-IG-0003_CKT05 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1055 |  | PS4-79-IG-0003_CKT06 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1056 |  | PS4-79-IG-0003_CKT07 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1057 |  | PS4-79-IG-0003_CKT08 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1058 |  | PS4-79-IG-0003_CKT09 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1059 |  | PS4-79-IG-0003_CKT10 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1060 |  | PS4-79-IG-0003_CKT11 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1061 |  | PS4-79-IG-0003_CKT12 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1062 |  | PS4-79-IG-0003_CKT13 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1063 |  | PS4-79-IG-0003_CKT14 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1064 |  | PS4-79-IG-0003_CKT15 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1065 |  | PS4-79-IG-0003_CKT16 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1066 |  | PS4-79-IG-0003_CKT17 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1067 |  | PS4-79-IG-0003_CKT18 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1068 |  | PS4-79-IG-0003_CKT19 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1069 |  | PS4-79-IG-0003_CKT20 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1070 |  | PS4-79-IG-0003_CKT21 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1071 |  | PS4-79-IG-0003_CKT22 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1072 |  | PS4-79-IG-0003_CKT23 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1073 |  | PS4-79-IG-0003_CKT24 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1074 |  | PS4-79-IG-0003_CKT25 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1075 |  | PS4-79-IG-0003_CKT26 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1076 |  | PS4-79-IG-0003_CKT27 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1077 |  | PS4-79-IG-0003_CKT28 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1078 |  | PS4-79-IG-0003_CKT31 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1079 |  | PS4-79-IG-0004_CKT01 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1080 |  | PS4-79-IG-0004_CKT02 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1081 |  | PS4-79-IG-0004_CKT03 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1082 |  | PS4-79-IG-0004_CKT04 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1083 |  | PS4-79-IG-0004_CKT05 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1084 |  | PS4-79-IG-0004_CKT06 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1085 |  | PS4-79-IG-0004_CKT07 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1086 |  | PS4-79-IG-0004_CKT08 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1087 |  | PS4-79-IG-0004_CKT09 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1088 |  | PS4-79-IG-0004_CKT10 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1089 |  | PS4-79-IG-0004_CKT11 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1090 |  | PS4-79-IG-0004_CKT12 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1091 |  | PS4-79-IG-0004_CKT13 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1092 |  | PS4-79-IG-0004_CKT14 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1093 |  | PS4-79-IG-0004_CKT15 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1094 |  | PS4-79-IG-0004_CKT16 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1095 |  | PS4-79-IG-0004_CKT17 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1096 |  | PS4-79-IG-0004_CKT18 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1097 |  | PS4-79-IG-0004_CKT19 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1098 |  | PS4-79-IG-0004_CKT20 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1099 |  | PS4-79-IG-0004_CKT21 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1100 |  | PS4-79-IG-0004_CKT22 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1101 |  | PS4-79-IG-0004_CKT23 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1102 |  | PS4-79-IG-0004_CKT24 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1103 |  | PS4-79-IG-0004_CKT25 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1104 |  | PS4-79-IG-0004_CKT26 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1105 |  | PS4-79-IG-0004_CKT28 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1106 |  | PS4-79-IG-0005_CKT01 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1107 |  | PS4-79-IG-0005_CKT02 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1108 |  | PS4-79-IG-0005_CKT03 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1109 |  | PS4-79-IG-0005_CKT04 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1110 |  | PS4-79-IG-0005_CKT05 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1111 |  | PS4-79-IG-0005_CKT06 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1112 |  | PS4-79-IG-0005_CKT07 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1113 |  | PS4-79-IG-0005_CKT08 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1114 |  | PS4-79-IG-0005_CKT09 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1115 |  | PS4-79-IG-0005_CKT10 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1116 |  | PS4-79-IG-0005_CKT11 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1117 |  | PS4-79-IG-0005_CKT12 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1118 |  | PS4-79-IG-0005_CKT13 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1119 |  | PS4-79-IG-0005_CKT14 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1120 |  | PS4-79-IG-0005_CKT15 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1121 |  | PS4-79-IG-0005_CKT16 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1122 |  | PS4-79-IG-0005_CKT17 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1123 |  | PS4-79-IG-0005_CKT18 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1124 |  | PS4-79-IG-0005_CKT19 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1125 |  | PS4-79-IG-0005_CKT20 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1126 |  | PS4-79-IG-0005_CKT21 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1127 |  | PS4-79-IG-0005_CKT22 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1128 |  | PS4-79-IG-0005_CKT23 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1129 |  | PS4-79-IG-0005_CKT24 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1130 |  | PS4-79-IG-0005_CKT25 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1131 |  | PS4-79-IG-0005_CKT26 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1132 |  | PS4-79-IG-0005_CKT27 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1133 |  | PS4-79-IG-0005_CKT28 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1134 |  | PS4-79-IG-0006_CKT01 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1135 |  | PS4-79-IG-0006_CKT02 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1136 |  | PS4-79-IG-0006_CKT03 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1137 |  | PS4-79-IG-0006_CKT04 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1138 |  | PS4-79-IG-0006_CKT05 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1139 |  | PS4-79-IG-0006_CKT06 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1140 |  | PS4-79-IG-0006_CKT07 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1141 |  | PS4-79-IG-0006_CKT08 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1142 |  | PS4-79-IG-0006_CKT09 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1143 |  | PS4-79-IG-0006_CKT10 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1144 |  | PS4-79-IG-0006_CKT11 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1145 |  | PS4-79-IG-0006_CKT12 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1146 |  | PS4-79-IG-0006_CKT13 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1147 |  | PS4-79-IG-0006_CKT14 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1148 |  | PS4-79-IG-0006_CKT15 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1149 |  | PS4-79-IG-0006_CKT16 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1150 |  | PS4-79-IG-0006_CKT17 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1151 |  | PS4-79-IG-0006_CKT18 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1152 |  | PS4-79-IG-0006_CKT19 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1153 |  | PS4-79-IG-0006_CKT20 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1154 |  | PS4-79-IG-0006_CKT21 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1155 |  | PS4-79-IG-0006_CKT22 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1156 |  | PS4-79-IG-0006_CKT23 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1157 |  | PS4-79-IG-0006_CKT24 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1158 |  | PS4-79-IG-0006_CKT25 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1159 |  | PS4-79-IG-0006_CKT26 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1160 |  | PS4-79-IG-0006_CKT27 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1161 |  | PS4-79-IG-0006_CKT28 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1162 |  | PS4-79-IG-0006_CKT29 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1163 |  | PS4-79-IG-0006_CKT30 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1164 |  | PS4-79-IG-0006_CKT31 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1165 |  | PS4-79-IG-0006_CKT34 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1166 |  | PS4-79-IG-0007_CKT01 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1167 |  | PS4-79-IG-0007_CKT02 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1168 |  | PS4-79-IG-0007_CKT03 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1169 |  | PS4-79-IG-0007_CKT04 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1170 |  | PS4-79-IG-0007_CKT05 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1171 |  | PS4-79-IG-0007_CKT06 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1172 |  | PS4-79-IG-0007_CKT07 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1173 |  | PS4-79-IG-0007_CKT08 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1174 |  | PS4-79-IG-0007_CKT09 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1175 |  | PS4-79-IG-0007_CKT10 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1176 |  | PS4-79-IG-0007_CKT11 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1177 |  | PS4-79-IG-0007_CKT12 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1178 |  | PS4-79-IG-0007_CKT13 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1179 |  | PS4-79-IG-0007_CKT14 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1180 |  | PS4-79-IG-0007_CKT15 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1181 |  | PS4-79-IG-0007_CKT16 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1182 |  | PS4-79-IG-0007_CKT17 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1183 |  | PS4-79-IG-0007_CKT18 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1184 |  | PS4-79-IG-0007_CKT19 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1185 |  | PS4-79-IG-0007_CKT20 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1186 |  | PS4-79-IG-0007_CKT21 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1187 |  | PS4-79-IG-0007_CKT22 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1188 |  | PS4-79-IG-0007_CKT23 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1189 |  | PS4-79-IG-0007_CKT24 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1190 |  | PS4-79-IG-0007_CKT25 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1191 |  | PS4-79-IG-0007_CKT26 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1192 |  | PS4-79-IG-0007_CKT27 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1193 |  | PS4-79-IG-0007_CKT28 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1194 |  | PS4-79-IG-0007_CKT29 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1195 |  | PS4-79-IG-0007_CKT30 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1196 |  | PS4-79-IG-0007_CKT31 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1197 |  | PS4-79-IG-0007_CKT40 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1198 |  | PS4-79-IG-0008_CKT01 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1199 |  | PS4-79-IG-0008_CKT02 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1200 |  | PS4-79-IG-0008_CKT03 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1201 |  | PS4-79-IG-0008_CKT04 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1202 |  | PS4-79-IG-0008_CKT05 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1203 |  | PS4-79-IG-0008_CKT06 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1204 |  | PS4-79-IG-0008_CKT07 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1205 |  | PS4-79-IG-0008_CKT08 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1206 |  | PS4-79-IG-0008_CKT09 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1207 |  | PS4-79-IG-0008_CKT10 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1208 |  | PS4-79-IG-0008_CKT11 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1209 |  | PS4-79-IG-0008_CKT12 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1210 |  | PS4-79-IG-0008_CKT13 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1211 |  | PS4-79-IG-0008_CKT14 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1212 |  | PS4-79-IG-0008_CKT15 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1213 |  | PS4-79-IG-0008_CKT16 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1214 |  | PS4-79-IG-0008_CKT17 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1215 |  | PS4-79-IG-0008_CKT18 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1216 |  | PS4-79-IG-0008_CKT19 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1217 |  | PS4-79-IG-0008_CKT20 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1218 |  | PS4-79-IG-0008_CKT21 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1219 |  | PS4-79-IG-0008_CKT22 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1220 |  | PS4-79-IG-0008_CKT23 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1221 |  | PS4-79-IG-0008_CKT24 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1222 |  | PS4-79-IG-0008_CKT25 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1223 |  | PS4-79-IG-0008_CKT26 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1224 |  | PS4-79-IG-0008_CKT27 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1225 |  | PS4-79-IG-0008_CKT28 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1226 |  | PS4-79-IG-0008_CKT29 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1227 |  | PS4-79-IG-0008_CKT30 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1228 |  | PS4-79-IG-0008_CKT31 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1229 |  | PS4-79-IG-0008_CKT40 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1230 |  | PS4-79-IG-0009_CKT01 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1231 |  | PS4-79-IG-0009_CKT02 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1232 |  | PS4-79-IG-0009_CKT03 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1233 |  | PS4-79-IG-0009_CKT04 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1234 |  | PS4-79-IG-0009_CKT05 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1235 |  | PS4-79-IG-0009_CKT06 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1236 |  | PS4-79-IG-0009_CKT07 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1237 |  | PS4-79-IG-0009_CKT08 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1238 |  | PS4-79-IG-0009_CKT09 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1239 |  | PS4-79-IG-0009_CKT10 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1240 |  | PS4-79-IG-0009_CKT11 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1241 |  | PS4-79-IG-0009_CKT12 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1242 |  | PS4-79-IG-0009_CKT13 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1243 |  | PS4-79-IG-0009_CKT14 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1244 |  | PS4-79-IG-0009_CKT15 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1245 |  | PS4-79-IG-0009_CKT16 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1246 |  | PS4-79-IG-0009_CKT17 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1247 |  | PS4-79-IG-0009_CKT18 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1248 |  | PS4-79-IG-0009_CKT19 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1249 |  | PS4-79-IG-0009_CKT20 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1250 |  | PS4-79-IG-0009_CKT21 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1251 |  | PS4-79-IG-0009_CKT22 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1252 |  | PS4-79-IG-0009_CKT23 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1253 |  | PS4-79-IG-0009_CKT24 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1254 |  | PS4-79-IG-0009_CKT25 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1255 |  | PS4-79-IG-0009_CKT26 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1256 |  | PS4-79-IG-0009_CKT27 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1257 |  | PS4-79-IG-0009_CKT28 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1258 |  | PS4-79-IG-0009_CKT29 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1259 |  | PS4-79-IG-0009_CKT30 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1260 |  | PS4-79-IG-0009_CKT31 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1261 |  | PS4-79-IG-0009_CKT40 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1262 |  | PS4-79-IG-0010_CKT01 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1263 |  | PS4-79-IG-0010_CKT02 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1264 |  | PS4-79-IG-0010_CKT03 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1265 |  | PS4-79-IG-0010_CKT04 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1266 |  | PS4-79-IG-0010_CKT05 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1267 |  | PS4-79-IG-0010_CKT06 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1268 |  | PS4-79-IG-0010_CKT07 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1269 |  | PS4-79-IG-0010_CKT08 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1270 |  | PS4-79-IG-0010_CKT09 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1271 |  | PS4-79-IG-0010_CKT10 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1272 |  | PS4-79-IG-0010_CKT11 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1273 |  | PS4-79-IG-0010_CKT12 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1274 |  | PS4-79-IG-0010_CKT13 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1275 |  | PS4-79-IG-0010_CKT14 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1276 |  | PS4-79-IG-0010_CKT15 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1277 |  | PS4-79-IG-0010_CKT16 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1278 |  | PS4-79-IG-0010_CKT17 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1279 |  | PS4-79-IG-0010_CKT18 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1280 |  | PS4-79-IG-0010_CKT19 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1281 |  | PS4-79-IG-0010_CKT20 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1282 |  | PS4-79-IG-0010_CKT21 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1283 |  | PS4-79-IG-0010_CKT22 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1284 |  | PS4-79-IG-0010_CKT23 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1285 |  | PS4-79-IG-0010_CKT24 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1286 |  | PS4-79-IG-0010_CKT25 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1287 |  | PS4-79-IG-0010_CKT26 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1288 |  | PS4-79-IG-0010_CKT27 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1289 |  | PS4-79-IG-0010_CKT28 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1290 |  | PS4-79-IG-0010_CKT29 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1291 |  | PS4-79-IG-0010_CKT31 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1292 |  | PS4-79-IG-0011_CKT01 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1293 |  | PS4-79-IG-0011_CKT02 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1294 |  | PS4-79-IG-0011_CKT03 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1295 |  | PS4-79-IG-0011_CKT04 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1296 |  | PS4-79-IG-0011_CKT05 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1297 |  | PS4-79-IG-0011_CKT06 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1298 |  | PS4-79-IG-0011_CKT07 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1299 |  | PS4-79-IG-0011_CKT08 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1300 |  | PS4-79-IG-0011_CKT09 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1301 |  | PS4-79-IG-0011_CKT10 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1302 |  | PS4-79-IG-0011_CKT11 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1303 |  | PS4-79-IG-0011_CKT12 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1304 |  | PS4-79-IG-0011_CKT13 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1305 |  | PS4-79-IG-0011_CKT14 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1306 |  | PS4-79-IG-0011_CKT15 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1307 |  | PS4-79-IG-0011_CKT16 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1308 |  | PS4-79-IG-0011_CKT17 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1309 |  | PS4-79-IG-0011_CKT18 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1310 |  | PS4-79-IG-0011_CKT19 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1311 |  | PS4-79-IG-0011_CKT20 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1312 |  | PS4-79-IG-0011_CKT21 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1313 |  | PS4-79-IG-0011_CKT22 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1314 |  | PS4-79-IG-0011_CKT23 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1315 |  | PS4-79-IG-0011_CKT24 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1316 |  | PS4-79-IG-0011_CKT25 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1317 |  | PS4-79-IG-0011_CKT26 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1318 |  | PS4-79-IG-0011_CKT27 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1319 |  | PS4-79-IG-0011_CKT28 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1320 |  | PS4-79-IG-0011_CKT29 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1321 |  | PS4-79-IG-0011_CKT30 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1322 |  | PS4-79-IG-0012_CKT01 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1323 |  | PS4-79-IG-0012_CKT02 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1324 |  | PS4-79-IG-0012_CKT03 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1325 |  | PS4-79-IG-0012_CKT04 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1326 |  | PS4-79-IG-0012_CKT05 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1327 |  | PS4-79-IG-0012_CKT06 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1328 |  | PS4-79-IG-0012_CKT07 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1329 |  | PS4-79-IG-0012_CKT08 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1330 |  | PS4-79-IG-0012_CKT09 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1331 |  | PS4-79-IG-0012_CKT10 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1332 |  | PS4-79-IG-0012_CKT11 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1333 |  | PS4-79-IG-0012_CKT12 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1334 |  | PS4-79-IG-0012_CKT13 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1335 |  | PS4-79-IG-0012_CKT14 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1336 |  | PS4-79-IG-0012_CKT15 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1337 |  | PS4-79-IG-0012_CKT16 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1338 |  | PS4-79-IG-0012_CKT17 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1339 |  | PS4-79-IG-0012_CKT18 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1340 |  | PS4-79-IG-0012_CKT19 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1341 |  | PS4-79-IG-0012_CKT20 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1342 |  | PS4-79-IG-0012_CKT21 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1343 |  | PS4-79-IG-0012_CKT22 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1344 |  | PS4-79-IG-0012_CKT23 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1345 |  | PS4-79-IG-0012_CKT24 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1346 |  | PS4-79-IG-0012_CKT25 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1347 |  | PS4-79-IG-0012_CKT26 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1348 |  | PS4-79-IG-0012_CKT27 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1349 |  | PS4-79-IG-0012_CKT28 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1350 |  | PS4-79-IG-0012_CKT29 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1351 |  | PS4-79-IG-0012_CKT30 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1352 |  | PS4-79-IG-0012_CKT31 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1353 |  | PS4-79-IG-0012_CKT32 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1354 |  | PS4-79-IG-0012_CKT33 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1355 |  | PS4-79-IG-0012_CKT34 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00244-1356 |  | PS4-79-IG-0012_CKT37 |  |  |  | TPX22 - Tape Trace Heating | PCOM - Precommissioning | E | Static Test | E - Electrical |  | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  | Tape Trace Heating |  | To be completed | PS4 - Milestone H | TM-00244
T-00247-0102 | PS4 - CFO AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  | 10 | TZ-MID-67-WPR2-151156 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0103 | PS4 - CHEMICAL AND WASTE STORAGE AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151146 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0104 | PS4 - CLOSED DRAIN DRUM AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  | 10 | TZ-MID-67-WPR2-151158 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0105 | PS4 - DIESEL FUEL STORAGE AND PUMP AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151148 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0106 | PS4 - FENCE EAST AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151161 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0107 | PS4 - FENCE SOUTH EAST AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151163 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0108 | PS4 - FENCE SOUTH WEST AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151162 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0109 | PS4 - FENCE WEST AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151160 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0110 | PS4 - LAUNCHER/RECEIVER AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151154 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0111 | PS4 - LOADING PUMP AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151155 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0112 | PS4 - OBSERVATION BASIN AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151151 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0113 | PS4 - POWER DISTRIBUTION AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151153 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing | 2026-02-13 07:57 | PS4-63-01 |  |  | Earthing System | E | Closed | PS4 - Milestone A | TM-00247 | tereshchenko, nikolai
T-00247-0114 | PS4 - POWER GENERATION BUILDING AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151157 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0115 | PS4 - POWER GENERATION COOLING TOWER AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151159 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0116 | PS4 - PUMP VSD AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  | 10 | TZ-MID-67-WPR2-151152 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0117 | PS4 - TURNSTILE GATE AND OFFICE BUILDING AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151147 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0118 | PS4 - UTILITY AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151149 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0119 | PS4 - UTILITY/FIRE WATER STORAGE TANK AREA_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151150 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0120 | PS4-82-OB-0001_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing for Office and Facilities building | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-CPP1-150005 | PS4 - TZA - PS4 - Tanzania | PS4-63-02 - Electrical Earthing - Office and Facilities building |  | PS4-63-02 |  |  | Earthing System | E | To be completed | PS4 - Milestone I | TM-00247
T-00247-0121 | PS4-82-OB-0005_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing for Guard House | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151183 | PS4 - TZA - PS4 - Tanzania | PS4-63-06 - Electrical Earthing - Guard House |  | PS4-63-06 |  |  | Earthing System | E | To be completed | PS4 - Milestone I | TM-00247
T-00247-0122 | PS4-82-OB-0009A_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing for Guard Hut A | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-CPP1-150012 | PS4 - TZA - PS4 - Tanzania | PS4-63-05 - Electrical Earthing - Guard Hut A & B |  | PS4-63-05 |  |  | Earthing System | E | To be completed | PS4 - Milestone I | TM-00247
T-00247-0123 | PS4-82-OB-0009B_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing for Guard Hut B | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-CPP1-150019 | PS4 - TZA - PS4 - Tanzania | PS4-63-05 - Electrical Earthing - Guard Hut A & B |  | PS4-63-05 |  |  | Earthing System | E | To be completed | PS4 - Milestone I | TM-00247
T-00247-0124 | PS4-84-OB-0001_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing for Workshop & Warehouse | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-CPP1-150026 | PS4 - TZA - PS4 - Tanzania | PS4-63-07 - Electrical Earthing - Workshop & Warehouse |  | PS4-63-07 |  |  | Earthing System | E | To be completed | PS4 - Milestone I | TM-00247
T-00247-0125 | PS4-84-OB-0003_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing for Hazardous Waste Shelter | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151187 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0126 | PS4-84-OB-0004_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing for Non-Hazardous Waste Shelter | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151187 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0127 | PS4-84-OB-0005_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing for Generator Electrical Building | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151185 | PS4 - TZA - PS4 - Tanzania | PS4-63-03 - Electrical Earthing - Generator Building |  | PS4-63-03 |  |  | Earthing System | E | To be completed | PS4 - Milestone B | TM-00247
T-00247-0128 | PS4-84-OB-0006_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing for Chemical Storage Shelter | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151187 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0129 | PS4-84-OB-0007_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing for Chemical Waste Storage Shelter | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151187 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0130 | PS4-86-OB-0001_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing for Closed Drain Drum Shelter | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151189 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0131 | PS4-86-OB-0002_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing for Relief Drain Drum Shelter | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151191 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0132 | PS4-86-OB-0003_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing for Fire Water Pump Shelter | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151193 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00247-0133 | PS4-86-OB-0004_Earthing |  |  |  |  | TPX26 - Earthing system | PCOM - Precommissioning | E | Static Test | E - Electrical | Earthing for Closed Drain Drum Shelter | EACOP | CPP AGI |  |  | 10 |  |  | TZ-MID-67-WPR2-151195 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Earthing System | E | To be completed | PS4 - Milestone A | TM-00247
T-00248-0038 | PS4 - RECEIVER AND LAUNCHER AREA_Lightning |  |  |  |  | TPX28 - Lightning protection system | PCOM - Precommissioning | E | Static Test | E - Electrical | Lightning | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-151613 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone A | TM-00248
T-00248-0039 | PS4-82-OB-0001_Lightning |  |  |  |  | TPX28 - Lightning protection system | PCOM - Precommissioning | E | Static Test | E - Electrical | Lightning for Office and Facilities building | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-150006 | PS4 - TZA - PS4 - Tanzania | PS4-63-02 - Electrical Earthing - Office and Facilities building |  | PS4-63-02 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone I | TM-00248
T-00248-0040 | PS4-82-OB-0005_Lightning |  |  |  |  | TPX28 - Lightning protection system | PCOM - Precommissioning | E | Static Test | E - Electrical | Lightning for Guard House | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-151197 | PS4 - TZA - PS4 - Tanzania | PS4-63-06 - Electrical Earthing - Guard House |  | PS4-63-06 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone I | TM-00248
T-00248-0041 | PS4-82-OB-0009A_Lightning |  |  |  |  | TPX28 - Lightning protection system | PCOM - Precommissioning | E | Static Test | E - Electrical | Lightning for Guard Hut A | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-150013 | PS4 - TZA - PS4 - Tanzania | PS4-63-05 - Electrical Earthing - Guard Hut A & B |  | PS4-63-05 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone I | TM-00248
T-00248-0042 | PS4-82-OB-0009B_Ligthning |  |  |  |  | TPX28 - Lightning protection system | PCOM - Precommissioning | E | Static Test | E - Electrical | Lightning for Guard Hut B | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-150020 | PS4 - TZA - PS4 - Tanzania | PS4-63-05 - Electrical Earthing - Guard Hut A & B |  | PS4-63-05 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone I | TM-00248
T-00248-0043 | PS4-84-OB-0001_Lightning |  |  |  |  | TPX28 - Lightning protection system | PCOM - Precommissioning | E | Static Test | E - Electrical | Lightning for Workshop & Warehouse | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-CPP1-150027 | PS4 - TZA - PS4 - Tanzania | PS4-63-07 - Electrical Earthing - Workshop & Warehouse |  | PS4-63-07 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone I | TM-00248
T-00248-0044 | PS4-84-OB-0003_Lightning |  |  |  |  | TPX28 - Lightning protection system | PCOM - Precommissioning | E | Static Test | E - Electrical | Lightning for Hazardous Waste Shelter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-151199 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone A | TM-00248
T-00248-0045 | PS4-84-OB-0005_Lightning |  |  |  |  | TPX28 - Lightning protection system | PCOM - Precommissioning | E | Static Test | E - Electrical | Lightning for Generator Electrical Building | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-151198 | PS4 - TZA - PS4 - Tanzania | PS4-63-03 - Electrical Earthing - Generator Building |  | PS4-63-03 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone B | TM-00248
T-00248-0046 | PS4-84-OB-0006_Lightning |  |  |  |  | TPX28 - Lightning protection system | PCOM - Precommissioning | E | Static Test | E - Electrical | Lightning for Chemical Storage Shelter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-151601 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone A | TM-00248
T-00248-0047 | PS4-84-OB-0007_Lightning |  |  |  |  | TPX28 - Lightning protection system | PCOM - Precommissioning | E | Static Test | E - Electrical | Lightning for Chemical Waste Storage Shelter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-151601 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone A | TM-00248
T-00248-0048 | PS4-86-OB-0001_Lightning |  |  |  |  | TPX28 - Lightning protection system | PCOM - Precommissioning | E | Static Test | E - Electrical | Lightning for Closed Drain Drum Shelter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-151603 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone A | TM-00248
T-00248-0049 | PS4-86-OB-0002_Lightning |  |  |  |  | TPX28 - Lightning protection system | PCOM - Precommissioning | E | Static Test | E - Electrical | Lightning for Relief Drain Drum Shelter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-151604 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone A | TM-00248
T-00248-0050 | PS4-86-OB-0003_Lightning |  |  |  |  | TPX28 - Lightning protection system | PCOM - Precommissioning | E | Static Test | E - Electrical | Lightning for Fire Water Pump Shelter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-151605 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone A | TM-00248
T-00248-0051 | PS4-86-OB-0004_Lightning |  |  |  |  | TPX28 - Lightning protection system | PCOM - Precommissioning | E | Static Test | E - Electrical | Lightning for Closed Drain Drum Shelter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-151606 | PS4 - TZA - PS4 - Tanzania | PS4-63-01 - Electrical Earthing |  | PS4-63-01 |  |  | Lighting Protection System | E | To be completed | PS4 - Milestone A | TM-00248
T-00249-0004 | PS4-53-TR-4100 |  |  |  |  | TPX33 - Cathodic protection | PCOM - Precommissioning | E | Static Test | E - Electrical | UTILITY WATER / FIRE WATER STORAGE TANK | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-FZC2-180013 | PS4 - TZA - PS4 - Tanzania | PS4-53-01 - Utility Water / Storage Tank |  | PS4-53-01 |  |  | Cathodic Protection | P | To be completed | PS4 - Milestone C | TM-00249
T-00249-0005 | PS4-71-TR-4100 |  |  |  |  | TPX33 - Cathodic protection | PCOM - Precommissioning | E | Static Test | E - Electrical | CRUDE FUEL OIL STORAGE TANK | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-FZC2-180096 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Cathodic Protection | P | To be completed | PS4 - Milestone H | TM-00249
T-00249-0006 | PS4-71-TR-4200 |  |  |  |  | TPX33 - Cathodic protection | PCOM - Precommissioning | E | Static Test | E - Electrical | CRUDE FUEL OIL SERVICE TANK | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-FZC2-180095 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Cathodic Protection | P | To be completed | PS4 - Milestone H | TM-00249
T-00249-0007 | PS4-71-TR-4400 |  |  |  |  | TPX33 - Cathodic protection | PCOM - Precommissioning | E | Static Test | E - Electrical | DIESEL FUEL STORAGE TANK | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-FZC2-180029 | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank |  | PS4-71-15 |  |  | Cathodic Protection | P | To be completed | PS4 - Milestone F | TM-00249
T-00251-0145 | PS4-25-PSV-1103 |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00251
T-00251-0146 | PS4-25-PSV-1203 |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00251
T-00251-0147 | PS4-28-PRV-0008 |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Relief Valve | I | To be completed | PS4 - Milestone G | TM-00251
T-00251-0148 | PS4-28-PRV-0040 |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Relief Valve | I | To be completed | PS4 - Milestone G | TM-00251
T-00251-0149 | PS4-28-PRV-0046A |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00251
T-00251-0150 | PS4-28-PRV-0046B |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00251
T-00251-0151 | PS4-28-PRV-0046C |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00251
T-00251-0152 | PS4-28-PRV-0047A |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00251
T-00251-0153 | PS4-28-PRV-0047B |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00251
T-00251-0154 | PS4-28-PRV-0047C |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00251
T-00251-0155 | PS4-28-PRV-0054 |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Relief Valve | I | To be completed | PS4 - Milestone E | TM-00251
T-00251-0156 | PS4-28-PRV-0055 |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Relief Valve | I | To be completed | PS4 - Milestone E | TM-00251
T-00251-0157 | PS4-28-PSV-0044 |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Relief Valve | I | To be completed | PS4 - Milestone G | TM-00251
T-00251-0158 | PS4-28-PSV-0061 |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Relief Valve | I | To be completed | PS4 - Milestone E | TM-00251
T-00251-0159 | PS4-28-PSV-0064A |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00251
T-00251-0160 | PS4-28-PSV-0064B |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00251
T-00251-0161 | PS4-28-PSV-0064C |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00251
T-00251-0162 | PS4-28-PSV-3901A |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00251
T-00251-0163 | PS4-28-PSV-3901B |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00251
T-00251-0164 | PS4-50-PSV-0004A |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-50-01 - Water Well Submersible Pumps (3100) |  | PS4-50-01 |  |  | Relief Valve | I | To be completed | PS4 - Milestone I | TM-00251
T-00251-0165 | PS4-50-PSV-0004B |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-50-02 - Water Well Submersible Pumps (3200) |  | PS4-50-02 |  |  | Relief Valve | I | To be completed | PS4 - Milestone I | TM-00251
T-00251-0166 | PS4-71-PRV-0015 |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00251
T-00251-0167 | PS4-71-PRV-0016 |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00251
T-00251-0168 | PS4-71-PRV-0018 |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00251
T-00251-0169 | PS4-71-PRV-0041 |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Self-Actuating / Regulating Press Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00251
T-00251-0170 | PS4-71-PSV-2403A |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00251
T-00251-0171 | PS4-71-PSV-2403B |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00251
T-00251-0172 | PS4-71-PVSV-4102 |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Pressure / Vacuum Safety Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00251
T-00251-0173 | PS4-71-PVSV-4202 |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Pressure / Vacuum Safety Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Relief Valve | I | To be completed | PS4 - Milestone H | TM-00251
T-00251-0174 | PS4-74-PSV-0003 |  |  |  |  | TJX03 - Relief valve | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Pressure Safety Relief Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-74-03 - Nitrogen Receiver |  | PS4-74-03 |  |  | Relief Valve | I | To be completed | PS4 - Milestone F | TM-00251
T-00254-10000 | PS4-03-RDOS-B601A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RMAC-B902 TO PS4-03-RDOS-B601A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10001 | PS4-03-RDOS-B701A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B901A TO PS4-03-RDOS-B701A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10002 | PS4-03-RDOS-B701B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B701B TO PS4-03-RDOS-B701C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10003 | PS4-03-RDOS-B701C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B701C TO PS4-03-RDOS-B701D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10004 | PS4-03-RDOS-B701D-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B701D TO PS4-03-RDOS-B701E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10005 | PS4-03-RDOS-B701E-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B701E TO PS4-03-RDOS-B701F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10006 | PS4-03-RDOS-B701F-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B701F TO PS4-03-RDOS-B701G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10007 | PS4-03-RDOS-B701G-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B701G TO PS4-03-RDOS-B701I | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10008 | PS4-03-RDOS-B701H-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B701H TO PS4-03-RDOS-B301D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10009 | PS4-03-RDOS-B701I-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B701I TO PS4-03-RDOS-B701H | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10010 | PS4-03-RDOS-B801A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B801B TO PS4-03-RDOS-B801A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10011 | PS4-03-RDOS-B801B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B701A TO PS4-03-RDOS-B801B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10012 | PS4-03-RDOS-B901A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B901B TO PS4-03-RDOS-B901A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10013 | PS4-03-RDOS-B901B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B801A TO PS4-03-RDOS-B901C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10014 | PS4-03-RDOS-B901C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B901C TO PS4-03-RDOS-B901D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10015 | PS4-03-RDOS-B901D-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B901D TO PS4-03-RDOS-B901E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10016 | PS4-03-RDOS-B901E-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B901E TO PS4-03-RMAC-B902 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10017 | PS4-03-RDOS-W201A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-W201B TO PS4-03-RDOS-W201A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10018 | PS4-03-RDOS-W201B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-W301A TO PS4-03-RDOS-W201B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10019 | PS4-03-RDOS-W201C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-W201D TO PS4-03-RDOS-W201C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10020 | PS4-03-RDOS-W201D-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-W501A TO PS4-03-RDOS-W201D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10021 | PS4-03-RDOS-W301A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-W401A TO PS4-03-RDOS-W301A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10022 | PS4-03-RDOS-W401A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-W201C TO PS4-03-RDOS-W401A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10023 | PS4-03-RDOS-W501A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-W501B TO PS4-03-RDOS-W501A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10024 | PS4-03-RDOS-W501B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-W501C TO PS4-03-RDOS-W501B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10025 | PS4-03-RDOS-W501C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-W501D TO PS4-03-RDOS-W501C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10026 | PS4-03-RDOS-W501D-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-W501E TO PS4-03-RDOS-W501D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10027 | PS4-03-RDOS-W501E-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-W501F TO PS4-03-RDOS-W501E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10028 | PS4-03-RDOS-W501F-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RMAC-W502 TO PS4-03-RDOS-W501F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10029 | PS4-03-RMAC-B402-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B401C TO PS4-03-RMAC-B402 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10030 | PS4-03-RMAC-B902-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-SEA-0005 TO PS4-03-RMAC-B902 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-10031 | PS4-03-RMAC-W502-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-SEA-0006 TO PS4-03-RMAC-W502 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-11338 | PS4-09-AH-8401-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AH-8401 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11339 | PS4-09-AH-8401-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AH-8401 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11340 | PS4-09-AH-8402-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AH-8402 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11341 | PS4-09-AH-8402-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AH-8402 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11342 | PS4-09-AH-8403-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AH-8403 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11343 | PS4-09-AH-8403-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AH-8403 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11344 | PS4-09-AS-8111A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8111A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11345 | PS4-09-AS-8111A-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8111A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11346 | PS4-09-AS-8111B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8111B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11347 | PS4-09-AS-8111B-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8111B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11348 | PS4-09-AS-8211A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8211A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11349 | PS4-09-AS-8211A-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8211A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11350 | PS4-09-AS-8211B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8211B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11351 | PS4-09-AS-8211B-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8211B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11352 | PS4-09-AS-8311A-A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8311A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11353 | PS4-09-AS-8311A-A-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8311A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11354 | PS4-09-AS-8311B-B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8311B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11355 | PS4-09-AS-8311B-B-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8311B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11356 | PS4-09-AS-8311C-A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8311C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11357 | PS4-09-AS-8311C-A-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8311C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11358 | PS4-09-AS-8311D-B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8311D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11359 | PS4-09-AS-8311D-B-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8311D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11360 | PS4-09-AS-8321A-A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8321A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11361 | PS4-09-AS-8321A-A-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8321A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11362 | PS4-09-AS-8321B-B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8321B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11363 | PS4-09-AS-8321B-B-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8321B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11364 | PS4-09-AS-8321C-A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8321C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11365 | PS4-09-AS-8321C-A-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8321C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11366 | PS4-09-AS-8321D-B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8321D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11367 | PS4-09-AS-8321D-B-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8321D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11368 | PS4-09-AS-8331A-A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8331A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11369 | PS4-09-AS-8331A-A-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8331A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11370 | PS4-09-AS-8331B-B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8331B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11371 | PS4-09-AS-8331B-B-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8331B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11372 | PS4-09-AS-8331C-A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8331C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11373 | PS4-09-AS-8331C-A-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8331C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11374 | PS4-09-AS-8331D-B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8331D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11375 | PS4-09-AS-8331D-B-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8331D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11376 | PS4-09-AS-8341A-A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8341A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11377 | PS4-09-AS-8341A-A-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8341A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11378 | PS4-09-AS-8341B-B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8341B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11379 | PS4-09-AS-8341B-B-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8341B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11380 | PS4-09-AS-8411A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8411A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11381 | PS4-09-AS-8411A-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8411A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11382 | PS4-09-AS-8411B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8411B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11383 | PS4-09-AS-8411B-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8411B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11384 | PS4-09-AS-8412A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8412A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11385 | PS4-09-AS-8412A-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8412A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11386 | PS4-09-AS-8412B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8412B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11387 | PS4-09-AS-8412B-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8412B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11388 | PS4-09-AS-8421A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8421A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11389 | PS4-09-AS-8421A-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8421A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11390 | PS4-09-AS-8421B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8421B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11391 | PS4-09-AS-8421B-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8421B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11392 | PS4-09-AS-8432A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8432A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11393 | PS4-09-AS-8432A-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8432A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11394 | PS4-09-AS-8432B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8432B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11395 | PS4-09-AS-8432B-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-AS-8432B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11396 | PS4-09-BI-8111A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8111A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11397 | PS4-09-BI-8111B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8111B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11398 | PS4-09-BI-8211A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8211A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11399 | PS4-09-BI-8211B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8211B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11400 | PS4-09-BI-8311A-A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8312A (PS4-09-BI-8311A-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11401 | PS4-09-BI-8311A-B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8312B (PS4-09-BI-8311A-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11402 | PS4-09-BI-8311B-A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8312C (PS4-09-BI-8311B-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11403 | PS4-09-BI-8311B-B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8312D (PS4-09-BI-8311B-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11404 | PS4-09-BI-8321A-A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8322A (PS4-09-BI-8321A-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11405 | PS4-09-BI-8321A-B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8322B (PS4-09-BI-8321A-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11406 | PS4-09-BI-8321B-A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8322C (PS4-09-BI-8321B-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11407 | PS4-09-BI-8321B-B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8322D (PS4-09-BI-8321B-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11408 | PS4-09-BI-8331A-A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8332A (PS4-09-BI-8331A-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11409 | PS4-09-BI-8331A-B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8332B (PS4-09-BI-8331A-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11410 | PS4-09-BI-8331B-A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8332C (PS4-09-BI-8331B-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11411 | PS4-09-BI-8331B-B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8332D (PS4-09-BI-8331B-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11412 | PS4-09-BI-8341A-A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8342A (PS4-09-BI-8341A-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11413 | PS4-09-BI-8341A-B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8342B (PS4-09-BI-8341A-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11414 | PS4-09-BI-8411A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8411A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11415 | PS4-09-BI-8411B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-BI-8411B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11416 | PS4-09-FCU-8442A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11417 | PS4-09-FCU-8442A-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11418 | PS4-09-FCU-8442B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11419 | PS4-09-FCU-8442B-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11420 | PS4-09-FCU-8442C-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11421 | PS4-09-FCU-8442C-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11422 | PS4-09-FCU-8442D-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11423 | PS4-09-FCU-8442D-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11424 | PS4-09-FCU-8442E-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11425 | PS4-09-FCU-8442E-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11426 | PS4-09-FCU-8442F-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11427 | PS4-09-FCU-8442F-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11428 | PS4-09-FCU-8442G-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11429 | PS4-09-FCU-8442G-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11430 | PS4-09-FCU-8442H-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442H | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11431 | PS4-09-FCU-8442H-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442H | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11432 | PS4-09-FD-0019-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0019 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11433 | PS4-09-FD-0019-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0019 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11434 | PS4-09-FD-0019-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0019 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11435 | PS4-09-FD-0021-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0021 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11436 | PS4-09-FD-0021-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0021 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11437 | PS4-09-FD-0021-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0021 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11438 | PS4-09-FD-0024-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0024 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11439 | PS4-09-FD-0024-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0024 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11440 | PS4-09-FD-0024-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0024 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11441 | PS4-09-FD-0025-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0025 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11442 | PS4-09-FD-0025-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0025 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11443 | PS4-09-FD-0025-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0025 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11444 | PS4-09-FD-0026-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0026 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11445 | PS4-09-FD-0026-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0026 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11446 | PS4-09-FD-0026-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0026 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11447 | PS4-09-FD-0027-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0027 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11448 | PS4-09-FD-0027-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0027 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11449 | PS4-09-FD-0027-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0027 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11450 | PS4-09-FD-0028-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0028 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11451 | PS4-09-FD-0028-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0028 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11452 | PS4-09-FD-0028-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0028 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11453 | PS4-09-FD-0029-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0029 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11454 | PS4-09-FD-0029-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0029 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11455 | PS4-09-FD-0029-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0029 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11456 | PS4-09-FD-0030-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0030 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11457 | PS4-09-FD-0030-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0030 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11458 | PS4-09-FD-0030-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0030 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11459 | PS4-09-FD-0031-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0031 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11460 | PS4-09-FD-0031-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0031 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11461 | PS4-09-FD-0031-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0031 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11462 | PS4-09-FD-0032-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0032 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11463 | PS4-09-FD-0032-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0032 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11464 | PS4-09-FD-0032-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0032 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11465 | PS4-09-FD-0033-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-BI-2503 TO PS4-09-FD-0033 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11466 | PS4-09-FD-0033-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0033 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11467 | PS4-09-FD-0033-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FD-0033 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11468 | PS4-09-HE-8401A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-61-IH-0004 TO PS4-09-HE-8401A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11469 | PS4-09-HE-8401B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-61-IH-0004 TO PS4-09-HE-8401B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11470 | PS4-09-LB-8111A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8111A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11471 | PS4-09-LB-8111B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8111B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11472 | PS4-09-LB-8211A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8211A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11473 | PS4-09-LB-8211B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8211B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11474 | PS4-09-LB-8311A-A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8311B (PS4-09-LB-8311A-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11475 | PS4-09-LB-8311A-B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8311C (PS4-09-LB-8311B-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11476 | PS4-09-LB-8311B-A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8311D (PS4-09-LB-8311B-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11477 | PS4-09-LB-8311B-B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8321A (PS4-09-LB-8321A-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11478 | PS4-09-LB-8321A-A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8321B (PS4-09-LB-8321A-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11479 | PS4-09-LB-8321A-B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8321C (PS4-09-LB-8321B-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11480 | PS4-09-LB-8321B-A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8321D (PS4-09-LB-8321B-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11481 | PS4-09-LB-8321B-B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8331A (PS4-09-LB-8331A-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11482 | PS4-09-LB-8331A-A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8331B (PS4-09-LB-8331A-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11483 | PS4-09-LB-8331A-B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8331C (PS4-09-LB-8331B-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11484 | PS4-09-LB-8331B-A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8331D (PS4-09-LB-8331B-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11485 | PS4-09-LB-8331B-B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8341A (PS4-09-LB-8341A-A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11486 | PS4-09-LB-8341A-A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8341B (PS4-09-LB-8341A-B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11487 | PS4-09-LB-8341A-B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8341A-B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11488 | PS4-09-LB-8411A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8411A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11489 | PS4-09-LB-8411B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8411B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11490 | PS4-09-LB-8442A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442A (PS4-09-LB-8442A) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11491 | PS4-09-LB-8442B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442B (PS4-09-LB-8442B) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11492 | PS4-09-LB-8442C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442C (PS4-09-LB-8442C) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11493 | PS4-09-LB-8442D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442D (PS4-09-LB-8442D) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11494 | PS4-09-LB-8442E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442E (PS4-09-LB-8442E) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11495 | PS4-09-LB-8442F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442F (PS4-09-LB-8442F) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11496 | PS4-09-LB-8442G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442G (PS4-09-LB-8442G) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11497 | PS4-09-LB-8442H-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-FCU-8442H (PS4-09-LB-8442H) | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11498 | PS4-09-LB-8451A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8451A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11499 | PS4-09-LB-8451A-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8451A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11500 | PS4-09-LB-8451B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8451B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11501 | PS4-09-LB-8451B-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8451B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11502 | PS4-09-PDIT-8207-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-PDIT-8207 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11503 | PS4-09-PDIT-8407-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-PDIT-8407 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11504 | PS4-09-PDIT-8408-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-PDIT-8408 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11505 | PS4-09-PDIT-8409-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-PDIT-8409 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11506 | PS4-09-PDIT-8411-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-PDIT-8411 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11507 | PS4-09-PIT-8401-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-PIT-8401 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11508 | PS4-09-PIT-8402-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-PIT-8402 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11509 | PS4-09-PIT-8403-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-PIT-8403 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11510 | PS4-09-PIT-8404-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-PIT-8404 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11511 | PS4-09-TCV-8401-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TCV-8401 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11512 | PS4-09-TCV-8401-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TCV-8401 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11513 | PS4-09-TCV-8402-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TCV-8402 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11514 | PS4-09-TCV-8402-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TCV-8402 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11515 | PS4-09-TIT-8101-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8101 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11516 | PS4-09-TIT-8201-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8201 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11517 | PS4-09-TIT-8301-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8301 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11518 | PS4-09-TIT-8302-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8302 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11519 | PS4-09-TIT-8303-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8303 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11520 | PS4-09-TIT-8304-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8304 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11521 | PS4-09-TIT-8401-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8401 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11522 | PS4-09-TIT-8402-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8402 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11523 | PS4-09-TIT-8403-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8403 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11524 | PS4-09-TIT-8404-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8404 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11525 | PS4-09-TIT-8405-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8405 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11526 | PS4-09-TIT-8406-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8406 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11527 | PS4-09-TIT-8407-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8407 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11528 | PS4-09-TIT-8408-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-TIT-8408 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11529 | PS4-09-UZ-84600-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-UZ-84600 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11530 | PS4-09-UZ-84600-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-UZ-84600 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11531 | PS4-09-XV-8401-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8401 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11532 | PS4-09-XV-8401-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8401 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11533 | PS4-09-XV-8402-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8402 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11534 | PS4-09-XV-8402-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8402 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11535 | PS4-09-XV-8403-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8403 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11536 | PS4-09-XV-8403-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8403 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11537 | PS4-09-XV-8404-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8404 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11538 | PS4-09-XV-8404-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8404 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11539 | PS4-09-XV-8413-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8413 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11540 | PS4-09-XV-8413-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8413 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11541 | PS4-09-XV-8414-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8414 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11542 | PS4-09-XV-8414-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-09-XV-8414 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11543 | PS4-61-IH-0004A-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11544 | PS4-61-IH-0004A-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11545 | PS4-61-IH-0004A-CU03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11546 | PS4-61-IH-0004A-CU04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11547 | PS4-61-IH-0004B-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11548 | PS4-61-IH-0004B-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11549 | PS4-61-IH-0004B-CU03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11550 | PS4-61-IH-0004B-CU04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11551 | PS4-61-IH-0004C-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11552 | PS4-61-IH-0004C-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11553 | PS4-61-IH-0004C-CU03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11554 | PS4-61-IH-0004C-CU04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11555 | PS4-61-IH-0004-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11556 | PS4-61-IH-0004-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11557 | PS4-61-IH-0004-CU03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11558 | PS4-61-IH-0004-CU04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11559 | PS4-61-IH-0004-CU05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11560 | PS4-61-IH-0004-CU06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11561 | PS4-61-IH-0004-CU07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11562 | PS4-61-IH-0004-CU08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11563 | PS4-61-IH-0004-CU09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11564 | PS4-61-IH-0004-CU10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11565 | PS4-61-IH-0004-CU11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11566 | PS4-61-IH-0004-CU12 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11567 | PS4-61-IH-0004-CU13 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11568 | PS4-61-IH-0004-CU14 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11569 | PS4-61-IH-0004-CU15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11570 | PS4-61-IH-0004-CU16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11571 | PS4-61-IH-0004-CU17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11572 | PS4-61-IH-0004-CU18 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11573 | PS4-61-IH-0004-CU19 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11574 | PS4-61-IH-0004-CU20 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11575 | PS4-61-IH-0004-CU21 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11576 | PS4-61-IH-0004-CU22 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11577 | PS4-61-IH-0004-CU23 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11578 | PS4-61-IH-0004-CU24 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11579 | PS4-61-IH-0004-CU25 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11580 | PS4-61-IH-0004-CU26 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11581 | PS4-61-IH-0004-CU27 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11582 | PS4-61-IH-0004-CU28 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11583 | PS4-61-IH-0004-CU29 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11584 | PS4-61-IH-0004D-CU01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-11585 | PS4-61-IH-0004D-CU02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-09-LB-0008 TO PS4-61-IH-0004D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-13022 | PS4-60-BI-0001A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-20 17:20 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-13023 | PS4-60-BI-0001B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-20 17:23 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-13024 | PS4-60-BI-0001C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-BI-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-22 19:09 | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13025 | PS4-60-BI-0001D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-BI-0001D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-20 17:26 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13026 | PS4-60-BI-0001E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-BI-0001E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-22 19:12 | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13027 | PS4-60-BI-0001F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001F TO PS4-60-BI-0001F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-20 17:30 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13028 | PS4-60-BI-0001G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001G TO PS4-60-BI-0001G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-22 19:14 | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-13029 | PS4-60-BI-0003-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-20 17:39 | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-13030 | PS4-60-IE-0002A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-06 07:51 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-13031 | PS4-60-IE-0002A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-06 07:52 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-13032 | PS4-60-IE-0002A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-06 07:55 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-13033 | PS4-60-IE-0002B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-06 07:57 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-13034 | PS4-60-IE-0002B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-06 08:00 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-13035 | PS4-60-IE-0002B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-06 08:02 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-13036 | PS4-60-IE-0002C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-06 08:05 | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13037 | PS4-60-IE-0002C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-06 08:07 | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13038 | PS4-60-IE-0002C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-06 08:09 | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13039 | PS4-60-IE-0002D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-06 08:11 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13040 | PS4-60-IE-0002D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-06 08:14 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13041 | PS4-60-IE-0002D-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-06 08:16 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13042 | PS4-60-IE-0002E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-06 08:18 | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13043 | PS4-60-IE-0002E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-06 08:19 | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13044 | PS4-60-IE-0002E-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-06 08:21 | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13045 | PS4-60-IE-0002F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001F TO PS4-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-06 08:25 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13046 | PS4-60-IE-0002F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001F TO PS4-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-06 08:28 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13047 | PS4-60-IE-0002F-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001F TO PS4-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-06 08:31 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13048 | PS4-60-IE-0002G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001G TO PS4-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-06 08:33 | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-13049 | PS4-60-IE-0002G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001G TO PS4-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-06 08:35 | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-13050 | PS4-60-IE-0002G-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001G TO PS4-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-07-06 08:38 | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-13051 | PS4-60-IH-0001A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS4-60-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00254
T-00254-13052 | PS4-60-IH-0001A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IH-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs |  | PS4-60-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00254
T-00254-13053 | PS4-60-IH-0001B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS4-60-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00254
T-00254-13054 | PS4-60-IH-0001B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IH-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs |  | PS4-60-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00254
T-00254-13055 | PS4-60-IH-0001C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS4-60-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-13056 | PS4-60-IH-0001C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IH-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs |  | PS4-60-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-13057 | PS4-60-IH-0001D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS4-60-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-13058 | PS4-60-IH-0001D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IH-0001D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs |  | PS4-60-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-13059 | PS4-60-IH-0001E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS4-60-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-13060 | PS4-60-IH-0001E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IH-0001E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs |  | PS4-60-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-13061 | PS4-60-IH-0001F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS4-60-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-13062 | PS4-60-IH-0001F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IH-0001F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs |  | PS4-60-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-13063 | PS4-60-IH-0001G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS4-60-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-13064 | PS4-60-IH-0001G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IH-0001G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs |  | PS4-60-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-13065 | PS4-60-IH-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00254
T-00254-13066 | PS4-60-IH-0002-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IH-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00254
T-00254-13067 | PS4-60-IN-0004A-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IN-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-13068 | PS4-60-IN-0004B-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IN-0004B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-13069 | PS4-60-PIT-8113A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-PIT-8113A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A | 2026-07-22 19:17 | PS4-60-56 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-13070 | PS4-60-PIT-8113B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-PIT-8113B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B | 2026-07-22 19:20 | PS4-60-58 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-13071 | PS4-60-PIT-8113C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-PIT-8113C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C | 2026-07-22 19:22 | PS4-60-60 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13072 | PS4-60-PIT-8113D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-PIT-8113D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D | 2026-07-22 19:25 | PS4-60-62 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13073 | PS4-60-PIT-8113E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-PIT-8113E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E | 2026-07-22 19:28 | PS4-60-64 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13074 | PS4-60-PIT-8113F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001F TO PS4-60-PIT-8113F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F | 2026-07-22 19:31 | PS4-60-66 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13075 | PS4-60-PIT-8113G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001G TO PS4-60-PIT-8113G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G | 2026-07-22 19:34 | PS4-60-68 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-13076 | PS4-60-PIT-8114A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-PIT-8114A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A | 2026-07-22 19:37 | PS4-60-56 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-13077 | PS4-60-PIT-8114B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-PIT-8114B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B | 2026-07-22 19:41 | PS4-60-58 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-13078 | PS4-60-PIT-8114C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-PIT-8114C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C | 2026-07-22 19:47 | PS4-60-60 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13079 | PS4-60-PIT-8114D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-PIT-8114D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D | 2026-07-22 19:49 | PS4-60-62 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13080 | PS4-60-PIT-8114E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-PIT-8114E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E | 2026-07-22 19:52 | PS4-60-64 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13081 | PS4-60-PIT-8114F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001F TO PS4-60-PIT-8114F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F | 2026-07-22 19:54 | PS4-60-66 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-13082 | PS4-60-PIT-8114G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001G TO PS4-60-PIT-8114G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G | 2026-07-22 19:57 | PS4-60-68 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-7993 | PS4-01-BI-0007-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-BI-0007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling | 2026-06-26 08:36 | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-7994 | PS4-01-BI-0008-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-BI-0008 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling | 2026-06-26 08:47 | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-7995 | PS4-01-BI-0009-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-BI-0009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling | 2026-06-26 08:50 | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8006 | PS4-01-FCV-0003A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-FCV-0003A-HPU TO PS4-01-FCV-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00254
T-00254-8007 | PS4-01-FCV-0003B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-FCV-0003B-HPU TO PS4-01-FCV-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00254
T-00254-8008 | PS4-01-FCV-0004A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-FCV-0004A-HPU TO PS4-01-FCV-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00254
T-00254-8009 | PS4-01-FCV-0004B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-FCV-0004B-HPU TO PS4-01-FCV-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00254
T-00254-8010 | PS4-01-FIT-0003A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1117 TO PS4-01-FIT-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A | 2026-07-07 12:32 | PS4-01-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8011 | PS4-01-FIT-0003B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1117 TO PS4-01-FIT-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B | 2026-07-07 12:33 | PS4-01-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8012 | PS4-01-FIT-0004A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1117 TO PS4-01-FIT-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B | 2026-07-07 12:34 | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8013 | PS4-01-FIT-0004B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1117 TO PS4-01-FIT-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B | 2026-07-07 12:34 | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8014 | PS4-01-FXS-0003A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-2110 TO PS4-01-FCV-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00254
T-00254-8015 | PS4-01-FXS-0003B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-2110 TO PS4-01-FCV-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B | 2026-07-08 04:43 | PS4-01-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8016 | PS4-01-FXS-0004A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-2110 TO PS4-01-FCV-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B | 2026-07-08 04:46 | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8017 | PS4-01-FXS-0004B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-2110 TO PS4-01-FCV-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00254
T-00254-8018 | PS4-01-FY-0003A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1118 TO PS4-01-FCV-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A | 2026-07-07 12:35 | PS4-01-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8019 | PS4-01-FY-0003B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1118 TO PS4-01-FCV-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B | 2026-07-07 12:36 | PS4-01-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8020 | PS4-01-FY-0004A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1118 TO PS4-01-FCV-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B | 2026-07-07 12:37 | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8021 | PS4-01-FY-0004B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1118 TO PS4-01-FCV-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B | 2026-07-07 12:39 | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8022 | PS4-01-HS-3108AB-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-IE-0009A TO PS4-03-MTX-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00254
T-00254-8023 | PS4-01-HS-3108BB-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-IE-0009B TO PS4-03-MTX-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00254
T-00254-8035 | PS4-01-LB-6101A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-LB-6101A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8036 | PS4-01-LB-6102A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-LB-6102A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8037 | PS4-01-LB-6103A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-LB-6103A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8038 | PS4-01-LB-6104A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-LB-6104A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8039 | PS4-01-LIT-4101A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-IE-0009A TO PS4-01-LIT-4101A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00254
T-00254-8040 | PS4-01-LIT-4101B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-IE-0009B TO PS4-01-LIT-4101B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone C | TM-00254
T-00254-8042 | PS4-01-NMR-61001-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-NMR-61001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8043 | PS4-01-NMR-61002-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-NMR-61002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8044 | PS4-01-NMR-61003-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-NMR-61003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8045 | PS4-01-NMR-61004-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-NMR-61004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8046 | PS4-01-NMRA-61001-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-NMRA-61001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8047 | PS4-01-NMRA-61002-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-NMRA-61002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8048 | PS4-01-NMRA-61003-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-NMRA-61003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8049 | PS4-01-NMRA-61004-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-NMRA-61004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8050 | PS4-01-PDIT-0011A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1515 TO PS4-01-PDIT-0011A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B | 2026-07-08 04:05 | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8051 | PS4-01-PDIT-0011B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1515 TO PS4-01-PDIT-0011B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B | 2026-07-08 04:08 | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8052 | PS4-01-PDIT-0012A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1515 TO PS4-01-PDIT-0012A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A | 2026-07-08 04:13 | PS4-01-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8053 | PS4-01-PDIT-0012B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1515 TO PS4-01-PDIT-0012B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B | 2026-07-08 04:15 | PS4-01-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8054 | PS4-01-PIT-0003AA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1118 TO PS4-01-FCV-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A | 2026-07-07 12:36 | PS4-01-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8055 | PS4-01-PIT-0003BA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1118 TO PS4-01-FCV-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B | 2026-07-07 12:37 | PS4-01-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8056 | PS4-01-PIT-0004AA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1118 TO PS4-01-FCV-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B | 2026-07-07 12:38 | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8057 | PS4-01-PIT-0004BA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1118 TO PS4-01-FCV-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B | 2026-07-07 12:39 | PS4-01-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8058 | PS4-01-PIT-0010-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1501 TO PS4-01-PIT-0010 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-07 - Fire Water Ring Main & Distribution | 2026-07-08 04:03 | PS4-01-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8059 | PS4-01-PIT-0013-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1515 TO PS4-01-PIT-0013 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-07 - Fire Water Ring Main & Distribution | 2026-07-08 04:17 | PS4-01-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8064 | PS4-01-PIT-8101A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1520 TO PS4-01-PIT-8101A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package | 2026-07-08 04:19 | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8065 | PS4-01-PIT-8101B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1520 TO PS4-01-PIT-8101B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package | 2026-07-08 04:21 | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8066 | PS4-01-PIT-8101C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1520 TO PS4-01-PIT-8101C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package | 2026-07-08 04:24 | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8067 | PS4-01-PIT-8101D-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1520 TO PS4-01-PIT-8101D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package | 2026-07-08 04:27 | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8068 | PS4-01-PIT-8101E-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1520 TO PS4-01-PIT-8101E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package | 2026-07-08 04:30 | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8069 | PS4-01-PIT-8101F-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1520 TO PS4-01-PIT-8101F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package | 2026-07-08 04:33 | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8070 | PS4-01-PIT-8101G-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1520 TO PS4-01-PIT-8101G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package | 2026-07-08 04:37 | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8071 | PS4-01-PIT-8101H-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-1520 TO PS4-01-PIT-8101H | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package | 2026-07-08 04:40 | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8072 | PS4-01-RAB-61001A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-RAB-61001A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8073 | PS4-01-RAB-61001B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-RAB-61001B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8074 | PS4-01-RAB-61002A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-RAB-61002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8075 | PS4-01-RAB-61002B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-RAB-61002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8076 | PS4-01-RAB-61003A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-RAB-61003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8077 | PS4-01-RAB-61003B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-RAB-61003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8078 | PS4-01-RAB-61004A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-RAB-61004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8079 | PS4-01-RAB-61004B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-LB-0004 TO PS4-01-RAB-61004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8080 | PS4-01-SY-8101A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-2520 TO PS4-01-SY-8101A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package | 2026-07-08 04:49 | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8081 | PS4-01-SY-8101B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-2520 TO PS4-01-SY-8101B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package | 2026-07-08 04:55 | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8082 | PS4-01-SY-8101C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-2520 TO PS4-01-SY-8101C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package | 2026-07-08 04:57 | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8083 | PS4-01-SY-8101D-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-2520 TO PS4-01-SY-8101D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package | 2026-07-08 04:59 | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8084 | PS4-01-SY-8101E-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-2520 TO PS4-01-SY-8101E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package | 2026-07-08 05:02 | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8085 | PS4-01-SY-8101F-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-2520 TO PS4-01-SY-8101F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package | 2026-07-08 05:04 | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8086 | PS4-01-SY-8101G-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-2520 TO PS4-01-SY-8101G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package | 2026-07-08 05:07 | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8087 | PS4-01-SY-8101H-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-01-BI-2520 TO PS4-01-SY-8101H | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package | 2026-07-08 05:14 | PS4-01-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8114 | PS4-03-GDIR-0901-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-0901 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | 2026-06-24 14:03 | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8115 | PS4-03-GDIR-0902-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-0902 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | 2026-06-24 14:07 | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8116 | PS4-03-GDIR-0903-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-0903 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | 2026-06-24 14:09 | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8117 | PS4-03-GDIR-0904-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-0904 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | 2026-06-25 05:01 | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8118 | PS4-03-GDIR-0906-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-0906 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | 2026-06-25 05:08 | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8119 | PS4-03-GDIR-0907-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-0907 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | 2026-06-25 05:11 | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8120 | PS4-03-GDIR-0908-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-0908 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | 2026-06-25 05:14 | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8121 | PS4-03-GDIR-0909-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-0909 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | 2026-06-25 05:18 | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8122 | PS4-03-GDIR-1001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | 2026-06-25 05:21 | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8123 | PS4-03-GDIR-1002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | 2026-06-25 05:27 | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8124 | PS4-03-GDIR-1003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | 2026-06-25 05:30 | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8125 | PS4-03-GDIR-1004-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | 2026-06-25 05:33 | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8126 | PS4-03-GDIR-1006-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | 2026-06-25 05:38 | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8127 | PS4-03-GDIR-1007-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | 2026-06-25 05:40 | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8128 | PS4-03-GDIR-1008-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1008 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | 2026-06-25 05:45 | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8129 | PS4-03-GDIR-1009-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | 2026-06-25 06:23 | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8130 | PS4-03-GDIR-1101-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | 2026-06-25 06:28 | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8131 | PS4-03-GDIR-1102-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1102 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | 2026-06-25 06:43 | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8132 | PS4-03-GDIR-1103-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1103 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | 2026-06-25 06:48 | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8133 | PS4-03-GDIR-1104-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1104 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | 2026-06-25 06:52 | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8134 | PS4-03-GDIR-1106-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1106 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | 2026-06-25 06:55 | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8135 | PS4-03-GDIR-1107-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1107 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | 2026-06-25 06:58 | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8136 | PS4-03-GDIR-1108-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1108 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | 2026-06-25 07:00 | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8137 | PS4-03-GDIR-1109-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1109 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | 2026-06-25 07:47 | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8138 | PS4-03-GDIR-1201-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1201 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | 2026-06-25 07:49 | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8139 | PS4-03-GDIR-1202-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1202 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | 2026-06-25 07:52 | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8140 | PS4-03-GDIR-1203-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1203 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | 2026-06-25 07:55 | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8141 | PS4-03-GDIR-1204-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-SEA-0001 TO PS4-03-GDIR-1204 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | 2026-06-25 08:00 | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8142 | PS4-03-GDLHP-0137-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2511 TO PS4-03-GDLHP-0137 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8143 | PS4-03-GDLHP-0142-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2511 TO PS4-03-GDLHP-0142 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8144 | PS4-03-GDLHP-0143-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2511 TO PS4-03-GDLHP-0143 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-09 06:00 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8145 | PS4-03-GDLHP-0144-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2511 TO PS4-03-GDLHP-0144 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-09 06:02 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8146 | PS4-03-GDLHP-0146-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2511 TO PS4-03-GDLHP-0146 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-09 06:06 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8147 | PS4-03-GDLHP-0147-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2511 TO PS4-03-GDLHP-0147 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-09 06:09 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8148 | PS4-03-GDLHP-0149-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2511 TO PS4-03-GDLHP-0149 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-09 06:11 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8149 | PS4-03-GDLHP-0150-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2511 TO PS4-03-GDLHP-0150 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-09 06:14 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8150 | PS4-03-GDLHP-0401-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2512 TO PS4-03-GDLHP-0401 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | 2026-07-09 06:16 | PS4-03-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-8164 | PS4-03-RDH-0302-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2510 TO PS4-03-RDH-0302 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-03 - FZ-03 - Buildings Area |  | PS4-03-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8165 | PS4-03-RDH-0303-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2510 TO PS4-03-RDH-0303 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-03 - FZ-03 - Buildings Area |  | PS4-03-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8166 | PS4-03-RDH-0601-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2502 TO PS4-03-RDH-0601 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8167 | PS4-03-RDH-0602-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2502 TO PS4-03-RDH-0602 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8168 | PS4-03-RDH-0603-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2502 TO PS4-03-RDH-0603 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8169 | PS4-03-RDH-0604-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2502 TO PS4-03-RDH-0604 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8170 | PS4-03-RDH-0605-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2502 TO PS4-03-RDH-0605 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8171 | PS4-03-RDH-0606-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2502 TO PS4-03-RDH-0606 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8172 | PS4-03-RDH-0607-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2503 TO PS4-03-RDH-0607 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8173 | PS4-03-RDH-0608-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2503 TO PS4-03-RDH-0608 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8174 | PS4-03-RDH-0609-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2503 TO PS4-03-RDH-0609 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8175 | PS4-03-RDH-0610-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2503 TO PS4-03-RDH-0610 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8176 | PS4-03-RDH-0611-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2503 TO PS4-03-RDH-0611 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8177 | PS4-03-RDH-0612-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2503 TO PS4-03-RDH-0612 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8178 | PS4-03-RDH-0614-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2501 TO PS4-03-RDH-0614 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area | 2026-07-08 07:34 | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8179 | PS4-03-RDH-0615-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2501 TO PS4-03-RDH-0615 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area | 2026-07-08 07:36 | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8180 | PS4-03-RDH-0616-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2501 TO PS4-03-RDH-0616 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area | 2026-07-08 07:39 | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8181 | PS4-03-RDH-0617-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2502 TO PS4-03-RDH-0617 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8182 | PS4-03-RDH-0618-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2502 TO PS4-03-RDH-0618 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8183 | PS4-03-RDH-0620-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2502 TO PS4-03-RDH-0620 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8184 | PS4-03-RDH-0828-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2505 TO PS4-03-RDH-0828 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8185 | PS4-03-RDH-0829-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2505 TO PS4-03-RDH-0829 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External | 2026-07-22 20:02 | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8186 | PS4-03-RDH-0830-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2503 TO PS4-03-RDH-0830 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External | 2026-07-08 13:58 | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8187 | PS4-03-RDH-0831-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2503 TO PS4-03-RDH-0831 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External | 2026-07-08 14:26 | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8188 | PS4-03-RDH-0901-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RDH-0901 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | 2026-07-09 05:02 | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8189 | PS4-03-RDH-0902-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RDH-0902 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | 2026-07-13 06:01 | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8190 | PS4-03-RDH-0903-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RDH-0903 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | 2026-07-09 05:04 | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8191 | PS4-03-RDH-0904-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RDH-0904 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | 2026-07-09 05:40 | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8192 | PS4-03-RDH-0905-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RDH-0905 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | 2026-07-09 05:42 | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8193 | PS4-03-RDH-0906-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RDH-0906 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8194 | PS4-03-RDH-0909-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RDH-0909 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8195 | PS4-03-RDH-0910-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RDH-0910 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8196 | PS4-03-RDH-0911-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RDH-0911 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8197 | PS4-03-RDH-0912-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RDH-0912 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8198 | PS4-03-RDH-1001-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2507 TO PS4-03-RDH-1001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8199 | PS4-03-RDH-1002-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2507 TO PS4-03-RDH-1002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8200 | PS4-03-RDH-1003-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2507 TO PS4-03-RDH-1003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8201 | PS4-03-RDH-1004-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2507 TO PS4-03-RDH-1004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8202 | PS4-03-RDH-1005-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2507 TO PS4-03-RDH-1005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8203 | PS4-03-RDH-1006-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2507 TO PS4-03-RDH-1006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8204 | PS4-03-RDH-1009-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2507 TO PS4-03-RDH-1009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8205 | PS4-03-RDH-1010-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2507 TO PS4-03-RDH-1010 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8206 | PS4-03-RDH-1011-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2507 TO PS4-03-RDH-1011 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8207 | PS4-03-RDH-1012-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2507 TO PS4-03-RDH-1012 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8208 | PS4-03-RDH-1101-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2508 TO PS4-03-RDH-1101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8209 | PS4-03-RDH-1102-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2508 TO PS4-03-RDH-1102 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8210 | PS4-03-RDH-1103-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2508 TO PS4-03-RDH-1103 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8211 | PS4-03-RDH-1104-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2508 TO PS4-03-RDH-1104 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8212 | PS4-03-RDH-1105-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2508 TO PS4-03-RDH-1105 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8213 | PS4-03-RDH-1106-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2508 TO PS4-03-RDH-1106 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8214 | PS4-03-RDH-1109-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2508 TO PS4-03-RDH-1109 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8215 | PS4-03-RDH-1110-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2508 TO PS4-03-RDH-1110 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8216 | PS4-03-RDH-1111-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2508 TO PS4-03-RDH-1111 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8217 | PS4-03-RDH-1112-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2508 TO PS4-03-RDH-1112 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8218 | PS4-03-RDH-1201-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2514 TO PS4-03-RDH-1201 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8219 | PS4-03-RDH-1202-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2514 TO PS4-03-RDH-1202 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8220 | PS4-03-RDH-1203-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2514 TO PS4-03-RDH-1203 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8221 | PS4-03-RDH-1204-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2514 TO PS4-03-RDH-1204 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8222 | PS4-03-RDH-1205-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2514 TO PS4-03-RDH-1205 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8223 | PS4-03-RDH-1302-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2515 TO PS4-03-RDH-1302 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | 2026-07-09 06:18 | PS4-03-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8224 | PS4-03-RDH-1303-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2515 TO PS4-03-RDH-1303 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | 2026-07-09 06:20 | PS4-03-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8225 | PS4-03-RDH-1304-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2515 TO PS4-03-RDH-1304 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | 2026-07-09 06:22 | PS4-03-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8226 | PS4-03-RDH-1901-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDH-1903 TO PS4-03-RDH-1901 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-19 - FZ-19 - Power Generation Building - Battery Room |  | PS4-03-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8227 | PS4-03-RDH-1902-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDH-1901 TO PS4-03-RDH-1902 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-19 - FZ-19 - Power Generation Building - Battery Room |  | PS4-03-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8228 | PS4-03-RDH-1903-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RMAC-1410 TO PS4-03-RDH-1903 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-19 - FZ-19 - Power Generation Building - Battery Room |  | PS4-03-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8229 | PS4-03-RDIR-0104-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1507 TO PS4-03-RDIR-0104 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 06:11 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8230 | PS4-03-RDIR-0105-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1507 TO PS4-03-RDIR-0105 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 06:13 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8231 | PS4-03-RDIR-0106-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1507 TO PS4-03-RDIR-0106 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 06:16 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8232 | PS4-03-RDIR-0107-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1507 TO PS4-03-RDIR-0107 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 06:20 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8233 | PS4-03-RDIR-0108-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1508 TO PS4-03-RDIR-0108 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 06:27 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8234 | PS4-03-RDIR-0109-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1508 TO PS4-03-RDIR-0109 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 06:29 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8235 | PS4-03-RDIR-0110-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1508 TO PS4-03-RDIR-0110 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 06:32 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8236 | PS4-03-RDIR-0111-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1508 TO PS4-03-RDIR-0111 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 06:35 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8237 | PS4-03-RDIR-0112-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1508 TO PS4-03-RDIR-0112 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 06:39 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8238 | PS4-03-RDIR-0113-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1508 TO PS4-03-RDIR-0113 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 06:37 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8239 | PS4-03-RDIR-0114-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1509 TO PS4-03-RDIR-0114 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 06:44 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8240 | PS4-03-RDIR-0115-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1509 TO PS4-03-RDIR-0115 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 06:46 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8241 | PS4-03-RDIR-0116-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1509 TO PS4-03-RDIR-0116 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 06:48 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8242 | PS4-03-RDIR-0117-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1509 TO PS4-03-RDIR-0117 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 06:50 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8243 | PS4-03-RDIR-0118-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1509 TO PS4-03-RDIR-0118 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 06:53 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8244 | PS4-03-RDIR-0121-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0121 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8245 | PS4-03-RDIR-0122-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0122 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8246 | PS4-03-RDIR-0123-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0123 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8247 | PS4-03-RDIR-0124-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0124 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8248 | PS4-03-RDIR-0125-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0125 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8249 | PS4-03-RDIR-0126-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0126 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 06:04 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8250 | PS4-03-RDIR-0127-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0127 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 06:07 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8251 | PS4-03-RDIR-0128-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0128 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 05:46 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8252 | PS4-03-RDIR-0129-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0129 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 05:50 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8253 | PS4-03-RDIR-0130-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0130 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 05:52 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8254 | PS4-03-RDIR-0131-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0131 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 05:55 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8255 | PS4-03-RDIR-0132-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0132 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 05:59 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8256 | PS4-03-RDIR-0133-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1506 TO PS4-03-RDIR-0133 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 06:01 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8257 | PS4-03-RDIR-0137-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1507 TO PS4-03-RDIR-0137 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 06:23 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8258 | PS4-03-RDIR-0138-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1508 TO PS4-03-RDIR-0138 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 06:41 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8259 | PS4-03-RDIR-0141-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1507 TO PS4-03-RDIR-0141 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-08 06:25 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8260 | PS4-03-RDIR-0142-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1507 TO PS4-03-RDIR-0142 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8261 | PS4-03-RDIR-0403-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1503 TO PS4-03-RDIR-0403 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | 2026-07-08 05:29 | PS4-03-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-8262 | PS4-03-RDIR-0404-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1503 TO PS4-03-RDIR-0404 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | 2026-07-08 05:37 | PS4-03-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-8263 | PS4-03-RDIR-0405-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1502 TO PS4-03-RDIR-0405 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | 2026-07-08 05:17 | PS4-03-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-8264 | PS4-03-RDIR-0406-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1502 TO PS4-03-RDIR-0406 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | 2026-07-08 05:24 | PS4-03-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-8265 | PS4-03-RDIR-0409-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1503 TO PS4-03-RDIR-0409 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | 2026-07-08 05:41 | PS4-03-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-8266 | PS4-03-RDIR-0411-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1503 TO PS4-03-RDIR-0411 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | 2026-07-08 05:44 | PS4-03-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-8267 | PS4-03-RDIR-0819-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1510 TO PS4-03-RDIR-0819 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External | 2026-07-08 06:55 | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8268 | PS4-03-RDIR-0820-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1510 TO PS4-03-RDIR-0820 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External | 2026-07-08 06:58 | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8269 | PS4-03-RDIR-0832-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1510 TO PS4-03-RDIR-0832 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External | 2026-07-08 07:18 | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8270 | PS4-03-RDIR-0833-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1510 TO PS4-03-RDIR-0833 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External | 2026-07-08 07:20 | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8271 | PS4-03-RDOS-1401-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RMAC-1411 TO PS4-03-RDOS-1401 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-20 19:13 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8272 | PS4-03-RDOS-1402-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-1401 TO PS4-03-RDOS-1402 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-20 19:16 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8273 | PS4-03-RDOS-1403-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-1402 TO PS4-03-RDOS-1403 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-21 04:37 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8274 | PS4-03-RDOS-1404-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-1403 TO PS4-03-RDOS-1404 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-21 04:39 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8275 | PS4-03-RDOS-1405-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-1404 TO PS4-03-RDOS-1405 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-21 04:41 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8276 | PS4-03-RDOS-1406-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-1503 TO PS4-03-RDOS-1406 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-21 04:43 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8277 | PS4-03-RDOS-1407-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-1405 TO PS4-03-RDOS-1407 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-21 04:45 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8278 | PS4-03-RDOS-1408-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-1407 TO PS4-03-RDOS-1408 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-21 04:46 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8279 | PS4-03-RDOS-1501-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-1603 TO PS4-03-RDOS-1501 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-15 - FZ-15 - Power Generation Building - Generator Room 1 |  | PS4-03-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8280 | PS4-03-RDOS-1502-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-1501 TO PS4-03-RDOS-1502 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-15 - FZ-15 - Power Generation Building - Generator Room 1 |  | PS4-03-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8281 | PS4-03-RDOS-1503-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-1502 TO PS4-03-RDOS-1503 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-15 - FZ-15 - Power Generation Building - Generator Room 1 |  | PS4-03-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8282 | PS4-03-RDOS-1601-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-1703 TO PS4-03-RDOS-1601 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-16 - FZ-16 - Power Generation Building - Generator Room 2 |  | PS4-03-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8283 | PS4-03-RDOS-1602-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-1601 TO PS4-03-RDOS-1602 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-16 - FZ-16 - Power Generation Building - Generator Room 2 |  | PS4-03-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8284 | PS4-03-RDOS-1603-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-1602 TO PS4-03-RDOS-1603 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-16 - FZ-16 - Power Generation Building - Generator Room 2 |  | PS4-03-16 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8285 | PS4-03-RDOS-1701-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-1803 TO PS4-03-RDOS-1701 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-17 - FZ-17 - Power Generation Building - Generator Room 3 |  | PS4-03-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8286 | PS4-03-RDOS-1702-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-1701 TO PS4-03-RDOS-1702 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-17 - FZ-17 - Power Generation Building - Generator Room 3 |  | PS4-03-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8287 | PS4-03-RDOS-1703-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-1702 TO PS4-03-RDOS-1703 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-17 - FZ-17 - Power Generation Building - Generator Room 3 |  | PS4-03-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8288 | PS4-03-RDOS-1801-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDH-1902 TO PS4-03-RDOS-1801 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-18 - FZ-18 - Power Generation Building - Generator Room 4 |  | PS4-03-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8289 | PS4-03-RDOS-1802-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-1801 TO PS4-03-RDOS-1802 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-18 - FZ-18 - Power Generation Building - Generator Room 4 |  | PS4-03-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8290 | PS4-03-RDOS-1803-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-1802 TO PS4-03-RDOS-1803 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-18 - FZ-18 - Power Generation Building - Generator Room 4 |  | PS4-03-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8291 | PS4-03-RDOS-2101-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RMAC-1409 TO PS4-03-RDOS-2101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-21 - FZ-21 - Power Generation Building - Air Handling Unit |  | PS4-03-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8292 | PS4-03-RDOS-2102-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-2101 TO PS4-03-RDOS-2102 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-21 - FZ-21 - Power Generation Building - Air Handling Unit |  | PS4-03-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8293 | PS4-03-RDOS-2103-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-2102 TO PS4-03-RDOS-2103 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-21 - FZ-21 - Power Generation Building - Air Handling Unit |  | PS4-03-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8294 | PS4-03-RDOS-G101A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-G101B TO PS4-03-RDOS-G101A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-22 - FZ-G1 Guard House |  | PS4-03-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-8295 | PS4-03-RDOS-G101B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-SEA-0002 TO PS4-03-RDOS-G101B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-22 - FZ-G1 Guard House |  | PS4-03-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-8296 | PS4-03-RDUIR-0701-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1511 TO PS4-03-RDUIR-0701 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area | 2026-07-08 07:22 | PS4-03-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8297 | PS4-03-RDUIR-0702-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1511 TO PS4-03-RDUIR-0702 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area | 2026-07-08 07:25 | PS4-03-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8298 | PS4-03-RDUIR-0703-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1511 TO PS4-03-RDUIR-0703 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area | 2026-07-08 07:27 | PS4-03-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8299 | PS4-03-RDUIR-0704-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1511 TO PS4-03-RDUIR-0704 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area | 2026-07-08 07:29 | PS4-03-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8300 | PS4-03-RDUIR-0705-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1511 TO PS4-03-RDUIR-0705 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area | 2026-07-08 07:31 | PS4-03-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8301 | PS4-03-RDUIR-0907-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1512 TO PS4-03-RDUIR-0907 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8302 | PS4-03-RDUIR-0908-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1512 TO PS4-03-RDUIR-0908 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | 2026-07-22 19:59 | PS4-03-09 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8303 | PS4-03-RDUIR-1007-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1513 TO PS4-03-RDUIR-1007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8304 | PS4-03-RDUIR-1008-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1513 TO PS4-03-RDUIR-1008 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8305 | PS4-03-RDUIR-1107-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1514 TO PS4-03-RDUIR-1107 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8306 | PS4-03-RDUIR-1108-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1514 TO PS4-03-RDUIR-1108 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8307 | PS4-03-RDUIR-1207-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1516 TO PS4-03-RDUIR-1207 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8308 | PS4-03-RDUIR-1208-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-1516 TO PS4-03-RDUIR-1208 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8309 | PS4-03-RMAC-0101-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2504 TO PS4-03-RMAC-0101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-09 04:55 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8310 | PS4-03-RMAC-0102-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2504 TO PS4-03-RMAC-0102 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-09 04:59 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8311 | PS4-03-RMAC-0103-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2504 TO PS4-03-RMAC-0103 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area | 2026-07-09 05:01 | PS4-03-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8313 | PS4-03-RMAC-0301-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2509 TO PS4-03-RMAC-0301 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-03 - FZ-03 - Buildings Area | 2026-07-09 05:56 | PS4-03-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8314 | PS4-03-RMAC-0304-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2509 TO PS4-03-RMAC-0304 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-03 - FZ-03 - Buildings Area | 2026-07-09 05:58 | PS4-03-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8315 | PS4-03-RMAC-0401-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2509 TO PS4-03-RMAC-0401 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | 2026-07-09 05:51 | PS4-03-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-8316 | PS4-03-RMAC-0402-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2509 TO PS4-03-RMAC-0402 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | 2026-07-09 05:53 | PS4-03-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-8317 | PS4-03-RMAC-0613-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2503 TO PS4-03-RMAC-0613 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area | 2026-07-08 07:41 | PS4-03-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8318 | PS4-03-RMAC-0706-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2515 TO PS4-03-RMAC-0706 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area | 2026-07-09 06:28 | PS4-03-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8319 | PS4-03-RMAC-0707-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2515 TO PS4-03-RMAC-0707 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area | 2026-07-09 06:30 | PS4-03-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8321 | PS4-03-RMAC-0825-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2506 TO PS4-03-RMAC-0825 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External | 2026-07-09 05:45 | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8322 | PS4-03-RMAC-0827-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2505 TO PS4-03-RMAC-0827 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External | 2026-07-22 20:05 | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8323 | PS4-03-RMAC-0834-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2514 TO PS4-03-RMAC-0834 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8324 | PS4-03-RMAC-1301-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-BI-2515 TO PS4-03-RMAC-1301 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | 2026-07-09 06:24 | PS4-03-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8325 | PS4-03-RMAC-1409-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-SEA-0003 TO PS4-03-RMAC-1409 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8326 | PS4-03-RMAC-1410-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-2103 TO PS4-03-RMAC-1410 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-21 04:56 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8327 | PS4-03-RMAC-1411-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-1406 TO PS4-03-RMAC-1411 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-21 04:58 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8328 | PS4-03-SEA-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | 2026-07-28 12:05 | PS4-03-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8337 | PS4-05-BI-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 12:08 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8338 | PS4-05-BI-0002-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 12:10 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8339 | PS4-05-BI-0002-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 12:14 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8340 | PS4-05-BI-0002-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 12:18 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8341 | PS4-05-BI-0002-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-11 08:06 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8342 | PS4-05-BI-0002-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-11 08:07 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8345 | PS4-05-BI-0002-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 12:22 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8346 | PS4-05-BI-0002-CJ02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 12:25 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8347 | PS4-05-BI-0002-CJ03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 12:28 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8348 | PS4-05-GC-8100-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 12:33 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8351 | PS4-05-IE-8101-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 12:36 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8352 | PS4-05-IG-0009-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 12:39 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8353 | PS4-05-IG-0009-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 12:44 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8354 | PS4-05-IG-0009-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 12:46 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8355 | PS4-05-LIT-4101-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 13:04 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8356 | PS4-05-UH-8100-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 13:14 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8357 | PS4-05-UH-8100-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-05-IE-8100 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-05-01 - Emergency Diesel Generator Package | 2026-07-28 13:21 | PS4-05-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8397 | PS4-25-BI-1802A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-61-IDH-3100A TO PS4-25-BI-1802A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-06-22 06:54 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8399 | PS4-25-BI-1802B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-61-IDH-3100B TO PS4-25-BI-1802B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-06-21 10:59 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8401 | PS4-25-BI-1802C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-61-IDH-3100C TO PS4-25-BI-1802C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-06-21 11:10 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8428 | PS4-25-ESDV-0021-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1201 TO PS4-25-ESDV-0021 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-09 11:10 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8429 | PS4-25-ESDV-0021-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2201 TO PS4-25-ESDV-0021 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-13 07:09 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8430 | PS4-25-ESDV-0021-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2203 TO PS4-25-ESDV-0021 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-13 07:17 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8431 | PS4-25-ESDV-0023-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1201 TO PS4-25-ESDV-0023 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-07-09 11:12 | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8432 | PS4-25-ESDV-0023-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2201 TO PS4-25-ESDV-0023 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-07-13 07:10 | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8433 | PS4-25-ESDV-0023-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2203 TO PS4-25-ESDV-0023 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-07-13 07:18 | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8434 | PS4-25-ESY-0021A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2205 TO PS4-25-ESDV-0021 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-13 07:19 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8435 | PS4-25-ESY-0021B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2309 TO PS4-25-ESDV-0021 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-13 10:39 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8436 | PS4-25-ESY-0023B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2309 TO PS4-25-ESDV-0023 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-07-13 10:42 | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8437 | PS4-25-FCV-0003A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-FCV-0003A-HPU TO PS4-25-FCV-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-14 06:13 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8438 | PS4-25-FCV-0003B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-FCV-0003B-HPU TO PS4-25-FCV-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-14 06:14 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8439 | PS4-25-FCV-0003C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-FCV-0003C-HPU TO PS4-25-FCV-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-14 06:14 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8440 | PS4-25-FCV-0004-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-FCV-0004-HPU TO PS4-25-FCV-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8441 | PS4-25-FIT-0001-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-25-FIT-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-09 06:35 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8442 | PS4-25-FIT-0003A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-FIT-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-09 07:05 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8443 | PS4-25-FIT-0003B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-FIT-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-09 07:07 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8444 | PS4-25-FIT-0003C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1104 TO PS4-25-FIT-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-09 07:41 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8445 | PS4-25-FIT-0004-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1115 TO PS4-25-FIT-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge | 2026-07-09 11:03 | PS4-25-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8446 | PS4-25-FXS-0003A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2106 TO PS4-25-FCV-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-13 06:14 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8447 | PS4-25-FXS-0003B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2106 TO PS4-25-FCV-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-13 06:15 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8448 | PS4-25-FXS-0003C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2106 TO PS4-25-FCV-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-13 06:16 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8449 | PS4-25-FXS-0004-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2105 TO PS4-25-FCV-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge | 2026-07-13 06:13 | PS4-25-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8450 | PS4-25-FY-0003A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-FCV-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-09 07:09 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8451 | PS4-25-FY-0003B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-FCV-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-09 07:24 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8452 | PS4-25-FY-0003C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1104 TO PS4-25-FCV-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-09 10:44 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8453 | PS4-25-FY-0004-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1115 TO PS4-25-FCV-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge | 2026-07-09 11:04 | PS4-25-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8454 | PS4-25-HS-8101A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-HS-8101A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8455 | PS4-25-HS-8101B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-HS-8101B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8456 | PS4-25-HS-8101C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-HS-8101C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8457 | PS4-25-HS-8102A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-HS-8102A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8458 | PS4-25-HS-8102B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-HS-8102B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8459 | PS4-25-HS-8102C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-HS-8102C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8460 | PS4-25-MOV-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2101 TO PS4-25-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-09 12:16 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8461 | PS4-25-MOV-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2101 TO PS4-25-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-09 12:36 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8462 | PS4-25-MOV-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2101 TO PS4-25-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-09 12:38 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8463 | PS4-25-MOV-0008-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2102 TO PS4-25-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-07-09 12:41 | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8464 | PS4-25-MOV-0011-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2102 TO PS4-25-MOV-0011 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-07-09 12:47 | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8465 | PS4-25-MOV-0012-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2102 TO PS4-25-MOV-0012 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-07-09 12:46 | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8466 | PS4-25-MOV-0025-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2101 TO PS4-25-MOV-0025 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-09 12:21 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8467 | PS4-25-MOV-0026-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2103 TO PS4-25-MOV-0026 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-09 12:49 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8468 | PS4-25-MOV-0026-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-25-MOV-0026 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-09 06:54 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8469 | PS4-25-MOV-0027-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2103 TO PS4-25-MOV-0027 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge | 2026-07-09 12:52 | PS4-25-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8470 | PS4-25-MOV-0027-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-25-MOV-0027 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge | 2026-07-09 06:56 | PS4-25-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8471 | PS4-25-MOV-0028-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2102 TO PS4-25-MOV-0028 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-07-09 12:44 | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8472 | PS4-25-MXS-0001-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2101 TO PS4-25-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-09 12:14 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8473 | PS4-25-MXS-0008-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2102 TO PS4-25-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-07-09 12:39 | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8474 | PS4-25-MXS-0025-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2101 TO PS4-25-MOV-0025 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-09 12:18 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8475 | PS4-25-MXS-0028-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2102 TO PS4-25-MOV-0028 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-07-09 12:43 | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8482 | PS4-25-PDIT-0034A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-PDIT-0034A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-09 07:12 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8483 | PS4-25-PDIT-0034B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-PDIT-0034B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-09 07:39 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8484 | PS4-25-PDIT-0034C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1104 TO PS4-25-PDIT-0034C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-09 10:48 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8485 | PS4-25-PDIT-0050-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-25-PDIT-0050 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge | 2026-07-09 11:47 | PS4-25-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8486 | PS4-25-PI-1102B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-PIT-1102 TO PS4-25-PI-1102B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-14 06:09 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8487 | PS4-25-PI-1202B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-PIT-1202 TO PS4-25-PI-1202B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-07-14 06:10 | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8488 | PS4-25-PIT-0001-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-25-PIT-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-09 06:46 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8489 | PS4-25-PIT-0003AA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-FCV-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-09 07:11 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8490 | PS4-25-PIT-0003BA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-FCV-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-09 07:26 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8491 | PS4-25-PIT-0003CA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1104 TO PS4-25-FCV-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-09 10:46 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8492 | PS4-25-PIT-0004AA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1115 TO PS4-25-FCV-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge | 2026-07-09 11:06 | PS4-25-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8493 | PS4-25-PIT-0004A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-25-PIT-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-09 11:28 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8494 | PS4-25-PIT-0004B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-25-PIT-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-09 11:26 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8495 | PS4-25-PIT-0004C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-25-PIT-0004C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-09 11:45 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8496 | PS4-25-PIT-0005A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-PIT-0005A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-09 07:15 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8497 | PS4-25-PIT-0005B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-PIT-0005B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-09 07:16 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8498 | PS4-25-PIT-0005C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1104 TO PS4-25-PIT-0005C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-09 10:50 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8499 | PS4-25-PIT-0007A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-PIT-0007A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-09 07:18 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8500 | PS4-25-PIT-0007B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-PIT-0007B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-09 07:21 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8501 | PS4-25-PIT-0007C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1104 TO PS4-25-PIT-0007C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-09 10:52 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8502 | PS4-25-PIT-0008A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1301 TO PS4-25-PIT-0008A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-07-09 11:14 | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8503 | PS4-25-PIT-0008B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-25-PIT-0008B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-07-09 11:49 | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8504 | PS4-25-PIT-0008C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-25-PIT-0008C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-07-09 11:41 | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8505 | PS4-25-PIT-0013-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1115 TO PS4-25-PIT-0013 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge | 2026-07-09 11:01 | PS4-25-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8506 | PS4-25-PIT-0018-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-PIT-0018 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-09 07:22 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8507 | PS4-25-PIT-0022-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1301 TO PS4-25-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-09 11:21 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8508 | PS4-25-PIT-0035A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-25-SDV-0035A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-09 11:30 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8509 | PS4-25-PIT-0035B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-25-SDV-0035B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-09 11:32 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8510 | PS4-25-PIT-0035C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-25-SDV-0035C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-09 11:51 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8511 | PS4-25-PIT-0036A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-25-SDV-0036A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-09 11:36 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8512 | PS4-25-PIT-0036B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-25-SDV-0036B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-09 11:53 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8513 | PS4-25-PIT-0036C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-25-SDV-0036C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-09 11:55 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8514 | PS4-25-PIT-0046-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-25-SDV-0046 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass | 2026-07-09 12:01 | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8516 | PS4-25-PIT-0053-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1115 TO PS4-25-XV-0053 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass | 2026-07-09 11:08 | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8517 | PS4-25-PIT-0054A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-25-SDV-0054A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-09 11:39 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8518 | PS4-25-PIT-0054B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-25-SDV-0054B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-09 12:11 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8519 | PS4-25-PIT-0054C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-25-SDV-0054C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-09 12:04 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8520 | PS4-25-PIT-0070-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-XV-0070 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass | 2026-07-09 07:34 | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8524 | PS4-25-PIT-1102-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-25-PIT-1102 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-09 06:37 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8525 | PS4-25-PIT-1202-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-25-PIT-1202 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-07-09 06:39 | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8526 | PS4-25-SDV-0022-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-13 10:31 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8527 | PS4-25-SDV-0022-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-SDV-0022-HPU TO PS4-25-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8528 | PS4-25-SDV-0035A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-SDV-0035A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-13 07:35 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8529 | PS4-25-SDV-0035B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-SDV-0035B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-13 07:36 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8530 | PS4-25-SDV-0035C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2315 TO PS4-25-SDV-0035C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-13 11:38 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8531 | PS4-25-SDV-0036A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-SDV-0036A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-13 07:37 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8532 | PS4-25-SDV-0036B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2315 TO PS4-25-SDV-0036B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-13 17:47 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8533 | PS4-25-SDV-0036C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2315 TO PS4-25-SDV-0036C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-13 17:48 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8534 | PS4-25-SDV-0046-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-SDV-0046 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass | 2026-07-13 07:38 | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8537 | PS4-25-SDV-0054A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-SDV-0054A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-13 10:28 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8538 | PS4-25-SDV-0054B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-25-SDV-0054B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-13 10:29 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8539 | PS4-25-SDV-0054C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2315 TO PS4-25-SDV-0054C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-13 17:55 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8541 | PS4-25-SXS-0022-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2302 TO PS4-25-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-13 07:33 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8542 | PS4-25-SXS-0035A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2301 TO PS4-25-SDV-0035A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-13 07:26 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8543 | PS4-25-SXS-0035B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2301 TO PS4-25-SDV-0035B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-13 07:27 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8544 | PS4-25-SXS-0035C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2312 TO PS4-25-SDV-0035C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-13 10:44 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8545 | PS4-25-SXS-0036A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2301 TO PS4-25-SDV-0036A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8546 | PS4-25-SXS-0036B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2312 TO PS4-25-SDV-0036B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-13 10:46 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8547 | PS4-25-SXS-0036C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2312 TO PS4-25-SDV-0036C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-13 10:47 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8548 | PS4-25-SXS-0046-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2312 TO PS4-25-SDV-0046 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass | 2026-07-13 10:49 | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8550 | PS4-25-SXS-0054A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2301 TO PS4-25-SDV-0054A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-13 07:31 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8551 | PS4-25-SXS-0054B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2312 TO PS4-25-SDV-0054B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-13 10:51 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8552 | PS4-25-SXS-0054C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2312 TO PS4-25-SDV-0054C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-13 10:56 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8553 | PS4-25-SY-0022-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2308 TO PS4-25-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-13 10:34 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8554 | PS4-25-SY-0035AA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2308 TO PS4-25-SDV-0035A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8555 | PS4-25-SY-0035AB-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2109 TO PS4-25-SDV-0035A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-13 06:23 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8556 | PS4-25-SY-0035BA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2308 TO PS4-25-SDV-0035B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8557 | PS4-25-SY-0035BB-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2109 TO PS4-25-SDV-0035B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-13 06:24 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8558 | PS4-25-SY-0035CA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2316 TO PS4-25-SDV-0035C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-13 17:58 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8559 | PS4-25-SY-0035CB-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2108 TO PS4-25-SDV-0035C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-13 06:17 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8560 | PS4-25-SY-0036AA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2308 TO PS4-25-SDV-0036A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8561 | PS4-25-SY-0036AB-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2109 TO PS4-25-SDV-0036A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-13 06:28 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8562 | PS4-25-SY-0036BA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2316 TO PS4-25-SDV-0036B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-13 18:01 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8563 | PS4-25-SY-0036BB-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2108 TO PS4-25-SDV-0036B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-13 06:19 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8564 | PS4-25-SY-0036CA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2316 TO PS4-25-SDV-0036C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-13 18:00 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8565 | PS4-25-SY-0036CB-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2108 TO PS4-25-SDV-0036C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-13 06:20 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8566 | PS4-25-SY-0046A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2308 TO PS4-25-SDV-0046 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8567 | PS4-25-SY-0046B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2109 TO PS4-25-SDV-0046 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass | 2026-07-13 06:36 | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8569 | PS4-25-SY-0052B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2316 TO PS4-25-SDV-0052 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-07-13 18:08 | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8570 | PS4-25-SY-0054AA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2308 TO PS4-25-SDV-0054A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8571 | PS4-25-SY-0054AB-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2109 TO PS4-25-SDV-0054A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-13 06:32 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8572 | PS4-25-SY-0054BA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2316 TO PS4-25-SDV-0054B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-13 18:02 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8573 | PS4-25-SY-0054BB-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2108 TO PS4-25-SDV-0054B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-13 06:22 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8574 | PS4-25-SY-0054CA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2316 TO PS4-25-SDV-0054C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-13 18:03 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8575 | PS4-25-SY-0054CB-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2108 TO PS4-25-SDV-0054C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-13 06:23 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8576 | PS4-25-TIT-0001-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-25-TIT-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-09 06:41 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8577 | PS4-25-TIT-0002A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-25-TIT-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-09 11:22 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8578 | PS4-25-TIT-0002B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-25-TIT-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-09 11:25 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8579 | PS4-25-TIT-0002C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-25-TIT-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-09 11:43 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8580 | PS4-25-TIT-0003A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-TIT-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-09 07:30 | PS4-25-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8581 | PS4-25-TIT-0003B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-25-TIT-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-09 07:32 | PS4-25-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8582 | PS4-25-TIT-0003C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1104 TO PS4-25-TIT-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C | 2026-07-09 10:55 | PS4-25-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8583 | PS4-25-TIT-0004-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-25-TIT-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge | 2026-07-09 06:44 | PS4-25-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8584 | PS4-25-TIT-1101-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-25-TIT-1101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-09 06:50 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8585 | PS4-25-TIT-1201-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-25-TIT-1201 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-07-09 06:52 | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8586 | PS4-25-XV-0053-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2104 TO PS4-25-XV-0053 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass | 2026-07-09 12:54 | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8587 | PS4-25-XV-0053-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-XV-0053-HPU TO PS4-25-XV-0053 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8588 | PS4-25-XV-0070-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2104 TO PS4-25-XV-0070 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass | 2026-07-09 12:56 | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8589 | PS4-25-XXS-0053-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2105 TO PS4-25-XV-0053 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass | 2026-07-13 06:02 | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8590 | PS4-25-XXS-0070-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2105 TO PS4-25-XV-0070 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass | 2026-07-13 06:08 | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8591 | PS4-25-XY-0053-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2109 TO PS4-25-XV-0053 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass | 2026-07-13 06:36 | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8592 | PS4-25-XY-0070-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2109 TO PS4-25-XV-0070 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass | 2026-07-13 07:08 | PS4-25-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8593 | PS4-25-ZIT-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1102 TO PS4-25-ZIT-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-09 07:00 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8594 | PS4-25-ZIT-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1102 TO PS4-25-ZIT-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-07-09 07:03 | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8595 | PS4-25-ZS-1101-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2104 TO PS4-25-ZS-1101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver | 2026-07-09 12:58 | PS4-25-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8596 | PS4-25-ZS-1201-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2104 TO PS4-25-ZS-1201 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher | 2026-07-12 08:40 | PS4-25-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8604 | PS4-28-HXA-1402-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2115 TO PS4-28-HXA-1402 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 | 2026-07-14 05:40 | PS4-28-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8605 | PS4-28-HY-3901A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1105 TO PS4-28-HY-3901A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump | 2026-07-13 18:12 | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8606 | PS4-28-HY-3901B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1105 TO PS4-28-HY-3901B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump | 2026-07-13 18:14 | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8609 | PS4-28-LI-1101B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-LIT-1101 TO PS4-28-LI-1101B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 | 2026-07-14 06:11 | PS4-28-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone G | TM-00254 | sridhar, muthu
T-00254-8610 | PS4-28-LI-1101C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1101 TO PS4-28-LI-1101C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 | 2026-07-09 06:58 | PS4-28-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone G | TM-00254 | sridhar, muthu
T-00254-8611 | PS4-28-LI-1402B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-LIT-1402 TO PS4-28-LI-1402B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 | 2026-07-14 06:12 | PS4-28-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8612 | PS4-28-LIT-0002-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-50-BI-1107 TO PS4-28-LIT-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps | 2026-07-13 18:48 | PS4-28-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone G | TM-00254 | sridhar, muthu
T-00254-8613 | PS4-28-LIT-0008-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-50-BI-1107 TO PS4-28-LIT-0008 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps | 2026-07-13 18:51 | PS4-28-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone G | TM-00254 | sridhar, muthu
T-00254-8614 | PS4-28-LIT-1101-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1105 TO PS4-28-LIT-1101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 | 2026-07-13 18:10 | PS4-28-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone G | TM-00254 | sridhar, muthu
T-00254-8615 | PS4-28-LIT-1102-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1303 TO PS4-28-LIT-1102 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 | 2026-07-13 18:29 | PS4-28-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone G | TM-00254 | sridhar, muthu
T-00254-8616 | PS4-28-LIT-1201-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1106 TO PS4-28-LIT-1201 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump | 2026-07-13 18:16 | PS4-28-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone G | TM-00254 | sridhar, muthu
T-00254-8617 | PS4-28-LIT-1202-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1303 TO PS4-28-LIT-1202 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump | 2026-07-13 18:32 | PS4-28-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone G | TM-00254 | sridhar, muthu
T-00254-8618 | PS4-28-LIT-1301A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-28-LIT-1301A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A | 2026-07-09 07:36 | PS4-28-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8619 | PS4-28-LIT-1301B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1103 TO PS4-28-LIT-1301B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B | 2026-07-09 07:28 | PS4-28-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8620 | PS4-28-LIT-1301C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1104 TO PS4-28-LIT-1301C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C | 2026-07-09 10:59 | PS4-28-15 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8621 | PS4-28-LIT-1401-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1307 TO PS4-28-LIT-1401 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 | 2026-07-13 18:43 | PS4-28-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8622 | PS4-28-LIT-1402-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1114 TO PS4-28-LIT-1402 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Submitted | PS4 - Milestone E | TM-00254
T-00254-8623 | PS4-28-PIT-0015-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1105 TO PS4-28-PIT-0015 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 | 2026-07-13 18:09 | PS4-28-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone G | TM-00254 | sridhar, muthu
T-00254-8624 | PS4-28-PIT-0033-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1106 TO PS4-28-PIT-0033 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump | 2026-07-13 18:18 | PS4-28-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone G | TM-00254 | sridhar, muthu
T-00254-8625 | PS4-28-PIT-0041-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1303 TO PS4-28-PIT-0041 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump | 2026-07-13 18:34 | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8626 | PS4-28-PIT-0045-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1303 TO PS4-28-SDV-0045 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump | 2026-07-13 18:35 | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8627 | PS4-28-PIT-0053A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-28-SDV-0053A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A | 2026-07-09 11:34 | PS4-28-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8628 | PS4-28-PIT-0053B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1302 TO PS4-28-SDV-0053B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B | 2026-07-09 11:38 | PS4-28-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8629 | PS4-28-PIT-0053C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-1310 TO PS4-28-SDV-0053C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C | 2026-07-09 12:09 | PS4-28-15 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8630 | PS4-28-PIT-3901A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1303 TO PS4-28-PIT-3901A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump | 2026-07-13 18:39 | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8631 | PS4-28-PIT-3901B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1303 TO PS4-28-PIT-3901B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump | 2026-07-13 18:41 | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8632 | PS4-28-SDV-0045-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-2304 TO PS4-28-SDV-0045 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump | 2026-07-13 18:47 | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8633 | PS4-28-SDV-0045-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-SDV-0045-HPU TO PS4-28-SDV-0045 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump | 2026-07-14 06:18 | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8634 | PS4-28-SDV-0053A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2305 TO PS4-28-SDV-0053A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A | 2026-07-13 10:33 | PS4-28-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8635 | PS4-28-SDV-0053A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-SDV-0053A-HPU TO PS4-28-SDV-0053A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8636 | PS4-28-SDV-0053B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2315 TO PS4-28-SDV-0053B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B | 2026-07-13 17:49 | PS4-28-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8637 | PS4-28-SDV-0053B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-SDV-0053B-HPU TO PS4-28-SDV-0053B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8638 | PS4-28-SDV-0053C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2315 TO PS4-28-SDV-0053C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C | 2026-07-13 17:50 | PS4-28-15 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8639 | PS4-28-SDV-0053C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-SDV-0053C-HPU TO PS4-28-SDV-0053C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-8640 | PS4-28-SXS-0045-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2302 TO PS4-28-SDV-0045 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump | 2026-07-13 07:34 | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8641 | PS4-28-SXS-0053A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2301 TO PS4-28-SDV-0053A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A | 2026-07-13 07:28 | PS4-28-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8642 | PS4-28-SXS-0053B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2301 TO PS4-28-SDV-0053B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B | 2026-07-13 07:30 | PS4-28-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8643 | PS4-28-SXS-0053C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2312 TO PS4-28-SDV-0053C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C | 2026-07-13 10:50 | PS4-28-15 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8644 | PS4-28-SY-0045A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2309 TO PS4-28-SDV-0045 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump | 2026-07-13 10:43 | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8645 | PS4-28-SY-0045B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2109 TO PS4-28-SDV-0045 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump | 2026-07-13 06:34 | PS4-28-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8646 | PS4-28-SY-0053AA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2308 TO PS4-28-SDV-0053A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A | 2026-07-13 10:37 | PS4-28-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8647 | PS4-28-SY-0053AB-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2109 TO PS4-28-SDV-0053A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A | 2026-07-13 06:31 | PS4-28-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8648 | PS4-28-SY-0053BA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2308 TO PS4-28-SDV-0053B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B | 2026-07-13 10:38 | PS4-28-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8649 | PS4-28-SY-0053BB-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2109 TO PS4-28-SDV-0053B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B | 2026-07-13 06:31 | PS4-28-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8650 | PS4-28-SY-0053CA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2316 TO PS4-28-SDV-0053C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C | 2026-07-13 18:04 | PS4-28-15 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8651 | PS4-28-SY-0053CB-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2108 TO PS4-28-SDV-0053C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C | 2026-07-13 06:21 | PS4-28-15 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-8652 | PS4-28-TIT-1104-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1105 TO PS4-28-TIT-1104 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 | 2026-07-13 18:11 | PS4-28-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone G | TM-00254 | sridhar, muthu
T-00254-8653 | PS4-28-TIT-1105-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1303 TO PS4-28-TIT-1105 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 | 2026-07-13 18:38 | PS4-28-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone G | TM-00254 | sridhar, muthu
T-00254-8654 | PS4-28-TIT-1201-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1106 TO PS4-28-TIT-1201 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump | 2026-07-13 18:19 | PS4-28-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone G | TM-00254 | sridhar, muthu
T-00254-8655 | PS4-28-TIT-1401-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1114 TO PS4-28-TIT-1401 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 | 2026-07-13 18:25 | PS4-28-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8656 | PS4-28-TIT-1402-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1307 TO PS4-28-TIT-1402 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 | 2026-07-13 18:42 | PS4-28-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8657 | PS4-28-TIT-2101-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1303 TO PS4-28-TIT-2101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone G | TM-00254
T-00254-8658 | PS4-28-TIT-2201-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1307 TO PS4-28-TIT-2201 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8660 | PS4-50-FIT-0001-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-50-BI-1107 TO PS4-50-FIT-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-50-03 - Water Pre-Treatment Package | 2026-07-13 18:50 | PS4-50-03 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-8668 | PS4-53-LIT-4101-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-53-BI-1108 TO PS4-53-LIT-4101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-53-01 - Utility Water / Storage Tank | 2026-07-13 18:53 | PS4-53-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8669 | PS4-53-LIT-4102-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-53-BI-1304 TO PS4-53-LIT-4102 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-53-01 - Utility Water / Storage Tank | 2026-07-13 18:57 | PS4-53-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone C | TM-00254 | sridhar, muthu
T-00254-8670 | PS4-53-PIT-0005-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-53-BI-1108 TO PS4-53-PIT-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-53-02 - Water Distribution Pump A/B | 2026-07-13 18:55 | PS4-53-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8671 | PS4-60-BE-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-BE-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-27 - Compressed Air Starting Skid | 2026-06-21 08:20 | PS4-60-27 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8672 | PS4-60-BE-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-BE-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-26 - Instrument Air Compressor Skid | 2026-06-21 08:22 | PS4-60-26 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8673 | PS4-60-BE-0004A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0001A TO PS4-60-BE-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-49 - Lube Oil Separator Module PS4-60-UO-81100A | 2026-06-26 11:17 | PS4-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8674 | PS4-60-BE-0004B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0001B TO PS4-60-BE-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-50 - Lube Oil Separator Module PS4-60-UO-81100B | 2026-06-26 11:19 | PS4-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8675 | PS4-60-BE-0004C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0001C TO PS4-60-BE-0004C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-51 - Lube Oil Separator Module PS4-60-UO-81100C | 2026-07-06 06:23 | PS4-60-51 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8676 | PS4-60-BE-0004D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0001D TO PS4-60-BE-0004D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-52 - Lube Oil Separator Module PS4-60-UO-81100D | 2026-07-06 06:22 | PS4-60-52 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8677 | PS4-60-BE-0004E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0001E TO PS4-60-BE-0004E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-53 - Lube Oil Separator Module PS4-60-UO-81100E | 2026-07-06 06:21 | PS4-60-53 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8678 | PS4-60-BE-0004F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0001F TO PS4-60-BE-0004F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-54 - Lube Oil Separator Module PS4-60-UO-81100F | 2026-07-06 06:28 | PS4-60-54 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8679 | PS4-60-BE-0004G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0001G TO PS4-60-BE-0004G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-55 - Lube Oil Separator Module PS4-60-UO-81100G | 2026-07-06 06:30 | PS4-60-55 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8680 | PS4-60-BI-0001A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-21 07:04 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8681 | PS4-60-BI-0001A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-21 07:00 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8682 | PS4-60-BI-0001B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-21 07:08 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8683 | PS4-60-BI-0001B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-21 07:02 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8684 | PS4-60-BI-0001C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0001C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-06-21 07:10 | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8685 | PS4-60-BI-0001C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0001C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-8686 | PS4-60-BI-0001D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0001D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-21 07:13 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8687 | PS4-60-BI-0001D-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0001D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-06 06:26 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8688 | PS4-60-BI-0001E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0001E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-06-21 07:15 | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8689 | PS4-60-BI-0001E-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0001E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-06 06:25 | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8690 | PS4-60-BI-0001F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0001F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-21 07:18 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8691 | PS4-60-BI-0001F-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0001F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-06 06:24 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8692 | PS4-60-BI-0001G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0001G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-06-21 07:25 | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8693 | PS4-60-BI-0001G-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0001G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8694 | PS4-60-BI-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-23 14:24 | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8695 | PS4-60-BI-0002-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-22 07:06 | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8696 | PS4-60-BI-0002-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-21 06:58 | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8697 | PS4-60-BI-0002-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-21 06:56 | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8698 | PS4-60-BI-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-21 14:12 | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8699 | PS4-60-BI-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-06-22 05:37 | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8700 | PS4-60-BI-0004A-CCO1 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-BI-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-20 17:43 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8701 | PS4-60-BI-0004B-CCO1 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-BI-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-20 17:47 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8702 | PS4-60-BI-0004C-CCO1 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-BI-0004C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-8703 | PS4-60-BI-0004D-CCO1 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-BI-0004D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-20 17:55 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8704 | PS4-60-BI-0004E-CCO1 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-BI-0004E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-8705 | PS4-60-BI-0004F-CCO1 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001F TO PS4-60-BI-0004F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-20 17:59 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8706 | PS4-60-BI-0004G-CCO1 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001G TO PS4-60-BI-0004G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8707 | PS4-60-BI-0005A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0005A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-22 07:11 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8708 | PS4-60-BI-0005A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0005A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-22 07:16 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8709 | PS4-60-BI-0005B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0005B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-22 07:20 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8710 | PS4-60-BI-0005B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0005B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-22 07:25 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8711 | PS4-60-BI-0005C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0005C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-06-22 07:57 | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8712 | PS4-60-BI-0005C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0005C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-06-22 08:10 | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8713 | PS4-60-BI-0005D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0005D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-22 08:14 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8714 | PS4-60-BI-0005D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0005D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-22 08:20 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8715 | PS4-60-BI-0005E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0005E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-06-22 08:27 | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8716 | PS4-60-BI-0005E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0005E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-06-22 08:39 | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8717 | PS4-60-BI-0005F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0005F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-22 08:42 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8718 | PS4-60-BI-0005F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0005F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-22 08:47 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8719 | PS4-60-BI-0005G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0005G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-06-22 08:51 | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8720 | PS4-60-BI-0005G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0005G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-06-22 08:59 | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8721 | PS4-60-BI-0006A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-06 07:02 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8722 | PS4-60-BI-0006A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-06-22 13:19 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8723 | PS4-60-BI-0006A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-06-26 11:39 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8724 | PS4-60-BI-0006A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-06-24 12:22 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8725 | PS4-60-BI-0006A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-06-26 11:21 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8726 | PS4-60-BI-0006A-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0006A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-06-26 11:41 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8727 | PS4-60-BI-0006B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-06 07:04 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8728 | PS4-60-BI-0006B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-06-22 14:09 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8729 | PS4-60-BI-0006B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-06-26 11:43 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8730 | PS4-60-BI-0006B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-06-24 12:24 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8731 | PS4-60-BI-0006B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-06-26 11:24 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8732 | PS4-60-BI-0006B-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0006B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-06-26 11:47 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8733 | PS4-60-BI-0006C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-07-06 07:06 | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8734 | PS4-60-BI-0006C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) | 2026-06-26 12:39 | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8735 | PS4-60-BI-0006C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) | 2026-06-26 11:57 | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8736 | PS4-60-BI-0006C-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) | 2026-06-24 12:26 | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8737 | PS4-60-BI-0006C-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) | 2026-06-26 11:26 | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8738 | PS4-60-BI-0006C-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0006C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) | 2026-06-26 11:59 | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8739 | PS4-60-BI-0006D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-07-06 07:09 | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8740 | PS4-60-BI-0006D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) | 2026-06-26 13:00 | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8741 | PS4-60-BI-0006D-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) | 2026-06-26 12:01 | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8742 | PS4-60-BI-0006D-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) | 2026-06-24 12:36 | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8743 | PS4-60-BI-0006D-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) | 2026-06-26 11:28 | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8744 | PS4-60-BI-0006D-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0006D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) | 2026-06-26 12:04 | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8745 | PS4-60-BI-0006E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-07-06 07:13 | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8746 | PS4-60-BI-0006E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) | 2026-06-26 13:33 | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8747 | PS4-60-BI-0006E-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) | 2026-06-26 12:06 | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8748 | PS4-60-BI-0006E-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) | 2026-06-24 12:39 | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8749 | PS4-60-BI-0006E-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) | 2026-06-26 11:31 | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8750 | PS4-60-BI-0006E-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0006E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) | 2026-06-26 12:08 | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8751 | PS4-60-BI-0006F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-07-06 07:19 | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8752 | PS4-60-BI-0006F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) | 2026-06-26 13:36 | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8753 | PS4-60-BI-0006F-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) | 2026-06-26 12:11 | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8754 | PS4-60-BI-0006F-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) | 2026-06-24 12:46 | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8755 | PS4-60-BI-0006F-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) | 2026-06-26 11:35 | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8756 | PS4-60-BI-0006F-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0006F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) | 2026-06-26 12:13 | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8757 | PS4-60-BI-0006G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-07-06 07:24 | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8758 | PS4-60-BI-0006G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) | 2026-06-26 13:39 | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8759 | PS4-60-BI-0006G-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) | 2026-06-26 12:16 | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8760 | PS4-60-BI-0006G-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) | 2026-06-24 12:49 | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8761 | PS4-60-BI-0006G-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) | 2026-06-26 11:37 | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8762 | PS4-60-BI-0006G-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0006G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) | 2026-06-26 12:25 | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8763 | PS4-60-BI-0008A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-11 11:13 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8764 | PS4-60-BI-0008A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IH-0001A TO PS4-60-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-11 12:10 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8765 | PS4-60-BI-0008B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-11 11:14 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8766 | PS4-60-BI-0008B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IH-0001A TO PS4-60-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-11 12:11 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8767 | PS4-60-BI-0009A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0009A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-11 11:16 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8768 | PS4-60-BI-0009A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IH-0001B TO PS4-60-BI-0009A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-11 12:13 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8769 | PS4-60-BI-0009B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0009B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-11 11:18 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8770 | PS4-60-BI-0009B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IH-0001B TO PS4-60-BI-0009B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-11 12:15 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8771 | PS4-60-BI-0010A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0010A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-11 11:20 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8772 | PS4-60-BI-0010A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IH-0001C TO PS4-60-BI-0010A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-20 18:03 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8773 | PS4-60-BI-0010B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0010B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-11 11:22 | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8774 | PS4-60-BI-0010B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IH-0001C TO PS4-60-BI-0010B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-07-11 12:17 | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8775 | PS4-60-BI-0011A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-20 18:05 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8776 | PS4-60-BI-0011A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IH-0001D TO PS4-60-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-20 18:08 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8777 | PS4-60-BI-0011B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-20 18:11 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8778 | PS4-60-BI-0011B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IH-0001D TO PS4-60-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-07-11 12:19 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8779 | PS4-60-BI-0012A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0012A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-20 18:16 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8780 | PS4-60-BI-0012A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IH-0001E TO PS4-60-BI-0012A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-11 12:21 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8781 | PS4-60-BI-0012B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0012B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone D | TM-00254
T-00254-8782 | PS4-60-BI-0012B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IH-0001E TO PS4-60-BI-0012B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-07-11 12:24 | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8783 | PS4-60-BI-0013A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0013A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-20 18:19 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8784 | PS4-60-BI-0013A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IH-0001F TO PS4-60-BI-0013A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-20 18:23 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8785 | PS4-60-BI-0013B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0013B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-20 18:27 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8786 | PS4-60-BI-0013B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IH-0001F TO PS4-60-BI-0013B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-07-20 18:31 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8787 | PS4-60-BI-0014A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0014A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-20 18:34 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8788 | PS4-60-BI-0014A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IH-0001G TO PS4-60-BI-0014A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-11 12:26 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8789 | PS4-60-BI-0014B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0014B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8790 | PS4-60-BI-0014B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IH-0001G TO PS4-60-BI-0014B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone E | TM-00254
T-00254-8791 | PS4-60-BI-0016A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-22 05:43 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8792 | PS4-60-BI-0016A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-24 13:24 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8793 | PS4-60-BI-0016A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-11 08:05 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8794 | PS4-60-BI-0016A-CCO4 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-BI-0016A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-24 12:51 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8795 | PS4-60-BI-0016B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-22 05:47 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8796 | PS4-60-BI-0016B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-24 13:27 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8797 | PS4-60-BI-0016B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-21 07:59 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8798 | PS4-60-BI-0016B-CCO4 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-BI-0016B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-24 12:56 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8799 | PS4-60-BI-0016C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-06-22 05:55 | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8800 | PS4-60-BI-0016C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-06-24 13:29 | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8801 | PS4-60-BI-0016C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-06-21 08:01 | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8802 | PS4-60-BI-0016C-CCO4 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-BI-0016C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-06-24 12:58 | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8803 | PS4-60-BI-0016D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-22 06:02 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8804 | PS4-60-BI-0016D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-24 13:36 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8805 | PS4-60-BI-0016D-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-21 08:03 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8806 | PS4-60-BI-0016D-CCO4 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-BI-0016D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-24 13:01 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8807 | PS4-60-BI-0016E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0016E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-06-22 06:29 | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8808 | PS4-60-BI-0016E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0016E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-06-24 13:41 | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8809 | PS4-60-BI-0016E-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0016E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-06-21 08:08 | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8810 | PS4-60-BI-0016E-CCO4 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-BI-0016E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-06-24 13:15 | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8811 | PS4-60-BI-0016F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0016F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-22 06:35 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8812 | PS4-60-BI-0016F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0016F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-24 13:59 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8813 | PS4-60-BI-0016F-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0016F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-21 08:11 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8814 | PS4-60-BI-0016F-CCO4 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001F TO PS4-60-BI-0016F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-24 13:17 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8815 | PS4-60-BI-0016G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0016G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-06-22 06:42 | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8816 | PS4-60-BI-0016G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0016G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-06-24 14:01 | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8817 | PS4-60-BI-0016G-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0016G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-06-21 08:14 | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8818 | PS4-60-BI-0016G-CCO4 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001G TO PS4-60-BI-0016G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-06-24 13:22 | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8819 | PS4-60-BI-0017A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002A TO PS4-60-BI-0017A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-56 - Fuel Conditioning Module PS4-60-UZ-8900A | 2026-06-27 11:31 | PS4-60-56 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8820 | PS4-60-BI-0017B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002B TO PS4-60-BI-0017B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-58 - Fuel Conditioning Module PS4-60-UZ-8900B | 2026-06-27 11:32 | PS4-60-58 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8821 | PS4-60-BI-0017C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002C TO PS4-60-BI-0017C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-60 - Fuel Conditioning Module PS4-60-UZ-8900C | 2026-06-27 11:35 | PS4-60-60 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8822 | PS4-60-BI-0017D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002D TO PS4-60-BI-0017D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-62 - Fuel Conditioning Module PS4-60-UZ-8900D | 2026-06-27 11:37 | PS4-60-62 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8823 | PS4-60-BI-0017E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002E TO PS4-60-BI-0017E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-64 - Fuel Conditioning Module PS4-60-UZ-8900E | 2026-06-27 11:39 | PS4-60-64 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8824 | PS4-60-BI-0017F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002F TO PS4-60-BI-0017F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-66 - Fuel Conditioning Module PS4-60-UZ-8900F | 2026-06-27 11:41 | PS4-60-66 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8825 | PS4-60-BI-0017G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IN-0002G TO PS4-60-BI-0017G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-68 - Fuel Conditioning Module PS4-60-UZ-8900G | 2026-06-27 11:46 | PS4-60-68 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8826 | PS4-60-BI-0019A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0019A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-23 11:49 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8827 | PS4-60-BI-0019A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-BI-0019A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-23 12:30 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8828 | PS4-60-BI-0019B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0019B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-23 11:52 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8829 | PS4-60-BI-0019B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-BI-0019B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-23 12:33 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8830 | PS4-60-BI-0019C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0019C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-06-23 11:54 | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8831 | PS4-60-BI-0019C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-BI-0019C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-06-23 12:38 | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8832 | PS4-60-BI-0019D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0019D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-23 11:58 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8833 | PS4-60-BI-0019D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-BI-0019D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-23 12:46 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8834 | PS4-60-BI-0019E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0019E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-06-23 12:09 | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8835 | PS4-60-BI-0019E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-BI-0019E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-06-23 12:48 | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8836 | PS4-60-BI-0019F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0019F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-23 12:12 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8837 | PS4-60-BI-0019F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-BI-0019F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-23 12:51 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8838 | PS4-60-BI-0019G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0019G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-06-23 12:15 | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8839 | PS4-60-BI-0019G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-BI-0019G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-06-23 12:53 | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8840 | PS4-60-IE-0002B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002A TO PS4-60-IE-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-26 08:53 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8841 | PS4-60-IE-0002C-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002B TO PS4-60-IE-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-06-26 08:56 | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8842 | PS4-60-IE-0002D-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002C TO PS4-60-IE-0002D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-26 10:58 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8843 | PS4-60-IE-0002E-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002D TO PS4-60-IE-0002E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-06-26 11:02 | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8844 | PS4-60-IE-0002F-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002E TO PS4-60-IE-0002F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-26 11:05 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8845 | PS4-60-IE-0002G-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002F TO PS4-60-IE-0002G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-06-26 11:12 | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8846 | PS4-60-IE-0003A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-24 10:34 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8847 | PS4-60-IE-0003A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-24 10:33 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8848 | PS4-60-IE-0003A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-22 14:21 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8849 | PS4-60-IE-0003A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-24 11:21 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8850 | PS4-60-IE-0003A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-24 11:54 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8851 | PS4-60-IE-0003A-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-23 12:56 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8852 | PS4-60-IE-0003A-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-22 10:23 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8853 | PS4-60-IE-0003A-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-23 14:26 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8854 | PS4-60-IE-0003A-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-23 14:28 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8855 | PS4-60-IE-0003A-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-23 14:30 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8856 | PS4-60-IE-0003A-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-23 14:36 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8857 | PS4-60-IE-0003A-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-21 14:10 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8858 | PS4-60-IE-0003A-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-23 12:59 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8859 | PS4-60-IE-0003A-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-23 13:10 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8864 | PS4-60-IE-0003A-CC25 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-TX-41100A TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-21 10:52 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8865 | PS4-60-IE-0003A-CC26 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-TX-41100B TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-06-21 10:54 | PS4-60-02 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8866 | PS4-60-IE-0003B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-24 10:36 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8867 | PS4-60-IE-0003B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-24 10:49 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8868 | PS4-60-IE-0003B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-22 14:26 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8869 | PS4-60-IE-0003B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-24 11:24 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8870 | PS4-60-IE-0003B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-24 11:41 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8871 | PS4-60-IE-0003B-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-22 10:28 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8872 | PS4-60-IE-0003B-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-22 10:32 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8873 | PS4-60-IE-0003B-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-23 14:39 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8874 | PS4-60-IE-0003B-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-23 14:41 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8875 | PS4-60-IE-0003B-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-27 11:50 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8876 | PS4-60-IE-0003B-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-27 11:52 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8877 | PS4-60-IE-0003B-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-20 18:38 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8878 | PS4-60-IE-0003B-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-23 13:19 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8879 | PS4-60-IE-0003B-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-23 13:22 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8884 | PS4-60-IE-0003B-CC25 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-TX-41200A TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-21 11:02 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8885 | PS4-60-IE-0003B-CC26 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-TX-41200B TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-06-21 11:05 | PS4-60-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8886 | PS4-60-IE-0003C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-06-24 10:53 | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8887 | PS4-60-IE-0003C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-06-24 10:57 | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8888 | PS4-60-IE-0003C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-06-22 14:31 | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8889 | PS4-60-IE-0003C-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-06-24 11:27 | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8890 | PS4-60-IE-0003C-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-06-24 11:43 | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8891 | PS4-60-IE-0003C-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-06-22 10:36 | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8892 | PS4-60-IE-0003C-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-06-22 10:42 | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8893 | PS4-60-IE-0003C-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-06-24 05:31 | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8894 | PS4-60-IE-0003C-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-06-24 05:33 | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8895 | PS4-60-IE-0003C-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-06-27 11:55 | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8896 | PS4-60-IE-0003C-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-06-27 11:57 | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8897 | PS4-60-IE-0003C-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-06-23 12:17 | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8898 | PS4-60-IE-0003C-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-06-23 13:24 | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8899 | PS4-60-IE-0003C-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002C TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-06-23 13:27 | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8904 | PS4-60-IE-0003C-CC25 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-TX-41300A TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-06-21 11:07 | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8905 | PS4-60-IE-0003C-CC26 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-TX-41300B TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-06-21 11:09 | PS4-60-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8906 | PS4-60-IE-0003D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-06-24 10:59 | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8907 | PS4-60-IE-0003D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-06-24 11:01 | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8908 | PS4-60-IE-0003D-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-06-22 14:33 | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8909 | PS4-60-IE-0003D-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-06-24 11:32 | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8910 | PS4-60-IE-0003D-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-06-24 11:46 | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8911 | PS4-60-IE-0003D-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-06-22 10:47 | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8912 | PS4-60-IE-0003D-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-06-22 11:27 | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8913 | PS4-60-IE-0003D-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-06-24 05:36 | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8914 | PS4-60-IE-0003D-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-06-24 05:54 | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8915 | PS4-60-IE-0003D-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-06-27 11:59 | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8916 | PS4-60-IE-0003D-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-06-27 12:02 | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8917 | PS4-60-IE-0003D-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-06-23 12:19 | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8918 | PS4-60-IE-0003D-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-06-23 13:30 | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8919 | PS4-60-IE-0003D-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002D TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-06-23 13:35 | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8924 | PS4-60-IE-0003D-CC25 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-TX-41400A TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-06-21 11:39 | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8925 | PS4-60-IE-0003D-CC26 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-TX-41400B TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-06-21 11:41 | PS4-60-11 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8926 | PS4-60-IE-0003E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-06-24 11:05 | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8927 | PS4-60-IE-0003E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-06-24 11:08 | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8928 | PS4-60-IE-0003E-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-06-22 14:37 | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8929 | PS4-60-IE-0003E-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-06-24 11:34 | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8930 | PS4-60-IE-0003E-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IE-0001E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-06-24 11:48 | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8931 | PS4-60-IE-0003E-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-06-22 11:34 | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8932 | PS4-60-IE-0003E-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-06-22 11:39 | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8933 | PS4-60-IE-0003E-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-06-24 05:59 | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8934 | PS4-60-IE-0003E-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-06-24 06:06 | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8935 | PS4-60-IE-0003E-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-06-27 12:11 | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8936 | PS4-60-IE-0003E-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-06-27 12:13 | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8937 | PS4-60-IE-0003E-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-06-23 12:22 | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8938 | PS4-60-IE-0003E-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-06-23 13:55 | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8939 | PS4-60-IE-0003E-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002E TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-06-23 14:09 | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8944 | PS4-60-IE-0003E-CC25 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-TX-41500A TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-06-21 11:43 | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8945 | PS4-60-IE-0003E-CC26 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-TX-41500B TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-06-21 11:46 | PS4-60-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8946 | PS4-60-IE-0003F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IF-0003F TO PS4-60-IF-0001F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-06-24 11:11 | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8947 | PS4-60-IE-0003F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IF-0003F TO PS4-60-IF-0001F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-06-24 11:14 | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8948 | PS4-60-IE-0003F-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-06-22 14:41 | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8949 | PS4-60-IE-0003F-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IF-0003F TO PS4-60-IF-0001F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-06-24 11:36 | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8950 | PS4-60-IE-0003F-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IE-0001F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-06-24 11:50 | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8951 | PS4-60-IE-0003F-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-06-22 11:43 | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8952 | PS4-60-IE-0003F-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-06-22 11:47 | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8953 | PS4-60-IE-0003F-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-06-27 12:16 | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8954 | PS4-60-IE-0003F-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-06-27 12:18 | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8955 | PS4-60-IE-0003F-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-06-27 12:20 | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8956 | PS4-60-IE-0003F-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-06-27 12:22 | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8957 | PS4-60-IE-0003F-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-06-23 12:24 | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8958 | PS4-60-IE-0003F-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-06-23 14:11 | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8959 | PS4-60-IE-0003F-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002F TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-06-23 14:13 | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8964 | PS4-60-IE-0003F-CC25 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-TX-41600A TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-06-21 11:59 | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8965 | PS4-60-IE-0003F-CC26 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-TX-41600B TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-06-21 12:02 | PS4-60-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-8966 | PS4-60-IE-0003G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IG-0003G TO PS4-60-IG-0001G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-06-24 11:17 | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8967 | PS4-60-IE-0003G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IG-0003G TO PS4-60-IG-0001G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-06-24 11:19 | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8968 | PS4-60-IE-0003G-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-06-23 14:15 | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8969 | PS4-60-IE-0003G-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IG-0003G TO PS4-60-IG-0001G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-06-24 11:39 | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8970 | PS4-60-IE-0003G-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0001G TO PS4-60-IE-0003H | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-06-24 11:52 | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8971 | PS4-60-IE-0003G-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-06-22 11:52 | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8972 | PS4-60-IE-0003G-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-06-22 11:54 | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8973 | PS4-60-IE-0003G-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-06-27 12:24 | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8974 | PS4-60-IE-0003G-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-06-27 12:26 | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8975 | PS4-60-IE-0003G-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-06-27 12:28 | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8976 | PS4-60-IE-0003G-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-06-27 12:33 | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8977 | PS4-60-IE-0003G-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-06-23 12:26 | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8978 | PS4-60-IE-0003G-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-06-23 14:17 | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8979 | PS4-60-IE-0003G-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0002G TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-06-23 14:20 | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8984 | PS4-60-IE-0003G-CC25 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-TX-41700A TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-06-21 12:04 | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8985 | PS4-60-IE-0003G-CC26 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-TX-41700B TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) | 2026-06-21 12:06 | PS4-60-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-8986 | PS4-60-IE-0004-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-11 11:43 | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8987 | PS4-60-IE-0004-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-11 11:47 | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8988 | PS4-60-IE-0004-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-11 11:49 | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8989 | PS4-60-IE-0004-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-11 11:51 | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8990 | PS4-60-IE-0004-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-11 11:54 | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8991 | PS4-60-IE-0004-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-11 11:56 | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8992 | PS4-60-IE-0004-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-11 12:06 | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8996 | PS4-60-IN-0001A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-49 - Lube Oil Separator Module PS4-60-UO-81100A | 2026-06-21 12:09 | PS4-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8997 | PS4-60-IN-0001A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-49 - Lube Oil Separator Module PS4-60-UO-81100A | 2026-06-21 11:11 | PS4-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8998 | PS4-60-IN-0001A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-49 - Lube Oil Separator Module PS4-60-UO-81100A | 2026-06-21 13:50 | PS4-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-8999 | PS4-60-IN-0001A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0001A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-49 - Lube Oil Separator Module PS4-60-UO-81100A | 2026-06-21 06:23 | PS4-60-49 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9000 | PS4-60-IN-0001B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-50 - Lube Oil Separator Module PS4-60-UO-81100B | 2026-06-21 12:12 | PS4-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9001 | PS4-60-IN-0001B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-50 - Lube Oil Separator Module PS4-60-UO-81100B | 2026-06-21 11:12 | PS4-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9002 | PS4-60-IN-0001B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-50 - Lube Oil Separator Module PS4-60-UO-81100B | 2026-06-21 13:53 | PS4-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9003 | PS4-60-IN-0001B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0001B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-50 - Lube Oil Separator Module PS4-60-UO-81100B | 2026-06-21 06:26 | PS4-60-50 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9004 | PS4-60-IN-0001C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-51 - Lube Oil Separator Module PS4-60-UO-81100C | 2026-06-21 12:15 | PS4-60-51 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9005 | PS4-60-IN-0001C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-51 - Lube Oil Separator Module PS4-60-UO-81100C | 2026-06-21 11:13 | PS4-60-51 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9006 | PS4-60-IN-0001C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-51 - Lube Oil Separator Module PS4-60-UO-81100C | 2026-06-21 13:55 | PS4-60-51 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9007 | PS4-60-IN-0001C-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0001C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-51 - Lube Oil Separator Module PS4-60-UO-81100C | 2026-06-21 06:30 | PS4-60-51 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9008 | PS4-60-IN-0001D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-52 - Lube Oil Separator Module PS4-60-UO-81100D | 2026-06-21 12:17 | PS4-60-52 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9009 | PS4-60-IN-0001D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-52 - Lube Oil Separator Module PS4-60-UO-81100D | 2026-06-21 11:14 | PS4-60-52 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9010 | PS4-60-IN-0001D-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-52 - Lube Oil Separator Module PS4-60-UO-81100D | 2026-06-21 13:58 | PS4-60-52 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9011 | PS4-60-IN-0001D-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0001D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-52 - Lube Oil Separator Module PS4-60-UO-81100D | 2026-06-21 06:33 | PS4-60-52 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9012 | PS4-60-IN-0001E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0001E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-53 - Lube Oil Separator Module PS4-60-UO-81100E | 2026-06-21 12:22 | PS4-60-53 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9013 | PS4-60-IN-0001E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0001E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-53 - Lube Oil Separator Module PS4-60-UO-81100E | 2026-06-21 11:15 | PS4-60-53 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9014 | PS4-60-IN-0001E-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0001E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-53 - Lube Oil Separator Module PS4-60-UO-81100E | 2026-06-21 14:01 | PS4-60-53 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9015 | PS4-60-IN-0001E-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0001E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-53 - Lube Oil Separator Module PS4-60-UO-81100E | 2026-06-21 06:38 | PS4-60-53 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9016 | PS4-60-IN-0001F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0001F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-54 - Lube Oil Separator Module PS4-60-UO-81100F | 2026-06-21 12:24 | PS4-60-54 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9017 | PS4-60-IN-0001F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0001F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-54 - Lube Oil Separator Module PS4-60-UO-81100F | 2026-06-21 11:16 | PS4-60-54 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9018 | PS4-60-IN-0001F-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0001F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-54 - Lube Oil Separator Module PS4-60-UO-81100F | 2026-06-21 14:04 | PS4-60-54 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9019 | PS4-60-IN-0001F-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0001F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-54 - Lube Oil Separator Module PS4-60-UO-81100F | 2026-06-21 06:45 | PS4-60-54 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9020 | PS4-60-IN-0001G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0001G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-55 - Lube Oil Separator Module PS4-60-UO-81100G | 2026-06-21 12:26 | PS4-60-55 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9021 | PS4-60-IN-0001G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0001G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-55 - Lube Oil Separator Module PS4-60-UO-81100G | 2026-06-21 11:17 | PS4-60-55 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9022 | PS4-60-IN-0001G-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0001G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-55 - Lube Oil Separator Module PS4-60-UO-81100G | 2026-06-21 14:07 | PS4-60-55 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9023 | PS4-60-IN-0001G-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0001G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-55 - Lube Oil Separator Module PS4-60-UO-81100G | 2026-06-21 06:53 | PS4-60-55 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9024 | PS4-60-IN-0002A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-06-22 11:57 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9025 | PS4-60-IN-0002A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-06-24 06:08 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9026 | PS4-60-IN-0002A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-06-22 14:45 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9027 | PS4-60-IN-0002A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-06-22 12:01 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9028 | PS4-60-IN-0002A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-06-23 07:46 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9029 | PS4-60-IN-0002A-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) | 2026-06-21 14:15 | PS4-60-57 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9030 | PS4-60-IN-0002B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-06-22 12:06 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9031 | PS4-60-IN-0002B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-06-24 06:50 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9032 | PS4-60-IN-0002B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-06-23 07:48 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9033 | PS4-60-IN-0002B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-06-22 12:10 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9034 | PS4-60-IN-0002B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-06-23 08:07 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9035 | PS4-60-IN-0002B-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) | 2026-06-21 14:20 | PS4-60-59 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9036 | PS4-60-IN-0002C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) | 2026-06-22 12:13 | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9037 | PS4-60-IN-0002C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) | 2026-06-24 07:00 | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9038 | PS4-60-IN-0002C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) | 2026-06-23 08:12 | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9039 | PS4-60-IN-0002C-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) | 2026-06-22 12:17 | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9040 | PS4-60-IN-0002C-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) | 2026-06-23 08:15 | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9041 | PS4-60-IN-0002C-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) | 2026-06-21 14:23 | PS4-60-61 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9042 | PS4-60-IN-0002D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) | 2026-06-22 12:19 | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9043 | PS4-60-IN-0002D-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) | 2026-06-24 07:07 | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9044 | PS4-60-IN-0002D-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) | 2026-06-23 08:18 | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9045 | PS4-60-IN-0002D-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) | 2026-06-22 12:21 | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9046 | PS4-60-IN-0002D-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) | 2026-06-23 08:20 | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9047 | PS4-60-IN-0002D-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) | 2026-06-21 14:26 | PS4-60-63 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9048 | PS4-60-IN-0002E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) | 2026-06-22 12:27 | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9049 | PS4-60-IN-0002E-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) | 2026-06-24 07:13 | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9050 | PS4-60-IN-0002E-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) | 2026-06-23 08:22 | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9051 | PS4-60-IN-0002E-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) | 2026-06-22 12:31 | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9052 | PS4-60-IN-0002E-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) | 2026-06-23 08:24 | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9053 | PS4-60-IN-0002E-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) | 2026-06-21 14:30 | PS4-60-65 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9054 | PS4-60-IN-0002F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) | 2026-06-22 12:33 | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9055 | PS4-60-IN-0002F-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) | 2026-06-24 07:28 | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9056 | PS4-60-IN-0002F-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) | 2026-06-23 08:33 | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9057 | PS4-60-IN-0002F-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) | 2026-06-22 12:38 | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9058 | PS4-60-IN-0002F-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) | 2026-06-23 08:42 | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9059 | PS4-60-IN-0002F-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) | 2026-06-21 14:33 | PS4-60-67 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9060 | PS4-60-IN-0002G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) | 2026-06-22 12:42 | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9061 | PS4-60-IN-0002G-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) | 2026-06-24 07:35 | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9062 | PS4-60-IN-0002G-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) | 2026-06-23 08:51 | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9063 | PS4-60-IN-0002G-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) | 2026-06-22 12:50 | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9064 | PS4-60-IN-0002G-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) | 2026-06-23 08:58 | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9065 | PS4-60-IN-0002G-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) | 2026-06-21 14:36 | PS4-60-69 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9066 | PS4-60-LA-0002A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-26 13:41 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9067 | PS4-60-LA-0002A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-26 13:44 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9068 | PS4-60-LA-0002A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-26 13:46 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9069 | PS4-60-LA-0002A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-26 13:48 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9070 | PS4-60-LA-0002A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-26 13:50 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9071 | PS4-60-LA-0002A-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-26 13:53 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9072 | PS4-60-LA-0002A-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-26 13:55 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9073 | PS4-60-LA-0002A-CC08 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-26 14:07 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9074 | PS4-60-LA-0002A-CC09 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-LA-0002A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-26 14:09 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9075 | PS4-60-LA-0002B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-26 14:11 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9076 | PS4-60-LA-0002B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-26 14:13 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9077 | PS4-60-LA-0002B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-26 14:16 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9078 | PS4-60-LA-0002B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-26 14:18 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9079 | PS4-60-LA-0002B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-26 14:21 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9080 | PS4-60-LA-0002B-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-26 14:24 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9081 | PS4-60-LA-0002C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-26 14:26 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9082 | PS4-60-LA-0002C-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-26 14:28 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9083 | PS4-60-LA-0002C-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-26 14:31 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9084 | PS4-60-LA-0002C-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-26 14:33 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9085 | PS4-60-LA-0002C-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-27 10:52 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9086 | PS4-60-LA-0002C-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-27 10:55 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9087 | PS4-60-LA-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00254
T-00254-9088 | PS4-60-LA-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00254
T-00254-9089 | PS4-60-LA-0003-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-LA-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00254
T-00254-9090 | PS4-60-LIT-4301-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1113 TO PS4-60-LIT-4301 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-24 - Cooling Water Tank & Pump | 2026-07-13 19:38 | PS4-60-24 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9091 | PS4-60-LIT-4401-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1113 TO PS4-60-LIT-4401 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-25 - Cooling Water Maintenance Tank & Return Pump | 2026-07-13 19:39 | PS4-60-25 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9092 | PS4-60-MOV-0005-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2120 TO PS4-60-MOV-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-14 05:49 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9093 | PS4-60-MOV-0005-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2124 TO PS4-60-MOV-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-14 05:58 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9094 | PS4-60-MOV-0006-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2121 TO PS4-60-MOV-0006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-14 05:51 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9095 | PS4-60-MOV-0006-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2125 TO PS4-60-MOV-0006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-14 06:02 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9096 | PS4-60-MOV-0011-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2118 TO PS4-60-MOV-0011 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-14 05:45 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9097 | PS4-60-MOV-0011-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2122 TO PS4-60-MOV-0011 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-14 05:53 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9098 | PS4-60-MOV-0012-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2119 TO PS4-60-MOV-0012 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-14 05:47 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9099 | PS4-60-MOV-0012-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2123 TO PS4-60-MOV-0012 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-14 05:56 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9100 | PS4-60-SEA-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-06-27 11:00 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9101 | PS4-60-SEA-0001-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-06-27 11:05 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9102 | PS4-60-SEA-0001-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-06-27 11:07 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9103 | PS4-60-SEA-0001-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-06-27 11:09 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9104 | PS4-60-SEA-0001-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-06-27 11:11 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9105 | PS4-60-SEA-0001-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-06-27 11:13 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9106 | PS4-60-SEA-0001-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-06-27 11:28 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9107 | PS4-60-SEA-0001-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-06 07:27 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9108 | PS4-60-SEA-0001-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-06 07:29 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9109 | PS4-60-SEA-0001-CC12 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-06 07:32 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9110 | PS4-60-SEA-0001-CC13 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-06 07:35 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9111 | PS4-60-SEA-0001-CC14 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-06 07:37 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9112 | PS4-60-SEA-0001-CC15 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-06 07:40 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9113 | PS4-60-SEA-0001-CC16 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-06 07:43 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9114 | PS4-60-SEA-0001-CC17 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 2026-07-06 07:46 | PS4-03-14 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9116 | PS4-60-SY-0007-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-SY-0007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-28 - Air Receiver A & Air Regulator A | 2026-07-06 06:33 | PS4-60-28 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9117 | PS4-60-SY-0008-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-SY-0008 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-29 - Air Receiver B & Air Regulator B | 2026-07-06 06:36 | PS4-60-29 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9118 | PS4-60-SY-0009-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-SY-0009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-30 - Air Receiver C & Air Regulator C | 2026-07-06 06:38 | PS4-60-30 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9119 | PS4-60-SY-0010-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-SY-0010 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-31 - Air Receiver D & Air Regulator D | 2026-07-06 06:41 | PS4-60-31 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9120 | PS4-60-SY-0011-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-SY-0011 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-32 - Air Receiver E & Air Regulator E | 2026-07-06 06:44 | PS4-60-32 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9121 | PS4-60-SY-0012-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-SY-0012 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-33 - Air Receiver F & Air Regulator F | 2026-07-06 06:49 | PS4-60-33 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9122 | PS4-60-SY-0013-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-60-SY-0013 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-34 - Air Receiver G & Air Regulator G | 2026-07-06 06:52 | PS4-60-34 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9123 | PS4-60-VS-9101A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-60-VS-9101A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-42 - Oil Mist Separator Skid PS4-60-VS-9100A | 2026-07-11 08:23 | PS4-60-42 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9124 | PS4-60-VS-9101B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-60-VS-9101B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-43 - Oil Mist Separator Skid PS4-60-VS-9100B | 2026-07-11 10:38 | PS4-60-43 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9125 | PS4-60-VS-9101C-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-60-VS-9101C | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-44 - Oil Mist Separator Skid PS4-60-VS-9100C | 2026-06-22 13:11 | PS4-60-44 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9126 | PS4-60-VS-9101D-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-60-VS-9101D | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-45 - Oil Mist Separator Skid PS4-60-VS-9100D | 2026-07-11 10:44 | PS4-60-45 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9127 | PS4-60-VS-9101E-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-60-VS-9101E | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-46 - Oil Mist Separator Skid PS4-60-VS-9100E | 2026-07-11 10:48 | PS4-60-46 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9128 | PS4-60-VS-9101F-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-60-VS-9101F | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-47 - Oil Mist Separator Skid PS4-60-VS-9100F | 2026-07-11 10:50 | PS4-60-47 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9129 | PS4-60-VS-9101G-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-60-VS-9101G | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-48 - Oil Mist Separator Skid PS4-60-VS-9100G | 2026-07-11 10:52 | PS4-60-48 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9130 | PS4-61-BI-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-25 08:04 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9131 | PS4-61-BI-0001-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003A TO PS4-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-23 10:18 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9132 | PS4-61-BI-0001-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-61-TE-0003A TO PS4-61-BI-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-06-21 07:27 | PS4-60-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9133 | PS4-61-BI-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-25 08:06 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9134 | PS4-61-BI-0002-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003B TO PS4-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-23 10:20 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9135 | PS4-61-BI-0002-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-61-TE-0003B TO PS4-61-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-06-21 07:30 | PS4-60-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9136 | PS4-61-BI-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-61-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-06-25 08:08 | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9137 | PS4-61-BI-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003C TO PS4-61-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-06-23 10:22 | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9138 | PS4-61-BI-0003-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-61-TE-0003C TO PS4-61-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C | 2026-06-21 07:33 | PS4-60-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9139 | PS4-61-BI-0004-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-61-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-25 08:10 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9140 | PS4-61-BI-0004-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003D TO PS4-61-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-23 10:25 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9141 | PS4-61-BI-0004-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-61-TE-0003D TO PS4-61-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D | 2026-06-21 07:36 | PS4-60-10 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9142 | PS4-61-BI-0005-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-61-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-06-25 08:13 | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9143 | PS4-61-BI-0005-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003E TO PS4-61-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-06-23 10:28 | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9144 | PS4-61-BI-0005-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-61-TE-0003E TO PS4-61-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E | 2026-06-21 07:52 | PS4-60-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9145 | PS4-61-BI-0006-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-61-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-25 08:16 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9146 | PS4-61-BI-0006-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003F TO PS4-61-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-23 10:31 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9147 | PS4-61-BI-0006-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-61-TE-0003F TO PS4-61-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F | 2026-06-21 07:54 | PS4-60-16 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone D | TM-00254 | sridhar, muthu
T-00254-9148 | PS4-61-BI-0007-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-61-BI-0007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-06-25 08:18 | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9149 | PS4-61-BI-0007-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0003G TO PS4-61-BI-0007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-06-23 10:37 | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9150 | PS4-61-BI-0007-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-61-TE-0003G TO PS4-61-BI-0007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G | 2026-06-21 07:57 | PS4-60-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone E | TM-00254 | sridhar, muthu
T-00254-9160 | PS4-71-BAV-0058-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2113 TO PS4-71-BAV-0058 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00254
T-00254-9161 | PS4-71-BAV-0059-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2113 TO PS4-71-BAV-0059 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00254
T-00254-9162 | PS4-71-BI-0001A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0001A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module | 2026-07-20 18:41 | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9163 | PS4-71-BI-0001B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0001B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9165 | PS4-71-BI-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0001 TO PS4-71-BI-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00254
T-00254-9166 | PS4-71-BI-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-06-22 05:21 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9167 | PS4-71-BI-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0002 TO PS4-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-20 18:46 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9168 | PS4-71-BI-0003-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0002 TO PS4-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-20 18:49 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9169 | PS4-71-BI-0003-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0002 TO PS4-71-BI-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-11 10:54 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9170 | PS4-71-BI-0004-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0002 TO PS4-71-BI-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-20 18:53 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9171 | PS4-71-BI-0005-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0003 TO PS4-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-07-11 11:10 | PS4-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9172 | PS4-71-BI-0005-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-BI-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-06-22 05:32 | PS4-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9173 | PS4-71-BI-0006-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0003 TO PS4-71-BI-0006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-11 10:59 | PS4-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9174 | PS4-71-BI-0008A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module | 2026-07-20 19:01 | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9175 | PS4-71-BI-0008A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0008A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9176 | PS4-71-BI-0008B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9177 | PS4-71-BI-0008B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0008B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9178 | PS4-71-BI-0009-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0001 TO PS4-71-BI-0009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00254
T-00254-9179 | PS4-71-BI-0009-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0001 TO PS4-71-BI-0009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00254
T-00254-9180 | PS4-71-BI-0009-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0001 TO PS4-71-BI-0009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module |  | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00254
T-00254-9181 | PS4-71-BI-0009-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0001 TO PS4-71-BI-0009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module | 2026-07-11 11:04 | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9182 | PS4-71-BI-0010-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0001 TO PS4-71-BI-0010 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module | 2026-07-11 11:06 | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9183 | PS4-71-BI-0011A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9184 | PS4-71-BI-0011A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9185 | PS4-71-BI-0011A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module | 2026-07-11 11:08 | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9186 | PS4-71-BI-0011A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module | 2026-07-20 19:04 | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9187 | PS4-71-BI-0011A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0011A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9188 | PS4-71-BI-0011B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9189 | PS4-71-BI-0011B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9190 | PS4-71-BI-0011B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module | 2026-07-20 19:07 | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9191 | PS4-71-BI-0011B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module | 2026-07-20 19:10 | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9192 | PS4-71-BI-0011B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0004A TO PS4-71-BI-0011B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-06 - Crude Fuel Separation Module |  | PS4-71-06 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9225 | PS4-71-FCV-0018-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-FCV-0018-HPU TO PS4-71-FCV-0018 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9226 | PS4-71-FCV-0019-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-FCV-0019-HPU TO PS4-71-FCV-0019 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone B | TM-00254
T-00254-9227 | PS4-71-FCV-0020-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-FCV-0020-HPU TO PS4-71-FCV-0020 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9228 | PS4-71-FIT-0005-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1111 TO PS4-71-FIT-0005 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-17 - Diesel Fuel Distribution Header | 2026-07-13 19:28 | PS4-71-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9229 | PS4-71-FIT-0011A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-FIT-0011A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater | 2026-07-13 19:16 | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9230 | PS4-71-FIT-0011B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-FIT-0011B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater | 2026-07-13 19:07 | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9231 | PS4-71-FIT-0012-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1112 TO PS4-71-FIT-0012 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-17 - Diesel Fuel Distribution Header |  | PS4-71-17 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00254
T-00254-9232 | PS4-71-FIT-0018-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1110 TO PS4-71-FIT-0018 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B | 2026-07-13 19:23 | PS4-71-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9233 | PS4-71-FIT-0019-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1110 TO PS4-71-FIT-0019 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B | 2026-07-13 19:24 | PS4-71-21 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9234 | PS4-71-FIT-0020-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1110 TO PS4-71-FIT-0020 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B | 2026-07-13 19:22 | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9235 | PS4-71-FXS-0018-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2107 TO PS4-71-FCV-0018 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B | 2026-07-14 05:31 | PS4-71-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9236 | PS4-71-FXS-0019-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2114 TO PS4-71-FCV-0019 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B | 2026-07-14 05:37 | PS4-71-21 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9237 | PS4-71-FXS-0020-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2107 TO PS4-71-FCV-0020 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B | 2026-07-14 05:30 | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9238 | PS4-71-FY-0018-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1116 TO PS4-71-FCV-0018 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B | 2026-07-13 19:43 | PS4-71-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9239 | PS4-71-FY-0019-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1113 TO PS4-71-FCV-0019 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B | 2026-07-13 19:33 | PS4-71-21 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9240 | PS4-71-FY-0020-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1116 TO PS4-71-FCV-0020 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B | 2026-07-13 19:46 | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9241 | PS4-71-IN-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) | 2026-06-26 12:27 | PS4-71-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9242 | PS4-71-IN-0001-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) | 2026-06-26 12:30 | PS4-71-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9243 | PS4-71-IN-0001-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) | 2026-07-06 06:55 | PS4-71-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9244 | PS4-71-IN-0001-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-0011A TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) | 2026-06-21 08:32 | PS4-71-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9245 | PS4-71-IN-0001-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-0011B TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) | 2026-06-21 10:40 | PS4-71-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9246 | PS4-71-IN-0001-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) | 2026-06-23 11:00 | PS4-71-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9247 | PS4-71-IN-0001-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) | 2026-06-23 11:02 | PS4-71-19 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9251 | PS4-71-IN-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-09 - CFO Pre-Pressure Module (UCP) | 2026-06-26 12:32 | PS4-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9252 | PS4-71-IN-0002-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-09 - CFO Pre-Pressure Module (UCP) | 2026-06-27 12:35 | PS4-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9253 | PS4-71-IN-0002-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-09 - CFO Pre-Pressure Module (UCP) | 2026-06-23 11:05 | PS4-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9254 | PS4-71-IN-0002-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-09 - CFO Pre-Pressure Module (UCP) | 2026-06-23 11:09 | PS4-71-09 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9258 | PS4-71-IN-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-06-26 12:34 | PS4-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9259 | PS4-71-IN-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-06-26 12:36 | PS4-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9260 | PS4-71-IN-0003-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-06-23 11:26 | PS4-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9261 | PS4-71-IN-0003-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 2026-06-23 11:32 | PS4-71-23 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9265 | PS4-71-IN-0004A-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-06-27 12:38 | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9266 | PS4-71-IN-0004A-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-06-27 12:42 | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9267 | PS4-71-IN-0004A-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-06 06:58 | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9268 | PS4-71-IN-0004A-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-0011A TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-06-21 10:43 | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9269 | PS4-71-IN-0004A-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-0011A TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-06-21 10:45 | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9270 | PS4-71-IN-0004A-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-06-23 11:38 | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9271 | PS4-71-IN-0004A-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-06-23 11:40 | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9274 | PS4-71-IN-0004A-CC10 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-11 12:08 | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9275 | PS4-71-IN-0004A-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-11 11:59 | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9277 | PS4-71-IN-0004A-CC13 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0004B TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-11 12:02 | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9278 | PS4-71-IN-0004B-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-06-27 12:45 | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9279 | PS4-71-IN-0004B-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-06-27 12:47 | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9280 | PS4-71-IN-0004B-CC03 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-06 07:00 | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9281 | PS4-71-IN-0004B-CC04 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-0011B TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-06-21 10:47 | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9282 | PS4-71-IN-0004B-CC05 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-0011B TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-06-21 10:49 | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9283 | PS4-71-IN-0004B-CC06 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-06-23 11:43 | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9284 | PS4-71-IN-0004B-CC07 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-06-23 11:47 | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9287 | PS4-71-IN-0004B-CC11 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-IN-0001 TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) | 2026-07-11 12:04 | PS4-71-07 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9289 | PS4-71-LCV-4101-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-LCV-4101-HPU TO PS4-71-LCV-4101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9290 | PS4-71-LI-4201B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-LIT-4201 TO PS4-71-LI-4201B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-14 06:12 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9291 | PS4-71-LIT-1201-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1113 TO PS4-71-LIT-1201 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank | 2026-07-13 19:35 | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9292 | PS4-71-LIT-1202-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1307 TO PS4-71-LIT-1202 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank | 2026-07-13 18:44 | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9293 | PS4-71-LIT-4101-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-LIT-4101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-07-13 18:59 | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9294 | PS4-71-LIT-4102-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1305 TO PS4-71-LIT-4102 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-07-13 19:53 | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9295 | PS4-71-LIT-4201-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-LIT-4201 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-13 19:14 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9296 | PS4-71-LIT-4202-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1306 TO PS4-71-LIT-4202 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-14 04:58 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9297 | PS4-71-LIT-4401-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1111 TO PS4-71-LIT-4401 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank | 2026-07-13 19:29 | PS4-71-15 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9298 | PS4-71-LIT-4402-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1308 TO PS4-71-LIT-4402 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank | 2026-07-14 05:02 | PS4-71-15 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9299 | PS4-71-LXS-4101-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2107 TO PS4-71-LCV-4101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-07-14 05:29 | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9300 | PS4-71-LY-4101-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-LCV-4101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Submitted | PS4 - Milestone H | TM-00254
T-00254-9301 | PS4-71-MOV-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2120 TO PS4-71-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-14 05:48 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9302 | PS4-71-MOV-0001-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2124 TO PS4-71-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-14 05:56 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9303 | PS4-71-MOV-0002-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2120 TO PS4-71-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-14 05:48 | PS4-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9304 | PS4-71-MOV-0002-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2124 TO PS4-71-MOV-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-14 05:57 | PS4-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9305 | PS4-71-MOV-0003-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2121 TO PS4-71-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-14 05:50 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9306 | PS4-71-MOV-0003-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2125 TO PS4-71-MOV-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-14 05:59 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9307 | PS4-71-MOV-0004-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2121 TO PS4-71-MOV-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-14 05:51 | PS4-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9308 | PS4-71-MOV-0004-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2125 TO PS4-71-MOV-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-14 06:02 | PS4-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9309 | PS4-71-MOV-0007-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2118 TO PS4-71-MOV-0007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-14 05:43 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9310 | PS4-71-MOV-0007-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2122 TO PS4-71-MOV-0007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-14 05:52 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9311 | PS4-71-MOV-0008-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2118 TO PS4-71-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-14 05:44 | PS4-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9312 | PS4-71-MOV-0008-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2122 TO PS4-71-MOV-0008 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-14 05:53 | PS4-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9313 | PS4-71-MOV-0009-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2119 TO PS4-71-MOV-0009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-14 05:45 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9314 | PS4-71-MOV-0009-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2123 TO PS4-71-MOV-0009 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-08 - CFO Pre-Pressure Module | 2026-07-14 05:54 | PS4-71-08 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9315 | PS4-71-MOV-0010-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2119 TO PS4-71-MOV-0010 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-14 05:46 | PS4-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9316 | PS4-71-MOV-0010-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2123 TO PS4-71-MOV-0010 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-22 - Diesel Fuel Pre Pressure Module | 2026-07-14 05:55 | PS4-71-22 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9317 | PS4-71-PDIT-0030-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-PDIT-0030 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater | 2026-07-13 19:13 | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9318 | PS4-71-PDIT-0056A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1110 TO PS4-71-PDIT-0056A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B | 2026-07-13 19:26 | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9319 | PS4-71-PDIT-0056B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1110 TO PS4-71-PDIT-0056B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B | 2026-07-13 19:21 | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9320 | PS4-71-PIT-0001-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-28-BI-1307 TO PS4-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank | 2026-07-13 18:46 | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9321 | PS4-71-PIT-0014-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1111 TO PS4-71-PIT-0014 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-17 - Diesel Fuel Distribution Header | 2026-07-13 19:31 | PS4-71-17 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9322 | PS4-71-PIT-0018A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1116 TO PS4-71-FCV-0018 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B | 2026-07-13 19:45 | PS4-71-13 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9323 | PS4-71-PIT-0019A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1113 TO PS4-71-FCV-0019 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B | 2026-07-13 19:34 | PS4-71-21 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9324 | PS4-71-PIT-0020A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1116 TO PS4-71-FCV-0020 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B | 2026-07-13 19:47 | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9325 | PS4-71-PIT-0022-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1305 TO PS4-71-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-07-14 04:53 | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9326 | PS4-71-PIT-0029-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1308 TO PS4-71-SDV-0029 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank | 2026-07-14 05:28 | PS4-71-15 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9327 | PS4-71-PIT-0039-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1306 TO PS4-71-SDV-0039 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-14 04:59 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9328 | PS4-71-PIT-0089-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1117 TO PS4-71-XV-0089 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-07-13 19:49 | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9329 | PS4-71-PIT-0090-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1117 TO PS4-71-XV-0090 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-13 19:50 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9330 | PS4-71-PIT-0091-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1113 TO PS4-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module | 2026-07-13 19:36 | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9331 | PS4-71-PIT-0092-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1113 TO PS4-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank | 2026-07-13 19:37 | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9332 | PS4-71-PIT-2402A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-PIT-2402A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater | 2026-07-13 19:08 | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9333 | PS4-71-PIT-2402B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-PIT-2402B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater | 2026-07-13 19:12 | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9334 | PS4-71-PIT-3301A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1306 TO PS4-71-PIT-3301A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9335 | PS4-71-PIT-3301B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1306 TO PS4-71-PIT-3301B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9336 | PS4-71-PIT-3302A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1110 TO PS4-71-PIT-3302A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B | 2026-07-13 19:27 | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9337 | PS4-71-PIT-3302B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1110 TO PS4-71-PIT-3302B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9338 | PS4-71-PIT-3401A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1306 TO PS4-71-PIT-3401A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9339 | PS4-71-PIT-3401B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1306 TO PS4-71-PIT-3401B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9340 | PS4-71-PIT-3402A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1110 TO PS4-71-PIT-3402A | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9341 | PS4-71-PIT-3402B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1110 TO PS4-71-PIT-3402B | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9342 | PS4-71-PIT-4101A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-LCV-4101 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-07-13 19:01 | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9343 | PS4-71-SDV-0001-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2315 TO PS4-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank | 2026-07-13 17:57 | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9344 | PS4-71-SDV-0001-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-SDV-0001-HPU TO PS4-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank | 2026-07-14 06:18 | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9345 | PS4-71-SDV-0022-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2306 TO PS4-71-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-07-14 06:03 | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9346 | PS4-71-SDV-0022-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-SDV-0022-HPU TO PS4-71-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9347 | PS4-71-SDV-0029-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2307 TO PS4-71-SDV-0029 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank | 2026-07-14 06:04 | PS4-71-15 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9348 | PS4-71-SDV-0029-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-SDV-0029-HPU TO PS4-71-SDV-0029 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank |  | PS4-71-15 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone F | TM-00254
T-00254-9349 | PS4-71-SDV-0039-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2306 TO PS4-71-SDV-0039 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-14 06:04 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9350 | PS4-71-SDV-0039-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-SDV-0039-HPU TO PS4-71-SDV-0039 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9351 | PS4-71-SXS-0001-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2312 TO PS4-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank | 2026-07-13 11:37 | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9352 | PS4-71-SXS-0022-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2314 TO PS4-71-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-07-14 06:07 | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9353 | PS4-71-SXS-0029-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2313 TO PS4-71-SDV-0029 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank | 2026-07-14 06:07 | PS4-71-15 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9354 | PS4-71-SXS-0039-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2314 TO PS4-71-SDV-0039 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-14 06:08 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9355 | PS4-71-SY-0001-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-25-BI-2316 TO PS4-71-SDV-0001 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank | 2026-07-13 18:07 | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9356 | PS4-71-SY-0022-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2310 TO PS4-71-SDV-0022 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-07-14 06:06 | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9357 | PS4-71-SY-0029-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2317 TO PS4-71-SDV-0029 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank | 2026-07-14 06:09 | PS4-71-15 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9358 | PS4-71-SY-0039-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2310 TO PS4-71-SDV-0039 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-14 06:05 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9359 | PS4-71-TIT-0003-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-TIT-0003 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater | 2026-07-13 19:06 | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9360 | PS4-71-TIT-0004-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-TIT-0004 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater | 2026-07-13 19:20 | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9361 | PS4-71-TIT-0006-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1305 TO PS4-71-TIT-0006 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater | 2026-07-14 04:55 | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9362 | PS4-71-TIT-0007-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1306 TO PS4-71-TIT-0007 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater | 2026-07-14 05:02 | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9363 | PS4-71-TIT-2204-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1306 TO PS4-71-TIT-2204 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9364 | PS4-71-TIT-2301-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1305 TO PS4-71-TIT-2301 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9365 | PS4-71-TIT-2402AA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1305 TO PS4-71-TIT-2402AA | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9366 | PS4-71-TIT-2402BA-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1306 TO PS4-71-TIT-2402BA | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone H | TM-00254
T-00254-9369 | PS4-71-TIT-4102-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-TIT-4102 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-07-13 19:17 | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9370 | PS4-71-TIT-4103-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1305 TO PS4-71-TIT-4103 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-07-14 04:56 | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9371 | PS4-71-TIT-4202-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1109 TO PS4-71-TIT-4202 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-13 19:19 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9372 | PS4-71-TIT-4203-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-1306 TO PS4-71-TIT-4203 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-14 05:01 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9373 | PS4-71-XV-0089-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2116 TO PS4-71-XV-0089 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-07-14 05:41 | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9374 | PS4-71-XV-0089-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-XV-0089-HPU TO PS4-71-XV-0089 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-07-14 06:15 | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9375 | PS4-71-XV-0090-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2116 TO PS4-71-XV-0090 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-14 05:42 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9376 | PS4-71-XV-0090-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-XV-0090-HPU TO PS4-71-XV-0090 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-14 06:16 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9377 | PS4-71-XV-0091-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2113 TO PS4-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module | 2026-07-14 05:34 | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9378 | PS4-71-XV-0091-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-XV-0091-HPU TO PS4-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module | 2026-07-14 06:16 | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9379 | PS4-71-XV-0092-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2113 TO PS4-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank | 2026-07-14 05:35 | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9380 | PS4-71-XV-0092-CC02 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-XV-0092-HPU TO PS4-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank | 2026-07-14 06:17 | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9381 | PS4-71-XXS-0089-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2107 TO PS4-71-XV-0089 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-07-14 05:31 | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9382 | PS4-71-XXS-0090-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2107 TO PS4-71-XV-0090 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-14 05:32 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9383 | PS4-71-XXS-0091-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2114 TO PS4-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module | 2026-07-14 05:35 | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9384 | PS4-71-XXS-0092-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2114 TO PS4-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank | 2026-07-14 05:36 | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9385 | PS4-71-XY-0089-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2101 TO PS4-71-XV-0089 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank | 2026-07-13 19:51 | PS4-71-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9386 | PS4-71-XY-0090-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2101 TO PS4-71-XV-0090 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank | 2026-07-13 19:52 | PS4-71-12 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone H | TM-00254 | sridhar, muthu
T-00254-9387 | PS4-71-XY-0091-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2115 TO PS4-71-XV-0091 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-18 - Diesel Separator Module | 2026-07-14 05:39 | PS4-71-18 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9388 | PS4-71-XY-0092-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-71-BI-2115 TO PS4-71-XV-0092 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-20 - Diesel Fuel Day Tank | 2026-07-14 05:40 | PS4-71-20 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone B | TM-00254 | sridhar, muthu
T-00254-9391 | PS4-74-PIT-0002-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-50-BI-1107 TO PS4-74-PIT-0002 | EACOP | CPP AGI |  |  | 4 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-74-04 - Nitrogen Distribution Header | 2026-07-13 18:52 | PS4-74-04 |  |  | Multi/Single-Core Instrument Control Cable | I | Closed | PS4 - Milestone F | TM-00254 | sridhar, muthu
T-00254-9954 | PS4-03-RAB-B403-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-SEA-0005 TO PS4-03-RAB-B402 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9955 | PS4-03-RAB-B903-CC01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-SEA-0005 TO PS4-03-RAB-B902 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9956 | PS4-03-RAB-W503-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-SEA-0006 TO PS4-03-RAB-W503 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9957 | PS4-03-RDHR-W101A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-W201A TO PS4-03-RDHR-W101A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9958 | PS4-03-RDHR-W101B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W101A TO PS4-03-RDHR-W101B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9959 | PS4-03-RDHR-W101C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W101B TO PS4-03-RDHR-W101C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9960 | PS4-03-RDHR-W101D-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W101C TO PS4-03-RDHR-W101D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9961 | PS4-03-RDHR-W101E-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W101D TO PS4-03-RDHR-W101E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9962 | PS4-03-RDHR-W101F-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W101E TO PS4-03-RDHR-W101F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9963 | PS4-03-RDHR-W101G-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W101F TO PS4-03-RDHR-W101G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9964 | PS4-03-RDHR-W101H-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W101G TO PS4-03-RDHR-W101H | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9965 | PS4-03-RDHR-W101I-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W101H TO PS4-03-RDHR-W101I | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9966 | PS4-03-RDHR-W601A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W601A TO PS4-03-RDHR-W601B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9967 | PS4-03-RDHR-W601B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W601B TO PS4-03-RDHR-W601C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9968 | PS4-03-RDHR-W601C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W601C TO PS4-03-RDHR-W601D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9969 | PS4-03-RDHR-W601D-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W601D TO PS4-03-RDHR-W601E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9970 | PS4-03-RDHR-W601E-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W601E TO PS4-03-RDHR-W601F | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9971 | PS4-03-RDHR-W601F-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W601F TO PS4-03-RDHR-W601G | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9972 | PS4-03-RDHR-W601G-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W601G TO PS4-03-RDHR-W601H | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9973 | PS4-03-RDHR-W601H-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W601H TO PS4-03-RDHR-W601I | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9974 | PS4-03-RDHR-W601I-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W601I TO PS4-03-RDHR-W601J | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9975 | PS4-03-RDHR-W601J-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W601J TO PS4-03-RDHR-W601K | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9976 | PS4-03-RDHR-W601K-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W601K TO PS4-03-RDHR-W601L | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9977 | PS4-03-RDHR-W601L-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W601L TO PS4-03-RDHR-W601M | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9978 | PS4-03-RDHR-W601M-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W601M TO PS4-03-RDHR-W601N | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9979 | PS4-03-RDHR-W601N-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W601N TO PS4-03-RDHR-W601O | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9980 | PS4-03-RDHR-W601O-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W601O TO PS4-03-RDHR-W601P | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9981 | PS4-03-RDHR-W601P-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDHR-W601P TO PS4-03-RMAC-W502 | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160003 | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9982 | PS4-03-RDOS-B101A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B101B TO PS4-03-RDOS-B101A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9983 | PS4-03-RDOS-B101B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B101C TO PS4-03-RDOS-B101B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9984 | PS4-03-RDOS-B101C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B101D TO PS4-03-RDOS-B101C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9985 | PS4-03-RDOS-B101D-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B401A TO PS4-03-RDOS-B101D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9986 | PS4-03-RDOS-B201A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B201B TO PS4-03-RDOS-B201A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9987 | PS4-03-RDOS-B201B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B201C TO PS4-03-RDOS-B201B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9988 | PS4-03-RDOS-B201C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B201D TO PS4-03-RDOS-B201C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9989 | PS4-03-RDOS-B201D-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B201E TO PS4-03-RDOS-B201D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9990 | PS4-03-RDOS-B201E-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-SEA-0005 TO PS4-03-RDOS-B201E | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9991 | PS4-03-RDOS-B301A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B101A TO PS4-03-RDOS-B301A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9992 | PS4-03-RDOS-B301B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B301A TO PS4-03-RDOS-B301B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9993 | PS4-03-RDOS-B301C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B301B TO PS4-03-RDOS-B301C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9994 | PS4-03-RDOS-B301D-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B301D TO PS4-03-RDOS-B901B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9995 | PS4-03-RDOS-B401A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B401B TO PS4-03-RDOS-B401A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9996 | PS4-03-RDOS-B401B-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RMAC-B401 TO PS4-03-RDOS-B401B | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9997 | PS4-03-RDOS-B401C-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B401D TO PS4-03-RDOS-B401C | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9998 | PS4-03-RDOS-B401D-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B501A TO PS4-03-RDOS-B401D | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00254-9999 | PS4-03-RDOS-B501A-CJ01 |  |  |  |  | TJX10 - Multi/Single-core instrument control cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-03-RDOS-B601A TO PS4-03-RDOS-B501A | EACOP | CPP AGI |  |  | 4 |  |  | TZ-MID-67-CPP1-160002 | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  | Multi/Single-Core Instrument Control Cable | I | To be completed | PS4 - Milestone I | TM-00254
T-00255-0067 | PS4-25-FO-0008 |  |  |  |  | TJX11 - Orifice plate | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 18 |  |  | TZ-MID-67-WPR2-134006 | PS4 - TZA - PS4 - Tanzania | PS4-25-05 - Crude Oil Export Pumps Bypass |  | PS4-25-05 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone H | TM-00255
T-00255-0068 | PS4-28-FO-0002A |  |  |  |  | TJX11 - Orifice plate | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 18 |  |  | TZ-MID-67-WPR2-135701 | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone G | TM-00255
T-00255-0069 | PS4-28-FO-0002B |  |  |  |  | TJX11 - Orifice plate | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 18 |  |  | TZ-MID-67-WPR2-135701 | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone G | TM-00255
T-00255-0070 | PS4-28-FO-0003 |  |  |  |  | TJX11 - Orifice plate | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 18 |  |  | TZ-MID-67-WPR2-135402 | PS4 - TZA - PS4 - Tanzania | PS4-28-05 - HP Relief Header |  | PS4-28-05 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone G | TM-00255
T-00255-0071 | PS4-28-FO-0004 |  |  |  |  | TJX11 - Orifice plate | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 18 |  |  | TZ-MID-67-WPR2-135402 | PS4 - TZA - PS4 - Tanzania | PS4-28-16 - LP Relief Header |  | PS4-28-16 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone G | TM-00255
T-00255-0072 | PS4-28-FO-0005 |  |  |  |  | TJX11 - Orifice plate | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 18 |  |  | TZ-MID-67-WPR2-135402 | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump |  | PS4-28-06 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone G | TM-00255
T-00255-0073 | PS4-28-FO-0006 |  |  |  |  | TJX11 - Orifice plate | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 18 |  |  | TZ-MID-67-WPR2-135701 | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone G | TM-00255
T-00255-0074 | PS4-28-FO-0007 |  |  |  |  | TJX11 - Orifice plate | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 18 |  |  | TZ-MID-67-WPR2-135401 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone G | TM-00255
T-00255-0075 | PS4-28-FO-0009A |  |  |  |  | TJX11 - Orifice plate | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 18 |  |  | TZ-MID-67-WPR2-135404 | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone E | TM-00255
T-00255-0076 | PS4-28-FO-0009B |  |  |  |  | TJX11 - Orifice plate | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 18 |  |  | TZ-MID-67-WPR2-135404 | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone E | TM-00255
T-00255-0077 | PS4-50-FE-0001 |  |  |  |  | TJX11 - Orifice plate | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Orifice Flow Element | EACOP | CPP AGI |  |  | 18 |  |  | TZ-MID-67-WPR2-135500 | PS4 - TZA - PS4 - Tanzania | PS4-50-03 - Water Pre-Treatment Package |  | PS4-50-03 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone F | TM-00255
T-00255-0078 | PS4-60-FO-0001 |  |  |  |  | TJX11 - Orifice plate | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 18 |  |  | TZ-MID-67-WPR2-135121 | PS4 - TZA - PS4 - Tanzania | PS4-60-25 - Cooling Water Maintenance Tank & Return Pump |  | PS4-60-25 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone E | TM-00255
T-00255-0079 | PS4-60-FO-0002 |  |  |  |  | TJX11 - Orifice plate | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 18 |  |  | TZ-MID-67-WPR2-135120 | PS4 - TZA - PS4 - Tanzania | PS4-60-24 - Cooling Water Tank & Pump |  | PS4-60-24 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone E | TM-00255
T-00255-0080 | PS4-71-FE-0018 |  |  |  |  | TJX11 - Orifice plate | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Orifice Flow Element | EACOP | CPP AGI |  |  | 18 |  |  | TZ-MID-67-WPR2-135007 | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone H | TM-00255
T-00255-0081 | PS4-71-FE-0019 |  |  |  |  | TJX11 - Orifice plate | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Orifice Flow Element | EACOP | CPP AGI |  |  | 18 |  |  | TZ-MID-67-WPR2-135008 | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone B | TM-00255
T-00255-0082 | PS4-71-FO-0013A |  |  |  |  | TJX11 - Orifice plate | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 18 |  |  | TZ-MID-67-WPR2-135203 | PS4 - TZA - PS4 - Tanzania | PS4-71-16 - Diesel Fuel Supply Pump A/B |  | PS4-71-16 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone F | TM-00255
T-00255-0083 | PS4-71-FO-0013B |  |  |  |  | TJX11 - Orifice plate | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 18 |  |  | TZ-MID-67-WPR2-135203 | PS4 - TZA - PS4 - Tanzania | PS4-71-16 - Diesel Fuel Supply Pump A/B |  | PS4-71-16 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone F | TM-00255
T-00255-0084 | PS4-74-FO-0001 |  |  |  |  | TJX11 - Orifice plate | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Restriction Orifice | EACOP | CPP AGI |  |  | 18 |  |  | TZ-MID-67-WPR2-135002 | PS4 - TZA - PS4 - Tanzania | PS4-74-04 - Nitrogen Distribution Header |  | PS4-74-04 |  |  | Orifice Plate | I | To be completed | PS4 - Milestone F | TM-00255
T-00256-0067 | PS4-09-LB-0006-CX01 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-09-LB-0006 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-09-01 - HVAC for Office and Facilities building |  | PS4-09-01 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone I | TM-00256
T-00256-0068 | PS4-09-LB-0007-CX01 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-09-LB-0007 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-09-04 - HVAC for Workshop & Warehouse |  | PS4-09-04 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone I | TM-00256
T-00256-0069 | PS4-09-LB-0008-CX01 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-09-LB-0008 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone D | TM-00256
T-00256-0070 | PS4-53-LA-0001-CX01 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-53-LA-0001 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-53-04 - Water Treatment Purification Package |  | PS4-53-04 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone F | TM-00256
T-00256-0071 | PS4-60-IE-0004-CX03 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone B | TM-00256
T-00256-0072 | PS4-60-IE-0004-CX04 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone B | TM-00256
T-00256-0073 | PS4-60-LA-0003-CX01 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone B | TM-00256
T-00256-0074 | PS4-74-LB-5101-CX01 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-74-LB-5101 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-74-02 - N2 Generation Skid (UCP) |  | PS4-74-02 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone F | TM-00256
T-00256-0075 | PS4-82-LA-0001-CX01 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-82-LA-0001 | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-82-03 - Sewage Treatment Plant Package (UCP) |  | PS4-82-03 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone I | TM-00256
T-00256-0084 | PS4-75-LA-6200-CX01 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-75-LA-6200 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-75-01 - DRA Injection Package |  | PS4-75-01 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone G | TM-00256
T-00256-0091 | PS4-60-LA-0003-CX02 |  |  |  |  | TJX12 - Optical fiber cable | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Cable FROM PS4-04-PNC-0001 TO PS4-60-LA-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Optical Fibre Cable | I | To be completed | PS4 - Milestone B | TM-00256
T-00257-0215 | PS4-25-TW-0001 |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134000 | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00257
T-00257-0216 | PS4-25-TW-0002A |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134003 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00257
T-00257-0217 | PS4-25-TW-0002B |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134004 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00257
T-00257-0218 | PS4-25-TW-0002C |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134005 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00257
T-00257-0219 | PS4-25-TW-0003A |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134003 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00257
T-00257-0220 | PS4-25-TW-0003B |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134004 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00257
T-00257-0221 | PS4-25-TW-0003C |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134005 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00257
T-00257-0222 | PS4-25-TW-0004 |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134007 | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00257
T-00257-0223 | PS4-28-TW-1104 |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135401 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Thermowell | I | To be completed | PS4 - Milestone G | TM-00257
T-00257-0224 | PS4-28-TW-1105 |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135401 | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Thermowell | I | To be completed | PS4 - Milestone G | TM-00257
T-00257-0225 | PS4-28-TW-1201 |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135402 | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump |  | PS4-28-06 |  |  | Thermowell | I | To be completed | PS4 - Milestone G | TM-00257
T-00257-0226 | PS4-28-TW-1401 |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135404 | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Thermowell | I | To be completed | PS4 - Milestone E | TM-00257
T-00257-0227 | PS4-28-TW-1402 |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135404 | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Thermowell | I | To be completed | PS4 - Milestone E | TM-00257
T-00257-0228 | PS4-60-TW-0005A |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135100 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-07-01 05:47 | PS4-60-70 |  |  | Thermowell | I | Closed | PS4 - Milestone B | TM-00257 | sridhar, muthu
T-00257-0229 | PS4-60-TW-0005B |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135103 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-07-01 05:52 | PS4-60-71 |  |  | Thermowell | I | Closed | PS4 - Milestone B | TM-00257 | sridhar, muthu
T-00257-0230 | PS4-60-TW-0005C |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135106 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system | 2026-07-29 12:47 | PS4-60-72 |  |  | Thermowell | I | Closed | PS4 - Milestone D | TM-00257 | sridhar, muthu
T-00257-0231 | PS4-60-TW-0005D |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135109 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system | 2026-07-29 12:51 | PS4-60-73 |  |  | Thermowell | I | Closed | PS4 - Milestone D | TM-00257 | sridhar, muthu
T-00257-0232 | PS4-60-TW-0005E |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135112 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | Thermowell | I | To be completed | PS4 - Milestone D | TM-00257
T-00257-0233 | PS4-60-TW-0005F |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135115 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | Thermowell | I | To be completed | PS4 - Milestone D | TM-00257
T-00257-0234 | PS4-60-TW-0005G |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135118 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | Thermowell | I | To be completed | PS4 - Milestone E | TM-00257
T-00257-0235 | PS4-60-TW-0006A |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135100 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-07-01 05:56 | PS4-60-70 |  |  | Thermowell | I | Closed | PS4 - Milestone B | TM-00257 | sridhar, muthu
T-00257-0236 | PS4-60-TW-0006B |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135103 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-07-01 05:59 | PS4-60-71 |  |  | Thermowell | I | Closed | PS4 - Milestone B | TM-00257 | sridhar, muthu
T-00257-0237 | PS4-60-TW-0006C |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135106 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system | 2026-07-29 13:00 | PS4-60-72 |  |  | Thermowell | I | Closed | PS4 - Milestone D | TM-00257 | sridhar, muthu
T-00257-0238 | PS4-60-TW-0006D |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135109 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system | 2026-07-29 13:10 | PS4-60-73 |  |  | Thermowell | I | Closed | PS4 - Milestone D | TM-00257 | sridhar, muthu
T-00257-0239 | PS4-60-TW-0006E |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135112 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | Thermowell | I | To be completed | PS4 - Milestone D | TM-00257
T-00257-0240 | PS4-60-TW-0006F |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135115 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | Thermowell | I | To be completed | PS4 - Milestone D | TM-00257
T-00257-0241 | PS4-60-TW-0006G |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135118 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | Thermowell | I | To be completed | PS4 - Milestone E | TM-00257
T-00257-0242 | PS4-60-TW-0007A |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135100 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-07-01 06:02 | PS4-60-70 |  |  | Thermowell | I | Closed | PS4 - Milestone B | TM-00257 | sridhar, muthu
T-00257-0243 | PS4-60-TW-0007B |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135103 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-07-01 06:06 | PS4-60-71 |  |  | Thermowell | I | Closed | PS4 - Milestone B | TM-00257 | sridhar, muthu
T-00257-0244 | PS4-60-TW-0007C |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135106 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system | 2026-07-29 13:20 | PS4-60-72 |  |  | Thermowell | I | Closed | PS4 - Milestone D | TM-00257 | sridhar, muthu
T-00257-0245 | PS4-60-TW-0007D |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135109 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system | 2026-07-29 13:24 | PS4-60-73 |  |  | Thermowell | I | Closed | PS4 - Milestone D | TM-00257 | sridhar, muthu
T-00257-0246 | PS4-60-TW-0007E |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135112 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | Thermowell | I | To be completed | PS4 - Milestone D | TM-00257
T-00257-0247 | PS4-60-TW-0007F |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135115 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | Thermowell | I | To be completed | PS4 - Milestone D | TM-00257
T-00257-0248 | PS4-60-TW-0007G |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135118 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | Thermowell | I | To be completed | PS4 - Milestone E | TM-00257
T-00257-0249 | PS4-60-TW-0008A |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135100 | PS4 - TZA - PS4 - Tanzania | PS4-60-70 - Engine A Cooling system | 2026-07-01 06:09 | PS4-60-70 |  |  | Thermowell | I | Closed | PS4 - Milestone B | TM-00257 | sridhar, muthu
T-00257-0250 | PS4-60-TW-0008B |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135103 | PS4 - TZA - PS4 - Tanzania | PS4-60-71 - Engine B Cooling system | 2026-07-01 06:12 | PS4-60-71 |  |  | Thermowell | I | Closed | PS4 - Milestone B | TM-00257 | sridhar, muthu
T-00257-0251 | PS4-60-TW-0008C |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135106 | PS4 - TZA - PS4 - Tanzania | PS4-60-72 - Engine C Cooling system | 2026-07-29 13:29 | PS4-60-72 |  |  | Thermowell | I | Closed | PS4 - Milestone D | TM-00257 | sridhar, muthu
T-00257-0252 | PS4-60-TW-0008D |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135109 | PS4 - TZA - PS4 - Tanzania | PS4-60-73 - Engine D Cooling system | 2026-07-29 13:32 | PS4-60-73 |  |  | Thermowell | I | Closed | PS4 - Milestone D | TM-00257 | sridhar, muthu
T-00257-0253 | PS4-60-TW-0008E |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135112 | PS4 - TZA - PS4 - Tanzania | PS4-60-74 - Engine E Cooling system |  | PS4-60-74 |  |  | Thermowell | I | To be completed | PS4 - Milestone D | TM-00257
T-00257-0254 | PS4-60-TW-0008F |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135115 | PS4 - TZA - PS4 - Tanzania | PS4-60-75 - Engine F Cooling system |  | PS4-60-75 |  |  | Thermowell | I | To be completed | PS4 - Milestone D | TM-00257
T-00257-0255 | PS4-60-TW-0008G |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135118 | PS4 - TZA - PS4 - Tanzania | PS4-60-76 - Engine G Cooling system |  | PS4-60-76 |  |  | Thermowell | I | To be completed | PS4 - Milestone E | TM-00257
T-00257-0256 | PS4-71-TW-0003 |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00257
T-00257-0257 | PS4-71-TW-0004 |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00257
T-00257-0258 | PS4-71-TW-0006 |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00257
T-00257-0259 | PS4-71-TW-0007 |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00257
T-00257-0260 | PS4-71-TW-4102 |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135000 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00257
T-00257-0261 | PS4-71-TW-4103 |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135000 | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00257
T-00257-0262 | PS4-71-TW-4202 |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135003 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00257
T-00257-0263 | PS4-71-TW-4203 |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135003 | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Thermowell | I | To be completed | PS4 - Milestone H | TM-00257
T-00257-0264 | PS4-74-TW-0001 |  |  |  |  | TJX13 - Thermowell | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Thermowell | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135002 | PS4 - TZA - PS4 - Tanzania | PS4-74-04 - Nitrogen Distribution Header |  | PS4-74-04 |  |  | Thermowell | I | To be completed | PS4 - Milestone F | TM-00257
T-00275-3628 | PS4-60-IE-0003B-CA02 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003A TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-11 11:33 | PS4-60-05 |  |  | RJ45 Cable | T | Closed | PS4 - Milestone B | TM-00275 | sridhar, muthu
T-00275-3629 | PS4-60-IE-0003B-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003A TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) |  | PS4-60-05 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone B | TM-00275
T-00275-3630 | PS4-60-IE-0003B-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003A TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) |  | PS4-60-05 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone B | TM-00275
T-00275-3631 | PS4-60-IE-0003B-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003A TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) |  | PS4-60-05 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone B | TM-00275
T-00275-3632 | PS4-60-IE-0003C-CA02 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003B TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) | 2026-07-11 11:36 | PS4-60-08 |  |  | RJ45 Cable | T | Closed | PS4 - Milestone D | TM-00275 | sridhar, muthu
T-00275-3633 | PS4-60-IE-0003C-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003B TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3634 | PS4-60-IE-0003C-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003B TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3635 | PS4-60-IE-0003C-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003B TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3636 | PS4-60-IE-0003D-CA02 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003C TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) | 2026-07-11 11:37 | PS4-60-11 |  |  | RJ45 Cable | T | Closed | PS4 - Milestone D | TM-00275 | sridhar, muthu
T-00275-3637 | PS4-60-IE-0003D-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003C TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3638 | PS4-60-IE-0003D-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003C TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3639 | PS4-60-IE-0003D-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003C TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3640 | PS4-60-IE-0003E-CA02 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003D TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) | 2026-07-11 11:39 | PS4-60-14 |  |  | RJ45 Cable | T | Closed | PS4 - Milestone D | TM-00275 | sridhar, muthu
T-00275-3641 | PS4-60-IE-0003E-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003D TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3642 | PS4-60-IE-0003E-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003D TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3643 | PS4-60-IE-0003E-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003D TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3644 | PS4-60-IE-0003F-CA02 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003E TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) | 2026-07-11 11:41 | PS4-60-17 |  |  | RJ45 Cable | T | Closed | PS4 - Milestone D | TM-00275 | sridhar, muthu
T-00275-3645 | PS4-60-IE-0003F-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003E TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3646 | PS4-60-IE-0003F-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003E TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3647 | PS4-60-IE-0003F-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003E TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3648 | PS4-60-IE-0003G-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003F TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone E | TM-00275
T-00275-3649 | PS4-60-IE-0003G-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003F TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone E | TM-00275
T-00275-3650 | PS4-60-IE-0003G-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003F TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone E | TM-00275
T-00275-3651 | PS4-60-IE-0004-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003A TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone B | TM-00275
T-00275-3652 | PS4-60-IE-0004-CA07 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003G TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone B | TM-00275
T-00275-3653 | PS4-60-IE-0004-CA08 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003A TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone B | TM-00275
T-00275-3654 | PS4-60-IE-0004-CA14 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003G TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone B | TM-00275
T-00275-3655 | PS4-60-IE-0004-CA15 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003A TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone B | TM-00275
T-00275-3656 | PS4-60-IE-0004-CA21 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003G TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone B | TM-00275
T-00275-3657 | PS4-60-IH-0001A-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003G TO PS4-60-IH-0001A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 2026-07-11 12:28 | PS4-60-03 |  |  | RJ45 Cable | T | Closed | PS4 - Milestone B | TM-00275 | sridhar, muthu
T-00275-3658 | PS4-60-IH-0001B-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0001B TO PS4-60-IH-0001B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 2026-07-11 12:29 | PS4-60-06 |  |  | RJ45 Cable | T | Closed | PS4 - Milestone B | TM-00275 | sridhar, muthu
T-00275-3659 | PS4-60-IH-0001C-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0001C TO PS4-60-IH-0001C | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | 2026-07-11 12:31 | PS4-60-09 |  |  | RJ45 Cable | T | Closed | PS4 - Milestone D | TM-00275 | sridhar, muthu
T-00275-3660 | PS4-60-IH-0001D-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0001D TO PS4-60-IH-0001D | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | 2026-07-11 12:32 | PS4-60-12 |  |  | RJ45 Cable | T | Closed | PS4 - Milestone D | TM-00275 | sridhar, muthu
T-00275-3661 | PS4-60-IH-0001E-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0001E TO PS4-60-IH-0001E | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | 2026-07-11 12:34 | PS4-60-15 |  |  | RJ45 Cable | T | Closed | PS4 - Milestone D | TM-00275 | sridhar, muthu
T-00275-3662 | PS4-60-IH-0001F-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0001F TO PS4-60-IH-0001F | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | 2026-07-11 12:36 | PS4-60-18 |  |  | RJ45 Cable | T | Closed | PS4 - Milestone D | TM-00275 | sridhar, muthu
T-00275-3663 | PS4-60-IH-0001G-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0001G TO PS4-60-IH-0001G | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | 2026-07-11 12:37 | PS4-60-21 |  |  | RJ45 Cable | T | Closed | PS4 - Milestone E | TM-00275 | sridhar, muthu
T-00275-3664 | PS4-60-IN-0001A-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0001A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-49 - Lube Oil Separator Module PS4-60-UO-81100A |  | PS4-60-49 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone B | TM-00275
T-00275-3665 | PS4-60-IN-0001B-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0001B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-50 - Lube Oil Separator Module PS4-60-UO-81100B |  | PS4-60-50 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone B | TM-00275
T-00275-3666 | PS4-60-IN-0001C-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0001C | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-51 - Lube Oil Separator Module PS4-60-UO-81100C |  | PS4-60-51 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3667 | PS4-60-IN-0001D-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0001D | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-52 - Lube Oil Separator Module PS4-60-UO-81100D |  | PS4-60-52 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3668 | PS4-60-IN-0001E-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0001E | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-53 - Lube Oil Separator Module PS4-60-UO-81100E |  | PS4-60-53 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3669 | PS4-60-IN-0001F-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0001F | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-54 - Lube Oil Separator Module PS4-60-UO-81100F |  | PS4-60-54 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3670 | PS4-60-IN-0001G-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0001G | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-55 - Lube Oil Separator Module PS4-60-UO-81100G |  | PS4-60-55 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone E | TM-00275
T-00275-3671 | PS4-60-IN-0002A-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003A TO PS4-60-IN-0002A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-57 - Fuel Conditioning Module PS4-60-UZ-8900A (UCP) |  | PS4-60-57 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone B | TM-00275
T-00275-3672 | PS4-60-IN-0002B-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003B TO PS4-60-IN-0002B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-59 - Fuel Conditioning Module PS4-60-UZ-8900B (UCP) |  | PS4-60-59 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone B | TM-00275
T-00275-3673 | PS4-60-IN-0002C-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003C TO PS4-60-IN-0002C | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-61 - Fuel Conditioning Module PS4-60-UZ-8900C (UCP) |  | PS4-60-61 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3674 | PS4-60-IN-0002D-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003D TO PS4-60-IN-0002D | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-63 - Fuel Conditioning Module PS4-60-UZ-8900D (UCP) |  | PS4-60-63 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3675 | PS4-60-IN-0002E-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003E TO PS4-60-IN-0002E | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-65 - Fuel Conditioning Module PS4-60-UZ-8900E (UCP) |  | PS4-60-65 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3676 | PS4-60-IN-0002F-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003F TO PS4-60-IN-0002F | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-67 - Fuel Conditioning Module PS4-60-UZ-8900F (UCP) |  | PS4-60-67 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3677 | PS4-60-IN-0002G-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003G TO PS4-60-IN-0002G | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-69 - Fuel Conditioning Module PS4-60-UZ-8900G (UCP) |  | PS4-60-69 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone E | TM-00275
T-00275-3678 | PS4-60-LA-0002B-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0004 TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3679 | PS4-60-LA-0002B-CA02 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-LA-0002A TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3680 | PS4-60-LA-0002B-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-LA-0002A TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3681 | PS4-60-LA-0002B-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-LA-0002A TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3682 | PS4-60-LA-0002B-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-LA-0002C TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3683 | PS4-60-LA-0002B-CA06 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-LA-0002C TO PS4-60-LA-0002B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3684 | PS4-60-LA-0002C-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0004 TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3685 | PS4-60-LA-0002C-CA02 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-LA-0002A TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3686 | PS4-60-LA-0002C-CA03 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-LA-0002A TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3687 | PS4-60-LA-0002C-CA04 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-LA-0002A TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3688 | PS4-60-LA-0002C-CA05 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-LA-0002B TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3689 | PS4-60-LA-0002C-CA06 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-LA-0002B TO PS4-60-LA-0002C | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-3690 | PS4-60-SEA-0001-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0004 TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone E | TM-00275
T-00275-3691 | PS4-71-IN-0001-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone F | TM-00275
T-00275-3692 | PS4-71-IN-0001-CA11 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0003A TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) | 2026-07-11 11:58 | PS4-71-19 |  |  | RJ45 Cable | T | Closed | PS4 - Milestone F | TM-00275 | sridhar, muthu
T-00275-3693 | PS4-71-IN-0002-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0002 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-09 - CFO Pre-Pressure Module (UCP) |  | PS4-71-09 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone H | TM-00275
T-00275-3694 | PS4-71-IN-0003-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0003 | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS4-71-23 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone B | TM-00275
T-00275-3695 | PS4-71-IN-0004A-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone H | TM-00275
T-00275-3696 | PS4-71-IN-0004B-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-60-IE-0004 TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 6 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone H | TM-00275
T-00275-4200 | PS4-09-LB-8451A-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8451A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00275-4201 | PS4-09-LB-8451B-CA01 |  |  |  |  | TIX01 - RJ45 Cable | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-09-LB-0008 TO PS4-09-LB-8451B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | RJ45 Cable | T | To be completed | PS4 - Milestone D | TM-00275
T-00284-0110 | PS4-01-PDIT-0011A |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125902 | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone C | TM-00284
T-00284-0111 | PS4-01-PDIT-0011B |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125902 | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone C | TM-00284
T-00284-0112 | PS4-01-PDIT-0012A |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125903 | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone C | TM-00284
T-00284-0113 | PS4-01-PDIT-0012B |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-125903 | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone C | TM-00284
T-00284-0114 | PS4-25-PDIT-0034A |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134003 | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone H | TM-00284
T-00284-0115 | PS4-25-PDIT-0034B |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134004 | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone H | TM-00284
T-00284-0116 | PS4-25-PDIT-0034C |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134005 | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone H | TM-00284
T-00284-0117 | PS4-25-PDIT-0050 |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-134006 | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone H | TM-00284
T-00284-0118 | PS4-71-PDIT-0030 |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135005 | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone H | TM-00284
T-00284-0119 | PS4-71-PDIT-0056A |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135006 | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone H | TM-00284
T-00284-0120 | PS4-71-PDIT-0056B |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Diff Press Ind Transmitter | EACOP | CPP AGI |  |  | 1 |  |  | TZ-MID-67-WPR2-135006 | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone H | TM-00284
T-00284-0191 | PS4-01-FCV-0003A |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone C | TM-00284
T-00284-0192 | PS4-01-FCV-0003B |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone C | TM-00284
T-00284-0193 | PS4-01-FCV-0004A |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone C | TM-00284
T-00284-0194 | PS4-01-FCV-0004B |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone C | TM-00284
T-00284-0195 | PS4-25-FCV-0003A |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone H | TM-00284
T-00284-0196 | PS4-25-FCV-0003B |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone H | TM-00284
T-00284-0197 | PS4-25-FCV-0003C |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone H | TM-00284
T-00284-0198 | PS4-25-FCV-0004 |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone H | TM-00284
T-00284-0199 | PS4-71-FCV-0018 |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone H | TM-00284
T-00284-0200 | PS4-71-FCV-0019 |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B |  | PS4-71-21 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone B | TM-00284
T-00284-0201 | PS4-71-FCV-0020 |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Flow Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone H | TM-00284
T-00284-0202 | PS4-71-LCV-4101 |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | Level Control Valve | EACOP | CPP AGI |  |  | 1 |  |  |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone H | TM-00284
T-00284-0203 | PS4-09-PDIT-8207 |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | DIFFERENTIAL PRESSURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone D | TM-00284
T-00284-0204 | PS4-09-PDIT-8407 |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | DIFFERENTIAL PRESSURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone D | TM-00284
T-00284-0205 | PS4-09-PDIT-8408 |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | DIFFERENTIAL PRESSURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone D | TM-00284
T-00284-0206 | PS4-09-PDIT-8409 |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | DIFFERENTIAL PRESSURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone D | TM-00284
T-00284-0207 | PS4-09-PDIT-8411 |  |  |  |  | TJX06 - Tubing pressure test | PCOM - Precommissioning | I | Static Test | I - Instrumentation | DIFFERENTIAL PRESSURE TRANSMITTER | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  | Tubing Pressure Test | I | To be completed | PS4 - Milestone D | TM-00284
T-00604-0308 | PS4-61-IJ-0001-CL01 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-63-NER-0010 TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-07-18 13:02 | PS4-61-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone D | TM-00604 | sridhar, muthu
T-00604-0309 | PS4-61-IJ-0001-CL02 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-63-NER-0011 TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-07-18 13:04 | PS4-61-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone D | TM-00604 | sridhar, muthu
T-00604-0310 | PS4-61-IJ-0010-CL01 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-NER-0010 TO PS4-61-IJ-0010 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-07-18 13:06 | PS4-61-02 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone G | TM-00604 | sridhar, muthu
T-00604-0311 | PS4-61-IK-0001-CG01 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  |  | E | To be completed | PS4 - Milestone D | TM-00604
T-00604-0312 | PS4-61-IK-0001-CG02 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  |  | E | To be completed | PS4 - Milestone D | TM-00604
T-00604-0313 | PS4-61-IK-0001-CG03 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  |  | E | To be completed | PS4 - Milestone D | TM-00604
T-00604-0314 | PS4-61-IK-0001-CG04 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  |  | E | To be completed | PS4 - Milestone D | TM-00604
T-00604-0315 | PS4-61-IK-0001-CL01 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-05 16:15 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0316 | PS4-61-IK-0001-CL02 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-05 16:16 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0317 | PS4-61-IK-0001-CL03 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-05 16:17 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0318 | PS4-61-IK-0001-CL04 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-05 16:18 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0319 | PS4-61-IK-0001-CL05 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-05 16:19 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0320 | PS4-61-IK-0001-CL06 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-05 16:19 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0321 | PS4-61-IK-0001-CL07 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-05 16:20 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0322 | PS4-61-IK-0001-CL08 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-05 16:21 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0323 | PS4-61-IK-0001-CL09 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-05 16:21 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0324 | PS4-61-IK-0001-CL10 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-05 16:22 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0325 | PS4-61-IK-0001-CL11 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-05 16:23 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0326 | PS4-61-IK-0001-CL12 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-05 16:24 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0327 | PS4-61-IK-0001-CL13 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-05 16:24 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0328 | PS4-61-IK-0001-CL14 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-05 16:25 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0329 | PS4-61-IK-0001-CL15 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-05 16:25 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0330 | PS4-61-IK-0001-CL16 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-05 16:26 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0331 | PS4-61-IK-0001-CL17 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-05 16:27 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0332 | PS4-61-IK-0001-CL18 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-05 16:28 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0333 | PS4-61-IK-0001-CL19 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-06 14:31 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0334 | PS4-61-IK-0001-CL20 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-06 14:32 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0335 | PS4-61-IK-0001-CL21 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-06 14:33 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0336 | PS4-61-IK-0001-CL22 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-06 14:33 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0337 | PS4-61-IK-0001-CL23 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-06 14:34 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0338 | PS4-61-IK-0001-CL24 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-06 14:36 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0339 | PS4-61-IK-0001-CL25 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-06 14:37 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0340 | PS4-61-IK-0001-CL26 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-06 14:37 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0341 | PS4-61-IK-0001-CL27 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-06 14:39 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0342 | PS4-61-IK-0001-CL28 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-06 14:47 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0343 | PS4-61-IK-0001-CL29 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-06 14:48 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0344 | PS4-61-IK-0001-CL30 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-06 14:49 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0345 | PS4-61-IK-0001-CL31 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-06 14:49 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0346 | PS4-61-IK-0001-CL32 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-06 14:50 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0347 | PS4-61-IK-0001-CL33 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-06 14:51 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0348 | PS4-61-IK-0001-CL34 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-06 14:52 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0349 | PS4-61-IK-0001-CL35 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-06 14:53 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0350 | PS4-61-IK-0001-CL36 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-06 14:56 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0351 | PS4-61-IK-0001-CL44 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-11 07:05 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0352 | PS4-61-IK-0001-CL45 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-11 07:12 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0353 | PS4-61-ISR-0101-CL01 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0008 TO PS4-61-ISR-0101 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-07-18 13:07 | PS4-61-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone D | TM-00604 | sridhar, muthu
T-00604-0354 | PS4-61-IU-0010-CL01 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0008 TO PS4-61-IU-0010 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-07-18 13:09 | PS4-61-02 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone G | TM-00604 | sridhar, muthu
T-00604-0355 | PS4-61-IU-0010-CL02 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0008 TO PS4-61-IU-0010 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-07-18 13:12 | PS4-61-02 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone G | TM-00604 | sridhar, muthu
T-00604-0356 | PS4-61-IV-0001A-CL01 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0008 TO PS4-61-IV-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-13 06:42 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0357 | PS4-61-IV-0001B-CL01 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0008 TO PS4-61-IV-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-13 06:43 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00604 | sridhar, muthu
T-00604-0358 | PS4-61-NER-0010-CL01 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0008 TO PS4-61-NER-0010 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) | 2026-07-18 13:15 | PS4-61-02 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone G | TM-00604 | sridhar, muthu
T-00604-0359 | PS4-63-IV-0010-CL01 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0008 TO PS4-63-IV-0010 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-07-18 13:16 | PS4-61-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone D | TM-00604 | sridhar, muthu
T-00604-0360 | PS4-63-IV-0011-CL01 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0008 TO PS4-63-IV-0011 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-07-18 13:58 | PS4-61-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone D | TM-00604 | sridhar, muthu
T-00604-0361 | PS4-63-NER-0010-CL01 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0008 TO PS4-63-NER-0010 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-05-24 06:33 | PS4-61-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone D | TM-00604 | sridhar, muthu
T-00604-0362 | PS4-63-NER-0011-CL01 |  |  |  |  | CPX09a - LV Power Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IG-0008 TO PS4-63-NER-0011 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) | 2026-07-18 13:24 | PS4-61-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone D | TM-00604 | sridhar, muthu
T-00606-0083 | PS4-61-IE-0002-CD01 |  |  |  |  | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0010 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00606
T-00606-0084 | PS4-61-IE-0002-CD02 |  |  |  |  | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0010 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00606
T-00606-0085 | PS4-61-IE-0002-CD03 |  |  |  |  | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0010 TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00606
T-00606-0086 | PS4-61-IJ-0001-CD01 |  |  |  |  | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-63-IV-0010 TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00606
T-00606-0087 | PS4-61-IJ-0001-CD03 |  |  |  |  | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-63-IV-0011 TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00606
T-00606-0088 | PS4-61-IJ-0001-CD32 |  |  |  |  | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001A TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-11 07:21 | PS4-61-06 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone A | TM-00606 | sridhar, muthu
T-00606-0089 | PS4-61-IJ-0001-CD33 |  |  |  |  | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0001B TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-11 07:20 | PS4-61-06 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone A | TM-00606 | sridhar, muthu
T-00606-0090 | PS4-61-IJ-0001-CD34 |  |  |  |  | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0010 TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) |  | PS4-61-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone G | TM-00606
T-00606-0091 | PS4-61-IJ-0001-CD35 |  |  |  |  | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0010 TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) |  | PS4-61-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone G | TM-00606
T-00606-0092 | PS4-61-IJ-0001-CD36 |  |  |  |  | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IU-0010 TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-02 - 6.6kV Switchboard and Transformer LLHT North & South - EITS Building (PS4-61-IJ-0010) |  | PS4-61-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone G | TM-00606
T-00606-0093 | PS4-61-IJ-0001-CD37 |  |  |  |  | CPX10a - Multicore Electrical Control Cable (both end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-ISR-0101 TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00606
T-00608-0483 | PS4-01-FIT-0003A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0002 TO PS4-01-FIT-0003A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  |  | E | To be completed | PS4 - Milestone C | TM-00608
T-00608-0484 | PS4-01-FIT-0003B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0002 TO PS4-01-FIT-0003B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  |  | E | To be completed | PS4 - Milestone C | TM-00608
T-00608-0485 | PS4-01-FIT-0004A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0002 TO PS4-01-FIT-0004A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  |  | E | To be completed | PS4 - Milestone C | TM-00608
T-00608-0486 | PS4-01-FIT-0004B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0002 TO PS4-01-FIT-0004B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  |  | E | To be completed | PS4 - Milestone C | TM-00608
T-00608-0487 | PS4-01-IE-0001A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-01-IE-0001A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-05 - Foam Skid | 2026-07-07 07:27 | PS4-01-05 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone F | TM-00608 | sridhar, muthu
T-00608-0488 | PS4-01-IE-0001B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-01-IE-0001B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-05 - Foam Skid | 2026-07-07 07:28 | PS4-01-05 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone F | TM-00608 | sridhar, muthu
T-00608-0489 | PS4-01-IE-0002A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-01-IE-0002A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B | 2026-07-07 07:20 | PS4-01-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone C | TM-00608 | sridhar, muthu
T-00608-0490 | PS4-01-IE-0002B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-01-IE-0002B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B | 2026-07-07 07:21 | PS4-01-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone C | TM-00608 | sridhar, muthu
T-00608-0491 | PS4-01-IE-0009A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-01-IE-0009A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  |  | E | To be completed | PS4 - Milestone C | TM-00608
T-00608-0492 | PS4-01-IE-0009B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-01-IE-0009B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  |  | E | To be completed | PS4 - Milestone C | TM-00608
T-00608-0493 | PS4-03-GDLHP-0137-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0002 TO PS4-03-GDLHP-0137 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0494 | PS4-03-GDLHP-0142-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0002 TO PS4-03-GDLHP-0142 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0495 | PS4-03-GDLHP-0143-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0002 TO PS4-03-GDLHP-0143 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0496 | PS4-03-GDLHP-0144-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0002 TO PS4-03-GDLHP-0144 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0497 | PS4-03-GDLHP-0146-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0002 TO PS4-03-GDLHP-0146 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0498 | PS4-03-GDLHP-0147-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0002 TO PS4-03-GDLHP-0147 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0499 | PS4-03-GDLHP-0149-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0002 TO PS4-03-GDLHP-0149 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0500 | PS4-03-GDLHP-0150-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0002 TO PS4-03-GDLHP-0150 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0501 | PS4-03-GDLHP-0401-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0002 TO PS4-03-GDLHP-0401 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  |  | E | To be completed | PS4 - Milestone F | TM-00608
T-00608-0502 | PS4-05-IG-0004-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-05-IG-0004 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-03 - Outdoor Emergency Lighting DB - PS4-05-IG-0004 |  | PS4-62-03 |  |  |  | E | To be completed | PS4 - Milestone G | TM-00608
T-00608-0503 | PS4-05-IG-0006-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-05-IG-0006 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-04 - Outdoor Emergency Lighting DB - PS4-05-IG-0006 | 2026-06-03 14:00 | PS4-62-04 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone G | TM-00608 | sridhar, muthu
T-00608-0504 | PS4-25-DM-3200A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-DM-3200A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-07 07:29 | PS4-25-02 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone H | TM-00608 | sridhar, muthu
T-00608-0505 | PS4-25-DM-3200B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-DM-3200B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-07 07:30 | PS4-25-02 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone H | TM-00608 | sridhar, muthu
T-00608-0506 | PS4-25-DM-3300A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-DM-3300A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-07 07:30 | PS4-25-03 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone H | TM-00608 | sridhar, muthu
T-00608-0507 | PS4-25-DM-3300B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-DM-3300B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-07 07:31 | PS4-25-03 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone H | TM-00608 | sridhar, muthu
T-00608-0508 | PS4-25-DM-3400A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-DM-3400A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0509 | PS4-25-DM-3400B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-DM-3400B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0510 | PS4-25-DM-6400A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-DM-6400A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-07 07:32 | PS4-25-02 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone H | TM-00608 | sridhar, muthu
T-00608-0511 | PS4-25-DM-6400B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-DM-6400B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-07 07:33 | PS4-25-02 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone H | TM-00608 | sridhar, muthu
T-00608-0512 | PS4-25-DM-6500A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-DM-6500A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-07 07:33 | PS4-25-03 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone H | TM-00608 | sridhar, muthu
T-00608-0513 | PS4-25-DM-6500B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-DM-6500B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-07 07:34 | PS4-25-03 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone H | TM-00608 | sridhar, muthu
T-00608-0514 | PS4-25-DM-6600A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-DM-6600A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0515 | PS4-25-DM-6600B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-DM-6600B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0516 | PS4-25-FIT-0001-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0002 TO PS4-25-FIT-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  |  | E | Started (not Completed) | PS4 - Milestone H | TM-00608
T-00608-0517 | PS4-25-FIT-0003A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0002 TO PS4-25-FIT-0003A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0518 | PS4-25-FIT-0003B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0002 TO PS4-25-FIT-0003B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0519 | PS4-25-FIT-0003C-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0002 TO PS4-25-FIT-0003C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0520 | PS4-25-FIT-0004-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0002 TO PS4-25-FIT-0004 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-06 - Crude Oil Export Pumps Discharge |  | PS4-25-06 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0521 | PS4-25-HE-2100-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-HE-2100 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0522 | PS4-25-HE-2200-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-HE-2200 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0523 | PS4-25-HE-2300-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-HE-2300 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0524 | PS4-25-UD-3100A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-UD-3100A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0525 | PS4-28-BE-0002A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-BE-0002A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0526 | PS4-28-BE-0002B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-BE-0002B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0527 | PS4-28-DM-3300-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-DM-3300 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump |  | PS4-28-06 |  |  |  | E | To be completed | PS4 - Milestone G | TM-00608
T-00608-0528 | PS4-28-DM-3400-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-DM-3400 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  |  | E | To be completed | PS4 - Milestone G | TM-00608
T-00608-0529 | PS4-28-DM-3500-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-DM-3500 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  |  | E | To be completed | PS4 - Milestone G | TM-00608
T-00608-0530 | PS4-28-DM-3600A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-DM-3600A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  |  | E | To be completed | PS4 - Milestone G | TM-00608
T-00608-0531 | PS4-28-DM-3600A-CL02 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-DM-3600A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  |  | E | To be completed | PS4 - Milestone G | TM-00608
T-00608-0532 | PS4-28-DM-3600B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-DM-3600B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  |  | E | To be completed | PS4 - Milestone G | TM-00608
T-00608-0533 | PS4-28-DM-3600B-CL02 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-DM-3600B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  |  | E | To be completed | PS4 - Milestone G | TM-00608
T-00608-0534 | PS4-28-DM-3700A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-DM-3700A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  |  | E | To be completed | PS4 - Milestone E | TM-00608
T-00608-0535 | PS4-28-DM-3700B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-DM-3700B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  |  | E | To be completed | PS4 - Milestone E | TM-00608
T-00608-0536 | PS4-28-DM-3800A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-DM-3800A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0537 | PS4-28-DM-3800B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-DM-3800B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0538 | PS4-28-DM-3800C-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-DM-3800C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0539 | PS4-28-DM-3900A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-DM-3900A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0540 | PS4-28-DM-3900B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-DM-3900B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0541 | PS4-28-HE-2100-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-HE-2100 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  |  | E | To be completed | PS4 - Milestone G | TM-00608
T-00608-0542 | PS4-28-HE-2200-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-HE-2200 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  |  | E | To be completed | PS4 - Milestone E | TM-00608
T-00608-0543 | PS4-28-ISO-2008-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-ISO-2008 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-10 - Oil Skimmer Package |  | PS4-28-10 |  |  |  | E | To be completed | PS4 - Milestone I | TM-00608
T-00608-0544 | PS4-50-IE-0001-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-50-IE-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-50-01 - Water Well Submersible Pumps (3100) |  | PS4-50-01 |  |  |  | E | To be completed | PS4 - Milestone I | TM-00608
T-00608-0545 | PS4-50-IE-0002-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-50-IE-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-50-02 - Water Well Submersible Pumps (3200) |  | PS4-50-02 |  |  |  | E | To be completed | PS4 - Milestone I | TM-00608
T-00608-0546 | PS4-53-DM-3100A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-53-DM-3100A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-53-02 - Water Distribution Pump A/B |  | PS4-53-02 |  |  |  | E | To be completed | PS4 - Milestone E | TM-00608
T-00608-0547 | PS4-53-DM-3100B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-53-DM-3100B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-53-02 - Water Distribution Pump A/B |  | PS4-53-02 |  |  |  | E | To be completed | PS4 - Milestone E | TM-00608
T-00608-0548 | PS4-53-IN-0001-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-53-IN-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-53-04 - Water Treatment Purification Package |  | PS4-53-04 |  |  |  | E | To be completed | PS4 - Milestone F | TM-00608
T-00608-0549 | PS4-60-DM-3300-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-60-DM-3300 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-24 - Cooling Water Tank & Pump | 2026-07-07 07:41 | PS4-60-24 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone E | TM-00608 | sridhar, muthu
T-00608-0550 | PS4-60-DM-3400-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-60-DM-3400 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-25 - Cooling Water Maintenance Tank & Return Pump |  | PS4-60-25 |  |  |  | E | To be completed | PS4 - Milestone E | TM-00608
T-00608-0551 | PS4-61-IDH-3100A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0001A TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0552 | PS4-61-IDH-3100B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0001B TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0553 | PS4-61-IDH-3100C-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0001B TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0554 | PS4-61-IG-0005-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-61-IG-0005 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 |  | PS4-62-08 |  |  |  | E | To be completed | PS4 - Milestone G | TM-00608
T-00608-0555 | PS4-61-IG-0007-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-61-IG-0007 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 | 2026-06-03 14:00 | PS4-62-09 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone G | TM-00608 | sridhar, muthu
T-00608-0556 | PS4-61-IG-0012A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-61-IG-0012A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0557 | PS4-61-IG-0012B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-61-IG-0012B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0558 | PS4-61-IG-0012C-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-61-IG-0012C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0559 | PS4-61-IG-0014-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-61-IG-0014 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-08 - Outdoor Power Distribution Board - PS4-61-IG-0014 |  | PS4-61-08 |  |  |  | E | To be completed | PS4 - Milestone G | TM-00608
T-00608-0560 | PS4-61-IG-0041-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-61-IG-0041 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-09 - Outdoor Valves Distribution Board - PS4-61-IG-0041 |  | PS4-61-09 |  |  |  | E | To be completed | PS4 - Milestone F | TM-00608
T-00608-0561 | PS4-61-IG-0042-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-61-IG-0042 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-10 - Outdoor Valves Distribution Board - PS4-61-IG-0042 |  | PS4-61-10 |  |  |  | E | To be completed | PS4 - Milestone F | TM-00608
T-00608-0562 | PS4-61-IK-0001-CL37 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-13 06:41 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00608 | sridhar, muthu
T-00608-0563 | PS4-61-IK-0001-CL38 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-13 06:40 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00608 | sridhar, muthu
T-00608-0564 | PS4-61-IK-0001-CL39 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-13 06:39 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00608 | sridhar, muthu
T-00608-0565 | PS4-61-IK-0001-CL40 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-13 06:38 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00608 | sridhar, muthu
T-00608-0566 | PS4-61-IK-0001-CL41 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-13 06:37 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00608 | sridhar, muthu
T-00608-0567 | PS4-61-IK-0001-CL42 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-13 06:36 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00608 | sridhar, muthu
T-00608-0568 | PS4-61-IK-0001-CL43 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IK-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-06 - 0.4kV Switchboard EITS Building (PS4-61-IK-0001) | 2026-05-13 05:18 | PS4-61-06 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone A | TM-00608 | sridhar, muthu
T-00608-0569 | PS4-61-IK-0003-CG01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  |  | E | To be completed | PS4 - Milestone B | TM-00608
T-00608-0570 | PS4-61-IK-0003-CG02 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  |  | E | To be completed | PS4 - Milestone B | TM-00608
T-00608-0571 | PS4-61-IK-0003-CG03 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  |  | E | To be completed | PS4 - Milestone B | TM-00608
T-00608-0572 | PS4-61-IK-0003-CG04 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  |  | E | To be completed | PS4 - Milestone B | TM-00608
T-00608-0573 | PS4-61-IK-0003-CG05 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  |  | E | To be completed | PS4 - Milestone B | TM-00608
T-00608-0574 | PS4-61-IK-0003-CG06 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IK-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) |  | PS4-61-04 |  |  |  | E | To be completed | PS4 - Milestone B | TM-00608
T-00608-0575 | PS4-61-IK-0006-CG01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  |  | E | To be completed | PS4 - Milestone D | TM-00608
T-00608-0576 | PS4-61-IK-0006-CG02 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  |  | E | To be completed | PS4 - Milestone D | TM-00608
T-00608-0577 | PS4-61-IK-0006-CG03 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  |  | E | To be completed | PS4 - Milestone D | TM-00608
T-00608-0578 | PS4-61-IK-0006-CG04 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IK-0006 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) |  | PS4-61-05 |  |  |  | E | To be completed | PS4 - Milestone D | TM-00608
T-00608-0579 | PS4-61-IV-0006A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-61-IV-0006A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0580 | PS4-61-IV-0006B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-61-IV-0006B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0581 | PS4-61-IV-0006C-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-61-IV-0006C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0582 | PS4-71-DM-3100A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-DM-3100A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-16 - Diesel Fuel Supply Pump A/B |  | PS4-71-16 |  |  |  | E | To be completed | PS4 - Milestone F | TM-00608
T-00608-0583 | PS4-71-DM-3100B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-DM-3100B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-16 - Diesel Fuel Supply Pump A/B |  | PS4-71-16 |  |  |  | E | To be completed | PS4 - Milestone F | TM-00608
T-00608-0584 | PS4-71-DM-3200-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-DM-3200 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-14 - Diesel Fuel Transfer and Dispensing Station |  | PS4-71-14 |  |  |  | E | To be completed | PS4 - Milestone F | TM-00608
T-00608-0585 | PS4-71-DM-3300A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-DM-3300A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0586 | PS4-71-DM-3300B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-DM-3300B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B |  | PS4-71-05 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0587 | PS4-71-DM-3400A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-DM-3400A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0588 | PS4-71-DM-3400B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-DM-3400B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B |  | PS4-71-13 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0589 | PS4-71-DM-3500A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-DM-3500A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B | 2026-07-07 07:22 | PS4-71-21 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone B | TM-00608 | sridhar, muthu
T-00608-0590 | PS4-71-DM-3500B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-DM-3500B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B | 2026-07-07 07:23 | PS4-71-21 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone B | TM-00608 | sridhar, muthu
T-00608-0591 | PS4-71-FIT-0011A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0002 TO PS4-71-FIT-0011A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater | 2026-07-07 07:42 | PS4-71-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone H | TM-00608 | sridhar, muthu
T-00608-0592 | PS4-71-FIT-0011B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0002 TO PS4-71-FIT-0011B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater | 2026-07-07 07:43 | PS4-71-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone H | TM-00608 | sridhar, muthu
T-00608-0593 | PS4-71-HE-2200-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-HE-2200 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0594 | PS4-71-HE-2300-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-HE-2300 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0595 | PS4-74-IG-5101-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-74-IG-5101 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-74-02 - N2 Generation Skid (UCP) |  | PS4-74-02 |  |  |  | E | To be completed | PS4 - Milestone F | TM-00608
T-00608-0596 | PS4-75-DM-3100A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-75-DM-3100A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-75-03 - Corrosion Inhibitor Injection Package |  | PS4-75-03 |  |  |  | E | To be completed | PS4 - Milestone G | TM-00608
T-00608-0597 | PS4-75-DM-3100B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-75-DM-3100B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-75-03 - Corrosion Inhibitor Injection Package |  | PS4-75-03 |  |  |  | E | To be completed | PS4 - Milestone G | TM-00608
T-00608-0598 | PS4-75-DM-3200A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-75-DM-3200A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-75-02 - Biocide Injection Package |  | PS4-75-02 |  |  |  | E | To be completed | PS4 - Milestone G | TM-00608
T-00608-0599 | PS4-75-DM-3200B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-75-DM-3200B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-75-02 - Biocide Injection Package |  | PS4-75-02 |  |  |  | E | To be completed | PS4 - Milestone G | TM-00608
T-00608-0600 | PS4-75-ISO-0001-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-75-ISO-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-75-01 - DRA Injection Package |  | PS4-75-01 |  |  |  | E | To be completed | PS4 - Milestone G | TM-00608
T-00608-0601 | PS4-75-ISO-0002-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-75-ISO-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-75-01 - DRA Injection Package |  | PS4-75-01 |  |  |  | E | To be completed | PS4 - Milestone G | TM-00608
T-00608-0602 | PS4-79-IV-0001-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-79-IV-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0603 | PS4-79-IV-0002-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-79-IV-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0604 | PS4-79-IV-0003-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-79-IV-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0605 | PS4-79-IV-0004-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-79-IV-0004 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0606 | PS4-79-IV-0005-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-79-IV-0005 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0607 | PS4-79-IV-0006-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-79-IV-0006 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0608 | PS4-79-IV-0007-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-79-IV-0007 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0609 | PS4-79-IV-0008-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-79-IV-0008 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0610 | PS4-79-IV-0009-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-79-IV-0009 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0611 | PS4-79-IV-0010-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-79-IV-0010 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0612 | PS4-79-IV-0011-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-79-IV-0011 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0613 | PS4-79-IV-0012-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-79-IV-0012 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  |  | E | To be completed | PS4 - Milestone H | TM-00608
T-00608-0614 | PS4-82-IN-0001-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-82-IN-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-82-02 - Sewage Treatment Plant Package |  | PS4-82-02 |  |  |  | E | To be completed | PS4 - Milestone I | TM-00608
T-00608-0941 | PS4-53-IN-0001-CL02 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0001A TO PS4-53-IN-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-53-04 - Water Treatment Purification Package |  | PS4-53-04 |  |  |  | E | To be completed | PS4 - Milestone F | TM-00608
T-00608-0942 | PS4-53-IN-0001-CL03 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-06-IG-0001B TO PS4-53-IN-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-53-04 - Water Treatment Purification Package |  | PS4-53-04 |  |  |  | E | To be completed | PS4 - Milestone F | TM-00608
T-00608-1060 | PS4-71-HE-2400A-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IE-0001 TO PS4-71-HE-2400A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater | 2026-07-07 07:10 | PS4-71-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone H | TM-00608 | sridhar, muthu
T-00608-1061 | PS4-71-HE-2400A-CL02 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IE-0001 TO PS4-71-HE-2400A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater | 2026-07-07 07:12 | PS4-71-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone H | TM-00608 | sridhar, muthu
T-00608-1062 | PS4-71-HE-2400A-CL03 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IE-0001 TO PS4-71-HE-2400A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater | 2026-07-07 07:12 | PS4-71-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone H | TM-00608 | sridhar, muthu
T-00608-1063 | PS4-71-HE-2400A-CL04 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IE-0001 TO PS4-71-HE-2400A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater | 2026-07-07 07:13 | PS4-71-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone H | TM-00608 | sridhar, muthu
T-00608-1064 | PS4-71-HE-2400B-CL01 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IE-0002 TO PS4-71-HE-2400B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater | 2026-07-07 07:14 | PS4-71-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone H | TM-00608 | sridhar, muthu
T-00608-1065 | PS4-71-HE-2400B-CL02 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IE-0002 TO PS4-71-HE-2400B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater | 2026-07-07 07:15 | PS4-71-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone H | TM-00608 | sridhar, muthu
T-00608-1066 | PS4-71-HE-2400B-CL03 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IE-0002 TO PS4-71-HE-2400B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater | 2026-07-07 07:15 | PS4-71-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone H | TM-00608 | sridhar, muthu
T-00608-1067 | PS4-71-HE-2400B-CL04 |  |  |  |  | CPX09b - LV Power Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-71-IE-0002 TO PS4-71-HE-2400B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater | 2026-07-07 07:16 | PS4-71-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | E | Closed | PS4 - Milestone H | TM-00608 | sridhar, muthu
T-00610-0290 | PS4-05-IE-8100-CD09 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IE-0002 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) |  | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00610
T-00610-0291 | PS4-05-IE-8100-CD22 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IE-0002 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) |  | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00610
T-00610-0292 | PS4-05-IE-8100-CD24 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IE-0002 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) |  | PS4-05-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00610
T-00610-0293 | PS4-05-IG-0004-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IE-0003 TO PS4-05-IG-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-03 - Outdoor Emergency Lighting DB - PS4-05-IG-0004 |  | PS4-62-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone G | TM-00610
T-00610-0294 | PS4-05-IG-0006-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IE-0003 TO PS4-05-IG-0006 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-04 - Outdoor Emergency Lighting DB - PS4-05-IG-0006 | 2026-06-03 14:01 | PS4-62-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone G | TM-00610 | sridhar, muthu
T-00610-0295 | PS4-05-IG-0014-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IE-0003 TO PS4-05-IG-0014 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-06 - CRO Generator Building Emergency Lighting DB - PS4-05-IG-0014 |  | PS4-62-06 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone B | TM-00610
T-00610-0296 | PS4-05-IG-0020-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IE-0003 TO PS4-05-IG-0020 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-07 - CRO Generator Electrical Building Emergency L&SP DB - PS4-05-IG-0020 |  | PS4-62-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone B | TM-00610
T-00610-0297 | PS4-06-GU-0003A-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IE-0002 TO PS4-06-GU-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building |  | PS4-06-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone B | TM-00610
T-00610-0298 | PS4-06-GU-0003B-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IE-0002 TO PS4-06-GU-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building |  | PS4-06-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone B | TM-00610
T-00610-0299 | PS4-06-IG-0004A-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IE-0002 TO PS4-06-IG-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-30 16:42 | PS4-06-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00610 | sridhar, muthu
T-00610-0300 | PS4-06-IG-0004B-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IE-0002 TO PS4-06-IG-0004B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building | 2026-07-30 16:45 | PS4-06-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00610 | sridhar, muthu
T-00610-0301 | PS4-25-HE-2100-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-HE-2100 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0302 | PS4-25-HE-2200-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-HE-2200 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0303 | PS4-25-HE-2300-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-HE-2300 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0304 | PS4-25-IES-3200A-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-IES-3200A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-07 07:35 | PS4-25-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00610 | sridhar, muthu
T-00610-0305 | PS4-25-IES-3200B-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-IES-3200B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-07 07:36 | PS4-25-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00610 | sridhar, muthu
T-00610-0306 | PS4-25-IES-3300A-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-IES-3300A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-07 07:36 | PS4-25-03 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00610 | sridhar, muthu
T-00610-0307 | PS4-25-IES-3300B-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-IES-3300B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-07 07:37 | PS4-25-03 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00610 | sridhar, muthu
T-00610-0308 | PS4-25-IES-3400A-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-IES-3400A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0309 | PS4-25-IES-3400B-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-IES-3400B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0310 | PS4-25-IES-6400A-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-IES-6400A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-07 07:38 | PS4-25-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00610 | sridhar, muthu
T-00610-0311 | PS4-25-IES-6400B-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-IES-6400B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A | 2026-07-07 07:38 | PS4-25-02 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00610 | sridhar, muthu
T-00610-0312 | PS4-25-IES-6500A-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-IES-6500A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-07 07:39 | PS4-25-03 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00610 | sridhar, muthu
T-00610-0313 | PS4-25-IES-6500B-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-IES-6500B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B | 2026-07-07 07:40 | PS4-25-03 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00610 | sridhar, muthu
T-00610-0314 | PS4-25-IES-6600A-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-IES-6600A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0315 | PS4-25-IES-6600B-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-25-IES-6600B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0316 | PS4-28-HE-2100-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-HE-2100 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone G | TM-00610
T-00610-0317 | PS4-28-HE-2200-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-HE-2200 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone E | TM-00610
T-00610-0318 | PS4-28-IES-2008-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-IES-2008 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-10 - Oil Skimmer Package |  | PS4-28-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone I | TM-00610
T-00610-0319 | PS4-28-IES-3300-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-IES-3300 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump |  | PS4-28-06 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone G | TM-00610
T-00610-0320 | PS4-28-IES-3400-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-IES-3400 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone G | TM-00610
T-00610-0321 | PS4-28-IES-3500-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-IES-3500 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone G | TM-00610
T-00610-0322 | PS4-28-IES-3600A-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-IES-3600A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone G | TM-00610
T-00610-0323 | PS4-28-IES-3600B-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-IES-3600B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-08 - Open Drain Sump and Pumps |  | PS4-28-08 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone G | TM-00610
T-00610-0324 | PS4-28-IES-3700A-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-IES-3700A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone E | TM-00610
T-00610-0325 | PS4-28-IES-3700B-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-IES-3700B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone E | TM-00610
T-00610-0326 | PS4-28-IES-3800A-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-IES-3800A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-13 - Seal Oil Drain Drum & Pump A |  | PS4-28-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0327 | PS4-28-IES-3800B-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-IES-3800B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-14 - Seal Oil Drain Drum & Pump B |  | PS4-28-14 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0328 | PS4-28-IES-3800C-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-IES-3800C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-15 - Seal Oil Drain Drum & Pump C |  | PS4-28-15 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0329 | PS4-28-IES-3900A-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-IES-3900A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0330 | PS4-28-IES-3900B-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-28-IES-3900B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0331 | PS4-53-IES-3100A-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-53-IES-3100A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-53-02 - Water Distribution Pump A/B |  | PS4-53-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone E | TM-00610
T-00610-0332 | PS4-53-IES-3100B-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-53-IES-3100B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-53-02 - Water Distribution Pump A/B |  | PS4-53-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone E | TM-00610
T-00610-0333 | PS4-60-IE-0003A-CD06 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-27 10:51 | PS4-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00610 | sridhar, muthu
T-00610-0334 | PS4-60-IE-0003A-CD08 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-27 10:58 | PS4-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00610 | sridhar, muthu
T-00610-0335 | PS4-60-IE-0003A-CD12 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-01 - Power Generation Package A | 2026-07-27 11:06 | PS4-60-01 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00610 | sridhar, muthu
T-00610-0336 | PS4-60-IE-0003B-CD06 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-27 11:12 | PS4-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00610 | sridhar, muthu
T-00610-0337 | PS4-60-IE-0003B-CD08 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-27 11:15 | PS4-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00610 | sridhar, muthu
T-00610-0338 | PS4-60-IE-0003B-CD12 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-04 - Power Generation Package B | 2026-07-27 11:22 | PS4-60-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00610 | sridhar, muthu
T-00610-0339 | PS4-60-IE-0003C-CD06 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00610
T-00610-0340 | PS4-60-IE-0003C-CD08 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00610
T-00610-0341 | PS4-60-IE-0003C-CD12 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-07 - Power Generation Package C |  | PS4-60-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00610
T-00610-0342 | PS4-60-IE-0003D-CD06 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00610
T-00610-0343 | PS4-60-IE-0003D-CD08 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00610
T-00610-0344 | PS4-60-IE-0003D-CD12 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-10 - Power Generation Package D |  | PS4-60-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00610
T-00610-0345 | PS4-60-IE-0003E-CD06 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00610
T-00610-0346 | PS4-60-IE-0003E-CD08 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00610
T-00610-0347 | PS4-60-IE-0003E-CD12 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-13 - Power Generation Package E |  | PS4-60-13 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00610
T-00610-0348 | PS4-60-IE-0003F-CD06 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00610
T-00610-0349 | PS4-60-IE-0003F-CD08 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00610
T-00610-0350 | PS4-60-IE-0003F-CD12 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-16 - Power Generation Package F |  | PS4-60-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00610
T-00610-0351 | PS4-60-IE-0003G-CD06 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone E | TM-00610
T-00610-0352 | PS4-60-IE-0003G-CD08 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone E | TM-00610
T-00610-0353 | PS4-60-IE-0003G-CD12 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-19 - Power Generation Package G |  | PS4-60-19 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone E | TM-00610
T-00610-0354 | PS4-60-IE-0004-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone B | TM-00610
T-00610-0355 | PS4-60-IE-0004-CD02 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone B | TM-00610
T-00610-0356 | PS4-60-IES-3300-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-60-IES-3300 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-24 - Cooling Water Tank & Pump | 2026-07-07 07:42 | PS4-60-24 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone E | TM-00610 | sridhar, muthu
T-00610-0357 | PS4-60-IES-3400-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-60-IES-3400 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-25 - Cooling Water Maintenance Tank & Return Pump |  | PS4-60-25 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone E | TM-00610
T-00610-0358 | PS4-61-IDH-3100A-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0359 | PS4-61-IDH-3100A-CD02 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IE-0003 TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0360 | PS4-61-IDH-3100B-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0361 | PS4-61-IDH-3100B-CD02 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IE-0002 TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0362 | PS4-61-IDH-3100C-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0363 | PS4-61-IDH-3100C-CD02 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IE-0002 TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0364 | PS4-61-IE-0003-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-82-LA-0001 TO PS4-61-IE-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00610
T-00610-0365 | PS4-61-IG-0005-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IE-0003 TO PS4-61-IG-0005 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-08 - Outdoor Normal Lighting DB - PS4-61-IG-0005 |  | PS4-62-08 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone G | TM-00610
T-00610-0366 | PS4-61-IG-0007-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IE-0003 TO PS4-61-IG-0007 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-09 - Outdoor Normal Lighting DB - PS4-61-IG-0007 | 2026-06-03 13:59 | PS4-62-09 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone G | TM-00610 | sridhar, muthu
T-00610-0367 | PS4-61-IG-0010-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IE-0003 TO PS4-61-IG-0010 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-10 - CRO Generator Electrical Building Normal L&SP DB - PS4-61-IG-0010 |  | PS4-62-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone B | TM-00610
T-00610-0368 | PS4-61-IG-0014-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IE-0003 TO PS4-61-IG-0014 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-08 - Outdoor Power Distribution Board - PS4-61-IG-0014 |  | PS4-61-08 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone G | TM-00610
T-00610-0369 | PS4-61-IG-0030-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IE-0003 TO PS4-61-IG-0030 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-11 - CRO Generator Building Normal L&SP DB - PS4-61-IG-0030 |  | PS4-62-11 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone B | TM-00610
T-00610-0370 | PS4-61-IG-0041-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IE-0002 TO PS4-61-IG-0041 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-09 - Outdoor Valves Distribution Board - PS4-61-IG-0041 |  | PS4-61-09 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone F | TM-00610
T-00610-0371 | PS4-61-IG-0042-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IE-0002 TO PS4-61-IG-0042 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-10 - Outdoor Valves Distribution Board - PS4-61-IG-0042 |  | PS4-61-10 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone F | TM-00610
T-00610-0372 | PS4-61-IJ-0001-CD04 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-07-07 07:25 | PS4-61-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00610 | sridhar, muthu
T-00610-0373 | PS4-61-IJ-0001-CD05 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0003 TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-07-07 07:26 | PS4-61-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00610 | sridhar, muthu
T-00610-0374 | PS4-61-IJ-0001-CD06 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-07-07 07:26 | PS4-61-05 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00610 | sridhar, muthu
T-00610-0375 | PS4-61-IJ-0001-CD07 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0006 TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-07-07 07:21 | PS4-61-05 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00610 | sridhar, muthu
T-00610-0376 | PS4-61-IJ-0001-CD23 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100A TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0377 | PS4-61-IJ-0001-CD24 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100B TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0378 | PS4-61-IJ-0001-CD25 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IDH-3100C TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0379 | PS4-61-IJ-0001-CD26 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002A TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-07-07 07:17 | PS4-61-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00610 | sridhar, muthu
T-00610-0380 | PS4-61-IJ-0001-CD27 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0002B TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-04 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0003) | 2026-07-07 07:18 | PS4-61-04 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00610 | sridhar, muthu
T-00610-0381 | PS4-61-IJ-0001-CD28 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007A TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-07-07 07:19 | PS4-61-05 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00610 | sridhar, muthu
T-00610-0382 | PS4-61-IJ-0001-CD29 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0007B TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-05 - 0.4kV Switchboard Power Generator Building (PS4-61-IK-0006) | 2026-07-07 07:19 | PS4-61-05 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone D | TM-00610 | sridhar, muthu
T-00610-0383 | PS4-61-IJ-0001-CD30 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0005A TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-03 - 0.4kV Switchboard Office & Facilities Building (PS4-61-IK-0005) |  | PS4-61-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone I | TM-00610
T-00610-0384 | PS4-61-IJ-0001-CD31 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IV-0005B TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-03 - 0.4kV Switchboard Office & Facilities Building (PS4-61-IK-0005) |  | PS4-61-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone I | TM-00610
T-00610-0385 | PS4-61-IK-0005-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IK-0005 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-03 - 0.4kV Switchboard Office & Facilities Building (PS4-61-IK-0005) |  | PS4-61-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone I | TM-00610
T-00610-0386 | PS4-61-IK-0005-CD02 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-61-IK-0005 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-03 - 0.4kV Switchboard Office & Facilities Building (PS4-61-IK-0005) |  | PS4-61-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone I | TM-00610
T-00610-0387 | PS4-62-IE-0002-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-08-15CB-1001 TO PS4-62-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-62-02 - Lighting Control Panel - PS4-62-IE-0002 |  | PS4-62-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone G | TM-00610
T-00610-0388 | PS4-71-HE-2200-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-HE-2200 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-12 - CFO Service Tank |  | PS4-71-12 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0389 | PS4-71-HE-2300-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-HE-2300 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-04 - CFO Storage Tank |  | PS4-71-04 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone H | TM-00610
T-00610-0390 | PS4-71-IES-3100A-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-IES-3100A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-16 - Diesel Fuel Supply Pump A/B |  | PS4-71-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone F | TM-00610
T-00610-0391 | PS4-71-IES-3100B-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-IES-3100B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-16 - Diesel Fuel Supply Pump A/B |  | PS4-71-16 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone F | TM-00610
T-00610-0392 | PS4-71-IES-3200-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-IES-3200 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-14 - Diesel Fuel Transfer and Dispensing Station |  | PS4-71-14 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone F | TM-00610
T-00610-0393 | PS4-71-IES-3300A-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-IES-3300A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B | 2026-07-07 07:44 | PS4-71-05 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00610 | sridhar, muthu
T-00610-0394 | PS4-71-IES-3300B-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-IES-3300B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-05 - CFO Transfer Pump A/B | 2026-07-07 07:44 | PS4-71-05 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00610 | sridhar, muthu
T-00610-0395 | PS4-71-IES-3400A-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-IES-3400A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B | 2026-07-07 07:45 | PS4-71-13 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00610 | sridhar, muthu
T-00610-0396 | PS4-71-IES-3400B-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-IES-3400B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-13 - CFO Service Pump A/B | 2026-07-07 07:46 | PS4-71-13 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone H | TM-00610 | sridhar, muthu
T-00610-0397 | PS4-71-IES-3500A-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-IES-3500A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B | 2026-07-07 07:24 | PS4-71-21 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00610 | sridhar, muthu
T-00610-0398 | PS4-71-IES-3500B-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-71-IES-3500B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-21 - Diesel Transfer Pump A/B | 2026-07-07 07:24 | PS4-71-21 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00610 | sridhar, muthu
T-00610-0399 | PS4-75-IES-3100A-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-75-IES-3100A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-75-03 - Corrosion Inhibitor Injection Package |  | PS4-75-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone G | TM-00610
T-00610-0400 | PS4-75-IES-3100B-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-75-IES-3100B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-75-03 - Corrosion Inhibitor Injection Package |  | PS4-75-03 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone G | TM-00610
T-00610-0401 | PS4-75-IES-3200A-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-75-IES-3200A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-75-02 - Biocide Injection Package |  | PS4-75-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone G | TM-00610
T-00610-0402 | PS4-75-IES-3200B-CD01 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IK-0001 TO PS4-75-IES-3200B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-75-02 - Biocide Injection Package |  | PS4-75-02 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone G | TM-00610
T-00610-0557 | PS4-60-IE-0004-CD14 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-27 11:35 | PS4-60-22 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00610 | sridhar, muthu
T-00610-0558 | PS4-60-IE-0004-CD15 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-30 16:47 | PS4-60-22 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone B | TM-00610 | sridhar, muthu
T-00610-0559 | PS4-60-IE-0004-CD16 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-61-IJ-0001 TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP |  | PS4-60-22 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone B | TM-00610
T-00610-0560 | PS4-61-IE-0002-CD41 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0003D TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00610
T-00610-0561 | PS4-61-IE-0002-CD42 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0003E TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00610
T-00610-0562 | PS4-61-IE-0002-CD43 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0003F TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00610
T-00610-0563 | PS4-61-IE-0002-CD44 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0003G TO PS4-61-IE-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00610
T-00610-0564 | PS4-61-IE-0003-CD02 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0003A TO PS4-61-IE-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System | 2026-07-27 12:23 | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | Closed | PS4 - Milestone C | TM-00610 | sridhar, muthu
T-00610-0565 | PS4-61-IE-0003-CD03 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0003B TO PS4-61-IE-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00610
T-00610-0566 | PS4-61-IE-0003-CD04 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0003C TO PS4-61-IE-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-07 - Electrical Control System |  | PS4-61-07 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone C | TM-00610
T-00610-0567 | PS4-61-IJ-0001-CD61 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0003A TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00610
T-00610-0568 | PS4-61-IJ-0001-CD62 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0003B TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00610
T-00610-0569 | PS4-61-IJ-0001-CD63 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0003C TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00610
T-00610-0570 | PS4-61-IJ-0001-CD64 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0003D TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00610
T-00610-0571 | PS4-61-IJ-0001-CD65 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0003E TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00610
T-00610-0572 | PS4-61-IJ-0001-CD66 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0003F TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00610