T-00610-0573 | PS4-61-IJ-0001-CD67 |  |  |  |  | CPX10b - Multicore Electrical Control Cable (One end by HU CTR) | PCOM - Precommissioning | E | Conformity Check | E - Electrical | Cable FROM PS4-60-IE-0003G TO PS4-61-IJ-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-61-01 - 33kV Switchboard EITS Building (PS4-61-IJ-0001) |  | PS4-61-01 |  |  | Multicore Electrical Control Cable | E | To be completed | PS4 - Milestone D | TM-00610
T-00614-1253 | PS4-01-BI-0001-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0009 TO PS4-01-BI-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-05 - Foam Skid |  | PS4-01-05 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-1254 | PS4-01-BI-0002-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0009 TO PS4-01-BI-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1255 | PS4-01-BI-0003-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0010 TO PS4-01-BI-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1256 | PS4-01-BI-0004-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0012 TO PS4-01-BI-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1257 | PS4-01-BI-0005-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0012 TO PS4-01-BI-0005 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-05 - Foam Skid |  | PS4-01-05 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-1258 | PS4-01-BI-0006-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0007 TO PS4-01-BI-0006 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-05 - Foam Skid |  | PS4-01-05 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-1259 | PS4-01-BI-1117-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0002 TO PS4-01-BI-1117 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 07:53 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1260 | PS4-01-BI-1118-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0001 TO PS4-01-BI-1118 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 07:54 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1261 | PS4-01-BI-1501-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0007 TO PS4-01-BI-1501 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-07 - Fire Water Ring Main & Distribution |  | PS4-01-07 |  |  |  | I | To be completed | PS4 - Milestone C | TM-00614
T-00614-1262 | PS4-01-BI-1515-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0008 TO PS4-01-BI-1515 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:27 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1263 | PS4-01-BI-1520-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0008 TO PS4-01-BI-1520 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1264 | PS4-01-BI-1571-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0008 TO PS4-01-BI-1571 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-08 - PS4 Deluge Valve Skid (PS4-01-UK-6100) |  | PS4-01-08 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-1265 | PS4-01-BI-2110-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-01-BI-2110 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 07:55 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1266 | PS4-01-BI-2520-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0012 TO PS4-01-BI-2520 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1267 | PS4-01-BI-2571A-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0012 TO PS4-01-BI-2571A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-08 - PS4 Deluge Valve Skid (PS4-01-UK-6100) |  | PS4-01-08 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-1268 | PS4-01-BI-2571B-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0012 TO PS4-01-BI-2571B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-08 - PS4 Deluge Valve Skid (PS4-01-UK-6100) |  | PS4-01-08 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-1269 | PS4-01-IE-0002A-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0009 TO PS4-01-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  |  | I | To be completed | PS4 - Milestone C | TM-00614
T-00614-1270 | PS4-01-IE-0002A-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0013 TO PS4-01-IE-0002A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  |  | I | To be completed | PS4 - Milestone C | TM-00614
T-00614-1271 | PS4-01-IE-0002B-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0009 TO PS4-01-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  |  | I | To be completed | PS4 - Milestone C | TM-00614
T-00614-1272 | PS4-01-IE-0002B-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0013 TO PS4-01-IE-0002B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-01 - Fire Water Jockey Pump A/B |  | PS4-01-01 |  |  |  | I | To be completed | PS4 - Milestone C | TM-00614
T-00614-1273 | PS4-01-IE-0009A-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0009 TO PS4-01-IE-0009A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  |  | I | To be completed | PS4 - Milestone C | TM-00614
T-00614-1274 | PS4-01-IE-0009A-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0012 TO PS4-01-IE-0009A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-02 - Fire Water Pump A |  | PS4-01-02 |  |  |  | I | To be completed | PS4 - Milestone C | TM-00614
T-00614-1275 | PS4-01-IE-0009B-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0009 TO PS4-01-IE-0009B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  |  | I | To be completed | PS4 - Milestone C | TM-00614
T-00614-1276 | PS4-01-IE-0009B-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0012 TO PS4-01-IE-0009B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-03 - Fire Water Pump B |  | PS4-01-03 |  |  |  | I | To be completed | PS4 - Milestone C | TM-00614
T-00614-1277 | PS4-01-LB-0004-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0011 TO PS4-01-LB-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1278 | PS4-01-LB-0004-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0012 TO PS4-01-LB-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1279 | PS4-01-LB-0004-CC03 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0010 TO PS4-01-LB-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-11 - Inergen for Power Gen Buidling |  | PS4-01-11 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1280 | PS4-01-LIT-4201-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0007 TO PS4-01-LIT-4201 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-10 - Water Mist Package |  | PS4-01-10 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1281 | PS4-01-PIT-0014-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0007 TO PS4-01-PIT-0014 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-07 - Fire Water Ring Main & Distribution |  | PS4-01-07 |  |  |  | I | To be completed | PS4 - Milestone C | TM-00614
T-00614-1282 | PS4-01-PIT-0015-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0007 TO PS4-01-PIT-0015 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-07 - Fire Water Ring Main & Distribution |  | PS4-01-07 |  |  |  | I | To be completed | PS4 - Milestone C | TM-00614
T-00614-1283 | PS4-01-PIT-0016-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0008 TO PS4-01-PIT-0016 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-07 - Fire Water Ring Main & Distribution |  | PS4-01-07 |  |  |  | I | To be completed | PS4 - Milestone C | TM-00614
T-00614-1284 | PS4-01-PIT-0017-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0008 TO PS4-01-PIT-0017 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-01-07 - Fire Water Ring Main & Distribution |  | PS4-01-07 |  |  |  | I | To be completed | PS4 - Milestone C | TM-00614
T-00614-1285 | PS4-03-BI-1502-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0007 TO PS4-03-BI-1502 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-1286 | PS4-03-BI-1503-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0008 TO PS4-03-BI-1503 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-1287 | PS4-03-BI-1506-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0008 TO PS4-03-BI-1506 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1288 | PS4-03-BI-1507-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0007 TO PS4-03-BI-1507 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1289 | PS4-03-BI-1508-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0007 TO PS4-03-BI-1508 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1290 | PS4-03-BI-1509-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0007 TO PS4-03-BI-1509 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1291 | PS4-03-BI-1510-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0007 TO PS4-03-BI-1510 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1292 | PS4-03-BI-1511-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0007 TO PS4-03-BI-1511 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-07 - FZ-07 - Pretreatment Area |  | PS4-03-07 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1293 | PS4-03-BI-1512-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0008 TO PS4-03-BI-1512 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 |  | PS4-03-09 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1294 | PS4-03-BI-1513-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0008 TO PS4-03-BI-1513 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1295 | PS4-03-BI-1514-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0008 TO PS4-03-BI-1514 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1296 | PS4-03-BI-1516-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0008 TO PS4-03-BI-1516 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 |  | PS4-03-12 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1297 | PS4-03-BI-2501-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0009 TO PS4-03-BI-2501 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1298 | PS4-03-BI-2502-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0009 TO PS4-03-BI-2502 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-06 - FZ-06 - Transformer Area |  | PS4-03-06 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1299 | PS4-03-BI-2503-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0009 TO PS4-03-BI-2503 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:28 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1300 | PS4-03-BI-2504-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0009 TO PS4-03-BI-2504 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1301 | PS4-03-BI-2505-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0009 TO PS4-03-BI-2505 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1302 | PS4-03-BI-2506-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0010 TO PS4-03-BI-2506 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 07:56 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1303 | PS4-03-BI-2507-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0010 TO PS4-03-BI-2507 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 |  | PS4-03-10 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1304 | PS4-03-BI-2508-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0010 TO PS4-03-BI-2508 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 |  | PS4-03-11 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1305 | PS4-03-BI-2509-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0010 TO PS4-03-BI-2509 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-29 09:50 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1306 | PS4-03-BI-2510-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0010 TO PS4-03-BI-2510 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-03 - FZ-03 - Buildings Area |  | PS4-03-03 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1307 | PS4-03-BI-2511-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0009 TO PS4-03-BI-2511 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1308 | PS4-03-BI-2512-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0010 TO PS4-03-BI-2512 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas |  | PS4-03-04 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-1309 | PS4-03-BI-2514-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0009 TO PS4-03-BI-2514 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 07:57 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1310 | PS4-03-BI-2515-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0009 TO PS4-03-BI-2515 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 07:58 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1311 | PS4-03-HS-7002-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0001 TO PS4-03-HS-7002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-03 - FZ-03 - Buildings Area |  | PS4-03-03 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1312 | PS4-03-MTX-0001-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0001 TO PS4-03-MTX-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-04-02 - Office Building SIS/FGS System |  | PS4-04-02 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1313 | PS4-03-MTX-0001-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0001 TO PS4-03-MTX-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-04-02 - Office Building SIS/FGS System |  | PS4-04-02 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1314 | PS4-03-MTX-0001-CC03 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0004 TO PS4-03-MTX-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-04-02 - Office Building SIS/FGS System |  | PS4-04-02 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1315 | PS4-03-MTX-0001-CC04 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0005 TO PS4-03-MTX-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-04-02 - Office Building SIS/FGS System |  | PS4-04-02 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1316 | PS4-03-MTX-0001-CC05 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0010 TO PS4-03-MTX-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-04-02 - Office Building SIS/FGS System |  | PS4-04-02 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1317 | PS4-03-MTX-0001-CC06 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0011 TO PS4-03-MTX-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-04-02 - Office Building SIS/FGS System |  | PS4-04-02 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1318 | PS4-03-MTX-0001-CC07 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0011 TO PS4-03-MTX-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-04-02 - Office Building SIS/FGS System |  | PS4-04-02 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1319 | PS4-03-MTX-0001-CC08 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0012 TO PS4-03-MTX-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-04-02 - Office Building SIS/FGS System |  | PS4-04-02 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1320 | PS4-03-NMR-0801-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0009 TO PS4-03-NMR-0801 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1321 | PS4-03-NMR-0802-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0009 TO PS4-03-NMR-0802 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1322 | PS4-03-NMR-0803-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0009 TO PS4-03-NMR-0803 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1323 | PS4-03-NMR-0804-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0009 TO PS4-03-NMR-0804 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1324 | PS4-03-RMAC-0120-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0010 TO PS4-03-RMAC-0120 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-01 - FZ-01 - Process Area |  | PS4-03-01 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1325 | PS4-03-RMAC-0824-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0009 TO PS4-03-RMAC-0824 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-08 - FZ-08 - Utilities - Power Generation Area - External |  | PS4-03-08 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1326 | PS4-03-SEA-0002-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0010 TO PS4-03-SEA-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-22 - FZ-G1 Guard House |  | PS4-03-22 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1327 | PS4-03-SEA-0002-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-03-SEA-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-22 - FZ-G1 Guard House |  | PS4-03-22 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1328 | PS4-03-SEA-0003-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0010 TO PS4-03-SEA-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1329 | PS4-03-SEA-0003-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-03-SEA-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1330 | PS4-03-SEA-0005-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0010 TO PS4-03-SEA-0005 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1331 | PS4-03-SEA-0005-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-03-SEA-0005 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-24 - FZ-B1 to B9 - Office and Facilities Building |  | PS4-03-24 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1332 | PS4-03-SEA-0006-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0010 TO PS4-03-SEA-0006 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1333 | PS4-03-SEA-0006-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-03-SEA-0006 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-25 - FZ-W1 to W6 - Workshop & Warehouse |  | PS4-03-25 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1334 | PS4-05-BI-0002-CC11 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0009 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | 2026-07-30 14:55 | PS4-03-20 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone C | TM-00614 | sridhar, muthu
T-00614-1335 | PS4-05-BI-0002-CC12 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0011 TO PS4-05-BI-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | 2026-07-30 14:59 | PS4-03-20 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone C | TM-00614 | sridhar, muthu
T-00614-1336 | PS4-05-IE-8100-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) | 2026-07-30 14:52 | PS4-05-02 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone C | TM-00614 | sridhar, muthu
T-00614-1337 | PS4-05-IE-8100-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0003 TO PS4-05-IE-8100 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-05-02 - Emergency Diesel Generator Package (UCP) |  | PS4-05-02 |  |  |  | I | To be completed | PS4 - Milestone C | TM-00614
T-00614-1338 | PS4-06-GU-0003A-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0003 TO PS4-06-GU-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building |  | PS4-06-02 |  |  |  | I | To be completed | PS4 - Milestone B | TM-00614
T-00614-1339 | PS4-06-GU-0003B-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0003 TO PS4-06-GU-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-06-02 - AC UPS - Power Generator Building |  | PS4-06-02 |  |  |  | I | To be completed | PS4 - Milestone B | TM-00614
T-00614-1340 | PS4-09-BI-2501-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0010 TO PS4-09-BI-2501 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-04 - HVAC for Workshop & Warehouse |  | PS4-09-04 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1341 | PS4-09-BI-2502-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0011 TO PS4-09-BI-2502 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-01 - HVAC for Office and Facilities building |  | PS4-09-01 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1342 | PS4-09-BI-2503-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0011 TO PS4-09-BI-2503 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1343 | PS4-09-LB-0006-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0013 TO PS4-09-LB-0006 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-01 - HVAC for Office and Facilities building |  | PS4-09-01 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1344 | PS4-09-LB-0006-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0011 TO PS4-09-LB-0006 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-01 - HVAC for Office and Facilities building |  | PS4-09-01 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1345 | PS4-09-LB-0006-CC03 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0003 TO PS4-09-LB-0006 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-01 - HVAC for Office and Facilities building |  | PS4-09-01 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1346 | PS4-09-LB-0006-CC04 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0011 TO PS4-09-LB-0006 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-01 - HVAC for Office and Facilities building |  | PS4-09-01 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1347 | PS4-09-LB-0007-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0013 TO PS4-09-LB-0007 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-04 - HVAC for Workshop & Warehouse |  | PS4-09-04 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1348 | PS4-09-LB-0007-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0011 TO PS4-09-LB-0007 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-04 - HVAC for Workshop & Warehouse |  | PS4-09-04 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1349 | PS4-09-LB-0007-CC03 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0005 TO PS4-09-LB-0007 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-04 - HVAC for Workshop & Warehouse |  | PS4-09-04 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1350 | PS4-09-LB-0007-CC04 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0011 TO PS4-09-LB-0007 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-04 - HVAC for Workshop & Warehouse |  | PS4-09-04 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1351 | PS4-09-LB-0008-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0013 TO PS4-09-LB-0008 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1352 | PS4-09-LB-0008-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0011 TO PS4-09-LB-0008 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1353 | PS4-09-LB-0008-CC03 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0005 TO PS4-09-LB-0008 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1354 | PS4-09-LB-0008-CC04 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0011 TO PS4-09-LB-0008 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1355 | PS4-09-LB-0008-CC05 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0012 TO PS4-09-LB-0008 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1356 | PS4-09-LB-0008-CC06 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0012 TO PS4-09-LB-0008 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1357 | PS4-09-LB-0008-CC07 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0012 TO PS4-09-LB-0008 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1358 | PS4-09-LB-0008-CC08 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0011 TO PS4-09-LB-0008 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-03 - HVAC for Generator Building |  | PS4-09-03 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1359 | PS4-25-BI-1101-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0001 TO PS4-25-BI-1101 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 07:59 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1360 | PS4-25-BI-1102-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0002 TO PS4-25-BI-1102 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 07:59 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1361 | PS4-25-BI-1103-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0001 TO PS4-25-BI-1103 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:00 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1362 | PS4-25-BI-1104-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0002 TO PS4-25-BI-1104 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:01 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1363 | PS4-25-BI-1115-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0002 TO PS4-25-BI-1115 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:02 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1364 | PS4-25-BI-1174A-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0001 TO PS4-25-BI-1174A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1365 | PS4-25-BI-1174B-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0001 TO PS4-25-BI-1174B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1366 | PS4-25-BI-1174C-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0001 TO PS4-25-BI-1174C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1367 | PS4-25-BI-1201-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0001 TO PS4-25-BI-1201 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:02 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1368 | PS4-25-BI-1274A-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0002 TO PS4-25-BI-1274A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1369 | PS4-25-BI-1274B-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0002 TO PS4-25-BI-1274B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1370 | PS4-25-BI-1274C-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0001 TO PS4-25-BI-1274C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1371 | PS4-25-BI-1301-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0002 TO PS4-25-BI-1301 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:03 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1372 | PS4-25-BI-1302-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0002 TO PS4-25-BI-1302 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:04 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1373 | PS4-25-BI-1310-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0002 TO PS4-25-BI-1310 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:04 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1374 | PS4-25-BI-1801A-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-IE-0001 TO PS4-25-BI-1801A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1375 | PS4-25-BI-1801B-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-IE-0001 TO PS4-25-BI-1801B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1376 | PS4-25-BI-1801C-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-IE-0001 TO PS4-25-BI-1801C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1377 | PS4-25-BI-1802A-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-IE-0001 TO PS4-25-BI-1802A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1378 | PS4-25-BI-1802B-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-IE-0001 TO PS4-25-BI-1802B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1379 | PS4-25-BI-1802C-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-IE-0001 TO PS4-25-BI-1802C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1380 | PS4-25-BI-1803A-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-IE-0001 TO PS4-25-BI-1803A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1381 | PS4-25-BI-1803A-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-IE-0001 TO PS4-25-BI-1803A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1382 | PS4-25-BI-1803B-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-IE-0001 TO PS4-25-BI-1803B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1383 | PS4-25-BI-1803B-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-IE-0001 TO PS4-25-BI-1803B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1384 | PS4-25-BI-1803C-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-IE-0001 TO PS4-25-BI-1803C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1385 | PS4-25-BI-1803C-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-25-IE-0001 TO PS4-25-BI-1803C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1386 | PS4-25-BI-2101-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0003 TO PS4-25-BI-2101 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1387 | PS4-25-BI-2102-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0003 TO PS4-25-BI-2102 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1388 | PS4-25-BI-2103-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-25-BI-2103 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-29 09:43 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1389 | PS4-25-BI-2104-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0003 TO PS4-25-BI-2104 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-29 09:47 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1390 | PS4-25-BI-2105-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-25-BI-2105 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:05 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1391 | PS4-25-BI-2106-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-25-BI-2106 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:28 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1392 | PS4-25-BI-2108-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-25-BI-2108 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:06 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1393 | PS4-25-BI-2109-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-25-BI-2109 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:07 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1394 | PS4-25-BI-2201-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0001 TO PS4-25-BI-2201 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-29 09:05 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1395 | PS4-25-BI-2203-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0001 TO PS4-25-BI-2203 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-29 09:09 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1396 | PS4-25-BI-2205-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0001 TO PS4-25-BI-2205 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-01 - Export Pipeline Pig Receiver |  | PS4-25-01 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1397 | PS4-25-BI-2301-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0003 TO PS4-25-BI-2301 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:08 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1398 | PS4-25-BI-2302-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0004 TO PS4-25-BI-2302 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-29 09:34 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1399 | PS4-25-BI-2305-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0003 TO PS4-25-BI-2305 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:29 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1400 | PS4-25-BI-2308-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0005 TO PS4-25-BI-2308 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:30 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1401 | PS4-25-BI-2309-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0005 TO PS4-25-BI-2309 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:09 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1402 | PS4-25-BI-2312-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0003 TO PS4-25-BI-2312 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:09 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1403 | PS4-25-BI-2315-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0003 TO PS4-25-BI-2315 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:10 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1404 | PS4-25-BI-2316-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0006 TO PS4-25-BI-2316 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:31 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1405 | PS4-25-MXS-3101AA-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0005 TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1406 | PS4-25-MXS-3101AB-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LA-0001 TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1407 | PS4-25-MXS-3101BA-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0005 TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1408 | PS4-25-MXS-3101BB-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LA-0001 TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1409 | PS4-25-MXS-3101CA-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0006 TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1410 | PS4-25-MXS-3101CB-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LA-0001 TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1411 | PS4-25-PIT-0052-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LA-0001 TO PS4-25-SDV-0052 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1412 | PS4-25-PIT-0071A-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LA-0001 TO PS4-25-PIT-0071A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1413 | PS4-25-PIT-0071B-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LA-0001 TO PS4-25-PIT-0071B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1414 | PS4-25-PIT-0071C-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LA-0001 TO PS4-25-PIT-0071C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1415 | PS4-25-SDV-0052-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LA-0001 TO PS4-25-SDV-0052 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1416 | PS4-25-SDV-0052-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LA-0001 TO PS4-25-SDV-0052 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1417 | PS4-25-SHSR-0052-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0004 TO PS4-25-SDV-0052 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1418 | PS4-25-SXS-0052-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LA-0001 TO PS4-25-SDV-0052 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1419 | PS4-25-SY-0052A-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-01-LA-0001 TO PS4-25-SDV-0052 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-07 - Export Pipeline Pig Launcher |  | PS4-25-07 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1420 | PS4-28-BI-1105-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0001 TO PS4-28-BI-1105 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:11 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1421 | PS4-28-BI-1106-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0001 TO PS4-28-BI-1106 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-06 - Relief Drum and Pump |  | PS4-28-06 |  |  |  | I | To be completed | PS4 - Milestone G | TM-00614
T-00614-1422 | PS4-28-BI-1114-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0001 TO PS4-28-BI-1114 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-04 - Closed Drain Drum and Pump 02 |  | PS4-28-04 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1423 | PS4-28-BI-1303-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0001 TO PS4-28-BI-1303 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:12 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1424 | PS4-28-BI-1307-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0001 TO PS4-28-BI-1307 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-29 09:30 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1425 | PS4-28-BI-2304-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0004 TO PS4-28-BI-2304 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-17 - Reinjection Pump |  | PS4-28-17 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1426 | PS4-28-HXA-1101-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-28-HXA-1101 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-03 - Closed Drain Drum and Pump 01 |  | PS4-28-03 |  |  |  | I | To be completed | PS4 - Milestone G | TM-00614
T-00614-1427 | PS4-28-LB-8200-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-28-LB-8200 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-11 - Open Drain Interceptor |  | PS4-28-11 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1428 | PS4-28-LB-8200-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0005 TO PS4-28-LB-8200 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-11 - Open Drain Interceptor |  | PS4-28-11 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1429 | PS4-50-BI-1107-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0002 TO PS4-50-BI-1107 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:32 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1430 | PS4-50-IE-0001-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0008 TO PS4-50-IE-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-50-01 - Water Well Submersible Pumps (3100) |  | PS4-50-01 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1431 | PS4-50-IE-0001-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0007 TO PS4-50-IE-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-50-01 - Water Well Submersible Pumps (3100) |  | PS4-50-01 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1432 | PS4-50-LIT-0001-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0001 TO PS4-50-LIT-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-50-01 - Water Well Submersible Pumps (3100) |  | PS4-50-01 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1433 | PS4-53-BI-1108-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0002 TO PS4-53-BI-1108 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:13 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1434 | PS4-53-BI-1304-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0002 TO PS4-53-BI-1304 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-53-01 - Utility Water / Storage Tank |  | PS4-53-01 |  |  |  | I | To be completed | PS4 - Milestone C | TM-00614
T-00614-1435 | PS4-53-LA-0001-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0003 TO PS4-53-LA-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-53-04 - Water Treatment Purification Package |  | PS4-53-04 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-1436 | PS4-53-LA-0001-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0002 TO PS4-53-LA-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-53-04 - Water Treatment Purification Package |  | PS4-53-04 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-1437 | PS4-60-IE-0003A-CC21 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-16 14:42 | PS4-60-02 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone B | TM-00614 | sridhar, muthu
T-00614-1438 | PS4-60-IE-0003A-CC22 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0005 TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-16 14:44 | PS4-60-02 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone B | TM-00614 | sridhar, muthu
T-00614-1439 | PS4-60-IE-0003A-CC23 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0003 TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-16 14:46 | PS4-60-02 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone B | TM-00614 | sridhar, muthu
T-00614-1440 | PS4-60-IE-0003A-CC24 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0005 TO PS4-60-IE-0003A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-02 - Power Gen Package A (UCP) | 2026-07-16 14:51 | PS4-60-02 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone B | TM-00614 | sridhar, muthu
T-00614-1441 | PS4-60-IE-0003B-CC21 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-22 07:28 | PS4-60-05 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone B | TM-00614 | sridhar, muthu
T-00614-1442 | PS4-60-IE-0003B-CC22 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0005 TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-22 07:31 | PS4-60-05 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone B | TM-00614 | sridhar, muthu
T-00614-1443 | PS4-60-IE-0003B-CC23 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0003 TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-22 07:33 | PS4-60-05 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone B | TM-00614 | sridhar, muthu
T-00614-1444 | PS4-60-IE-0003B-CC24 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0005 TO PS4-60-IE-0003B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-05 - Power Gen Package B (UCP) | 2026-07-22 07:40 | PS4-60-05 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone B | TM-00614 | sridhar, muthu
T-00614-1445 | PS4-60-IE-0003C-CC21 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1446 | PS4-60-IE-0003C-CC22 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0005 TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1447 | PS4-60-IE-0003C-CC23 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0003 TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1448 | PS4-60-IE-0003C-CC24 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0006 TO PS4-60-IE-0003C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-08 - Power Gen Package C (UCP) |  | PS4-60-08 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1449 | PS4-60-IE-0003D-CC21 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1450 | PS4-60-IE-0003D-CC22 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0005 TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1451 | PS4-60-IE-0003D-CC23 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0003 TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1452 | PS4-60-IE-0003D-CC24 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0005 TO PS4-60-IE-0003D | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-11 - Power Gen Package D (UCP) |  | PS4-60-11 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1453 | PS4-60-IE-0003E-CC21 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1454 | PS4-60-IE-0003E-CC22 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0005 TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1455 | PS4-60-IE-0003E-CC23 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0003 TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1456 | PS4-60-IE-0003E-CC24 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0005 TO PS4-60-IE-0003E | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-14 - Power Gen Package E (UCP) |  | PS4-60-14 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1457 | PS4-60-IE-0003F-CC21 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1458 | PS4-60-IE-0003F-CC22 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0005 TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1459 | PS4-60-IE-0003F-CC23 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0004 TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1460 | PS4-60-IE-0003F-CC24 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0006 TO PS4-60-IE-0003F | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-17 - Power Gen Package F (UCP) |  | PS4-60-17 |  |  |  | I | To be completed | PS4 - Milestone D | TM-00614
T-00614-1461 | PS4-60-IE-0003G-CC21 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1462 | PS4-60-IE-0003G-CC22 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0005 TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1463 | PS4-60-IE-0003G-CC23 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0004 TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1464 | PS4-60-IE-0003G-CC24 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0006 TO PS4-60-IE-0003G | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-20 - Power Gen Package G (UCP) |  | PS4-60-20 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1465 | PS4-60-IE-0004-CC08 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-22 07:21 | PS4-60-22 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone B | TM-00614 | sridhar, muthu
T-00614-1466 | PS4-60-IE-0004-CC11 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0004 TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-22 07:23 | PS4-60-22 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone B | TM-00614 | sridhar, muthu
T-00614-1467 | PS4-60-IE-0004-CC12 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0005 TO PS4-60-IE-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-60-22 - Power Gen Master UCP | 2026-07-22 07:26 | PS4-60-22 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone B | TM-00614 | sridhar, muthu
T-00614-1468 | PS4-60-SEA-0001-CC18 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0009 TO PS4-60-SEA-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-03-14 - FZ-14 - Power Generation Building - Switchgear Room |  | PS4-03-14 |  |  |  | I | To be completed | PS4 - Milestone E | TM-00614
T-00614-1469 | PS4-61-IDH-3100A-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0001 TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1470 | PS4-61-IDH-3100A-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1471 | PS4-61-IDH-3100A-CC03 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-61-IDH-3100A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1472 | PS4-61-IDH-3100B-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0001 TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1473 | PS4-61-IDH-3100B-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1474 | PS4-61-IDH-3100B-CC03 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-61-IDH-3100B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1475 | PS4-61-IDH-3100C-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0002 TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1476 | PS4-61-IDH-3100C-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1477 | PS4-61-IDH-3100C-CC03 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-61-IDH-3100C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1478 | PS4-71-BI-0001-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-26-LA-0001 TO PS4-71-BI-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-02 - CFO Allocation Metering Package |  | PS4-71-02 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1479 | PS4-71-BI-0021-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-26-LA-0001 TO PS4-71-BI-0021 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-02 - CFO Allocation Metering Package |  | PS4-71-02 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1480 | PS4-71-BI-0021-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-26-LA-0001 TO PS4-71-BI-0021 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-02 - CFO Allocation Metering Package |  | PS4-71-02 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1481 | PS4-71-BI-1109-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0002 TO PS4-71-BI-1109 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:13 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1482 | PS4-71-BI-1110-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0001 TO PS4-71-BI-1110 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:33 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1483 | PS4-71-BI-1111-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0002 TO PS4-71-BI-1111 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:14 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1484 | PS4-71-BI-1112-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0002 TO PS4-71-BI-1112 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-17 - Diesel Fuel Distribution Header |  | PS4-71-17 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-1485 | PS4-71-BI-1113-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0002 TO PS4-71-BI-1113 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:15 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1486 | PS4-71-BI-1116-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0002 TO PS4-71-BI-1116 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:33 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1487 | PS4-71-BI-1117-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0001 TO PS4-71-BI-1117 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:34 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1488 | PS4-71-BI-1305-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0002 TO PS4-71-BI-1305 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:17 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1489 | PS4-71-BI-1306-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0002 TO PS4-71-BI-1306 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-29 09:17 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1490 | PS4-71-BI-1308-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0001 TO PS4-71-BI-1308 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank |  | PS4-71-15 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-1491 | PS4-71-BI-2101-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-71-BI-2101 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-29 09:39 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1492 | PS4-71-BI-2107-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-71-BI-2107 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:35 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1493 | PS4-71-BI-2113-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0003 TO PS4-71-BI-2113 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-29 08:59 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1494 | PS4-71-BI-2114-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-71-BI-2114 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:36 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1495 | PS4-71-BI-2115-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-71-BI-2115 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:37 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1496 | PS4-71-BI-2116-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0003 TO PS4-71-BI-2116 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:18 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1497 | PS4-71-BI-2118-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0005 TO PS4-71-BI-2118 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:19 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1498 | PS4-71-BI-2119-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0005 TO PS4-71-BI-2119 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:21 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1499 | PS4-71-BI-2120-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0005 TO PS4-71-BI-2120 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-22 07:18 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1500 | PS4-71-BI-2121-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0005 TO PS4-71-BI-2121 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:22 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1501 | PS4-71-BI-2122-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-71-BI-2122 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:23 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1502 | PS4-71-BI-2123-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-71-BI-2123 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:23 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1503 | PS4-71-BI-2124-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-71-BI-2124 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:25 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1504 | PS4-71-BI-2125-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-71-BI-2125 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:26 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1505 | PS4-71-BI-2306-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0004 TO PS4-71-BI-2306 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-29 09:26 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1506 | PS4-71-BI-2307-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0004 TO PS4-71-BI-2307 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank |  | PS4-71-15 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-1507 | PS4-71-BI-2310-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0006 TO PS4-71-BI-2310 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-07-09 08:37 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1508 | PS4-71-BI-2313-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0004 TO PS4-71-BI-2313 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank |  | PS4-71-15 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-1509 | PS4-71-BI-2314-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0004 TO PS4-71-BI-2314 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-91-01 - Multicore cables & JB | 2026-05-29 10:00 | PS4-91-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | I | Closed | PS4 - Milestone A | TM-00614 | sridhar, muthu
T-00614-1510 | PS4-71-BI-2317-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0006 TO PS4-71-BI-2317 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-15 - Diesel Fuel Storage Tank |  | PS4-71-15 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-1511 | PS4-71-IN-0001-CC08 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-1512 | PS4-71-IN-0001-CC09 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0004 TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-1513 | PS4-71-IN-0001-CC10 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0006 TO PS4-71-IN-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-19 - Diesel Separator Module (UCP) |  | PS4-71-19 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-1514 | PS4-71-IN-0002-CC05 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-09 - CFO Pre-Pressure Module (UCP) |  | PS4-71-09 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1515 | PS4-71-IN-0002-CC06 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0004 TO PS4-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-09 - CFO Pre-Pressure Module (UCP) |  | PS4-71-09 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1516 | PS4-71-IN-0002-CC07 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0006 TO PS4-71-IN-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-09 - CFO Pre-Pressure Module (UCP) |  | PS4-71-09 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1517 | PS4-71-IN-0003-CC05 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS4-71-23 |  |  |  | I | To be completed | PS4 - Milestone B | TM-00614
T-00614-1518 | PS4-71-IN-0003-CC06 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0004 TO PS4-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS4-71-23 |  |  |  | I | To be completed | PS4 - Milestone B | TM-00614
T-00614-1519 | PS4-71-IN-0003-CC07 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0006 TO PS4-71-IN-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-23 - Diesel Fuel Pre Pressure Module (UCP) |  | PS4-71-23 |  |  |  | I | To be completed | PS4 - Milestone B | TM-00614
T-00614-1520 | PS4-71-IN-0004A-CC08 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1521 | PS4-71-IN-0004A-CC09 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0003 TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1522 | PS4-71-IN-0004A-CC12 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0005 TO PS4-71-IN-0004A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1523 | PS4-71-IN-0004B-CC08 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0004 TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1524 | PS4-71-IN-0004B-CC09 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0003 TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1525 | PS4-71-IN-0004B-CC12 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0005 TO PS4-71-IN-0004B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-07 - Crude Fuel Separation Module (UCP) |  | PS4-71-07 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1526 | PS4-71-TIT-2403A-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IE-0001 TO PS4-71-TIT-2403A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1527 | PS4-71-TIT-2403B-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-71-IE-0002 TO PS4-71-TIT-2403B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-71-01 - CFO Storage Tank Feed Heater |  | PS4-71-01 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1528 | PS4-74-LB-5101-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-74-LB-5101 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-74-02 - N2 Generation Skid (UCP) |  | PS4-74-02 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-1529 | PS4-74-LB-5101-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0006 TO PS4-74-LB-5101 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-74-02 - N2 Generation Skid (UCP) |  | PS4-74-02 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-1530 | PS4-75-BI-1177-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0002 TO PS4-75-BI-1177 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-75-02 - Biocide Injection Package |  | PS4-75-02 |  |  |  | I | To be completed | PS4 - Milestone G | TM-00614
T-00614-1531 | PS4-75-BI-1178-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0002 TO PS4-75-BI-1178 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-75-03 - Corrosion Inhibitor Injection Package |  | PS4-75-03 |  |  |  | I | To be completed | PS4 - Milestone G | TM-00614
T-00614-1532 | PS4-75-BI-1371-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0002 TO PS4-75-BI-1371 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-75-02 - Biocide Injection Package |  | PS4-75-02 |  |  |  | I | To be completed | PS4 - Milestone G | TM-00614
T-00614-1533 | PS4-75-BI-1372-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0002 TO PS4-75-BI-1372 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-75-03 - Corrosion Inhibitor Injection Package |  | PS4-75-03 |  |  |  | I | To be completed | PS4 - Milestone G | TM-00614
T-00614-1534 | PS4-75-BI-0001-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0001 TO PS4-75-BI-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-75-01 - DRA Injection Package |  | PS4-75-01 |  |  |  | I | To be completed | PS4 - Milestone G | TM-00614
T-00614-1535 | PS4-75-BI-0002-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0005 TO PS4-75-BI-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-75-01 - DRA Injection Package |  | PS4-75-01 |  |  |  | I | To be completed | PS4 - Milestone G | TM-00614
T-00614-1536 | PS4-75-BI-0002-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS5-04-PMC-0006 TO PS4-75-BI-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-75-01 - DRA Injection Package |  | PS4-75-01 |  |  |  | I | To be completed | PS4 - Milestone G | TM-00614
T-00614-1537 | PS4-75-BI-0002-CC03 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0006 TO PS4-75-BI-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-75-01 - DRA Injection Package |  | PS4-75-01 |  |  |  | I | To be completed | PS4 - Milestone G | TM-00614
T-00614-1538 | PS4-75-MOV-0001-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-75-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-07 - Open Drains (OD2) |  | PS4-28-07 |  |  |  | I | To be completed | PS4 - Milestone G | TM-00614
T-00614-1539 | PS4-75-MOV-0001-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0003 TO PS4-75-MOV-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-28-07 - Open Drains (OD2) |  | PS4-28-07 |  |  |  | I | To be completed | PS4 - Milestone G | TM-00614
T-00614-1540 | PS4-79-IG-0001-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0003 TO PS4-79-IG-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS4-79-IG-0001) |  | PS4-79-01 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1541 | PS4-79-IG-0002-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0003 TO PS4-79-IG-0002 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS4-79-IG-0002) |  | PS4-79-02 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1542 | PS4-79-IG-0003-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0003 TO PS4-79-IG-0003 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS4-79-IG-0003) |  | PS4-79-03 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1543 | PS4-79-IG-0004-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0003 TO PS4-79-IG-0004 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS4-79-IG-0004) |  | PS4-79-04 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1544 | PS4-79-IG-0005-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0003 TO PS4-79-IG-0005 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS4-79-IG-0005) |  | PS4-79-05 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1545 | PS4-79-IG-0006-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0003 TO PS4-79-IG-0006 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS4-79-IG-0006) |  | PS4-79-06 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1546 | PS4-79-IG-0007-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0005 TO PS4-79-IG-0007 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS4-79-IG-0007) |  | PS4-79-07 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1547 | PS4-79-IG-0008-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0005 TO PS4-79-IG-0008 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS4-79-IG-0008) |  | PS4-79-08 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1548 | PS4-79-IG-0009-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0005 TO PS4-79-IG-0009 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS4-79-IG-0009) |  | PS4-79-09 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1549 | PS4-79-IG-0010-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0005 TO PS4-79-IG-0010 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS4-79-IG-0010) |  | PS4-79-10 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1550 | PS4-79-IG-0011-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0005 TO PS4-79-IG-0011 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS4-79-IG-0011) |  | PS4-79-11 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1551 | PS4-79-IG-0012-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0005 TO PS4-79-IG-0012 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS4-79-IG-0012) |  | PS4-79-12 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1552 | PS4-83-EHO-0001A-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0010 TO PS4-83-EHO-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1553 | PS4-83-EHO-0001A-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-83-EHO-0001A | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-02 - Crude Oil Export Pump A |  | PS4-25-02 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1554 | PS4-83-EHO-0001B-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0010 TO PS4-83-EHO-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1555 | PS4-83-EHO-0001B-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-83-EHO-0001B | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-03 - Crude Oil Export Pump B |  | PS4-25-03 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1556 | PS4-83-EHO-0001C-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0010 TO PS4-83-EHO-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1557 | PS4-83-EHO-0001C-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-83-EHO-0001C | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-25-04 - Crude Oil Export Pump C |  | PS4-25-04 |  |  |  | I | To be completed | PS4 - Milestone H | TM-00614
T-00614-1558 | PS4-09-BI-2504-CC01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0010 TO PS4-09-BI-2504 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-01 - HVAC for Office and Facilities building |  | PS4-09-01 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1559 | PS4-09-LB-0006-CC05 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-03-SFMC-0012 TO PS4-09-LB-0006 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-09-01 - HVAC for Office and Facilities building |  | PS4-09-01 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00614-1560 | PS4-74-LB-5101-CC02 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0006 TO PS4-74-LB-5101 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-74-02 - N2 Generation Skid (UCP) |  | PS4-74-02 |  |  |  | I | To be completed | PS4 - Milestone F | TM-00614
T-00614-2631 | PS4-50-IE-0001-CJ01 |  |  |  |  | CJX10a - Multi/Single-core instrument control cable (One end by HU CTR) | PCOM - Precommissioning | I | Conformity Check | I - Instrumentation | Cable FROM PS4-04-PMC-0001 TO PS4-50-LIT-0001 | EACOP | CPP AGI |  |  | 4 |  | 4 |  | PS4 - TZA - PS4 - Tanzania | PS4-50-01 - Water Well Submersible Pumps (3100) |  | PS4-50-01 |  |  |  | I | To be completed | PS4 - Milestone I | TM-00614
T-00618-0180 | PS4-08-11CB-1201-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1001 TO PS4-08-11CB-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-72 - Structured Cabling (FO) |  | PS4-08-72 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0181 | PS4-08-11CB-1501-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1001 TO PS4-08-11CB-1501 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-72 - Structured Cabling (FO) |  | PS4-08-72 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0182 | PS4-08-11CB-1601-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1001 TO PS4-08-11CB-1601 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-72 - Structured Cabling (FO) |  | PS4-08-72 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0183 | PS4-08-11CB-1901-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1001 TO PS4-08-11CB-1901 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-72 - Structured Cabling (FO) |  | PS4-08-72 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0184 | PS4-08-12BT-0001-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-12BT-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0185 | PS4-08-12BT-0104-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1001 TO PS4-08-12BT-0104 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0186 | PS4-08-12BT-0105-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1001 TO PS4-08-12BT-0105 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0187 | PS4-08-12BT-0106-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1001 TO PS4-08-12BT-0106 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0188 | PS4-08-12BT-0107-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-12BT-0107 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0189 | PS4-08-12BT-0108-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-12BT-0108 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0190 | PS4-08-12BT-0109-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-12BT-0109 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0191 | PS4-08-12BT-1903-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-12BT-1903 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0192 | PS4-08-12BT-1904-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-12BT-1904 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0193 | PS4-08-15CP-0001-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0008 TO PS4-08-15CP-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-15 - Security Data Network (SII SP3 SEC) |  | PS4-08-15 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0194 | PS4-08-15CP-0002-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0001 TO PS4-08-15CP-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-15 - Security Data Network (SII SP3 SEC) |  | PS4-08-15 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0195 | PS4-08-15CP-0003-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0002 TO PS4-08-15CP-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-15 - Security Data Network (SII SP3 SEC) |  | PS4-08-15 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0196 | PS4-08-15CP-0004-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0003 TO PS4-08-15CP-0004 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-15 - Security Data Network (SII SP3 SEC) |  | PS4-08-15 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0197 | PS4-08-15CP-0005-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0004 TO PS4-08-15CP-0005 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-15 - Security Data Network (SII SP3 SEC) |  | PS4-08-15 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0198 | PS4-08-15CP-0005-CX02 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CB-1001 TO PS4-08-15CP-0005 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-15 - Security Data Network (SII SP3 SEC) |  | PS4-08-15 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0199 | PS4-08-15CP-0006-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CB-1001 TO PS4-08-15CP-0006 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-15 - Security Data Network (SII SP3 SEC) |  | PS4-08-15 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0200 | PS4-08-15CP-0007-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0006 TO PS4-08-15CP-0007 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-15 - Security Data Network (SII SP3 SEC) |  | PS4-08-15 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0201 | PS4-08-15CP-0008-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0007 TO PS4-08-15CP-0008 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-15 - Security Data Network (SII SP3 SEC) |  | PS4-08-15 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0202 | PS4-08-36SP-0101-CX02 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-35CB-1001 TO PS4-08-36SP-0101 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-36 - Pipeline FO Cable & EPRS |  | PS4-08-36 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0203 | PS4-08-36SP-0102-CX02 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-35CB-1001 TO PS4-08-36SP-0102 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-36 - Pipeline FO Cable & EPRS |  | PS4-08-36 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0204 | PS4-08-52CM-0131-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CB-1001 TO PS4-08-52CM-0131 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00618
T-00618-0205 | PS4-08-52CM-0132-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CB-1001 TO PS4-08-52CM-0132 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00618
T-00618-0206 | PS4-08-52CM-0133-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CB-1001 TO PS4-08-52CM-0133 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00618
T-00618-0207 | PS4-08-52CM-0135-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-52CM-0135 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00618
T-00618-0208 | PS4-08-52CM-0136-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-52CM-0136 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00618
T-00618-0209 | PS4-08-52CM-0138-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CB-1001 TO PS4-08-52CM-0138 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00618
T-00618-0210 | PS4-08-52CM-0139-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CB-1001 TO PS4-08-52CM-0139 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00618
T-00618-0211 | PS4-08-83SP-0001-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CB-1001 TO PS4-08-83SP-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-83 - Perimeter & Pipeline intrusion detection system |  | PS4-08-83 |  |  |  | T | To be completed | PS4 - Milestone I | TM-00618
T-00618-0212 | PS4-08-83SP-0001-CX02 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CB-1001 TO PS4-08-83SP-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-83 - Perimeter & Pipeline intrusion detection system |  | PS4-08-83 |  |  |  | T | To be completed | PS4 - Milestone I | TM-00618
T-00618-0213 | PS4-08-85CP-0024-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CB-1001 TO PS4-08-85CP-0024 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00618
T-00618-0214 | PS4-08-85CP-0024-CX02 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CB-1001 TO PS4-08-85CP-0024 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00618
T-00618-0215 | PS4-08-85CP-0025-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CB-1001 TO PS4-08-85CP-0025 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00618
T-00618-0216 | PS4-08-85CP-0025-CX02 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CB-1001 TO PS4-08-85CP-0025 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00618
T-00618-0362 | PS4-08-13CB-1201-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-13CB-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-72 - Structured Cabling (FO) |  | PS4-08-72 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00618-0363 | PS4-08-14CB-1201-CX01 |  |  |  |  | CIX55a - Fiber Optic Cable (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-14CB-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-72 - Structured Cabling (FO) |  | PS4-08-72 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00618
T-00621-2088 | PS4-08-01BT-0001-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1201 TO PS4-08-01BT-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2089 | PS4-08-01BT-0001-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01OC-0001 TO PS4-08-01BT-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2090 | PS4-08-01BT-0002-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1202 TO PS4-08-01BT-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2091 | PS4-08-01BT-0002-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01OC-0001 TO PS4-08-01BT-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2092 | PS4-08-01BT-0003-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0102 TO PS4-08-01BT-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2093 | PS4-08-01BT-0003-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01OC-0002 TO PS4-08-01BT-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2094 | PS4-08-01BT-0004-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0201 TO PS4-08-01BT-0004 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:09 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2095 | PS4-08-01BT-0004-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01OC-0002 TO PS4-08-01BT-0004 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2096 | PS4-08-01BT-1201-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-01BT-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2097 | PS4-08-01BT-1201-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01BT-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2098 | PS4-08-01BT-1201-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01BT-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2099 | PS4-08-01BT-1201-CR03 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1203 TO PS4-08-01BT-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2100 | PS4-08-01BT-1202-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-01BT-1202 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2101 | PS4-08-01BT-1202-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01BT-1202 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2102 | PS4-08-01BT-1202-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01BT-1202 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2103 | PS4-08-01BT-1202-CR03 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1203 TO PS4-08-01BT-1202 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2104 | PS4-08-01BT-1203-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01BT-1203 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2105 | PS4-08-01BT-1203-CJ02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01BT-1203 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2106 | PS4-08-01BT-1203-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-01BT-1203 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2107 | PS4-08-01BT-1203-CN02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-01BT-1203 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2108 | PS4-08-01BT-1501-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0307 TO PS4-08-01BT-1501 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:25 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2109 | PS4-08-01BT-1501-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1503 TO PS4-08-01BT-1501 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2110 | PS4-08-01BT-1502-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0405 TO PS4-08-01BT-1502 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:31 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2111 | PS4-08-01BT-1502-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1503 TO PS4-08-01BT-1502 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2112 | PS4-08-01BT-1503-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01BT-1503 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:48 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2113 | PS4-08-01BT-1503-CJ02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01BT-1503 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:49 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2114 | PS4-08-01BT-1503-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-01BT-1503 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2115 | PS4-08-01BT-1503-CN02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-01BT-1503 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2116 | PS4-08-01BT-1601-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0720 TO PS4-08-01BT-1601 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2117 | PS4-08-01BT-1601-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01BT-1601 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:45 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2118 | PS4-08-01BT-1602-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-0002 TO PS4-08-01BT-1602 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:46 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2119 | PS4-08-01BT-1602-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01BT-1602 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:47 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2120 | PS4-08-01BT-1901-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1903 TO PS4-08-01BT-1901 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2121 | PS4-08-01BT-1901-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01BT-1901 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:33 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2122 | PS4-08-01BT-1902-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1904 TO PS4-08-01BT-1902 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2123 | PS4-08-01BT-1902-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01BT-1902 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:43 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2124 | PS4-08-01BT-1903-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01BT-1903 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:32 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2125 | PS4-08-01BT-1904-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01BT-1904 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:34 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2126 | PS4-08-01LS-0101-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01LS-0101 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 10:56 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2127 | PS4-08-01LS-0102-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0101 TO PS4-08-01LS-0102 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 10:57 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2128 | PS4-08-01LS-0103-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01OC-0002 TO PS4-08-01LS-0103 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2129 | PS4-08-01LS-0104-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-0003 TO PS4-08-01LS-0104 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2130 | PS4-08-01LS-0105-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0104 TO PS4-08-01LS-0105 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 10:59 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2131 | PS4-08-01LS-0106-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0105 TO PS4-08-01LS-0106 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:00 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2132 | PS4-08-01LS-0107-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0106 TO PS4-08-01LS-0107 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:01 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2133 | PS4-08-01LS-0108-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0107 TO PS4-08-01LS-0108 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:02 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2134 | PS4-08-01LS-0109-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0108 TO PS4-08-01LS-0109 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:04 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2135 | PS4-08-01LS-0110-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0109 TO PS4-08-01LS-0110 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:05 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2136 | PS4-08-01LS-0110-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01LS-0110 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:07 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2137 | PS4-08-01LS-0201-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01LS-0201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:08 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2138 | PS4-08-01LS-0202-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01OC-0002 TO PS4-08-01LS-0202 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2139 | PS4-08-01LS-0203-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-0004 TO PS4-08-01LS-0203 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2140 | PS4-08-01LS-0204-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0203 TO PS4-08-01LS-0204 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:10 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2141 | PS4-08-01LS-0205-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0204 TO PS4-08-01LS-0205 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:11 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2142 | PS4-08-01LS-0206-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0205 TO PS4-08-01LS-0206 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:12 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2143 | PS4-08-01LS-0207-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0206 TO PS4-08-01LS-0207 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:13 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2144 | PS4-08-01LS-0208-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0207 TO PS4-08-01LS-0208 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:13 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2145 | PS4-08-01LS-0209-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0208 TO PS4-08-01LS-0209 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:14 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2146 | PS4-08-01LS-0210-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0209 TO PS4-08-01LS-0210 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:15 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2147 | PS4-08-01LS-0211-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0210 TO PS4-08-01LS-0211 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:16 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2148 | PS4-08-01LS-0211-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01LS-0211 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:17 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2149 | PS4-08-01LS-0301-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01LS-0301 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:18 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2150 | PS4-08-01LS-0302-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0301 TO PS4-08-01LS-0302 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:19 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2151 | PS4-08-01LS-0303-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0302 TO PS4-08-01LS-0303 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:20 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2152 | PS4-08-01LS-0304-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0303 TO PS4-08-01LS-0304 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:21 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2153 | PS4-08-01LS-0305-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0304 TO PS4-08-01LS-0305 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:22 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2154 | PS4-08-01LS-0306-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0305 TO PS4-08-01LS-0306 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:23 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2155 | PS4-08-01LS-0307-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0306 TO PS4-08-01LS-0307 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:24 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2156 | PS4-08-01LS-0308-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1501 TO PS4-08-01LS-0308 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2157 | PS4-08-01LS-0309-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0308 TO PS4-08-01LS-0309 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2158 | PS4-08-01LS-0310-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1501 TO PS4-08-01LS-0310 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:25 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2159 | PS4-08-01LS-0310-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01LS-0310 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2160 | PS4-08-01LS-0318-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01LS-0318 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2161 | PS4-08-01LS-0401-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01LS-0401 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:26 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2162 | PS4-08-01LS-0402-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0401 TO PS4-08-01LS-0402 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:28 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2163 | PS4-08-01LS-0403-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0402 TO PS4-08-01LS-0403 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:29 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2164 | PS4-08-01LS-0404-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0403 TO PS4-08-01LS-0404 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:30 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2165 | PS4-08-01LS-0405-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0404 TO PS4-08-01LS-0405 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:30 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2166 | PS4-08-01LS-0406-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1502 TO PS4-08-01LS-0406 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2167 | PS4-08-01LS-0407-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0406 TO PS4-08-01LS-0407 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2168 | PS4-08-01LS-0408-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0407 TO PS4-08-01LS-0408 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2169 | PS4-08-01LS-0409-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1502 TO PS4-08-01LS-0409 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-27 13:52 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2170 | PS4-08-01LS-0410-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0409 TO PS4-08-01LS-0410 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-27 13:55 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2171 | PS4-08-01LS-0411-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0410 TO PS4-08-01LS-0411 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2172 | PS4-08-01LS-0411-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01LS-0411 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2173 | PS4-08-01LS-0418-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01LS-0418 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2174 | PS4-08-01LS-0501-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1903 TO PS4-08-01LS-0501 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2175 | PS4-08-01LS-0502-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0501 TO PS4-08-01LS-0502 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2176 | PS4-08-01LS-0503-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0502 TO PS4-08-01LS-0503 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2177 | PS4-08-01LS-0504-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0503 TO PS4-08-01LS-0504 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2178 | PS4-08-01LS-0505-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0504 TO PS4-08-01LS-0505 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2179 | PS4-08-01LS-0506-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0505 TO PS4-08-01LS-0506 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2180 | PS4-08-01LS-0507-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0506 TO PS4-08-01LS-0507 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-27 13:57 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2181 | PS4-08-01LS-0508-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0507 TO PS4-08-01LS-0508 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2182 | PS4-08-01LS-0509-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0508 TO PS4-08-01LS-0509 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2183 | PS4-08-01LS-0510-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0509 TO PS4-08-01LS-0510 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-27 13:59 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2184 | PS4-08-01LS-0511-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0510 TO PS4-08-01LS-0511 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-27 14:07 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2185 | PS4-08-01LS-0512-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0511 TO PS4-08-01LS-0512 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-27 14:12 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2186 | PS4-08-01LS-0517-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0512 TO PS4-08-01LS-0517 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2187 | PS4-08-01LS-0518-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0517 TO PS4-08-01LS-0518 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2188 | PS4-08-01LS-0519-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0518 TO PS4-08-01LS-0519 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2189 | PS4-08-01LS-0520-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0519 TO PS4-08-01LS-0520 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2190 | PS4-08-01LS-0521-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0520 TO PS4-08-01LS-0521 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2191 | PS4-08-01LS-0522-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0521 TO PS4-08-01LS-0522 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2192 | PS4-08-01LS-0522-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1903 TO PS4-08-01LS-0522 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-27 14:13 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2193 | PS4-08-01LS-0523-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1901 TO PS4-08-01LS-0523 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2194 | PS4-08-01LS-0524-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0523 TO PS4-08-01LS-0524 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2195 | PS4-08-01LS-0525-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0524 TO PS4-08-01LS-0525 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2196 | PS4-08-01LS-0526-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0525 TO PS4-08-01LS-0526 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2197 | PS4-08-01LS-0527-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0526 TO PS4-08-01LS-0527 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2198 | PS4-08-01LS-0528-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0527 TO PS4-08-01LS-0528 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2199 | PS4-08-01LS-0529-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0528 TO PS4-08-01LS-0529 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2200 | PS4-08-01LS-0530-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0529 TO PS4-08-01LS-0530 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2201 | PS4-08-01LS-0530-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1901 TO PS4-08-01LS-0530 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2202 | PS4-08-01LS-0601-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1904 TO PS4-08-01LS-0601 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2203 | PS4-08-01LS-0602-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0601 TO PS4-08-01LS-0602 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2204 | PS4-08-01LS-0603-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0602 TO PS4-08-01LS-0603 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2205 | PS4-08-01LS-0604-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0603 TO PS4-08-01LS-0604 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2206 | PS4-08-01LS-0605-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0604 TO PS4-08-01LS-0605 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2207 | PS4-08-01LS-0606-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0605 TO PS4-08-01LS-0606 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2208 | PS4-08-01LS-0607-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0606 TO PS4-08-01LS-0607 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2209 | PS4-08-01LS-0608-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0607 TO PS4-08-01LS-0608 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2210 | PS4-08-01LS-0609-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0608 TO PS4-08-01LS-0609 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2211 | PS4-08-01LS-0610-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0609 TO PS4-08-01LS-0610 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-27 14:19 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2212 | PS4-08-01LS-0611-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0610 TO PS4-08-01LS-0611 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-27 12:41 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2213 | PS4-08-01LS-0612-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0611 TO PS4-08-01LS-0612 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2214 | PS4-08-01LS-0617-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0612 TO PS4-08-01LS-0617 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2215 | PS4-08-01LS-0618-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0617 TO PS4-08-01LS-0618 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2216 | PS4-08-01LS-0619-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0618 TO PS4-08-01LS-0619 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2217 | PS4-08-01LS-0620-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0619 TO PS4-08-01LS-0620 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2218 | PS4-08-01LS-0621-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0620 TO PS4-08-01LS-0621 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2219 | PS4-08-01LS-0621-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1904 TO PS4-08-01LS-0621 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-27 14:21 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2220 | PS4-08-01LS-0622-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1902 TO PS4-08-01LS-0622 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2221 | PS4-08-01LS-0623-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0622 TO PS4-08-01LS-0623 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2222 | PS4-08-01LS-0624-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0623 TO PS4-08-01LS-0624 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2223 | PS4-08-01LS-0625-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0624 TO PS4-08-01LS-0625 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2224 | PS4-08-01LS-0626-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0625 TO PS4-08-01LS-0626 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2225 | PS4-08-01LS-0627-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0626 TO PS4-08-01LS-0627 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2226 | PS4-08-01LS-0628-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0627 TO PS4-08-01LS-0628 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2227 | PS4-08-01LS-0629-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0628 TO PS4-08-01LS-0629 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2228 | PS4-08-01LS-0629-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1902 TO PS4-08-01LS-0629 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2229 | PS4-08-01LS-0701-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1201 TO PS4-08-01LS-0701 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2230 | PS4-08-01LS-0702-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0701 TO PS4-08-01LS-0702 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2231 | PS4-08-01LS-0703-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0704 TO PS4-08-01LS-0703 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2232 | PS4-08-01LS-0704-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0702 TO PS4-08-01LS-0704 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2233 | PS4-08-01LS-0705-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1201 TO PS4-08-01LS-0705 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2234 | PS4-08-01LS-0706-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0703 TO PS4-08-01LS-0706 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2235 | PS4-08-01LS-0707-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0706 TO PS4-08-01LS-0707 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2236 | PS4-08-01LS-0708-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0707 TO PS4-08-01LS-0708 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2237 | PS4-08-01LS-0709-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0708 TO PS4-08-01LS-0709 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2238 | PS4-08-01LS-0710-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0709 TO PS4-08-01LS-0710 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2239 | PS4-08-01LS-0711-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0710 TO PS4-08-01LS-0711 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2240 | PS4-08-01LS-0712-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1201 TO PS4-08-01LS-0712 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2241 | PS4-08-01LS-0713-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0712 TO PS4-08-01LS-0713 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2242 | PS4-08-01LS-0714-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0711 TO PS4-08-01LS-0714 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2243 | PS4-08-01LS-0715-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0714 TO PS4-08-01LS-0715 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2244 | PS4-08-01LS-0716-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0715 TO PS4-08-01LS-0716 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2245 | PS4-08-01LS-0716-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1201 TO PS4-08-01LS-0716 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2246 | PS4-08-01LS-0717-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0713 TO PS4-08-01LS-0717 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2247 | PS4-08-01LS-0718-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0717 TO PS4-08-01LS-0718 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2248 | PS4-08-01LS-0719-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01OC-0001 TO PS4-08-01LS-0719 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2249 | PS4-08-01LS-0720-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-0001 TO PS4-08-01LS-0720 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 11:44 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2250 | PS4-08-01LS-0721-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1601 TO PS4-08-01LS-0721 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2251 | PS4-08-01LS-0722-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0721 TO PS4-08-01LS-0722 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2252 | PS4-08-01LS-0723-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0722 TO PS4-08-01LS-0723 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2253 | PS4-08-01LS-0724-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0723 TO PS4-08-01LS-0724 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2254 | PS4-08-01LS-0725-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0724 TO PS4-08-01LS-0725 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2255 | PS4-08-01LS-0726-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0725 TO PS4-08-01LS-0726 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2256 | PS4-08-01LS-0727-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0726 TO PS4-08-01LS-0727 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2257 | PS4-08-01LS-0728-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0727 TO PS4-08-01LS-0728 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2258 | PS4-08-01LS-0729-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0728 TO PS4-08-01LS-0729 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2259 | PS4-08-01LS-0730-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0729 TO PS4-08-01LS-0730 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2260 | PS4-08-01LS-0731-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0730 TO PS4-08-01LS-0731 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2261 | PS4-08-01LS-0732-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0731 TO PS4-08-01LS-0732 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2262 | PS4-08-01LS-0733-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0732 TO PS4-08-01LS-0733 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2263 | PS4-08-01LS-0733-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1601 TO PS4-08-01LS-0733 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2264 | PS4-08-01LS-0801-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1202 TO PS4-08-01LS-0801 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2265 | PS4-08-01LS-0802-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0801 TO PS4-08-01LS-0802 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2266 | PS4-08-01LS-0803-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0802 TO PS4-08-01LS-0803 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2267 | PS4-08-01LS-0804-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1202 TO PS4-08-01LS-0804 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2268 | PS4-08-01LS-0805-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0803 TO PS4-08-01LS-0805 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2269 | PS4-08-01LS-0806-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0805 TO PS4-08-01LS-0806 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2270 | PS4-08-01LS-0807-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0806 TO PS4-08-01LS-0807 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2271 | PS4-08-01LS-0808-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0807 TO PS4-08-01LS-0808 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2272 | PS4-08-01LS-0809-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0808 TO PS4-08-01LS-0809 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2273 | PS4-08-01LS-0810-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0809 TO PS4-08-01LS-0810 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2274 | PS4-08-01LS-0811-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1202 TO PS4-08-01LS-0811 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2275 | PS4-08-01LS-0812-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0811 TO PS4-08-01LS-0812 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2276 | PS4-08-01LS-0813-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0810 TO PS4-08-01LS-0813 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2277 | PS4-08-01LS-0814-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0813 TO PS4-08-01LS-0814 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2278 | PS4-08-01LS-0815-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0814 TO PS4-08-01LS-0815 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2279 | PS4-08-01LS-0816-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0815 TO PS4-08-01LS-0816 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2280 | PS4-08-01LS-0816-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1202 TO PS4-08-01LS-0816 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2281 | PS4-08-01LS-0817-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0812 TO PS4-08-01LS-0817 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2282 | PS4-08-01LS-0818-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0817 TO PS4-08-01LS-0818 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2283 | PS4-08-01LS-0819-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01OC-0001 TO PS4-08-01LS-0819 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2284 | PS4-08-01LS-0820-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1602 TO PS4-08-01LS-0820 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2285 | PS4-08-01LS-0821-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0820 TO PS4-08-01LS-0821 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2286 | PS4-08-01LS-0822-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0821 TO PS4-08-01LS-0822 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2287 | PS4-08-01LS-0823-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0822 TO PS4-08-01LS-0823 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2288 | PS4-08-01LS-0824-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0823 TO PS4-08-01LS-0824 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2289 | PS4-08-01LS-0825-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0824 TO PS4-08-01LS-0825 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2290 | PS4-08-01LS-0826-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0825 TO PS4-08-01LS-0826 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2291 | PS4-08-01LS-0827-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0826 TO PS4-08-01LS-0827 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2292 | PS4-08-01LS-0828-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0827 TO PS4-08-01LS-0828 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2293 | PS4-08-01LS-0829-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0828 TO PS4-08-01LS-0829 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2294 | PS4-08-01LS-0830-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0829 TO PS4-08-01LS-0830 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2295 | PS4-08-01LS-0831-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0830 TO PS4-08-01LS-0831 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2296 | PS4-08-01LS-0832-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0831 TO PS4-08-01LS-0832 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2297 | PS4-08-01LS-0833-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0832 TO PS4-08-01LS-0833 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2298 | PS4-08-01LS-0834-CR01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01LS-0833 TO PS4-08-01LS-0834 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2299 | PS4-08-01LS-0834-CR02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1602 TO PS4-08-01LS-0834 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2300 | PS4-08-01MP-0001-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-13CB-1001 TO PS4-08-01MP-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 10:41 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2301 | PS4-08-01MP-0001-CC02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-13CB-1001 TO PS4-08-01MP-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 10:54 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2302 | PS4-08-01MP-0001-CC03 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-13CB-1001 TO PS4-08-01MP-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 10:55 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2303 | PS4-08-01MP-0001-CC04 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-13CB-1001 TO PS4-08-01MP-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA | 2026-07-10 10:56 | PS4-08-01 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2304 | PS4-08-01OC-0001-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01OC-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2305 | PS4-08-01OC-0001-CJ02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01OC-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2306 | PS4-08-01OC-0001-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01OC-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2307 | PS4-08-01OC-0001-CN02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01OC-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2308 | PS4-08-01OC-0002-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01OC-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2309 | PS4-08-01OC-0002-CJ02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01OC-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2310 | PS4-08-01OC-0002-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01OC-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2311 | PS4-08-01OC-0002-CN02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01MP-0001 TO PS4-08-01OC-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2312 | PS4-08-01PA-1201-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-01PA-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2313 | PS4-08-01PA-1201-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1203 TO PS4-08-01PA-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2314 | PS4-08-01PA-1501-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-01PA-1501 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2315 | PS4-08-01PA-1501-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-01BT-1503 TO PS4-08-01PA-1501 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2316 | PS4-08-03TP-0001-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1001 TO PS4-08-03TP-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-03 - Telephone | 2026-07-10 11:53 | PS4-08-03 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2317 | PS4-08-03TP-0001-CJ02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-03FB-0001 TO PS4-08-03TP-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-03 - Telephone |  | PS4-08-03 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2318 | PS4-08-03TP-0002-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1001 TO PS4-08-03TP-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-03 - Telephone | 2026-07-10 11:53 | PS4-08-03 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2319 | PS4-08-03TP-0002-CJ02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-03FB-0002 TO PS4-08-03TP-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-03 - Telephone |  | PS4-08-03 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2320 | PS4-08-03TP-0003-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1001 TO PS4-08-03TP-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-03 - Telephone |  | PS4-08-03 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2321 | PS4-08-03TP-0003-CJ02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-03FB-0003 TO PS4-08-03TP-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-03 - Telephone |  | PS4-08-03 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2322 | PS4-08-03TP-0004-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-03TP-0004 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-03 - Telephone |  | PS4-08-03 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2323 | PS4-08-03TP-0004-CJ02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-03FB-0004 TO PS4-08-03TP-0004 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-03 - Telephone |  | PS4-08-03 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2324 | PS4-08-03TP-0101-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1001 TO PS4-08-03TP-0101 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-03 - Telephone |  | PS4-08-03 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2325 | PS4-08-03TP-0101-CJ02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-03FB-0101 TO PS4-08-03TP-0101 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-03 - Telephone |  | PS4-08-03 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2326 | PS4-08-03TP-0102-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-03TP-0102 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-03 - Telephone |  | PS4-08-03 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2327 | PS4-08-03TP-0102-CJ02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-03FB-0102 TO PS4-08-03TP-0102 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-03 - Telephone |  | PS4-08-03 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2328 | PS4-08-03TP-0103-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1001 TO PS4-08-03TP-0103 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-03 - Telephone | 2026-07-10 11:54 | PS4-08-03 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2329 | PS4-08-03TP-0103-CJ02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-03FB-0103 TO PS4-08-03TP-0103 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-03 - Telephone |  | PS4-08-03 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2330 | PS4-08-03TP-1903-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-03TP-1903 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-03 - Telephone | 2026-07-10 11:55 | PS4-08-03 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2331 | PS4-08-03TP-1903-CJ02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-03FB-1903 TO PS4-08-03TP-1903 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-03 - Telephone |  | PS4-08-03 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2332 | PS4-08-03TP-1904-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-03TP-1904 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-03 - Telephone | 2026-07-10 11:56 | PS4-08-03 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2333 | PS4-08-03TP-1904-CJ02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-03FB-1904 TO PS4-08-03TP-1904 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-03 - Telephone |  | PS4-08-03 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2334 | PS4-08-05IN-0001-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-05IN-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2335 | PS4-08-05IN-0002-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0004 TO PS4-08-05IN-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2336 | PS4-08-05IN-0003-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-05IN-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2337 | PS4-08-05IN-0004-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-05IN-0004 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2338 | PS4-08-05IN-0005-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-05IN-0005 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2339 | PS4-08-12AP-0001-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-12BT-0001 TO PS4-08-12AP-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2340 | PS4-08-12AP-0002-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-12BT-0002 TO PS4-08-12AP-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2341 | PS4-08-12AP-0003-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-12BT-0003 TO PS4-08-12AP-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2342 | PS4-08-12AP-0101-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-12BT-0101 TO PS4-08-12AP-0101 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2343 | PS4-08-12AP-0103-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-12BT-0103 TO PS4-08-12AP-0103 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2344 | PS4-08-12AP-0104-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-12BT-0104 TO PS4-08-12AP-0104 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2345 | PS4-08-12AP-0105-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-12BT-0105 TO PS4-08-12AP-0105 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2346 | PS4-08-12AP-0106-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-12BT-0106 TO PS4-08-12AP-0106 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2347 | PS4-08-12AP-0107-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-12BT-0107 TO PS4-08-12AP-0107 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2348 | PS4-08-12AP-0108-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-12BT-0108 TO PS4-08-12AP-0108 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2349 | PS4-08-12AP-0109-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-12BT-0109 TO PS4-08-12AP-0109 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2350 | PS4-08-12AP-1903-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-12BT-1903 TO PS4-08-12AP-1903 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2351 | PS4-08-12AP-1904-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-12BT-1904 TO PS4-08-12AP-1904 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2352 | PS4-08-12BT-0002-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-12BT-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2353 | PS4-08-12BT-0003-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-12BT-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2354 | PS4-08-12BT-0101-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-12BT-0101 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2355 | PS4-08-12BT-0103-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-12BT-0103 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) | 2026-07-10 11:52 | PS4-08-12 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone C | TM-00621 | sridhar, muthu
T-00621-2356 | PS4-08-13CB-1201-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-13CB-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-13 - Safety Data Network (SII SP3 SAF) |  | PS4-08-13 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2357 | PS4-08-13CB-1201-CA02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-13CB-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-13 - Safety Data Network (SII SP3 SAF) |  | PS4-08-13 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2358 | PS4-08-13CB-1201-CA03 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-13CB-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-13 - Safety Data Network (SII SP3 SAF) |  | PS4-08-13 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2359 | PS4-08-13CB-1201-CA04 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-13CB-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-13 - Safety Data Network (SII SP3 SAF) |  | PS4-08-13 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2360 | PS4-08-13CB-1201-CA05 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-13CB-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-13 - Safety Data Network (SII SP3 SAF) |  | PS4-08-13 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2361 | PS4-08-13CB-1201-CA06 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-13CB-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-13 - Safety Data Network (SII SP3 SAF) |  | PS4-08-13 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2362 | PS4-08-13CB-1201-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-14CB-1201 TO PS4-08-13CB-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-93 - Telecom Monitoring System |  | PS4-08-93 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2363 | PS4-08-13CB-1201-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-04-PMC-0006 TO PS4-08-13CB-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-13 - Safety Data Network (SII SP3 SAF) |  | PS4-08-13 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2364 | PS4-08-14CB-1201-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-14CB-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-14 - Industrial Data Network (SII SP1) |  | PS4-08-14 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2365 | PS4-08-14CB-1201-CA02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-14CB-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-14 - Industrial Data Network (SII SP1) |  | PS4-08-14 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2366 | PS4-08-14CB-1201-CA03 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-14CB-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-14 - Industrial Data Network (SII SP1) |  | PS4-08-14 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2367 | PS4-08-14CB-1201-CA04 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-14CB-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-14 - Industrial Data Network (SII SP1) |  | PS4-08-14 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2368 | PS4-08-14CB-1201-CA05 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-14CB-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-14 - Industrial Data Network (SII SP1) |  | PS4-08-14 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2369 | PS4-08-14CB-1201-CA06 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-14CB-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-14 - Industrial Data Network (SII SP1) |  | PS4-08-14 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2370 | PS4-08-23AN-0001-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-23LA-1201 TO PS4-08-23AN-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-23 - VHF Trunk Radio System |  | PS4-08-23 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2371 | PS4-08-23AN-0002-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-23LA-1501 TO PS4-08-23AN-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-23 - VHF Trunk Radio System |  | PS4-08-23 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2372 | PS4-08-23AN-0003-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-23LA-1601 TO PS4-08-23AN-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-23 - VHF Trunk Radio System |  | PS4-08-23 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2373 | PS4-08-23AN-0005-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-23LA-1901 TO PS4-08-23AN-0005 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-23 - VHF Trunk Radio System |  | PS4-08-23 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2374 | PS4-08-23AN-0901-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-23LA-1202 TO PS4-08-23AN-0901 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-23 - VHF Trunk Radio System |  | PS4-08-23 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2375 | PS4-08-23AN-1201-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-13CB-1201 TO PS4-08-23AN-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-23 - VHF Trunk Radio System |  | PS4-08-23 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2376 | PS4-08-23AN-1601-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-23LA-1601 TO PS4-08-23AN-1601 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-23 - VHF Trunk Radio System |  | PS4-08-23 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2377 | PS4-08-23AN-1901-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-23LA-1901 TO PS4-08-23AN-1901 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-23 - VHF Trunk Radio System |  | PS4-08-23 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2378 | PS4-08-23LA-1201-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-23BS-1201 TO PS4-08-23LA-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-23 - VHF Trunk Radio System |  | PS4-08-23 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2379 | PS4-08-23LA-1202-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-13CB-1201 TO PS4-08-23LA-1202 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-23 - VHF Trunk Radio System |  | PS4-08-23 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2380 | PS4-08-23LA-1501-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-23BS-1501 TO PS4-08-23LA-1501 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-23 - VHF Trunk Radio System |  | PS4-08-23 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2381 | PS4-08-34AN-0001-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-34LA-1201 TO PS4-08-34AN-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-34 - Satphone |  | PS4-08-34 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2382 | PS4-08-34AN-0002-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-34LA-1501 TO PS4-08-34AN-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-34 - Satphone |  | PS4-08-34 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2383 | PS4-08-34LA-1201-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-34DS-1211 TO PS4-08-34LA-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-34 - Satphone |  | PS4-08-34 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2384 | PS4-08-34LA-1501-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-34DS-1511 TO PS4-08-34LA-1501 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-34 - Satphone |  | PS4-08-34 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2385 | PS4-08-51AN-0001-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-51LA-1201 TO PS4-08-51AN-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-51 - Entertainment |  | PS4-08-51 |  |  |  | T | To be completed | PS4 - Milestone I | TM-00621
T-00621-2386 | PS4-08-51AN-0001-CV02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-51LA-1202 TO PS4-08-51AN-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-51 - Entertainment |  | PS4-08-51 |  |  |  | T | To be completed | PS4 - Milestone I | TM-00621
T-00621-2387 | PS4-08-51AN-0001-CV03 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-51LA-1203 TO PS4-08-51AN-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-51 - Entertainment |  | PS4-08-51 |  |  |  | T | To be completed | PS4 - Milestone I | TM-00621
T-00621-2388 | PS4-08-51AN-0001-CV04 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-51LA-1204 TO PS4-08-51AN-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-51 - Entertainment |  | PS4-08-51 |  |  |  | T | To be completed | PS4 - Milestone I | TM-00621
T-00621-2389 | PS4-08-51LA-1201-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-51LA-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-51 - Entertainment |  | PS4-08-51 |  |  |  | T | To be completed | PS4 - Milestone I | TM-00621
T-00621-2390 | PS4-08-51LA-1202-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-51LA-1202 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-51 - Entertainment |  | PS4-08-51 |  |  |  | T | To be completed | PS4 - Milestone I | TM-00621
T-00621-2391 | PS4-08-51LA-1203-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-51LA-1203 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-51 - Entertainment |  | PS4-08-51 |  |  |  | T | To be completed | PS4 - Milestone I | TM-00621
T-00621-2392 | PS4-08-51LA-1204-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-51LA-1204 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-51 - Entertainment |  | PS4-08-51 |  |  |  | T | To be completed | PS4 - Milestone I | TM-00621
T-00621-2393 | PS4-08-51SK-1201-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-51SK-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-51 - Entertainment |  | PS4-08-51 |  |  |  | T | To be completed | PS4 - Milestone I | TM-00621
T-00621-2394 | PS4-08-51SK-1202-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-51SK-1202 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-51 - Entertainment |  | PS4-08-51 |  |  |  | T | To be completed | PS4 - Milestone I | TM-00621
T-00621-2395 | PS4-08-51SK-1203-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-51SK-1203 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-51 - Entertainment |  | PS4-08-51 |  |  |  | T | To be completed | PS4 - Milestone I | TM-00621
T-00621-2396 | PS4-08-51SK-1204-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-51SK-1204 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-51 - Entertainment |  | PS4-08-51 |  |  |  | T | To be completed | PS4 - Milestone I | TM-00621
T-00621-2397 | PS4-08-51SK-1205-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-51SK-1205 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-51 - Entertainment |  | PS4-08-51 |  |  |  | T | To be completed | PS4 - Milestone I | TM-00621
T-00621-2398 | PS4-08-51SK-1206-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-51SK-1206 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-51 - Entertainment |  | PS4-08-51 |  |  |  | T | To be completed | PS4 - Milestone I | TM-00621
T-00621-2399 | PS4-08-51SK-1207-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-51SK-1207 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-51 - Entertainment |  | PS4-08-51 |  |  |  | T | To be completed | PS4 - Milestone I | TM-00621
T-00621-2400 | PS4-08-51SK-1208-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-51SK-1208 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-51 - Entertainment |  | PS4-08-51 |  |  |  | T | To be completed | PS4 - Milestone I | TM-00621
T-00621-2401 | PS4-08-51SK-1209-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-51SK-1209 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-51 - Entertainment |  | PS4-08-51 |  |  |  | T | To be completed | PS4 - Milestone I | TM-00621
T-00621-2402 | PS4-08-51SK-1210-CV01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-51SK-1210 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-51 - Entertainment |  | PS4-08-51 |  |  |  | T | To be completed | PS4 - Milestone I | TM-00621
T-00621-2403 | PS4-08-52CM-0001-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-52CM-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2404 | PS4-08-52CM-0002-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-52CM-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2405 | PS4-08-52CM-0003-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-52CM-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2406 | PS4-08-52CM-0004-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-52CM-0004 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2407 | PS4-08-52CM-0005-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-52CM-0005 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2408 | PS4-08-52CM-0031-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0002 TO PS4-08-52CM-0031 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2409 | PS4-08-52CM-0032-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0006 TO PS4-08-52CM-0032 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2410 | PS4-08-52CM-0033-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0008 TO PS4-08-52CM-0033 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2411 | PS4-08-52CM-0034-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-52CM-0034 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2412 | PS4-08-52CM-0071-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0001 TO PS4-08-52CM-0071 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2413 | PS4-08-52CM-0072-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0002 TO PS4-08-52CM-0072 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2414 | PS4-08-52CM-0073-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0003 TO PS4-08-52CM-0073 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2415 | PS4-08-52CM-0074-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0004 TO PS4-08-52CM-0074 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2416 | PS4-08-52CM-0075-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0005 TO PS4-08-52CM-0075 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2417 | PS4-08-52CM-0076-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0006 TO PS4-08-52CM-0076 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2418 | PS4-08-52CM-0077-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0007 TO PS4-08-52CM-0077 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2419 | PS4-08-52CM-0078-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0008 TO PS4-08-52CM-0078 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2420 | PS4-08-52CM-0134-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-52CM-0134 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV | 2026-07-10 11:50 | PS4-08-52 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2421 | PS4-08-52CM-0137-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-52CM-0137 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2422 | PS4-08-52CM-0140-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-52CM-0140 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2423 | PS4-08-52CM-0931-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-52CM-0931 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2424 | PS4-08-52CM-1201-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-52CM-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2425 | PS4-08-52CM-1202-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-52CM-1202 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2426 | PS4-08-52CM-1901-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-52CM-1901 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2427 | PS4-08-52CM-1902-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-52CM-1902 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2428 | PS4-08-52CM-1903-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-52CM-1903 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2429 | PS4-08-52TK-0031-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-52CM-0031 TO PS4-08-52TK-0031 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2430 | PS4-08-52TK-0032-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-52CM-0032 TO PS4-08-52TK-0032 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2431 | PS4-08-52TK-0033-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-52CM-0033 TO PS4-08-52TK-0033 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2432 | PS4-08-52TK-0131-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-52CM-0131 TO PS4-08-52TK-0131 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2433 | PS4-08-52TK-0132-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-52CM-0132 TO PS4-08-52TK-0132 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2434 | PS4-08-52TK-0133-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-52CM-0133 TO PS4-08-52TK-0133 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2435 | PS4-08-52TK-0134-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-52CM-0134 TO PS4-08-52TK-0134 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2436 | PS4-08-52TK-0135-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-52CM-0135 TO PS4-08-52TK-0135 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2437 | PS4-08-52TK-0136-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-52CM-0136 TO PS4-08-52TK-0136 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2438 | PS4-08-52TK-0137-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-52CM-0137 TO PS4-08-52TK-0137 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2439 | PS4-08-52TK-0138-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-52CM-0138 TO PS4-08-52TK-0138 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2440 | PS4-08-52TK-0139-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-52CM-0139 TO PS4-08-52TK-0139 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2441 | PS4-08-52TK-0140-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-52CM-0140 TO PS4-08-52TK-0140 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2442 | PS4-08-52TK-0931-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-52CM-0931 TO PS4-08-52TK-0931 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2443 | PS4-08-61BT-0001-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-14CB-1201 TO PS4-08-61BT-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-61 - Meteocean |  | PS4-08-61 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2444 | PS4-08-61BT-0001-CC02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-14CB-1201 TO PS4-08-61BT-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-61 - Meteocean |  | PS4-08-61 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2445 | PS4-08-61BT-0001-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-14CB-1201 TO PS4-08-61BT-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-61 - Meteocean |  | PS4-08-61 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2446 | PS4-08-61BT-0002-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-14CB-1201 TO PS4-08-61BT-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-61 - Meteocean |  | PS4-08-61 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2447 | PS4-08-61BT-0901-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-61BT-0001 TO PS4-08-61BT-0901 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-61 - Meteocean |  | PS4-08-61 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2448 | PS4-08-61SN-0003-CZ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-61BT-0001 TO PS4-08-61SN-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-61 - Meteocean |  | PS4-08-61 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2449 | PS4-08-61SN-0004-CZ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-61BT-0001 TO PS4-08-61SN-0004 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-61 - Meteocean |  | PS4-08-61 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2450 | PS4-08-61SN-0005-CZ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-61BT-0002 TO PS4-08-61SN-0005 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-61 - Meteocean |  | PS4-08-61 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2451 | PS4-08-61SN-0005-CZ02 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-61BT-0002 TO PS4-08-61SN-0005 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-61 - Meteocean |  | PS4-08-61 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2452 | PS4-08-61SN-0901-CZ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-61BT-0901 TO PS4-08-61SN-0901 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-61 - Meteocean |  | PS4-08-61 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2453 | PS4-08-71SK-1201-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2454 | PS4-08-71SK-1202-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1202 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2455 | PS4-08-71SK-1203-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1203 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2456 | PS4-08-71SK-1204-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1204 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2457 | PS4-08-71SK-1205-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1205 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2458 | PS4-08-71SK-1206A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1206A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2459 | PS4-08-71SK-1206B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1206B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2460 | PS4-08-71SK-1207-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1207 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2461 | PS4-08-71SK-1208-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1208 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2462 | PS4-08-71SK-1209-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1209 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2463 | PS4-08-71SK-1210-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1210 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2464 | PS4-08-71SK-1211-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1211 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2465 | PS4-08-71SK-1212A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1212A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2466 | PS4-08-71SK-1212B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1212B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2467 | PS4-08-71SK-1213-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1213 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2468 | PS4-08-71SK-1214A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1214A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2469 | PS4-08-71SK-1214B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1214B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2470 | PS4-08-71SK-1214C-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1214C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2471 | PS4-08-71SK-1214D-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1214D | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2472 | PS4-08-71SK-1215A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1215A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2473 | PS4-08-71SK-1215B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1215B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2474 | PS4-08-71SK-1216A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1216A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2475 | PS4-08-71SK-1216B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1216B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2476 | PS4-08-71SK-1217A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1217A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2477 | PS4-08-71SK-1217B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1217B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2478 | PS4-08-71SK-1218A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1218A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2479 | PS4-08-71SK-1218B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1218B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2480 | PS4-08-71SK-1219A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1219A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2481 | PS4-08-71SK-1219B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1219B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2482 | PS4-08-71SK-1220A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1220A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2483 | PS4-08-71SK-1220B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1220B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2484 | PS4-08-71SK-1221A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1221A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2485 | PS4-08-71SK-1221B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1221B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2486 | PS4-08-71SK-1222A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1222A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2487 | PS4-08-71SK-1222B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1222B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2488 | PS4-08-71SK-1223A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1223A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2489 | PS4-08-71SK-1223B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1223B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2490 | PS4-08-71SK-1224A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1224A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2491 | PS4-08-71SK-1224B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1224B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2492 | PS4-08-71SK-1225A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1225A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2493 | PS4-08-71SK-1225B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1225B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2494 | PS4-08-71SK-1226A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1226A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2495 | PS4-08-71SK-1226B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1226B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2496 | PS4-08-71SK-1227A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1227A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2497 | PS4-08-71SK-1227B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1227B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2498 | PS4-08-71SK-1228A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1228A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2499 | PS4-08-71SK-1228B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1228B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2500 | PS4-08-71SK-1229-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1229 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2501 | PS4-08-71SK-1230A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1230A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2502 | PS4-08-71SK-1230B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1230B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2503 | PS4-08-71SK-1231-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1231 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2504 | PS4-08-71SK-1232A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1232A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2505 | PS4-08-71SK-1232B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1232B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2506 | PS4-08-71SK-1233A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1233A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2507 | PS4-08-71SK-1233B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1233B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2508 | PS4-08-71SK-1234-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1234 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2509 | PS4-08-71SK-1235-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1235 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2510 | PS4-08-71SK-1236A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1236A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2511 | PS4-08-71SK-1236B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1236B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2512 | PS4-08-71SK-1237-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1237 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2513 | PS4-08-71SK-1238-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1238 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2514 | PS4-08-71SK-1239-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1239 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2515 | PS4-08-71SK-1240-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1240 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2516 | PS4-08-71SK-1241A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1241A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2517 | PS4-08-71SK-1241B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1241B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2518 | PS4-08-71SK-1242A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1242A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2519 | PS4-08-71SK-1242B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1242B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2520 | PS4-08-71SK-1243A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1243A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2521 | PS4-08-71SK-1243B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1243B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2522 | PS4-08-71SK-1244A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1244A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2523 | PS4-08-71SK-1244B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1244B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2524 | PS4-08-71SK-1245A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1245A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2525 | PS4-08-71SK-1245B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1245B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2526 | PS4-08-71SK-1246A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1246A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2527 | PS4-08-71SK-1246B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1246B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2528 | PS4-08-71SK-1247-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1247 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2529 | PS4-08-71SK-1248-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1248 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2530 | PS4-08-71SK-1249A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1249A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2531 | PS4-08-71SK-1249B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1249B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2532 | PS4-08-71SK-1249C-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1249C | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2533 | PS4-08-71SK-1249D-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1249D | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2534 | PS4-08-71SK-1250A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1250A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2535 | PS4-08-71SK-1250B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1250B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2536 | PS4-08-71SK-1501A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1501A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2537 | PS4-08-71SK-1501B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1501B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2538 | PS4-08-71SK-1502A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1502A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2539 | PS4-08-71SK-1502B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1502B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2540 | PS4-08-71SK-1503A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1503A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2541 | PS4-08-71SK-1503B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1503B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2542 | PS4-08-71SK-1504A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1504A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2543 | PS4-08-71SK-1504B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1504B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2544 | PS4-08-71SK-1505-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1505 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2545 | PS4-08-71SK-1506-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1506 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2546 | PS4-08-71SK-1507-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1507 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2547 | PS4-08-71SK-1508-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1508 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2548 | PS4-08-71SK-1509-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1509 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2549 | PS4-08-71SK-1510A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1510A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2550 | PS4-08-71SK-1510B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1510B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2551 | PS4-08-71SK-1511A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1511A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2552 | PS4-08-71SK-1511B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1511B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2553 | PS4-08-71SK-1512-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1512 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2554 | PS4-08-71SK-1513-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1513 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2555 | PS4-08-71SK-1601A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1601A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2556 | PS4-08-71SK-1601B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1601B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2557 | PS4-08-71SK-1602A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1602A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2558 | PS4-08-71SK-1602B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1602B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2559 | PS4-08-71SK-1603A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1603A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2560 | PS4-08-71SK-1603B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1603B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2561 | PS4-08-71SK-1604A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1604A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2562 | PS4-08-71SK-1604B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1604B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2563 | PS4-08-71SK-1605A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1605A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2564 | PS4-08-71SK-1605B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1605B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2565 | PS4-08-71SK-1606-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1606 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2566 | PS4-08-71SK-1607-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1607 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2567 | PS4-08-71SK-1608-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1608 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2568 | PS4-08-71SK-1609-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1609 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2569 | PS4-08-71SK-1610-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1610 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2570 | PS4-08-71SK-1611-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1611 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2571 | PS4-08-71SK-1901-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-71SK-1901 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2572 | PS4-08-71SK-1903A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-71SK-1903A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2573 | PS4-08-71SK-1903B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-71SK-1903B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2574 | PS4-08-71SK-1904A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-71SK-1904A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2575 | PS4-08-71SK-1904B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-71SK-1904B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2576 | PS4-08-71SK-1905A-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-71SK-1905A | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2577 | PS4-08-71SK-1905B-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-71SK-1905B | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00621
T-00621-2578 | PS4-08-85BG-1201-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1201 TO PS4-08-85BG-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2579 | PS4-08-85BG-1202-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1202 TO PS4-08-85BG-1202 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2580 | PS4-08-85BG-1203-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1203 TO PS4-08-85BG-1203 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2581 | PS4-08-85BG-1204-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1205 TO PS4-08-85BG-1204 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2582 | PS4-08-85BG-1501-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1503 TO PS4-08-85BG-1501 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2583 | PS4-08-85BG-1601-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1603 TO PS4-08-85BG-1601 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2584 | PS4-08-85BG-1602-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1605 TO PS4-08-85BG-1602 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2585 | PS4-08-85BG-1603-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1606 TO PS4-08-85BG-1603 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2586 | PS4-08-85BG-1604-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1607 TO PS4-08-85BG-1604 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2587 | PS4-08-85BG-1605-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1608 TO PS4-08-85BG-1605 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2588 | PS4-08-85BG-1901-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1901 TO PS4-08-85BG-1901 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2589 | PS4-08-85BG-1902-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1902 TO PS4-08-85BG-1902 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2590 | PS4-08-85BR-0001-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1501 TO PS4-08-85BR-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering | 2026-07-27 14:47 | PS4-08-85 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2591 | PS4-08-85BR-0002-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1501 TO PS4-08-85BR-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering | 2026-07-27 14:51 | PS4-08-85 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2592 | PS4-08-85BR-0003-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1501 TO PS4-08-85BR-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering | 2026-07-27 14:42 | PS4-08-85 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2593 | PS4-08-85BR-0004-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1501 TO PS4-08-85BR-0004 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering | 2026-07-27 14:44 | PS4-08-85 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2594 | PS4-08-85BR-0005-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1501 TO PS4-08-85BR-0005 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering | 2026-07-27 14:37 | PS4-08-85 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2595 | PS4-08-85BR-0006-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1501 TO PS4-08-85BR-0006 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering | 2026-07-27 14:39 | PS4-08-85 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2596 | PS4-08-85BR-0007-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1501 TO PS4-08-85BR-0007 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering | 2026-07-27 14:56 | PS4-08-85 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2597 | PS4-08-85BR-0008-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1501 TO PS4-08-85BR-0008 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering | 2026-07-27 14:58 | PS4-08-85 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2598 | PS4-08-85BR-0009-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1201 TO PS4-08-85BR-0009 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2599 | PS4-08-85BR-0010-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1202 TO PS4-08-85BR-0010 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2600 | PS4-08-85BR-0011-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-0024 TO PS4-08-85BR-0011 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2601 | PS4-08-85BR-0012-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-0025 TO PS4-08-85BR-0012 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2602 | PS4-08-85BR-1201-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1201 TO PS4-08-85BR-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2603 | PS4-08-85BR-1202-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1201 TO PS4-08-85BR-1202 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2604 | PS4-08-85BR-1203-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1201 TO PS4-08-85BR-1203 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2605 | PS4-08-85BR-1204-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1202 TO PS4-08-85BR-1204 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2606 | PS4-08-85BR-1205-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1201 TO PS4-08-85BR-1205 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2607 | PS4-08-85BR-1206-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1202 TO PS4-08-85BR-1206 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2608 | PS4-08-85BR-1501-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1501 TO PS4-08-85BR-1501 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2609 | PS4-08-85BR-1502-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1501 TO PS4-08-85BR-1502 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2610 | PS4-08-85BR-1601-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1601 TO PS4-08-85BR-1601 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2611 | PS4-08-85BR-1602-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1601 TO PS4-08-85BR-1602 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2612 | PS4-08-85BR-1603-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1601 TO PS4-08-85BR-1603 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2613 | PS4-08-85BR-1604-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1601 TO PS4-08-85BR-1604 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2614 | PS4-08-85BR-1605-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1601 TO PS4-08-85BR-1605 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2615 | PS4-08-85BR-1901-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1901 TO PS4-08-85BR-1901 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2616 | PS4-08-85BR-1902-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1901 TO PS4-08-85BR-1902 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2617 | PS4-08-85BT-0001-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0004 TO PS4-08-85BT-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2618 | PS4-08-85BT-0002-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0004 TO PS4-08-85BT-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2619 | PS4-08-85BT-0003-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0004 TO PS4-08-85BT-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2620 | PS4-08-85BT-0004-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0005 TO PS4-08-85BT-0004 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2621 | PS4-08-85BT-0005-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0005 TO PS4-08-85BT-0005 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2622 | PS4-08-85BT-0006-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0005 TO PS4-08-85BT-0006 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2623 | PS4-08-85BT-0007-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0005 TO PS4-08-85BT-0007 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2624 | PS4-08-85BT-0008-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0007 TO PS4-08-85BT-0008 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2625 | PS4-08-85BT-0009-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0007 TO PS4-08-85BT-0009 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2626 | PS4-08-85BT-0010-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0007 TO PS4-08-85BT-0010 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2627 | PS4-08-85BT-0011-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0007 TO PS4-08-85BT-0011 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2628 | PS4-08-85BT-0012-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0007 TO PS4-08-85BT-0012 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2629 | PS4-08-85BT-0013-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0002 TO PS4-08-85BT-0013 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2630 | PS4-08-85BT-0014-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0002 TO PS4-08-85BT-0014 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2631 | PS4-08-85BT-0015-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0002 TO PS4-08-85BT-0015 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2632 | PS4-08-85BT-0016-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0002 TO PS4-08-85BT-0016 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2633 | PS4-08-85BT-0017-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1501 TO PS4-08-85BT-0017 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering | 2026-07-27 14:23 | PS4-08-85 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2634 | PS4-08-85BT-0017-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-85BT-0017 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering | 2026-07-27 14:25 | PS4-08-85 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2635 | PS4-08-85BT-0018-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0004 TO PS4-08-85BT-0018 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2636 | PS4-08-85BT-0019-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1501 TO PS4-08-85BT-0019 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering | 2026-07-27 14:29 | PS4-08-85 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2637 | PS4-08-85BT-0020-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1501 TO PS4-08-85BT-0020 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2638 | PS4-08-85BT-0021-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1501 TO PS4-08-85BT-0021 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2639 | PS4-08-85BT-0022-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1501 TO PS4-08-85BT-0022 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering | 2026-07-27 14:40 | PS4-08-85 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2640 | PS4-08-85BT-0023-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1501 TO PS4-08-85BT-0023 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering | 2026-07-27 14:54 | PS4-08-85 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2641 | PS4-08-85BT-0024-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0004 TO PS4-08-85BT-0024 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering | 2026-07-27 14:31 | PS4-08-85 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2642 | PS4-08-85BT-0025-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0004 TO PS4-08-85BT-0025 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering | 2026-07-27 14:45 | PS4-08-85 |  |  | Smart Form PLACEHOLDER (DO NOT DELETE) | T | Closed | PS4 - Milestone F | TM-00621 | sridhar, muthu
T-00621-2643 | PS4-08-85BT-0026-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-15CP-0004 TO PS4-08-85BT-0026 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2644 | PS4-08-85BT-0027-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-85BT-0027 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2645 | PS4-08-85BT-0028-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-85BT-0028 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2646 | PS4-08-85BT-1201-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1201 TO PS4-08-85BT-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2647 | PS4-08-85BT-1201-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-85BT-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2648 | PS4-08-85BT-1202-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1201 TO PS4-08-85BT-1202 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2649 | PS4-08-85BT-1202-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-85BT-1202 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2650 | PS4-08-85BT-1203-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1201 TO PS4-08-85BT-1203 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2651 | PS4-08-85BT-1203-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-85BT-1203 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2652 | PS4-08-85BT-1204-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1201 TO PS4-08-85BT-1204 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2653 | PS4-08-85BT-1205-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1201 TO PS4-08-85BT-1205 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2654 | PS4-08-85BT-1205-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-85BT-1205 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2655 | PS4-08-85BT-1501-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1501 TO PS4-08-85BT-1501 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2656 | PS4-08-85BT-1502-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1501 TO PS4-08-85BT-1502 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2657 | PS4-08-85BT-1503-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1501 TO PS4-08-85BT-1503 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2658 | PS4-08-85BT-1503-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-85BT-1503 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2659 | PS4-08-85BT-1601-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1601 TO PS4-08-85BT-1601 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2660 | PS4-08-85BT-1602-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1601 TO PS4-08-85BT-1602 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2661 | PS4-08-85BT-1603-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1601 TO PS4-08-85BT-1603 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2662 | PS4-08-85BT-1603-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-85BT-1603 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2663 | PS4-08-85BT-1604-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1601 TO PS4-08-85BT-1604 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2664 | PS4-08-85BT-1605-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1601 TO PS4-08-85BT-1605 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2665 | PS4-08-85BT-1605-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-85BT-1605 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2666 | PS4-08-85BT-1606-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1601 TO PS4-08-85BT-1606 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2667 | PS4-08-85BT-1606-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-85BT-1606 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2668 | PS4-08-85BT-1607-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1601 TO PS4-08-85BT-1607 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2669 | PS4-08-85BT-1607-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-85BT-1607 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2670 | PS4-08-85BT-1608-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1601 TO PS4-08-85BT-1608 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2671 | PS4-08-85BT-1608-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-85BT-1608 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2672 | PS4-08-85BT-1609-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1601 TO PS4-08-85BT-1609 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2673 | PS4-08-85BT-1610-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1601 TO PS4-08-85BT-1610 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2674 | PS4-08-85BT-1611-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1601 TO PS4-08-85BT-1611 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2675 | PS4-08-85BT-1612-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1601 TO PS4-08-85BT-1612 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2676 | PS4-08-85BT-1613-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1601 TO PS4-08-85BT-1613 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2677 | PS4-08-85BT-1614-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1601 TO PS4-08-85BT-1614 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2678 | PS4-08-85BT-1901-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1901 TO PS4-08-85BT-1901 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2679 | PS4-08-85BT-1901-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-85BT-1901 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2680 | PS4-08-85BT-1902-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1901 TO PS4-08-85BT-1902 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2681 | PS4-08-85BT-1902-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-85BT-1902 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2682 | PS4-08-85BT-1903-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1901 TO PS4-08-85BT-1903 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2683 | PS4-08-85BT-1904-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1901 TO PS4-08-85BT-1904 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2684 | PS4-08-85BT-1905-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1901 TO PS4-08-85BT-1905 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2685 | PS4-08-85BT-1906-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1901 TO PS4-08-85BT-1906 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2686 | PS4-08-85BT-1907-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1901 TO PS4-08-85BT-1907 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2687 | PS4-08-85BT-1908-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1901 TO PS4-08-85BT-1908 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2688 | PS4-08-85BT-1909-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1901 TO PS4-08-85BT-1909 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2689 | PS4-08-85CP-1201-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-85CP-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2690 | PS4-08-85CP-1202-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-85CP-1202 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2691 | PS4-08-85CP-1501-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-85CP-1501 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2692 | PS4-08-85CP-1601-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-85CP-1601 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2693 | PS4-08-85CP-1901-CA01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-85CP-1901 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2694 | PS4-08-85DC-0001-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0017 TO PS4-08-85DC-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2695 | PS4-08-85DC-0002-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0001 TO PS4-08-85DC-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2696 | PS4-08-85DC-0003-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0019 TO PS4-08-85DC-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2697 | PS4-08-85DC-0004-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0002 TO PS4-08-85DC-0004 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2698 | PS4-08-85DC-0005-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0003 TO PS4-08-85DC-0005 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2699 | PS4-08-85DC-0006-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0004 TO PS4-08-85DC-0006 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2700 | PS4-08-85DC-0007-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0005 TO PS4-08-85DC-0007 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2701 | PS4-08-85DC-0008-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0006 TO PS4-08-85DC-0008 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2702 | PS4-08-85DC-0009-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0007 TO PS4-08-85DC-0009 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2703 | PS4-08-85DC-0010-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0008 TO PS4-08-85DC-0010 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2704 | PS4-08-85DC-0011-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0010 TO PS4-08-85DC-0011 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2705 | PS4-08-85DC-0012-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0009 TO PS4-08-85DC-0012 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2706 | PS4-08-85DC-0013-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0012 TO PS4-08-85DC-0013 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2707 | PS4-08-85DC-0014-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0011 TO PS4-08-85DC-0014 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2708 | PS4-08-85DC-0015-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0013 TO PS4-08-85DC-0015 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2709 | PS4-08-85DC-0016-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0014 TO PS4-08-85DC-0016 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2710 | PS4-08-85DC-0017-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0015 TO PS4-08-85DC-0017 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2711 | PS4-08-85DC-0018-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0016 TO PS4-08-85DC-0018 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2712 | PS4-08-85DC-0019-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0024 TO PS4-08-85DC-0019 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2713 | PS4-08-85DC-0021-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0025 TO PS4-08-85DC-0021 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2714 | PS4-08-85DC-0022-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0026 TO PS4-08-85DC-0022 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2715 | PS4-08-85DC-0023-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0018 TO PS4-08-85DC-0023 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2716 | PS4-08-85DC-0024-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0001 TO PS4-08-85DC-0024 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2717 | PS4-08-85DC-0025-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0009 TO PS4-08-85DC-0025 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2718 | PS4-08-85DC-0026-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0024 TO PS4-08-85DC-0026 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2719 | PS4-08-85DC-0027-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0025 TO PS4-08-85DC-0027 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2720 | PS4-08-85DC-0028-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0026 TO PS4-08-85DC-0028 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2721 | PS4-08-85DC-1201-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1201 TO PS4-08-85DC-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2722 | PS4-08-85DC-1202-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1202 TO PS4-08-85DC-1202 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2723 | PS4-08-85DC-1203-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1202 TO PS4-08-85DC-1203 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2724 | PS4-08-85DC-1204-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1203 TO PS4-08-85DC-1204 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2725 | PS4-08-85DC-1205-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1204 TO PS4-08-85DC-1205 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2726 | PS4-08-85DC-1206-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1204 TO PS4-08-85DC-1206 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2727 | PS4-08-85DC-1207-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1205 TO PS4-08-85DC-1207 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2728 | PS4-08-85DC-1501-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1501 TO PS4-08-85DC-1501 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2729 | PS4-08-85DC-1502-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1502 TO PS4-08-85DC-1502 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2730 | PS4-08-85DC-1503-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1503 TO PS4-08-85DC-1503 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2731 | PS4-08-85DC-1601-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1601 TO PS4-08-85DC-1601 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2732 | PS4-08-85DC-1602-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1602 TO PS4-08-85DC-1602 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2733 | PS4-08-85DC-1603-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1603 TO PS4-08-85DC-1603 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2734 | PS4-08-85DC-1604-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1603 TO PS4-08-85DC-1604 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2735 | PS4-08-85DC-1605-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1604 TO PS4-08-85DC-1605 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2736 | PS4-08-85DC-1606-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1604 TO PS4-08-85DC-1606 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2737 | PS4-08-85DC-1607-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1607 TO PS4-08-85DC-1607 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2738 | PS4-08-85DC-1608-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1606 TO PS4-08-85DC-1608 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2739 | PS4-08-85DC-1609-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1606 TO PS4-08-85DC-1609 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2740 | PS4-08-85DC-1610-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1614 TO PS4-08-85DC-1610 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2741 | PS4-08-85DC-1611-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1613 TO PS4-08-85DC-1611 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2742 | PS4-08-85DC-1612-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1613 TO PS4-08-85DC-1612 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2743 | PS4-08-85DC-1613-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1612 TO PS4-08-85DC-1613 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2744 | PS4-08-85DC-1614-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1611 TO PS4-08-85DC-1614 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2745 | PS4-08-85DC-1615-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1610 TO PS4-08-85DC-1615 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2746 | PS4-08-85DC-1616-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1609 TO PS4-08-85DC-1616 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2747 | PS4-08-85DC-1617-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1605 TO PS4-08-85DC-1617 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2748 | PS4-08-85DC-1618-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1608 TO PS4-08-85DC-1618 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2749 | PS4-08-85DC-1901-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1903 TO PS4-08-85DC-1901 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2750 | PS4-08-85DC-1902-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1903 TO PS4-08-85DC-1902 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2751 | PS4-08-85DC-1903-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1904 TO PS4-08-85DC-1903 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2752 | PS4-08-85DC-1904-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1904 TO PS4-08-85DC-1904 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2753 | PS4-08-85DC-1905-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1905 TO PS4-08-85DC-1905 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2754 | PS4-08-85DC-1906-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1905 TO PS4-08-85DC-1906 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2755 | PS4-08-85DC-1907-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1906 TO PS4-08-85DC-1907 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2756 | PS4-08-85DC-1908-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1906 TO PS4-08-85DC-1908 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2757 | PS4-08-85DC-1909-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1907 TO PS4-08-85DC-1909 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2758 | PS4-08-85DC-1910-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1907 TO PS4-08-85DC-1910 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2759 | PS4-08-85DC-1911-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1901 TO PS4-08-85DC-1911 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2760 | PS4-08-85DC-1912-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1902 TO PS4-08-85DC-1912 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2761 | PS4-08-85DC-1913-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1908 TO PS4-08-85DC-1913 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2762 | PS4-08-85DC-1914-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1908 TO PS4-08-85DC-1914 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2763 | PS4-08-85DC-1915-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1908 TO PS4-08-85DC-1915 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2764 | PS4-08-85DC-1916-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1909 TO PS4-08-85DC-1916 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2765 | PS4-08-85ML-0001-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0017 TO PS4-08-85ML-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2766 | PS4-08-85ML-1201-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1201 TO PS4-08-85ML-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2767 | PS4-08-85ML-1202-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1202 TO PS4-08-85ML-1202 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2768 | PS4-08-85ML-1203-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1203 TO PS4-08-85ML-1203 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2769 | PS4-08-85ML-1204-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1205 TO PS4-08-85ML-1204 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2770 | PS4-08-85ML-1501-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1503 TO PS4-08-85ML-1501 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2771 | PS4-08-85ML-1601-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1603 TO PS4-08-85ML-1601 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2772 | PS4-08-85ML-1602-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1605 TO PS4-08-85ML-1602 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2773 | PS4-08-85ML-1603-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1606 TO PS4-08-85ML-1603 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2774 | PS4-08-85ML-1604-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1608 TO PS4-08-85ML-1604 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2775 | PS4-08-85ML-1605-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1607 TO PS4-08-85ML-1605 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2776 | PS4-08-85ML-1901-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1901 TO PS4-08-85ML-1901 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2777 | PS4-08-85ML-1902-CN01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1902 TO PS4-08-85ML-1902 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2778 | PS4-08-85PB-0001-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0017 TO PS4-08-85PB-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2779 | PS4-08-85PB-1201-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1201 TO PS4-08-85PB-1201 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2780 | PS4-08-85PB-1202-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1202 TO PS4-08-85PB-1202 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2781 | PS4-08-85PB-1203-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1203 TO PS4-08-85PB-1203 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2782 | PS4-08-85PB-1204-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1205 TO PS4-08-85PB-1204 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2783 | PS4-08-85PB-1501-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85CP-1501 TO PS4-08-85PB-1501 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2784 | PS4-08-85PB-1601-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1603 TO PS4-08-85PB-1601 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2785 | PS4-08-85PB-1602-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1605 TO PS4-08-85PB-1602 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2786 | PS4-08-85PB-1603-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1606 TO PS4-08-85PB-1603 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2787 | PS4-08-85PB-1604-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1607 TO PS4-08-85PB-1604 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2788 | PS4-08-85PB-1605-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1608 TO PS4-08-85PB-1605 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2789 | PS4-08-85PB-1901-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1901 TO PS4-08-85PB-1901 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2790 | PS4-08-85PB-1902-CJ01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-1902 TO PS4-08-85PB-1902 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2791 | PS4-82-MBA-0001-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0021 TO PS4-82-MBA-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2792 | PS4-82-MBA-0002-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0023 TO PS4-82-MBA-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2793 | PS4-82-MBA-0003-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0020 TO PS4-82-MBA-0003 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2794 | PS4-82-MGV-0002-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0019 TO PS4-82-MGV-0002 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00621-2795 | PS4-82-MTL-0001-CC01 |  |  |  |  | CIX09a - Telecom cable power / Control / Multicore (Both end by EITS) | PCOM - Precommissioning | T | Conformity Check | T - Telecom | Cable FROM PS4-08-85BT-0022 TO PS4-82-MTL-0001 | EACOP | CPP AGI |  |  | 1 |  | 1 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00621
T-00624-0582 | PS4-08-01PA-1201-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-01PA-1201 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0583 | PS4-08-01PA-1501-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-01PA-1501 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-01 - PAGA |  | PS4-08-01 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0584 | PS4-08-05IN-0001-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-05IN-0001 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0585 | PS4-08-05IN-0002-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-15CP-0004 TO PS4-08-05IN-0002 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0586 | PS4-08-05IN-0003-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-05IN-0003 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0587 | PS4-08-05IN-0004-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-05IN-0004 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0588 | PS4-08-05IN-0005-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-05IN-0005 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0589 | PS4-08-12AP-0002-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-12BT-0002 TO PS4-08-12AP-0002 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0590 | PS4-08-12AP-0003-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-12BT-0003 TO PS4-08-12AP-0003 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0591 | PS4-08-12AP-0101-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-12BT-0101 TO PS4-08-12AP-0101 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0592 | PS4-08-12AP-0103-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-12BT-0103 TO PS4-08-12AP-0103 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0593 | PS4-08-12BT-0002-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-12BT-0002 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0594 | PS4-08-12BT-0003-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-12BT-0003 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0595 | PS4-08-12BT-0101-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-12BT-0101 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0596 | PS4-08-12BT-0103-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-12BT-0103 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-12 - Corporate Wireless LAN (SIE) |  | PS4-08-12 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0597 | PS4-08-13CB-1201-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-13CB-1201 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-13 - Safety Data Network (SII SP3 SAF) |  | PS4-08-13 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0598 | PS4-08-13CB-1201-CA02 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-13CB-1201 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-13 - Safety Data Network (SII SP3 SAF) |  | PS4-08-13 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0599 | PS4-08-13CB-1201-CA03 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-13CB-1201 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-13 - Safety Data Network (SII SP3 SAF) |  | PS4-08-13 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0600 | PS4-08-13CB-1201-CA04 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-13CB-1201 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-13 - Safety Data Network (SII SP3 SAF) |  | PS4-08-13 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0601 | PS4-08-13CB-1201-CA05 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-13CB-1201 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-13 - Safety Data Network (SII SP3 SAF) |  | PS4-08-13 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0602 | PS4-08-13CB-1201-CA06 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-13CB-1201 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-13 - Safety Data Network (SII SP3 SAF) |  | PS4-08-13 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0603 | PS4-08-14CB-1201-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-14CB-1201 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-14 - Industrial Data Network (SII SP1) |  | PS4-08-14 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0604 | PS4-08-14CB-1201-CA02 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-14CB-1201 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-14 - Industrial Data Network (SII SP1) |  | PS4-08-14 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0605 | PS4-08-14CB-1201-CA03 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-14CB-1201 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-14 - Industrial Data Network (SII SP1) |  | PS4-08-14 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0606 | PS4-08-14CB-1201-CA04 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-14CB-1201 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-14 - Industrial Data Network (SII SP1) |  | PS4-08-14 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0607 | PS4-08-14CB-1201-CA05 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-14CB-1201 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-14 - Industrial Data Network (SII SP1) |  | PS4-08-14 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0608 | PS4-08-14CB-1201-CA06 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-14CB-1201 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-14 - Industrial Data Network (SII SP1) |  | PS4-08-14 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0609 | PS4-08-52CM-0001-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-52CM-0001 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0610 | PS4-08-52CM-0002-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-52CM-0002 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0611 | PS4-08-52CM-0003-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-52CM-0003 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0612 | PS4-08-52CM-0004-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-52CM-0004 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0613 | PS4-08-52CM-0005-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-52CM-0005 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0614 | PS4-08-52CM-0031-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-15CP-0002 TO PS4-08-52CM-0031 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0615 | PS4-08-52CM-0032-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-15CP-0006 TO PS4-08-52CM-0032 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0616 | PS4-08-52CM-0033-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-15CP-0008 TO PS4-08-52CM-0033 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0617 | PS4-08-52CM-0034-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-52CM-0034 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0618 | PS4-08-52CM-0071-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-15CP-0001 TO PS4-08-52CM-0071 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0619 | PS4-08-52CM-0072-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-15CP-0002 TO PS4-08-52CM-0072 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0620 | PS4-08-52CM-0073-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-15CP-0003 TO PS4-08-52CM-0073 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0621 | PS4-08-52CM-0074-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-15CP-0004 TO PS4-08-52CM-0074 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0622 | PS4-08-52CM-0075-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-15CP-0005 TO PS4-08-52CM-0075 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0623 | PS4-08-52CM-0076-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-15CP-0006 TO PS4-08-52CM-0076 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0624 | PS4-08-52CM-0077-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-15CP-0007 TO PS4-08-52CM-0077 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0625 | PS4-08-52CM-0078-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-15CP-0008 TO PS4-08-52CM-0078 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0626 | PS4-08-52CM-0134-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-52CM-0134 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0627 | PS4-08-52CM-0137-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-52CM-0137 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0628 | PS4-08-52CM-0140-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-52CM-0140 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0629 | PS4-08-52CM-0931-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-52CM-0931 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0630 | PS4-08-52CM-1201-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-52CM-1201 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0631 | PS4-08-52CM-1202-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-52CM-1202 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0632 | PS4-08-52CM-1901-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-52CM-1901 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0633 | PS4-08-52CM-1902-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-52CM-1902 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0634 | PS4-08-52CM-1903-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-52CM-1903 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-52 - Process & Security CCTV |  | PS4-08-52 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0635 | PS4-08-71SK-1201-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1201 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0636 | PS4-08-71SK-1202-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1202 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0637 | PS4-08-71SK-1203-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1203 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0638 | PS4-08-71SK-1204-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1204 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0639 | PS4-08-71SK-1205-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1205 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0640 | PS4-08-71SK-1206A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1206A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0641 | PS4-08-71SK-1206B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1206B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0642 | PS4-08-71SK-1207-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1207 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0643 | PS4-08-71SK-1208-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1208 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0644 | PS4-08-71SK-1209-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1209 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0645 | PS4-08-71SK-1210-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1210 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0646 | PS4-08-71SK-1211-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1211 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0647 | PS4-08-71SK-1212A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1212A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0648 | PS4-08-71SK-1212B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1212B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0649 | PS4-08-71SK-1213-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1213 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0650 | PS4-08-71SK-1214A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1214A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0651 | PS4-08-71SK-1214B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1214B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0652 | PS4-08-71SK-1214C-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1214C | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0653 | PS4-08-71SK-1214D-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1214D | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0654 | PS4-08-71SK-1215A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1215A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0655 | PS4-08-71SK-1215B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1215B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0656 | PS4-08-71SK-1216A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1216A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0657 | PS4-08-71SK-1216B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1216B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0658 | PS4-08-71SK-1217A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1217A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0659 | PS4-08-71SK-1217B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1217B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0660 | PS4-08-71SK-1218A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1218A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0661 | PS4-08-71SK-1218B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1218B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0662 | PS4-08-71SK-1219A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1219A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0663 | PS4-08-71SK-1219B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1219B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0664 | PS4-08-71SK-1220A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1220A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0665 | PS4-08-71SK-1220B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1220B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0666 | PS4-08-71SK-1221A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1221A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0667 | PS4-08-71SK-1221B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1221B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0668 | PS4-08-71SK-1222A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1222A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0669 | PS4-08-71SK-1222B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1222B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0670 | PS4-08-71SK-1223A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1223A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0671 | PS4-08-71SK-1223B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1223B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0672 | PS4-08-71SK-1224A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1224A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0673 | PS4-08-71SK-1224B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1224B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0674 | PS4-08-71SK-1225A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1225A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0675 | PS4-08-71SK-1225B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1225B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0676 | PS4-08-71SK-1226A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1226A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0677 | PS4-08-71SK-1226B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1226B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0678 | PS4-08-71SK-1227A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1227A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0679 | PS4-08-71SK-1227B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1227B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0680 | PS4-08-71SK-1228A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1228A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0681 | PS4-08-71SK-1228B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1228B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0682 | PS4-08-71SK-1229-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1229 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0683 | PS4-08-71SK-1230A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1230A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0684 | PS4-08-71SK-1230B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1230B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0685 | PS4-08-71SK-1231-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1231 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0686 | PS4-08-71SK-1232A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1232A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0687 | PS4-08-71SK-1232B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1232B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0688 | PS4-08-71SK-1233A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1233A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0689 | PS4-08-71SK-1233B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1233B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0690 | PS4-08-71SK-1234-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1234 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0691 | PS4-08-71SK-1235-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1235 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0692 | PS4-08-71SK-1236A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1236A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0693 | PS4-08-71SK-1236B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1236B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0694 | PS4-08-71SK-1237-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1237 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0695 | PS4-08-71SK-1238-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1238 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0696 | PS4-08-71SK-1239-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1239 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0697 | PS4-08-71SK-1240-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1240 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0698 | PS4-08-71SK-1241A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1241A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0699 | PS4-08-71SK-1241B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1241B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0700 | PS4-08-71SK-1242A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1242A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0701 | PS4-08-71SK-1242B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1242B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0702 | PS4-08-71SK-1243A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1243A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0703 | PS4-08-71SK-1243B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1243B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0704 | PS4-08-71SK-1244A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1244A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0705 | PS4-08-71SK-1244B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1244B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0706 | PS4-08-71SK-1245A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1245A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0707 | PS4-08-71SK-1245B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1245B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0708 | PS4-08-71SK-1246A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1246A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0709 | PS4-08-71SK-1246B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1246B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0710 | PS4-08-71SK-1247-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1247 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0711 | PS4-08-71SK-1248-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1248 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0712 | PS4-08-71SK-1249A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1249A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0713 | PS4-08-71SK-1249B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1249B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0714 | PS4-08-71SK-1249C-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1249C | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0715 | PS4-08-71SK-1249D-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1249D | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0716 | PS4-08-71SK-1250A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1250A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0717 | PS4-08-71SK-1250B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-71SK-1250B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0718 | PS4-08-71SK-1501A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1501A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0719 | PS4-08-71SK-1501B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1501B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0720 | PS4-08-71SK-1502A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1502A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0721 | PS4-08-71SK-1502B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1502B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0722 | PS4-08-71SK-1503A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1503A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0723 | PS4-08-71SK-1503B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1503B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0724 | PS4-08-71SK-1504A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1504A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0725 | PS4-08-71SK-1504B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1504B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0726 | PS4-08-71SK-1505-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1505 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0727 | PS4-08-71SK-1506-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1506 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0728 | PS4-08-71SK-1507-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1507 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0729 | PS4-08-71SK-1508-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1508 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0730 | PS4-08-71SK-1509-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1509 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0731 | PS4-08-71SK-1510A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1510A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0732 | PS4-08-71SK-1510B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1510B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0733 | PS4-08-71SK-1511A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1511A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0734 | PS4-08-71SK-1511B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1511B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0735 | PS4-08-71SK-1512-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1512 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0736 | PS4-08-71SK-1513-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-71SK-1513 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0737 | PS4-08-71SK-1601A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1601A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0738 | PS4-08-71SK-1601B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1601B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0739 | PS4-08-71SK-1602A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1602A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0740 | PS4-08-71SK-1602B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1602B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0741 | PS4-08-71SK-1603A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1603A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0742 | PS4-08-71SK-1603B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1603B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0743 | PS4-08-71SK-1604A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1604A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0744 | PS4-08-71SK-1604B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1604B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0745 | PS4-08-71SK-1605A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1605A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0746 | PS4-08-71SK-1605B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1605B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0747 | PS4-08-71SK-1606-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1606 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0748 | PS4-08-71SK-1607-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1607 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0749 | PS4-08-71SK-1608-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1608 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0750 | PS4-08-71SK-1609-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1609 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0751 | PS4-08-71SK-1610-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1610 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0752 | PS4-08-71SK-1611-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-71SK-1611 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0753 | PS4-08-71SK-1901-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-71SK-1901 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0754 | PS4-08-71SK-1903A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-71SK-1903A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0755 | PS4-08-71SK-1903B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-71SK-1903B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0756 | PS4-08-71SK-1904A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-71SK-1904A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0757 | PS4-08-71SK-1904B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-71SK-1904B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0758 | PS4-08-71SK-1905A-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-71SK-1905A | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0759 | PS4-08-71SK-1905B-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-71SK-1905B | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-71 - Structured Cabling (CAT6) |  | PS4-08-71 |  |  |  | T | To be completed | PS4 - Milestone C | TM-00624
T-00624-0760 | PS4-08-85BT-0027-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-85BT-0027 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0761 | PS4-08-85BT-0028-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-85BT-0028 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0762 | PS4-08-85CP-1201-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-85CP-1201 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0763 | PS4-08-85CP-1202-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1201 TO PS4-08-85CP-1202 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0764 | PS4-08-85CP-1501-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1501 TO PS4-08-85CP-1501 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0765 | PS4-08-85CP-1601-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1601 TO PS4-08-85CP-1601 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624
T-00624-0766 | PS4-08-85CP-1901-CA01 |  |  |  |  | TIX01a - RJ45 Cable (Both end by EITS) | PCOM - Precommissioning | T | Static Test | T - Telecom | Cable FROM PS4-08-11CB-1901 TO PS4-08-85CP-1901 | EACOP | CPP AGI |  |  | 6 |  | 6 |  | PS4 - TZA - PS4 - Tanzania | PS4-08-85 - Access Control, POB & e-Mustering |  | PS4-08-85 |  |  |  | T | To be completed | PS4 - Milestone F | TM-00624