## 6 · SUBSYSTEM
PS5 COMPLETION PLATFORM ¦ SUB SYSTEM - 290 subsystem(s)
SID | SUB SYSTEM | PUNCH T | PUNCH CL | PUNCH % | ITR T | ITR CL | ITR % | E CPP CL/T | I CPP CL/T | T CPP CL/T | TOTAL % | RFC SIGNED
PS5-01-01 | PS5-01-01 - Fire Water Jockey Pump A/B | 12 | 2 | 17% | 128 | 38 | 30% | 4/12 | 15/40 | 0/0 | 30% | -
PS5-01-02 | PS5-01-02 - Fire Water Pump A | 7 | 2 | 29% | 114 | 49 | 43% | 2/6 | 10/27 | 0/0 | 43% | -
PS5-01-03 | PS5-01-03 - Fire Water Pump B | 8 | 0 | 0% | 106 | 43 | 41% | 2/6 | 8/23 | 0/0 | 41% | -
PS5-01-04 | PS5-01-04 - Fire Water Pump Mini Flow Recycle | 0 | 0 | 0% | 10 | 3 | 30% | 0/0 | 0/0 | 0/0 | 30% | -
PS5-01-05 | PS5-01-05 - Foam Skid | 14 | 5 | 36% | 60 | 14 | 23% | 3/9 | 2/7 | 0/0 | 23% | -
PS5-01-06 | PS5-01-06 - Foam Concentrate Distribution | 2 | 0 | 0% | 10 | 5 | 50% | 0/0 | 0/0 | 0/0 | 50% | -
PS5-01-07 | PS5-01-07 - Fire Water Ring Main & Distribution | 0 | 0 | 0% | 151 | 62 | 41% | 0/0 | 2/16 | 0/0 | 41% | -
PS5-01-08 | PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | 5 | 2 | 40% | 75 | 22 | 29% | 1/3 | 3/7 | 0/0 | 29% | -
PS5-01-09 | PS5-01-09 - Inergen for EITS Building | 6 | 5 | 83% | 218 | 217 | 100% | 0/0 | 0/0 | 0/0 | 100% | 2026-08-08
PS5-01-10 | PS5-01-10 - Water Mist Package | 13 | 1 | 8% | 151 | 51 | 34% | 1/5 | 5/44 | 0/0 | 34% | -
PS5-01-11 | PS5-01-11 - Inergen for Power Gen Building | 5 | 0 | 0% | 116 | 3 | 3% | 2/7 | 0/74 | 0/0 | 3% | -
PS5-02-01 | PS5-02-01 - Miscellaneous Safety equipment | 4 | 1 | 25% | 75 | 8 | 11% | 2/4 | 0/0 | 0/0 | 11% | -
PS5-02-02 | PS5-02-02 - Portable Fire Fighting Equipments | 2 | 0 | 0% | 85 | 7 | 8% | 0/0 | 0/0 | 0/0 | 8% | -
PS5-03-01 | PS5-03-01 - FZ-01 - Process Area | 0 | 0 | 0% | 223 | 40 | 18% | 0/8 | 40/143 | 0/0 | 18% | -
PS5-03-03 | PS5-03-03 - FZ-03 - Buildings Area | 0 | 0 | 0% | 26 | 1 | 4% | 0/0 | 1/16 | 0/0 | 4% | -
PS5-03-04 | PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | 0 | 0 | 0% | 53 | 13 | 25% | 0/1 | 13/33 | 0/0 | 25% | -
PS5-03-06 | PS5-03-06 - FZ-06 - Transformer Area | 1 | 1 | 100% | 86 | 15 | 17% | 0/0 | 15/62 | 0/0 | 17% | -
PS5-03-07 | PS5-03-07 - FZ-07 - Pretreatment Area | 0 | 0 | 0% | 34 | 1 | 3% | 0/0 | 1/23 | 0/0 | 3% | -
PS5-03-08 | PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | 0 | 0 | 0% | 73 | 9 | 12% | 0/0 | 9/47 | 0/0 | 12% | -
PS5-03-09 | PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | 1 | 0 | 0% | 78 | 32 | 41% | 0/0 | 31/62 | 0/0 | 41% | -
PS5-03-10 | PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | 0 | 0 | 0% | 81 | 10 | 12% | 0/0 | 10/64 | 0/0 | 12% | -
PS5-03-11 | PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | 0 | 0 | 0% | 81 | 2 | 2% | 0/0 | 2/64 | 0/0 | 2% | -
PS5-03-12 | PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | 0 | 0 | 0% | 46 | 2 | 4% | 0/0 | 2/35 | 0/0 | 4% | -
PS5-03-13 | PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | 0 | 0 | 0% | 18 | 0 | 0% | 0/0 | 0/12 | 0/0 | 0% | -
PS5-03-14 | PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 8 | 0 | 0% | 105 | 22 | 21% | 3/6 | 14/68 | 1/2 | 21% | -
PS5-03-15 | PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1 | 0 | 0 | 0% | 11 | 0 | 0% | 0/0 | 0/9 | 0/0 | 0% | -
PS5-03-16 | PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2 | 0 | 0 | 0% | 11 | 0 | 0% | 0/0 | 0/9 | 0/0 | 0% | -
PS5-03-17 | PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3 | 0 | 0 | 0% | 11 | 0 | 0% | 0/0 | 0/9 | 0/0 | 0% | -
PS5-03-18 | PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4 | 0 | 0 | 0% | 11 | 0 | 0% | 0/0 | 0/9 | 0/0 | 0% | -
PS5-03-19 | PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | 0 | 0 | 0% | 11 | 0 | 0% | 0/0 | 0/9 | 0/0 | 0% | -
PS5-03-20 | PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | 8 | 0 | 0% | 11 | 9 | 82% | 0/0 | 5/5 | 0/0 | 82% | 2026-08-07
PS5-03-21 | PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit | 0 | 0 | 0% | 11 | 0 | 0% | 0/0 | 0/9 | 0/0 | 0% | -
PS5-03-22 | PS5-03-22 - FZ-G1 - Guard House | 0 | 0 | 0% | 22 | 0 | 0% | 0/2 | 0/9 | 0/0 | 0% | -
PS5-03-23 | PS5-03-23 - FZ-E1 to E3 - EITS Building | 2 | 0 | 0% | 96 | 95 | 99% | 0/0 | 0/0 | 0/0 | 99% | -
PS5-03-24 | PS5-03-24 - FZ - Office and Facilities Building | 0 | 0 | 0% | 131 | 0 | 0% | 0/0 | 0/120 | 0/0 | 0% | -
PS5-03-25 | PS5-03-25 - FZ - Workshop & Warehouse | 0 | 0 | 0% | 131 | 0 | 0% | 0/0 | 0/120 | 0/0 | 0% | -
PS5-04-01 | PS5-04-01 - Office Building PCS System | 0 | 0 | 0% | 3 | 0 | 0% | 0/0 | 0/0 | 0/0 | 0% | -
PS5-04-02 | PS5-04-02 - Office Building SIS/FGS System | 0 | 0 | 0% | 79 | 0 | 0% | 0/0 | 0/9 | 0/0 | 0% | -
PS5-04-03 | PS5-04-03 - 33kV ICSS System | 2 | 1 | 50% | 83 | 77 | 93% | 0/0 | 0/0 | 0/0 | 93% | -
PS5-04-04 | PS5-04-04 - 33kV PCS System | 37 | 27 | 73% | 403 | 382 | 95% | 0/0 | 0/0 | 0/0 | 95% | -
PS5-04-05 | PS5-04-05 - 33kV SIS/FGS System | 27 | 25 | 93% | 472 | 416 | 88% | 0/0 | 0/0 | 0/0 | 88% | -
PS5-05-01 | PS5-05-01 - Emergency Diesel Generator Package | 75 | 69 | 92% | 128 | 113 | 88% | 70/70 | 36/36 | 0/0 | 88% | PARTIAL(22-08-2026)
PS5-05-02 | PS5-05-02 - Emergency Diesel Generator Package (UCP) | 18 | 0 | 0% | 72 | 62 | 86% | 51/51 | 2/2 | 0/0 | 86% | 2026-08-22
PS5-06-01 | PS5-06-01 - AC UPS - EITS Building | 20 | 17 | 85% | 185 | 129 | 70% | 0/0 | 0/0 | 0/0 | 70% | -
PS5-06-02 | PS5-06-02 - AC UPS - Power Generator Building | 24 | 17 | 71% | 97 | 70 | 72% | 60/60 | 2/2 | 0/0 | 72% | COMPLETE
PS5-06-03 | PS5-06-03 - AC UPS - Office & Facilities Building | 0 | 0 | 0% | 9 | 0 | 0% | 0/8 | 0/0 | 0/0 | 0% | -
PS5-06-04 | PS5-06-04 - AC UPS - Guard House | 0 | 0 | 0% | 4 | 0 | 0% | 0/2 | 0/0 | 0/0 | 0% | -
PS5-06-05 | PS5-06-05 - AC UPS - Workshop & Warehouse | 0 | 0 | 0% | 7 | 0 | 0% | 0/6 | 0/0 | 0/0 | 0% | -
PS5-08-01 | PS5-08-01 - PAGA | 8 | 0 | 0% | 799 | 60 | 8% | 0/0 | 0/0 | 12/230 | 8% | -
PS5-08-03 | PS5-08-03 - Telephone | 0 | 0 | 0% | 161 | 4 | 2% | 0/0 | 0/0 | 2/18 | 2% | -
PS5-08-04 | PS5-08-04 - Hotline | 0 | 0 | 0% | 6 | 0 | 0% | 0/0 | 0/0 | 0/0 | 0% | -
PS5-08-07 | PS5-08-07 - Multi-Channel Voice Recorder | 0 | 0 | 0% | 4 | 0 | 0% | 0/0 | 0/0 | 0/0 | 0% | -
PS5-08-11 | PS5-08-11 - Corporate LAN (SIE) | 1 | 0 | 0% | 88 | 55 | 62% | 2/8 | 0/0 | 0/0 | 62% | -
PS5-08-12 | PS5-08-12 - Corporate Wireless LAN (SIE) | 0 | 0 | 0% | 155 | 6 | 4% | 0/0 | 0/0 | 0/34 | 4% | -
PS5-08-13 | PS5-08-13 - Safety Data Network (SII SP3 SAF) | 3 | 2 | 67% | 98 | 69 | 70% | 0/0 | 0/0 | 0/13 | 70% | -
PS5-08-14 | PS5-08-14 - Industrial Data Network (SII SP1) | 0 | 0 | 0% | 16 | 0 | 0% | 0/0 | 0/0 | 0/12 | 0% | -
PS5-08-15 | PS5-08-15 - Security Data Network (SII SP3 SEC) | 3 | 1 | 33% | 119 | 59 | 50% | 0/0 | 0/0 | 0/9 | 50% | -
PS5-08-23 | PS5-08-23 - VHF Trunk Radio System | 4 | 0 | 0% | 103 | 12 | 12% | 0/0 | 0/0 | 0/11 | 12% | -
PS5-08-34 | PS5-08-34 - Satphone | 0 | 0 | 0% | 20 | 0 | 0% | 0/0 | 0/0 | 0/4 | 0% | -
PS5-08-35 | PS5-08-35 - Optical Transport Network | 1 | 0 | 0% | 61 | 49 | 80% | 0/0 | 0/0 | 0/0 | 80% | -
PS5-08-36 | PS5-08-36 - Pipeline FO Cable & EPRS | 0 | 0 | 0% | 6 | 0 | 0% | 0/0 | 0/0 | 0/2 | 0% | -
PS5-08-51 | PS5-08-51 - Entertainment | 0 | 0 | 0% | 60 | 0 | 0% | 0/0 | 0/0 | 0/18 | 0% | -
PS5-08-52 | PS5-08-52 - Process & Security CCTV | 0 | 0 | 0% | 279 | 27 | 10% | 0/1 | 0/0 | 0/73 | 10% | -
PS5-08-55 | PS5-08-55 - Videoconference | 0 | 0 | 0% | 5 | 0 | 0% | 0/0 | 0/0 | 0/0 | 0% | -
PS5-08-61 | PS5-08-61 - Meteocean | 0 | 0 | 0% | 36 | 0 | 0% | 0/0 | 0/0 | 0/10 | 0% | -
PS5-08-71 | PS5-08-71 - Structured Cabling (CAT6) | 0 | 0 | 0% | 412 | 36 | 9% | 0/0 | 0/0 | 0/250 | 9% | -
PS5-08-72 | PS5-08-72 - Structured Cabling (FO) | 0 | 0 | 0% | 16 | 4 | 25% | 0/0 | 0/0 | 0/6 | 25% | -
PS5-08-81 | PS5-08-81 - Guard tour | 0 | 0 | 0% | 12 | 0 | 0% | 0/0 | 0/0 | 0/0 | 0% | -
PS5-08-82 | PS5-08-82 - Key Management | 0 | 0 | 0% | 6 | 0 | 0% | 0/0 | 0/0 | 0/0 | 0% | -
PS5-08-83 | PS5-08-83 - Perimeter & Pipeline intrusion detection system | 0 | 0 | 0% | 9 | 0 | 0% | 0/0 | 0/0 | 0/2 | 0% | -
PS5-08-85 | PS5-08-85 - Access Control, POB & e-Mustering | 1 | 1 | 100% | 796 | 97 | 12% | 0/6 | 0/0 | 25/243 | 12% | -
PS5-08-86 | PS5-08-86 - Integrated Security Management System | 0 | 0 | 0% | 16 | 0 | 0% | 0/0 | 0/0 | 0/0 | 0% | -
PS5-08-92 | PS5-08-92 - Telecom Mast | 0 | 0 | 0% | 2 | 0 | 0% | 0/0 | 0/0 | 0/0 | 0% | -
PS5-08-93 | PS5-08-93 - Telecom Monitoring System | 0 | 0 | 0% | 6 | 2 | 33% | 0/0 | 0/0 | 0/1 | 33% | -
PS5-09-01 | PS5-09-01 - HVAC for Office and Facilities building | 0 | 0 | 0% | 60 | 0 | 0% | 0/0 | 0/10 | 0/0 | 0% | -
PS5-09-02 | PS5-09-02 - HVAC for Guard House | 0 | 0 | 0% | 6 | 0 | 0% | 0/4 | 0/0 | 0/0 | 0% | -
PS5-09-03 | PS5-09-03 - HVAC for Generator Building | 3 | 1 | 33% | 1137 | 19 | 2% | 17/380 | 0/620 | 0/4 | 2% | -
PS5-09-04 | PS5-09-04 - HVAC for Workshop & Warehouse | 0 | 0 | 0% | 42 | 0 | 0% | 0/0 | 0/8 | 0/0 | 0% | -
PS5-09-05 | PS5-09-05 - HVAC for EITS Building | 25 | 14 | 56% | 294 | 276 | 94% | 0/0 | 0/0 | 0/0 | 94% | PARTIAL
PS5-0H-01 | PS5-0H-01 - HIPPS | 4 | 1 | 25% | 28 | 20 | 71% | 0/0 | 0/0 | 0/0 | 71% | -
PS5-25-01 | PS5-25-01 - Export Pipeline Pig Receiver | 9 | 4 | 44% | 191 | 66 | 35% | 7/15 | 25/84 | 0/0 | 35% | -
PS5-25-02 | PS5-25-02 - Crude Oil Export Pump A | 79 | 15 | 19% | 365 | 136 | 37% | 63/95 | 24/95 | 0/0 | 37% | -
PS5-25-03 | PS5-25-03 - Crude Oil Export Pump B | 70 | 15 | 21% | 337 | 116 | 34% | 63/92 | 23/95 | 0/0 | 34% | -
PS5-25-04 | PS5-25-04 - Crude Oil Export Pump C | 70 | 16 | 23% | 337 | 110 | 33% | 63/92 | 17/95 | 0/0 | 33% | -
PS5-25-05 | PS5-25-05 - Crude Oil Export Pumps Bypass | 2 | 2 | 100% | 61 | 17 | 28% | 3/6 | 10/33 | 0/0 | 28% | -
PS5-25-06 | PS5-25-06 - Crude Oil Export Pumps Discharge | 1 | 0 | 0% | 73 | 21 | 29% | 2/5 | 8/32 | 0/0 | 29% | -
PS5-25-07 | PS5-25-07 - Export Pipeline Pig Launcher | 9 | 3 | 33% | 175 | 52 | 30% | 6/12 | 15/73 | 0/0 | 30% | -
PS5-28-01 | PS5-28-01 - Closed Drain Header 1 | 0 | 0 | 0% | 19 | 9 | 47% | 0/0 | 0/0 | 0/0 | 47% | -
PS5-28-02 | PS5-28-02 - Closed Drain Header 2 | 0 | 0 | 0% | 20 | 8 | 40% | 0/0 | 0/0 | 0/0 | 40% | -
PS5-28-03 | PS5-28-03 - Closed Drain Drum and Pump 01 | 12 | 3 | 25% | 139 | 59 | 42% | 1/10 | 7/35 | 0/0 | 42% | -
PS5-28-04 | PS5-28-04 - Closed Drain Drum and Pump 02 | 11 | 2 | 18% | 146 | 55 | 38% | 3/14 | 11/38 | 0/0 | 38% | -
PS5-28-05 | PS5-28-05 - HP Relief Header | 0 | 0 | 0% | 17 | 4 | 24% | 0/0 | 0/2 | 0/0 | 24% | -
PS5-28-06 | PS5-28-06 - Relief Drum and Pump | 10 | 2 | 20% | 87 | 35 | 40% | 0/4 | 3/20 | 0/0 | 40% | -
PS5-28-07 | PS5-28-07 - Open Drains (OD2) | 7 | 0 | 0% | 286 | 174 | 61% | 1/2 | 0/3 | 0/0 | 61% | -
PS5-28-08 | PS5-28-08 - Open Drain Sump and Pumps | 3 | 0 | 0% | 102 | 27 | 26% | 0/14 | 2/18 | 0/0 | 26% | -
PS5-28-09 | PS5-28-09 - Observation Basin | 1 | 0 | 0% | 15 | 9 | 60% | 0/0 | 0/0 | 0/0 | 60% | -
PS5-28-10 | PS5-28-10 - Oil Skimmer Package | 5 | 0 | 0% | 20 | 1 | 5% | 0/8 | 0/1 | 0/0 | 5% | -
PS5-28-11 | PS5-28-11 - Open Drain Interceptor | 4 | 0 | 0% | 24 | 6 | 25% | 1/2 | 0/2 | 0/0 | 25% | -
PS5-28-12 | PS5-28-12 - Open Drains (OD3) | 1 | 0 | 0% | 44 | 27 | 61% | 0/0 | 0/0 | 0/0 | 61% | -
PS5-28-13 | PS5-28-13 - Seal Oil Drain Drum & Pump A | 2 | 1 | 50% | 91 | 30 | 33% | 1/6 | 3/24 | 0/0 | 33% | -
PS5-28-14 | PS5-28-14 - Seal Oil Drain Drum & Pump B | 2 | 1 | 50% | 91 | 30 | 33% | 1/6 | 3/24 | 0/0 | 33% | -
PS5-28-15 | PS5-28-15 - Seal Oil Drain Drum & Pump C | 2 | 1 | 50% | 91 | 30 | 33% | 1/6 | 3/24 | 0/0 | 33% | -
PS5-28-16 | PS5-28-16 - LP Relief Header | 0 | 0 | 0% | 17 | 5 | 29% | 0/0 | 0/2 | 0/0 | 29% | -
PS5-28-17 | PS5-28-17 - Reinjection Pump | 14 | 4 | 29% | 125 | 38 | 30% | 4/16 | 11/37 | 0/0 | 30% | -
PS5-50-01 | PS5-50-01 - Water Well Submersible Pumps (3100) | 0 | 0 | 0% | 42 | 10 | 24% | 1/5 | 0/7 | 0/0 | 24% | -
PS5-50-02 | PS5-50-02 - Water Well Submersible Pumps (3200) | 0 | 0 | 0% | 42 | 10 | 24% | 1/5 | 0/7 | 0/0 | 24% | -
PS5-50-03 | PS5-50-03 - Water Pre-Treatment Package | 0 | 0 | 0% | 31 | 7 | 23% | 0/1 | 1/7 | 0/0 | 23% | -
PS5-53-01 | PS5-53-01 - Utility Water / Storage Tank | 10 | 8 | 80% | 58 | 24 | 41% | 1/6 | 2/10 | 0/0 | 41% | -
PS5-53-02 | PS5-53-02 - Water Distribution Pump A/B | 5 | 0 | 0% | 47 | 11 | 23% | 2/8 | 2/7 | 0/0 | 23% | -
PS5-53-03 | PS5-53-03 - Water Softener Package | 0 | 0 | 0% | 26 | 5 | 19% | 0/1 | 0/1 | 0/0 | 19% | -
PS5-53-04 | PS5-53-04 - Water Treatment Purification Package | 0 | 0 | 0% | 31 | 0 | 0% | 0/4 | 0/5 | 0/0 | 0% | -
PS5-53-05 | PS5-53-05 - Water Distribution Header | 0 | 0 | 0% | 61 | 40 | 66% | 0/0 | 0/0 | 0/0 | 66% | -
PS5-53-06 | PS5-53-06 - Water Distribution Consumers | 0 | 0 | 0% | 42 | 26 | 62% | 0/0 | 0/0 | 0/0 | 62% | -
PS5-60-01 | PS5-60-01 - Power Generation Package A | 86 | 19 | 22% | 246 | 188 | 76% | 91/93 | 67/67 | 0/0 | 76% | PARTIAL
PS5-60-02 | PS5-60-02 - Power Gen Package A (UCP) | 30 | 1 | 3% | 64 | 50 | 78% | 6/6 | 38/38 | 0/0 | 78% | COMPLETE
PS5-60-03 | PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 10 | 0 | 0% | 35 | 17 | 49% | 14/18 | 2/4 | 1/2 | 49% | PARTIAL
PS5-60-04 | PS5-60-04 - Power Generation Package B | 51 | 16 | 31% | 215 | 165 | 77% | 85/89 | 50/50 | 0/0 | 77% | PARTIAL
PS5-60-05 | PS5-60-05 - Power Gen Package B (UCP) | 22 | 0 | 0% | 73 | 52 | 71% | 6/6 | 38/38 | 4/8 | 71% | PARTIAL
PS5-60-06 | PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 12 | 0 | 0% | 33 | 16 | 48% | 13/16 | 2/4 | 1/2 | 48% | -
PS5-60-07 | PS5-60-07 - Power Generation Package C | 41 | 16 | 39% | 214 | 127 | 59% | 72/89 | 26/50 | 0/0 | 59% | -
PS5-60-08 | PS5-60-08 - Power Gen Package C (UCP) | 0 | 0 | 0% | 73 | 25 | 34% | 5/6 | 16/38 | 4/8 | 34% | -
PS5-60-09 | PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | 0 | 0 | 0% | 35 | 11 | 31% | 8/18 | 2/4 | 1/2 | 31% | -
PS5-60-10 | PS5-60-10 - Power Generation Package D | 41 | 17 | 41% | 247 | 140 | 57% | 71/93 | 33/63 | 6/12 | 57% | -
PS5-60-11 | PS5-60-11 - Power Gen Package D (UCP) | 0 | 0 | 0% | 73 | 25 | 34% | 5/6 | 16/38 | 4/8 | 34% | -
PS5-60-12 | PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | 0 | 0 | 0% | 33 | 16 | 48% | 13/16 | 2/4 | 1/2 | 48% | PARTIAL
PS5-60-13 | PS5-60-13 - Power Generation Package E | 38 | 7 | 18% | 214 | 89 | 42% | 45/89 | 16/50 | 0/0 | 42% | -
PS5-60-14 | PS5-60-14 - Power Gen Package E (UCP) | 0 | 0 | 0% | 73 | 15 | 21% | 3/6 | 8/38 | 4/8 | 21% | -
PS5-60-15 | PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | 0 | 0 | 0% | 35 | 10 | 29% | 7/18 | 2/4 | 1/2 | 29% | -
PS5-60-16 | PS5-60-16 - Power Generation Package F | 40 | 5 | 12% | 247 | 101 | 41% | 45/93 | 21/63 | 6/12 | 41% | -
PS5-60-17 | PS5-60-17 - Power Gen Package F (UCP) | 0 | 0 | 0% | 73 | 20 | 27% | 3/6 | 13/38 | 4/8 | 27% | -
PS5-60-18 | PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | 0 | 0 | 0% | 33 | 5 | 15% | 2/16 | 2/4 | 1/2 | 15% | -
PS5-60-19 | PS5-60-19 - Power Generation Package G | 40 | 5 | 12% | 215 | 85 | 40% | 44/89 | 13/50 | 0/0 | 40% | -
PS5-60-20 | PS5-60-20 - Power Gen Package G (UCP) | 0 | 0 | 0% | 71 | 18 | 25% | 3/6 | 12/38 | 3/6 | 25% | -
PS5-60-21 | PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | 0 | 0 | 0% | 35 | 7 | 20% | 4/18 | 2/4 | 1/2 | 20% | -
PS5-60-22 | PS5-60-22 - Power Gen Master UCP | 11 | 0 | 0% | 166 | 72 | 43% | 39/57 | 27/48 | 6/12 | 43% | -
PS5-60-23 | PS5-60-23 - Instrument Air Distribution lines | 5 | 2 | 40% | 11 | 7 | 64% | 0/0 | 0/0 | 0/0 | 64% | -
PS5-60-24 | PS5-60-24 - Cooling Water Tank & Pump | 18 | 0 | 0% | 73 | 55 | 75% | 4/4 | 5/8 | 0/0 | 75% | -
PS5-60-25 | PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | 15 | 1 | 7% | 68 | 50 | 74% | 4/4 | 5/8 | 0/0 | 74% | -
PS5-60-26 | PS5-60-26 - Instrument Air Compressor Skid | 15 | 5 | 33% | 43 | 28 | 65% | 9/9 | 3/3 | 0/0 | 65% | COMPLETE
PS5-60-27 | PS5-60-27 - Compressed Air Starting Skid | 21 | 8 | 38% | 42 | 25 | 60% | 7/7 | 3/3 | 0/0 | 60% | PARTIAL
PS5-60-28 | PS5-60-28 - Air Receiver A & Air Regulator A | 6 | 2 | 33% | 17 | 12 | 71% | 0/0 | 4/4 | 0/0 | 71% | PARTIAL
PS5-60-29 | PS5-60-29 - Air Receiver B & Air Regulator B | 6 | 3 | 50% | 17 | 12 | 71% | 0/0 | 4/4 | 0/0 | 71% | PARTIAL
PS5-60-30 | PS5-60-30 - Air Receiver C & Air Regulator C | 6 | 3 | 50% | 17 | 12 | 71% | 0/0 | 4/4 | 0/0 | 71% | -
PS5-60-31 | PS5-60-31 - Air Receiver D & Air Regulator D | 6 | 4 | 67% | 17 | 12 | 71% | 0/0 | 4/4 | 0/0 | 71% | -
PS5-60-32 | PS5-60-32 - Air Receiver E & Air Regulator E | 2 | 1 | 50% | 17 | 6 | 35% | 0/0 | 1/4 | 0/0 | 35% | -
PS5-60-33 | PS5-60-33 - Air Receiver F & Air Regulator F | 2 | 1 | 50% | 17 | 6 | 35% | 0/0 | 1/4 | 0/0 | 35% | -
PS5-60-34 | PS5-60-34 - Air Receiver G & Air Regulator G | 5 | 1 | 20% | 17 | 7 | 41% | 0/0 | 1/4 | 0/0 | 41% | -
PS5-60-35 | PS5-60-35 - Injector Tip Cooling Module A | 15 | 4 | 27% | 47 | 34 | 72% | 9/9 | 3/3 | 0/0 | 72% | COMPLETE
PS5-60-36 | PS5-60-36 - Injector Tip Cooling Module B | 14 | 4 | 29% | 42 | 34 | 81% | 9/9 | 3/3 | 0/0 | 81% | COMPLETE
PS5-60-37 | PS5-60-37 - Injector Tip Cooling Module C | 11 | 6 | 55% | 43 | 30 | 70% | 6/9 | 3/3 | 0/0 | 70% | -
PS5-60-38 | PS5-60-38 - Injector Tip Cooling Module D | 13 | 8 | 62% | 43 | 30 | 70% | 6/9 | 3/3 | 0/0 | 70% | -
PS5-60-39 | PS5-60-39 - Injector Tip Cooling Module E | 6 | 1 | 17% | 42 | 21 | 50% | 3/9 | 0/3 | 0/0 | 50% | -
PS5-60-40 | PS5-60-40 - Injector Tip Cooling Module F | 4 | 2 | 50% | 43 | 21 | 49% | 3/9 | 0/3 | 0/0 | 49% | -
PS5-60-41 | PS5-60-41 - Injector Tip Cooling Module G | 6 | 4 | 67% | 43 | 19 | 44% | 3/9 | 0/3 | 0/0 | 44% | -
PS5-60-42 | PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 11 | 4 | 36% | 35 | 29 | 83% | 3/3 | 3/3 | 0/0 | 83% | COMPLETE
PS5-60-43 | PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 12 | 5 | 42% | 34 | 29 | 85% | 3/3 | 3/3 | 0/0 | 85% | COMPLETE
PS5-60-44 | PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | 8 | 4 | 50% | 34 | 24 | 71% | 2/3 | 2/3 | 0/0 | 71% | -
PS5-60-45 | PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | 7 | 3 | 43% | 34 | 24 | 71% | 2/3 | 2/3 | 0/0 | 71% | -
PS5-60-46 | PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | 4 | 1 | 25% | 34 | 20 | 59% | 1/3 | 1/3 | 0/0 | 59% | -
PS5-60-47 | PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | 3 | 1 | 33% | 34 | 20 | 59% | 1/3 | 1/3 | 0/0 | 59% | -
PS5-60-48 | PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | 3 | 1 | 33% | 34 | 19 | 56% | 1/3 | 1/3 | 0/0 | 56% | -
PS5-60-49 | PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 13 | 4 | 31% | 44 | 33 | 75% | 5/5 | 11/11 | 1/2 | 75% | PARTIAL
PS5-60-50 | PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 11 | 5 | 45% | 44 | 33 | 75% | 5/5 | 11/11 | 1/2 | 75% | PARTIAL
PS5-60-51 | PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | 7 | 5 | 71% | 44 | 25 | 57% | 3/5 | 6/11 | 1/2 | 57% | -
PS5-60-52 | PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | 8 | 3 | 38% | 44 | 25 | 57% | 3/5 | 6/11 | 1/2 | 57% | -
PS5-60-53 | PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | 6 | 1 | 17% | 44 | 21 | 48% | 2/5 | 5/11 | 0/2 | 48% | -
PS5-60-54 | PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | 6 | 1 | 17% | 44 | 21 | 48% | 2/5 | 5/11 | 0/2 | 48% | -
PS5-60-55 | PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | 1 | 1 | 100% | 44 | 18 | 41% | 2/5 | 5/11 | 0/2 | 41% | -
PS5-60-56 | PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 38 | 6 | 16% | 76 | 62 | 82% | 38/38 | 6/8 | 0/0 | 82% | PARTIAL
PS5-60-57 | PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | 6 | 0 | 0% | 41 | 30 | 73% | 7/10 | 22/22 | 1/2 | 73% | PARTIAL
PS5-60-58 | PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 36 | 3 | 8% | 73 | 63 | 86% | 38/38 | 6/8 | 0/0 | 86% | PARTIAL
PS5-60-59 | PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | 9 | 0 | 0% | 41 | 30 | 73% | 7/10 | 22/22 | 1/2 | 73% | PARTIAL
PS5-60-60 | PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 11 | 5 | 45% | 73 | 38 | 52% | 16/38 | 5/8 | 0/0 | 52% | -
PS5-60-61 | PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | 0 | 0 | 0% | 41 | 25 | 61% | 6/10 | 18/22 | 1/2 | 61% | -
PS5-60-62 | PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 11 | 3 | 27% | 73 | 38 | 52% | 17/38 | 4/8 | 0/0 | 52% | -
PS5-60-63 | PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | 0 | 0 | 0% | 41 | 13 | 32% | 4/10 | 8/22 | 1/2 | 32% | -
PS5-60-64 | PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | 10 | 1 | 10% | 73 | 30 | 41% | 11/38 | 2/8 | 0/0 | 41% | -
PS5-60-65 | PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | 0 | 0 | 0% | 41 | 9 | 22% | 3/10 | 6/22 | 0/2 | 22% | -
PS5-60-66 | PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | 12 | 1 | 8% | 73 | 27 | 37% | 8/38 | 2/8 | 0/0 | 37% | -
PS5-60-67 | PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | 0 | 0 | 0% | 41 | 9 | 22% | 3/10 | 6/22 | 0/2 | 22% | -
PS5-60-68 | PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | 6 | 1 | 17% | 73 | 24 | 33% | 8/38 | 2/8 | 0/0 | 33% | -
PS5-60-69 | PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | 0 | 0 | 0% | 41 | 9 | 22% | 3/10 | 6/22 | 0/2 | 22% | -
PS5-60-70 | PS5-60-70 - Engine A Cooling system | 61 | 26 | 43% | 90 | 69 | 77% | 8/8 | 16/16 | 0/0 | 77% | PARTIAL
PS5-60-71 | PS5-60-71 - Engine B Cooling system | 61 | 31 | 51% | 78 | 69 | 88% | 8/8 | 16/16 | 0/0 | 88% | PARTIAL
PS5-60-72 | PS5-60-72 - Engine C Cooling system | 47 | 24 | 51% | 78 | 58 | 74% | 6/8 | 8/16 | 0/0 | 74% | -
PS5-60-73 | PS5-60-73 - Engine D Cooling system | 50 | 13 | 26% | 78 | 58 | 74% | 6/8 | 8/16 | 0/0 | 74% | -
PS5-60-74 | PS5-60-74 - Engine E Cooling system | 32 | 8 | 25% | 78 | 47 | 60% | 2/8 | 4/16 | 0/0 | 60% | -
PS5-60-75 | PS5-60-75 - Engine F Cooling system | 33 | 8 | 24% | 78 | 46 | 59% | 2/8 | 4/16 | 0/0 | 59% | -
PS5-60-76 | PS5-60-76 - Engine G Cooling system | 14 | 6 | 43% | 78 | 32 | 41% | 2/8 | 0/16 | 0/0 | 41% | -
PS5-61-01 | PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | 88 | 6 | 7% | 399 | 252 | 63% | 47/74 | 0/0 | 0/0 | 63% | -
PS5-61-02 | PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | 5 | 0 | 0% | 98 | 40 | 41% | 11/32 | 0/0 | 0/0 | 41% | -
PS5-61-03 | PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | 10 | 1 | 10% | 98 | 37 | 38% | 11/32 | 0/0 | 0/0 | 38% | -
PS5-61-04 | PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | 0 | 0 | 0% | 35 | 0 | 0% | 0/18 | 0/0 | 0/0 | 0% | -
PS5-61-05 | PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | 36 | 34 | 94% | 155 | 115 | 74% | 114/114 | 0/0 | 0/0 | 74% | COMPLETE
PS5-61-06 | PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | 31 | 31 | 100% | 130 | 48 | 37% | 48/94 | 0/0 | 0/0 | 37% | -
PS5-61-07 | PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | 104 | 3 | 3% | 358 | 271 | 76% | 64/65 | 0/0 | 0/0 | 76% | -
PS5-61-08 | PS5-61-08 - Electrical Control System | 14 | 8 | 57% | 239 | 157 | 66% | 0/28 | 0/0 | 0/0 | 66% | -
PS5-61-09 | PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | 0 | 0 | 0% | 34 | 1 | 3% | 1/20 | 0/0 | 0/0 | 3% | -
PS5-61-10 | PS5-61-10 - Outdoor Valves Distribution Board - PS5-61-IG-0042 | 0 | 0 | 0% | 15 | 1 | 7% | 1/4 | 0/0 | 0/0 | 7% | -
PS5-61-11 | PS5-61-11 - Outdoor Valves Distribution Board - PS5-61-IG-0043 | 0 | 0 | 0% | 15 | 1 | 7% | 1/4 | 0/0 | 0/0 | 7% | -
PS5-61-12 | PS5-61-12 - EITS 33kV Bld. Normal Auxiliary DP - PS5-61-IG-0008 | 0 | 0 | 0% | 25 | 8 | 32% | 0/0 | 0/0 | 0/0 | 32% | -
PS5-61-13 | PS5-61-13 - Power Distribution Board Office Building - PS5-61-IG-0020 | 0 | 0 | 0% | 5 | 0 | 0% | 0/4 | 0/0 | 0/0 | 0% | -
PS5-61-14 | PS5-61-14 - Power Distribution Board Workshop & Warehouse - PS5-61-IG-0009 | 0 | 0 | 0% | 5 | 0 | 0% | 0/4 | 0/0 | 0/0 | 0% | -
PS5-62-01 | PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | 2 | 2 | 100% | 94 | 4 | 4% | 4/64 | 0/0 | 0/0 | 4% | -
PS5-62-02 | PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | 1 | 1 | 100% | 102 | 3 | 3% | 3/67 | 0/0 | 0/0 | 3% | -
PS5-62-03 | PS5-62-03 - Outdoor Emergency Lighting DB - PS5-05-IG-0004 | 0 | 0 | 0% | 15 | 1 | 7% | 1/4 | 0/0 | 0/0 | 7% | -
PS5-62-04 | PS5-62-04 - Outdoor Emergency Lighting DB - PS5-05-IG-0006 | 0 | 0 | 0% | 24 | 1 | 4% | 1/4 | 0/0 | 0/0 | 4% | -
PS5-62-05 | PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | 0 | 0 | 0% | 36 | 0 | 0% | 0/20 | 0/0 | 0/0 | 0% | -
PS5-62-06 | PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | 0 | 0 | 0% | 36 | 1 | 3% | 1/19 | 0/0 | 0/0 | 3% | -
PS5-62-07 | PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | 1 | 0 | 0% | 34 | 2 | 6% | 2/17 | 0/0 | 0/0 | 6% | -
PS5-62-08 | PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | 0 | 0 | 0% | 43 | 1 | 2% | 1/22 | 0/0 | 0/0 | 2% | -
PS5-62-09 | PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | 2 | 0 | 0% | 44 | 11 | 25% | 11/24 | 0/0 | 0/0 | 25% | -
PS5-62-10 | PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | 1 | 0 | 0% | 67 | 1 | 1% | 1/39 | 0/0 | 0/0 | 1% | -
PS5-62-11 | PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | 0 | 0 | 0% | 37 | 1 | 3% | 1/19 | 0/0 | 0/0 | 3% | -
PS5-62-12 | PS5-62-12 - EITS 33kV Bld. Emergency L&SP DP - PS5-05-IG-0003 | 0 | 0 | 0% | 26 | 19 | 73% | 0/0 | 0/0 | 0/0 | 73% | -
PS5-62-13 | PS5-62-13 - EITS 33kV Bld. Normal L&SP DP - PS5-61-IG-0003 | 1 | 0 | 0% | 34 | 25 | 74% | 0/0 | 0/0 | 0/0 | 74% | -
PS5-62-14 | PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | 0 | 0 | 0% | 32 | 1 | 3% | 1/30 | 0/0 | 0/0 | 3% | -
PS5-62-15 | PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | 0 | 0 | 0% | 47 | 0 | 0% | 0/46 | 0/0 | 0/0 | 0% | -
PS5-62-16 | PS5-62-16 - Guard Hut A Normal L&SP DB - PS5-61-IG-0111 | 0 | 0 | 0% | 7 | 0 | 0% | 0/6 | 0/0 | 0/0 | 0% | -
PS5-62-17 | PS5-62-17 - Guard Hut B Normal L&SP DB - PS5-61-IG-0112 | 0 | 0 | 0% | 7 | 0 | 0% | 0/6 | 0/0 | 0/0 | 0% | -
PS5-62-18 | PS5-62-18 - Workshop & Warehouse Normal L&SP DB - PS5-61-IG-0004 | 0 | 0 | 0% | 5 | 0 | 0% | 0/4 | 0/0 | 0/0 | 0% | -
PS5-62-19 | PS5-62-19 - Workshop & Warehouse Emergency L&SP DB - PS5-05-IG-0101 | 0 | 0 | 0% | 5 | 0 | 0% | 0/4 | 0/0 | 0/0 | 0% | -
PS5-62-20 | PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010 | 0 | 0 | 0% | 11 | 0 | 0% | 0/10 | 0/0 | 0/0 | 0% | -
PS5-63-01 | PS5-63-01 - Electrical Earthing | 57 | 0 | 0% | 69 | 16 | 23% | 16/68 | 0/0 | 0/0 | 23% | -
PS5-63-02 | PS5-63-02 - Electrical Earthing - Office and Facilities building | 0 | 0 | 0% | 5 | 0 | 0% | 0/4 | 0/0 | 0/0 | 0% | -
PS5-63-03 | PS5-63-03 - Electrical Earthing - Generator Building | 0 | 0 | 0% | 5 | 2 | 40% | 2/4 | 0/0 | 0/0 | 40% | PARTIAL
PS5-63-04 | PS5-63-04 - Electrical Earthing - EITS Building | 8 | 2 | 25% | 28 | 28 | 100% | 0/0 | 0/0 | 0/0 | 100% | -
PS5-63-05 | PS5-63-05 - Electrical Earthing - Guard Hut A & B | 0 | 0 | 0% | 9 | 0 | 0% | 0/8 | 0/0 | 0/0 | 0% | -
PS5-63-06 | PS5-63-06 - Electrical Earthing - Guard House | 0 | 0 | 0% | 5 | 0 | 0% | 0/4 | 0/0 | 0/0 | 0% | -
PS5-63-07 | PS5-63-07 - Electrical Earthing - Workshop & Warehouse | 0 | 0 | 0% | 5 | 0 | 0% | 0/4 | 0/0 | 0/0 | 0% | -
PS5-71-01 | PS5-71-01 - CFO Storage Tank Feed Heater | 15 | 5 | 33% | 164 | 57 | 35% | 0/14 | 11/48 | 0/0 | 35% | -
PS5-71-02 | PS5-71-02 - CFO Allocation Metering Package | 4 | 1 | 25% | 31 | 8 | 26% | 0/1 | 0/4 | 0/0 | 26% | -
PS5-71-03 | PS5-71-03 - CFO Allocation Metering Package (UCP) | 0 | 0 | 0% | 15 | 7 | 47% | 0/0 | 0/0 | 0/0 | 47% | -
PS5-71-04 | PS5-71-04 - CFO Storage Tank | 23 | 16 | 70% | 157 | 51 | 32% | 6/22 | 8/58 | 0/0 | 32% | -
PS5-71-05 | PS5-71-05 - CFO Transfer Pump A/B | 8 | 1 | 12% | 95 | 25 | 26% | 3/10 | 10/35 | 0/0 | 26% | -
PS5-71-06 | PS5-71-06 - Crude Fuel Separation Module | 18 | 5 | 28% | 70 | 30 | 43% | 2/2 | 7/34 | 0/0 | 43% | -
PS5-71-07 | PS5-71-07 - Crude Fuel Separation Module (UCP) | 1 | 0 | 0% | 138 | 24 | 17% | 6/64 | 16/44 | 2/4 | 17% | -
PS5-71-08 | PS5-71-08 - CFO Pre-Pressure Modules | 13 | 1 | 8% | 88 | 51 | 58% | 12/25 | 24/31 | 0/0 | 58% | -
PS5-71-09 | PS5-71-09 - CFO Pre-Pressure Modules (UCP) | 1 | 0 | 0% | 36 | 21 | 58% | 8/8 | 11/11 | 1/2 | 58% | PARTIAL
PS5-71-12 | PS5-71-12 - CFO Service Tank | 28 | 23 | 82% | 160 | 52 | 32% | 8/24 | 21/69 | 0/0 | 32% | -
PS5-71-13 | PS5-71-13 - CFO Service Pump A/B | 5 | 1 | 20% | 85 | 22 | 26% | 2/10 | 8/27 | 0/0 | 26% | -
PS5-71-14 | PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | 24 | 2 | 8% | 42 | 12 | 29% | 2/7 | 1/4 | 0/0 | 29% | -
PS5-71-15 | PS5-71-15 - Diesel Fuel Storage Tank | 7 | 1 | 14% | 72 | 29 | 40% | 2/8 | 14/27 | 0/0 | 40% | -
PS5-71-16 | PS5-71-16 - Diesel Fuel Supply Pump A/B | 2 | 0 | 0% | 54 | 12 | 22% | 2/8 | 2/10 | 0/0 | 22% | -
PS5-71-17 | PS5-71-17 - Diesel Fuel Distribution Header | 2 | 0 | 0% | 39 | 16 | 41% | 0/0 | 3/13 | 0/0 | 41% | -
PS5-71-18 | PS5-71-18 - Diesel Separator Module | 18 | 2 | 11% | 74 | 34 | 46% | 2/3 | 11/28 | 0/0 | 46% | -
PS5-71-19 | PS5-71-19 - Diesel Separator Module (UCP) | 6 | 0 | 0% | 52 | 15 | 29% | 4/16 | 7/17 | 1/4 | 29% | -
PS5-71-20 | PS5-71-20 - Diesel Fuel Day Tank | 18 | 5 | 28% | 67 | 46 | 69% | 4/4 | 22/30 | 0/0 | 69% | -
PS5-71-21 | PS5-71-21 - Diesel Transfer Pump A/B | 30 | 2 | 7% | 79 | 52 | 66% | 10/10 | 17/25 | 0/0 | 66% | -
PS5-71-22 | PS5-71-22 - Diesel Fuel Pre Pressure Module | 29 | 13 | 45% | 90 | 65 | 72% | 13/13 | 23/23 | 0/0 | 72% | -
PS5-71-23 | PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 9 | 1 | 11% | 39 | 20 | 51% | 4/8 | 12/15 | 1/2 | 51% | -
PS5-74-01 | PS5-74-01 - N2 Generation Skid | 14 | 3 | 21% | 18 | 3 | 17% | 0/4 | 0/1 | 0/0 | 17% | -
PS5-74-02 | PS5-74-02 - N2 Generation Skid (UCP) | 2 | 2 | 100% | 26 | 2 | 8% | 2/4 | 0/5 | 0/0 | 8% | -
PS5-74-03 | PS5-74-03 - Nitrogen Receiver | 6 | 1 | 17% | 27 | 10 | 37% | 0/0 | 0/3 | 0/0 | 37% | -
PS5-74-04 | PS5-74-04 - Nitrogen Distribution Header | 0 | 0 | 0% | 22 | 4 | 18% | 0/0 | 1/8 | 0/0 | 18% | -
PS5-75-01 | PS5-75-01 - DRA Injection Package | 0 | 0 | 0% | 58 | 6 | 10% | 0/7 | 0/7 | 0/0 | 10% | -
PS5-75-02 | PS5-75-02 - Biocide Injection Package | 15 | 1 | 7% | 55 | 12 | 22% | 0/5 | 0/3 | 0/0 | 22% | -
PS5-75-03 | PS5-75-03 - Corrosion Inhibitor Injection Package | 7 | 1 | 14% | 54 | 11 | 20% | 0/5 | 0/3 | 0/0 | 20% | -
PS5-78-01 | PS5-78-01 - Lifting and handling equipment | 95 | 70 | 74% | 43 | 27 | 63% | 4/8 | 0/0 | 0/0 | 63% | PARTIAL(05-03-2026)
PS5-79-01 | PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | 0 | 0 | 0% | 109 | 3 | 3% | 2/67 | 0/1 | 0/0 | 3% | -
PS5-79-02 | PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | 0 | 0 | 0% | 112 | 3 | 3% | 2/69 | 0/1 | 0/0 | 3% | -
PS5-79-03 | PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | 0 | 0 | 0% | 109 | 3 | 3% | 2/67 | 0/1 | 0/0 | 3% | -
PS5-79-04 | PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | 0 | 0 | 0% | 103 | 3 | 3% | 2/63 | 0/1 | 0/0 | 3% | -
PS5-79-05 | PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | 0 | 0 | 0% | 106 | 3 | 3% | 2/65 | 0/1 | 0/0 | 3% | -
PS5-79-06 | PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | 0 | 0 | 0% | 118 | 3 | 3% | 2/73 | 0/1 | 0/0 | 3% | -
PS5-79-07 | PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | 0 | 0 | 0% | 118 | 3 | 3% | 2/73 | 0/1 | 0/0 | 3% | -
PS5-79-08 | PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | 0 | 0 | 0% | 118 | 3 | 3% | 2/73 | 0/1 | 0/0 | 3% | -
PS5-79-09 | PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | 0 | 0 | 0% | 118 | 3 | 3% | 2/73 | 0/1 | 0/0 | 3% | -
PS5-79-10 | PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | 0 | 0 | 0% | 112 | 3 | 3% | 2/69 | 0/1 | 0/0 | 3% | -
PS5-79-11 | PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | 0 | 0 | 0% | 112 | 3 | 3% | 2/69 | 0/1 | 0/0 | 3% | -
PS5-79-12 | PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | 0 | 0 | 0% | 127 | 1 | 1% | 0/79 | 0/1 | 0/0 | 1% | -
PS5-82-01 | PS5-82-01 - Sanitary Sewage Collection | 0 | 0 | 0% | 52 | 30 | 58% | 0/0 | 0/0 | 0/0 | 58% | -
PS5-82-02 | PS5-82-02 - Sewage Treatment Plant Package | 45 | 1 | 2% | 17 | 1 | 6% | 0/2 | 0/1 | 0/0 | 6% | -
PS5-82-03 | PS5-82-03 - Sewage Treatment Plant Package (UCP) | 0 | 0 | 0% | 4 | 0 | 0% | 0/0 | 0/2 | 0/0 | 0% | -
PS5-82-04 | PS5-82-04 - Sewage Treatment Plant Discharge Piping | 0 | 0 | 0% | 11 | 4 | 36% | 0/0 | 0/0 | 0/0 | 36% | -
PS5-82-05 | PS5-82-05 - Office and Facilities building | 0 | 0 | 0% | 14 | 0 | 0% | 0/2 | 0/0 | 0/0 | 0% | -
PS5-82-06 | PS5-82-06 - Guard House Building | 0 | 0 | 0% | 14 | 0 | 0% | 0/2 | 0/0 | 0/0 | 0% | -
PS5-82-07 | PS5-82-07 - Guard Huts | 0 | 0 | 0% | 7 | 0 | 0% | 0/0 | 0/0 | 0/0 | 0% | -
PS5-83-01 | PS5-83-01 - EITS Building | 50 | 25 | 50% | 11 | 7 | 64% | 0/1 | 0/0 | 0/0 | 64% | -
PS5-84-01 | PS5-84-01 - Generator Building | 0 | 0 | 0% | 14 | 0 | 0% | 0/2 | 0/0 | 0/0 | 0% | -
PS5-84-02 | PS5-84-02 - Workshop & Warehouse | 0 | 0 | 0% | 10 | 0 | 0% | 0/0 | 0/0 | 0/0 | 0% | -
PS5-84-03 | PS5-84-03 - Shelters | 0 | 0 | 0% | 5 | 0 | 0% | 0/0 | 0/0 | 0/0 | 0% | -
PS5-86-01 | PS5-86-01 - Shelters | 0 | 0 | 0% | 5 | 0 | 0% | 0/0 | 0/0 | 0/0 | 0% | -
PS5-91-01 | PS5-91-01 - Multicore cables & JB | 50 | 11 | 22% | 194 | 145 | 75% | 0/0 | 128/128 | 0/0 | 75% | COMPLETE
PS5-99-01 | PS5-99-01 - Area Completion for Building area | 0 | 0 | 0% | 8 | 0 | 0% | 0/2 | 0/0 | 0/0 | 0% | -
PS5-99-02 | PS5-99-02 - Area Completion for Utility area | 0 | 0 | 0% | 5 | 0 | 0% | 0/1 | 0/0 | 0/0 | 0% | -
PS5-99-03 | PS5-99-03 - Area Completion for Power Distribution area | 0 | 0 | 0% | 5 | 0 | 0% | 0/1 | 0/0 | 0/0 | 0% | -
PS5-99-04 | PS5-99-04 - Area Completion for Process area | 0 | 0 | 0% | 11 | 0 | 0% | 0/3 | 0/0 | 0/0 | 0% | -
PS5-99-05 | PS5-99-05 - Area Completion for CFO area | 0 | 0 | 0% | 5 | 0 | 0% | 0/1 | 0/0 | 0/0 | 0% | -
PS5-99-06 | PS5-99-06 - Area Completion for Power Generation area | 0 | 0 | 0% | 5 | 0 | 0% | 0/1 | 0/0 | 0/0 | 0% | -

## SIDMAP (hidden)
PS5-01-01 - Fire Water Jockey Pump A/B | PS5-01-01
PS5-01-02 - Fire Water Pump A | PS5-01-02
PS5-01-03 - Fire Water Pump B | PS5-01-03
PS5-01-04 - Fire Water Pump Mini Flow Recycle | PS5-01-04
PS5-01-05 - Foam Skid | PS5-01-05
PS5-01-06 - Foam Concentrate Distribution | PS5-01-06
PS5-01-07 - Fire Water Ring Main & Distribution | PS5-01-07
PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | PS5-01-08
PS5-01-09 - Inergen for EITS Building | PS5-01-09
PS5-01-10 - Water Mist Package | PS5-01-10
PS5-01-11 - Inergen for Power Gen Building | PS5-01-11
PS5-02-01 - Miscellaneous Safety equipment | PS5-02-01
PS5-02-02 - Portable Fire Fighting Equipments | PS5-02-02
PS5-03-01 - FZ-01 - Process Area | PS5-03-01
PS5-03-03 - FZ-03 - Buildings Area | PS5-03-03
PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | PS5-03-04
PS5-03-06 - FZ-06 - Transformer Area | PS5-03-06
PS5-03-07 - FZ-07 - Pretreatment Area | PS5-03-07
PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | PS5-03-08
PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | PS5-03-09
PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | PS5-03-10
PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | PS5-03-11
PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | PS5-03-12
PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | PS5-03-13
PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | PS5-03-14
PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1 | PS5-03-15
PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2 | PS5-03-16
PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3 | PS5-03-17
PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4 | PS5-03-18
PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | PS5-03-19
PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | PS5-03-20
PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit | PS5-03-21
PS5-03-22 - FZ-G1 - Guard House | PS5-03-22
PS5-03-23 - FZ-E1 to E3 - EITS Building | PS5-03-23
PS5-03-24 - FZ - Office and Facilities Building | PS5-03-24
PS5-03-25 - FZ - Workshop & Warehouse | PS5-03-25
PS5-04-01 - Office Building PCS System | PS5-04-01
PS5-04-02 - Office Building SIS/FGS System | PS5-04-02
PS5-04-03 - 33kV ICSS System | PS5-04-03
PS5-04-04 - 33kV PCS System | PS5-04-04
PS5-04-05 - 33kV SIS/FGS System | PS5-04-05
PS5-05-01 - Emergency Diesel Generator Package | PS5-05-01
PS5-05-02 - Emergency Diesel Generator Package (UCP) | PS5-05-02
PS5-06-01 - AC UPS - EITS Building | PS5-06-01
PS5-06-02 - AC UPS - Power Generator Building | PS5-06-02
PS5-06-03 - AC UPS - Office & Facilities Building | PS5-06-03
PS5-06-04 - AC UPS - Guard House | PS5-06-04
PS5-06-05 - AC UPS - Workshop & Warehouse | PS5-06-05
PS5-08-01 - PAGA | PS5-08-01
PS5-08-03 - Telephone | PS5-08-03
PS5-08-04 - Hotline | PS5-08-04
PS5-08-07 - Multi-Channel Voice Recorder | PS5-08-07
PS5-08-11 - Corporate LAN (SIE) | PS5-08-11
PS5-08-12 - Corporate Wireless LAN (SIE) | PS5-08-12
PS5-08-13 - Safety Data Network (SII SP3 SAF) | PS5-08-13
PS5-08-14 - Industrial Data Network (SII SP1) | PS5-08-14
PS5-08-15 - Security Data Network (SII SP3 SEC) | PS5-08-15
PS5-08-23 - VHF Trunk Radio System | PS5-08-23
PS5-08-34 - Satphone | PS5-08-34
PS5-08-35 - Optical Transport Network | PS5-08-35
PS5-08-36 - Pipeline FO Cable & EPRS | PS5-08-36
PS5-08-51 - Entertainment | PS5-08-51
PS5-08-52 - Process & Security CCTV | PS5-08-52
PS5-08-55 - Videoconference | PS5-08-55
PS5-08-61 - Meteocean | PS5-08-61
PS5-08-71 - Structured Cabling (CAT6) | PS5-08-71
PS5-08-72 - Structured Cabling (FO) | PS5-08-72
PS5-08-81 - Guard tour | PS5-08-81
PS5-08-82 - Key Management | PS5-08-82
PS5-08-83 - Perimeter & Pipeline intrusion detection system | PS5-08-83
PS5-08-85 - Access Control, POB & e-Mustering | PS5-08-85
PS5-08-86 - Integrated Security Management System | PS5-08-86
PS5-08-92 - Telecom Mast | PS5-08-92
PS5-08-93 - Telecom Monitoring System | PS5-08-93
PS5-09-01 - HVAC for Office and Facilities building | PS5-09-01
PS5-09-02 - HVAC for Guard House | PS5-09-02
PS5-09-03 - HVAC for Generator Building | PS5-09-03
PS5-09-04 - HVAC for Workshop & Warehouse | PS5-09-04
PS5-09-05 - HVAC for EITS Building | PS5-09-05
PS5-0H-01 - HIPPS | PS5-0H-01
PS5-25-01 - Export Pipeline Pig Receiver | PS5-25-01
PS5-25-02 - Crude Oil Export Pump A | PS5-25-02
PS5-25-03 - Crude Oil Export Pump B | PS5-25-03
PS5-25-04 - Crude Oil Export Pump C | PS5-25-04
PS5-25-05 - Crude Oil Export Pumps Bypass | PS5-25-05
PS5-25-06 - Crude Oil Export Pumps Discharge | PS5-25-06
PS5-25-07 - Export Pipeline Pig Launcher | PS5-25-07
PS5-28-01 - Closed Drain Header 1 | PS5-28-01
PS5-28-02 - Closed Drain Header 2 | PS5-28-02
PS5-28-03 - Closed Drain Drum and Pump 01 | PS5-28-03
PS5-28-04 - Closed Drain Drum and Pump 02 | PS5-28-04
PS5-28-05 - HP Relief Header | PS5-28-05
PS5-28-06 - Relief Drum and Pump | PS5-28-06
PS5-28-07 - Open Drains (OD2) | PS5-28-07
PS5-28-08 - Open Drain Sump and Pumps | PS5-28-08
PS5-28-09 - Observation Basin | PS5-28-09
PS5-28-10 - Oil Skimmer Package | PS5-28-10
PS5-28-11 - Open Drain Interceptor | PS5-28-11
PS5-28-12 - Open Drains (OD3) | PS5-28-12
PS5-28-13 - Seal Oil Drain Drum & Pump A | PS5-28-13
PS5-28-14 - Seal Oil Drain Drum & Pump B | PS5-28-14
PS5-28-15 - Seal Oil Drain Drum & Pump C | PS5-28-15
PS5-28-16 - LP Relief Header | PS5-28-16
PS5-28-17 - Reinjection Pump | PS5-28-17
PS5-50-01 - Water Well Submersible Pumps (3100) | PS5-50-01
PS5-50-02 - Water Well Submersible Pumps (3200) | PS5-50-02
PS5-50-03 - Water Pre-Treatment Package | PS5-50-03
PS5-53-01 - Utility Water / Storage Tank | PS5-53-01
PS5-53-02 - Water Distribution Pump A/B | PS5-53-02
PS5-53-03 - Water Softener Package | PS5-53-03
PS5-53-04 - Water Treatment Purification Package | PS5-53-04
PS5-53-05 - Water Distribution Header | PS5-53-05
PS5-53-06 - Water Distribution Consumers | PS5-53-06
PS5-60-01 - Power Generation Package A | PS5-60-01
PS5-60-02 - Power Gen Package A (UCP) | PS5-60-02
PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | PS5-60-03
PS5-60-04 - Power Generation Package B | PS5-60-04
PS5-60-05 - Power Gen Package B (UCP) | PS5-60-05
PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | PS5-60-06
PS5-60-07 - Power Generation Package C | PS5-60-07
PS5-60-08 - Power Gen Package C (UCP) | PS5-60-08
PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | PS5-60-09
PS5-60-10 - Power Generation Package D | PS5-60-10
PS5-60-11 - Power Gen Package D (UCP) | PS5-60-11
PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | PS5-60-12
PS5-60-13 - Power Generation Package E | PS5-60-13
PS5-60-14 - Power Gen Package E (UCP) | PS5-60-14
PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | PS5-60-15
PS5-60-16 - Power Generation Package F | PS5-60-16
PS5-60-17 - Power Gen Package F (UCP) | PS5-60-17
PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | PS5-60-18
PS5-60-19 - Power Generation Package G | PS5-60-19
PS5-60-20 - Power Gen Package G (UCP) | PS5-60-20
PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | PS5-60-21
PS5-60-22 - Power Gen Master UCP | PS5-60-22
PS5-60-23 - Instrument Air Distribution lines | PS5-60-23
PS5-60-24 - Cooling Water Tank & Pump | PS5-60-24
PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | PS5-60-25
PS5-60-26 - Instrument Air Compressor Skid | PS5-60-26
PS5-60-27 - Compressed Air Starting Skid | PS5-60-27
PS5-60-28 - Air Receiver A & Air Regulator A | PS5-60-28
PS5-60-29 - Air Receiver B & Air Regulator B | PS5-60-29
PS5-60-30 - Air Receiver C & Air Regulator C | PS5-60-30
PS5-60-31 - Air Receiver D & Air Regulator D | PS5-60-31
PS5-60-32 - Air Receiver E & Air Regulator E | PS5-60-32
PS5-60-33 - Air Receiver F & Air Regulator F | PS5-60-33
PS5-60-34 - Air Receiver G & Air Regulator G | PS5-60-34
PS5-60-35 - Injector Tip Cooling Module A | PS5-60-35
PS5-60-36 - Injector Tip Cooling Module B | PS5-60-36
PS5-60-37 - Injector Tip Cooling Module C | PS5-60-37
PS5-60-38 - Injector Tip Cooling Module D | PS5-60-38
PS5-60-39 - Injector Tip Cooling Module E | PS5-60-39
PS5-60-40 - Injector Tip Cooling Module F | PS5-60-40
PS5-60-41 - Injector Tip Cooling Module G | PS5-60-41
PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | PS5-60-42
PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | PS5-60-43
PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | PS5-60-44
PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | PS5-60-45
PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | PS5-60-46
PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | PS5-60-47
PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | PS5-60-48
PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | PS5-60-49
PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | PS5-60-50
PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | PS5-60-51
PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | PS5-60-52
PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | PS5-60-53
PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | PS5-60-54
PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | PS5-60-55
PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | PS5-60-56
PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | PS5-60-57
PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | PS5-60-58
PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | PS5-60-59
PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | PS5-60-60
PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | PS5-60-61
PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | PS5-60-62
PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | PS5-60-63
PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | PS5-60-64
PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | PS5-60-65
PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | PS5-60-66
PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | PS5-60-67
PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | PS5-60-68
PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | PS5-60-69
PS5-60-70 - Engine A Cooling system | PS5-60-70
PS5-60-71 - Engine B Cooling system | PS5-60-71
PS5-60-72 - Engine C Cooling system | PS5-60-72
PS5-60-73 - Engine D Cooling system | PS5-60-73
PS5-60-74 - Engine E Cooling system | PS5-60-74
PS5-60-75 - Engine F Cooling system | PS5-60-75
PS5-60-76 - Engine G Cooling system | PS5-60-76
PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | PS5-61-01
PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | PS5-61-02
PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | PS5-61-03
PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | PS5-61-04
PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | PS5-61-05
PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | PS5-61-06
PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | PS5-61-07
PS5-61-08 - Electrical Control System | PS5-61-08
PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | PS5-61-09
PS5-61-10 - Outdoor Valves Distribution Board - PS5-61-IG-0042 | PS5-61-10
PS5-61-11 - Outdoor Valves Distribution Board - PS5-61-IG-0043 | PS5-61-11
PS5-61-12 - EITS 33kV Bld. Normal Auxiliary DP - PS5-61-IG-0008 | PS5-61-12
PS5-61-13 - Power Distribution Board Office Building - PS5-61-IG-0020 | PS5-61-13
PS5-61-14 - Power Distribution Board Workshop & Warehouse - PS5-61-IG-0009 | PS5-61-14
PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | PS5-62-01
PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | PS5-62-02
PS5-62-03 - Outdoor Emergency Lighting DB - PS5-05-IG-0004 | PS5-62-03
PS5-62-04 - Outdoor Emergency Lighting DB - PS5-05-IG-0006 | PS5-62-04
PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | PS5-62-05
PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | PS5-62-06
PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | PS5-62-07
PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | PS5-62-08
PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | PS5-62-09
PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | PS5-62-10
PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | PS5-62-11
PS5-62-12 - EITS 33kV Bld. Emergency L&SP DP - PS5-05-IG-0003 | PS5-62-12
PS5-62-13 - EITS 33kV Bld. Normal L&SP DP - PS5-61-IG-0003 | PS5-62-13
PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | PS5-62-14
PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | PS5-62-15
PS5-62-16 - Guard Hut A Normal L&SP DB - PS5-61-IG-0111 | PS5-62-16
PS5-62-17 - Guard Hut B Normal L&SP DB - PS5-61-IG-0112 | PS5-62-17
PS5-62-18 - Workshop & Warehouse Normal L&SP DB - PS5-61-IG-0004 | PS5-62-18
PS5-62-19 - Workshop & Warehouse Emergency L&SP DB - PS5-05-IG-0101 | PS5-62-19
PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010 | PS5-62-20
PS5-63-01 - Electrical Earthing | PS5-63-01
PS5-63-02 - Electrical Earthing - Office and Facilities building | PS5-63-02
PS5-63-03 - Electrical Earthing - Generator Building | PS5-63-03
PS5-63-04 - Electrical Earthing - EITS Building | PS5-63-04
PS5-63-05 - Electrical Earthing - Guard Hut A & B | PS5-63-05
PS5-63-06 - Electrical Earthing - Guard House | PS5-63-06
PS5-63-07 - Electrical Earthing - Workshop & Warehouse | PS5-63-07
PS5-71-01 - CFO Storage Tank Feed Heater | PS5-71-01
PS5-71-02 - CFO Allocation Metering Package | PS5-71-02
PS5-71-03 - CFO Allocation Metering Package (UCP) | PS5-71-03
PS5-71-04 - CFO Storage Tank | PS5-71-04
PS5-71-05 - CFO Transfer Pump A/B | PS5-71-05
PS5-71-06 - Crude Fuel Separation Module | PS5-71-06
PS5-71-07 - Crude Fuel Separation Module (UCP) | PS5-71-07
PS5-71-08 - CFO Pre-Pressure Modules | PS5-71-08
PS5-71-09 - CFO Pre-Pressure Modules (UCP) | PS5-71-09
PS5-71-12 - CFO Service Tank | PS5-71-12
PS5-71-13 - CFO Service Pump A/B | PS5-71-13
PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | PS5-71-14
PS5-71-15 - Diesel Fuel Storage Tank | PS5-71-15
PS5-71-16 - Diesel Fuel Supply Pump A/B | PS5-71-16
PS5-71-17 - Diesel Fuel Distribution Header | PS5-71-17
PS5-71-18 - Diesel Separator Module | PS5-71-18
PS5-71-19 - Diesel Separator Module (UCP) | PS5-71-19
PS5-71-20 - Diesel Fuel Day Tank | PS5-71-20
PS5-71-21 - Diesel Transfer Pump A/B | PS5-71-21
PS5-71-22 - Diesel Fuel Pre Pressure Module | PS5-71-22
PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | PS5-71-23
PS5-74-01 - N2 Generation Skid | PS5-74-01
PS5-74-02 - N2 Generation Skid (UCP) | PS5-74-02
PS5-74-03 - Nitrogen Receiver | PS5-74-03
PS5-74-04 - Nitrogen Distribution Header | PS5-74-04
PS5-75-01 - DRA Injection Package | PS5-75-01
PS5-75-02 - Biocide Injection Package | PS5-75-02
PS5-75-03 - Corrosion Inhibitor Injection Package | PS5-75-03
PS5-78-01 - Lifting and handling equipment | PS5-78-01
PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | PS5-79-01
PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | PS5-79-02
PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | PS5-79-03
PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | PS5-79-04
PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | PS5-79-05
PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | PS5-79-06
PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | PS5-79-07
PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | PS5-79-08
PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | PS5-79-09
PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | PS5-79-10
PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | PS5-79-11
PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | PS5-79-12
PS5-82-01 - Sanitary Sewage Collection | PS5-82-01
PS5-82-02 - Sewage Treatment Plant Package | PS5-82-02
PS5-82-03 - Sewage Treatment Plant Package (UCP) | PS5-82-03
PS5-82-04 - Sewage Treatment Plant Discharge Piping | PS5-82-04
PS5-82-05 - Office and Facilities building | PS5-82-05
PS5-82-06 - Guard House Building | PS5-82-06
PS5-82-07 - Guard Huts | PS5-82-07
PS5-83-01 - EITS Building | PS5-83-01
PS5-84-01 - Generator Building | PS5-84-01
PS5-84-02 - Workshop & Warehouse | PS5-84-02
PS5-84-03 - Shelters | PS5-84-03
PS5-86-01 - Shelters | PS5-86-01
PS5-91-01 - Multicore cables & JB | PS5-91-01
PS5-99-01 - Area Completion for Building area | PS5-99-01
PS5-99-02 - Area Completion for Utility area | PS5-99-02
PS5-99-03 - Area Completion for Power Distribution area | PS5-99-03
PS5-99-04 - Area Completion for Process area | PS5-99-04
PS5-99-05 - Area Completion for CFO area | PS5-99-05
PS5-99-06 - Area Completion for Power Generation area | PS5-99-06